## BOH Wave Team
S.no | Application Name | Developer | Description | Status | Comments
1 | Extensions AI | Rajiv / Deepika / Joel | Extensions AI packages in console application | Completed
2 | Extensions AI | Rajiv / Deepika / Joel | Extensions AI packages integration in BOH application | Completed
3 | Extensions AI | Rajiv / Deepika / Joel | Extensions AI packages integration in BOH application with OpenAI | Completed
4 | Extensions AI | Rajiv / Deepika / Joel | Extensions AI packages integration in BOH application with AzureAI | Completed
5 | Extensions AI | Rajiv / Deepika / Joel | Extensions AI packages integration in BOH application with Vertex AI | Completed | Vertex not supported
6 | Sementic Kernal | Rajiv / Deepika / Joel | Using Sementic Kernal In Console application | Completed
7 | Sementic Kernal | Rajiv / Deepika / Joel | Using Sementic Kernal In BOH application with Openai | Completed
8 | Sementic Kernal | Rajiv / Deepika / Joel | Using Sementic Kernal In BOH application with Azureai | Completed
9 | Sementic Kernal | Rajiv / Deepika / Joel | Using Sementic Kernal In BOH application with Vertexai | Completed
10 | Prompt Optimization | Rajiv / Deepika / Joel | Optimized prompt using sementic kernal in console application | Completed
11 | Prompt Optimization | Rajiv / Deepika / Joel | Optimized prompt using sementic kernal with Vertex & Openai | Completed
12 | API | Rajiv / Deepika / Joel | New API using sementic kernal with multiple LLM's | Completed
13 | API | Rajiv / Deepika / Joel | New API without using sementic kernal with multiple LLM's | Completed
14 | BOH AI Connectivity | Rajiv / Deepika / Joel | Creating new option in existing AI menu | Completed
15 | BOH AI Connectivity | Rajiv / Deepika / Joel | Consume the new API to integrate with existing BOH | Completed
16 | BOH AI Connectivity | Rajiv / Deepika / Joel | UI Changes to pass the LLM | Completed
17 | BOH AI Connectivity | Rajiv / Deepika / Joel | Pass Token counts and display to the AI connectivity output | Completed
18 | BOH AI Connectivity | Rajiv / Deepika / Joel | Optimize the code to use only sementic kernal in API | Completed
19 | BOH AI Connectivity | Rajiv / Deepika / Joel | UI changes to display the Raw response from the API | Completed
20 | BOH AI Connectivity | Rajiv / Deepika / Joel | Reviewing the POC | Completed
21 | GCP Access | Rajiv / Deepika / Joel | Explore the vertex setting on the newly created account | Completed
22 | Testing | Priyadharshini | Testing assigned test cases, reviewing the existing BOH code and learning C# | Completed
23 | Document Preparation | Rajiv | PPT document preparation about AI | Completed
24 | Extensions AI - API | Rajiv | Creating new API using Extensions AI with Vertex alone | Completed
25 | Extensions AI - API | Rajiv | Creating new API using Extensions AI with mutilple LLM's | Completed
26 | Testing | Priyadharshini | Writing test scripts on recipe module | Completed
27 | Vertor db | Joel | Vector db embeddings | Completed
28 | Extensions AI - API | Deepika | Image search | Completed
29 | Story - 47271 | Rajiv | 47271 - Tiered Access Levels - aka Feature Flags (Acceleration) | Completed
30 | BigQuery | Joel | Working on finishing up BigQuery Semantic search | Completed
31 | OCR | Joel | OCR document intelligence | Completed
32 | ImageToText | Rajiv | Uploaded Image to text conversion | Completed
33 | Incremental Indexing | Joel | Incremental indexing to optimize the search | Completed
34 | Story - 47451 | Rajiv | QR code Login | Completed
35 | Story - 47441 | Deepika | Import Suggested Menus | Completed
36 | Story - 46936 | Joel & Rajiv | Implement RAG | Completed
37 | Story - 47452 | Joel & Rajiv | Implement AI Abstraction Layer | On Hold
38 | Story - 46935 | Joel & Rajiv | Additional Instructions Improvements | Completed

## Defect-template
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## Dashboard
Current Sprint | 26.06 Sprint 4 | Current Sprint Sheet | 26.06 Sprint 4-Status | Sprint Start Date | 2026-05-13 | Sprint End Date | 2026-05-26 | Application Name | BOH Wave | Users | rajivgandhi.sugumaran@relevantz.com;deepika.saravanan@relevantz.com;priyadharsini.kamalakannan@relevantz.com;krupa.bhatkar@relevantz.com;pradeepa.shanmugham@relevantz.com | Teams Name(GP-HSS-Mosaic BOH Wave) | 19:9509f03b5d034514b73c6b54be3710da@thread.v2
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story points introduced/removed | Sprint Summary | Accomplishments (Sprint Goal) | Remarks | Retro Points (Internal & External) | Planned Leave | Total Leave | Data sanity Audit Status | AuditDate | Backlog Health
NA | 3.18 Sprint 7 | 2024-01-09 | 2024-01-23 | 25 | 22 |  |  |  | Regression sprint | Internal: External:
NA | 3.18 Sprint 8 | 2024-01-24 | 2024-02-06 | 26 | 21 |  |  |  | 43230 - Story carried due to reports validation pending in Regression | Internal: External:
NA | 3.18 Sprint 9 | 2024-02-07 | 2024-02-20 | 16 | 16 |  |  |  | Regression sprint | Internal: External:
NA | 3.19 Sprint 1 | 2024-02-21 | 2024-03-05 | 23 | 16 |  |  |  | Took a long time for regression of the production record and production record formats. Dev and QA focusing on 3.18 release, so not started testing 3.19 release stories. | Internal: External:
NA | 3.19 Sprint 2 | 2024-03-06 | 2024-03-19 | 20 | 26 |  |  |  | 1 story carry forwarded and completed 4 stories from stretch. | Internal: External:
NA | 3.19 Sprint 3 | 2024-03-20 | 2024-04-02 | 22 | 17 |  |  |  | 1 Story carried due to lot of testing scope involved and underestimated the effort. 2 Stretch stories completed. | Internal: External:
NA | 3.19 Sprint 4 | 2024-04-03 | 2024-04-16 | 21 | 27 |  |  |  | Addition to current sprint, completed 3 stories from stretch | Internal: External:
NA | 3.19 Sprint 5 | 2024-04-17 | 2024-04-30 | 18 | 18 |  |  |  | One 13 SP carried to next sprint, Client CRC fix is inprogress. | Internal: External:
NA | 3.19 Sprint 6 | 2024-05-01 | 2024-05-14 | 36 | 36 |  |  |  | Regression sprint | Internal: External:
NA | 3.19 Sprint 7 | 2024-05-15 | 2024-05-28 | 30 | 30 |  |  |  | Regression sprint | Internal: External:
NA | 3.19 Sprint 8 | 2024-05-29 | 2024-06-11 | 14 | 14 |  |  |  | Regression sprint and worked on regression defects(which doesn't have sp) | Internal: External:
NA | 3.20 Sprint 1 | 2024-06-12 | 2024-06-25 | 18 | 18 |  |  |  | Completed all the assigned stories | Internal: External:
NA | 3.20 Sprint 2 | 2024-06-26 | 2024-07-23 | 31 | 31 |  |  |  | Completed all the assigned stories | Internal: External:
NA | 3.20 Sprint 3 | 2024-07-24 | 2024-08-06 | 25 | 25 |  |  |  | Addition to current sprint, completed 2 stories from stretch | Internal: External:
NA | 3.20 Sprint 4 | 2024-08-07 | 2024-08-20 | 19 | 24 |  |  |  | Addition to current sprint, completed 1 story from stretch | Internal: External:
NA | 3.20 Sprint 5 | 2024-08-21 | 2024-09-03 | 17 | 17 |  |  |  | Due to Public Holiday(2 Days) and onsite QA PTO, dev scope was reduced in the sprint and team worked and completed development on stretch stories. Even though development completed, those stories are pending for onsite QA testing, so carried to the next sprint. 03-Sep-24: CRC Peer - 0, Onsite - 0, Client - 1. Internal Defect - 0, External Defect - 1. | Internal: External: |  |  | Completed
NA | 3.20 Sprint 6 | 2024-09-04 | 2024-09-17 | 23 | 37 | 14 sp - Introduced |  |  | Addition to current sprint, completed 2 stories from stretch 17-Sep-24: CRC Peer - 0, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 2. | Internal: External: |  |  | Completed
NA | 3.20 Sprint 7 | 2024-09-18 | 2024-10-01 | 8 | 20 |  |  |  | Addition to current sprint, completed 3 stories and 1 defect from stretch 01-Oct-24: CRC Peer - 0, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 1. | Internal: External: |  |  | Completed
NA | 3.20 Sprint 8 | 2024-10-02 | 2024-10-15 | 18 | 15 |  |  |  | "Addition to current sprint, completed 1 stories from stretch and 2 Stories in QA 15-Oct-24: CRC Peer - 1, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 0." | Internal: External: |  |  | Completed
NA | 3.20 Sprint 9 | 2024-10-16 | 2024-10-29 | 25 | 30 |  |  |  | Addition to current sprint, completed 1 stories from stretch 29-Oct-24: CRC Peer - 0, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 0. | Internal: External: Completed sprint and stretch stories |  |  | Completed
NA | 3.20 Sprint 10 | 2024-10-30 | 2024-11-12 | 30 | 30 | 4/3 |  | Completed regression on "Recipes",''Ingredients","Products" and "Inventory" Modules | "46411" Mosaic BOH - 3.20 Regression - Ordering (Big Module) - Currently being in progress was removed and introduced 46412 and 46413. Development Cum Regression sprint CRC Peer - 0, CRC Onsite - 0, CRC Client - 0. Internal Defect - 0, External Defect - 0. | Internal: External: |  |  | Completed
NA | 3.20 Sprint 11 | 2024-11-13 | 2024-12-10 | 25 | 20 |  |  | Completed Regression and Regression defects and worked on few production defects | The development for story "46525"-Mosaic BOH - Bidding - Add the ability to attach any doc in bid analysis - is completed however the testing and review is incomplete due to hot fix release and one of the hot fix change was affecting the story. Until that is fixed it could not be pushed Development Cum Regression sprint CRC Peer - 0, CRC Onsite - 0, CRC Client - 0. Internal Defect - 2 Regression Defect- 10 External Defect - 0. | Internal: External: Performance issue after 3.20 release |  |  | Completed
NA | 3.21 Sprint 1 | 2024-12-11 | 2025-01-07 | 25 | 25 |  |  | Completed committed stories on time and worked on a few production defects. | The development for story "46743" - is in progress as we have to update the Kendo controls to latest version and fix affected components across the application.The story could spill over few more sprints as the same was done earlier (story 35612) which took total 316 hrs. It is a Development ---- Working control wise,once done with one will move to next control CRC Peer - 1, CRC Onsite - 0, CRC Client - 0. Internal Defect - 1 External Defect - 0. | External: Kendo Update broke many screens Completed a few defects from stretch Completed the committed stories other than Kendo |  |  | Completed
NA | 3.21 Sprint 2 | 2025-01-08 | 2025-01-21 | 20 | 20 |  |  | Bidding - Ability to Edit Bid Pricelist, Adding Substitute Recipes(by site in Production Qtys), Adding User Visibility/Last Modified details to Menus and Vendors, and Defects. | 46674 - Fixed the failed test cases in the Product and Ingredient Module 43702 - Development completed and in QA CRC Peer - 1, CRC Onsite - 1, CRC Client - 0. Internal Defect - 2 External Defect - 2. | External: Automation parallel execution Substitution Recipe Story progress |  |  | Completed
NA | 3.21 Sprint 3 | 2025-01-22 | 2025-02-04 | 15 | 47.25 |  |  | Add substitute recipe in the Production Quantities for a site for a menu date - (Step 3), Adding Privacy Policy and Terms of Use, Combining “copy” buttons to dropdown option on Menu/Production Qty’s page, and Defect fixes for 3.21.. | Addition to current sprint, completed 2 stories from stretch and 2 more stories in QA 46674 - Fixed the failed test cases in the Inventory Module (10.75 StP) CRC Peer - 0, CRC Onsite -1, CRC Client - 0. Internal Defect - 0 External Defect - 0. | Internal: External: Completed sprint and stretch stories.Client appreciated for completing all the stories and defect in the actual commit |  |  | Completed
NA | 3.21 Sprint 4 | 2025-02-05 | 2025-02-18 | 16 | 17 |  |  | Adding Substituted Recipes in Production Record Report, Adding note to Bid Analysis Page, and begin 3.21 Regression Testing. WAVE(Gen AI) - UI Design. | Addition to current sprint, worked on stories from stretch and 1 story in QA CRC Peer - 0, CRC Onsite -0, CRC Client - 0. Internal Defect - 3 External Defect - 0. | Internal: External: Completed Regression, Completed committed stories and a few from stretch |  |  | Completed
NA | 3.22 Sprint 1 | 2025-02-19 | 2025-03-04 | 13 | 26 |  |  | Substitute Recipes - Updating Inventory Usage, Tech Debt(Updating 3rd parties), Separating Order Quantities(Vendor, Warehouse, & CK), and Defects. | Addition to current sprint, worked on stories from stretch and 2 stories in QA CRC Peer - 0, CRC Onsite -0, CRC Client - 0. Internal Defect - 2 External Defect - 1. | Internal: External: Completed sprint and stretch stories.Craig and Richard B appreciated for completing all the stories and defect in the actual commit |  |  | Completed
NA | 3.22 Sprint 2 | 2025-03-05 | 2025-03-18 | 21 | 38 |  |  | Substitute Recipes - Include in MealViewer, Auto-Generate Production Planning Recap, Add Product Status in Product List report, and Tiered Access Levels(WAVE Acceleration) . | Addition to current sprint, completed 1 story from the stretch 46857 - Carry over to next sprint, due to the lot of scenarios to cover from menu planning screen to meal viewer sync. We completed menus and working on meal viewer sync.Also Unplanned PTO. Krupa working on Stretch story 46743 - Kendo Update, this requires more dev hours to fix the broken component and test all over the application, we keep the stories in stretch and working on. The effort we put into this was not included. CRC Peer - 0, CRC Onsite -1, CRC Client - 1. Internal Defect - 0 External Defect - 1. | Internal: External: Richard Boutin and Andrew - Got lot of work completed and reviewed. What didn't go well: Unplanned PTO MV - Substitute recipe story. |  |  | Completed
NA | 3.22 Sprint 3 | 2025-03-19 | 2025-04-01 | 32 | 50 |  |  | Substitute Recipes (Include in MealViewer and Add to Production Costing Report), Location change for Vendor Orders Export Formats, Defects, and WAVE GenAI: Importing Suggested Menus | 47441 -[WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Import Suggested Menus Carry over to next sprint due to amount of work and testing involved. Underestimated the effort during planning. CRC Peer - 0, CRC Onsite -0, CRC Client - 0. Internal Defect - 3 External Defect - 1. Considerd 47615 and 47461 - 13sp/ each for automation coverage | Internal: External: Richard Boutin and Andrew - Got lot of work completed and reviewed. What didn't go well: MV - Substitute recipe story. Underestimated AI story (47441) |  |  | Completed
NA | 3.22 Sprint 4 | 2025-04-02 | 2025-04-15 | 37 | 34 |  |  | CN2025 Updates, Tech Debt(Kendo Update), Substitute Recipes - Include in MealViewer, and WAVE GenAI(QR Code Login, Import Suggested Menus, and Implement AI Abstraction Layer). | CRC Peer - 1, CRC Onsite -3, CRC Client - 3. Internal Defect - 0 External Defect - 0. | Internal: External: What went well : Gen AI work Kendo ready for testing What didn’t go well : AI story not compatible with . Net |  |  | Completed
NA | 3.22 Sprint 5 | 2025-04-16 | 2025-04-29 | 35 | 32 |  |  | Tech Debt(Kendo Update), WAVE GenAI, and begin 3.22 Regression Testing | 47441 - story got carry forwarded - Issues found by the team and needs rework 47902 - Dev completed, Testing pending CRC Peer - 0, CRC Onsite -1, CRC Client - 0, Internal Defect - 0 External Defect - 0. | Internal: External: What went well : 1)Regression Testing 2)AI Development What didn’t go well : 1)COVID(unexpected PTO) 2)Accidental workflow step changes(defect marked for POV when was PR) 3)Underestimated work Wave/UI - Andrew's story |  |  | Completed
NA | 3.22 Sprint 6 | 2025-04-30 | 2025-05-13 | 9 | 16 | Introduced - 10 SP 48174 - 5 SP 48175 - 5 SP |  | 3.22 Regression Testing and WAVE GenAI | CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 0 External Defect - 0. | Internal: External: What went well : 1) Defects fixed turnaround. 2)Regression time reduced What didn’t go well : 1)Regression defects found(Most caused by Kendo updates) 2)Web server authentication issues with AI. 3)Craig locked out of computer/system |  |  | Completed
NA | 3.23 Sprint 1 | 2025-05-14 | 2025-05-27 | 19 | 14 |  |  | 3.22 Regression Testing, Defect fixes for 3.22.1 Interim release, and WAVE GenAI & Tier Model. | Stories: 3 out of 4 committed stories has been completed and 1 not completed Defects: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 0 External Defect - 0. | Internal: External: What went well :Completed many defects What didn’t go well : Nil |  |  | Completed
NA | 3.23 Sprint 2 | 2025-05-28 | 2025-06-10 | 14 | 16 |  |  | Fixed a lot of defects, Good progress in the AI work | Stories: 1 out of 4 committed stories and 1 from stretch has been completed Defects: CRC Peer - 1, CRC Onsite -0, CRC Client - 1, Internal Defect - 0 External Defect - 0. | Internal: External: What went well : Completed many defects and good progress in the AI work What didn’t go well : Could not test wave stories, no test environment due to interim release |  |  | Completed
NA | 3.23 Sprint 3 | 2025-06-11 | 2025-06-24 | 42 | 34.5 |  |  | Defect fixes, 3.22.1 Interim Release Prep/Checkout, and WAVE GenAI & Tier Model. | Remarks: Client is not ready to setup their GCP accounts on the web servers, due to this environment issue, we cannot tested the stories in this sprint, we have re-structured the database and call the AI through scheduler service. Stories: 1 out of 6 committed stories has been completed, 5 committed stories not completed. Defects: 1 stretch defect fixed CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 2 External Defect - 0. | Internal: External: What went well : 1)Tino had 50 handwritten test cases for AI, 2) fixed AI defects What didn’t go well : GEN AI testing environmental Issues |  |  | Completed
NA | 3.23 Sprint 4 | 2025-06-25 | 2025-07-08 | 28 | 28 | Introduced - 5 SP 49065 - 5 SP 1 defect fixed 25498 - 2SP | Tier Model , Nutrition Facts Labels, Create Ingredient, Creative Recipe - Portion size - Update the original response, Parent Data Table - Child Data Table , Add Allergens details to the Get Creative Recipes , Nutrients - measurement conversion | WAVE GenAI Nutrient fact label - create ingredient, Get Creative Recipe enhancement | Stories: 8 out of 9 committed stories has been completed and 1 not completed Defects: 1 defect not completed CRC Peer - 0, CRC Onsite -1, CRC Client - 0, Internal Defect - 1 External Defect - 0. | Internal: External: What went well : Nutrient fact label story completion, Get Creative Recipe enhancement What didn’t go well : AI Accuracy |  |  | Completed | /
NA | 3.23 Sprint 5 | 2025-07-09 | 2025-07-22 | 13 | 20 |  | Tier Model - Feature/Menus visibility based on the Tier levels, Nutrition Facts Label-Attach Image, Filter Task by list, Adjust background to Full screen, Physical Count worksheet. | Tier Level, Image attachment from nutrition fact label | Stories: 3 out of 3 committed stories and 3 from stretch has been completed Defects: HIghlights: Tier Level, Nutrition Fact Label Kudos: Lot of tickets has been compteted from committed and stretch CRC Peer - 0, CRC Onsite -1, CRC Client - 0, Internal Defect - 1 External Defect - 0. | Internal: What went well : Tier Models, Introduction of grooming session What didn’t go well : Test Data was not clear, Due to introduction of Vega Components issue in testing DOM elements External: What went well : What didn’t go well : |  |  | Completed
NA | 3.23 Sprint 6 | 2025-07-23 | 2025-08-05 | 26 | 26 | Introduced 49415 - 5 sp | Iterative AI call to parse Inventory Worksheet images, UI for verification and Editing the AI Response of the Inventory Parsing, Model switching, Ability to upload images from the system for nutrition fact label | Inventory worksheet image parsing, model switching | Stories: Out of 4 Committed stories, 3 has been completed and 1 not completed Defects: 1 committed defect has been completed Highlights: Inventory worksheet parsing and lot of research and testing on invertory work sheet parsing Kudos: Most of the stories were completed CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 1 External Defect - 0. | What went well : 2 main stories was completed What didn’t go well : Unable to test 1 story, due to onshore tester not available |  |  | Completed
NA | 4.0 Sprint 1 | 2025-08-06 | 2025-08-19 | 10 | 20 | Introduced 49653 - 5 sp | AI Assistant - Add the ability to upload images from the system, Improve Quality of Breakfast Menu Suggestions, Offer More Recipe Variety, Model switching - UI, Rework on the Mobile experience for Image/doc upload | Gen AI(Performance Improvements, Importing Physical Count, and Mobile) | Stories: 4 Out of 4 Committed stories and 1 stretch story has been completed Defects: 1 stretch defect has been completed Highlights: New UI from mobile upload Kudos: Client is happy for the new mobile upload UI CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 1 External Defect - 0. | What went well : Completed all the committed stories and some stretch stories What didn’t go well : NA |  |  | Completed
NA | 4.0 Sprint 2 | 2025-08-20 | 2025-09-02 | 18 | 29 | Introduced 49685 - 5 SP 49820 - 5 SP | Rework on the Mobile experience for Image/doc upload, Import AI-extracted Physical Count values into products/items,User Ratings, UI Refresh (Import Menu Popup Changes), Submit physical count, AI Entry Point screen 4 columns, UI Refresh (Nutrition Facts Labels Edit Screen), Gen AI Assistant and Tasks Pages | Gen AI Improvements: Data from Images (Nutrient Fact Labels) | Stories: 3 out of 3 committed stories and 2 from stretch has been completed Defects: 1 committed defect has been completed Highlights: Import physical count values, User Ratings, New Mobile UI, New breadcrumbs Kudos: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 1 External Defect - 0. | What went well : Completed all the committed stories and devlopment completed most of the stretch stories What didn’t go well : NA |  |  | Completed
NA | 4.0 Sprint 3 | 2025-09-03 | 2025-09-30 | 13 | 99 |  | Gen AI UI Refresh - AI Entry Point screen 4 columns, UI Refresh (Nutrition Facts Labels Edit Screen), Gen AI Assistant and Tasks Pages, Additional search details to identify a unique physical count record, Gen AI - Conversation Workflow, Refactor AI Code to use common API call, Nutrition facts label UI changes, UI changes for physical count upload, Mobile Workflow Changes, UI changes for Production Records, Gen AI - Terms of Service,Additional Physical Count Assistant UXUI Modifications (23 SEP 2025), Production Record Assistant - AI Production Record Format & Execute | Gen AI Improvements: Data from Images (Nutrient Fact Labels), Production Record, UI changes for physical count | Stories: 5 out of 5 committed stories and 10 stories from stretch has been completed Defects: 2 defects from stretch has been completed Highlights: AI Entry Point, UI changes for nutrition fact label, additional search details, code refactor, Conversation workflow, UI Changes physical count worksheet upload, Production records, UI changes for production record,Terms of Service Kudos: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 5 External Defect - 1. | What went well : Completed all the committed stories and most of the stretch stories What didn’t go well : |  |  | Completed
NA | 4.1 Sprint 1 | 2025-10-01 | 2025-10-14 | 25 | 28 |  | AI Task Grid Status values, Physical Count - Freeze Column Headers from scrolling, Production Record UI changes, Menu Generation Additional Instructions workflow issue, Support multiple images for a Production Record Import, Move prompts to the database, Sanitize uploaded image parsing | Improvements to Gen AI UX | Stories: 4 out of 3 committed stories and 2 stretch story has been completed Defects: 5 defects has been completed Highlights: UI changes in both physical and production worksheet upload Kudos: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 0 External Defect - 0. | What went well : 1. AI release 2. Completed committed stories and 2 stories from stretch What didn’t go well : 1. Token Limits AI |  |  | Completed
NA | 4.1 Sprint 2 | 2025-10-15 | 2025-10-28 | 36 | 39 |  | Production Record - Move Image to top & Edit grid to botton & freeze column headers & Recipe column, Move prompts to the database, Physical Count, Production Record, and Nutrition Facts Label Image viewer, Filter Site selectors based on the user's Site Group access, AI Task Status Values (Menu Gen & Nutrition Facts), Add Additional Logs in AI, AI Should be 'Edit Fields' not individual Security Page items | UI changes in Physical count, production record and nutrition fact label, AI Task Status changes, Security pages, Move prompt to DB | Stories: 4 out of 4 committed stories and 2 from stretch has been completed Defects: 5 out of 6 committed defects has been completed, 1 defect under dispute Highlights: UI changes in Physical count, production record and nutrition fact label, AI Task Status changes, Security pages Kudos: CRC Peer - 0, CRC Onsite -1, CRC Client - 0, Internal Defect - 1 External Defect - 6. | What went well : Completed all the committed stories and 2 from stretch What didn’t go well : Scheduler some times not working in QA Environment |  |  | Completed
NA | 4.1 Sprint 3 | 2025-10-29 | 2025-11-11 | 37 | 36 |  | Nutrition Facts Label - Create a Measurement from the Serving Size, Image upload functionality should filter to acceptable document types, Gen AI - In-App AI Marketing, Production Record Upload - Add Note that only menus with Planned Quantities will show up | Nutrition Facts Label - Create a Measurement from the Serving Size, In-App AI Marketing images | Stories: 4 out of 4 committed stories and 1 bounce back story has been completed Defects: 4 out of 6 commtted defects has been completed Highlights: Kudos: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 1 External Defect - 7 | BOH: What went well: Completed 3 stretch stories & 4 defects. What didn't go well Firewall issue/Random messages appearing in the application. Wave: What went well : Completed all the committed , stretch stories & defects. What didn't go well Firewall issue/Random messages appearing in the application & environmental issues in QA. |  |  | Completed
NA | 4.2 Sprint 1 | 2025-11-12 | 2025-12-09 | 8 | 37 |  | ER Have categories or more specific storage categories be able to be filtered out on the Transfer Pull Sheet report, Requisition# needs to be shown in the Transfers for Warehouse orders, Persist filter options on Receiving screen, Bidding - Estimated Quantity - Warning message, Bidding - Expand the Vendor Quotes - Bid Analysis grid for better view, Warehouse - Add Delivery Route field to Transfers screen, Warehouse - Add Delivery Route field to Warehouse Orders Bulk Approval screen, Warehouse - Add Delivery Route field to Warehouse Orders screen, Inventory Inquiry - Item Availability Report, Mosaic BOH - Bidding - Add Bid Status search filter under bidding response | Bidding UI Changes, Transfer pull sheet report, Persist filter, Add Delivery route field.in warehouse orders, Inquiry item Report, Bid Status Search filter | Stories: 3 out of 3 committed stories and 7 from stretch has been completed Defects: 1 stretch defect fixed Highlights: Kudos: RCA Mitigation: It's a existing common issue in all muliselect dropdownlist Mitigation Plan: Updating the kendo common code to fix CRC Peer - 0, CRC Onsite -1, CRC Client - 0, Internal Defect - 2 External Defect - 0 | What went well : Completed all the committed stories and 7 from stretch What didn’t go well : |  |  | Completed
NA | 4.2 Sprint 2 | 2025-12-10 | 2026-01-06 | 35 | 42 | Introduced Regression 50799, 50800 | Add page-break between days option to Production record report format setup (NK conversion feature gap), Warehouse Orders - 'View Report' - show the status with the date, Addition of new filter for Inventory Worksheet Physical counts, Warehouse - Add Delivery Route to Warehouse Orders report, Bidding Status Change, Regression - Inventory, Products, Bidding | Regression | Stories: 7 out of 7 committed stories and 3 from stretch has been completed Defects: 1 stretch defect fixed Highlights: Kudos: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 1 External Defect - 1 | What went well : Completed all the committed stories and 3 from stretch What didn’t go well : N/A |  |  | Completed
NA | 26.1 Sprint 3 | 2026-01-07 | 2026-01-20 | 16 | 18 |  | Inventory - Option to Export Inventory Worksheet,Regression - Bidding, Regression - Inventory, Regression - Inventory | Regression - Inventory and Bidding,Option to Export Inventory Worksheet | Stories: 3 out of 3 stories has been completed and 1 from stretch Defects: 4 out of 4 Defects has been completed and 2 from strech completed Highlights: Kudos: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 4 External Defect - 0 | What went well : Completed all the committed stories and 1 from stretch. Completed all defects in commited and 2 from stretch defects completed . Completed Regression. What didn’t go well : NA` |  |  | Completed
NA | 26.3 Sprint 1 | 2026-01-21 | 2026-02-03 | 18 | 24 |  | Inventory Transfer Report - Add "consolidated" filter (Nampa) Bidding - Bid Status Change from Awarded - Deactivate/Delete Pricelist Bidding - Calculate Estimated Qty Warehouse/Central Kitchen Item Availability Report - Add site level order quantity details | Bidding, Inventory Transfer Report (Adding consolidated Filter), and Defect Fixes. | Stories: Completed all the 4 committed stories and 2 stories from stretch. Defects: Completed 2 commited and 1 stretch defect. Highlights: Kudos: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 3 External Defect - 0 | What went well :Completed all the 4 committed stories and 2 stories from stretch. Completed 2 commited defects and 1 from stretch . What didn’t go well :NA | 0 | 2.5 | Completed
NA | 26.3 Sprint 2 | 2026-02-04 | 2026-02-17 | 16 | 16 |  | Display Warehouse Availability when Creating Warehouse Orders, Hide Bid Priority field on Product Maintenance, Warehouse/Central Kitchen Item Availability Report - Add Items On Hand filter, Add button to print Bidding Responses to Bid Maintenance screen, Bid Response/Analysis - Requested item vs Quoted Item [Substitution Workflow] | Warehouse availability report, Removing Bidpriority, Bidding requested and quoted items | Stories: Completed 5 out of 5 committed stories Defects: Nil Highlights: Kudos: CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 0 External Defect - 0 | What went well : Completed all the committed stories What didn’t go well : | 3 | 3 | Completed
NA | 26.3 Sprint 3 | 2026-02-18 | 2026-03-03 | 11 | 18 | 2 Stories Completed from Stretch (7 SP) | Central Kitchen - Bulk Order Approval. Bidding - Cleanup Bid Priority related code in the backend. Add the ability to Bulk commit transfers. Bidding - Bid Response/Analysis - Requested item vs Quoted Item [Substitution Workflow] - Bottom Line. Transfers - Search By Warehouse Order Number. | Central Kitchen and Transfers - Bulk Approvals, Bid Priority code cleanup, WO# at Transfers, Bid Analysis/Response screen with warnings when quoted item differ from requested | Stories: Completed 3 out of 3 commited stories and 2 from stretch Defects: Completed 2 Defects CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 0 External Defect - 2 | What went well : Completed 3 commited stories and 2 from stretch What didn’t go well : Nil | 2 | 2 | Completed
NA | 26.3 Sprint 4 | 2026-03-04 | 2026-03-31 | 41 | 54 | Stretch story - 2 SP Stretch defects - 11 SP Total 13 SP completed from stretch | Regression - Inventory,Products and Bidding modules. And also completed some stories : Transfers - Search and Replace - View Report, Products - Add security group for Products - Bulk Fulfillment (1),Ability to sort P/U Quantity and S/U Quantity for the physical counts screen,Products - Add Bulk Fulfillment menu option (2) | Regression - Inventory,Products and Bidding modules. And also completed some stories : Transfers - Search and Replace - View Report, Products - Add security group for Products - Bulk Fulfillment (1),Ability to sort P/U Quantity and S/U Quantity for the physical counts screen,Products - Add Bulk Fulfillment menu option (2) | Stories: Completed 7 out of 7 committed stories and 1 Story from stretch Defects: Completed 4 Defects CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 4 External Defect - 0 | What went well: Got thru regression quicker than estimated (3 weeks) Found and Fixed Lots of Defects Updates to regression test cases What didn't go well: Found 4 defects in regression | 7 | 8 | Completed
NA | 26.06 Sprint 1 | 2026-04-01 | 2026-04-14 | 29 | 35 | 6 SP - Defects completed from stretch | Bid Analysis - Add the Bid import document to the Bid Analysis attachment Inventory - Restrict duplicate items(Transfers and Usage) Product List Report - Add a new filter for Item Origin Products - Origin - Add new option "Non-Domestic (unspecified)" to droplist Ingredients - Add Notes Bidding - Add Last modified details in Bid Response and Bid Analysis Inventory - Bulk Adjustments - 1 - Security page Inventory - Bulk Adjustments - 2 - Search for Products | Bidding, Bulk Adjustments, Adding Item Origin Filter to Product List report, and Defect Fixes | Stories: Completed 8 out of 8 committed stories CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 1 External Defect - 1 | What went well : Completed 8 commited stories What didn’t go well : Nil | 2 | 2 | Completed
NA | 26.06 Sprint 2 | 2026-04-15 | 2026-04-28 | 24 | 24 |  | Inventory - Bulk Adjustments - New screen to update the bulk adjustments, Inventory - Search Transfers by Transfer # - added new filter to search by transfer #, Performance improvisation on product group to retrieve the data faster to show in the result grid, Inventory - Add User Tracking for Physical Count transactions to who added, modified and committed the record, Item Maintenance - 3 - Left Side Nav Menu and landing page, Products - Addition of new Bulk Fulfillment screen (3) - to update the bulk fulfillment | Bulk Adjustments, Item Maintenance, Bulk fulfillment, Report filters | Stories: Completed 5 out of 6 committed stories Defects: Completed 1 stretch defect CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 1 External Defect - 0 | What went well : Completed 5 commited stories What didn’t go well : QA server issue on build release | 2 | 2 | Completed
NA | 26.06 Sprint 3 | 2026-04-29 | 2026-05-12 | 23 | 23 |  | Inventory - Bulk Adjustments - Create Bulk Adjustments screen, Products - Adding Bulk Fulfillment by Group (4), Report - Inventory Transfer - Add category filters to filter the data Report - Shopping List - Add the ability to exclude a product from the shopping list report. | Bulk Adjustments, Bulk fulfillment, Report filters, Exclustion list in reports | Stories: Completed 4 out of 5 committed stories Defects: Nil CRC Peer - 0, CRC Onsite -0, CRC Client - 0, Internal Defect - 0 External Defect - 0 | What went well : Completed 4 commited stories What didn’t go well: PTOs | 3 | 3 | Completed
NA | 26.06 Sprint 4 | 2026-05-13 | 2026-05-26
Note on M53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: 1 Unplanned Leave (Deepika)

## 26.06 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-05-13 | 2026-05-26 | 26.06 Sprint 4 | Rajiv | 53024 | [WAVE] Mosaic BOH - Central Kitchen - Who Can Order Finished Products - Site Setting | Story Being Developed | 3 | 1.75 | 7 | 2026-05-06 | 2026-05-15 | Yes |  |  | Krupa | Default "Yes" option is not working | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48990 | 2026-05-12 | [7 empty] | If CK flag is no then Finished Product ingredient linked product should show. |  | Meets Expectation
2 | BOH Wave | 2026-05-13 | 2026-05-26 | 26.06 Sprint 4 Stretch | Rajiv | 53229 | Mosaic BOH - ExcludeFromSuggestion cleanup - code & db clean up | Story Peer Review | 1 | 0.5 | 2 | 2026-05-12 | 2026-05-12 | NA | Charles | Nil | Charles | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48993 | 2026-05-12 | 2026-05-12 | Charles | Nil | Charles | 2026-05-12 | Nil | Nil | Nil | Nil | Meets Expectation
3 | BOH Wave | 2026-05-13 | 2026-05-26 | 26.06 Sprint 4 Stretch | Rajiv | 53066 | [WAVE] Mosaic BOH - Central Kitchen - Who Can Order Finished Products - Overrides | Story Being Developed | 8 | 2.75 | 11 | 2026-05-14
4 | BOH Wave | 2026-05-13 | 2026-05-26 | 26.06 Sprint 4 Stretch | Krupa | 53046 | [WAVE] Mosaic BOH - Products - Adding Bulk Fulfillment by Group - Add Product (4b) | Story Being Developed | 8 | 1 | 4 | 2026-05-13
5 | BOH Wave | 2026-05-13 | 2026-05-26 | 26.06 Sprint 4 Stretch | Priya | 53285 | Mosaic-BOH-Wave-Acceleration-Bidding Response Automation Story | Story Being Developed | 13

## 26.06 Sprint 4 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
26.06 Sprint 4 Stretch | 27315 |  | Deepika |  | Mosaic BOH - Site & Other dropdown values are disappeared in Product Fulfilment while using Keyboard selection | High | Manual | Internal | Defect Being Fixed | 2 | 1.5 | 6 | Existing_Issues

## 26.06 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-04-29 | 2026-05-12 | 26.06 Sprint 3 | Deepika | 52617 | [WAVE] Mosaic BOH - Inventory - Bulk Adjustments - 3 - Create Bulk Adjustments screen | Story Completed | 2 | 2.25 | 9 | 2026-04-29 | 2026-05-04 | Done | Priya | Sugesstion : Enter button should redirects to the Bulk Adjustment screen | Rajiv | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48952 | 2026-05-08 | 2026-05-08 | Charles | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Meets Expectation
2 | BOH Wave | 2026-04-29 | 2026-05-12 | 26.06 Sprint 3 | Deepika | 52618 | [WAVE] Mosaic BOH - Inventory - Bulk Adjustments - 4 - Managing Bulk Adjustments | Story Being Developed | 8 | 10 | 40 | 2026-04-29 | 2026-05-08 | Yes | Rajiv | Nil | Rajiv | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48952 | 2026-05-11 | 2026-05-11 | Charles | Nil | Nil | Nil | Nil | UI Mistakes and AC points missing | Nil | P/U and S/U are mentioned as Mandatory field in AC by Robyn(Client side), Craig suggessted Either one is Mandatory field. Added few Bouncebacks and developer also on PTO. So story will carry forward to next sprint. | Meets Expectation
3 | BOH Wave | 2026-04-29 | 2026-05-12 | 26.06 Sprint 3 | Krupa | 51840 | [WAVE] Mosaic BOH - Products - Adding Bulk Fulfillment by Group (4) | Story Completed | 5 | 6.75 | 27 | 2026-04-29 | 2026-05-05 | Yes | Priya | Cosmetic and UI sugesstion given | Rajiv | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48841 | 2026-05-05 | 2026-05-08 | Charles | Nil | Charles | 2026-05-08 | Nil | Nil | Nil | Nil | Meets Expectation
4 | BOH Wave | 2026-04-29 | 2026-05-12 | 26.06 Sprint 3 | Rajiv | 52505 | [WAVE] Mosaic BOH - Report - Inventory Transfer - Add category filters (Independence 30, MO) | Story Completed | 3 | 1.5 | 6 | 2026-04-24 | 2026-04-29 | Yes | Priya | Nil | Krupa | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48678 | 2026-04-29 | 2026-04-30 | Charles | Nil | Charles | 2026-04-30 | Nil | Remove blank selection in the dropdown | Nil | Nil | Meets Expectation
5 | BOH Wave | 2026-04-29 | 2026-05-12 | 26.06 Sprint 3 | Rajiv | 44925 | Mosaic BOH - Report - Shopping List - Add the ability to exclude a product (Fresno) | Story Completed | 5 | 5.75 | 23 | 2026-04-29 | 2026-05-06 | Yes | Priya | Sugesstion : Order must allow to select from the dropdown | Deepika | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48840 | 2026-05-06 | 2026-05-06 | Charles | Nil | Charles | 2026-05-06 | Nil | Nil | Nil | Nil | Meets Expectation
7 | BOH Wave | 2026-04-29 | 2026-05-12 | 26.06 Sprint 3 Stretch | Priya | 53119 | [Wave] Mosaic BOH - Bidding Automation Testing | Story Completed | 10 | 10.5 | 42 | 2026-04-29 | 2026-05-12 | Yes | Priya | NA | NA | NA | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/48996 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | BOH Wave | 2026-04-29 | 2026-05-12 | 26.06 Sprint 3 Stretch | Rajiv | 53024 | [WAVE] Mosaic BOH - Central Kitchen - Who Can Order Finished Products - Site Setting | Story Being Developed | 8 | 6.75 | 27 | 2026-05-06 | [17 empty] | Meets Expectation
6 | BOH Wave | 2026-04-29 | 2026-05-12 | 26.06 Sprint 3 Stretch | Krupa | 53046 | [WAVE] Mosaic BOH - Products - Adding Bulk Fulfillment by Group - Add Product (4b) | Story Being Developed | 8 | 5.75 | 23 | 2026-05-05 | [17 empty] | Meets Expectation

## 26.06 Sprint 3 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments

## 26.06 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-04-15 | 2026-04-28 | 26.06 Sprint 2 | Rajiv | 28830 | [WAVE] Mosaic BOH - Inventory - Search Transfers by Transfer # | Story Completed | 1 | 0.5 | 2 | 2026-04-08 | 2026-04-13 | NA | Deepika | Nil | Deepika | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48373 | 2026-04-13 | 2026-04-15 | Charles | Nil | Charles | 2026-04-15 | Nil | Nil | Nil | Nil | Meets Expectation
2 | BOH Wave | 2026-04-15 | 2026-04-28 | 26.06 Sprint 2 | Rajiv | 52863 | [WAVE] - Mosaic BOH - Performance improvisation on product group | Story Completed | 3 | 3 | 12 | 2026-04-14 | 2026-04-15 | NA | Deepika | Nil | Deepika | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48416 | 2026-04-15 | 2026-04-16 | Charles | Nil | Charles | 2026-04-16 | Nil | Nil | Nil | Nil | Meets Expectation
3 | BOH Wave | 2026-04-15 | 2026-04-28 | 26.06 Sprint 2 | Rajiv | 52501 | [WAVE] Mosaic BOH - Inventory - Add User Tracking for Physical Count transactions | Story Completed | 5 | 3 | 12 | 2026-04-15 | 2026-04-17 | Yes | Deepika | Nil | Deepika | Remove commented lines | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48460 | 2026-04-16 | 2026-04-16 | Charles | Nil | Charles | 2026-04-16 | Nil | Nil | Nil | Nil | Meets Expectation
4 | BOH Wave | 2026-04-15 | 2026-04-28 | 26.06 Sprint 2 | Rajiv | 52685 | [WAVE] Mosaic BOH - Item Maintenance - 3 - Left Side Nav Menu and landing page | Story Completed | 5 | 4.5 | 18 | 2026-04-17 | 2026-04-22 | NA | Deepika | Nil | Deepika | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48531 | 2026-04-22 | 2026-04-22 | Charles | Nil | Charles | 2026-04-27 | Nil | Breadcrumbs issue | Nil | Nil | Meets Expectation
5 | BOH Wave | 2026-04-15 | 2026-04-28 | 26.06 Sprint 2 | Krupa | 51824 | [WAVE] Mosaic BOH - Products - Addition of new Bulk Fulfillment screen (3) | Story Completed | 5 | 4 | 16 | 2026-04-15 | 2026-04-21 | NA | Rajiv | Nil | Rajiv | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48536 | 2026-04-21 | 2026-04-22 | Charles | Nil | Charles | 2026-04-22 | Nil | Nil | Nil | Nil | Meets Expectation
6 | BOH Wave | 2026-04-15 | 2026-04-28 | 26.06 Sprint 2 Stretch | Priya | 52913 | MosaiC_BOH_Wave_Acceleration Automation Script | Story Completed | 10 | 10 | 40 | 2026-04-16 | 28-04-26 | Yes | Priya | Nil | Suresh | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48631 | 2026-04-24 | 2026-04-28 | Charles | Nil | NA | NA | Nil | Nil | Nil | Nil | NA

## 26.06 Sprint 2 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
26.06 Sprint 2 Stretch | 27150 |  | Deepika | Defect | Mosaic - BOH -Wave-Acceleration-Bidding Multiple issues | High | Manual | Internal | Defect Fixed | 2 | 2 | 8 | Existing_Issues | Existing Production Issue, defect was not identified in the previous test cycles

## 26.06 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 | Krupa | 52097 | [Wave]Mosaic BOH - Bidding - Add Last modified details in Bid Response and Bid Analysis | Story Completed | 3 | 0.75 | 3 | 2026-04-01 | 2026-04-02 | Yes | Priya | Cosmetic issue :Last Modified On:' follow the same format in bid response screen , like other screens 'Last modified on: | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48046 | 2026-03-26 | 2026-04-01 | Charles | Nil | Charles | 2026-04-01 | Nil | Nil | Nil | Nil | Meets Expectation
2 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 | Krupa | 52382 | [Wave] Mosaic BOH - Inventory - Restrict duplicate items(Transfers and Usage) | Story Completed | 2 | 1.5 | 6 | 2026-04-01 | 2026-04-02 | Yes | Priya | By Product Group search is not working in Transfer,Usage and Warehouse Hotspot Transfer screen(existing issue). | Deepika | nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48130 | 2026-03-31 | 2026-04-01 | Charles | Nil | Charles | 2026-04-01 | Nil | Nil | Nil | Nil | Meets Expectation
3 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 | Rajiv | 51702 | [WAVE]Mosaic BOH - Products - Origin - Add new option "Non-Domestic (unspecified)" to droplist | Story Completed | 1 | 0.5 | 2 | 2026-04-01 | 2026-04-01 | NA | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48099 | 2026-03-30 | 2026-03-31 | Charles | Nil | Charles | 2026-03-31 | Nil | Nil | Nil | NIl | Meets Expectation
4 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 | Rajiv | 51452 | [WAVE]Mosaic BOH - Product List Report - Add a new filter for Item Origin | Story Completed | 8 | 7.5 | 30 | 2026-04-01 | 2026-04-07 | NA | Priya | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48261 | 2026-04-07 | 2026-04-08 | Charles | Nil | Charles | 2026-04-08 | Nil | Remove the extra space | Nil | NIl | Meets Expectation
5 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 | Deepika | 51745 | [WAVE] Mosaic BOH - Ingredients - Add Notes | Story Completed | 2 | 2.5 | 10 | 2026-04-01 | 2026-04-02 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48100 | 2026-03-30 | 2026-04-02 | Charles | Nil | Charles | 2026-04-02 | Nil | Nil | Nil | NIl | Meets Expectation
6 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 | Deepika | 52614 | [WAVE] Mosaic BOH - Inventory - Bulk Adjustments - 1 - Security page | Story Completed | 2 | 1 | 4 | 2026-04-02 | 2026-04-02 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48195 | 2026-04-02 | 2026-04-06 | Charles | Nil | Charles | 2026-04-06 | Nil | Nil | Nil | NIl | Meets Expectation
7 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 | Krupa | 52257 | [Wave]Mosaic BOH - Bid Analysis - Add the Bid import document to the Bid Analysis attachment | Story Completed | 8 | 9 | 36 | 2026-04-01 | 2026-04-08 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48286 | 2026-04-08 | 2026-04-08 | Charles | Nil | Charles | 2026-04-08 | Nil |  | Nil | It is blocking to test the story, because when click on the 'Import Test' button from the Bidding Response screen getting server error | Meets Expectation
8 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 | Deepika | 52615 | [WAVE] Mosaic BOH - Inventory - Bulk Adjustments - 2 - Search for Products | Story Completed | 3 | 2.25 | 9 | 2026-04-02 | 2026-04-06 | Yes | Priya | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/48226 | 2026-04-03 | 2026-04-06 | Charles | Nil | Charles | 2026-04-06 | Nil | Check all box is checked even when any box is checked | Nil | NIl | Meets Expectation
10 | BOH Wave | 2026-04-01 | 2026-04-14 | 26.06 Sprint 1 Stretch | Priya | 52682 | Mosaic Boh-Wave-Acceleration - Bidding Automation Test Scripts | Story Completed | 10 | 9.5 | 38 | 2026-04-01 | 2026-04-14 | Yes | Priya | NIL | Suresh |  | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/48403 | 2026-04-14 | 2026-04-14 | Charles |  | Charles |  |  |  | Nil | Completed 8 Test Cases from the Bid Responses screen.

## 26.06 Sprint 1 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
26.06 Sprint 1 Stretch | 27159 |  | Krupa | Defect | Mosaic - BOH -Wave-Acceleration- By Product Group is not working | High | Manual | Internal | Defect Fixed | 5 | 3 | 12 | Existing_Issues | The defect was related to CSS issue.Found during internal testing.
26.06 Sprint 1 Stretch | 27144 |  | Rajiv | Defect | Mosaic BoH - multiple - Cannot bulk export vendor orders after approval | High | Manual | External | Defect Fixed | 1 | 1 | 4 | Development | In the defect 26863 we have disabled the approved button functionality on approved status in all bulk approval screens, but in vendor bulk approval button caption is changed

## 26.3 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 | Rajiv | 47650 | [Wave] - Mosaic BOH(WH) - Transfers - Search and Replace - View Report | Story Completed | 3 | 1.5 | 6 | 2026-03-04 | 2026-03-04 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47594 | 2026-03-04 | 2026-03-05 | Charles | Nil | Charles | 2026-03-05 | Nil | 1. Product name can be in a single line instead of wrapping 2. On Hand, On Order, Reserved details are hidden 3. Records should not be broken; it can be on the new page 4. Purchase unit and Stock unit combined need to be displayed in the Unit (refer to Quantity per purchase unit in the transfers) 5. It should be "Sending Site:" It should not be SiteName | Nil | Nil | Needs Improvement
2 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 | Krupa | 51819 | [WAVE] Mosaic BOH - Products - Add security group for Products - Bulk Fulfillment (1) | Story Completed | 2 | 0.625 | 2.5 | 2026-03-04 | 2026-03-04 | Yes | Priya | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47481 | 2026-02-25 | 2026-02-25 | Charles | Nil | Charles | 2026-02-25 | Nil | For the Admin security group, it needs to be checked by default | Nil | NIl | Meets Expectation
3 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 | Deepika | 51429 | [WAVE]-Mosaic BOH- Ability to sort P/U Quantity and S/U Quantity for the physical counts screen | Story Completed | 2 | 2 | 8 | 2026-03-05 | 2026-03-09 | Yes | Priya | 1) Sorting not cleared when dropdown value is changed. 2. At the time of storing some of the P/Q and S/Q Values are vanished and values are mismatching after sorting | Krupa | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47507 | 2026-03-09 | 2026-03-10 | Charles | Nil | Charles | 2026-03-10 | Nil | NA | NA | An Existing issue - while sorting any column some product datas are interchanged or not saved | Meets Expectation
4 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 | Krupa | 51811 | [WAVE] Mosaic BOH - Products - Add Bulk Fulfillment menu option (2) | Story Completed | 1 | 0.875 | 3.5 | 2026-03-04 | 2026-03-04 | Yes | Priya | Issue : Menus visibility based on the Tier Levels not handled. | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47514 | 2026-02-26 | 2026-02-26 | Charles | Nil | Charles | 2026-02-26 | Nil | Nil | Nil | NIl | Meets Expectation
5 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 | Team | 52158 | [WAVE]Mosaic BOH - 26.3 Regression - Inventory | Story Completed | 13 | 15.75 | 63 | 2026-03-04 | 2026-03-10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 | Team | 52159 | [Wave]Mosaic BOH - 26.3 Regression - Products | Story Completed | 5 | 11.25 | 45 | 2026-03-03 | 2026-03-20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 | Team | 52163 | [Wave]Mosaic BOH - 26.3 Regression - Bidding | Story Completed | 13 | 10.75 | 43 | 2026-03-12 | 2026-03-20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 Stretch | Krupa | 52185 | [Wave] Mosaic BOH - Hide Bulk Fulfillment menu | Story Completed | 2 | 0.5 | 2 | 2026-03-04 | 2026-03-04 | Yes | Rajiv | Nil | Rajiv | Nil | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47597 | 2026-03-04 | 2026-03-04 | Charles | Nil | Charles | 2026-03-04 | Nil | NA | NA | NA | Meets Expectation
9 | BOH Wave | 2026-03-04 | 2026-03-31 | 26.3 Sprint 4 Stretch | Priya | 52183 | [Wave] Mosaic -BOH Bidding Maintenance Edit Screen Automation Test Scripts | Story Completed | 10 | 9.5 | 38 | 2026-03-23 | 2026-03-31 | Yes | Priya | Nil | Suresh | Nil | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/48132 | 2026-03-31 |  | Suresh | NA |  |  |  | NA | NA | Completed 6 stories and 3 Inprogress created PR

## ExportData
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments
1 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 | Deepika | 48436 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - AI Assistant - Add the ability to upload images from the system | Story Peer Review | 2 | 2.25 | 9 | 2025-06-25 | 2025-07-22 | NIL | NIL | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43487 | 2025-07-19 | Nil | Nil | Nil | Nil | Nil | NIl | NIL
2 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 | Joel | 49285 | [Wave]Mosaic BOH - Iterative AI call to parse Inventory Worksheet images | Story Peer Review | 5 | 8 | 32 | 2025-07-18 | 2025-07-31 | Yes | NIL | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43668 | 2025-07-31 |  | Charles | Nil | Andrew
3 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 | Rajiv | 49286 | [Wave]Mosaic BOH - UI for verification and Editing the AI Response of the Inventory Parsing | Story Peer Review | 8 | 7.5 | 30 | 2025-07-22 | 2025-07-31 | Yes | NIL | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43668 | 2025-07-31 |  | Charles | Nil | Andrew
4 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 | Joel | 49005 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Model switching | Story Peer Review | 5 | 6 | 24 | 2025-06-25 | 2025-08-04 | Yes | NIL | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43743 | 2025-08-04
5 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 [Stretch] | Deepika | 48742 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Improve Quality of Breakfast Menu Suggestions | Story Peer Review | 5 | 3.75 | 15 | 2025-07-23 | 2025-07-27 | NIL | NIL | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43610 | 2025-07-27 | 2025-07-29 | Charles | NIL | NIL | 2025-07-29 | NIL | NIL
6 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 [Stretch] | Deepika | 48743 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Offer More Recipe Variety | Story Being Developed | 5 | 3 | 12 | 2025-07-31
7 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 [Stretch] | Rajiv | 49415 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Model switching - UI | Story Peer Review | 5 | 4.5 | 18 | 2025-07-31 | 2025-08-04 | Yes | NIL | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43743 | 2025-08-04
8 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 [Stretch] | Priyadharshini | 49307 | [Wave]Mosaic BOH - Automation for Create a Menu Plan | Story Being Developed | 13 | 7.5 | 30

## 26.3 Sprint 4 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
26.3 Sprint 4 | 26857 |  | Deepika | Defect | Mosaic BOH - Wave- Orders within par level - Not Set is not working- Common issue in All Bulk Approvals | Minor | Manual | External | Defect Fixed | 2 | 4 | 16 | Requirements | Existng code Issue found in production. Common issue and fixed it on all bulk approval screen
26.3 Sprint 4 Stretch | 26926 |  | Deepika | Defect | [Wave]Mosaic BOH - Bidding - Estimated Qty issue | Minor | Manual | External | Defect Fixed | 2 | 3.75 | 15 | Development | Existing issues & Javascript error , missed at manual Test
26.3 Sprint 4 Stretch | 26957 |  | Rajiv | Defect | Mosaic BOH Wave - Common Issue in All Orders Screens | Minor | Manual | External | Defect Fixed | 2 | 0.25 | 1 | Existing_Issues | Existing issues, and it's not identified in earlier test cycles
26.3 Sprint 4 | 26966 |  | Rajiv | Defect | Mosaic BOH - Regression - Transfers - Search and Replace - Can see Shipped status in the replace screen | Minor | Manual | External | Defect Fixed | NA | NA | NA | Existing_Issues | Defect found in regression, issue not identified in earlier test cycles
26.3 Sprint 4 | 26981 |  | Krupa | Defect | Mosaic BOH - Regression - Bidding - Responses - Bid Response # field not searching correctly | Minor | Manual | External | Defect Fixed | NA | NA | NA | Existing_Issues | Defect found in regression
26.3 Sprint 4 | 27017 |  | Rajiv | Defect | Mosaic BOH - Regression - Ordering - All order pages - Par Level validation calculation is not being flagged correctly | Minor | Manual | External | Defect Fixed | NA | NA | NA | Existing_Issues | Existing issues, and it's not identified in earlier test cycles
26.3 Sprint 4 | 27041 |  | Rajiv | Defect | Mosaic BOH - Regression - Inventory - Physical Counts screen - Buttons not all on one line | Minor | Manual | External | Defect Fixed | NA | NA | NA | Existing_Issues | Existing issues, and it's not identified in earlier test cycles
26.3 Sprint 4 Stretch | 26863 |  | Rajiv | Defect | Mosaic BOH - Wave - System Allows Multiple Approvals for Already Approved Orders in all Bulk Approval Screens(WH & CK) | Minor | Manual | External | Defect Fixed | 5 | 3 | 12 | Existing_Issues | Existing issues, and it's not identified in earlier test cycles
26.3 Sprint 4 Stretch | 27070 |  | Rajiv | Defect | Mosaic BOH - Wave-Acceleration - Bid Analysis - Application Throws Console Error on Cancel Button Click | Minor | Manual | External | Defect Fixed | 2 | 1.5 | 6 | Existing_Issues | Existing issues, and it's not identified in earlier test cycles
26.3 Sprint 4 | 27007 |  | Rajiv | Defect | Mosaic BOH - Regression - Central Kitchen Orders - Created transfer is showing status of committed but is only submitted | Minor | Manual | External | Defect Fixed | NA | NA | NA | Existing_Issues | Existing issues, and it's not identified in earlier test cycles

## 26.3 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-02-18 | 2026-03-03 | 26.3 Sprint 3 | Rajiv | 48560 | [WAVE] Mosaic BOH - Central Kitchen - Bulk Order Approval | Story Completed | 3 | 1.5 | 6 | 2026-02-05 | 2026-02-11 | Yes | Krupa | NIL | Krupa | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47171 | 2026-02-11 | 2026-02-23 | Charles | Nil | Charles | 2026-02-23 | Nil | Par Level - Not set Not working properly | Nil | Testing only moved to this sprint | Meets Expectation
2 | BOH Wave | 2026-02-18 | 2026-03-03 | 26.3 Sprint 3 | Rajiv | 51889 | [Wave]Mosaic BOH - Bidding - Cleanup Bid Priority related code in the backend | Story Completed | 2 | 0.75 | 3 | 2026-02-12 | 2026-02-16 | Yes | Charles | NIL | Charles | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47265 | 2026-02-16 | 2026-02-24 | Charles | Nil | Charles | 2026-02-24 | Nil | Nil | Nil | Testing only moved to this sprint | Meets Expectation
3 | BOH Wave | 2026-02-18 | 2026-03-03 | 26.3 Sprint 3 | Krupa | 48557 | [WAVE]Mosaic BOH - Add the ability to Bulk commit transfers | Story Completed | 3 | 2.125 | 8.5 | 2026-02-19 | 2026-02-25 | Yes | Priya | Here are suggestions to keep the application consistent 1. If any required fields not selected, consolidate all warning messages and display to Failure Reason popup 2. When click the Transfer# hyperlink, open transfer item to the new tab | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47312 | 2026-02-20 | 2026-02-26 | Charles | Nil | Charles | 2026-02-26 | Nil | Nil | Increase the width of warning window | NIl | Meets Expectation
4 | BOH Wave | 2026-02-18 | 2026-03-03 | 26.3 Sprint 3 Stretch | Deepika | 51981 | [Wave]Mosaic BOH - Bidding - Bid Response/Analysis - Requested item vs Quoted Item [Substitution Workflow] - Bottom Line | Story Completed | 5 | 5.25 | 21 | 2026-02-18 | 2026-02-20 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47396 | 2026-02-20 | 2026-02-27 | Charles | Nil | NA | 2026-02-27 | Nil | Nil | Nil | NIl | Meets Expectation
5 | BOH Wave | 2026-02-18 | 2026-03-03 | 26.3 Sprint 3 Stretch | Rajiv | 51850 | [Wave] Mosaic BOH - Transfers - Search By Warehouse Order Number | Story Completed | 2 | 1.5 | 6 | 2026-02-18 | 2026-02-18 | Yes | Priya | NIL | Krupa | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47316 | 2026-02-18 | 2026-02-19 | Charles | Nil | Charles | 2026-02-19 | Nil | Need hyperlink in warehouse order # | Nil | Nil | Needs Improvement

## 26.3 Sprint 3 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
26.3 Sprint 3 | 26744 |  | Rajiv | Defect | [WAVE] Mosaic BOH - Delivery and Source Site Details are showing even after removing the products-Vendor and Warehouse Order | Minor | Manual | Internal | Defect Fixed | 1 | 1.75 | 7 | Existing_Issues | The defect was not identified in the previous test cycles
26.3 Sprint 3 | 26797 |  | Krupa | Defect | [WAVE] Mosaic BOH - Bidding - "Selecting a Vendor" warning message | Minor | Manual | External | Defect Fixed | 2 | 1.5 | 6 | Existing_Issues | The defect was not identified in the previous test cycles

## 26.3 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-02-04 | 2026-02-17 | 26.3 Sprint 2 | Rajiv | 51516 | [WAVE] Mosaic BOH - Display Warehouse Availability when Creating Warehouse Orders | Story Completed | 2 | 1.25 | 5 | 2026-01-27 | 2026-01-29 | Done | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46936 | 2026-01-29 | 2026-01-30 | Charles | NIL | Charles | 2026-01-30 | NIL | NIL | NIL | NIL | Meets Expectation
2 | BOH Wave | 2026-02-04 | 2026-02-17 | 26.3 Sprint 2 | Rajiv | 51550 | [WAVE] Mosaic BOH - Bidding - Hide Bid Priority field on Product Maintenance | Story Completed | 1 | 0.75 | 3 | 2026-01-30 | 2026-01-30 | Done | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46941 | 2026-01-29 | 2026-02-04 | Charles | NIL | Charles | 2026-02-04 | NIL | NIL | NIL | NIL | Meets Expectation
3 | BOH Wave | 2026-02-04 | 2026-02-17 | 26.3 Sprint 2 | Rajiv | 28879 | [WAVE] Mosaic BOH - Warehouse/Central Kitchen Item Availability Report - Add Items On Hand filter | Story Completed | 3 | 3 | 12 | 2026-02-04 | 2026-02-05 | Done | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47058 | 2026-02-05 | 2026-02-10 | Charles | NIL | Charles | 2026-02-10 | NIL | NIL | NIL | NIL | Meets Expectation
4 | BOH Wave | 2026-02-04 | 2026-02-17 | 26.3 Sprint 2 | Deepika | 51347 | [WAVE] Mosaic BOH - Add button to print Bidding Responses to Bid Maintenance screen | Story Completed | 2 | 1.75 | 7 | 2026-02-04 | 2026-02-04 | Done | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46955 | 2026-02-11 | 2026-02-11 | Charles | NIL | NIL | NIL | NIL | NIL | NIL | NIL | Meets Expectation
5 | BOH Wave | 2026-02-04 | 2026-02-17 | 26.3 Sprint 2 | Deepika | 49576 | [Wave]Mosaic BOH - Bidding - Bid Response/Analysis - Requested item vs Quoted Item [Substitution Workflow] | Story Completed | 8 | 12.75 | 51 | 2026-02-04 | 2026-02-17 | Done | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/47292 | 2026-02-16 | 2026-02-16 | Charles | NIL | NIL | NIL | NIL | NIL | NIL | Testing was not completed by myself at Line Item and was having validation errors | Meets Expectation
6 | BOH Wave | 2026-02-04 | 2026-02-17 | 26.3 Sprint 2 Stretch | Priya | 51786 | [Wave] Mosaic-BOH- Automation for Bidding Maintenance Screen | Story Completed | 8 | 8 | 32 | 2026-02-04 | 17-02-2026 | Done | Priya | NIL |  | NIL | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/47291 | 2026-02-17 |  | Charles | NIL | NIL | NIL | NIL | NIL | NIL | 8 Test Script written in Bidding Menu

## 26.3 Sprint 2 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments

## 26.3 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-01-21 | 2026-02-03 | 26.3 Sprint 1 | Rajiv | 51357 | [Wave] - Mosaic BOH - Bidding - Bid Status Change from Awarded - Deactivate/Delete Pricelist | Story Completed | 2 | 0.75 | 3 | 2026-01-12 | 2026-01-14 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46639 | 2026-01-14 | 2026-01-19 | Charles | NIL | Charles | 2026-01-19 | NIL | NIL | NIL |  | Meets Expectation
2 | BOH Wave | 2026-01-21 | 2026-02-03 | 26.3 Sprint 1 | Rajiv | 50120 | [WAVE] Mosaic BOH - Warehouse/Central Kitchen Item Availability Report - Add site level order quantity details | Story Completed | 5 | 4.5 | 18 | 2026-01-19 | 2026-01-22 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46775 | 2026-01-22 | 2026-01-23 | Charles | NIL | Charles | 2026-01-23 | NIL | Site# is missing in the report | NIL |  | Needs Improvement
3 | BOH Wave | 2026-01-21 | 2026-02-03 | 26.3 Sprint 1 | Deepika | 50816 | [Wave]Mosaic BOH - Bidding - Calculate Estimated Qty | Story Completed | 2 | 2 | 8 | 2026-01-19 | 2026-01-21 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46710 | 2026-01-19 | 2026-01-21 | Rajiv | NIL | Charles | 2026-01-21 | NA | Alignment and font needs to be corrected | NA | Gary: To test it with 200+ records. -Working as directed. Craig- cosmetic changes | Meets Expectation
4 | BOH Wave | 2026-01-21 | 2026-02-03 | 26.3 Sprint 1 | Krupa | 51517 | [WAVE] Mosaic BOH - Inventory Transfer Report - Add "consolidated" filter (Nampa) | Story Completed | 5 | 4.5 | 18 | 2026-01-21 | 2026-01-28 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46905 | 2026-01-28 | 2026-01-29 | Rajiv | NIL | Charles | 2026-02-02 | NIL | NIL | NIL |  | Meets Expectation
5 | BOH Wave | 2026-01-21 | 2026-02-03 | 26.3 Sprint 1 Stretch | Priya | 51635 | [Wave] - Mosaic BOH - Bidding Maintenance Automation Test Cases | Story Completed | 13 | 6 | 24 | 2026-01-21 | 2026-02-03 | Yes | Priya | NIL | NIL | NIL | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/47036 | 2026-03-02 |  |  | NIL |  |  | NIL | NIL | NIL | HeartLand Logo is blocking the Automation script in this Sprint 5 Test Cases Completed and 2 in Progress
6 | BOH Wave | 2026-01-21 | 2026-02-03 | 26.3 Sprint 1 Stretch | Rajiv | 51551 | [WAVE] Mosaic BOH - Bidding - Remove Bid Priority column from Bid Maintenance | Story Completed | 2 | 1.5 | 6 | 2026-01-30 | 2026-01-30 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46942 | 2026-01-30 | 2026-01-30 | Charles | NIL | Charles | 2026-01-30 | NIL | NIL | NIL |  | Meets Expectation
7 | BOH Wave | 2026-01-21 | 2026-02-03 | 26.3 Sprint 1 Stretch | Rajiv | 51552 | [WAVE] Mosaic BOH - Bidding - Hide Bidding Setup menu | Story Completed | 2 | 0.75 | 3 | 2026-01-30 | 2026-01-30 | Yes | Charles | NIL | Charles | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46974 | 2026-01-30 | 2026-01-30 | Charles | NIL | Charles | 2026-01-30 | NIL | NIL | NIL |  | Meets Expectation

## 26.3 Sprint 1 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
26.3 Sprint 1 | 26546 |  | Deepika | Defect | Mosaic BOH - Wave-Acceleration- Bidding Security Group Page | Minor | Manual | Internal | Defect Fixed | 2 | 0.25 | 1 | Existing_Issues | The defect was identified during regression testing but was not detected in the earlier test cycles
26.3 Sprint 1 Strech | 26640 |  | Deepika | Defect | Mosaic_Wave_Acceleration Inventory-Physical Count- Usage Category not showing in the generated Excel sheet for some reports | Minor | Manual | Internal | Defect Fixed | 2 | 2.25 | 9 | Existing_Issues | The usage category which was mentioned has not shown at excel sheet.It has not handled when it needs to be shown at left side in excel sheet. So added the existing methods that all other categories is assigned with
26.3 Sprint 1 | 26416 |  | Krupa | Defect | [Wave] Mosaic BOH - Common issue in Filter Search Dropdown | Minor | Manual | Internal | Defect Fixed | 2 | 2 | 8 | Existing_Issues | The defect was identified during regression testing but was not detected in the earlier test cycles

## 26.1 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2026-01-07 | 2026-01-20 | 26.1 Sprint 3 | Deepika | 51036 | [Wave]Mosaic BOH - Inventory - Option to Export Inventory Worksheet | Story Completed | 2 | 2 | 8 | 2025-12-12 | 2025-12-22 | Yes | Suresh | 1) Search based on the UI data even if user changed the date and doesnt save it 2) Product Item Number Missing | Rajiv | N/A | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46342 | 2025-12-23 | 2026-01-09 | Rajiv | NA | Charles | 2026-01-16 | NA | 1. Disable the Export button before saving the new physical count 2. Sort Order - needs to be corrected 3. Product Number to Product # in sort order 4. Space b/w two words in sort order | NIL | Fix the review comment | Meets Expectation
2 | BOH Wave | 2026-01-07 | 2026-01-20 | 26.1 Sprint 3 | Team | 51368 | [Wave]Mosaic BOH - 4.2 Regression - Bidding | Story Completed | 1 | 0 | 0 | 2026-01-07 | 2026-01-07 | NA | NA | NA | NA | NA | NA | NA | NA | Craig | NA | NA | NA | NA | NA | NIL | This regression story is completed in the last sprint
3 | BOH Wave | 2026-01-07 | 2026-01-20 | 26.1 Sprint 3 | Team | 51423 | [Wave]Mosaic BOH - 26.1 Regression - Inventory | Story Completed | 13 | 18.25 | 73 | 2026-01-07 | 2026-01-13 | NA | NA | NA | NA | NA | NA | NA | NA | Craig | NA | NA | NA | NA | NA | NIL | 162+ test cases has been completed
6 | BOH Wave | 2026-01-07 | 2026-01-20 | 26.1 Sprint 3 Stretch | Krupa | 51250 | [WAVE] Mosaic BOH - Add "App Switcher" to feature flag | Story Completed | 2 | 2 | 8 | 2026-01-14 | 2026-01-14 | Yes | Rajiv | Nil | Rajiv | Nil | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/46640 | 2026-01-14 | 2026-01-14 | Rajiv | NA | Charles | 2026-01-16 | NA | NA | NA | App Switcher' is showing in the feature flag | Meets Expectation

## 26.1 Sprint 3 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
26.1 Sprint 3 | 26510 |  | Rajiv | Defect | [WAVE]Mosaic BOH - Regression - Inventory - Receiving - Exception Hyperlink not working on committed or uncommitted receiving trx | Minor | Manual | Internal | Defect Fixed |  |  |  | Existing_Issues | The defect was identified during regression testing but was not detected in the earlier test cycles
26.1 Sprint 3 | 26509 |  | Deepika | Defect | [WAVE]Mosaic BOH -Regression - Inventory - Physical Counts - Tab order on grid is not working correctly | Minor | Manual | Internal | Defect Fixed |  |  |  | Existing_Issues | It was not handled in javascript earlier.Can do prevented by doing proper UI testing
26.1 Sprint 3 | 26512 |  | Rajiv | Defect | [WAVE]Mosaic BOH - Regression - Bidding - Setup - Can't type a decimal in the Discount % search box | Minor | Manual | Internal | Defect Fixed |  |  |  | Existing_Issues | The defect was identified during regression testing but was not detected in the earlier test cycles
26.1 Sprint 3 | 26511 |  | Krupa | Defect | [WAVE]Mosaic BOH - Regression - Inventory - Physical Count Screen - The Show Less/Show More option is hard to see because of font color | Minor | Manual | Internal | Defect Fixed |  |  |  | Existing_Issues | Kalida team updated the UI from Black to white that caused this issue.
26.1 Sprint 3 Stretch | 26489 |  | Rajiv | Defect | [WAVE] Mosaic BOH - Error when importing bid response | Minor | Manual | Internal | Defect Fixed |  |  |  | Existing_Issues | The defect was identified during regression testing but was not detected in the earlier test cycles
26.1 Sprint 3 Stretch | 26544 |  | Krupa | Defect | Mosaic BOH - Regression - Bidding - View Only Security Group permissions do not change what the user can do. | Minor | Manual | Internal | Defect Fixed |  |  |  | Existing_Issues | multiple issues mentioned in the ticket, developer fixed 1 issue only in the code and forgot to clear data from database and other issues were like a new requirement since it was never coded the expected way.

## 4.2 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 | Rajiv | 50627 | [WAVE] Mosaic BOH - Add page-break between days option to Production record report format setup (NK conversion feature gap) | Story Completed | 1 | 0 |  | 2025-11-19 | 2025-11-26 | Yes | Deepika | NIL | Deepika | NIL | [Wave]Mosaic BOH - Warehouse Orders - 'View Report' - show the status with the date | 2025-11-21 | 2025-11-26 | Charles | Nil | Charles | 2025-11-26 | Nil | Nil | Nil | Nil | Meets Expectation
2 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 | Rajiv | 50824 | [Wave]Mosaic BOH - Warehouse Orders - 'View Report' - show the status with the date | Story Completed | 1 | 0 |  | 2025-11-19 | 2025-11-20 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45866 | 2025-11-21 | 2025-11-24 | Charles | Nil | Charles | 2025-11-24 | Nil | Nil | Nil | Nil | Meets Expectation
3 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 | Rajiv | 50775 | [WAVE] - Mosaic BOH- Addition of new filter for Inventory Worksheet Physical counts | Story Completed | 5 | 4.75 | 19 | 2025-12-08 | 2025-12-11 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46170 | 2025-12-11 | 2025-11-22 | Charles | Nil | Charles | 2025-11-22 | Nil | Nil | Nil | AC Updated for display the new filed in the report as well as in search grid in setup page | Meets Expectation
4 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 | Deepika | 48556 | [WAVE] Mosaic BOH - Warehouse - Add Delivery Route to Warehouse Orders report | Story Completed | 1 | 0 |  | 26/11/25 | 2025-01-12 | Yes | Rajiv | NIL | Rajiv | Remove unneccesary namespace | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46002 | 2025-02-12 | 2025-12-04 | Charles | Nil | Charles | 2025-12-04 | Nil | Gap variations in report | Nil | Nil | Meets Expectation
5 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 | Deepika | 47504 | [WAVE]Mosaic BOH - ER - Add Receiving Invoice Total column in the receiving search screen | Story Completed | 1 | 2 | 8 | 2025-12-05 | 2025-12-08 | Yes | Rajiv | NIL | Rajiv | Remove unneccesary spaces | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46106 | 2025-08-12 | 2025-12-09 | Charles | Nil | Charles | 2025-12-09 | Nil | Missing $ symbol and sorting issue | Nil | Nil | Meets Expectation
6 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 | Team | 50799 | [WAVE]Mosaic BOH - 4.2 Regression - Inventory | Story Completed | 13 | 14 | 56 | 2025-12-22
7 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 Stretch | Priya | 51199 | BOH [Wave] - Automation Acceleration-Bidding stories | Story Completed | 13 | 7.5 | 30 | 2025-12-11 | [16 empty] | Completed 4 Test Cases but PR not created, working on Regression in this sprint
8 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 Stretch | Rajiv | 45875 | [WAVE] Mosaic BOH - Bidding Status Change | Story Completed | 5 | 6 | 24 | 2025-12-12 | 2025-12-16 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/46235 | 2025-12-16 | 2025-12-18 | Charles | Nil | Charles | 2025-12-18 | Nil | Nil | Nil | Nil | Meets Expectation
9 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 Stretch | Deepika | 51036 | [Wave]Mosaic BOH - Inventory - Option to Export Inventory Worksheet | Story Being Developed |  | 5.75 | 23 | 2025-12-12 | [17 empty] | Meets Expectation
10 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 | Team | 50800 | [Wave]Mosaic BOH - 4.2 Regression - Products | Story Completed | 13 | 12 | 48 | 2025-12-22
11 | BOH Wave | 2025-12-10 | 2026-01-06 | 4.2 Sprint 2 Stretch | Team | 51368 | [Wave]Mosaic BOH - 4.2 Regression - Bidding | Story Being Developed | 13 | 14.5 | 58 | 2025-12-31

## 4.2 Sprint 2 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
4.2 Sprint 2 Stretch | 26205 |  | Deepika | Defect | [WAVE] Mosaic BOH - Inventory Receiving - Inactive Sites Show up in Search Filters | Minor | Manual | External | Defect Fixed | 2 | 2 | 8 | Existing_Issues | RCA : In Testing it has been missed and Mitigation Plan: Will do a proper unit testing to prevent issues
4.2 Sprint 2 Stretch |  | 47504 | Deepika | Bounce back | [WAVE]Mosaic BOH - ER - Add Receiving Invoice Total column in the receiving search screen | Minor | Manual | Internal | Defect Fixed |  | 0 |  | Development | RCA: Due to code checkin after fixing POV comments and didn't test the scenario . Mitigation Plan: Will do a proper unit testing to prevent issues

## 4.2 Sprint 2 - Praveen
Sprint # | Estimated(sp) | Story/Defect ID | Developer | Issue Type | Description | Status | POV Comments
4.2 Sprint 2 Stretch | 5 | 50938 | Praveen | Story | [WAVE] Mosaic BOH - ER - Add category filters (usage, storage, etc) to the EOM Inventory report | Story Ready for testing | Need to check the alignment in MS Word
4.2 Sprint 2 Stretch | 3 | 26469 | Praveen | Defect | Mosaic BOH - Inventory Inquiry - Hitting the Print Inventory Trans. Report button multiple times produces popup that doesn't go away if Yes is clicked | Defect Peer review | Nil
4.2 Sprint 2 Regression | 3 | 50801 | Praveen | Testing | [BAU]Mosaic BOH - 4.2 Regression - Ordering | Story Completed | NA
4.2 Sprint 2 Regression | 3 | 50795 | Praveen | Testing | [BAU]Mosaic BOH - 4.2 Regression - Menu | Story Completed | NA
4.2 Sprint 2 Regression | 3 | 50796 | Praveen | Testing | [BAU]Mosaic BOH - 4.2 Regression - Reports | Story being developed | NA

## 4.2 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 Sprint 1 | Rajiv | 50318 | (WAVE)Mosaic BOH - ER - Have categories or more specific storage categories be able to be filtered out on the Transfer Pull Sheet report | Story Completed | 3 | 3 | 12 | 2025-11-12 | 2025-11-17 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45699 | 2025-11-13 | 2025-11-17 | Charles | Nil | Charles | 2025-11-17 | Nil | Shenba: Storage category not needed in the report if filter not selectable in UI | Nil | Nil | Meets Expectation
2 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 Sprint 1 | Deepika | 50041 | [WAVE] Mosaic BOH(WH)- Requisition# needs to be shown in the Transfers for Warehouse orders | Story Completed | 2 | 2 | 8 | 2025-11-12 | 2025-11-12 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45668 | 2025-11-12 | 2025-11-12 | Charles | Nil | Charles | 2025-11-12 | Nil | Nil | Nil | Nil | Meets Expectation
3 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 Sprint 1 | Deepika | 50804 | [WAVE] Mosaic BOH - Persist filter options on Receiving screen | Story Completed | 3 | 3 | 12 | 2025-11-13 | 2025-11-14 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45809 | 2025-11-19 | 2025-11-19 | Charles | Nil | Charles | 2025-11-19 | Nil | Nil | Nil | Nil | Meets Expectation
4 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 - Sprint 1 Stretch | Rajiv | 50845 | [Wave]Mosaic BOH - Bidding - Estimated Quantity - Warning message | Story Completed | 3 | 3 | 12 | 2025-11-14 | 2025-11-14 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45721 | 2025-11-14 | 2025-11-14 | Charles | Nil | Charles | 2025-11-14 | Nil | Nil | Nil | Nil | Meets Expectation
5 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 - Sprint 1 Stretch | Rajiv | 50181 | [Wave] Mosaic BOH - Bidding - Expand the Vendor Quotes - Bid Analysis grid for better view | Story Completed | 3 | 1.5 | 6 | 2025-11-18 | 2025-11-18 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45786 | 2025-11-18 | 2025-11-18 | Charles | Nil | Charles | 2025-11-18 | Nil | Nil | Nil | Nil | Meets Expectation
6 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 - Sprint 1 Stretch | Deepika | 49557 | [WAVE] Mosaic BOH - Warehouse - Add Delivery Route field to Transfers screen | Story Completed | 3 | 7 | 28 | 2025-11-17 | 2025-11-24 | Yes | Rajiv | NIL | Rajiv | To remove commented lines | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45896 | 2025-11-21 | 2025-11-25 | Charles | Nil | Charles | 2025-11-25 | Nil | Nil | Nil | Nil | Meets Expectation
9 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 - Sprint 1 Stretch | Rajiv | 48555 | [WAVE] Mosaic BOH - Warehouse - Add Delivery Route field to Warehouse Orders Bulk Approval screen | Story Completed | 3 | 1.5 | 6 | 2025-11-24 | 2025-11-25 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45913 | 2025-11-25 | 2025-11-25 | Charles | Nil | Charles | 2025-11-25 | Nil | Nil | Nil | Nil | Meets Expectation
10 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 - Sprint 1 Stretch | Deepika | 48554 | [WAVE] Mosaic BOH - Warehouse - Add Delivery Route field to Warehouse Orders screen | Story Completed | 3 | 3 | 12 | 2025-11-24 | 2025-11-25 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45896 | 2025-11-24 | 2025-11-25 | Charles | Nil | Charles | 2025-11-25 | Nil | Nil | Nil | Nil | Meets Expectation
11 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 - Sprint 1 Stretch | Rajiv | 40915 | [WAVE]Mosaic BOH - Inventory Inquiry - Item Availability Report | Story Completed | 8 | 6 | 24 | 2025-11-27 | 2025-12-03 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45986 | 2025-12-02 | 2025-12-04 | Charles | Nil | Charles | 2025-12-04 | Nil | Shenba: Alignment issue | Nil | Nil | Meets Expectation
13 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 - Sprint 1 Stretch | Rajiv | 51090 | [Wave]- Mosaic BOH - Bidding - Add Bid Status search filter under bidding response | Story Completed | 3 | 1.5 | 6 | 2025-12-03 | 2025-12-04 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45986 | 2025-12-04 | 2025-12-04 | Charles | Nil | Charles | 2025-12-04 | Nil |  | Nil | Nil | Meets Expectation
14 | BOH Wave | 2025-11-12 | 2025-12-09 | 4.2 - Sprint 1 Stretch | Priya | 50997 | [WAVE] Mosaic BOH- Acceleration-Automation | Story Completed | 13 | 9.5 | 38 | 2025-11-17 | 2025-12-09 | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | NIL | Ready with the skeleton once story completed without bug will create the PR in the Next Sprint

## 4.2 Sprint 1 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
4.2 - Sprint 1 Stretch | 26378 |  | Deepika | Defect | [Wave] Mosaic BOH - Bidding - Responses and Bid Analysis UI issues | Minor | Manual | External | Defect Fixed | 3 | 4 | 16 | Development | It's not updated in the AC
4.2 - Sprint 1 Stretch | 26416 |  |  | Defect | [Wave] Mosaic BOH - Common issue in Filter Search Dropdown | Minor | Manual | External |  |  |  |  | Existing_Issues | It's a existing common issue
4.2 - Sprint 1 Stretch | 50627 |  | Rajiv | Bounceback | When selected it causes a blank page at beginning of report | Minor | Manual | Internal |  |  |  |  | Design | Header option is missed during the devlopment, due to it's in seperate tab with more settings options
4.2 - Sprint 1 Stretch | 50845 |  | Rajiv | Bounceback | Click 'Cancel' button from warning popup, Estimated Qty field will get highlighted with RED color, Now click on the SAVE button 'Required Field are missing information' warning message is showing.EXPECTED is system should not through warning message when click on the SAVE Button | Minor | Manual | Internal |  |  |  |  | Development | Focused only on the popup cancel button, combination of both cancel and save button missed out

## 4.2 Sprint 1 - Praveen
Sprint # | Story/Defect ID | Developer | Issue Type | Description | Status | POV Comments
4.2 Sprint 1 | 26204 | Praveen | Defect | (BAU) Mosaic BOH - AI - Next Navigation is not working in the Physical Count | Completed | Also check the Previous button navigation Performance.
4.2 Sprint 1 | 50824 | Praveen | story | [Wave]Mosaic BOH - Warehouse Orders - 'View Report' - show the status with the date | Completed | Change date format to DD/MM/YYYY
4.2 Sprint 1 | 42586 | Praveen | story | Mosaic BOH - ER - Product List Report - Add a new filter for Notes - 'Has Notes:' | Story Ready For Testing | Has Notes - should have space empty page is seen in the report Has Notes in the report header having spacing - its not aligned Has Notes 'No' and Needs Attention scenario is not implemented

## 4.1 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-10-29 | 2025-11-11 | 4.1 Sprint 3 | Rajiv | 50437 | [WAVE] Mosaic BOH - GenAI - Nutrition Facts Label - Create a Measurement from the Serving Size | Story Completed | 5 | 3 | 12 | 2025-10-27 | 2025-10-29 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45359 | 2025-10-29 | 2025-10-29 | Charles | Nil | Richard | 2025-10-29 | Nil | Nil | Nil |  | Meets Expectation
2 | BOH Wave | 2025-10-29 | 2025-11-11 | 4.1 Sprint 3 | Rajiv | 50452 | [Wave]Mosaic BOH - Gen AI - Image upload functionality should filter to acceptable document types | Story Completed | 3 | 3 | 12 | 2025-10-30 | 2025-10-31 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45400 | 2025-10-31 | 2025-10-31 | Charles | Nil | Richard | 2025-10-31 | Nil | Nil | Nil |  | Meets Expectation
3 | BOH Wave | 2025-10-29 | 2025-11-11 | 4.1 Sprint 3 | Rajiv | 50597 | [Wave] Mosaic BOH - Gen AI - In-App AI Marketing | Story Completed | 5 | 4.5 | 18 | 2025-11-04 | 2025-11-05 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45456 | 2025-11-05 | 2025-11-06 | Charles | Nil | Richard | 2025-11-06 | Nil | Nil | Nil |  | Meets Expectation
4 | BOH Wave | 2025-10-29 | 2025-11-11 | 4.1 Sprint 3 | Rajiv | 50601 | (WAVE)Mosaic BOH - AI - Suggested Change for UI - Production Record Upload - Add Note that only menus with Planned Quantities will show up | Story Completed | 3 | 3 | 12 | 2025-10-30 | 2025-10-31 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45524 | 2025-11-06 | 2025-11-06 | Charles | Nil | Richard | 2025-11-06 | Nil | Nil | Nil |  | Meets Expectation
5 | BOH Wave | 2025-10-29 | 2025-11-11 | 4.1 Sprint 3-Strech | Priya | 50659 | [Wave]Mosaic BOH - Automation | Story Completed | 5 | 5.5 | 22 | 2025-10-30 | 2025-11-11 | Yes | Suresh | NIL | Suresh | NIL | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/45647 | 2025-11-11 | Nil | Charles | Nil | Nil | Nil | Nil | Nil | Nil | 13 Test cases completed
6 | BOH Wave | 2025-10-29 | 2025-11-11 | 4.1 Sprint 3 | Deepika | 50459 | [Wave] Mosaic BOH - AI Should be 'Edit Fields' not individual Security Page items | Story Completed | 2 | 2.25 | 9 | 2025-11-04 | 2025-11-04 | Yes | Rajiv | NIL | Krupa | create common variable for table names instead of hardcoding it. also refactor the code to reuse data table creation for field and page in single function. | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45562 | 2025-11-07 | 2025-11-07 | Charles | Nil | Richard | 2025-11-07 | NIL | NIL | NIL |  | Meets Expectation

## 4.1 Sprint 3 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
4.1 Sprint 3 | 25851 |  | Rajiv | Defect | [Wave] Mosaic BOH - AI Assistant- Scan Handwritten Counts-Not Allowing to Upload the Large Files | Minor | Manual | External | Defect Being Fixed | 2 | 1.5 | 6 | Development | Issue not reproduced
4.1 Sprint 3 | 26204 |  | Deepika | Defect | [Wave] Mosaic BOH-GEN AI-Next Navigation is not working in the Physical Count | Minor | Manual | External | Defect Being Fixed | 2 | 1.5 | 6 | Development | Issue not reproduced for 1st 2 cases
4.1 Sprint 3 | 26170 |  | Deepika | Defect | (WAVE)Mosaic BOH - AI - Production Record Upload is showing the wrong menu date when you click on the AI Production Record Task link | Minor | Manual | External | Defect Fixed | 2 | 0.375 | 1.5 | Development
4.1 Sprint 3 | 26195 |  | Joel | Defect | [Wave] Mosaic BOH Wave-Gen AI-Menu Assistant-Menu Options Buttons are disabled and Menu Plan screen become empty | Minor | Manual | External | Defect Fixed | 2 | 0 |  | Development
4.1 Sprint 3 | 26219 |  | Deepika | Defect | [WAVE] Mosaic BOH - GEN AI- Production Record- Production Record showing wrong values because Duplication of Recipes not Recognized by the AI | Minor | Manual | External | Defect Fixed | 3 | 3.375 | 13.5 | Development
4.1 Sprint 3 | 26131 |  | Deepika | Defect | 26131 - [Wave]Mosaic BOH - Gen AI - Scan Production Records-Warning Message issue | Minor | Manual | External | Defect Fixed | 3 | 0 |  | Development
4.1 - Sprint 3 Stretch | 26262 |  | Deepika | Defect | Mosaic BOH[Wave] - Gen AI - Nutrition Fact Label - Warning Popup for Save button not showing | Minor | Manual | External | Defect Fixed | 3 | 1.5 | 6 | Development
4.1 Sprint 3 |  | 50459 | Deepika | Bounceback | Create a Menu Plan screen is not displaying..Announcement details are showing | Minor | Manual | Internal | Defect Fixed |  |  |  | Development | Bounce Back. Authorization Issue at Menu . And Some districts page s were not shown

## 4.1 Sprint 3 - Praveen
Sprint # | Story/Defect ID | Developer | Issue Type | Description | Status | POV Comments
4.1 Sprint 3 | 26131 | Praveen | Defect | [Wave]Mosaic BOH - Gen AI - Scan Production Records- Warning Message issue | Completed | Need to apply in Physical count page also.
4.1 Sprint 3 | 50601 | Praveen | Story | (WAVE)Mosaic BOH - GenAI - Changes for UI - Production Record Upload & Physical Count Upload | Completed | Changes in Alignment.

## 4.1 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-10-15 | 2025-10-28 | 4.1 Sprint 2 | Deepika | 50274 | [WAVE] Mosaic BOH - GEN AI - Production Record - Move Image to top & Edit grid to botton & freeze column headers & Recipe column | Story Completed | 2 | 0.5 | 2 | 2025-10-09 | 2025-10-10 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45102 | 2025-10-13 | 2025-10-15 | Charles | Nil | Richard | 2025-10-15 | Nil | Image Zoom controls change | Nil |  | Meets Expectation
2 | BOH Wave | 2025-10-15 | 2025-10-28 | 4.1 Sprint 2 | Joel | 50297 | [WAVE] Mosaic BOH - GEN AI - Move prompts to the database | Story Completed | 13 | 5.25 | 21 | 2025-10-09 | 2025-10-27 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45295 | 2025-10-27 | 2025-10-27 | Charles | Nil | Richard | 2025-10-27 | Nil | Nil | Nil |  | Meets Expectation
3 | BOH Wave | 2025-10-15 | 2025-10-28 | 4.1 Sprint 2 | Rajiv | 50272 | [WAVE] Mosaic BOH - GEN AI - Physical Count, Production Record, and Nutrition Facts Label Image viewer | Story Completed | 8 | 4.5 | 18 | 2025-10-15 | 2025-10-23 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45156 | 2025-10-23 | 2025-10-23 | Charles | Nil | Richard | 2025-10-23 | Typo mistake in variable name | Nil | Nil |  | Meets Expectation
4 | BOH Wave | 2025-10-15 | 2025-10-28 | 4.1 Sprint 2 | Deepika | 50284 | [WAVE] Mosaic BOH - GEN AI - Filter Site selectors based on the user's Site Group access | Story Completed | 2 | 2 | 8 | 2025-10-15 | 2025-10-16 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45157 | 2025-10-17 | 2025-10-17 | Charles | Nil | Richard | 2025-10-17 | Nil | Inactive sites are shown remove it and SSO users check |  |  | Meets Expectation
5 | BOH Wave | 2025-10-15 | 2025-10-28 | 4.1 Sprint 2 [Stretch] | Rajiv | 50436 | [WAVE] Mosaic BOH - GenAI - AI Task Status Values (Menu Gen & Nutrition Facts) | Story Completed | 2 | 1.5 | 6 | 2025-10-16 | 2025-10-16 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45158 | 2025-10-16 | 2025-10-16 | Charles | Nil | Richard | 2025-10-16 | Nil | Nil | Nil |  | Meets Expectation
6 | BOH Wave | 2025-10-15 | 2025-10-28 | 4.1 Sprint 2 [Stretch] | Rajiv | 50476 | [Wave] Mosaic BOH - Gen AI - Add Additional Logs in AI | Story Completed | 3 | 1.5 | 6 | 2025-10-17 | 2025-10-17 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45180 | 2025-10-17 | 2025-10-17 | Charles | Nil | Richard | 2025-10-17 | Nil | Nil | Nil |  | Meets Expectation
7 | BOH Wave | 2025-10-15 | 2025-10-28 | 4.1 Sprint 2 [Stretch] | Rajiv | 50437 | [WAVE] Mosaic BOH - GenAI - Nutrition Facts Label - Create a Measurement from the Serving Size | Story Being Developed | 5 | 3 | 12 | 2025-10-27
8 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 [Stretch] | Priya | 50392 | [Wave]Mosaic BOH - Automation | Story Being Developed | 13 | 0
9 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 [Stretch] | Deepika | 50459 | [Wave] Mosaic BOH - AI Should be 'Edit Fields' not individual Security Page items | Story Peer Review | 4 | 6.5 | 26 | 2025-10-16 | 2025-10-23 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45253 | 2025-10-23 | 2025-10-24 | Charles | Nil | Richard | 2025-10-24 | Nil | Nil | Nil |  | Meets Expectation

## 4.1 Sprint 2 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
4.1 Sprint 2 | 25851 |  | Rajiv | Defect | [Wave] Mosaic BOH - AI Assistant- Scan Handwritten Counts-Not Allowing to Upload the Large Files | Minor | Manual | External | Story Ready For Testing | 2 | 0 |  | Design | Issue not reproduced
4.1 Sprint 2 | 26036 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - Physical Count Worksheet UI Issues | Minor | Manual | External | Defect Fixed | 1 | 0 |  | Development | After the AI Release some issues are found,so created a defect.All these issues are existing in the Production Environment
4.1 Sprint 2 | 26040 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - AI Parsed Values P/U and S/U Qty Some values are not fetching in Inventory Physical Count Worksheet | Minor | Manual | External | Defect Fixed | 2 | 1.5 | 6 | Design | After the AI Release some issues are found,so created a defect.All these issues are existing in the Production Environment
4.1 Sprint 2 | 26041 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - Physical Count Updated Results - "Not Matching" is showing wrong value | Minor | Manual | External | Defect Fixed | 2 | 1.5 | 6 | Development | After the AI Release some issues are found,so created a defect.All these issues are existing in the Production Environment
4.1 Sprint 2 | 26054 |  | Deepika | Defect | [WAVE] Mosaic BOH - GEN AI - Production Record Assistant - Results when an unrelated Prod Rec image is uploaded | Minor | Manual | External | Defect Fixed | 2 | 3 | 12 | Requirements | After the AI Release some issues are found,so created a defect.All these issues are existing in the Production Environment
4.1 Sprint 2 | 26070 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - Menu Generation failing due to exceeding the token limit | Minor | Manual | External | Defect Fixed | 2 | 0 |  | Design | This must be tested in the Staging Environment once Latest code is updated in the staging will test this defect.not reproduced in the MPTest env
4.1 Sprint 2 |  | 50272 | Rajiv | Bounceback | The container specifications must remain consistent across the Nutrition Facts, Production Records, and Physical Counts. Additionally, the container should be stable and must not vary from the reference image provided. | Minor | Manual | Internal | Defect Fixed |  |  |  | Development
4.1 Sprint 2 Stretch | 26195 |  | Joel | Defect | [Wave] Mosaic BOH Wave-Gen AI-Menu Assistant-Menu Options Buttons are disabled and Menu Plan screen become empty | Minor | Manual | External | Defect Being Fixed |  |  |  | Design
4.1 Sprint 2 Stretch | 26181 |  | Deepika | Defect | Mosaic BOH - AI - Creating menus - After clicking Generate Menus the program says Generating Menus but doesn't come back | Minor | Manual | External | Defect Peer Review | 2 | 3 | 12 | Development
4.1 Sprint 2 Stretch | 26131 |  | Deepika | Defect | [Wave]Mosaic BOH - Gen AI - Scan Production Records- Warning Message issue | Minor | Manual | External | Defect Being Fixed | 2 | 1.5 | 6 | Development
4.1 Sprint 2 Stretch | 26204 |  | Rajiv | Defect | [Wave] Mosaic BOH-GEN AI-Next Navigation is not working in the Physical Count | Minor | Manual | External | [5 empty] | Issue not reproduced

## 4.1 Sprint 2 - Praveen
Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Status
4.1 Sprint 2 | 26185 | Praveen | Defect | Mosaic BOH - AI - (ON QA MPTest) Upload Production Record page - I am seeing site names in a non-alphabetical order - Using Site Number not Site Name | Completed

## 4.1 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 | Rajiv | 50271 | [WAVE] Mosaic BOH - GEN AI - AI Task Grid Status values | Story Completed | 1 | 1 | 4 | 2025-10-03 | 2025-10-03 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44940 | 2025-10-03 | 2025-10-07 | Charles | Nil | Charles | 2025-10-07 | NIL | NIL | NIL |  | Meets Expectation
2 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 | Rajiv | 50273 | [WAVE] Mosaic BOH - GEN AI - Physical Count - Freeze Column Headers from scrolling | Story Completed | 2 | 2 | 8 | 2025-10-03 | 2025-10-06 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44941 | 2025-10-03 | 2025-10-07 | Charles | Nil | Charles | 2025-10-07 | NIL | NIL | NIL |  | Meets Expectation
3 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 | Deepika | 50274 | [WAVE] Mosaic BOH - GEN AI - Production Record - Move Image to top & Edit grid to botton & freeze column headers & Recipe column | Story Peer Review | 3 | 2 | 8 | 2025-10-09 | 2025-10-10 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45102 | 2025-10-13 | - | Charles | - | - | - | - | Image Zoom controls change, Add Recipe Desc column | - | Gary and Tino suggested a few changes for zooming and fixed those changes | Meets Expectation
4 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 | Deepika | 50277 | [WAVE] Mosaic BOH - GEN AI - Menu Generation Additional Instructions workflow issue | Story Completed | 5 | 1.5 | 6 | 2025-10-03 | 2025-10-03 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44942 | 2025-10-03 | 2025-10-13 | Charles | Nil | Charles | 2025-10-13 | NIL | NIL | NIL |  | Meets Expectation
5 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 [Stretch] | Joel | 50314 | [Wave]Mosaic BOH - Gen AI - Support multiple images for a Production Record Import | Story Completed | 5 | 6.75 | 27 | 2025-10-03 | 2025-10-09 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/45023 | 2025-10-10 | 2025-10-10 | Charles | Nil | Charles | 2025-10-10 | NIL | NIL | NIL |  | Meets Expectation
6 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 [Stretch] | Joel | 50297 | [WAVE] Mosaic BOH - GEN AI - Move prompts to the database | Story Being Developed | 13 | 5.25 | 21 | 2025-10-09
7 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 [Stretch] | Rajiv | 50279 | [WAVE] Mosaic BOH - GEN AI - Sanitize uploaded image parsing | Story Completed | 5 | 3 | 12 | 2025-10-06 | 2025-10-07 | Yes | Deepika | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44983 | 2025-10-07 | 2025-10-07 | Charles | Nil | Charles | 2025-10-07 | NIL | NIL | NIL |  | Meets Expectation
8 | BOH Wave | 2025-10-01 | 2025-10-14 | 4.1 Sprint 1 [Stretch] | priya | 50392 | [Wave]Mosaic BOH - Automation | Story Being Developed | 13 | 2.5 | 11 | 2025-10-07 | [16 empty] | Frequent UI changes so PR not created for the current sprint.Automation test script writting is inprogress

## 4.1 Sprint 1 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
4.1 Sprint 1 | 25851 | 49464 | Rajiv | Defect | [Wave] Mosaic BOH - AI Assistant- Scan Handwritten Counts-Not Allowing to Upload the Large Files | Minor | Manual | Internal | Defect Being Fixed | 2 | 1.5 | 6 | Development | Issue is still existing(no warning message is showing),When trying to attach the same image again
4.1 Sprint 1 | 25925 |  | Rajiv | Defect | Mosaic BOH Wave-AI Assistant-Nutrition Fact Label Issues | Minor | Manual | Internal | Defect Fixed | 2 | 0.75 | 3 | Development
4.1 Sprint 1 | 25902 |  | Deepika | Defect | [Wave] Mosaic BOH - AI Assistant-Menu Plan- Sometimes Date not selecting from the calendar,when click on the Date | Minor | Manual | Internal | Defect Fixed | 2 | 3 | 12 | Development
4.1 Sprint 1 | 26039 |  | Rajiv | Defect | Mosaic BOH Wave-AI Assistant- Nutrition Fact Labels Issues | Minor | Manual | External | Defect Fixed | 2 | 1.5 | 6 | Development
4.1 Sprint 1 | 26036 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - Physical Count Worksheet UI Issues | Minor | Manual | External | Defect Being Fixed | 1 | 0.75 | 3 | Development | Some issues are not fixed
4.1 Sprint 1 | 26040 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - AI Parsed Values P/U and S/U Qty Some values are not fetching in Inventory Physical Count Worksheet | Minor | Manual | External | Defect Being Fixed | 1 | 0.75 | 3 | Development | Some Values are not fetching in the inventory
4.1 Sprint 1 | 26041 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - Physical Count Updated Results - "Not Matching" is showing wrong value | Minor | Manual | External | Defect Being Fixed | 1 | 0.75 | 3 | Development
4.1 Sprint 1 | 26043 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - Physical Count Worksheet QR Code Mobile Flow issue | Minor | Manual | External | Defect Fixed | 2 | 1.5 | 6 | Development
4.1 Sprint 1 | 26054 |  | Deepika | Defect | [WAVE] Mosaic BOH - GEN AI - Production Record Assistant - Results when an unrelated Prod Rec image is uploaded | Minor | Manual | External | Defect Peer Review | 1 | 1.5 | 6 | Development
4.1 - Sprint 1 Stretch | 26070 |  | Rajiv | Defect | [WAVE] Mosaic BOH - GEN AI - Menu Generation failing due to exceeding the token limit | Minor | Manual | External | Story Ready For Testing | 2 | 1.5 | 6 | Development | This must be tested in the Staging Environment once Latest code is updated in the staging will test this defect.not reproduced in the MPTest env
4.1 Sprint 1 | 26115 |  | Deepika | Defect | [Wave] Mosaic BOH - AI Assistant- Production Record Cosmetic and UI issues | Minor | Manual | External | Defect Fixed | 2 | 2.5 | 10 | Development

## 4.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 | Deepika | 49684 | [Wave]Mosaic BOH - Gen AI UI Refresh - AI Entry Point screen 4 columns | Story Completed | 2 | 0.5 | 2 | 2025-08-22 | NIL | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44222 | 2025-08-28 | 2025-08-28 | Charles | Nil | Charles | 2025-08-28 | NIL | NIL | NIL |  | Meets Expectation
2 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 | Rajiv & Joel | 49685 | [WAVE] Gen AI - UI Refresh (Nutrition Facts Labels Edit Screen) | Story Completed | 3 | 1.5 | 6 | 2025-08-26 | 2025-09-02 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44298 | 2025-09-02 | 2025-09-04 | Charles | Nil | Charles | 2025-09-04 | NIL | NIL | NIL |  | Meets Expectation
3 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 | Rajiv | 49820 | [Wave]Mosaic BOH - Gen AI Assistant and Tasks Pages | Story Completed | 3 | 1.5 | 6 | 2025-08-28 | 2025-08-29 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44265 | 2025-08-29 | 2025-09-02 | Charles | Nil | Charles | 2025-09-02 | NIL | NIL | NIL |  | Meets Expectation
4 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 | Charles | 49846 | [Wave]Mosaic BOH - Gen AI - Additional search details to identify a unique physical count record | Story Completed | 5 | 3.5 | 13 | 2025-09-03 | 2025-09-08 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44422 | 2025-09-05 | 2025-09-08 | Charles | Nil | Richard | 2025-09-08 | NIL | NIL | NIL |  | Exceeds Expectation
5 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 | Joel | 47756 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Production Record | Story Completed | 13 | 14.5 | 58 | 2025-09-10 | 2025-09-26 | [5 empty] | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44548
6 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Deepika & Joel | 49657 | Gen AI - Conversation Workflow | Story Completed | 13 | 7.5 | 30 | 2025-09-03 | 2025-09-25 | Yes | Joel | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44503 | 2025-09-11 | 2025-09-25 | Charles | Nil | Charles | 2025-09-25 | NIL | 2 menu day throws error | NIL |  | Meets Expectation
7 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Joel | 49922 | Refactor AI Code to use common API call | Story Completed | 5 | 3.75 | 15 | 2025-09-02 | 2025-09-05 | Yes | Joel | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44380 | 2025-09-05 | 2025-09-05 | Charles | Nil | Charles | 2025-09-05 | NIL | NIL | NIL |  | Meets Expectation
8 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Rajiv | 49960 | [Wave]Mosaic BOH - Nutrition facts label UI changes | Story Completed | 5 | 3 | 12 | 2025-09-09 | 2025-09-18 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44639 | 2025-09-18 | 2025-09-18 | Charles | Nil | Charles | 2025-09-18 | NIL | NIL | NIL |  | Meets Expectation
9 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Rajiv | 49847 | [Wave]Mosaic BOH - Gen AI - UI changes for Physical Count Worksheet Upload | Story Completed | 8 | 7.5 | 30 | 2025-09-12 | 2025-09-23 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44689 | 2025-09-22 | 2025-09-23 | Charles | Nil | Charles | 2025-09-23 | NIL | Radio buttons need gap, Dialoge box needs to added | NIL |  | Meets Expectation
10 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Deepika | 50000 | [Wave]Mosaic BOH - Gen AI - Mobile Workflow Changes | Story Completed | 5 | 2.5 | 10 | 2025-09-15 | 2025-09-16 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44548 | 2025-09-15 | 2025-09-17 | Charles | Nil | Charles | 2025-09-17 | NIL | NIL | NIL |  | Meets Expectation
11 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Deepika | 50004 | [Wave]Mosaic BOH - Gen AI - UI changes for Production Records | Story Completed | 13 | 12 | 48 | 2025-09-17 | 2025-09-25 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44548 | 2025-09-22 | 2025-09-25 | Charles | Nil | Charles | 2025-09-25 | NIL | NIL | NIL | Minor changes TBD v2.o | Meets Expectation
12 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Deepika | 49957 | [Wave]Mosaic BOH - Gen AI - Terms of Service | Story Completed | 3 | 1.5 | 6 | 2025-09-18 | 2025-09-19 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44656 | 2025-09-19 | 2025-09-19 | Charles | Nil | Charles | 2025-09-19 | NIL | NIL | NIL |  | Meets Expectation
13 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Krupa | 50122 | [Wave]Mosaic BOH - Gen AI - Terms of Service (Acceptance workflow) | Story Completed | 5 | 4.25 | 17 | 2025-09-18 | 2025-09-23 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44711 | 2025-09-23 | 2025-09-23 | Charles | Nil | Charles | 2025-09-23 | NIL | NIL | NIL |  | Meets Expectation
14 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Rajiv | 50202 | [WAVE] Mosaic BOH (GEN AI) - Additional Physical Count Assistant UXUI Modifications (23 SEP 2025) | Story Completed | 5 | 3 | 12 | 2025-09-24 | 2025-09-24 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44756 | 2025-09-24 | 2025-09-24 | Charles | Nil | Charles | 2025-09-24 | NIL | NIL | NIL |  | Meets Expectation
15 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Krupa | 50164 | [WAVE] Mosaic BOH - Production Record Assistant - AI Production Record Format & Execute | Story Completed | 5 | 4 | 16 | 2025-09-24 | 2025-09-29 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44849 | 2025-09-29 | 2025-09-29 | Charles | Nil | Charles | 2025-09-29 | NIL | NIL | NIL |  | Meets Expectation
16 | BOH Wave | 2025-09-03 | 2025-09-30 | 4.0 Sprint 3 [Stretch] | Priyadharshini | 49912 | [Wave]Mosaic BOH - Automation for nutrition fact label | Story Completed | 13 | 1.25 | 5 | [7 empty] | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/44394

## 4.0 Sprint 3 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
4.0 Sprint 3 [Stretch] | 25851 | 49464 | Rajiv | Defect | [Wave] Mosaic BOH - AI Assistant- Scan Handwritten Counts-Not Allowing to Upload the Large Files | Minor | Manual | Internal | Defect Being Fixed | 3 | 3 | 12 | Development
4.0 Sprint 3 [Stretch] | 25852 | 49708 | Rajiv | Defect | [WAVE] Mosaic BOH-AI Assistant-Physical Count Worksheet-AI Task-Task Status-Submit Review Button Displayed in AI Task | Minor | Manual | Internal | Defect Fixed | 3 | 3 | 12 | Development
4.0 Sprint 3 [Stretch] | 25925 |  | Rajiv | Defect | Mosaic BOH Wave-AI Assistant-Nutrition Fact Label Issues | Minor | Manual | Internal | Story Ready For Testing | 3 | 1.5 | 6 | Development
4.0 Sprint 3 [Stretch] | 25902 |  | Deepika | Defect | [Wave] Mosaic BOH - AI Assistant-Menu Plan- Sometimes Date not selecting from the calendar,when click on the Date | Minor | Manual | Internal | Defect Ready For Testing | 3 | 3 | 12 | Development
4.0 Sprint 3 [Stretch] | 25935 |  | Rajiv | Defect | [Wave] Mosaic BOH - AI Assistant - AI not recognizing hyphens in Product Number (Inventory Worksheets) | Minor | Manual | External | Defect Fixed | 3 | 1.5 | 6 | Development
4.0 Sprint 3 [Stretch] | 26039 |  | Rajiv | Defect | Mosaic BOH Wave-AI Assistant- Nutrition Fact Labels Issues | Minor | Manual | External | Defect Being Fixed | 3 | 1.5 | 6 | Development

## 4.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 | Rajiv | 49464 | [WAVE]Mosaic BOH - Gen AI - Rework on the Mobile experience for Image/doc upload | Story Completed | 3 | 3.75 | 15 | 2025-08-06 | 2025-08-18 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44169 | 2025-08-26 | 2025-08-26 | Charles | Nil | Andrew | 2025-08-26 | NIl | NIL | NIL |  | Meets Expectation
2 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 | Joel | 49602 | [Wave]Mosaic BOH - Import AI-extracted Physical Count values into products/items | Story Completed | 13 | 8.5 | 34 | 2025-08-11 | 2025-08-26 | Yes | Joel | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44165 | 2025-08-26 | 2025-08-27 | Charles | Nil | Charles | 2025-08-27 | NIl | NIL | NIL |  | Meets Expectation
3 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 | Deepika | 49653 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - User Ratings | Story Completed | 2 | 0.5 | 2 | 2025-08-14 | 2025-08-19 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44022 | 2025-08-19 | 2025-08-22 | Charles | Nil | Charles | 2025-08-22 | NIl | NIL | NIL |  | Meets Expectation
4 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 [Stretch] | Deepika | 49704 | Gen AI - UI Refresh (Import Menu Popup Changes) | Story Completed | 3 | 3 | 12 | 2025-08-20 | 2025-08-28 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44237 | 2025-08-28 | 2025-08-28 | Charles | Nil | Charles | 2025-08-28 | NIl | NIL | NIL
5 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 [Stretch] | Rajiv | 49708 | [Wave]Mosaic BOH - GenAI - Submit physical count | Story Completed | 5 | 6 | 24 | 2025-08-20 | 2025-08-26 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44165 | 2025-08-26 | 2025-08-27 | Charles | Nil | Charles | 2025-08-27 | NIl | NIL | NIL |  | Meets Expectation
6 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 [Stretch] | Deepika | 49684 | [Wave]Mosaic BOH - Gen AI UI Refresh - AI Entry Point screen 4 columns | Story Being Developed | 3 | 6 | 24 | 2025-08-22 | NIL | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44222 | 2025-08-28 | 2025-08-28 | Charles | Nil | Charles | 2025-08-28 | NIL | NIL | NIL | BounceBack
7 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 [Stretch] | Rajiv & Joel | 49685 | [WAVE] Gen AI - UI Refresh (Nutrition Facts Labels Edit Screen) | Story Peer Review | 5 | 4.5 | 18 | 2025-08-26 | 2025-09-02 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44298 | 2025-09-02 | [9 empty] | Meets Expectation
8 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 [Stretch] | Rajiv | 49820 | [Wave]Mosaic BOH - Gen AI Assistant and Tasks Pages | Story Peer Review | 5 | 4.5 | 18 | 2025-08-28 | 2025-08-29 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44265 | 2025-08-29 | [9 empty] | Meets Expectation
9 | BOH Wave | 2025-08-20 | 2025-09-02 | 4.0 Sprint 2 [Stretch] | Priyadharshini | 49746 | [Wave]Mosaic BOH - Automation for AI Task creation Use my Recipe and Get creative | Story Completed | 13 | 3 | 12 | [7 empty] | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/44308 | 2025-09-02

## 4.0 Sprint 2 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
4.0 Sprint 2 | 25606 |  | Deepika | Defect | Mosaic BOH GenAI - Create a Menu Plan-My Recipes-Add Menu- Menu's are importing in the preview screen,clicking on the empty Dates from the Calendar | Minor | Manual | Internal | Defect Fixed | 3 | 1.5 | 6 | Development | fixed

## 4.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 | Deepika | 48436 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - AI Assistant - Add the ability to upload images from the system | Story Completed | 3 | 1.5 | 6 | 2025-06-25 | 2025-07-22 | NIL | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43487 | 2025-07-19 | Nil | Nil | Nil | Nil | Nil | NIl | NIL | Nil |  | Meets Expectation
2 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 | Deepika | 48742 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Improve Quality of Breakfast Menu Suggestions | Story Completed | 1 | 0 |  | 2025-07-23 | 2025-07-27 | NIL | Deepika | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43610 | 2025-07-27 | 2025-07-29 | Charles | NIL | NIL | Nil | NIL | NIL | NIL |  | Meets Expectation
3 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 | Deepika | 48743 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Offer More Recipe Variety | Story Completed | 3 | 3 | 12 | 2025-07-31 | 2025-08-07 | NIL | Deepika | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43845 | 2025-08-07 | 2025-08-11 | Charles | NIL | NIL | 2025-08-11 | NIL | NIL | NIL |  | Meets Expectation
4 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 | Rajiv | 49415 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Model switching - UI | Story Completed | 3 | 0.75 | 3 | 2025-07-31 | 2025-08-04 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43743 | 2025-08-04 | 2025-08-13 | Charles | Nil | Andrew | 2025-08-13 | NIl | NIL | Nil |  | Meets Expectation
5 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 [Stretch] | Rajiv | 49464 | [WAVE]Mosaic BOH - Gen AI - Rework on the Mobile experience for Image/doc upload | Story Being Developed | 13 | 9.5 | 38 | 2025-08-06 | 2025-08-18 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43888 | 2025-08-13 | 2025-08-18 | Charles | Nil | Andrew | 2025-08-18 | NIl | NIL | Logo Need to change |  | Meets Expectation
6 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 [Stretch] | Joel | 49495 | [Wave]Mosaic BOH - Gen AI - Specific AI task types | Story Completed | 8 | 9 | 36 | 2025-07-31 | 2025-08-12 | Yes | Joel | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43833 | 2025-08-07 | 2025-08-12 | Charles | Nil | Andrew | 2025-08-07 | NIl | NIL | Nil |  | Meets Expectation
7 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 [Stretch] | Joel | 49602 | [Wave]Mosaic BOH - Import AI-extracted Physical Count values into products/items | Story Being Developed | 13 | 6 | 24 | 2025-08-11
8 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 [Stretch] | Deepika | 49653 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - User Ratings | Story Peer Review | 5 | 4.5 | 18 | 2025-08-14 | 2025-08-19 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/44022 | 2025-08-19 | [9 empty] | Meets Expectation
9 | BOH Wave | 2025-08-06 | 2025-08-19 | 4.0 Sprint 1 [Stretch] | Priyadharshini | 49307 | [Wave]Mosaic BOH - Automation for Create a Menu Plan | Story Being Developed | 13 | 4.5 | 18

## 4.0 Sprint 1 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
4.0 Sprint 1 [Stretch] | 25727 | 49286 | Rajiv | Defect | [Wave]Mosaic BOH -AI Assistant-Scan HandWritten Count- Tasks | Minor | Manual | Internal | Story Completed | 2 | 1.5 | 6 | Development

## 3.23 Sprint 6-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 | Deepika | 48436 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - AI Assistant - Add the ability to upload images from the system | Story Being Developed | 2 | 2.25 | 9 | 2025-06-25 | 2025-07-22 | NIL | NIL | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43487 | 2025-07-19 | Nil | Nil | Nil | Nil | Nil | NIl | NIL | Nil | Added Bounce Bank and Assign back to the developer | Meets Expectation
2 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 | Joel | 49285 | [Wave]Mosaic BOH - Iterative AI call to parse Inventory Worksheet images | Story Completed | 8 | 8 | 32 | 2025-07-18 | 2025-07-31 | Yes | NIL | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43668 | 2025-07-31 | 2025-08-04 | Charles | Nil | Andrew | 2025-08-04 | NIl | NIL | Nil |  | Meets Expectation
3 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 | Rajiv | 49286 | [Wave]Mosaic BOH - UI for verification and Editing the AI Response of the Inventory Parsing | Story Completed | 8 | 7.5 | 30 | 2025-07-22 | 2025-07-31 | Yes | NIL | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43668 | 2025-07-31 | 2025-08-04 | Charles | Nil | Andrew | 2025-08-04 | NIl | NIL | Nil |  | Meets Expectation
4 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 | Joel | 49005 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Model switching | Story Completed | 8 | 7.5 | 30 | 2025-06-25 | 2025-08-04 | Yes | NIL | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43743 | 2025-08-04 | 2025-08-04 | Charles | Nil | Andrew | 2025-08-04 | NIl | NIL | Nil |  | Meets Expectation
5 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 [Stretch] | Deepika | 48742 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Improve Quality of Breakfast Menu Suggestions | Story Being Tested | 5 | 3.75 | 15 | 2025-07-23 | 2025-07-27 | NIL | NIL | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43610 | 2025-07-27 | 2025-07-29 | Charles | NIL | NIL | 2025-07-29 | NIL | NIL | NIL | Unable to Test because after adding Get Creative or Use My Recipe, Not showing in AI Task List | Meets Expectation
6 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 [Stretch] | Deepika | 48743 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Offer More Recipe Variety | Story Being Developed | 5 | 4.5 | 18 | 2025-07-31
7 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 [Stretch] | Rajiv | 49415 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Model switching - UI | Story Peer Review | 5 | 6.25 | 25 | 2025-07-31 | 2025-08-04 | Yes | NIL | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43743 | 2025-08-04 | 2025-08-04 | Charles | Nil | Andrew | 2025-08-04 | NIl | NIL | Nil |  | Meets Expectation
8 | BOH Wave | 2025-07-23 | 2025-08-05 | 3.23 Sprint 6 [Stretch] | Priyadharshini | 49307 | [Wave]Mosaic BOH - Automation for Create a Menu Plan | Story Being Developed | 13 | 7.5 | 30 | [7 empty] | https://heartlandschools.visualstudio.com/Mosaic/_git/BOH/pullrequest/43715 | 2025-08-01 | 2025-08-04 | Charles | Nil | [5 empty] | Created a Defect 25727

## 3.23 Sprint 6 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Root Cause Category | Comments
3.23 Sprint 6 | 25313 | 47441 | Rajiv | Bounceback | [WAVE]Mosaic BOH -AI Assistant-Menu Popup screen-Minor UI Issues | Minor | Manual | Internal | Story Completed | 2 | 1.5 | 6 | Design | Tool tip flickering issue fixed

## 3.23 Sprint 5-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev start date | Dev end date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 | Deepika | 48449 | Mosaic BOH [WAVE] - Tier Model - Feature/Menus visibility based on the Tier levels | Story Completed | 2 | 3.75 | 15 | 2025-05-29 | 2025-07-14 | Yes | Priya | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42631 | 2025-05-06 | - | Charles | NIL | - | - | - | Nil | Nil |  | Meets Expectation
2 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 | Rajiv | 49065 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels - Attach the image to the created ingredient | Story Completed | 3 | 1.5 | 6 | 2025-07-10 | 2025-07-15 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43386 | 2025-07-15 | 2025-07-15 | Charles | Extension type to constants | Andrew | 2025-07-17 | Nil | Nil | Nil |  | Meets Expectation
3 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 | Rajiv | 48649 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Get Creative - Add the option to print the menu details | Story Completed | 8 | 8.25 | 33 | 2025-07-10 | 2025-07-15 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43386 | 2025-07-15 | 2025-07-15 | Charles | Nil | Andrew | 2025-07-18 | Nil | Nil | Nil | Included physical count worksheet from the kendo UI to vega components | Meets Expectation
4 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 [Stretch] | Rajiv | 49117 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Filter task lists by district | Story Completed | 2 | 1.5 | 6 | 2025-07-09 | 2025-07-09 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43263 | 2025-07-09 | 2025-07-09 | Charles | Nil | Charles | 2025-07-09 | Nil | Nil | Nil |  | Meets Expectation
5 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 [Stretch] | Rajiv | 49118 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Adjust background to full screen | Story Completed | 2 | 1.5 | 6 | 2025-07-09 | 2025-07-09 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43276 | 2025-07-09 | 2025-07-09 | Charles | Nil | Charles | 2025-07-09 | Nil | Nil | Nil |  | Meets Expectation
6 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 [Stretch] | Joel | 47757 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Physical Count Worksheet | Story Completed | 3 | 7.5 | 30 | 2025-07-09 | 2025-07-22 | N/A | N/A | NIL | Joel | NIL | N/A | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | In this sprint, this stretch story is about 1) trying out document parsing with VertexAI for multiple batches of Inventory Worksheet Images, 2) fine tuning the parameters for better accuracy in extraction, and 3) coming up with an optimal AI prompt [22-Jul-25]: Testing Framework is ready. Prompt is complete. Testing with Image Transformation is complete. Prompt has been tuned and ready to be used in code. | Meets Expectation
7 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 [Stretch] | Deepika | 48436 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - AI Assistant - Add the ability to upload images from the system | Story Peer Review | 2 | 7.75 | 31 | 2025-06-25 | 2025-07-22 | NIL | NIL | NIL | Rajiv | Remove unused codes | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43487 | 2025-07-19 | Nil | Nil | Nil | Nil | Nil | NIl | UI changes | Nil |  | Meets Expectation
8 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 [Stretch] | Joel | 49285 | [Wave]Mosaic BOH - Iterative AI call to parse Inventory Worksheet images | Story Being Developed | 5 | 4.5 | 18
9 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 [Stretch] | Rajiv | 49286 | [Wave]Mosaic BOH - UI for verification and Editing the AI Response of the Inventory Parsing | Story Being Developed | 8 | 1.5 | 6
10 | BOH Wave | 2025-07-09 | 2025-07-22 | 3.23 Sprint 5 [Stretch] | Priyadharshini | 49171 | [Wave]Mosaic BOH - Automation for Create a Menu Plan | Story Being Developed | 13 | 3.75 | 15 | [17 empty] | Inprogress in writting the create menu

## 3.23 Sprint 5 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
5 | 25606 |  | Deepika | Defect | AI-Assistant-Create a Menu Plan-My Recipes-Add Menu- Menu's are importing in the preview screen,clicking on the empty Dates from the Calendar | Minor | Manual | Internal | Story Being Developed | Design

## 3.23 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Deepika | 48449 | Mosaic BOH [WAVE] - Tier Model - Feature/Menus visibility based on the Tier levels | Story Being Developed | 2 | 6.5 | 26 | Yes | Priya | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42631 | 2025-05-06 | - | Charles | NIL | - | - | - | Nil | Nil | Story Not Completed. This is due to problems that arrises in saving data through entities and navigation property. And I am facing some scenarios work for some part of code and some or not so working on it. | Meets Expectation
2 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Priyadharshini | 47755 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels | Story Completed | 3 | 0.75 | 3 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42535 | 2025-06-02 | 2025-06-03 | Charles | NIL | Andrew | 2025-06-09 | Nil | Nil | Nil |  | Meets Expectation
3 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Priyadharshini | 48488 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels - Create Ingredient | Story Completed | 2 | 1.25 | 5 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43162 | 2025-07-03 | 2025-07-03 | Charles | NIL | Andrew | 2025-07-03 | Nil | Nil | Nil |  | Meets Expectation
4 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Rajiv | 48568 | [WAVE] Mosaic BOH - AI Get Creative Recipe - Portion size - Update the original response | Story Completed | 2 | 0.25 | 1 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42723 | 2025-06-10 | 2025-06-10 | Charles | NIL | Andrew | 2025-06-10 | Nil | Nil | Nil |  | Meets Expectation
5 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Joel | 48569 | [WAVE] Mosaic BOH - Gen AI - Parent Data Table - Child Data Table | Story Completed | 2 | 0.25 | 1 | Yes | Priya | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42990 | 2025-06-25 | 2025-06-27 | Charles | NIL | Andrew | 2025-06-27 | Nil | Nil | Nil |  | Meets Expectation
6 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Priyadharshini | 48594 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Add Allergens details to the Get Creative Recipes | Story Completed | 3 | 0.5 | 2 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42879 | 2025-06-17 | 2025-06-20 | Charles | NIL | Andrew | 2025-06-20 | Nil | Nil | Nil |  | Meets Expectation
7 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Priyadharshini | 48665 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - AI should handle the Nutrients - measurement conversion | Story Completed | 3 | 0.5 | 2 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42831 | 2025-06-13 | 2025-06-16 | Charles | NIL | Andrew | 2025-06-16 | Nil | Nil | Nil |  | Meets Expectation
8 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Joel | 48695 | Mosaic BOH - Gen AI - Displaying the AI tasks - Update the existing module to the new schema | Story Completed | 3 | 0.5 | 2 | Yes | Priya | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42990 | 2025-06-25 | 2025-06-27 | Charles | Remove commented codes | Andrew | 2025-06-27 | Nil | Nil | Nil |  | Meets Expectation
9 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 | Rajiv | 48913 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Physical Count Worksheet - Code/Uploading images | Story Completed | 8 | 7.5 | 30 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43176 | 2025-07-04 | 2025-07-07 | Charles | Nil | Charles | 2025-07-07 | Nil | Nil | Nil |  | Meets Expectation
10 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 [Stretch] | Rajiv | 49065 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels - Attach the image to the created ingredient | Story Peer Review | 5 | 4.5 | 18 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/43175 | 2025-07-04 | 2025-07-07 | Charles | Nil | Charles | 2025-07-07 | Nil | Nil | Nil | Newly introduced story | Meets Expectation
11 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 [Stretch] | Joel | 47757 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Physical Count Worksheet | Story Being Developed | 13 | 14 | 56 | [15 empty] | In this sprint, this stretch story is about 1) trying out document parsing with VertexAI for multiple batches of Inventory Worksheet Images, 2) fine tuning the parameters for better accuracy in extraction, and 3) coming up with an optimal AI prompt [08-Jul-25]: Testing Framework is ready. Prompt is almost complete. Image Transformation is in progress. Data Extraction Testing is in progress. | Meets Expectation
12 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 [Stretch] | Rajiv | 48649 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Get Creative - Add the option to print the menu details | Story Being Developed | 8 | 0
13 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 [Stretch] | Deepika | 48436 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - AI Assistant - Add the ability to upload images from the system | Story Being Developed | 8 | 4 | 16
14 | BOH Wave | 2025-06-25 | 2025-07-08 | 3.23 Sprint 4 [Stretch] | Priyadharshini | 47615 | [WAVE]Mosaic BOH - Automation | Story Completed | 13 | 15 | 60

## 3.23 Sprint 4 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
3.23 - Sprint 4 | 25498 | 48569 | Rajiv | Defect | [Wave] Mosaic BOH -AI Assistant- Get Creative Recipe | Minor | Manual | Internal | Defect Fixed | Design | fixed the view recipe link issue

## 3.23 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 | Deepika | 48149 | Mosaic BOH [WAVE] - Tier Model | Story Completed | 2 | 0.75 | 3 | Yes | Priya | NIL | Charles | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42398 | 2025-05-27 | 2025-06-20 | Charles | NIL | Andrew | 2025-06-20 | NIL | Nil | Nil | Working as Expected | Meets Expectation
2 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 | Deepika | 48449 | Mosaic BOH [WAVE] - Tier Model - Feature/Menus visibility based on the Tier levels | Story Peer Review | 2 | 2.25 | 9 | Yes | Priya | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42631 | 2025-05-06 | 2025-06-20 | Charles | NIL | Andrew | 2025-06-20 | NIL | Nil | Nil | Backlog - Due to Admin security Group doesnt change on district Tier level | Meets Expectation
4 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 | Priyadharshini | 47755 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels | Story Ready For Testing | 3 | 0 |  | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42535 | 2025-06-02 | 2025-06-03 | Charles | NIL | Andrew | 2025-06-09 | Nil | Nil | Nil | Unable to test, due to JOB failed in MPtest, Andrew is working on it to fix the issue | Meets Expectation
6 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 | Priyadharshini | 48488 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels - Create Ingredient | Story Ready For Testing | 3 | 0 |  | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42535 | 2025-06-02 | 2025-06-03 | Charles | NIL | Andrew | 2025-06-09 | Nil | Nil | Nil | Unable to test, due to JOB failed in MPtest, Andrew is working on it to fix the issue | Meets Expectation
8 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 | Rajiv | 48568 | [WAVE] Mosaic BOH - AI Get Creative Recipe - Portion size - Update the original response | Story Ready For Testing | 3 | 0 |  | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42723 | 2025-06-10 | 2025-06-10 | Charles | NIL | Andrew | 2025-06-10 | Nil | Nil | Nil | Unable to test, due to JOB failed in MPtest, Andrew is working on it to fix the issue | Meets Expectation
7 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 | Joel | 48569 | [WAVE] Mosaic BOH - Gen AI - Parent Data Table - Child Data Table | Story Peer Review | 8 | 6 | 24 | Yes | Joel | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42990 | 2025-06-25 |  | Charles |  | Andrew |  |  | Nil | Nil | Database schema related changes to the story 48695
8 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 [Stretch] | Deepika | 48594 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Add Allergens details to the Get Creative Recipes | Story Ready For Testing | 8 | 7 | 28 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42879 | 2025-06-17 | 2025-06-20 | Charles | NIL | Andrew | 2025-06-20 | Nil | Nil | Nil | Unable to test, due to JOB failed in MPtest, Andrew is working on it to fix the issue | Meets Expectation
9 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 [Stretch] | Rajiv | 48665 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - AI should handle the Nutrients - measurement conversion | Story Ready For Testing | 5 | 3.75 | 15 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42831 | 2025-06-13 | 2025-06-16 | Charles | NIL | Andrew | 2025-06-16 | Nil | Nil | Nil | Unable to test, due to JOB failed in MPtest, Andrew is working on it to fix the issue | Meets Expectation
10 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 [Stretch] | Joel | 48695 | Mosaic BOH - Gen AI - Displaying the AI tasks - Update the existing module to the new schema | Story Peer Review | 8 | 14.75 | 59 | Yes | Rajiv | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42990 | 2025-06-25 |  | Charles | NIL | Andrew
11 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 [Stretch] | Rajiv | 48649 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Get Creative - Add the option to print the menu details | Story Being Developed | 8 | 1.5 | 6
12 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 [Stretch] | Joel | 47757 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Physical Count Worksheet | Story Being Developed | 13 | 4.5 | 18
13 | BOH Wave | 2025-06-11 | 2025-06-24 | 3.23 Sprint 3 [Stretch] | Priyadharshini | 47615 | [WAVE]Mosaic BOH - Automation | Story Being Developed | 13 | 12.25 | 49 | [15 empty] | Raised an defect 25465 and written manual test cases for the current sprint stories. For Automation Framework is changed from MStest to NUnit, couldn't write automation test script and also couldn't test the stories manually because of the status is Failing for all the stories .Andrew is fixing the issue.
Note on AB3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Testing Comment: Found an issue: District Tier 1, features are not visible to the admin users. Bounce back this story

## 3.23 Sprint 3 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
3.23 Sprint 3 [Stretch] | 25313 | 47441 | Rajiv | Bounceback | [WAVE]Mosaic BOH -AI Assistant-Menu Popup screen-Minor UI Issues | Minor | Manual | Internal | Defect Being Fixed | Development | Minor UI issues like alignment, text visibility has been fixed.. Task Status is getting Failed couldn't test the flow.
3.23 Sprint 3 [Stretch] | 25465 | 47755 | Rajiv | Bounceback | [Wave] Mosaic BOH - AI Assistant- Scan Nutrition Labels | Minor | Manual | Internal | Defect Fixed | Design | fixed session timeout, breadcrumbs, toaster
Note on L2: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Unable to test, due to JOB failed in MPtest, Andrew is working on to fix the issue

## 3.23 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 | Deepika | 48149 | Mosaic BOH [WAVE] - Tier Model | Story Ready For Testing | 5 | 3.75 | 15 | Yes | Deepika | NIL | Charles | implement POV comments | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42398 | 2025-05-27 | 2025-06-10 | Charles | NIL | Andrew | - | The SaveSecurityGroupForDistrict.cs file in the business project is setup to instantiate the class and pass in the _DBContext where normally in the Business logic classes they are all partial classes of MenuPlanning and have access to the _DBContext directly. Can we change this page to match our usual formatting? | Nil | Nil | Will wait for hotfix release | Meets Expectation
2 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 | Deepika | 48449 | Mosaic BOH [WAVE] - Tier Model - Feature/Menus visibility based on the Tier levels | Story Peer Review | 3 | 8.75 | 35 | Yes | Deepika | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42631 | 2025-05-06 | - | Charles | Remove the code changes done at getMembershipRoles and remove entries at table level | - | - | - | Nil | Nil | Since more files changes exist. First 48149 changes willbe moved then the current will moved . but willl wait for hotfix release. | Meets Expectation
3 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 | Priya | 48296 | [WAVE] Mosaic BOH - AI Get Creative Prompt Needs More Context | Story Completed | 3 | 2 | 8 | Yes | Priya | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42316 | 2025-05-21 | 2025-05-27 | Charles | NIL | Andrew | 2025-05-27 | Nil | Nil | Nil | Nil | Meets Expectation
4 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 | Rajiv | 47755 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels | Story Ready For Testing | 3 | 2 | 8 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42535 | 2025-06-02 | 2025-06-03 | Charles | NIL | Andrew | 2025-06-09 | Nil | Nil | Nil | Due to Hot fix release, we cannot test this story right now, option is hidden in MPTest | Meets Expectation
5 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 [Stretch] | Joel | 48164 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - RAG Continued | Story Completed | 13 | 3 | 12 | Yes | Joel | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42402 | 2025-05-26 | 2025-05-28 | Charles | NIL | Andrew | 2025-05-28 | Nil | Nil | Nil | [28-May-25] Continuing with AITask Hierarchy | Meets Expectation
6 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 [Stretch] | Rajiv | 48488 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels - Create Ingredient | Story Ready For Testing | 8 | 7.5 | 30 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42535 | 2025-06-02 | 2025-06-03 | Charles | NIL | Andrew | 2025-06-09 | Nil | Nil | Nil | Due to Hot fix release, we cannot test this story right now, option is hidden in MPTest | Meets Expectation
7 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 [Stretch] | Joel | 48569 | [WAVE] Mosaic BOH - Gen AI - Parent Data Table - Child Data Table | Story Being Developed | 13 | 9 | 36 | [15 empty] | DB Schema changes complete. Implementation in progress | Meets Expectation
8 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 [Stretch] | Rajiv | 48568 | [WAVE] Mosaic BOH - AI Get Creative Recipe - Portion size - Update the original response | Story Peer Review | 5 | 4.5 | 18 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42723 | 2025-06-10 | 2025-06-10 | Charles | NIL | Andrew | 2025-06-10 | Nil | Nil | Nil | Development completed, need to test. | Meets Expectation
9 | BOH Wave | 2025-05-28 | 2025-06-10 | 3.23 Sprint 2 [Stretch] | Priyadharshini | 47615 | [WAVE]Mosaic BOH - Automation | Story Being Developed | 13 | 10.5 | 42 | [15 empty] | Written Manual Test Case for the current sprint stories. No Environment to test the stories Due to Hot Fix Branch .Tested and closed the story 48296 in DB.And for Automation Framework is changing from MSTest to NUnit

## 3.23 Sprint 2 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## 3.23 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | BOH Wave | 2025-05-14 | 2025-05-27 | 3.23 Sprint 1 | Joel & Rajiv | 47226 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Add the ability to View Preparation Details for a 'Creative' Recipe in a Popup | Story Completed | 3 | 1 | 1 | Yes | Joel | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/41931 | 2025-04-28 | 2025-05-01 | Andrew | NIL | Andrew | 2025-05-01 | Nil | Add Measurement details | Nil | The functionality is completed and is working fine in the local dev environment. In this implementation, the call to the AI model is executed in the webserver as opposed to the scheduler's environment (The menu assistant implementation executes the call to the AI model in the scheduler's environment where the Google Application Default Credentials have been set up correctly). Since ADC is not yet set up in the webservers, the call to the AI model fails when accessing this functionality. This issue should get resolved once the authentication (ADC) is set up in the webservers. | Meets Expectation
2 | BOH Wave | 2025-05-14 | 2025-05-27 | 3.23 Sprint 1 | Rajiv | 48168 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Ability to add Name to the Image | Story Completed | 3 | 1 | 1 | Yes | Priya | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42030 | 2025-05-05 | 2025-05-16 | Charles | NIL | Andrew | 2025-05-16 | Nil | Nil | Nil | Could't Test because, Scan Nutrition Labels is showing Coming Soon, Not Clickable.Option is blocked in 3.22 release by Andrew, so unable to test in this sprintSame Functionality Available in 47755 | Meets Expectation
3 | BOH Wave | 2025-05-14 | 2025-05-27 | 3.23 Sprint 1 | Deepika | 48149 | Mosaic BOH [WAVE] - Tier Model | Story Peer Review | 5 | 16 | 64 | Yes | Deepika | NIL | Charles | implement POV comments | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42398 | 2025-05-27 | _ | Charles | NIL | _ | _ | NIL | Any change in tier level it should reflect in all the Security Groups | Tier level set in the security group should be specific to the district | Conducted Client POV on Tuesday, after that Gary asked to hold on this story and later discussed with the onshore team and asked to proceed with the story. Added the comments in the story | Meets Expectation
4 | BOH Wave | 2025-05-14 | 2025-05-27 | 3.23 Sprint 1 | Rajiv | 48296 | [WAVE] Mosaic BOH - AI Get Creative Prompt Needs More Context | Story Ready For Testing | 8 | 7 | 27 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42316 | 2025-05-21 | 2025-05-27 | Charles | NIL | Andrew | 2025-05-27 | Nil | Nil | Nil | Devlopment completed, Andrew needs to improve more prompt to get the creative recipe on 23rd May,so had to rework on the prompt | Meets Expectation
5 | BOH Wave | 2025-05-14 | 2025-05-27 | 3.23 Sprint 1 [Stretch] | Joel | 48164 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - RAG Continued | Story Being Developed | 13 | 13 | 53 | Yes | Joel | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42402 | 2025-05-26 | [7 empty] | Nil | Upgrading of Google.Cloud.AIPlatform.V1 from 2.27 to 3.31 has to be in a separate deliverable. | Meets Expectation
6 | BOH Wave | 2025-05-14 | 2025-05-27 | 3.23 Sprint 1 [Stretch] | Joel & Rajiv | 47755 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels | Story Peer Review | 13 | 10 | 40 | Yes | Rajiv | NIL | Joel | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42316 | 2025-05-22 | [6 empty] | Nil | 1.Product/Ingedient Name - you are right, 2.Display the image, though it's not a nutrition label 3. Show the picture and nutrition side by side - Left side image and right side nutrition fact label | Devlopment completed, PR not yet approved | Exceeds Expectation
7 | BOH Wave | 2025-05-14 | 2025-05-27 | 3.23 Sprint 1 [Stretch] | Priyadharshini | 47615 | [WAVE]Mosaic BOH - Automation | Story Being Developed | 13 | 13 | 52 | Yes | Priya | NIL | Suresh | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42410 | 2025-05-27 |  | Charles | [6 empty] | Written Automation test script for AI stories and Created a PR. 2. Written Manual test cases for the story 47902,47226,48168
Note on AB5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: We Don't have test Environment to Test the AI Story, there is a hot fix. QA Environment is against the hot fix branch

## 3.23 Sprint 1 - Defect Trac
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## 3.22 Sprint 6-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 | Priyadharshini | 47441 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Import Suggested Menus | Story Completed | 2 | 2 | 3 | Yes | Priya | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/41755 | 2025-04-11 | 2025-04-25 | Charles | Nil | Andrew | 2025-04-28 | NIL | Nil | NIL
2 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 | Priyadharshini | 47902 | [WAVE] Mosaic BOH - GEN AI (Initiative #37515) - Add a Security Page for 'AI Assistant' (Needed for Beta) | Story Completed | 2 | 2 | 3 | Yes | Priya | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/41852 | 2025-04-23 | 2025-04-23 | Charles | NIL | Andrew | 2025-04-23 | Nil | Nil | Nil
3 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 | Priyadharshini | 47451 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - QR Code Login | Story Completed | 2 | 2 | 13 | Yes | Priya | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/41427 | 2025-03-31 | 2025-04-15 | Charles | NIL | Andrew | 2025-04-15 | Nil | Nil | Nil
4 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 | Joel & Rajiv | 47226 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Add the ability to View Preparation Details for a 'Creative' Recipe in a Popup | Story Ready For Testing | 3 | 1 | 6 | Yes | Joel | NIL | Rajiv | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/41931 | 2025-04-28 | 2025-05-01 | Andrew | NIL | Andrew | 2025-05-01 | Nil | Nil | Nil | Andrew will push their ops team to set up the ADC in the webserver for 47226 to work. Not planned for Beta release
5 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 [Stretch] | Joel & Rajiv | 47755 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Nutrition Facts Labels | Story Being Developed | 8 | 4 | 24 | [15 empty] | Started working on 9th May
6 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 [Stretch] | Rajiv | 48168 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Ability to add Name to the Image | Story Peer Review | 5 | 7 | 30 | Yes | Rajiv | NIL | Deepika | NIL | https://dev.azure.com/heartlandschools/Mosaic/_git/BOH/pullrequest/42030 | 2025-05-05 | [8 empty] | Added Unit tests for all the AI stories, PR not approved yet.
7 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 [Stretch] | Deepika | 48174 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Discovery for Confidence score | Story Completed | 5 | 5 | 42 | Yes | Joel | NIL | Joel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Nil | NIL | POC for image upload
8 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 [Stretch] | Joel | 48175 | [WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Evaluate Google Vision API and Document API for parsing information from images | Story Completed | 5 | 5 | 24 | Yes | Joel | NIL | Joel | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Nil | NIL | POC for Evaluating Google Vision API. Conclusion: Vision API helps only with detecting text in the image. We need to process it further manually or with another AI call. Also, it would need additional resource provisioning. So, its decided to go with Vertex AI that has the multi-modal capability as well as downstream processing intelligence.
9 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 [Stretch] | Deepika | 48149 | Mosaic BOH [WAVE] - Tier Model | Story Being Developed | 5 | 1 | 6 | [15 empty] | Started working on 13th of May
10 | BOH Wave | 2025-04-30 | 2025-05-13 | 3.22 Sprint 6 [Stretch] | Priyadharshini | 47615 | [WAVE]Mosaic BOH - Automation | Story Being Developed | 13 | 13 | 42 | Yes | Priya | NIL | Joel | NIL | https://docs.google.com/document/d/1J7Qy8QJFFmA8YO_pHAZlEOdLtsaKGbtZVhQuiGmysVo/edit?addon_store&pli=1&tab=t.0 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | NIL | NIL | Written Manual Test cases for the AI stories in Azure. Written and Executed the Automation Test Script for AI Stories. Manually Tested and Closed the Stories 47441,47902,47451.
a

## 3.22 Sprint 5 - Defect Tracker
Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## Checklist
Code Review Comments received from Client for 2.5 Sprint |  | S No | Execution Steps | Status
1 | index.tsx /AugustWeb/Features/ContactMaintenance/Components/index.tsx Search doesn't work on the details page. Please remove the search component from the header. | 1 | Code conflict | FALSE
2 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs If the admin doesn't set up any of the new options, then the system rejects every registration. | 2 | Coding Standard | FALSE
3 | PickEnrollmentPlanView.tsx /ParentWeb/ClientApp/src/pages/Registration/PickEnrollmentPlanView.tsx This should be filtered before this ternary statement so the "No enrollment plans" message could be shown if all plans are at capacity and closed. | 3 | Existing Functionality | FALSE
4 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs Could we add a TermEnrollmentPlanId query parameter and query for it directly instead of pulling all the plans for the term? | 4 | Acceptance Criteria coverage | FALSE
|  | 5 | Code execute | FALSE
|  | 6 | Code Performance | FALSE
|  | 7 | Code cleanup | FALSE
|  | 8 | Understandable code comments | FALSE

## Details
Root Cause category
Enhancements
Existing_Issues
Requirements
QA
Design
Documentation
Development
Project_Management
Environment_Related

## Settings
Story Completed
Story Being Tested
Story Ready For Testing
Story Peer Review
Product Owner - Verify
Story Being Developed
Story Approved
Defect Found
Defect Verified
Defect Being Fixed
Defect Peer Review
Product Owner - Verify
Defect Ready For Testing
Defect Being Tested
Defect Fixed
Defect Rejected
Defect Needs More Info
Defect Blocked