## Dashboard
Current Sprint | GGO 8.4.0 Sprint 4 | Current Sprint Sheet | GGO 8.4.0 Sprint 4-Status | Sprint Start Date | 2026-05-14 | Sprint End Date | 2026-05-28 | Application Name | GGO Donor Wave | Users | vishnuram.balaji@relevantz.com;charles.rapheal@relevantz.com | Teams Name(GGO Donor_Web_API) | 19:4ae543cca7444593b1d022935b8fb11d@thread.v2
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story points introduced/removed | Sprint Summary | Accomplishments | Remarks | Retro Points (Internal & External) | Data sanity Audit Status | AuditDate | Planned Leaves | Availed Leaves | Backlog Health
NA | GGO 7.15.0 Sprint 4 | 2024-01-12 | 2024-01-25 | 17 | 15 | 7 |  |  | Completed all the introduced story in the mid of the sprint | Internal: External:
NA | GGO 7.16.0 Sprint 1 | 2024-01-26 | 2024-02-08 | 17 | 14 | 3 |  |  | Actual estimated stories (17pts) got completed from our end with Development and Testing, From Onsite QA (Nate) took time for testing 3 point story because of PRD release and he took half day leave and he got only 4 hrs of time. So from this I would like to say, we should plan to complete the estimated stories 2 days prior, else Nate won't close on the last day of sprint. Introduced Story - 3 point is Development completed, only Testing pending. | Internal: External:
NA | GGO 7.16.0 Sprint 2 | 2024-02-09 | 2024-02-22 | 23 | 22 | 2 |  |  | Completed all the stories on time, but we noticed one minor issue in GGO-13703 Bid-18 report on xls and xlsx formats. the column header occupying some aditional column . It require an report engine code changes.verified some other reports also having the same issue and it's an existing issue.completed introduced story as well | Internal: External:
NA | GGO 7.16.0 Sprint 3 | 2024-02-23 | 2024-03-07 | 27 | 23 | 7 |  |  | GGO-13801-onsite QA(Nathan) raised one bug , we tried to reproduce the issue on rounding but we are not able to do that. We have asked for the steps to reproduce the issue. GGO-13738 -Development has been completed on this story, it require's IT team support to complete the testing. Introduced Story - 7 points (Except GGO-13738 testing) all completed | Internal: External:
NA | GGO 7.16.0 Sprint 4 | 2024-03-08 | 2024-03-21 | 20 | 16 | 5 |  |  | GGO-13796 and GGO-13773 development has been completed.testing requires IT team support to complete,currently salesforce team doing some changes at their side we can't test salesforce api's .Introduced Story - 5 points Develpment has been completed for that. | Internal: External:
NA | GGO 7.17.0 Sprint 1 | 2024-03-22 | 2024-04-04 | 14 | 11 | 3 |  |  | Since we need support from sales force team for testing GGO -13773 ,PAPI-702 saranya supported Mike wall for testing We got info from Doug about the 4 PROD issues in planning meeting 1. Convenience Fee Issue - Not able to reproduce by our team and Onsite QA in DEV, TST & CRT, it is occurring only in PRD, finding a way to check the values, settings in PROD to replicate in lower envrionment 2. Package Tax Issue - Round off to whole number instead of 2 decimal, this is our mistake that has got in to PRD 3 months before, when fixing old code to replace SQL CLR to C# method. 3. Item tax added to Package - This was old issue, but many clients started to raise concern about this issue now, because of our new implementation for Convenience Fee. 4. Payment show error when Actually it is success in PAPI for Few Clients in PRD - Still don't know the reason, analysing the root cause of this issue. | Internal: External:
NA | GGO 7.17.0 Sprint 2 | 2024-04-05 | 2024-04-18 | 19 | 17 | 0 |  |  | This sprint we fixed production issues and macroscope security issues . PAPI-702 carried because card details need to verified with PAPI database, we don't have required permission for that, only onsite QA need to be verified. | Internal: External:
NA | GGO 7.17.0 Sprint 3 | 2024-04-19 | 2024-05-02 | 18 | 11 | 0 |  |  | 2 stories got carried. 1. Due to salesforce team confirmed they can't do any changes. 2. Onshore Testing is pending | Internal: External:
NA | GGO 7.17.0 Sprint 4 | 2024-05-03 | 2024-05-16 | 14 | 4 | 0 |  |  | CRT Regression Testing is still in Progress. 3 stores are blocked and carried because of IT dependencey (Certificate Issue and Permission issue for Report Instance folder in DEV & TST Environments), all the development and testing works are done from our end. | Internal: External:
NA | GGO 7.18.0 Sprint 1 | 2024-05-17 | 2024-05-30 | 15 | 14 | 0 |  |  | Testing blocked due to certificate issue | Internal: External:
NA | GGO 7.18.0 Sprint 2 | 2024-05-31 | 2024-06-13 | 20 | 16 | 0 |  |  |  | Internal: External:
NA | GGO 7.18.0 Sprint 3 | 2024-06-14 | 2024-06-27 | 17 | 15 | 2 |  |  |  | Internal: External:
NA | GGO 7.18.0 Sprint 4 | 2024-06-28 | 2024-07-11 | 20 | 20 | 0 |  |  |  | Internal: External:
NA | GGO 7.19.0 Sprint 1 | 2024-07-12 | 2024-07-25 | 15 | 15 | 5 |  |  | Two stretch stories got carried to next sprint. | Internal: External:
NA | GGO 7.19.0 Sprint 2 | 2024-07-26 | 2024-08-07 | 6 | 6 | 7 |  |  | Two stretch stories got carried to next sprint. | Internal: External:
NA | GGO 7.19.0 Sprint 3 | 2024-08-08 | 2024-08-22 | 16 | 16 | 2 |  |  |  | Internal: External:
NA | GGO 7.19.0 Sprint 4 | 2024-08-23 | 2024-09-05 | 17 | 14 | 2 |  |  | Automation Regression story got carried over as it was new for Offshore QA and there was some learning curve involved. | Internal: External:
NA | GGO 7.20.0 Sprint 1 | 2024-09-05 | 2024-09-19 | 15 | 13 | 2 |  |  | 2 point carry forwarded to next sprint, development and testing completed from our end, but onsite QA didn't complete it. | Internal: External:
NA | GGO 7.20.0 Sprint 2 | 2024-09-20 | 2024-10-03 | 19 | 14 | 2 |  |  | GGO-14067 got carried, We are migrating Bid-03 report to new RDLC framework, there is lot of existing logic present in RPT file. we need to exactly replicate same logic in SQL stored procedure for new RDLC format.understanding .rpt file logic is complication involved Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 | Internal: External:
NA | GGO 7.20.0 Sprint 3 | 2024-10-04 | 2024-10-17 | 17 | 12 |  |  |  | GGO-14067 got carried, Getting Timeout issue for large records,Suporterwise page breakup and some functionlity in spreadsheetlayout is pending Onsite CRC: 0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 | Internal: External:
NA | GGO 7.20.0 Sprint 4 | 2024-10-18 | 2024-10-31 | 16 | 13 |  |  | 1. Login Page Privacy policy update in MFA login page of GGO application 2. Paymen Receipt in new RDLC replacing form display helps users to download receipt as PDF and send email with attachment. | GGO-14067 got carried, Getting Timeout issue for large records Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 | Internal: External:
NA | GGO 7.21.0 Sprint 1 | 2024-11-01 | 2024-11-14 | 18 | 17 | 3/0 |  | 1.Fixed Timeout issue on Bid-03 RDLC report generation. 2.Completed two tickets introduced in the mid of the sprint | Completed all story points on time Onsite CRC: 0 Client CRC: 0 Internal Defects: 2 External Defects: 0 | Internal: External:
NA | GGO 7.21.0 Sprint 2 | 2024-11-15 | 2024-11-25 | 14 | 11 |  |  | 1. Fixed Grid selection issue on Bid-03 RDLC report generation. 2. Fixed Azure Images issue replacing content server url with azure url 3. Investigated GGO to OB Queue flow to replace it with Quartz Job. 4. Allow GGO to validate and support different card card types (JCB, Diners club & Discover Debit) | GGO-13319 story got rolled over due to Azure image access issue and a ticket with Microsoft has been opened​ by IT Onsite CRC: 0 Client CRC: 1 Internal Defects: 0 External Defects: 0 | Internal: External:Rajesh and offshore for continued work on reports Priya, Nathan and Conor for testing a lot of stories and completing them
NA | GGO 7.21.0 Sprint 3 | 2024-11-26 | 2024-12-12 | 14 | 14 | 7/0 |  | 1. Application images moved in Azure , previously we stored the images in DB as bytes 2. 7.20.1 Successfully deployed to PRD 3. EMV Implementation -completed most of the cardreader functionality | GGO-14325 - BID-06 story is a huge effort and cannot be completed in one sprint, hence it was taken as a strech goal Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 | Internal: External:
NA | GGO 7.21.0 Sprint 4 | 2024-12-13 | 2025-01-09 | 24 | 19 | 3/0 |  | 1. Fixed Duplicate Event X Code issue that was a PROD bug for more than 5 years. 2. Good progress on Bid-06 RDLC update and feel confident in completing it next sprint 3. Popup warning for Convenience fee validation implemented 4. Quartz Job implemented for Bid-06 email flow with our own effort and stored the PDF in Azure. | GGO-14427 - BID-06 - Part-3 story is a huge effort, this has got more than 100 scenario's, so it took more time for testing left out with 2 bugs at the end of sprint (development done for the bugs) only testing pending. Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 8 External Defects: 0 | Internal: External: Offshore team made great progress on Bid-06 report
NA | GGO 7.22.0 Sprint 1 | 2025-01-10 | 2025-01-23 | 21 | 17 | 4/0 |  | 1.GGO-14484 Jan 21 Prod Release 2. Successfully completed Bid-06 with new report tool set 3. CRT regression testing completed | GGO-14427 - BID-06 - Part-3 during the CRT testing noticed package item enabled scenario taking too long to complete the report - immediately addressed this Issue. GGO-14483 Completed CRT Release & Regression Testing Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 6 External Defects: 0 Reason for pending: GGO-14422, PAPI-789 - Development and Testing completed from our end, Pending testing from Nate (Onsite QA) because he was focusing more in CRT regression. GGO-14447 - Automation story completed from our end, pending review from Nate GGO-14450 - A.C change one day prior to Sprint end date, so it got carry forward to next sprint
NA | GGO 7.22.0 Sprint 2 | 2025-01-24 | 2025-02-06 | 18 | 11 | 2/0 |  | 1.Enhance RSVP Functionality with key features to enable better data gathering and management of attendee info. 2.Azure Thumbnail image creation issue fix - Add this project as part of GGO Solution and build it via Build pipeline and add it to GGO Artifact | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 1 Testing is pending by Onsite QA and we completed the stories (GGO-14503, GGO-14450) and deployed to TST 2 days prior Sprint end, that's the reason these stories got rolled over to next sprint.
NA | GGO 7.22.0 Sprint 3 | 2025-02-07 | 2025-02-20 | 18 | 8 |  |  | 1.Adjust Admission Functionality and Infrastructure(Graph) update 2.Bid-19 and Bid-15 Report Updates | Peer CRC:0 Onsite CRC: 0 Client CRC: 4 Internal Defects: 4 External Defects: 1 Reason for pending: GGO-14504 - The story was given Onisite QA for testing 3 days before the end of Sprint but Onsite QA logged bug on the last day of Thesprint. It was fixed and deployed before sprint prep, QA didn't get time to complete it. GGO-14070 - Development took a lot of time and got completed only on 1 day before Sprint end, the offshore QA logged a minor bug on the last day of sprint, fixed the bug and PR created for review. (Saranya worked on the RDLC report for the first time and there was a learning curve involved which took time)
NA | GGO 7.22.0 Sprint 4 | 2025-02-21 | 2025-03-06 | 20 | 15 | 2/0 |  | CRT Release & Regression testing for GGO 7.22.0 and PAPI 7.17.0 | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 4 External Defects: 0 Reason for pending: GGO-14510 - Bootstrap update - Development and Testing from Offshore got completed, the automation flow broken with this bootstrap update, so Nate created a automation change ticket under this story and this got carry forwarded to next sprint.
NA | GGO 7.23.0 Sprint 1 | 2025-03-07 | 2025-03-20 | 19 | 19 | 7/0 |  | Continued EMV Implementation and Infrastructure updates Allowed 19 digit card entry in GGAM, GGO and PAPI Cleared some Macroscope issues in PAPI Fixed cache issue in GGO Accomplishments: Addiitionally completed Developemnt for stretch goal stories | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 | Internal Retro 1. Sathiya/ Rajesh and Saranya for providing help to Priya testing the stories 2. Team for completing all the story points
NA | GGO 7.23.0 Sprint 2 | 2025-03-20 | 2025-04-03 | 13 | 19 | 10/0 |  | Completed Duplicate even code story and Invoice import and Invoice Payment Pages story Fixed Quartz Job access issues and Email Queue Issues. Accomplishments: Completing the development and testing for lot of stretch goal stories on the current sprint | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 2 External Defects: 0 Pending Story: 2 Stories has been carried forward 1.GGO-14573 -Hard to reproduce in the lower environements. The offshore developers made several attempts to reproduce the issue, but because it’s related to performance, it took a considerable amount of time to replicate. That’s why it got carried over. 2.PAPI-839(Stretch Goal) -Dependency on Onsite QA to complete it(Offshore QA has already completed testing for this story) | Retro: 1.Rajesh for supporting multiple escalation issues 2.Sathiya/ Rajesh and Saranya for covering such a wide spread of stories 3.Priya for completing the testing for the planned as well as lot of stretch jiras
NA | GGO 7.23.0 Sprint 3 | 2025-04-04 | 2025-04-17 | 22 | 24 | 6/0 |  | Completed Multiple RSVP Imports Accomplishments: Did some Redis changes which was very challenging and OP to GGO import timeouts(which is a esclation ticket) Completing the development for the stretch goal stories on the current sprint | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 Pending Story: 2 stories has been carried forward which includes 1 stretch PAPI-840(8spt)and GGO-14644[Stretch] -Development for this story was completed three days ahead of the sprint deadline. However, a last-minute AC request from the client required code modifications, which were implemented the timeline.The story was left in Peer Review upon completion, per the client's request to hold it and maintain this branch separately from the CERT branch.Offshore QA has completed verification in the lower environment. The story is now pending validation from Onsite QA. | Rajesh and offshore for taking the redis changes which was very challenging
NA | GGO 7.23.0 Sprint 4 | 2025-04-18 | 2025-05-01 | 23 | 27 | 5/0 |  | Accomplishments: Completed CRT testing Completed all planned stories and more Okta 1 Proof of concept Completed more macroscopic stories | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 Pending Story: 2 stories has been carried forward GGO-13722 ->we documented the alternative encryption change, client wanted to add new feature flag based on that need to follow the old and new encryption flow GGO-13723 ->we documented the alternative encryption change, client wanted to add new feature flag based on that need to follow the old and new encryption flow | To the whole team for helping remove all the blockers for testing Rajesh and offshore for helping with the fallback cases Rajesh for assisting with integrating the Okta proof-of-concept
NA | GGO 7.24.0 Sprint 1 | 2025-05-02 | 2025-05-15 | 19 | 16 | 2/0 |  | Accomplishments: Old Amex certification testing Nav Bar Updation Fixed Dashboard generation Issue and Enabled Online Bidding for the same Fixed Export Sales issue Completed more macroscopic stories | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending Story: 2 stories has been carried forward GGO-14628->Hard to reproduce in the lower environements. The offshore developers and QA's made several attempts to reproduce the issue, However, on the last day of the sprint,we found one way to reproduce it. But team need to ensure this after providing the solutions and to check whether this the cause of this issue. Team is still working on it.That’s why it got carried over. GGO-14656->Reskin-V2 is a complete overhaul of the existing Master Page. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness. Its taking more time to complete this story | Rajesh and Sathiyabharathi for working on the Nav bar update. Rajesh for helping with the Escalation issue
NA | GGO 7.24.0 Sprint 2 | 2025-05-16 | 2025-05-29 | 26 | 23 |  |  | Accomplishments: Completed Pendo Implementation Completed Nav Bar Implementation Fixed Amex card disable for select organizations Fixed Sale Grid Export issue | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending Story: 1 story has been carried forward GGO-14628->Hard to reproduce in the lower environements. The offshore developers and QA's made several attempts to reproduce the issue. Team is still working on it.That’s why it was put on hold as it is of low priority | Rajesh and Sathiyabharathi for the Nav bar update. Rajesh and offshore team on the quick implementation of pendo. Mike Horihan gave Kudos for the quick Pendo implementation
NA | GGO 7.24.0 Sprint 3 | 2025-05-29 | 2025-06-12 | 9 | 9 | 3 |  | Accomplishments: Completed Donor Web APIproject setup Completed Integration test Project setup Completed API Authentication for Donor Web API | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending story: 1 Story has been carried forward GDON-7 -> Stretch | New Donor team for completing the project setup, build issue and the publish fix. They are quick in implementing the changes Rajesh for helping multiple offshore teams and get them all set up and going
NA | GGO 7.24.0 Sprint 4 | 2025-06-12 | 2025-06-26 | 10 | 10 | 5 |  | Accomplishments: Completed Account Information for Donor Web API Completed Profile Information for Donor Web API Completed project release and pipeline set up | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending story: 1 Story has been carried forward GDON-11 -> Stretch | Good progress on the Donor API. Donor team dev and QA for completing all the donor team stories
NA | GGO 7.25.0 Sprint 1 | 2025-06-26 | 2025-07-10 | 8 | 8 | donor |  |  | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending story: 2 Story has been carried forward GDON-12 -> Stretch GDON-13 -> Stretch
NA | GGO 7.25.0 Sprint 2 | 2025-07-10 | 2025-07-24 | 16 | 16 | 2 - Removed 5- Strech (2 Completed , 3 Carried forward) |  |  | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Pending story: 1 Story has been carried forward GDON-28 -> Stretch
NA | GGO 7.25.0 Sprint 3 | 2025-07-24 | 2025-08-07 | 13 | 13 | 7 - Strech (2 - Completed, 5- Carried forward |  |  | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Pending story: 2 Story has been carried forward GDON- 32-> Stretch GDON- 33-> Stretch | Offshore Donor team for completing all the planned Donor stories
NA | GGO 7.25.0 Sprint 4 | 2025-08-07 | 2025-08-21 | 15 | 14 | 11 - Strech (11 Carried Forward) |  | Accomplishments : Completed fundraising team member API Completed Edit offline Donation API Completed Get offline Donation API | Peer CRC:0 Onsite CRC: 6 Client CRC: 1 Internal Defects: 1 (Bug Story GDON-38 Supporter image Id not updated while updating the profile image ) External Defects: 0 Suggestion: 0 Pending story: GDON18 - 1 story got carried forward - Devlopment and Testing completed from our end. Pending with Onsite QA GDON- 36-> Stretch got carried forward - Bug raised on last day of the sprint so unable to fix in the same sprint - CRC - 4 2 Stretch Story has been carried forward GDON- 37-> Stretch GDON- 34-> Stretch | Donor Team for Api and Offshore team for the reskin stuff both are very complicated
NA | GGO 8.0.0 Sprint 1 | 2025-08-21 | 2025-09-04 | 15 | 17 (11 Stretch) | 2-Strech (Completed - 2) |  | Accomplishments : Completed Profile Image Upload API Completed Logging mechinsm in Azure Completed Contacts Upload API Completed FundraisngTeamCoordinator API Completed Get Fundraising Info Completed Organization and events API | Peer CRC:0 Onsite CRC: 0 Client CRC: 1 (Suggestion) Internal Defects: 0 External Defects: 0 Suggestion: 0 Pending story: | Offshore Donor team for completing all planned and more stories
NA | GGO 8.0.0 Sprint 2 | 2025-09-04 | 2025-09-18 | 15 | 15 | 0 |  | Accomplishments: Completed save , get and update credit card API Completed the exception handling and logging in App Insights Completed the send email after update the profile API | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 | Rajesh and Donor offshore team for the Donor API progress+1
NA | GGO 8.0.0 Sprint 3 | 2025-09-18 | 2025-10-02 | 7 | 9 | 2 Story points Introduced - (Completed - 2) |  | Accomplishments: Completed Update ApAdmin settings Completed Get ApAdmin settings Completed Update GetOrganizationEvents | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 | Offshore team booth GGO and GDONOR for completing all the planned stories and more
NA | GGO 8.0.0 Sprint 4 | 2025-10-02 | 2025-10-16 | 7 | 9 | 2 Story points Introduced |  | Accomplishments: Completed GetOrCreateAccountProfileInfo Completed Update the Profile APIs to use Account ID instead of Profile ID Completed GetAddressInfo / UpdateAddressInfo Completed Donor API - Add Address Type for profile Completed Handle Image in Update Profile | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 | GGO and GDON team for meeting the goal +1 | GGO 8.1.0 Sprint 1
NA | GGO 8.1.0 Sprint 1 | 2025-10-16 | 2025-10-30 | 7 | 9 | 2 Story points Introduced |  | Accomplishments: Completed Add Company Name for the Business address type Completed Create OnlineBiddingActivity to accept multiple Credit Card and transfer default ClientXid to respective Org clientxid Completed Validate User Profile - Check Bidder/Supporter has got GGAM User Profile or not using "BidderKey" | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 | GGO and GDON team for meeting the goal +1
NA | GGO 8.1.0 Sprint 2 | 2025-10-30 | 2025-11-13 | 7 | 7 | 2 Story points Introduced |  | Accomplishments: 1. Completed Update Account Creation to include Online Bidding Activity creation if user login via OB 2. Completed Donor API - Update GGO Card reference in SaveCreditCard 3. Completed Donor API - Update ggo with multiple credit cards from Joinme card reference | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0
NA | GGO 8.1.0 Sprint 3 | 2025-11-13 | 2025-11-27 | 8 | 8 | 2 Story points Introduced |  | Accomplishments: 1. Completed Donor API - Update the Response code for all the donor API based 2. Completed Donor API - Delete Credit Card in donor app should also delete from GGO if no charge is made 3. Completed Donor API - Validate Card data when creating Online Bidding Activity (either card data or CardXid's) | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories | Offshore for completing the overall Sprint goal
NA | GGO 8.1.0 Sprint 4 | 2025-11-27 | 2025-12-11 | 7 | 7 | 2 Story points Introduced |  | Accomplishments: 1. Completed - Create Donor Admin Page 2. Completed - Donor API - Validate Online Bidding activity and Card address before creating OB activity 3. Developement started - Donor API - Create Online Bidding Activity without Credit Card Info* | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories | Rajesh for keeping up with everything and making sure the team is successful
NA | GGO 8.2.0 Sprint 1 | 2025-12-11 | 2026-01-08 | 10 | 10 | 2 Story points Introduced |  | Accomplishments: 1. Completed - Donor API - Create Online Bidding Activity without Credit Card Info* 2. Completed - Disabled the Online Bidding activity creation process and hide the display of OB activities in GGAM based on flag 3. Dev Completed - Donor API - Include AddressTypeId and CompanyName in the GetProfileCreditCards API * | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories | Charles and Vishnu for completing the GGAM online activity story
NA | GGO 8.2.0 Sprint 3 | 2026-01-08 | 2026-01-22 | 9 | 11 | 2 Story points Introduced |  | Accomplishments: 1. Testing Completed - Donor API - Include AddressTypeId and CompanyName in the GetProfileCreditCards API * 2. Completed - Create GG API to send Checkout information to Donor Platform 3. Completed - Donor API - Add Donation Sale for Donor 4. Completed - GetOrCreateAccount API throws error when sending resettokenutc as null* | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed more than the planned stories | Kudos to GGO and GDON team for completing all the committed work
NA | GGO 8.2.0 Sprint 4 | 2026-01-22 | 2026-02-05 | 10 | 10 | 2 Story points Introduced |  | Accomplishments: 1. Testing completed for all the assigned stories Completed - GDON - 71 - Create GGO Org Settings Completed - GDON - 82 - Donor Checkout - Charge CC, create Payment record/association 2. Have taken one story and started Development GDON - 72 - Create GGO Donor Project Settings | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories | Offshore GGO and GDON team for completing all the stories |  |  | 0 | 2
NA | GGO 8.3.0 Sprint 1 | 2026-02-05 | 2026-02-19 | 11 | 11 | 1 Story point introduced (Found an Issue) |  | Accomplisments: 1. Completed DEV & Testing - GDON - 72 - Create GGO Donor Project Settings 2. Completed DEV & Testing - GDON - 83 - Donor API - Update GetCheckout API to include Convenience Fee and Sale Payment Association flag 3. Completed DEV & Testing in Dev env., - GDON - 80 - Donor Checkout - Generate Receipt | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories Found an issue and fixed that in the current sprint itself Testing in TST env., alone is pending for the ticket GDON-80 | GDON team for completing the planned stories |  |  | 0 | 0
NA | GGO 8.3.0 Sprint 2 | 2026-02-19 | 2026-03-05 | 10 | 9 | 3 |  | Accomplisments: 1. Completed DEV & Testing in DEV env., - GDON - 84 - Donor Settings - Project Name to cascade to Ob Settings 2. Completed DEV & Testing in Dev & TST env.,- GDON - 86 - Display self checkout badge in GGO Manage Sales & Payments 3. Completed DEV & Testing in Dev & TST env., - GDON - 87 - Donor API - Update Charge Card using selected card in Donor App | Peer CRC:0 Onsite CRC:0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 1 Story carried forward for Testing in TST env.,. Development is completed | Offshore team for achieving the sprint goal |  |  | 1 | 1.5
NA | GGO 8.3.0 Sprint 3 | 2026-03-05 | 2026-03-19 | 12 | 12 | 3 |  | Accomplishments: 1. Completed DEV & TST Testing - GDON-84 - Donor Settings - Project Name to cascade to Ob Settings 2. Completed DEV & TST Testing - GDON - 81 - Donor Checkout - Generate email and send receipt 3. Completed DEV & TST Testing - GDON - 88 - Donor API - Common credit card model for both OnlineBidding and CreditCard APIs 4. Completed DEV & TST Testing - GDON - 89 - Donor API - Add payment source "DonorEngage" to differentiate the payment from Donor App 5. Started development on GDON - 90 - Donor API - Cleanup donor API's | Peer CRC:0 Onsite CRC:1 1.Is this file needed? It looks like config values come from the appsettings.json file Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 | Whole GGo offshore team for achieving the goal |  |  | 0 | 1.5
NA | GGO 8.3.0 Sprint 4 | 2026-03-19 | 2026-04-02 | 12 | 12 | 2 |  | Accomplishments: 1. Successfully implemented the Email Template and its subject of the mail once the check out is done 2. Implemented the Donor API's - Cleanup process 3. In Generate Payment Receipt API - successfully implemented the ReportGuId in the Params for generating the token 4. Implemented Email Address update in Update Profile API | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories and taken one bug ticket and started development | Offshore team for completing all the planned taken stories in the sprint |  |  | 1 | 1
NA | GGO 8.4.0 Sprint 1 | 2026-04-02 | 2026-04-16 | 11 | 11 | 3 |  | Accomplishments: 1. Successfully implemented the Text Template and SMS request once the check out is done 2. Implemented a new Donor API's - CheckBidderHouseHold for both Individual and Household supporters 3. Successfully implemented the GenerateCheckOut API with the below mentioned formats i. with AccountId, ProjectKey & BidderKey ii. with AccountId & ProjectKey iii. with AccountId & BidderKey 4. Implemented the GetCreditCards API which was always returning as 2 - while updating the AddressTypeId | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories and taken one ticket from the backlog and it is being developed | 1. Whole GGO and GDON offshore team for completing all the tickets 2. Conor, Priya and Charles for completing the testing for all the stories |  |  | 0 | 1
NA | GGO 8.4.0 Sprint 2 | 2026-04-16 | 2026-04-30 | 11 | 11 | - |  | Accomplishments: 1. Successfully implemented three new API's - Event details API, Tickets API and GetHouseHoldMembers 2. Successfully implemented the ProjectKey in the GetCheckout Result 3. Implemented the CreateAccount API without giving password in the JSON | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories | Offshore GGO and GDON for completing all the stories |  |  | 0 | 1
NA | GGO 8.4.0 Sprint 3 | 2026-04-30 | 2026-05-14 | 9 | 9 | - |  | Accomplishments: 1. Successfully implemented a new API - GetBidderHouseHoldAndTableInfo 2. Successfully implemented Self Checkin Settings under Donor Project settings and another new API GetCheckinInfo 3. Implemented the Online Bidding sceanrio without creating duplicate supporter in the list 4. Successfully implemented another new API - UpdateCheckinStatus | Peer CRC:0 Onsite CRC: Client CRC: 0 Internal Defects: 0 External Defects: 0 Suggestion: 0 Completed all the planned stories | GGO & GDON offshore team for achieving the sprint goal |  |  | 1 | 1.5
NA | GGO 8.4.0 Sprint 4 | 2026-05-14 | 2026-05-28 | 11 | [8 empty] | 0 | 0

## Unplanned Leaves
Total Unplanned Leaves | 0
Resource Name
Sprint Name | Charles Infant Rabi | Vishnu | Remarks
GGO 8.3.0 Sprint 1 (05-Feb-26 to 19-Feb-26) | 0 | 0
GGO 8.3.0 Sprint 2 (19-Feb-26 to 05-Mar-26) | 0.5 1 | 0 | Charles: Due to Fever (26/02) 2nd half Planned leave (05/03)
GGO 8.3.0 Sprint 3 (05-Mar-26 to 19-Mar-26) | 0.5 | 1 | Charles: Personal work (10/03) - 2nd half Vishnu: Personal reasons
GGO 8.3.0 Sprint 4 (19-Mar-26 to 02-Apr-26) | 1 | 0 | Charles: Planned leave (30/03)
GGO 8.4.0 Sprint 1 (02-Apr-26 to 16-Apr-26) | 0 | 1 | Vishnu: Personal work (16/04/2026)
GGO 8.4.0 Sprint 2 (16-Apr-26 to 30-Apr-26) | 0 | 0
GGO 8.4.0 Sprint 3 (30-Apr-26 to 14-May-26) | 1 | 0.5 | Charles: Family Function (04/05/2026) Vishnu: Personal work (13/05/2026)
Total | 4 | 2.5

## GGO 8.4.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Comments
1 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Vishnu | GDON-104 | Donor API - Update GetBidderHouseHoldAndTableInfo to include the Member details for OB | Being Developed | 3 |  |  | 2026-05-15
2 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Vishnu | GDON-105 | Donor API - Include Image Url in the GetCheckIn Details API | Refinement | 2
3 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Vishnu | GDON-106 | GGO - Indicate when a Supporter has a donor profile | Refinement | 3
4 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Vishnu | GDON-107 | GGO - Indicate when a Donor Self Checks In | Refinement | 3

## GGO 8.4.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Comments
1 | GGO Donor Wave | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Vishnu | GDON-100 | Donor API - Update table info in GetHousehold API call | Completed | 2 | 2 | 16.5 | 2026-05-04 | 2026-05-04 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9529 | 2026-05-04 | 2026-05-04 | Rajesh |  | Mccarty, Joseph | 2026-05-04 |  |  |  | Testing in TST env., completed on 05/05/2026 at 19:00 pm Working fine as expected / Updated the QA notes and comments in JIRA
2 | GGO Donor Wave | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Vishnu | GDON-101 | Donor Check In Settings | Completed | 3 | 3 | 34.5 | 2026-05-05 | 2026-05-07 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9546 | 2026-05-07 | 2026-05-11 | Rajesh |  | Mccarty, Joseph | 2026-05-11 |  |  |  | Dev completed on 07/05/2026 Testing in TST env., completed on 12/05/2026 at 16:30 pm Working fine as expected / Updated the QA notes and comments in JIRA
3 | GGO Donor Wave | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Vishnu | GDON-102 | Donor API - Update Online Bidding Activity API and cleanup | Completed | 2 | 2 | 30 | 2026-05-08 | 2026-05-11 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9553 | 2026-05-11 | 2026-05-12 | Rajesh |  | Mccarty, Joseph | 2026-05-12 |  |  |  | Testing in DEV env., - Completed on 12/05/2026 and 13/05/2026 It is working fine as expected. Updated the QA notes and comments in JIRA Unable to test in TST env., as the TST DONOR URL is not accessible
4 | GGO Donor Wave | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Vishnu | GDON-103 | Donor API - Checkin Supporter API | Completed | 2 | 2 | 34 | 2026-05-12 | 2026-05-13 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9559 | 2026-05-13 | 2026-05-13 | Rajesh |  | Mccarty, Joseph | 2026-05-13 |  |  |  | Testing in TST env., completed on 14/05/2026 at 14:00 pm Working fine as expected Will update the QA notes and comments shortly

## GGO 8.4.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Comments
1 | GGO Donor Wave | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Vishnu | GDON-94 | Create an Event Details API | Completed | 3 | 3 | 46.5 | 2026-04-21 | 2026-04-24 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9507 | 2026-04-24 | 2026-04-27 | Rajesh |  | Mccarty, Joseph | 2026-04-27 |  |  |  | Working fine as expected in DEV env., Testing completed on 27/04/2026 20:30PM Testing in TST env., completed on 28/04/2026 17:00PM and it is working fine as expected
2 | GGO Donor Wave | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Vishnu | GDON-95 | Create a Tickets API | Being Developed | 5 |  | 45.5 | 2026-04-27 | 2026-04-29 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9515 | 2026-04-29 | 2026-04-29 | Rajesh |  | Mccarty, Joseph | 2026-04-29 |  |  |  | Testing in TST env., Inprogress
3 | GGO Donor Wave | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Vishnu | GDON-98 | Donor API - Get Household members | Completed | 2 | 2 | 39.5 | 2026-04-15 | 2026-04-21 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9490 | 2026-04-21 | 2026-04-22 | Rajesh |  | Mccarty, Joseph | 2026-04-22 |  |  |  | Working fine as expected in DEV env., Testing completed on 22/04/2026 17:00PM Testing completed in TST env., 23/04/2026 18:30 PM and it is working fine as expected.
4 | GGO Donor Wave | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Rajesh | GDON-99 | Donor API - Update create account password to a random string instead of getting from Donor App | Completed | 1 | 1 | 9.5 | 2026-04-16 | 2026-04-17 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9486 | 2026-04-17 | 2026-04-17 | Rajesh |  | Mccarty, Joseph | 2026-04-17 |  |  |  | Working fine as expected in TST env., - Testing completed on 20/04/2026 17:30 PM

## GGO 8.4.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Comments
1 | GGO Donor Wave | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Rajesh | GDON-78 | Create Text Template | Completed | 3 | 3 | 26.5 | 2026-04-10 | 2026-04-14 | Done | Charles |  | Vishnu |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9466 | 2026-04-14 | 2026-04-14 | Rajesh |  | Horihan, Mike | 2026-04-14 |  |  |  | Working fine as expected in both DEV & TST env.,
2 | GGO Donor Wave | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Vishnu | GDON-93 | Update Online Bidding to Recognize HH vs Individual Bidder keys | Completed | 3 | 3 | 32.5 | 2026-04-09 | 2026-04-13 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9462 | 2026-04-13 | 2026-04-13 | Rajesh |  | Mccarty, Joseph | 2026-04-13 |  |  |  | In DEV Testing Result is coming as True for both the Bidderkeys - Individual and Household 1. True should be come only for Household Bidderkey 2. And It should be False for Individual Bidderkey Fixed the above issue and completed testing in TST env., it is working fine as expected now
3 | GGO Donor Wave | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Vishnu | GDON-96 | Donor API - Get Account and Project Info By BidderKey | Completed | 3 | 3 | 26 | 2026-04-06 | 2026-04-08 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9449 | 2026-04-08 | 2026-04-09 | Rajesh |  | Horihan, Mike | 2026-04-10 |  |  |  | Working fine as expected in both DEV & TST env.,
4 | GGO Donor Wave | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | VIshnu | GDON-97 | Donor API - AddressTypeId is always returning as Type 2 in GetCreditCards API | Completed | 2 | 2 | 35.5 | 2026-04-01 | 2026-04-06 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9438 | 2026-04-06 | 2026-04-09 | Rajesh |  | Horihan, Mike | 2026-04-09 | Is this the way normally determine first name and last name? |  |  | Working fine as expected in both DEV & TST env.,
5 | GGO Donor Wave | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 [Stretch] | VIshnu | GDON-98 | Donor API - Get Household members | Being Developed | 3 |  | 9 | 2026-04-15 | [16 empty] | Being Developed

## GGO 8.3.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Tester Comments | Developer comments | Remarks
1 | GGO Donor Wave | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Vishnu | GDON-90 | Donor API - Cleanup donor API's | Completed | 3 | 3 | 36 | 2026-03-20 | 2026-03-23 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9397 | 2026-03-23 | 2026-03-23 | Rajesh |  | Mccarty, Joseph | 2026-03-23 |  |  |  | Testing activity in TST env., - Completed on 24/03/2026 20:00PM | Dev started on 17/03/2026 Dev Completed on 23/03/2026 | Collection of APIs - Based on different scenarios - TST env.,
2 | GGO Donor Wave | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Vishnu | GDON-91 | Validate Generate receipt requester identity | Completed | 2 | 2 | 38.5 | 2026-03-27 | 2026-03-31 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9418 | 2026-03-31 | 2026-04-01 | Rajesh |  | Mccarty, Joseph | 2026-04-01 |  |  |  | Testing activity in DEV env., - Completed on 01/04/2026 13:00PM Testing activity in TSTenv., completed on 02/04/2026 - 16:00PM | Dev started on 27/03/2026 Dev Completed on 31/03/2026
3 | GGO Donor Wave | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Vishnu | GDON-92 | Donor API - Update profile and supporter email address based on change email request from donor app | Completed | 2 | 2 | 43 | 2026-03-24 | 2026-03-26 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9407 | 2026-03-26 | 2026-03-26 | Rajesh |  | Mccarty, Joseph | 2026-03-26 |  |  |  | Testing activity in DEV env., completed on 26/03/2026 - 20:00PM Testing activity in TSTenv., completed on 27/03/2026 - 21:00PM | Dev started on 24/03/2026 Dev Completed on 26/03/2026
4 | GGO Donor Wave | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Rajesh | GDON-74 | Create Email Template | Completed | 5 | 5 | 22.5 | 2026-03-20 | 2026-03-27 | Done | Charles |  | Vishnu |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9418 | 2026-03-31 | 2026-03-31 | Rajesh |  | Mccarty, Joseph | 2026-03-31 |  |  |  | Testing activity in DEV env., completed on 30/03/2026 - 20:00PM Testing activity in TSTenv., completed on 01/04/2026 - 16:00PM | Dev started on 20/03/2026 Dev Completed on 27/03/2026
4 | GGO Donor Wave | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 [Stretch] | Vishnu | GDON-97 | Donor API - AddressTypeId is always returning as Type 2 in GetCreditCards API | Being Developed | 2 | 1 | 10.5 | 2026-04-01

## GGO 8.3.0 Sprint 4-Defect
S.No | Sprint | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Found By | RCA Comment | Tester Comments | Developer comments | Remarks
[6 empty] | NO Defects | [9 empty] | Dev Started on 05-Feb-2026

## GGO 8.3.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Tester Comments | Developer comments | Remarks
1 | GGO Donor Wave | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Vishnu | GDON-84 | Donor Settings - Project Name to cascade to Ob Settings | Completed | 1 | 1 | 6 |  |  | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9341 | 2026-03-04 |  | Rajesh | [6 empty] | Testing activity in DEV env., completed on 27/02/2026 / 18:30PM Testing activity in TST env., completed on 06/03/2026 - 15:00PM | Dev completed on 04/03/2026
2 | GGO Donor Wave | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Rajesh/Vishnu | GDON-81 | Donor Checkout - Generate email and send receipt | Completed | 5 | 5 | 17.5 | 2026-03-06 | 2026-03-13 | Done | Charles |  | Vishnu |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9377 | 2026-03-16 | 2026-03-16 | Vishnu |  | Mccarty, Joseph | 2026-03-16 |  |  |  | Testing activity in DEV env., completed on 16/03/2026 - 12:00PM Testing activity in TSTenv., completed on 17/03/2026 - 17:00PM | Dev started on 06/03/2026 Dev completed on 16/03/2026
3 | GGO Donor Wave | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Vishnu | GDON-88 | Donor API - Common credit card model for both OnlineBidding and CreditCard APIs | Completed | 3 | 3 | 40.5 | 2026-03-06 | 2026-03-10 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9353 | 2026-03-10 | 2026-03-11 | Rajesh |  | Mccarty, Joseph | 2026-03-11 |  |  |  | Testing activity in DEV env., completed on 10/03/2026 - 21:00PM Testing activity in TST env.,Completed on 11/03/2026 - 20:00PM | Dev Started on 06/03/2026 Dev Completed on 10/03/2026
4 | GGO Donor Wave | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Vishnu | GDON-89 | Donor API - Add payment source "DonorEngage" to differentiate the payment from Donor App | Completed | 3 | 3 | 32 | 2026-03-11 | 2026-03-12 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9370 | 2026-03-12 | 2026-03-13 | Rajesh |  | Horihan, Mike | 2026-03-13 |  |  |  | Testing activity in DEV env., completed on 13/03/2026 - 15:00PM Testing activity in TST env.,Completed on 16/03/2026 - 16:00PM | Dev started on 11/03/2026 Dev Completed on 12/03/2026
4 | GGO Donor Wave | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 [Stretch] | Vishnu | GDON-90 | Donor API - Cleanup donor API's | Being Developed | 3 |  | 44.5 | 2026-03-17 | [17 empty] | Dev started on 17/03/2026 Dev Completed on | Collection of APIs - Scenarios based - TST env.,

## GGO 8.3.0 Sprint 3-Defect
S.No | Sprint | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Found By | RCA Comment | Tester Comments | Developer comments | Remarks
[6 empty] | NO Defects | [9 empty] | Dev Started on 05-Feb-2026

## GGO 8.3.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Tester Comments | Developer comments | Remarks
1 | GGO Donor Wave | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Rajesh | GDON-80 | Donor Checkout - Generate Receipt | Completed | 1 | 1 | 19.5 | 2026-02-12 | 2026-02-19 | Done | Charles |  | Vishnu |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9304 | 2026-02-19 |  | Vishnu |  | Horihan, Mike | 2026-02-19 | Question: Is this file needed? It looks like config values come from the appsettings.json file. |  |  | Testing activity completed in DEV env., on 19/02/2026 / 12:30PM Testing activity completed in TST env., on 20/02/2026 / 15:00PM | Dev completed on 19/02/2026
2 | GGO Donor Wave | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Vishnu | GDON-84 | Donor Settings - Project Name to cascade to Ob Settings | Verify | 3 | 2 | 31.5 | 2026-03-02 | 2026-03-04 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9341 | 2026-03-04 |  | Rajesh | [6 empty] | Testing activity completed in DEV env., on 27/02/2026 / 18:30PM Testing activity in TST env., completed on 06/03/2026 - 15:00PM | Dev completed on 04/03/2026
3 | GGO Donor Wave | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Vishnu | GDON-86 | Display self checkout badge in GGO Manage Sales & Payments | Completed | 3 | 3 | 4.5 | 2026-02-25 | 2026-02-27 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9324 | 2026-02-26 |  | Rajesh |  | Horihan, Mike | 2026-03-02 |  |  |  | Testing activity completed in DEV env., on 27/02/2026 / 18:30PM Testing activity completed in TST env., on 03/03/2026 / 14:30PM | Dev completed on 02/03/2026
4 | GGO Donor Wave | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Vishnu | GDON-87 | Donor API - Update Charge Card using selected card in Donor App | Completed | 3 | 3 | 35.5 | 2026-02-20 | 2026-02-24 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9316 | 2026-02-24 |  | Rajesh |  | Mccarty, Joseph | 2026-02-24 |  |  |  | Testing activity in TST env., completed on 25/02/2026 / 14:30 PM | Dev completed on 24/02/2026 | Found one issue while CreateCardPayment API - (Payment is not getting paid - Error type-1 - (Not found))
5 | GGO Donor Wave | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 [Stretch] | Vishnu | GDON-88 | Donor API - Common credit card model for both OnlineBidding and CreditCard APIs* | Being Developed | 3 |  | 6.5 | 2026-03-05

## GGO 8.3.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Tester Comments | Developer comments | Remarks
1 | GGO Donor Wave | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Vishnu | GDON-72 | Create GGO Donor Project Settings | Completed | 5 | 5 | x | 2026-02-05 | 2026-02-12 | Done | Charles | View Donor Project Settings is enabled for all the Projects | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9273 | 2026-02-12 | 2026-02-12 | Rajesh |  | Mccarty, Joseph | 2026-02-12 |  |  |  | Testing activity in TST env., Completed on 16/02/2026 / 17:00 | Dev completed on 12-Feb-2026 | Issue found is fixed and verified again in TST env., - (View Donor Project Settings is enabled for all the Projects)
2 | GGO Donor Wave | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Rajesh | GDON-80 | Donor Checkout - Generate Receipt | Peer Review | 3 |  | 36.5 | 2026-02-12 | 2026-02-18 | Done | Charles |  | Rajesh |  |  | 2026-02-19 |  | Rajesh |  | Mccarty, Joseph |  |  |  |  | Testing activity in DEV env., Completed on 19/02/2026 / 12:30 | Dev completed on 18-Feb-2026
3 | GGO Donor Wave | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Vishnu | GDON-83 | Donor API - Update GetCheckout API to include Convenience Fee and Sale Payment Association flag | Completed | 3 | 3 | 32.5 | 2026-02-13 | 2026-02-17 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9296 | 2026-02-17 | 2026-02-17 | Rajesh |  | Mccarty, Joseph | 2026-02-17 |  |  |  | Testing activity in TST env., Completed on 18/02/2026 / 15:00 | Dev completed on 17-Feb-2026
4 | GGO Donor Wave | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Vishnu | GDON-85 | View Donor Project Settings is enabled for all the Projects | Completed | 1 | 1 |  | 2026-02-13 | 2026-02-13 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9285 | 2026-02-13 | 2026-02-13 | Rajesh |  | Mccarty, Joseph | 2026-02-13 |  |  |  | Testing activity in TST env., Completed on 16/02/2026 / 17:00 | Dev completed on 13-Feb-2026

## GGO 8.3.0 Sprint 1-Defect
S.No | Sprint | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Found By | RCA Comment | Tester Comments | Developer comments | Remarks
[6 empty] | No Defects | [9 empty] | Dev Started on 05-Feb-2026

## GGO 8.2.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Tester Comments | Developer comments | Remarks
1 | GGO Donor Wave | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Vishnu | GDON-71 | Create GGO Org Settings | Completed | 5 | 5 | 53.5 | 2026-01-23 | 2026-01-29 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9227 | 2026-01-28 | 2026-01-30 | Rajesh |  | Mccarty, Joseph | 2026-01-30 |  |  |  | Testing activity has been completed in the DEV env., Done on 01/30/2026 - 17:30PM Testing activity has been completed in the TST env., Done on 02/02/2026 - 16:00PM | Dev completed on 29-Jan-2026 | Found few existing issues - when we go back from organization level
2 | GGO Donor Wave | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Vishnu | GDON-82 | Donor Checkout - Charge CC, create Payment record/association | Completed | 5 | 5 |  | 2026-01-30 | 2026-02-03 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9253 | 2026-02-03 | 2026-02-03 | Rajesh |  | Mccarty, Joseph | 2026-02-03 |  |  |  | Testing activity has been completed in the TST env., Done on 02/05/2026 - 17:00PM | Dev completed on 03-Feb-2026
3 | GGO Donor Wave | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 [Stretch] | Vishnu | GDON-72 | Create GGO Donor Project Settings | Being Developed | 5 |  | 12.5 | 2026-02-05 | [17 empty] | Dev Started on 05-Feb-2026

## GGO 8.2.0 Sprint 4-Defect
S.No | Sprint | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Found By | RCA Comment | Tester Comments | Developer comments | Remarks
[6 empty] | No Defects | [9 empty] | Dev Started on 05-Feb-2026

## GGO 8.2.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Tester Comments | Developer comments | Remarks
1 | GGO Donor Wave | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Vishnu | GDON-68 | Donor API - Include AddressTypeId and CompanyName in the GetProfileCreditCards API * | Completed | 1 | 1 | 12.5 | 2026-01-05 | 2026-01-08 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9155 | 2026-01-08 | 2026-01-08 | Rajesh |  | Mccarty, Joseph | 2026-01-08 |  |  |  | Testing activity has been completed in the TST env., Done on 01/09/2026 - 19:00PM
2 | GGO Donor Wave | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Vishnu | GDON-73 | Create GG API to send Checkout information to Donor Platform | Completed | 5 | 5 | 53.5 | 2026-01-09 | 2026-01-16 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9178 | 2026-01-16 | 2026-01-19 | Rajesh |  | Mccarty, Joseph | 2026-01-19 |  |  |  | Testing activity has been completed in the TST env., Done on 01/19/2026 - 21:00PM
3 | GGO Donor Wave | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Vishnu | GDON-75 | Donor API - Add Donation Sale for Donor | Completed | 3 | 3 | 33.5 | 2026-01-16 | 2026-01-20 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9188 | 2026-01-20 | 2026-01-20 | Rajesh |  | Mccarty, Joseph | 2026-01-20 |  |  |  | Testing activity has been completed in the DEV env., Done on 01/20/2026 - 19:20PM Testing activity has been completed in the TST env., Done on 01/21/2026 - 15:00PM
4 | GGO Donor Wave | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Vishnu | GDON-79 | GetOrCreateAccount API throws error when sending resettokenutc as null* | Completed | 2 | 2 | 19 | 2026-01-21 | 2026-01-22 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9200 | 2026-01-20 | 2026-01-21 | Rajesh |  | Mccarty, Joseph | 2026-01-21 |  |  |  | Testing activity has been completed in the TST env., Done on 01/22/2026 - 18:00PM

## GGO 8.2.0 Sprint 3-Defect
S.No | Sprint | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Found By | RCA Comment | Tester Comments | Developer comments | Remarks
[6 empty] | No Defects | [9 empty] | Dev Started on 05-Feb-2026

## GGO 8.2.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO - POV Comments | Client PO - POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Vishnu | GDON-66 | Donor API - Create Online Bidding Activity without Credit Card Info* | Completed | 5 | 5 | 66.5 | 2025-12-05 | 2025-12-18 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9104 | 2025-12-15 | 2025-12-23 | Rajesh |  | Mccarty, Joseph | 2025-12-23 |  |  |  | Testing activity has been completed in the DEV env., Done on 12/18/2025 - 17:00PM Testing activity has been completed in the TST env., Done on 12/24/2025 - 16:00PM | Coordinated with UI team and verified the following scenarios oba add profile update profile create account organization mapping process save credit card get credit card
2 | GGO Donor Wave | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Vishnu | GDON-67 | Disabled the Online Bidding activity creation process and hide the display of OB activities in GGAM based on flag | Completed | 5 | 5 | 105 | 2025-12-19 | 2026-01-02 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9133 | 2025-12-24 | 2026-01-07 | Rajesh |  | Mccarty, Joseph | 2026-01-07 |  |  |  | Testing activity has been completed in the DEV env., Done on 01/05/2026 - 18:00PM Testing activity has been completed in the TST env., Done on 01/07/2026 - 20:00PM
3 | GGO Donor Wave | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Vishnu | GDON-68 | Donor API - Include AddressTypeId and CompanyName in the GetProfileCreditCards API * | Verify | 2 | 2 | 19.5 | 2026-01-05 | 2026-01-08 |  | Charles |  | Rajesh

## GGO 8.2.0 Sprint 1-Defect
S.No | Sprint | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Found By | RCA Comment | Tester Comments | Developer comments | Remarks
[6 empty] | No Defects | [9 empty] | Dev Started on 05-Feb-2026

## GGO 8.1.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Vishnu | GDON-63 | Create Donor Admin Page | Completed | 5 | 5 |  | 2025-11-27 | 2025-12-03 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9066 | 2025-12-03 | 2025-12-03 | Rajesh |  | Mccarty, Joseph | 2025-12-03 |  |  |  | Testing activity has been completed in the TST env., Done on 12/04/2025 - 12:30PM
2 | GGO Donor Wave | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Vishnu | GDON-65 | Donor API - Validate Online Bidding activity and Card address before creating OB activity | Completed | 2 | 2 |  | 2025-12-03 | 2025-12-04 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9076 | 2025-12-04 | 2025-12-05 | Rajesh |  | Mccarty, Joseph | 2025-12-05 |  |  |  | Testing activity has been completed in the TST env., Done on 12/09/2025 - 13:00PM
3 | GGO Donor Wave | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Vishnu | GDON-66 | Donor API - Create Online Bidding Activity without Credit Card Info* | Being Developed | 3 |  |  | 2025-12-05 |  |  | Charles |  | Rajesh

## GGO 8.1.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Vishnu | GDON-59 | Donor API - Update the Response code for all the donor API based | Completed | 3 |  |  | 2025-11-21 | 2025-11-25 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9048 | 2025-11-25 | 2025-11-25 | Rajesh |  | Mccarty, Joseph | 2025-11-25 |  |  |  | Testing activity has been completed in the TST env., Done on 11/26/2025 - 17:30PM
2 | GGO Donor Wave | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Vishnu | GDON-61 | Donor API - Delete Credit Card in donor app should also delete from GGO if no charge is made | Completed | 3 |  |  | 2025-11-13 | 2025-11-18 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9018 | 2025-11-17 | 2025-11-17 | Rajesh |  | Mccarty, Joseph | 2025-11-17 |  |  |  | Testing activity has been completed in the TST env., Done on 11/18/2025 - 14:00PM
3 | GGO Donor Wave | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Vishnu | GDON-62 | Donor API - Validate Card data when creating Online Bidding Activity (either card data or CardXid's) | Completed | 2 |  |  | 2025-11-19 | 2025-11-21 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9037 | 2025-11-20 | 2025-11-21 | Rajesh |  | Mccarty, Joseph | 2025-11-21 |  |  |  | Testing activity has been completed in the TST env., Done on 11/25/2025 - 13:30PM

## GGO 8.1.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 [Strech] | Vishnu | GDON-56 | Update Account Creation to include Online Bidding Activity creation if user login via OB | Completed | 2 |  |  | 2025-10-29 | 2025-11-03 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8976 | 2025-11-03 | 2025-11-04 | Rajesh |  | Mccarty, Joseph | 2025-11-04 |  |  |  | Testing activity done in the DEV env., Completed on 11/04/2025 - 20:00PM Testing activity done in the TST env., Completed on 11/05/2025 - 13:00PM
2 | GGO Donor Wave | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Vishnu | GDON-57 | Donor API - Update GGO Card reference in SaveCreditCard | Ready for Testing | 2 |  |  | 2025-11-10 | 2025-11-12 |  | Charles |  | Rajesh |  |  | 2025-11-11 | 2025-11-12 | Rajesh |  | Mccarty, Joseph | 2025-11-12 |  |  |  | Testing activity done in the DEV env., Completed on 11/12/2025 - 23:00PM Testing activity done in the TST env., Completed on 11/13/2025 - 12:00PM
3 | GGO Donor Wave | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Vishnu | GDON-58 | Donor API - Update ggo with multiple credit cards from Joinme card reference | Completed | 3 |  |  | 2025-11-04 | 2025-11-10 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8993 | 2025-11-07 | 2025-11-10 | Rajesh |  | Mccarty, Joseph | 2025-11-10 |  |  |  | Testing activity done in the DEV env., Completed on 11/10/2025 - 19:00PM Testing activity done in the TST env., Completed on 11/11/2025 - 14:00PM

## GGO 8.1.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID / Defect ID | Description | Status | Estimated (sp) | Actual (sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-10-17 | 2025-10-30 | GGO 8.1.0 Sprint 1 | Vishnu | GDON-53 | Donor API - Add Company Name for the Business address type | Completed | 2 |  |  | 2025-10-17 | 2025-10-21 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8936 | 2025-10-21 | 2025-10-21 | Rajesh |  | Mccarty, Joseph | 2025-10-21 |  |  |  | Testing activity done in the TST env., Completed on 10/22/2025 - 17:00PM
2 | GGO Donor Wave | 2025-10-17 | 2025-10-30 | GGO 8.1.0 Sprint 1 | Vishnu | GDON-54 | Validate User Profile - Check Bidder/Supporter has got GGAM User Profile or not using "BidderKey" | Completed | 2 |  |  | 2025-10-22 | 2025-10-23 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8948 | 2025-10-23 | 2025-10-24 | Rajesh |  | Mccarty, Joseph | 2025-10-24 |  |  |  | Testing activity done in the DEV env., Completed on 10/24/2025 - 15:00PM Testing activity done in the TST env., Completed on 10/27/2025 - 12:00PM
3 | GGO Donor Wave | 2025-10-17 | 2025-10-30 | GGO 8.1.0 Sprint 1 | Vishnu | GDON-55 | Create OnlineBiddingActivity to accept multiple Credit Card and transfer default ClientXid to respective Org clientxid | Completed | 3 |  |  | 2025-10-24 | 2025-10-28 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8964 | 2025-10-28 | 2025-10-28 | Rajesh |  | Mccarty, Joseph | 2025-10-24 |  |  |  | Testing activity done in the DEV env., Completed on 10/29/2025 - 13:00PM Testing activity done in the TST env., Completed on 10/29/2025 - 21:00PM | Before CreateOnlineBiddingActivity >>>UPDATE JOINME.CardReference SET ClientXid ='Z10022' where CardXid ='PY179090'<<< “This is because, apart from the clientXId "S99999" no id's are working for credit card verification, so we are going with this approach”
4 | GGO Donor Wave | 2025-10-17 | 2025-10-30 | GGO 8.1.0 Sprint 1 [Strech] | Vishnu | GDON-56 | Update Account Creation to include Online Bidding Activity creation if user login via OB | Being Developed | 3 |  |  | 2025-10-29

## GGO 8.0.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 | Vishnu | GDON-50 | Donor API - Add Address Type for profile | Completed | 2 |  |  | 2025-10-03 | 2025-10-06 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8901 | 2025-10-06 | 2025-10-06 | Rajesh |  | Horihan, Mike | 2025-10-06 |  |  |  | Testing activity done in the DEV. & TST env., Completed on 10/07/2025 - 13:00PM
2 | GGO Donor Wave | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 | Vishnu | GDON-51 | Donor API - Modify Create Account API to validate email and return profile Info | Completed | 5 |  |  | 2025-10-08 | 2025-10-13 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8914 | 2025-10-09 | 2025-10-13 | Rajesh |  | Mccarty, Joseph | 2025-10-13 |  |  |  | Testing activity done on both DEV & TST env., Completed on 10/13/2025 - 18:30pm - DEV env., Completed on 10/14/2025 - 12:30pm - TST env.,
3 | GGO Donor Wave | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 [Strech] | Vishnu | GDON-52 | Handle Image in Update Profile | Completed | 2 |  |  | 2025-10-14 | 2025-10-15 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8921 | 2025-10-15 | 2025-10-15 | Rajesh |  | Mccarty, Joseph | 2025-10-15 |  |  |  | Testing activity done on both DEV & TST env., Completed on 10/16/2025 - 11:30am - DEV env., Completed on 10/16/2025 - 14:30pm - TST env.,

## GGO 8.0.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-09-19 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Vishnu | GDON-46 | Donor API - Update ApAdmin settings for Donor App | Completed | 5 |  |  | 2025-09-22 | 2025-09-26 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8866 | 2025-09-25 | 2025-09-26 | Rajesh |  | Mccarty, Joseph | 2025-09-26 |  |  |  | Testing activity done in the DEV. env., Completed on 09/26/2025 - 14:00PM
2 | GGO Donor Wave | 2025-09-19 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Vishnu | GDON-47 | Donor API - Get ApAdmin settings for Donor App | Completed | 2 |  |  | 2025-09-19 | 2025-09-24 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8866 | 2025-09-23 | 2025-09-26 | Rajesh |  | Mccarty, Joseph | 2025-09-26 |  |  |  | Testing activity done in the DEV. env., Completed on 09/24/2025 - 17:30PM
3 | GGO Donor Wave | 2025-09-19 | 2025-10-02 | GGO 8.0.0 Sprint 3 [Strech] | Vishnu | GDON-48 | Donor API - Update GetOrganizationEvents API | Completed | 2 |  |  | 2025-09-29 | 2025-09-30 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8887 | 2025-09-30 | 2025-10-01 | Rajesh |  | Mccarty, Joseph | 2025-10-01 |  |  |  | Testing activity done in the DEV. env., Completed on 10/03/2025 - 10:30AM

## GGO 8.0.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Kannan | GDON-31 | Donor API - GetCreditCards for Account/Profile | Completed | 3 |  |  | 2025-09-10 | 2025-09-15 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8840 | 2025-09-15 | 2025-09-16 | Rajesh |  | Wall-Iannarelli, Michael | 2025-09-16 |  |  |  | Testing activity done in the DEV. env., Completed on 09/16/2025 - 14:00PM
2 | GGO Donor Wave | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Kannan | GDON-43 | Donor API - Save Credit Card for Account/Profile | Completed | 3 |  |  | 2025-09-05 | 2025-09-10 |  | Charles |  | Rajesh |  | Pull Request 8836: [GDON-43] Save Credit Card for Profile | 2025-09-11 | 2025-09-11 | Rajesh |  | Wall-Iannarelli, Michael | 2025-09-11 |  |  |  | Testing activity done in the DEV & TST env., Completed on 09/11/2025 - 15:00PM - DEV env., Completed on 09/15/2025 - 12:00PM - TST env.,
3 | GGO Donor Wave | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Vishnu | GDON-44 | Donor API - UpdateCreditCard for Account/Profile (Update only Primary and Billing address) | Completed | 3 |  |  | 2025-09-12 | 2025-09-17 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8842 | 2025-09-17 | 2025-09-17 | Rajesh |  | Wall-Iannarelli, Michael | 2025-09-17 |  |  |  | Testing activity done in the DEV & TST env., Completed on 09/17/2025 - 17:00PM - DEV env., Completed on 09/18/2025 - 10:30PM - TST env.,
4 | GGO Donor Wave | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Ubaithullah | GDON-40 | Donor API - Exception Handling | Completed | 3 |  |  | 2025-09-05 | 2025-09-12 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8819 | 2025-09-12 | 2025-09-12 | Rajesh |  | Wall-Iannarelli, Michael | 2025-09-12 |  |  |  | Testing activity done in the DEV. env., Completed on 09/13/2025 - 18:20PM
| GGO Donor Wave | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Vishnu | GDON-41 | Donor API - Create Profile - Send Email to user after creating profile | Completed | 3 |  |  | 2025-09-04 | 2025-09-17 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8824 (edited) | 2025-09-10 | 2025-09-17 | Rajesh |  | Wall-Iannarelli, Michael | 2025-09-17 |  |  |  | Testing activity done on both DEV & TST env., Completed on 09/17/2025 - 18:30pm - DEV env., Completed on 09/18/2025 - 11:30am - TST env.,

## GGO 8.0.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Ubaithullah, Kannan | GDON-36 | Donor API - Update Profile Image | Completed | 2 |  |  | 2025-08-13 | 2025-08-19 |  | Charles |  | Prabhu | Provided some internal comments, which has been fixed mentioned in previous Sprint GGO 7.25.0 Sprint 4 | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8753 | 2025-08-19 | 2025-08-20 | Prabhu |  | Wall-Iannarelli, Michael | 2025-08-20 |  |  |  | Testing activity done in the TST. env., Completed on 012:00 PM 09/04/2025 | Found a defect and reported to the respective developer, also created a defect in JIRA - GDON-38. Also verified the updated comments mentioned on this ticket. Ascending and Descending scenarios for uploading a image. Also verified the image upload before OnlineBiddingActivity is created
2 | GGO Donor Wave | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Ubaithullah, Kannan | GDON-37 | API Request - Pull Organization and Events at the same time | Completed | 2 |  |  | 2025-08-20 | 2025-08-26 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8757 | 2025-08-26 | 2025-08-07 | Rajesh |  | Wall-Iannarelli, Michael | 2025-08-27 |  |  |  | Testing activity done in the Dev. env., Completed on 09:00 PM 08/28/2025
3 | GGO Donor Wave | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Vishnu , Ubaithullah | GDON-34 | Donor API - GetCoordinatorProgress | Completed | 2 |  |  | 2025-08-20 |  |  | Rajesh |  | Rajesh | I did analysis on the Team Coordinator display in GGAM and PROD data, noticed that functionality is disabled for all projects by default and also I verified the PROD data, that the last allowed Team Coordinator data is 2018. So I don’t want to spent much time on this Team Coordinator logic if it is not used in PROD. We will work on implementing new API’s once Donor team decide to add a new UI for this Teams Coordinator functionality in future. I would suggest to reduce the points to 2 and close this ticket.
4 | GGO Donor Wave | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Kannan | GDON-35 | Donor API - ContactsUpload | Completed | 3 |  |  | 2025-08-20 | 2025-08-26 |  | Charles |  | Rajesh | Client Suggestion 1: Do we have this regEx in a common place so that we aren't duplicating code? | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8771 | 2025-08-26 | 2025-08-30 | Rajesh |  | Wall-Iannarelli, Michael | 2025-08-30 |  |  |  | Testing activity done in the Dev. env., Completed on 03:00 PM 08/28/2025
5 | GGO Donor Wave | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Vishnu | GDON-18 | Donor API - Get/Create/Update/Delete FundraisingTeamCoordinator | Completed | 1 |  |  | 2025-08-11 | 2025-08-19 |  | Charles |  | Prabhu | Provided some internal comments, which has been fixed mentioned in previous Sprint GGO 7.25.0 Sprint 4 | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8754 | 2025-08-19 | 2025-08-20 | Prabhu |  | Wall-Iannarelli, Michael | 2025-08-20 |  |  |  | Tested in the Dev. env., Completed on 18:30 PM 08/20/2025. Onsite QA completed on 2:05AM 25/08/2025
6 | GGO Donor Wave | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 [Strech] | Vishnu | GDON-42 | Donor API - GetFundraisingInfo | Completed | 2 |  |  | 2025-08-28 | 2025-09-03 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8801 | 2025-09-03 | 2025-09-03 | Rajesh |  | Wall-Iannarelli, Michael | 2025-09-03 |  |  |  | Testing activity done in the TST. env., Completed on 08:00 PM 09/04/2025
7 | GGO Donor Wave | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Ubaithullah, Kannan | GDON-39 | Donor API - Logging | Completed | 5 |  |  | 2025-09-01 | 2025-09-03 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8793 | 2025-09-03 | 2025-09-03 | Rajesh |  | Wall-Iannarelli, Michael | 2025-09-03 |  |  |  | Testing activity done in the TST. env., Completed on 01:00 PM 09/04/2025

## GGO 7.25.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Remarks
1 | GGO Donor Wave | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Kannan,Ubaithullah | GDON-17 | Donor API - Get/Create/Update/Delete FundraisingTeamMember | Completed | 5 | 5 |  | 2025-08-08 | 2025-08-13 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8736 | 2025-08-13 | 2025-08-14 | Rajesh |  | Wall-Iannarelli, Michael | 2025-08-14 | Remove Semicolon |  |  | Tested in the Dev. env., Completed on 12:30 PM 08/14/2025
2 | GGO Donor Wave | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Vishnu | GDON-18 | Donor API - Get/Create/Update/Delete FundraisingTeamCoordinator | Completed | 5 | 4 | 85.25 | 2025-08-11 | 2025-08-19 |  | Charles |  | Prabhu |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8754 | 2025-08-19 | 2025-08-20 | Prabhu | 1. Correct the params here 2. Correct the param here 3. Don't we have to check teamCoordinator is not null here before accessing its property 4. correct the param name here 5. Why are we keeping empty class here? remove it if not needed Suggestion 1. rather than generic description like 'response' , why don't we use actual description 2. rather than generic description like 'response' , why don't we use actual description (i.e FundraisingTeamCoordinator) 3. You could use else or else if here Does there any edge case of equals 0 here 4. Consider renaming this variable here? to be more descriptive | Wall-Iannarelli, Michael | 2025-08-20 |  |  |  | Tested in the Dev. env., Completed on 18:30 PM 08/20/2025
3 | GGO Donor Wave | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Vishnu | GDON-32 | Donor API - GetOfflineDonation | Completed | 2 | 2 | 22.75 | 2025-08-05 | 2025-08-08 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8724 | 2025-08-09 | 2025-08-09 | Rajesh |  | Wall-Iannarelli, Michael | 2025-08-09 |  |  |  | Tested in the Dev. env., Completed on 12:30 PM 08/11/2025
4 | GGO Donor Wave | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Ubaithullah, Kannan | GDON-33 | Donor API - EditOfflineDonation | Completed | 3 | 3 | 26 | 2025-08-06 | 2025-08-08 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8724 | 2025-08-09 | 2025-08-09 | Rajesh |  | Wall-Iannarelli, Michael | 2025-08-09 |  |  |  | Tested in the Dev. env., Completed on 1:30 PM 08/11/2025
5 | GGO Donor Wave | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 [Strech] | Ubaithullah, Kannan | GDON-36 | Donor API - Update Profile Image | Verify | 3 |  | 33.75 | 2025-08-13 | 2025-08-19 |  | Charles |  | Prabhu | Comment/ Suggestions: 1. does the method name is descriptive enough to explain the functionality? 2. Why are we duplicating the if check here? 3. Avoid the Naming rule violation here by start with uppercase | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8753 | 2025-08-19 | 2025-08-20 | Prabhu | 1. does the method name is descriptive enough to explain the functionality? 2. Why are we duplicating the if check here? 3. Avoid the Naming rule violation here by start with uppercase 4. Does there any references also needs to be updated? | Wall-Iannarelli, Michael | 2025-08-20 |  |  |  | Tested in the Dev. env., Completed on 9:30 PM 08/29/2025 | Found a defect and reported to the respective developer, also created a defect in JIRA - GDON-38.
6 | GGO Donor Wave | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 [Strech] | Ubaithullah, Kannan | GDON-37 | API Request - Pull Organization and Events at the same time | Completed | 3 |  | 18 | 2025-08-20
7 | GGO Donor Wave | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 [Strech] | Vishnu | GDON-34 | Donor API - GetCoordinatorProgress | Completed | 5 |  | 17.5 | 2025-08-20

## GGO 7.25.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
1 | GGO 7.25.0 Sprint 4 | GDON-38 | GDON-36 | Kannan | Defect | Supporter image Id not updated while updating the profile image | Major | Manual | External | Inprogress | Enhancements | End User | Image URL is showing as null and not getting updated | Incorrect parameter passed during the internal test and also logic has changed
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.25.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Kannan | GDON-29 | Create API to send info from GGO to Donor Platform - Organizations | Completed | 3 |  |  | 2025-07-25 | 2025-07-28 |  | Charles |  | Rajesh |  | Pull Request 8692: GDON-29 Create API to send info from GGO to Donor Platform - Organizations | 2025-07-28 | 2025-07-30 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-30 |  |  |  | Tested in the Dev. env., Completed on 6:00 PM 07/31/2025
2 | GGO Donor Wave | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Ubaithullah, Kannan | GDON-28 | Upload Image for Fundraising pages * | Completed | 2 |  |  | 2025-07-23 | 2025-07-28 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8696 | 2025-07-28 | 2025-07-29 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-29 |  |  |  | Tested in the Dev. env., Completed on 2:00 PM 07/29/2025
3 | GGO Donor Wave | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Ubaithullah, Kannan | GDON-19 | Donor API - Get/Send Email | Completed | 5 |  |  | 2025-07-29 | 2025-08-05 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8713 | 2025-08-05 | 2025-08-05 | Rajesh |  | Wall-Iannarelli, Michael | 2025-08-05 |  |  |  | Tested in the Dev. env., Completed on 3:00 PM 08/06/2025
4 | GGO Donor Wave | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Vishnu | GDON-30 | Create GGO API for Donor Platform - Events | Completed | 3 |  |  | 2025-07-25 | 2025-08-05 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8704 | 2025-08-04 | 2025-08-05 | Rajesh |  | Wall-Iannarelli, Michael | 2025-08-05 |  |  |  | Tested in the Dev. env., Completed on 8:40 PM 08/05/2025
5 | GGO Donor Wave | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3[Strech] | Kannan | GDON-21 | Donor API - Delete FundraisingActivity | Completed | 2 |  |  | 2025-08-05 | 2025-08-05 |  | Charles |  | Rajesh |  | Pull Request 8708: [GDON-21] Donor API - Delete Fundraising Activity | 2025-08-05 | 2025-08-05 | Rajesh |  | Wall-Iannarelli, Michael | 2025-08-05 |  |  |  | Tested in the Dev. env., Completed on 4:30 PM 08/06/2025
6 | GGO Donor Wave | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3[Strech] | Vishnu | GDON-32 | Donor API - GetOfflineDonation | Being Developed | 2 |  |  | 2025-08-05 | [16 empty] | Tested in the Dev. env., Completed on 12:30 PM 08/11/2025
7 | GGO Donor Wave | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3[Strech] | Ubaithullah, Kannan | GDON-33 | Donor API - EditOfflineDonation | Being Developed | 3 |  |  | 2025-08-06 | [16 empty] | Tested in the Dev. env., Completed on 1:30 PM 08/11/2025

## GGO 7.25.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Kannan, Ubaithullah | GDON-25 | Donor APi - Create/Update Fundraising Page | Completed | 5 |  |  | 2025-07-10 | 2025-07-20 |  | Charles |  | Rajesh, Vishnu |  | Pull Request 8665: [GDON-25] Donor API - Create/Update Fundraising_Page | 2025-07-21 | 2025-07-21 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-21 |  |  |  | Tested in the Dev. Completed 6:30 PM 07/22/2025
2 | GGO Donor Wave | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Ubaithullah | GDON-26 | Donor API - Delete Fundraising Page | Rejected | 2 | [19 empty] | This stoy has been rejected due to fund raising details will be deleted while delete the fund raising activity. So Rajesh provided the justification to reject this story
3 | GGO Donor Wave | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Ubaithullah | GDON-16 | Donor API - Get FundraisingPage | Completed | 5 |  |  | 2025-07-15 | 2025-07-22 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8673 | 2025-07-22 | 2025-07-22 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-22 |  |  |  | Tested in the Dev. Completed 11:30 PM 07/23/2025
4 | GGO Donor Wave | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Charles | GDON-12 | Donor API - Get/Create/Update/Delete ElectronicContactInfo | Completed | 2 | [5 empty] | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8632 | [9 empty] | Tested in the Dev. Completed 12:30 PM 07/15/2025
5 | GGO Donor Wave | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Vishnu | GDON-13 | Donor API - Get/Create/Update/Delete AddressInfo | Completed | 2 |  |  | 2025-07-10 | 2025-07-11 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8645 | 2025-07-14 | 2025-07-14 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-14 |  |  |  | Tested in the Dev. Completed 2:00 PM 07/15/2025
6 | GGO Donor Wave | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Vishnu | GDON-20 | Donor API - GetImage for Fundraising Page | Completed | 2 |  |  | 2025-07-14 | 2025-07-18 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8666 | 2025-07-21 | 2025-07-21 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-21 |  |  |  | Tested in the Dev. Completed 8:30 PM 07/22/2025
7 | GGO Donor Wave | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 [Strech] | Kannan, Ubaithullah | GDON-28 | Upload image for Fundraising Page | Being Developed | 3 |  |  | 2025-07-23
8 | GGO Donor Wave | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 [Strech] | Vishnu | GDON-23 | Donor API - Get Promote* | Completed | 2 |  |  | 2025-07-21 | 2025-07-23 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8679 | 2025-07-23 | 2025-07-23 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-23 |  |  |  | Tested in the Dev. Completed 6:30 PM 07/24/2025

## GGO 7.25.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2025-06-27 | 2025-07-10 | GGO 7.25.0 Sprint 1 | Kannan, Ubaithullah | GDON-11 | Donor API - Get/Create/Update/Delete OnlineBiddingActivity | Completed | 5 |  |  |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8621 | 2025-07-07 | 2025-07-08 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-08 |  |  |  | Tested in the Dev. Completed 5:30 PM 07/08/2025
2 | GGO Donor Wave | 2025-06-27 | 2025-07-10 | GGO 7.25.0 Sprint 1 | Vishnu | GDON-15 | Donor API - Get/Create/Update/Delete AddressBookEntry | Completed | 3 |  |  |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8615 | 2025-07-02 | 2025-07-08 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-08 |  |  | do we need to make sure error type matches operation type for all these methods ? | Tested in the Dev. Completed 12:30 PM 07/10/2025
3 | GGO Donor Wave | 2025-06-27 | 2025-07-10 | GGO 7.25.0 Sprint 1 [Stretch] | Kannan, Ubaithullah | GDON-14 | Donor API - Get/Create/Update/Delete CreditCardInfo | Completed | 3 |  |  |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8627 | 2025-07-08 | 2025-07-08 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-08 |  |  |  | Tested in the Dev. Completed 3:30 PM 07/09/2025
4 | GGO Donor Wave | 2025-06-27 | 2025-07-10 | GGO 7.25.0 Sprint 1 [Stretch] | Ubaithullah | GDON-12 | Donor API - Get/Create/Update/Delete ElectronicContactInfo | Verify | 2 |  |  |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8632 | 2025-07-09 | 2025-07-10 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-10 |  |  |  | Tested in the Dev. Completed 12:30 PM 07/15/2025
5 | GGO Donor Wave | 2025-06-27 | 2025-07-10 | GGO 7.25.0 Sprint 1 [Stretch] | Vishnu | GDON-13 | Donor API - Get/Create/Update/Delete AddressInfo | Being Developed | 2 |  |  |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8645 | 2025-07-14 | 2025-07-14 | Rajesh |  | Wall-Iannarelli, Michael | 2025-07-14 |  |  |  | Tested in the Dev. Completed 2:00 PM 07/15/2025
6

## GGO 7.24.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Kannan, Ubaithullah | GDON-9 | Donor API - Get/Create/Update/Delete Account Information | Completed | 5 |  |  | Kannan | Charles |  | Rajesh |  | Pull Request 8592: [GDON-9] Donor API - Get/Create/Update/Delete Account Information | 2025-06-20 | 2025-06-24 | Rajesh |  | Wall-Iannarelli, Michael | 2025-06-20 |  |  |  | Tested in the Dev. Completed 4:45 PM 06/25/2025
2 | GGO Donor Wave | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 3[Stretch] | Vishnu | GDON-7 | GGO Donor Api Project Pipeline and Release setup | Completed | 2 |  | 8 | Vishnu | Rajesh |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8573 | 2025-06-11 | 2025-06-17 | Rajesh |  | Horihan, Mike | 2025-06-17
3 | GGO Donor Wave | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Vishnu | GDON-10 | Donor API - Get/Create/Update/Delete Profile Information | Completed | 5 |  | 36 | Vishnu | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8593 | 2025-06-20 | 2025-06-21 | Rajesh |  | Wall-Iannarelli, Michael | 2025-06-21 | Suggestion can we rename Phones to PhoneNumbers ? "Phones" by itself implies the hardware |  |  | Tested in the Dev. Completed 5:30 PM 06/24/2025
4 | GGO Donor Wave | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint [Stretch] | Kannan, Ubaithullah | GDON-11 | Donor API - Get/Create/Update/Delete OnlineBiddingActivity | Analysis Completed | 5

## GGO 7.24.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Kannan | GDON-4 | GGO Donor Api Project Setup (WebApi Project in GGO Repo) | Completed | 3 | 3 | 25 | Vishnu | Rajesh |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8547 | 2025-06-05 | 2025-06-09 | Rajesh |  | Mccarty, Mike | 2025-06-09
2 | GGO Donor Wave | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Vishnu | GDON-5 | Create a Integration Test Project to unit test WebApi calls | Completed | 3 | 3 | 39 | Vishnu | Kannan |  | Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8553 | 2025-06-06 | 2025-06-10 | Rajesh |  | Mccarty,Mike Wall | 2025-06-10
3 | GGO Donor Wave | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Ubaithullah | GDON-6 | GGO Donor Api Authentication | Completed | 3 | 3 | 60 | Ubaithullah | Rajesh |  | Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8566 | 2025-06-10 | 2025-06-11 | Rajesh |  | Mccarty | 2025-10-06 | If we hardcode password, even temporarily as a placeholder, macroscope will flag it as a critical issue
4 | GGO Donor Wave | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3[Stretch] | Kannan | GDON-7 | GGO Donor Api Project Pipeline and Release setup | Being Developed | 3 |  | 43.5 | Vishnu | Rajesh |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8573 | 2025-06-11

## GGO 7.24.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 |  | 27.5 | [15 empty] | Issue not reproduceable in Dev and TST.Need to check query execution CRT The work around has been provided and ticket has been put on hold for now as it only impacts only one client/org and is of low priority
2 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Rajesh/ Sathiya | GGO-14656 | Nav Bar Update | Completed | 5 | 5 | 107 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8525 | 2025-05-28 | 2025-05-28 | Rajesh |  | Michael Wall | 2025-05-28 |  |  |  | Testing this in the Dev. In Progress 4:32 PM 5/27/2025
3 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Saranya | GGO-14679 | Sales Grid and Details Update for old Convenience Fee assets | Completed | 3 | 3 | 19 | Saranya | Rajesh |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8496 | 2025-05-16 | 2025-05-20 | Rajesh |  | Michael Wall | 2025-05-20 |  |  |  | Verified in the TST env successfully. 20 May 2025 at 05:52
4 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Saranya | GGO-9991 | "Purchaser Company Name" column causes error when the "Export" link is selected | Completed | 2 | 2 | 11.5 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8502 | 2025-05-19 | 2025-05-20 | Rajesh |  | Michael Wall | 2025-05-19 |  |  |  | Verified this in the TST env. 21 May 2025 at 09:23
5 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Rajesh | GGO-14708 | Remove Pivotal WebApi Project from GGO Repo - Unused project and it is using .Net Core 6 (deprecated version)* | Completed | 2 | 2 | 33 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8498 | 2025-05-17 | 2025-05-19 | Saranya |  | Michael Wall | 2025-05-20 |  |  |  | Offshore QA Verified this in the TST env. 21 May 2025 at 09:23
6 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Mike Wall/Rajesh/Saranya | GGO-14701 | Update Implementation of Flag to Disable Card Types in select Organizations | Completed | 2 | 2 | 23.75 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8508 | 2025-05-21 | 2025-05-21 | Rajesh |  | Michael Wall | 2025-05-21 |  |  |  | Verified in the TST env. 22 May 2025 at 08:01
7 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Mike Wall/Rajesh/Saranya | PAPI-858 | Update Flag to Disable Amex in select Organizations With Pre-Token Check* | Completed | 2 | 2 | 38 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8518 | 2025-05-22 | 2025-05-23 | Rajesh |  | Mike H | 2025-05-23 |  |  |  | Verified in the TST env. 22 May 2025 at 08:01
8 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Rajesh/Saranya | GGO-14684 | Implement Pendo for GGO | Completed | 5 | 5 | 41.75 | Rajesh | Priya |  | Saranyas |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8523 | 2025-05-27 | 2025-05-29 | Rajesh | 1. Let's add the following to the account metadata Environment: pendoEnvironment, 2. PendoUserID should be prefixed with PendoEnvironment so that UserID is unique across all environments 3. Dev and local should not fall under the same environment label | Mike H | 2025-05-29 |  |  |  | Testing this in the Dev. In Progress 4:32 PM 5/27/2025
9 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Saranya | GGO-14313 | HIGH- Usage of Manual HTML Sanitization (XSS) | Completed | 2 | 2 | 20.5 | Saranya | Rajesh |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8524 | 2025-05-27 | 2025-05-28 | Rajesh |  | Michael Wall | 2025-05-28

## GGO 7.24.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.24.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-13722 | High - Weak Encryption: Insecure Mode of Operation - Cryptography.cs: 56 | Completed | 1 | 1 | 15 | Sathiya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8458 | 2025-05-02 | 2025-05-02 | Rajesh |  | Michael Wall | 2025-05-03 |  |  |  | Verified in the TST env.5 May 2025 at 08:36
2 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-13723 | High - Weak Encryption: Insecure Mode of Operation - SymmetricAlgorithmProvider.cs: 35 | Completed | 1 | 1 | 34.5 | Sathiya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8457 | 2025-05-02 | 2025-05-06 | Rajesh |  | Michael Wall, Loan Troung | 2025-05-07 |  |  |  | Tested in the TST env 7 May 2025 at 09:20
3 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-14618 | MEDIUM - BDSA-2024-4605 - System.IdentityModel.Tokens.Jwt/5.5.0 | Completed | 2 | 2 | 10.25 | Sathiya | Rajesh |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8474 | 2025-05-07 | 2025-05-08 | Rajesh |  | Michael Wall | 2025-05-08 |  |  |  | Tested in the Dev env 8:09 PM 5/7/2025
4 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Rajesh/Saranya | PAPI-841 | Fix ValidateAndGetPorticoToken calls to handle when Token or CardBrandTransactionId exists | Completed | 2 | 2 | 18 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8477 | 2025-05-08 | 2025-05-09 | Rajesh |  | Michael Wall | 2025-05-09 |  |  |  | Did one round of Payment Regression Testing for this story in the TST env.9 May 2025 at 09:19
5 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Saranya | GGO-14601 | Project UI accepting Invalid Email address results in error on GGO to SF sync | Completed | 2 | 2 | 35 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8463 | 2025-05-05 | 2025-05-06 | Rajesh |  | Michael Wall | 2025-05-06 |  |  |  | Test Cycle executed Successfully in the TST env.7 May 2025 at 07:30
6 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Saranya | GGO-14652 | Enable Online Bidding - Blocked when users mistakenly generate Display Board | Completed | 5 | 5 | 49.5 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8476 | 2025-05-08 | 2025-05-10 | Rajesh |  | Michael Wall | 2025-05-12 |  |  |  | Tested in the TST env 13 May 2025 at 09:16
7 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1[Stretch] | Rajesh | GGO-14678 | Unable to Export Sales* | Completed | 2 | 2 | 19 | Rajesh | Sathiya,Priya |  |  |  | NA | NA | NA | NA |  | NA | NA
8 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 | 0 | 50.5 | [15 empty] | Issue not reproduceable in Dev and TST.Need to check query execution CRT
9 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Rajesh/ Sathiya | GGO-14656 | Nav Bar Update | Being Developed | 3 | 0 | 64.5 | [15 empty] | Reskin-V2 is a complete overhaul of the existing Master Page, focusing on delivering a fully responsive design. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness.
10 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Priya-QA | GGO-14619 | MEDIUM - CVE-2024-43485 - System.Text.Json/8.0.4 | Completed | 1 | 1 | 29 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env.

## GGO 7.24.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 7.24.0 Sprint 1 | GGO-14678 | GGO-13890 | Rajesh | Defect | Unable to Export Sales* | Major | Manual | External | Closed | Enhancements | End User | This is a production issue. The export sale grid functionality broke due to changes in the SLS report | For every small change implemented, a complete regression testing cycle must be performed to ensure system stability. This includes updating both automation and manual test cases to reflect any new or impacted scenarios. Additionally, thorough verification of all buttons across all application pages must be included, and corresponding scenarios should be documented and maintained in the manual test cases to ensure comprehensive coverage.
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.23.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Saranya | PAPI-840 | Remove the use of StringHashTable | Completed | 3 | 3 | 23.5
2 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Rajesh, Saranya | GGO-14644 | Remove Hash table in PAPI - GGO need to pass Bluetooth Swipe data on StoreFront scenario* | Completed | 1 | 1 | 14.5 | [15 empty] | Completed One round of Payment Regression
3 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Rajesh | GGO-14614 | HIGH - Microsoft.AspNetCore.Http.Connections.Client:1.0.0 | Completed | 2 | 2 | 19.5 | Rajesh | Sathish,Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8431 | 2025-04-23 | 2025-04-23 | Rajesh |  | Loan Troung | 2025-04-23 |  |  |  | Completed One round of Standard Regression
4 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Sathya | GGO-14613 | HIGH - Cross-Site Scripting: DOM - MaintenanceNotification.js: 22 & 25 | Completed | 2 | 2 | 34.5 | Sathiya | Rajesh,Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8434 | 2025-04-24 | 2025-04-28 | Rajesh |  | Michael Wall, Loan Troung | 2025-04-28
5 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4[Stretch] | Sathya | GGO-14658 | CRITICAL - CVE-2021-43569 - starkbank-ecdsa/1.3.1* | Completed | 1 | 1 | 14 | Sathiya | Rajesh,Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8436 | 2025-04-25 | 2025-04-28 | Rajesh |  | Michael Wall | 2025-04-28 |  |  |  | Development has been completed and tested in local and Dev enviroment[28-April-2025] Completed One round of Standard Regression
6 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Sathiya, Rajesh | GGO-13722 | High - Weak Encryption: Insecure Mode of Operation - Cryptography.cs: 56 | Peer review | 1 | 0.5 | 12.5 | Sathiya | Rajesh |  |  |  | NA
7 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Saranya | GGO-14615 | HIGH - Microsoft.Bcl.Async:1.0.168 | Completed | 2 | 2 | 10.5 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8427 | 2025-04-22 | 2025-04-22 | Rajesh |  | Loan Troung | 2025-04-22 |  |  |  | Completed One round of Standard Regression
8 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Saranya | GGO-13723 | High - Weak Encryption: Insecure Mode of Operation - SymmetricAlgorithmProvider.cs: 35 | Peer review | 1 | 0.5 | 22 | [5 empty] | NA
9 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4[Stretch] | MikeW, Rajesh, Saranya | GGO-14651 | Pass New IsFallback Swipe Flag from GoTime to PAPI | Completed | 2 | 2 | 36 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8440 | 2025-04-28 | 2025-04-28 | Rajesh |  | Michael Wall | 2025-04-28
10 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | MikeW, Rajesh, Saranya | PAPI-846 | EMV Fallback Requires <EMVChipCondition> Tag along with Swipe Data* | Completed | 3 | 3 | 48 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8441 | 2025-04-28 | 2025-04-28 | Rajesh |  | Michael Wall | 2025-04-28
11 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Priya-QA | GGO-14649 | 22 APR GGO 7.23.0 CRT Release & Regression Testing | Completed | 5 | 5 | 35.5 | [15 empty] | CRT Regression Testing in Progress
12 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Priya-QA | PAPI-851 | 22 APR PAPI 7.18.0 CRT Release & Regression Testing | Completed | 3 | 3 | 22 | [15 empty] | CRT Regression Testing in Progress
13 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4[Stretch] | Sathiya | GGO-14616 | HIGH & MEDIUM - Microsoft.Owin.Security.OpenIdConnect:4.2.2 | Completed | 2 | 2 | 5.5 | N/A | N/A | N/A | Rajesh |  | N/A | [9 empty] | Since we can't move Reskin Project from .net framework to .netcore update the comments in the story [04/30/2025]

## GGO 7.23.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO Web | GGO-14614 | GGO-14662 | Sathiya | Defect | Section Times Page Fails to Load After Launch – 500 Internal Server Error in Console | Significant | Manual | Internal | Closed | Development | Priya/Rajesh |  | As we updated Microsoft.AspNetCore.Http.Connections.Client:1.0.0 package to latest version 6.0.0.0 but it's dependent package Microsoft.Azure.SignalR.Asp.Net not updated by default Visual Studio and Pipeline doesn't show any exception
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.23.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Sathiya | GGO-14573 | OP to GGO import timeouts | Completed | 3 | 3 | 42 | Sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8370 | 2025-04-07 | 2025-04-08 | Rajesh |  | Mike Wall and Loan | 2025-04-08
2 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Rajesh | GGO-14633 | Allow Household Share on RSVP Imported Cards | Completed | 3 | 3 | 53 | Rajesh | Priya | Nill
3 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Sathiya | GGO-14457 | Allow Multiple RSVP Import from OP | Completed | 5 | 5 | 83 | sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8380 | 2025-04-14 | 2025-04-15 | Rajesh |  | Mike Wall and Loan | 2025-04-15
4 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3-[Stretch] | Saranya/Sathiya | GGO-14620 | BID-19 Admissions Count issue* | Completed | 3 | 3 | 13.5 | Sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8407 | 2025-04-16 | 2025-04-16 | Rajesh |  | Mike Wall | 2025-04-16
5 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3-[Stretch] | Priya-QA,Rajesh | PAPI-839 | Ensure all Portico calls use the client's API Key* | Completed | 1 | 1 | 13.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
6 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Priya-QA | GGO-14617 | HIGH & MEDIUM-Serilog.Sinks.File:4.0.0 | Completed | 1 | 1 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed 'testing in the TST env. 11:19 PM 4/7/2025
7 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Priya-QA,Rajesh | PAPI-842 | Fix issue where Payer Records CreditCardStatus are being set to Invalid | Completed | 2 | 2 | 17.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rajesh - Supported to analyze the root cause. Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario
8 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Saranya | PAPI-840 | Remove the use of StringHashTable | Peer Review | 8 | 5 | 90.5 | Sathiya | Priya | Nill | [12 empty] | Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario. The story was left in Peer Review upon completion, per the client's request to hold it and maintain this branch separately from the CERT branch. Dependency on Onsite QA now
9 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3-[Stretch] | Saranya,Rajesh | GGO-14644 | Remove Hash table in PAPI - GGO need to pass Bluetooth Swipe data on StoreFront scenario* | Peer Review | 2 | 1 | 19.5 | Sathiya | Priya | Nill | [12 empty] | Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario. The story was left in Peer Review upon completion, per the client's request to hold it and maintain this branch separately from the CERT branch. Dependency on Onsite QA now

## GGO 7.23.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO Web | GGO-14646 | GGO-14457 | Rajesh | Defect | Code mistakenly overwritten for GGO-14457 | Significant | Manual | Internal | Closed | Development | Rajesh | GGO-14633 Code mistakenly overwritten for GGO-14457. TThe team addressed the issue promptly, and the defect was resolved and closed on the same day. | Going forward team will make sure these kinds of overwrites will not be repeated and will do the review process accordingly
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.23.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Rajesh | GGO-14594 | Invoice Payment Pages are calculating unapplied convenience fees | Completed | 2 | 2 | 22.5 | Rajesh | Saranya/Priya | NA |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8336 | 2025-03-24 | 2025-03-24 | Rajesh |  | Loan Troung | 2025-03-24 |  |  |  | Email Queues and Quartz job issue blocked us to test this. Verified this story in the TST env. 3/28/2025. But still Quartz job issue exists.
2 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14621 | Email queues in TST repeatedly disabling* | Completed | 1 | 1 | 9 |  |  | NIL | [12 empty] | Email Queues issue got fixed. But still Quartz job issue exists in the TST env.
3 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14626 | Quartz Job not sending email in TST environment* | Completed | 1 | 1 | 2 |  |  | NIL | [12 empty] | Quartz job issue exists in the TST env.
4 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Sathiya | GGO-14589 | New clients don't have Invoicing capabilities | Completed | 2 | 2 | 13 | Sathya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8330 | 2025-03-21 | 2025-03-21 | Rajesh |  | Mike Horihan | 2025-03-22 |  |  |  | Completed Testing in the TST env. 3/25/2025
5 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Sathiya | GGO-14606 | Duplicate EventXCode's are Being Created | Completed | 3 | 3 | 71 | Sathya | Rajesh,Priya | NIL |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8355 | 2025-03-27 | 2025-03-28 | Rajesh |  | Loan Troung,Michael Wall | 2025-03-28 |  |  |  | Testing in progres 7:17 PM 3/28/2025
6 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Saranya | GGO-14587 | Invoice is not importing or clearing from import area | Completed | 2 | 2 | 32 | Saranya | Sathya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8338 | 2025-03-24 | 2025-03-25 | Rajesh |  | Loan Troung | 2025-03-25 |  |  |  | Completed Testing in the TST env. 3/28/2025
7 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Saranya | GGO-14573 | OP to GGO import timeouts | Being Developed | 3 | 5 | 97 | [15 empty] | We have reproduced this issue in DEV and TST environments but are still unable to reproduce it locally. Based on our analysis, GetClosedMatches method seems to be causing the issue. This method is used to find the closest matched names for the given input names and utilizes the Jaro-Winkler algorithm
8 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Priya-QA | GGO-14161 | Rewrite AGG-13 to a new report toolset | Completed | 1 | 1 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/25/2025
9 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14597 | Deprecated "DOMNodeInserted" & "DOMSubtreeModified" event throwing error in multiple places * | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/28/2025
10 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | PAPI-807 | Not all Credit Card Last 4 being added to payments table after hotfix PAPI-795* | Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
11 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14592 | Not all Credit Card Last 4 being added to payments table after hotfix PAPI-795* | Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
12 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14473 | Remove equipment banner* | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/25/2025
13 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | PAPI-839 | Ensure all Portico calls use the client's API Key* | Being Tested | 1 | 1 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test Client API Key's. Offshore QA did payment Regression Testing only.
14 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh,Sathiya | GGO-14602 | Handle message for 3X Reader Wi-Fi connection failed - StoreFront* | Completed | 2 | 2 | 1 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8362 | 2025-04-01 | 2025-04-01 | Rajesh | NA | Loan
14 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14624 | Previous/Next Month buttons not displaying in apAdmin* | Completed | 1 | 1 | 1 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8363 | 2025-04-01 | 2025-04-01 | Rajesh | NA | MikeWall |  |  |  |  | Supported Loan for this story

## GGO 7.23.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | RCA Comment
| GGO 7.23.0 Sprint 2 | GGO-14626 | NA | Rajesh | Defect | Quartz Job not sending email in TST environment* | Significant | Manual | Internal | Closed | Environment_Related | Priya | Deops team did setup new access rule for Azure Image Storage, missed to include Quartz Job server that results in failure of Quartz Job, finally fixed it by giving access for Quartz job server.
| GGO 7.23.0 Sprint 2 | GGO-14621 | NA | Rajesh | Defect | Email queues in TST repeatedly disabling* | Significant | Manual | Internal | Closed | Environment_Related | Priya,Nathan | This was issue related to Aesop Service bounce email not validated in Send Grid, removing the bounce email from Queue fixed this issue.
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.23.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Rajesh | GGO-14535 | OPStats.GetRsvpCount not being cached correctly | Completed | 2 | 2 | 22 | Rajesh | Priya | NIL |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8288 | 2025-03-06 | 2025-03-07 | Rajesh |  | Michael Wall | 2025-03-07 |  |  |  | Completed Testing 3/11/2025 7:40 PM
2 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Rajesh | PAPI-822 | Handle SystemError Response From Portico SOAP Call | Completed | 2 | 2 | 2.25 | Rajesh |  |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8291 | 2025-03-07 | 2025-03-08 | Rajesh |  | Michael Wall, Loan Troung | 2025-03-08
3 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | SathiyaBharathi | GGO-13890 | Rewrite and Update SLS-10 | Completed | 3 | 3 | 45.5 | Sathiya/Rajesh | Priya | NIL | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8300 | 2025-03-11 | 2025-03-11 | Rajesh |  | Michael Wall | 2025-03-11 |  |  |  | Completed Testing in the TST env 8:00 PM 3/12/2025
4 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Saranya | PAPI-816 | Investigate Check-In not storing Card or Payer record for Go-Time Enter Card on EMV TAP when flag Portico_TestingNeverSendToProcessor=true | Completed | 2 | 2 | 14.25 | Saranya | Sathiya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8293 | 2025-03-07 | 2025-03-10 | Rajesh |  | Michael Wall | 2025-03-11 |  |  |  | Completed Testing in the TST env. 3/11/2025 7:40 PM
5 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Rajesh | GGO-14576 | Investigate Card Verify Failure Message | Completed | 2 | 2 | 2.25 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8292 | 2025-03-07 | 2025-03-08 | Rajesh |  | Michael Wall, Loan Troung | 2025-03-08
6 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Saranya | PAPI-809 | HIGH - jQuery/2.0.0 in PapiAdmin | Completed | 2 | 2 | 33.75 | Saranya | Rajesh |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8314 | 2025-03-14 | 2025-03-14 | Rajesh |  | Michael Wall, Loan Troung | 2025-03-14 |  |  |  | Did one round of Payment Regression Testing in the TST env
7 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Rajesh | PAPI-808 | HIGH - CVE-2024-43485 System.Text.Json 8.0.4 | Completed | 2 | 2 | 11.75 | Rajesh | Saranya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8312 | 2025-03-13 | 2025-03-14 | Rajesh |  | Michael Wall, Loan Troung | 2025-03-14 |  |  |  | Did one round of Payment Regression Testing in the TST env
8 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1-[Stretch] | SathiyaBharathi/ Saranya/Rajesh | GGO-14586 | At Least 3 Card Brands Can Have Up to 19 Digit PAN* | Ready For Testing | 5 | 5 | 72 | Saranya/Rajesh | Priya | NIL | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8320 | 2025-03-18 | 2025-03-19 | Rajesh |  | Michael Wall | 2025-03-19 |  |  |  | Development has been completed and partially completed testing in dev environment[03/19/2025]. Did one round of payment Regression for this story in the TST env.
9 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1-[Stretch] | SathiyaBharathi/Rajesh | PAPI-829 | At Least 3 Card Brands Can Have Up to 19 Digit PAN* | Ready For Testing | 2 | 2 | 11.5 | Sathiya/Rajesh | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8318 | 2025-03-18 | 2025-03-19 | Rajesh |  | Michael Wall | 2025-03-19 |  |  |  | Development has been completed and partially completed testing in dev environment. [03/19/2025]
10 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1-[Stretch] | Rajesh | GGO-14587 | Invoice is not importing or clearing from import area* | Being Developed | 3 |  | 14.5
11 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Priya-QA | GGO-14584 | Resolve new issues introduced to automation | Completed | 1 | 1 | 22 | [15 empty] | Dev completed. Testing in Progress. Facing Mailinator Issues in the TST env. Completed Coding and Execution and Raised PR
12 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Priya-QA/ Sathiyabharathi/ Rajesh | PAPI-820 | Update the Portico Batch delayed interval | Completed | 1 | 1 | 18 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
13 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Priya-QA/ Rajesh | GGO-14596 | Add 3X SWIPE card payment method type* | Completed | 1 | 1 | 2 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
14 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Priya-QA | PAPI-819 | Fix 3X Swipe not Storing CCN Last4 GoTime ¦ Checkin ¦ Enter Card, & StoreFront | Completed | 1 | 1 | 1 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.

## GGO 7.23.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | RCA Comment
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.22.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Saranya | GGO-14070 | Rewrite BID-15 to a new report toolset | Completed | 2 | 2 | 15.5 | Saranya | Priya | Alignment Issues/ Design Issues | [12 empty] | Test Case Prepartion is done 5:48 PM 2/7/2025. Tested in dev env. 7:30 PM 2/19/2025 Carry forwarded to next sprint : Saranya worked on the RDLC report and own the full task took some time for her to learn and implement. Bug GGO-14564 was created on 20/02/2025. Pull request created on 20/02/2025 and Closed on 21 February 2025 at 03:41
3 | GGO Donor Wave | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Sathiyabharathi | GGO-14547 | Edit Package Image Display Issue | Completed | 2 | 1 | 9 | Sathiya | Priya | NA |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8265 | 2025-02-21 |  | Rajesh | [6 empty] | Peer testing N/A for this bug it's required DB update. Priya: Verified in TST env.8:56 PM 2/24/2025
4 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Sathiyabharathi | GGO-14545 | Move the Azure Storage Settings in to Redis/IIS cache to avoid multiple DB calls | Completed | 2 | 3 | 40.25 | Sathiya | Priya | NA |  |  | http://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8272 | 2025-02-26 | 2025-02-26 | Rajesh | [6 empty] | [02/25/2025]-Created draft PR. Dev Testing in Progress. Tested in the TST env. Working well 7:47 PM2/27/2025
5 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Loan/Sathiyabharathi | GGO-14510 | High - BDSA-2024-4305 - bootstrap/4.6.2 | Being Tested | 5 | 3 | 75.25 | Sathiya |  | NA | [7 empty] | Loan Troung | 2025-02-26 |  |  |  | This story is developed by an onsite developer (Loan). After a Bootstrap version update, we’re facing some UI issues. Offshore developer (Sathiya) is assisting with that. Tested this in the TST env. Raised a bug under this. 5:51 PM 3/5/2025. Nathan Comments: Got some Errors in Automation. So It require automation code updates or app code fix.
6 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Saranya | GGO-14567 | Bypass Verify on 3X Storefront swipe | Completed | 2 | 2 | 34.5 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8281 | 2025-02-28 | 2025-03-04 | Rajesh |  | Loan Troung | 2025-03-05 |  |  |  | We dont have access to test EMV transactions. Did Payment Regression Testing using manual cards. Since Portico is down, we were not able to verify swipe transactions. Portico is UP on last day of sprint, Verified and Completed.
7 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Saranya | PAPI-811 | Bypass Verify on 3X Storefront swipe | Completed | 2 | 2 | 35.75 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8282 | 2025-02-28 | 2025-03-04 | Rajesh |  | Loan Troung | 2025-03-05 |  |  |  | We dont have access to test EMV transactions. Did Payment Regression Testing using manual cards. Since Portico is down, we were not able to verify swipe transactions. Portico is UP on last day of sprint, Verified and Completed.
8 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4-[Stretch] | Saranya | GGO-14535 | OPStats.GetRsvpCount not being cached correctly | Being Developed | 2 | 2 | 31 | [15 empty] | Stretch story taken 1 day before sprint end, so got carry forwarded to next sprint.
8 | GGO Donor Wave | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14546 | Automation Maintenance | Completed | 1 | 1 | 10 | [15 empty] | Coding is still in progress 8:55 PM 2/24/2025. Completed almost all the files. Execution is in Progress 8:33 PM 3/3/2025 Execution Completed on 3/5/2025.
9 | GGO Donor Wave | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | PAPI-797 | Ensure Credit Card Last 4 is stored in Payers and Payments tables for 3X tap/dip | Completed | 1 | 1 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only. Testing blocked (since yesterday) by partial Portico outage – cannot generate successful EMV transactions.
10 | GGO Donor Wave | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14566 | 25 Feb GGO 7.22.0 CRT Release & Regression Testing | Completed | 1 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | CRT Regression Testing is in Progress. 8:31 PM 3/3/2025.Partially blocked by Portico transaction failures in CRT.Completed Remaining scenario from our end
11 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14509 | Critical - Privacy Violation | Completed | 1 | 1 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in TST env. 8:31 PM 3/3/2025
12 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | PAPI-812 | 25 Feb PAPI 7.17.0 CRT Release & Regression Testing | Completed | 1 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | CRT Regression Testing is in Progress. 8:31 PM 3/3/2025.Partially blocked by Portico transaction failures in CRT. Completed Remaining scenario from our end

## GGO 7.22.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | RCA Comment
| GGO 7.22.0 Sprint 4 | GGO-14563 | GGO-14504 | Sathiyabharathi | Defect | If Adjusted Admissions purchased by one supporter 'even out,' Supporter Form -> Sales Summary does not show asterisk | Significant | Manual | Internal | Closed | Development | Nathan
| GGO 7.22.0 Sprint 4 | GGO-14564 | GGO-14070 | Saranya | Defect | Negative Price Amounts Not Displaying Correctly | Significant | Manual | Internal | Closed | Development | Priya
| GGO 7.22.0 Sprint 4 | GGO-14571 | GGO-14070 | Rajesh | Defect | Extra line appears after the Package Name in few scenario's | Significant | Manual | Internal | Closed | Development | Priya
| GGO 7.22.0 Sprint 4 | GGO-14510 | GGO-14579 | Loan/Sathiyabharathi | Defect | Alignment Issues in GGO-apAdmin Page | Significant | Manual | Internal | Closed | Development | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.22.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14503 | Adjust Admission Functionality - add/remove | Completed | 2 | 2 | 23 | Sathiya | Priya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8189 | 2025-02-03 | 2025-02-04 | Rajesh |  | Loan Troung | 2025-02-04 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025 Deletion of attendee row if supporter chosen showed the popup confirmation, working on Adjusted amount calculation [1/29/2025] Did developer testing in dev environment no issues found [02/05/2025] Automation is pending[02/19/2025]. Nathan Closed the Automation Ticket
2 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | RajeshKannan | GGO-14450 | GGO Image Thumbnail Creation error | Completed | 2 | 2 | 2 | Rajesh | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8197 | 2025-02-04 | 2025-02-05 | Rajesh |  | Loan Troung | 2025-02-05
3 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Rajesh/Saranya | GGO-14529 | Invoice Timeout Fix | Completed | 1 | 1 | 7.5 |  | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8204
4 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Saranya | GGO-14070 | Rewrite BID-15 to a new report toolset | Peer Review | 5 | 5 | 84.5 |  | Priya | [13 empty] | Test Case Prepartion is done 5:48 PM 2/7/2025. Tested in dev env. 7:30 PM 2/19/2025 Carry forwarded to next sprint : Saranya worked on the RDLC report and own the full task took some time for her to learn and implement
6 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14530 | Image Manager Fix | Completed | 1 | 1 | 25.5 | Rajesh | Priya |  | Priya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8218 | 2025-02-07 | 2025-02-07 | Rajesh |  | Loan Troung | 2025-02-07 |  |  |  | 02/08/2025: This issue was Identitfied by CS and this is not a development or QA miss, this happens because the Javascript [DOM] component was deprecated and the code need to be updated accordingly.
7 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14504 | Adjust Admission Functionality - graph updates | Ready for Testing | 5 | 5 | 60 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8228 | 2025-02-12 | 2025-02-18 | Rajesh |  | Loan Troung | 2025-02-18 | GO PRINT N'Drop Procedure [dbo].[sp_GetAdjustedAdmissionCount]' GO IF OBJECT_ID('[dbo].[sp_GetAdjustedAdmissionCount]') IS NOT NULL DROP PROCEDURE [dbo].[sp_GetAdjustedAdmissionCount]; GO It is not necessary, but we do usually add PRINT statement. |  |  | Tested in the Dev env. 5:09 PM 2/17/2025. Completed testing the TST env. 8:27 PM 2/18/2025 Onsite QA Logged bug on last day of sprint, we fixed it deployed before sprint prep, QA didn't get time to complete it.
8 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Priya-QA | GGO-14071 | Rewrite BID-19 to a new report toolset | Completed | 1 | 1 | 22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Test Case Prepartion is done 5:48 PM 2/7/2025. Testing in dev env. 8:41 PM 2/13/2025. Completed Testing in the TST env.
9 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Priya-QA | PAPI-758 | Add support for additional Card Types | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. Verified all the cards 8:26 PM2/18/2025

## GGO 7.22.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| GGO 7.22.0 Sprint 3 | GGO-14542 | GGO-14503 | Sathiyabharathi | Bounceback/Sub-Defect | Admission UI should display even after saving sale with admissions adjusted to 0 | Significant | Manual | Internal | Closed/Rejected | Development
| GGO 7.22.0 Sprint 3 | GGO-14544 | GGO-14503 | Sathiyabharathi | Bounceback/Sub-Defect | Fix for GGO-1077 no longer working (allocation deleted via supporter) | Significant | Manual | Internal | Closed/Rejected | Development
| GGO 7.22.0 Sprint 3 | GGO-14563 | GGO-14504 | Sathiyabharathi | Bounceback/Sub-Defect | If Adjusted Admissions purchased by one supporter 'even out,' Supporter Form -> Sales Summary does not show asterisk | Significant | Manual | Internal | Inprogress | Development
| GGO 7.22.0 Sprint 3 | GGO-14564 | GGO-14070 | Sathiyabharathi | Bounceback/Sub-Defect | Negative Price Amounts Not Displaying Correctly | Significant | Manual | Internal | Inprogress | Development
| GGO 7.22.0 Sprint 3 | GGO-14530 |  |  | Defect | Image Manager Fix - the Scroll was not working so the CS was only able to see the 1st set of records and nothing beyond that | Significant | Manual | External | Closed/Rejected | Enhancements | This issue was Identitfied by CS and this is not a development or QA miss, this happens because the Javascript [DOM] component was deprecated and the code need to be updated accordingly.

## GGO 7.22.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Saranya | GGO-12487 | Adjust Admission Functionality - sale details | Completed | 5 | 5 | 23 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8184 | 2025-01-30 | 2025-01-30 | Rajesh |  | Loan Troung | 2025-01-30 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025. Priya - Testing in dev env is in progress 4:48 PM 1/30/2025
2 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Sathiyabharathi | GGO-14503 | Adjust Admission Functionality - add/remove | Ready for Testing | 5 | 5 |  | Sathiya |  |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8189 | 2025-02-03 | 2025-02-04 | Rajesh |  | Loan Troung | 2025-02-04 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025 Deletion of attendee row if supporter chosen showed the popup confirmation, working on Adjusted amount calculation [1/29/2025] Did developer testing in TST environment no issues found [02/04/2025] Onsite QA testing pending since [02/04/2025]
3 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | RajeshKannan | GGO-14514 | Update remaining admission allocated attendee count in GGO webserivce to OP | Completed | 1 | 1 |  | Rajesh | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8174 | 2025-01-24 | 2025-01-24 | Rajesh |  | Loan Troung | 2025-01-24 |  |  |  | Completed Testing in the TST env. 8:31 PM 1/29/2025
4 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Sathiyabharathi | GGO-14477 | BID-06 Header Settings Update | Completed | 2 | 2 |  | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8170 | 2025-01-23 | 2025-01-24 | Rajesh |  | Michael Wall | 2025-01-24 |  | This is QA automation which comes under Infrastructure improvement |  | Picked on 01/22/2025.Development in progress 23/01/2025 Deployed in dev and completed developer testing. Priya - Completed Testing in Dev. Working well 5:07 PM 1/24/2025. Completed Testing in TST 5:02 PM 1/27/2025
5 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | RajeshKannan | GGO-14450 | GGO Image Thumbnail Creation error | Ready for Testing | 2 | 2 |  | Rajesh | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8197 | 2025-02-04 | 2025-02-05 | Rajesh |  | Loan Troung | 2025-02-05 |  |  |  | It is completed and given for testing 3 days prior to Sprint end, Offshore QA doesn't got any access to test in TST, only MikeH and Nate got access to test it.
6 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Priya-QA | GGO-14511 | GoTime SF Tap card generate Null Ref Error | Completed | 2 | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Priya- Did one round of Payment Regression Testing since we dont have access to Tap cards. 5:01 PM 1/27/2025
7 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Priya-QA | PAPI-794 | Add Tag 9F6E to List of Acceptable Tags in ParseC3XJsonDataToTLV* | Completed | 1` | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Priya- Did one round of Payment Regression Testing since we dont have access to Tap cards. 8:00 PM1/28/2025
8 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Saranya | GGO-14529 | Stretch --Invoice Timeout Fix* | Peer Review | 2 | 2 | 12 | [5 empty] | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8204

## GGO 7.22.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| GGO 7.22.0 Sprint 2 | GGO-14529 | Production bug |  | Defect | Invoice timeout fix | Major | Manual | External | Open | Development | A miss from both Onsite and Offshore QA and Onsite and offshore developemnt because the old report generation handled it but the new report didn't so a miss on both testing and developement end. Extended testing needs to be done with a lot more combination of data which could be infinite combination.Moving forward this type of complex reports must be tested by all the team members including onsite lead before pushing to TST environment.

## GGO 7.22.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Sathiyabharathi/Rajesh Kannan | GGO-14427 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 3 (Sales & Payments) | Completed | 2 | 2 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8097 | 2024-12-31 | 2002-12-31 | Rajesh |  | Michael Wall | 2024-12-31 |  |  |  | Tested in the TST env. And it is In Progress 1/3/2025 8:13 PM. Tested in the Dev as well as in TST Env- 8:28 PM 1/6/2025. Testing is still in progress. 1/8/2025 8:10 PM
2 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Sathiyabharathi | GGO-14474 | Mismatch between the net invoice count and the report being generated. | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8112 | 2025-01-07 | 2025-01-08 | Rajesh |  | Loan Troung | 2025-01-08 |  |  |  | Tested in the Dev env. Looks good. 5:01 PM 1/21/2025.Tested in the TST env. Working well. 6:18 PM 1/22/2025
3 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Saranya | PAPI-790 | Insecure Transport: Database - App.config: 5 | Completed | 1 | 1 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8136 | 2025-01-11 | 2025-01-11 | Rajesh |  | Loan Troung | 2025-01-11 |  |  |  | Did one round of payment related regression Testing in the TST env. Looks good. 7:13 PM 1/16/2025
4 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Saranya/Rajesh Kannan | GGO-14450 | GGO Image Thumbnail Creation error | Being Developed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8158 | 2025-01-17 | 2025-01-21 | Rajesh |  | Loan Troung | 2025-01-21
5 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | GGO-14422 | Storefront Implement Signature Workflow in legacy go time code | Ready for Testing | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of payment Regression Testing in the TST env and checked cash and Check flow only(since I dont have EMV acces) Working well. 1/16/2025. 7:13 PM.
6 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA/Rajesh Kannan | GGO-14483 | 9 Jan CRT Release & Regression Testing | Completed | 5 | 5 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing in the progress CRT env.1/17/2025 4:37 PM. Testing is still in progress in CRT env. 1/20/2025 8:12 PM
7 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Saranya | PAPI-791 | Privacy Violation - PorticoSoapXmlBuilder.cs: 290 | Completed | 2 | 2 | [6 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | attempted to encrypt the entire XML section, but this failed during XML loading and saving. I observed this same privacy policy violation in two files: PorticoSoapXMLBuilder.cs and PorticoAdminBase.cs We chose PorticoAdminBase.cs for debugging and testing, this file SOAP envelope contains a username and password for Portico access. I encrypted only the username and password. However, I received a 'remote server returned 500 error' upon execution. Since the necessary data is encrypted, marking this as a false positive.
8 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | GGO-14469 | EMV Storefront - Implement Success Message for Card Entry flow | Completed | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of payment Regression Testing in the TST env. Working well. 1/17/2025 4:36 PM
9 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | GGO-14468 | EMV Checkin - Implement Success Message for Card Entry flow | Completed | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of payment Regression Testing in the TST env. Working well. 1/17/2025 4:36 PM
10 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | GGO-14447 | QA Automation - update EquipmentExpressVerification to account for date changes | Being Developed | 1 | 1 |  |  |  | NA |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGAutomation/pullrequest/8157 | 2025-01-17
11 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | PAPI-789 | refactor apConstants.EMV_SUCCESS_CODE and apConstants.EMV_FAILURE_CODE usage | Ready for Testing | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of payment Regression Testing in the TST env. Working well. 4:35 PM 1/18/2025
12 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Saranya | GGO-14471 | Stretch --Update UI for Receipt Dialogue* | Completed | 2 | 2 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8166 | 2025-01-21 | 2025-01-22 | Rajesh |  | Loan Troung | 2025-01-22 |  |  |  | Tested in the TST env. Looks good. 6:17 PM 1/22/2025
13 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Sathiyabharathi | GGO-14477 | Stretch -- BID-06 Header Settings Update.* | Being Developed | 2 | 2 | [16 empty] | Picked on 01/22/2025.Development in progress 23/01/2025 Deployed in dev and completed developer testing

## GGO 7.22.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| GGO 7.22.0 Sprint 1 | GGO-14489 | GGO-14427 | Sathiya | Defect | When the package number is entered under "omit sales and payments," it applies to all supporters, preventing the individual package values from being displayed for each supporter | Significant | Manual | Internal | Closed | Development
| GGO 7.22.0 Sprint 1 | GGO-14490 | GGO-14427 | Rajesh | Defect | Invoice link in email appearing twice when triggered from "Print/Email batch" | Significant | Manual | Internal | Closed | Development
| GGO 7.22.0 Sprint 1 | GGO-14500 | GGO-14483 | Rajesh | Defect | Print or Email Invoices - Over ride setting for "Show Invoice Page Link" & "Invoice Page Link Label" is not reflecting for a new email batch | Significant | Manual | Internal | Closed | Development | Verified in TST.Working well. 7:15 PM 1/16/2025
| GGO 7.22.0 Sprint 1 | GGO-14499 | GGO-14483 | Rajesh | Defect | implement quartz retry logic for invoice emails | Significant | Manual | Internal | Closed | Development | Unable to reproduce this issue in TST. Email sent successfully within few secs without getting any failures 7:18 PM 1/16/2025
| GGO 7.22.0 Sprint 1 | GGO-14512 | GGO-14483 | Rajesh | Defect | Report Bid-06 taking more time when selecting "View Items" in "Edit Invoice & Receipts settings" | Significant | Manual | Internal | Closed | Development | Tested in TST env. Working well. 8:11 PM 1/20/2025.

## GGO 7.21.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | SathyaBharathi/Rajesh Kannan | GGO-14325 | Rewrite and Update BID-06 (Invoice) using RDLC Part 1 | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan/Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8075 | 2024-12-17 | 2024-12-17 | Rajesh |  | Michael Wall | 2024-12-17 |  |  |  | Tested in the Dev environment - Informed few issues to the Team.12/17/202410:48 PM. Tested in the TST Env- 12/18/2024 7:20 PM.
2 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | SathyaBharathi/Rajesh Kannan | GGO-14426 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 2 (Sales Only) | Completed | 5 | 5 |  |  | Priya |  | Rajesh Kannan | [11 empty] | Rolling over remaining testing to this story - GGO-14427
3 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Saranya | GGO-14418 | Modify GGO SFDC Webservice | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8079 | 2024-12-13 | 2024-12-17 | Rajesh |  | Michael Wall | 2024-12-17 |  |  |  | Coordinated with saranya and Tested in Local -12/16/2024 8:56 PM.
4 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Saranya | GGO-14445 | Project Website - Remove Deprecated Share Functionality | Completed | 2 | 2 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8080 | 2024-12-13 | 2024-12-16 | Rajesh |  | Loan Troung | 2024-12-16 |  |  |  | Tested in the Dev environment - 12/16/2024 8:57 PM. Tested in the TST env. Working well. 12/17/2024 10:47 PM
5 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Rajesh Kannan | GGO-14419 | Duplicate EventXcode updated when GGO sync with SF | Completed | 3 | 3 |  |  | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8092 | 2024-12-27 | 2024-12-30 | Rajesh |  | Michael Wall | 2024-12-30
6 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Saranya/Rajesh Kannan | GGO-14375 | Pop-up warning on batch process with unapplied convenience fees | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8096 | 2024-12-31 | 2024-12-31 | Rajesh |  | Michael Wall | 2024-12-31 |  |  |  | Tested in the TST env. Working well 1/3/2025 8:13 PM
7 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Sathiyabharathi/Rajesh Kannan | GGO-14427 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 3 (Sales & Payments) | Being Tested | 5 | 5 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8097 | 2024-12-31 | 2002-12-31 | Rajesh |  | Michael Wall | 2024-12-31 |  |  |  | Tested in the TST env. And it is In Progress 1/3/2025 8:13 PM. Tested in the Dev as well as in TST Env- 8:28 PM 1/6/2025. Testing is still in progress. 1/8/2025 8:10 PM
8 | GGO Donor Wave | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Sathiyabharathi | GGO-14474 | Stretch -- Mismatch between the net invoice count and the report being generated.* | Ready For Testing | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8112 | 2025-01-07 | 2025-01-08 | Rajesh |  | Loan | 2025-01-08

## GGO 7.21.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
| GGO 7.21.0 Sprint 4 | GGO-14479 | Sathiya | Defect | Design issues | Minor | Internal | Closed | Design
| GGO 7.21.0 Sprint 4 | GGO-14480 | Rajesh | Defect | Express indicator displaying on Top right in compact scenario even the Supporter is not marked as "Express Checkout" | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14481 | Sathiya | Defect | When the "Only Show Sales That Are Paid" option is enabled in the invoice settings, the "Total Due" field should not be displayed in the Bid 06 report but it is still visible | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14486 | Rajesh | Defect | Font not changing in Bid-06 RDLC report based on "General Accounts & Settings" | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14488 | Rajesh | Defect | Receipt Settings Override while sending Invoice email is not working | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14476 | Saranya | Defect | When the convenience fee is disabled, clicking on "Start New Batch" does not navigate to the next page. | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14489 | Sathiya | Defect | When the package number is entered under "omit sales and payments," it applies to all supporters, preventing the individual package values from being displayed for each supporter | Significant | Internal | Inprogress | Development
| GGO 7.21.0 Sprint 4 | GGO-14490 | Rajesh | Defect | Invoice link in email appearing twice when triggered from "Print/Email batch" | Significant | Internal | Closed | Development

## GGO 7.21.0 Sprint 3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO 7.21.0 Sprint 3 | SathyaBharathi/Rajesh Kannan | GGO-14325 | Strech--Rewrite and Update BID-06 (Invoice) using RDLC | Inprogress | 5 | 5 | [15 empty] | It will get carry forward to next sprint, due to requirement change by MikeH. 2.[12/12/2024] Invoice Email Failed becuase of Quratz service required DB permission
2 | GGO 7.21.0 Sprint 3 | Saranya | PAPI-725 | High - Weak Encryption: Insecure Mode of Operation - Dukpt.cs: 102 | Completed | 3 | 3 | [15 empty] | Waiting for macroscope result 12/12 : Was marked out of Scope by Mike Horihan
3 | GGO 7.21.0 Sprint 3 | Saranya | GGO-12835 | Update to event date range fields and logic in GGO Project Builder* | Completed | 3 | 3 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8056 | 2024-12-04 | 2024-12-06 | Rajesh |  | Loan Troung, Michael Wall | 6-Dec-024
4 | GGO 7.21.0 Sprint 3 | Rajesh Kannan | GGO-14414 | Investigate GGO Client create/update API to handle Client sync process with SF* | Completed | 2 | 2 | [15 empty] | Investigation completed
5 | GGO 7.21.0 Sprint 3 | Priya | GGO-13319 | Azure Images CRT Testing | Completed | 1 | 1 | [15 empty] | Completed from our end
6 | GGO 7.21.0 Sprint 3 | Priya | GGO-14402 | 03 DEC GGO 7.20.1 CRT Release | Completed | 2 | 2
7 | GGO 7.21.0 Sprint 3 | Saranya | GGO-14383 | Stretch --Refund Reference Number Not Generating* | Completed | 2 | 2 | [5 empty] | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8071 | 2024-12-10 | 2024-12-11 | Rajesh |  | Loan Troung, Michael Wall | 2024-12-11 |  |  |  | Completed from our end
8 | GGO 7.21.0 Sprint 3 | Priya | PAPI-773 | Update to PAPI TLV response for success / fail Verify (Check-In) if not included | Ready for Testing | 1 | 1 | [15 empty] | Did one Round of Payment Regression Testing, Final testing pending for onsite QA
9 | GGO 7.21.0 Sprint 3 | Priya | PAPI-781 | Required Zip Code Problems with EMV Verify (AMEX Only) | Ready for Testing | 1 | 1 | [15 empty] | Did one Round of Payment Regression Testing, Final testing pending for onsite QA
10 | GGO 7.21.0 Sprint 3 | Priya | GGO-14425 | Remove "Transaction was Successful!" pop-up at the right corner of screen for EMV (Storefront & CheckInOut)* | Completed | 1 | 1 | [15 empty] | Did one Round of Payment Regression Testing

## GGO 7.21.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No Defects

## GGO 7.21.0 Sprint 2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO 7.21.0 Sprint 2 | SathyaBharathi | GGO-14386 | BID-03 RDLC version ignoring grid selection for output | Completed | 3 | 3 | Sathiyabharathi | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8003 | 2024-11-18 | 2024-11-19 | Rajesh |  |  |  |  | Bug fix - Completed
2 | GGO 7.21.0 Sprint 2 | Saranya | GGO-14355 | Update Help Center URLS | Completed | 2 | 2 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8000 | 2024-11-15 | 2024-11-16 | Rajesh |  | Loan Troung | 2024-11-16 | The target has been assigned with a "_blank" but we still keep this button and ID. Where/which file is this ID being used? Looks like you removed the popup properties for it in file "GoTime.ts" line: 533 | Updated New helpcenter content - Completed
3 | GGO 7.21.0 Sprint 2 | Priya-QA | GGO-14361 | Add support for additional Card Types | Completed | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | GGO 7.21.0 Sprint 2 | Priya-QA | GGO-13319 | Azure Images CRT Testing | InProgress | 3 | 3 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | GGO 7.21.0 Sprint 2 | Saranya | GGO-14395 | Unable to add Discover cards in orgs enabled for Discover | Completed | 1 | 1 | Saranya | Priya | No | Sathiya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8022 | 2024-11-22 | 2024-11-22 | Rajesh | No | Mike Wall | 2024-11-22 | No | Defect story for GGO-14361 - Completed | No
6 | GGO 7.21.0 Sprint 2 | Rajesh | GGO-14397 | Image is not being retrieved from Azure after saving the Project or settings, even though Azure configuration is enabled | Completed | 2 | 2 | Rajesh | Priya | No | Sathiya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8022 | 2024-11-22 | 2024-11-22 | Sathiya | No | Mike Wall | 2024-11-22 | No | Bug fix - Completed | No
7 | GGO 7.21.0 Sprint 2 | SathyaBharathi/Rajesh | GGO-14385 | Investigate New App Svc for OB Queue Replacement | Completed | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Investigation - Completed | NA | It's an investingation story we prepared document and attached the jira ticket

## GGO 7.21.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments

## GGO 7.21.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.21.0 Sprint 1 | Rajesh/SathyaBharathi | GGO-14067 | Rewrite BID-03 to a new report toolset | 5 | 5 | Sathiyabharathi/Rajesh | Priya | GGO-14353 Alignment Issues and GGO-14378 Throwing 504 Gateway Timeout error while rendering Bid-03 report | Saranya | No | NA | NA | NA | NA |  | NA |  |  | Moving report to new toolset - Completed |  | Completed | Cretaed bugs under this story (GGO-14353 and GGO-14378) PR created and completed under those bugs
2 | GGO 7.21.0 Sprint 1 | Rajesh | GGO-14244 | Error when trying to create project website | 3 | 3 | Rajesh | Priya | No | Sathiya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7961 | 2024-11-06 | 2024-11-06 | Loan | I think if we are going to catch it, then we should log it. Log "info". |  | 2024-11-06 |  | Bug fix - Completed |  | Completed
3 | GGO 7.21.0 Sprint 1 | Sathiyabharathi | GGO-14353 | Alignment Issues | NA | NA | Sathiyabharathi | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7949 | 2024-11-08 | 2024-11-08 |  | No Comments | Michael Wall/Loan | 2024-11-08 | No Comments |  |  | Completed
4 | GGO 7.21.0 Sprint 1 | Sathiyabharathi | GGO-14378 | Throwing 504 Gateway Timeout error while rendering Bid-03 report | NA | NA | Sathiyabharathi | Priya |  | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7981 | 2024-11-12 | 2024-11-12 | Rajesh | No Comments | Michael Wall/Loan | 2024-11-12 | 1.is this variable name a typo ? "foud" vs "found" 2.Could we move all these spacing into a variable/constant before using? The variable naming provides meaning to why all these spacing are used. | Defect story for GGO-14067 - Completed |  | Completed
5 | GGO 7.21.0 Sprint 1 | Saranya | GGO-14295 | Handle Deleted User Session | 3 | 3 | Saranya | Priya |  | Sathiya | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7983 | 2024-11-13 | 2024-11-13 | Rajesh |  | Michael Wall | 2024-11-13 |  | Rolled over |  | InProgress | Trying to reproduce the issue in local
6 | GGO 7.21.0 Sprint 1 | Rajesh | GGO-14373 | ManageSalesAndPayments Error* | 2 | 2 | Rajesh | Priya | No | Sathiya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7968 | 2024-11-07 | 2024-11-08 | Loan | No Comments |  |  |  | Bug fix - Completed |  | Completed
6 | GGO 7.21.0 Sprint 1 | Saranya | GGO-14355 | Update Help Center URLS* | 3 | 2 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7988 | 2024-11-13 |  | Rajesh |  |  |  |  | Rolled over |  | InProgress | Development completed
7 | GGO 7.21.0 Sprint 1 | Priya-QA | PAPI-774 | Refunds failing to process | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | completed
8 | GGO 7.21.0 Sprint 1 | Priya-QA | GGO-14361 | Add support for additional Card Types | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | InProgress
9 | GGO 7.21.0 Sprint 1 | Priya-QA | GGO-14373 | ManageSalesAndPayments Error* | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed
10 | GGO 7.21.0 Sprint 1 | Priya-QA | GGO-14244 | Error when trying to create project website | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed

## GGO 7.21.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
| GGO 7.21.0 Sprint 1 | GGO-14244 | Rajesh | Defect | Error when trying to create project website | Major | Internal | Closed
| GGO 7.21.0 Sprint 1 | GGO-14378 | Sathiya | Defect | Throwing 504 Gateway Timeout error while rendering Bid-03 report | Significant | Internal | Closed
| GGO 7.21.0 Sprint 1 | GGO-14373 | OP Team | Defect | ManageSalesAndPayments Error | Major | External | Closed |  | Production Bug missed by OP Client team and fixed by GGO team . It is a defect which needs to be documented on OP team sheet but was fixed by GGO team

## GGO 7.20.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.20.0 Sprint 4 | Rajesh/SathyaBharathi | GGO-14067 | Rewrite BID-03 to a new report toolset | 5 |  |  | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7869 | 2024-10-24 | 2024-10-24 | Rajesh | No | Michael Wall | 2024-10-24 | can we have a folder for each report ? | Moving the report to new toolset - Rolled over |  | InProgress | We got an timeout issue while running the report in dev enviroment.
2 | GGO 7.20.0 Sprint 4 | Saranya | GGO-14340 | Login Page Update - Expiring Privacy Policy Message | 3 | 3 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7916 | 2024-10-23 | 2024-10-25 | Rajesh |  | Michael Wall | 2024-10-25 |  | To implement an expiring message with a url informing customers of an updated privacy policy on the GGO login page, to maintain compliance with corporate legal - Completed |  | completed
3 | GGO 7.20.0 Sprint 4 | Saranya | GGO-14244 | Error when trying to create project website* | 3 | 3 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7945 | 2024-10-30 | 2024-10-30 | Rajesh | No | Michael Wall | 2024-10-30 |  | Priority defect fix - Rolled over |  | InProgress
4 | GGO 7.20.0 Sprint 4 | Rajesh | GGO-14352] | Update Report Path in Publish XML | NA | NA |  | NA |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7930 | 2024-10-24 | 2024-10-24 |  |  | Michael Wall | 2024-10-24 | No |  |  | completed
5 | GGO 7.20.0 Sprint 4 | Priya-QA | GGO-13860 | GGO - handle emv dip/tap in check in/out | 1 | 1 | Loan | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | Rolled over | NA | completed
6 | GGO 7.20.0 Sprint 4 | Rajesh | PAPI-769 | PAPI-769 Update PAPI Web References* | 2 | 2 | Rajesh | Priya | No | NA | NA | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7934 | 2024-10-25 | 2024-10-25 | Mike Wall | No | NA | NA | No | Bug fix - Completed |  | completed
7 | GGO 7.20.0 Sprint 4 | Rajesh | GGO-14347 | Update the format of amount in payment receipt* | 1 | 1 | Sathiya | Priya | [11 empty] | Bug fix - Completed |  | Completed
8 | GGO 7.20.0 Sprint 4 | Saranya | GGO-14356 | Footer statement appears in the middle of the report instead of at the bottom when a footer is included. | 1 | 1 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7945 | [9 empty] | Completed

## GGO 7.20.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
| GGO 7.20.0 Sprint 4 | GGO-14353 | Sathiya | Defect | Alignment Issues | Minor | Internal | Open

## GGO 7.20.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.20.0 Sprint 3 | Rajesh/SathyaBharathi/Saranya | GGO-14067 | Rewrite BID-03 to a new report toolset | 5 | [14 empty] | Rewriting all the reports to new toolset and BID-03 is the Proof of Concept. Rolled over and team is still working on it.In a single report, multiple layouts are there |  | Inprogress
2 | GGO 7.20.0 Sprint 3 | Rajesh/Saranya | GGO-14079 | Rewrite BID-06 (Payment Receipt) using RDLC | 5 | 5 | Rajesh/Saranya | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7892 | 2024-10-12 | 2024-10-12 | Rajesh | No | Loan Troung, Michael Wall | 2024-10-12 | No | Similar to BID-03 |  | Closed
3 | GGO 7.20.0 Sprint 3 | Saranya | PAPI-751 | High - jQuery.UI.Combined/1.12.1 | 2 | 2 | Saranya | Rajesh |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7894 | 2024-10-15 | 2024-10-15 | Rajesh | No | Loan Troung, Michael Wall | 2024-10-15 | No | Part of Macroscope scanning epic |  | Closed
4 | GGO 7.20.0 Sprint 3 | Rajesh | GGO-14323 | Adding new GG Build Server for GGO Pipeline build replacing Azure Build server | 1 | 1 | Rajesh | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7873 | 2024-10-05 | 2024-10-05 | NA | No | Loan Troung, Michael Wall,Mike Horihan | 2024-10-05 | No |  |  | Closed
5 | GGO 7.20.0 Sprint 3 | Rajesh | GGO-14324 | Send PDF for email payment receipt | 3 | 3 | Rajesh/Saranya | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7892 | 2024-10-12 | 2024-10-12 |  | No | Loan Troung, Michael Wall | 2024-10-12 | No |  |  | Closed
6 | GGO 7.20.0 Sprint 3 | Priya-QA | GGO-14199 | Fix Deleted Credit Card Online Payment Pop-up Message / Function | 1 | 1 | Loan | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
7 | GGO 7.20.0 Sprint 3 | Rajesh/Saranya | GGO-14332 | Unable to view the Header and Footer Statement in the Payment Receipt even though they have already been added to the payment receipt settings |  |  | Rajesh/Saranya | Sathya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7896 | 2024-10-16 | 2024-10-16 | Rajesh | No | Michael Wall | 2024-10-16 | No | Bug for the Story GGO-14079 |  | Closed

## GGO 7.20.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
| GGO 7.20.0 Sprint 3 | GGO-14332 | Rajesh/Saranya | Defect | Unable to view the Header and Footer Statement in the Payment Receipt even though they have already been added to the payment receipt settings | Major | Internal | Closed | Enhancements

## GGO 7.20.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.20.0 Sprint 2 | Sathiyabharathi | GGO-14002 | Update AGG-03 | 3 | 3 | sathiya | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7840 | 2024-09-23 | 2024-09-26 | Rajesh | No | Loan Troung | 2024-09-26 | No | Concept of moving all the reports to new toolset | No | Closed
2 | GGO 7.20.0 Sprint 2 | Rajesh/SathyaBharathi/Saranya | GGO-14067 | Rewrite BID-03 to a new report toolset | 5 | [14 empty] | Concept of moving all the reports to new toolset |  | Inprogress
3 | GGO 7.20.0 Sprint 2 | Saranya | GGO-14300 | GetAdmissionInfo API update for mobile team | 3 | 3 |  | Priya | Yes(Found one Issue while testing this in Dev Env) | SathiyaBharathi | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7842 | 2024-09-23 | 2024-09-24 | Rajesh | No | Loan Troung, Michael Wall | 2024-09-24 | No | No | No | Closed
4 | GGO 7.20.0 Sprint 2 | Saranya | GGO-14302 | SFDC Release Support | 2 | 2 |  | Priya |  | SathyaBharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7835 | 2024-09-20 | 2024-09-20 | Rajesh | No | MikeH,Loan Troung | 2024-09-20 | No |  |  | Closed
5 | GGO 7.20.0 Sprint 2 | Sathiyabharathi | GGO-14255 | API update for nextgen search* | 1 | 1 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7817 | 2024-09-13 | 2024-09-19 | Rajesh | No | Loan Troung | 2024-09-19 | No | No | No | Closed
5 | GGO 7.20.0 Sprint 2 | Priya-QA | GGO-14267 | GGO Image Server | 2 | 2 | Loan | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
6 | GGO 7.20.0 Sprint 2 | Rajesh | GGO-13842 | Fallback Strategy for Report Migration | 2 | 2 | Rajesh | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7838 | 2024-09-20 | 2024-09-23 | Loan | No | Mike Wall | 2024-09-23 | No | This is for the new reporting toolset | No | Closed
7 | GGO 7.20.0 Sprint 2 | Priya-QA | PAPI-750 | Portico SOAP - Token and CardBrandTxnId* | 1 | 1 | Mike Wall | Priya | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed

## GGO 7.20.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments

## GGO 7.20.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.20.0 Sprint 1 | Sathiyabharathi | GGO-14287 | Renew localtest Certificate | 1 | 1 | Rajesh | Rajesh | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7791 | 2024-09-09 | 2024-09-09 | Rajesh |  | MikeH | 2024-09-09 | No | No | No | Closed
2 | GGO 7.20.0 Sprint 1 | Rajesh | GGO-14293 | Event payments processed under wrong event name, GGO and SF not synced correctly* | 1 | 1 | Rajesh | Rajesh | No | Rajesh |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
3 | GGO 7.20.0 Sprint 1 | Saranya | GGO-14218 | High - CVE-2024-30105 - System.Text.Json/4.7.2 & CVE-2024-30105 - System.Text.Json/4.6.0 | 2 | 2 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7702 | 2024-09-11 | 2024-09-11 | Rajesh | No | Michael Wall | 2024-09-11 | No | Macroscope scanning - fixed | No | Closed
4 | GGO 7.20.0 Sprint 1 | Sathiyabharathi | GGO-14215 | Cannot create/update Project Template in PROD | 2 | 2 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7800 | 2024-09-12 | 2024-09-12 | Rajesh | No | Loan Troung | 2024-09-12 | No | Priority defect - Fixed | No | Closed
5 | GGO 7.20.0 Sprint 1 | Sathiyabharathi/Saranya | GGO-14255 | API update for nextgen search* | 2 | 2 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7817 | 2024-09-13 | 2024-09-19 | Rajesh | No | Loan Troung | 2024-09-19 | No | No | No | Inprogress
6 | GGO 7.20.0 Sprint 1 | Priya-QA | GGO-14275 | Add Edit Remove User Test Case* - Automation | 2 | 2 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGAutomation/pullrequest/7822 | 2024-09-18 | 2024-09-19 | Owen | 1. All Console.Writelines can be removed. Only should be used for debugging purposes. 2. This function should be moved into SeleniumActions. that file is in alphabetical order. 3. We have a function called VerifyCheckBoxInner. that should be used and this one removed. | Owen | 2024-09-19 | No | No | No | Closed
7 | GGO 7.20.0 Sprint 1 | Saranya | PAPI-733 | Refactor Polly Retry code for Portico to have "Try" block inside "Polly.Execute" block | 5 | 5 | Priya | Sathiya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7820 | 2024-09-16 | 2024-09-16 | Rajesh | No | Loan Troung, MikeW | 2024-09-16 | No | No | No | Closed

## GGO 7.20.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.19.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.19.0 Sprint 4 | Sathiyabharathi/Saranya | GGO-14269 | Project builder to pull images from the Azure CDN instead of Content server url if Azure setting is enabled | 2 | 2 |  | Sathiyabharathi/Saranya | No | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7766 | 2024-08-23 | 2024-09-03 | Rajesh |  | Michael Wall | 2024-09-03 | No | No | No | Closed
2 | GGO 7.19.0 Sprint 4 | Priya-QA | https://greatergiving.atlGGO-14270 | GGO 7.19.0 CRT Release & Regression Testing | 3 |  | Priya | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
3 | GGO 7.19.0 Sprint 4 | Priya-QA | PAPI-734 | PAPI 7.14.0 CRT Release & Regression Testing | 1 | 1 | Priya | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
4 | GGO 7.19.0 Sprint 4 | Saranya | GGO-14216 | High - ASP.NET MVC Bad Practices: Model With Required Non-Nullable Property - ProjectDto.cs* | 1 | 1 | Priya |  |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7770 | 2024-08-23 | 2024-08-23 | Rajesh | No | Loan Troung | 2024-08-23 | No |  |  | Closed
5 | GGO 7.19.0 Sprint 4 | Sathiya/Rajesh | GGO-14264 | Duplicate Supporters that are imported in through sales does not trigger check for duplicate* | 3 | 3 | Priya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7780 | 2024-08-29 | 2024-08-30 | Rajesh | No | Michael Wall | 2024-08-30 | No |  |  | Closed
6 | GGO 7.19.0 Sprint 4 | Sathiyabharathi/Saranya | GGO-14255 | API update for nextgen search* | 2 | 1 | Priya | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7817 | [9 empty] | Inprogress
7 | GGO 7.19.0 Sprint 4 | Saranya | GGO-14240 | NextGen API update for supporter card on file status | 2 | 2 | Saranya | Priya |  | SathiyaBharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7765 | 2024-08-23 | 2024-08-23 | Rajesh | No | Loan Troung | 2024-08-23 | No | No | No | Closed
8 | GGO 7.19.0 Sprint 4 | Priya-QA | GGO-14275 | Add Edit Remove User Test Case* - Automation | 3 |  | Priya | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress

## GGO 7.19.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.19.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.19.0 Sprint 3 | Saranya/Rajesh/Sathiya | GGO-14232 | PRD Issue with Recalculate Name Fields is timing out | 2 | 1 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7758 | 2024-08-20 | 2024-08-20 | Rajesh | NA | Mike W | 2024-08-20 | NVARCHAR(MAX) should not be used with Split. | Prod issue - Fixed | NA | Closed
2 | GGO 7.19.0 Sprint 3 | Sathiyabharathi | GGO-14236 | Convert asp.net core | 5 | 5 | Sathiyabharathi | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7753 | 2024-08-13 | 2024-08-19 | Rajesh | NA | Loan | 2024-08-19 | No | NA | NA | Closed
3 | GGO 7.19.0 Sprint 3 | Saranya | GGO-14225 | Update the left nav menu | 2 | 2 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7746 | 2024-08-07 | 2024-08-07 | Rajesh |  | Mike Horihan | 2024-08-13 |  | Part of Invoicing epic - Completed |  | Closed
4 | GGO 7.19.0 Sprint 3 | Priya-QA | GGO-14253 | CRT Release Support GGO 7.18.2 | 3 |  | Priya | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
5 | GGO 7.19.0 Sprint 3 | Saranya | GGO-14216 | High - ASP.NET MVC Bad Practices: Model With Required Non-Nullable Property - ProjectDto.cs* | 2 | 1 | Saranya | Priya |  | Rajesh |  | NA | [7 empty] | Macroscope scanning - Rolled oved |  | Closed | Macroscope error should be resoved by our changes.But it takes 3 days. once it is done we have to check whether the issue is resolved or not
6 | GGO 7.19.0 Sprint 3 | Sathiyabharathi | GGO-14262 | Investigation - RSVP Page cannot be edited or deleted; leads to an error* | 2 | 2 | Sathiyabharathi | NA | NA | Rajesh |  | NA | NA | NA | Rajesh | NA | NA | NA | NA | Priority defect - Fixed | NA | Closed | It is an investigation story, we found that some of the RSVP pages in PROD is marked as “IsRsvp = 0” in “ap_WebsiteRegistrationPage” table instead of “IsRsvp=1“.

## GGO 7.19.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.19.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.19.0 Sprint 2 | Sathiyabharathi | GGO-14204 | High & Medium - BDSA-2023-3833 - jQuery.Validation/1.19.5 & BDSA-2021-3651 - jQuery/3.5.1 | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7691 | 2024-07-16 | 2024-07-18 | Rajesh | No | Loan | 2024-07-18 | Query is part of the BundleConfig for Reskin. Is this reference necessary? | Part of macroscope scanning - Completed |  | Closed | Instead of using JQuery reference directly in User control or content pages, we can use Script Manager proxy to define Jquery. So i have removed jquery reference link and used ScriptManagerProxy. In our application some of the pages(ClientView.aspx) we have used script manager proxy. It is used to add scripts and services to content pages and to user controls if the master page or host page already contains a ScriptManager control. We are not used any master pages in PreMfaLanding.aspx page but still this file handling click events so retains Jquery reference link in this file alone. (edited)
2 | GGO 7.19.0 Sprint 2 | Priya-QA | GGO-14233 | Landing page "admissionsChart" and "totalSalesChart" Throwing Console Error* | 1 | 1 | NA | Priya | Yes - Found one issue while testing this bug in Dev env | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Part of Quality of life epic | NA | Closed
3 | GGO 7.19.0 Sprint 2 | Priya-QA | GGO-14247 | Users unable to set/reset GGO password in Chrome & Edge* | 3 | 2 | NA | Priya |  | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Priority defect - Fixed | NA | Closed
4 | GGO 7.19.0 Sprint 2 [STRETCH] | Saranya | GGO-14232 | PRD Issue with Recalculate Name Fields is timing out | 2 | 1 |  | Priya |  | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | Rolled over | NA | Inprogress | Unable to reproduce this issue in lower environments. Team is still finding out the way to fix this issue.
5 | GGO 7.19.0 Sprint 2 [STRETCH] | Sathiyabharathi | GGO-14236 | Convert asp.net core | 5 | 5 |  | NA | [11 empty] | Rolled over |  | Inprogress

## GGO 7.19.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.19.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.19.0 Sprint 1 | Rajesh | GGO-14197 | issue with Template List not appearing on Project Creator | 3 | 3 | Rajesh | N/A | N/A | N/A | N/A | N/A | [7 empty] | Prod issue - Fixed and closed |  | Closed | Rajesh coordianted with Carlos and found the root cause.user deleted the project that is associated with project template
2 | GGO 7.19.0 Sprint 1 [STRETCH] | Sathiyabharathi | GGO-14204 | High & Medium - BDSA-2023-3833 - jQuery.Validation/1.19.5 & BDSA-2021-3651 - jQuery/3.5.1 | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7691 | 2024-07-16 | [6 empty] | Part of macroscope scanning - Rolled over |  | Inprogress
3 | GGO 7.19.0 Sprint 1 | Saranya | GGO-14308 | Update Replace Tokens Task version in GGO-VMSS Release Pipeline | 1 | 1 | Saranya | Priya | No | Sathiyabharathi | No | NA | [7 empty] | Version upgrade - Completed |  | Closed | Version of the task is deprecated in release Pipelines. So we upgraded task version 3 to 6 in GGO_VMSS and PAPI_VMSS pipelines.
4 | GGO 7.19.0 Sprint 1 | Saranya | PAPI-724 | Critical: Insecure Transport: Database - App.config: 5* | 1 | 1 | Saranya | Sathiyabharathi and Priya | No | Sathiyabharathi | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/7692 | 2024-07-16 | 2024-07-16 | Rajesh | No | Loan Troung | 2024-07-17 | No | Part of macroscope scanning - completed |  | Closed
5 | GGO 7.19.0 Sprint 1 [STRETCH] | Sathiyabharathi | GGO-14210 | High - Investigate Projects using Microsoft.AspNetCore* | 3 | [14 empty] | Part of macroscope scanning - completed |  | Inprogress
6 | GGO 7.19.0 Sprint 1 | Priya-QA | GGO-14185 | GGO 7.18.0 CRT Release & Regression Testing | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
7 | GGO 7.19.0 Sprint 1 | Priya-QA | PAPI-721 | PAPI 7.13.0 CRT Release & Regression testing | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
8 | GGO 7.19.0 Sprint 1 | Sathiyabharathi | GGO-14200 | Updated Aspose.Cells license* | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7665 | 2024-07-05 | 2024-07-08 | Rajesh | No Comments | Loan | 2024-07-08 | No Comments |  |  | Closed
9 | GGO 7.19.0 Sprint 1 | Saranya | GGO-13995 | Update AddSalesAndPayments call from OB to handle duplicate calls* | 2 | 2 | Sathiyabharathi | Priya | No | Sathiya | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7669 | 2024-07-04 | 2024-07-09 | Rajesh | No Comments | Loan | 2024-07-09 | No Comments | Part of infrastructure improvement - Completed |  | Closed
10 | GGO 7.19.0 Sprint 1 | Rajesh | GGO-14223 | Transfer Special instruction information to SF on Project creation before equipment order update* | 2 | 2 | Rajesh | Priya | [11 empty] | Salesforce update |  | Closed
11 | GGO 7.19.0 Sprint 1 | Rajesh | GGO-14201 | Throwing Error while uploading the new images when Azure Image setting enabled in DEV environment* | 1 | 1 | Rajesh | Priya | [11 empty] | Part of macroscope scanning - completed |  | Closed
12 | GGO 7.19.0 Sprint 1 | Priya-QA | PAPI-726 | High & Medium - CVE-2024-30105 System.Text.Json 8.0.0 * | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed

## GGO 7.19.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.18.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.18.0 Sprint 4 | Saranya | GGO-13995 | Update AddSalesAndPayments call from OB to handle duplicate calls* | 2 | 2 | Sathiyabharathi | Priya | No | Sathiya | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7669 | 2024-07-04 | 2024-07-09 | Rajesh | No Comments | Loan | 2024-07-09 | No Comments | Stretch story on Infrasturcture epic - Rolled over |  | Closed
2 | GGO 7.18.0 Sprint 4 | Sathiyabharathi | GGO-14200 | Updated Aspose.Cells license* | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7665 | 2024-07-05 | 2024-07-08 | Rajesh | No Comments | Loan | 2024-07-08 | No Comments |  |  | Closed
3 | GGO 7.18.0 Sprint 4 | Saranya/Sathiyabharathi | GGO-14004 | Error when attempting to edit users | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7663 | 2024-07-03 | 2024-07-04 | Rajesh | No Comments | Loan | 2024-07-04 | Replace "" with string.Empty | Part of infrastructure epic - Completed |  | Closed
4 | GGO 7.18.0 Sprint 4 | Sathiyabharathi/Rajesh | GGO-14187 | Analyze impact of .net update | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Loan |  |  |  |  | Closed | Investingation story
5 | GGO 7.18.0 Sprint 4 | Rajesh | GGO-14193 | console app udpate* | 2 | 2 | Rajesh | Sathiya | No | Sathiya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7658 | 2024-06-28 | 2024-06-29 | Sathiya | No Comments | Loan | 2024-06-29 | No Comments |  |  | Closed
6 | GGO 7.18.0 Sprint 4 | Saranya/Rajesh | GGO-13999 | Quartz Service - Replace hard coded Application Insights key* | 2 | 2
7 | GGO 7.18.0 Sprint 4 | Priya-QA | GGO-13947 | Medium - CVE-2022-30187 - Azure.Storage.Blobs/12.10.0 & 12.15.0 | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Part of macroscope scanning - Completed | NA | Closed
8 | GGO 7.18.0 Sprint 4 | Priya-QA | GGO-13982 | Console errors, blank output when printing shipping labels from Firefox | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Priority defect - Implemented successfully | NA | Closed
9 | GGO 7.18.0 Sprint 4 | Priya-QA | GGO-13993 | Supporter - Handle MaxRequestLength* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
10 | GGO 7.18.0 Sprint 4 | Priya-QA | GGO-14185 | GGO 7.18.0 CRT Release & Regression Testing | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
11 | GGO 7.18.0 Sprint 4 | Rajesh | GGO-14201 | Throwing Error while uploading the new images when Azure Image setting enabled in DEV environment* | 1 | 1 | Rajesh | Priya | [13 empty] | Closed
12 | GGO 7.18.0 Sprint 4 | Priya-QA | PAPI-721 | PAPI 7.13.0 CRT Release & Regression testing | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed

## GGO 7.18.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.18.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.18.0 Sprint 3 | Sathiyabharathi | GGO-14003 | Recalculate Name Fields times out every time | 3 | 3 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7628 | 2024-06-24 | 2024-06-24 | Rajesh | No | Loan Troung | 2024-06-24 | No | Bug fix - Implemented successfully | No | Closed | Mike Wall did the script level changes but the issue occued for the org which is having more supporters we updated the name fields by Batch processing and it worked as expected
2 | GGO 7.18.0 Sprint 3 | Rajesh/Sathiyabharathi | GGO-13655 | Enable CDC for GGO | 3 | 3 | Sathiyabharathi | N/A | N/A | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7629 | 2024-06-18 | 2024-06-24 | Rajesh | No | Loan Troung | 2024-06-24 | Fix typo/misspell privilege. | Rolled over | No | Closed | Completed the implementation and tested in local and Dev environment.verification in TST is pending.it is script changes.Onsite QA confirmation is pending.
3 | GGO 7.18.0 Sprint 3 | Priya-QA | PAPI-716 | PAPI 7.12.0 CRT Release | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
4 | GGO 7.18.0 Sprint 3 | Priya-QA | GGO-14062 | GGO 7.17.0 CRT Release and Regression Testing | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
5 | GGO 7.18.0 Sprint 3 | Priya-QA | GGO-13856 | Medium - Microsoft.IdentityModel.JsonWebTokens:5.5.0 & Microsoft.IdentityModel.JsonWebTokens:6.10.0* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
6 | GGO 7.18.0 Sprint 3 |  | GGO-13998 | Can not permanently delete projects from APAdmin | 2 | 2 |  | Priya | [13 empty] | Closed
7 | GGO 7.18.0 Sprint 3 | Priya-QA | GGO-14169 | MSR Certification test - iOS | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Swipe certification tests for iOS from Self testing portal | NA | Closed
8 | GGO 7.18.0 Sprint 3 | Saranya | PAPI-710 | Remove apConstants.PORTICO_TESTING_TOKEN* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
10 | GGO 7.18.0 Sprint 3 STRETCH | Sathiyabharathi | GGO-13947 | Medium - CVE-2022-30187 - Azure.Storage.Blobs/12.10.0 & 12.15.0* | 2 | 2 | Sathiyabharathi | Priya | No | N/A | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7641 | 2024-06-24 | [6 empty] | Macroscope scanning - Rolled over |  | Inprogress
11 | GGO 7.18.0 Sprint 3 | Saranya | GGO-14004 | Error when attempting to edit users | 2 | 2 |  | Priya | [11 empty] | Part of infrastructure epic - Rolled over |  | Inprogress | It is a production issue. Reproduced in local and it should be fixed

## GGO 7.18.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.18.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.18.0 Sprint 2 | Sathiyabharathi | GGO-13691 | Issue with ClearExpiredTrialUsers | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7599 | 2024-06-04 | 2024-06-05 | Rajesh | No Comments | Loan | 2024-06-05 | No Comments | Implemented successfully |  | Closed
2 | GGO 7.18.0 Sprint 2 | Sathiyabharathi | GGO-13994 | Update Capital letter tagging validation for Bidder and Supporter welcome SMS | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7592 | 2024-05-31 | 2024-06-01 | Rajesh | No Comments | Loan | 2024-06-01 | No Comments | Implemented successfully |  | Closed
3 | GGO 7.18.0 Sprint 2 | Sathiyabharathi | GGO-14037 | MSR Certification test - Manually Keyed Transaction (Purchase/Full Reversal-V1 01 & M1 03) | 5 | 4 | Sathiyabharathi | [12 empty] | This has been added a flag in ApAdmin to toggle the card present setting for GoTime>Storefront - Rolled over |  | Closed | Development has been completed. Client dependency (Portico side test cases required some additional params)
4 | GGO 7.18.0 Sprint 2 | Saranya | PAPI-714 | MSR Certification test - Manually Keyed Transaction (Purchase/Full Reversal-V1 01 & M1 03) | 3 | 2 | Saranya | Priya |  | Sathya | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/7613 | 2024-10-06 | 2024-12-06 | Rajesh |  | Loan Troung |  |  | This has also been rolled over |  | Closed | Development has been completed. Client dependency (Portico side test cases required some additional params)
5 | GGO 7.18.0 Sprint 2 | Saranya | PAPI-712 | High - jquery-ui-1-11-4/1.11.4 | 3 | 3 | Saranya | Priya |  | Rajesh | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/7598 | 2024-04-06 | 2024-04-06 | Rajesh | No Comments | Loan Troung | 2024-04-06 | No Comments | This is a part of macroscope - completed |  | Closed
6 | GGO 7.18.0 Sprint 2 | Priya-QA | PAPI-713 | Bluetooth Swipe Refund Transactions are Processed as Credit Sale* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
7 | GGO 7.18.0 Sprint 2 | Priya-QA | PAPI-716 | PAPI 7.12.0 CRT Release | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Deployement happened at the end of the sprint. Testing is still in progress
8 | GGO 7.18.0 Sprint 2 | Priya-QA | GGO-14062 | GGO 7.17.0 CRT Release and Regression Testing | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Deployement happened at the end of the sprint. Testing is still in progress

## GGO 7.18.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.18.0 Sprint 1 | Sathiyabharathi/Rajesh | GGO-13819 | Migrate Reporting to Quartz | 5 | 5 | Sathiyabharathi |  |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7553 | 2024-05-24 | [8 empty] | Closed | Development has been completed for this story and did local testing need to test in Dev environment is pending it requires client IT team support
2 | GGO 7.18.0 Sprint 1 | Sathiyabharathi | PAPI-711 | Critical - Secret Detected in Source/config/apCalcSolution/cacl | 2 | 2 | Sathiyabharathi |  |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7584 | 2024-05-28 | [8 empty] | Closed
3 | GGO 7.18.0 Sprint 1 | Rajesh | GGO-14039 | Legacy iOS - Login button for some reason is listed as Update* | 1 | 1 | Rajesh | [14 empty] | Closed
4 | GGO 7.18.0 Sprint 1 | Priya-QA | GGO-13985 | GGO 7.16.2 CRT Release & Regression Testing | 2 | 2 | Saranya | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
5 | GGO 7.18.0 Sprint 1 | Saranya | GGO-13954 | AGG-07 Report not pull LY numbers | 3 | [5 empty] | NA | NA | NA | NA | [7 empty] | Closed | Analyzed and found out the rootcause and updated required details in that story's comment section. That info is shared to Customer Service
6 | GGO 7.18.0 Sprint 1 | Priya-QA | GGO-14005 | Wrong Credit Card Method Type Assignment | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Testing is Blocked due to Certificate Issues.
7 | GGO 7.18.0 Sprint 1 | Saranya | GGO-14006 | Shipping label generation not working in CRT | 1 | 1 | NA | NA | NA | NA | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7567 | 2024-05-20 | 2024-05-21 | Rajesh | No | Mike Horihan | 2024-05-21 | it looks like we need to remove a hyphen from zip code before we check the length and truncate | No | No | Closed

## GGO 7.18.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.18.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.17.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.17.0 Sprint 4 | Rajesh | GGO-13981 | Remove Bluetooth Data logging from GoTime.AddCreditCard* | 1 | 1 | Rajesh | Priya | No | Sathiyabharathi | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7521 | [9 empty] | Closed
2 | GGO 7.17.0 Sprint 4 | Sathiyabharathi | GGO-13948 | Value uneditable when splitting a sale | 2 | 2 | Sathiyabharathi | Priya | No | Rajesh | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7516 | 2024-04-30 | 2024-05-01 | Rajesh | NA | Loan | 2024-05-01 | No | No | No | Closed
3 | GGO 7.17.0 Sprint 4 | Saranya | GGO-13939 | Thumbnail images are not scaled proportionately by Quartz Job | 3 | 2 | Saranya | Priya | No | Rajesh | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7527 | 2024-05-03 | 2024-05-07 | Rajesh | NA | Michael Wall | 2024-05-07 | No | No | No | Inprogress | Development completed and marked this one as Impediment. Client IT team has to do some configuration.
4 | GGO 7.17.0 Sprint 4 | Priya-QA | GGO-13985 | GGO 7.16.2 CRT Release & Regression Testing | 3 | 2 | Saranya | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Testing completed. Client IT team has to do some configuration to resolve Shipping label generation.
5 | GGO 7.17.0 Sprint 4 | Rajesh | GGO-13983 | Move GGO Websvcs to its own application | 5 | 3 | [15 empty] | Inprogress | Marked this one as Impediment. Client IT team has to do some configuration.

## GGO 7.17.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.17.0 Sprint 3 | Saranya Namachivayam | GGO-13760 | UPS Oauth Credentials | 3 | 3 | Saranya | Priya | No | Sathiya | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7498 | 2024-04-24 | 2024-04-24 | Rajesh | NO | Michael Wall | 2024-04-26 | No | NA | NA | Closed
2 | GGO 7.17.0 Sprint 3 | Priya-QA | GGO-13836 | API call for testing card readers | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.
3 | GGO 7.17.0 Sprint 3 | Saranya Namachivayam | GGO-13940 | Length Validation for Bidder and Supporter SMS | 2 | 2 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7501 | 2024-04-24 | 2024-04-24 | Rajesh | No | Michael Wall | 2024-04-24 | NA | NA | NA | Closed
4 | GGO 7.17.0 Sprint 3 | Priya-QA | PAPI-708 | Allow CardVerify Response Code 91 and store CardBrandTransactionID | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Mike Wall and we tested it and updated the comments in JIRA.
5 | GGO 7.17.0 Sprint 3 | Priya-QA | PAPI-702 | GGAM & All Client Apps: Test to determine if they are saving Tokens instead of encrypted CCN/PAN | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Mike Wall and we tested it and updated the comments in JIRA.
6 | GGO 7.17.0 Sprint 3 | Rajesh | GGO-13981 | Remove Bluetooth Data logging from GoTime.AddCreditCard* | 1 | 1 | Rajesh | Priya | No | Sathiyabharathi | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7521 | [9 empty] | Closed
7 | GGO 7.17.0 Sprint 3 | Sathiyabharathi | GGO-13948 | Value uneditable when splitting a sale | 2 | 1 | Sathiyabharathi | Priya | No | Rajesh | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7516 | 2024-04-30 | 2024-05-01 | Rajesh | NA | Loan | 2024-05-01 | No | No | No | Inprogress | We offshore tested and provided the comments. And Informed one existing issue. Nathan raised an new issue for the same and also testing is still pending from his side.
8 | GGO 7.17.0 Sprint 3 | Sathiyabharathi | GGO-13773 | create method for running pivotal and sfdc event sync simultaneously | 5 | 4 | Sathiyabharathi | N/A | No | Rajesh | No Comments | N/A | [9 empty] | Inprogress | salesforce team confirmed they can't do any changes

## GGO 7.17.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.17.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.17.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.17.0 Sprint 2 | Saranya Namachivayam | GGO-13877 | Tax rate in view packages cuts off decimal amounts of percentage | 3 | 3 | Saranya | Priya | No | SathiyaBharathi | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7453 | 2024-04-05 | 2024-04-08 | Rajesh | No | Loan Truong | 2024-04-08 | No | No | No | Closed
2 | GGO 7.17.0 Sprint 2 | Sathiyabharathi Paramasivam | GGO-13878 | Issues with convenience fee rounding | 3 | 3 | Sathiyabharathi | Rajesh | No | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7465 | 2024-04-10 | 2024-04-11 | Rajesh | No | Mike Wall | 2024-04-11 | No | No | No | Closed
3 | GGO 7.17.0 Sprint 2 | Saranya Namachivayam | GGO-13879 | Payments shown in GGO as Error actually processed | 3 | 3 | Saranya | Priya | No | Rajesh | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7469 | 2024-04-10 | 2024-04-11 | Rajesh | No | Loan Truong | 2024-04-11 | No | No | No | Closed
4 | GGO 7.17.0 Sprint 2 | Rajesh | GGO-13925 | Tax Rate on Create Sale inaccurate | 2 | 2 | Rajesh | Priya | No | SathiyaBharathi | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7466 | 2024-04-10 | 2024-04-10 | Loan | No | Mike Wall | 2024-04-10 | No | No | No | Closed
5 | GGO 7.17.0 Sprint 2 | Rajesh | GGO-13917 | ManageSalesAndPayments Nullable object must have a value | 2 | 2 | Rajesh | Priya | No | SathiyaBharathi | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7454 | 2024-04-05 | 2024-04-05 | Sathiyabharathi | No | Loan Truong | 2024-04-06 | No | No | No | Closed
6 | GGO 7.17.0 Sprint 2 | Priya-QA | PAPI-702 | GGAM & All Client Apps: Test to determine if they are saving Tokens instead of encrypted CCN/PAN | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Scope of the Story is only testing.And this is Fully Developed by Mike Wall and we tested and updated the comments in JIRA.card details need to verified with PAPI database, we don't have required permission for that only onsite QA need to be verified.
7 | GGO 7.17.0 Sprint 2 | Priya-QA | GGO-13834 | Tax Rate on Packages showing as 0 | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.
8 | GGO 7.17.0 Sprint 2 | Priya-QA | GGO-13938 | High - CVE-2024-0056 - System.Data.SqlClient/4.5.1* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.
9 | GGO 7.17.0 Sprint 2 | Priya-QA | GGO-13927 | High - Detector AzureStorage Found Result* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.
10 | GGO 7.17.0 Sprint 2 | Priya-QA | GGO-13857 | (High & Medium) - BDSA-2018-5195 - Newtonsoft.Json/9.0.1 & BDSA-2018-5195 - Newtonsoft.Json/12.0.2 & Newtonsoft.Json:11.0.2* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.

## GGO 7.17.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.17.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.17.0 Sprint 1 | Sathiyabharathi | GGO-13843 | High - MessagePack:1.7.3.4 ¦ MessagePack for C# and Unity Before Version 1.9.11 and 2.1.90 Has a Vulnerability | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7422 | 2024-03-27 | 2024-03-28 | Prabhu | No | Loan | 2024-03-28 | No | No | No | Closed
2 | GGO 7.17.0 Sprint 1 [Stretch] | Sathiyabharathi | GGO-13844 | create method for running pivotal and sfdc event sync simultaneously* | 3 | 3 | Sathiyabharathi | N/A | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7442 | 2024-04-02 |  | Rajesh | No | [5 empty] | Inprogress | Development has been completed , require salesforce team support to test
3 | GGO 7.17.0 Sprint 1 | Saranya Namachivayam | GGO-13854 | Critical - Insecure Transport: Database - App.config: 5 | 3 | 3 | Saranya | Priya | No | SathiyaBharathi | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7439 | 2024-04-01 | 2024-04-01 | Rajesh | No | Mike Wall | 2024-04-01 | No | No | No | Closed
4 | GGO 7.17.0 Sprint 1 | Saranya Namachivayam / Mike Wall | PAPI-702 | GGAM & All Client Apps: Test to determine if they are saving Tokens instead of encrypted CCN/PAN | 2 | 2 | Saranya | Priya, Saranya | No | Rajesh | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7437 | 2024-03-30 | 2024-03-30 | Loan Truong | No | Rajesh | 2024-04-03 | No | No | No | Closed | Scope of the Story is only testing. We are doing testing support to onsite resource
5 | GGO 7.17.0 Sprint 1 | Priya-QA | GGO-13816 | GGO 7.16.0 CRT Release & Regression Testing | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
6 | GGO 7.17.0 Sprint 1 | Priya-QA | GGO-13785 | Go Time Card Entry update for old readers | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.(Fully Developed by Loan and we tested and updated the comments in JIRA)

## GGO 7.17.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.17.0 Sprint 1 | GGO-13893 | Saranya | Defect | CancelledDate' from SF always saved as 1969-12-31 in GGO database | Significant | Internal | Closed | Development

## GGO 7.16.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.16.0 Sprint 4 | Saranya Namachivayam | GGO-13815 | When importing Online Registrations & Purchases, Sale/Payment Association Status will be Partial | 5 | 5 | Saranya | Priya | No | SathiyaBharathi | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7370 | 2024-03-09 | 2024-03-08 | Rajesh | No | Mike Wall | 2024-03-12 | No | The bug was fixed successfully | No | Closed
2 | GGO 7.16.0 Sprint 4 | Sathiyabharathi | GGO-13801 | Supporter Details household behavior | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7366 | 2024-03-08 | 2024-03-08 | Rajesh | No | Loan | 2024-03-08 | No | Implemented as per AC | No | Closed
3 | GGO 7.16.0 Sprint 4 | Sathiyabharathi | GGO-13773 | create method for running pivotal and sfdc event sync simultaneously* | 5 | 5 | [13 empty] | Got some issue with GGOApi user for transfer of data from GGO to SF - Rolled over |  | Inprogress | Development has been completed , require salesforce team support to test
4 | GGO 7.16.0 Sprint 4 | Saranya Namachivayam | GGO-13738 | Coordinate with IT to add Bluetooth hardware column in SF | 1 | 1 | Saranya | Priya | No | SathiyaBharathi | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7364 | 2024-03-07 | 2024-03-14 | Rajesh | No | Mike Wall | 2024-03-14 | No | Implemented as per AC | No | Closed
5 | GGO 7.16.0 Sprint 4 | Saranya Namachivayam | GGO-13796 | TST verification for SFDC Enhancements | 3 |  | Saranya | Priya | No | SathiyaBharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7383 | 2024-03-13 |  | Rajesh |  |  |  |  | In Progress - Rolled over |  | Inprogress
6 | GGO 7.16.0 Sprint 4 | Priya-QA | GGO-13816 | GGO 7.16.0 CRT Release & Regression Testing | 3 | 3 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Rolled Over | NA | Inprogress
6 | GGO 7.16.0 Sprint 4 | Priya-QA | GGO-13737 | GGO Storefront handle Mobile Transaction card data for swipe | 3 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Implemented as per AC | NA | Inprogress | This story was developed by Loan and I have tested this and updated my comments

## GGO 7.16.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.16.0 Sprint 4 | GGO-13837 | Saranya | Defect | Package you have chosen is not a multisale package and it is already sold. Getting error while trying to add another sale of this package | Significant | Internal | Closed | Development
2 | GGO 7.16.0 Sprint 4 | GGO-13838 | Saranya | Defect | Supporter Grid display issues in Fundraiser-only projects | Significant | Internal | Closed | Development
3 | GGO 7.16.0 Sprint 4 | GGO-13835 | Loan | Defect | GoTime-Storefront - Web- Getting Error while making the payment through Cash | Significant | Internal | Closed | Development

## GGO 7.16.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.16.0 Sprint 3 | SathiyaBharathi | GGO-13733 | Go time checkin update | 3 | 3 | Sathiyabharathi | Saranya,Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7344 | 2024-02-26 | 2024-02-26 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-02-27 | No Comments | Implemented as per AC, no issues found. |  | Closed
2 | GGO 7.16.0 Sprint 3 | SathiyaBharathi / Saranya Namachivayam | GGO-13699 | Go time checkout update | 5 | 5 | Sathiyabharathi/Saranya | Saranya,Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7345 | 2024-03-01 | 2024-03-01 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-03-01 | No Comments | Implemented as per AC. |  | Closed
3 | GGO 7.16.0 Sprint 3 | Saranya | GGO-13807 | Apply Fees Logic Update | 5 | 5 | Sathiyabharathi | Sathiyabharathi,Priya |  | Sathiyabharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7347 | 2024-02-28 | 2024-02-28 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-02-29 | No Comments | No comments |  | Closed
4 | GGO 7.16.0 Sprint 3 | Saranya/SathiyaBharathi | GGO-13801 | Supporter Details household behavior | 3 | 3 | Sathiyabharathi/Saranya | Saranya,Sathiyabharathi,Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7352 | 2024-03-01 | 2024-03-02 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-03-02 | No Comments | Found a new defect. Still in progress |  | Inprogress
5 | GGO 7.16.0 Sprint 3 | Rajesh | GGO-13744 | Convenience Fee Enabled Setting Persistence across templates and copied projects | 2 | 2 | Rajesh | Priya |  | Sathiyabharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7346 | 2024-02-27 | 2024-02-27 | SathiyaBharathi | No Comments | Loan Truong | 2024-02-28 | No Comments | Implemented as per AC. |  | Closed
6 | GGO 7.16.0 Sprint 3 | Saranya | GGO-13738 | Coordinate with IT to add Bluetooth hardware column in SF* | 3 |  | Saranya | Sathiyabharathi |  | Sathiyabharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7364 | 2024-03-07 |  | Rajesh |  |  |  |  | Still in progress |  | Inprogress | Development is completed. Testing is pending. It requires IT team support
7 | GGO 7.16.0 Sprint 3 | SathiyaBharathi | GGO-13824 | When updating equipment orders, it will only update one card reader field at a time.* | 3 | 3 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7358 | 2024-03-05 | 2024-03-05 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-03-05 | No Comments | This bug was fixed |  | Closed
8 | GGO 7.16.0 Sprint 3 | Priya-QA | GGO-13703 | Bid-18 Update | 2 | 2 | Saranya | Priya | No Defects | Sathiyabharathi,Rajesh | No | NA | NA | NA | NA | No Comments | NA | NA | NA | No comments | NA | Closed
9 | GGO 7.16.0 Sprint 4 | Rajesh | GGO-13820 | Salesforce Support* | 1 | 1 | Rajesh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No comments | N/A | Closed

## GGO 7.16.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.16.0 | Saranya Namachivayam / Rajesh | GGO-13612 | Update Redis Cache Clearing on Release | 5 | 5 |  | SathiyaBharathi,Priya |  | SathiyaBharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7317 | 2024-02-15 | 2024-02-16 | Rajesh |  | Loan Truong | 2024-02-16 |  | No comments |  | Closed
2 | GGO 7.16.0 | SathiyaBharathi / Saranya Namachivayam | GGO-13703 | Bid-18 Update | 3 | 2 |  | Priya |  | Saranya | [9 empty] | The column header was occupying additional column for the report BID-18, however it’s look like an existing issue. |  | Inprogress
3 | GGO 7.16.0 | Priya-QA | GGO-13696 | Add option to supporter record | 1 | 1 | Sathiyabharathi/Rajesh | Saranya,Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7316 | 2024-02-14 | 2024-02-15 | Rajesh | Move constant variable to common file convenienceFee.cs | Loan Truong | 2024-02-15 | No Comments | Implemented as per AC | No Comments | Closed
4 | GGO 7.16.0 | SathiyaBharathi | GGO-13701 | Charge Batch Update | 5 | 5 | Sathiyabharathi | Saranya,Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7306 | 2024-02-12 | 2024-02-15 | Rajesh |  | Loan Truong | 2024-02-15 | move methods to common place | One Defect Sub-task has been created to update the window height based on AC. It was fixed and the story was completed. | No Comments | Closed
5 | GGO 7.16.0 | SathiyaBharathi/Rajesh | GGO-13795 | Manually added Convenience Fee sales not counted as 'Convenience Fee Applied' | 2 | 2 | Sathiyabharathi/Rajesh | Saranya,Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7316 | 2024-02-14 | 2024-02-15 | Rajesh | No Comments | Loan Truong | 2024-02-15 | No Comments | No Comments | No Comments | Closed | Parent story-GGO-13702
6 | GGO 7.16.0 | SathiyaBharathi | GGO-13771 | Update label on supporter record* | 2 | 2 | Sathiyabharathi | N/A | N/A | N/A | N/A | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7330 | 2024-02-21 | 2024-02-21 | Rajesh | Move variable declaration to common file convenienceFee.cs | Loan Truong | 2024-02-21 | No Comments | Implemented as per AC | No Comments | Closed
7 | GGO 7.16.0 | Priya- QA | GGO-13702 | Supporter Advanced Search update | 3 | 3 | Sathiyabharathi | Priya | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Implemented as per AC | N/A | Closed | Testing completed in this sprint
8 | GGO 7.16.0 | Priya- QA | GGO-13783 | Go Time Card Entry Interface for new readers | 2 | 2 | Rajesh | Priya | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Implemented as per AC | N/A | Closed | Worked and Tested with the Mobile team to check the new popup doesn't affect any existing flow.

## GGO 7.16.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.16.0 Sprint 3 | GGO-13821 | Saranya | Defect | Manually created negative Conv fee sale is displayed in both Total sales and Conv fee applied and the total due is calculated based on these two values... | Significant | Internal | Closed | Development
2 | GGO 7.16.0 Sprint 3 | GGO-13825 | Sathiya | Defect | Negative convenience amount is calculated in the report Bid- 18 if the supporter has a negative due and covering conv fee is enabled | Significant | Internal | Closed | Development
3 | GGO 7.16.0 Sprint 3 | GGO-13828 | Sathiya | Defect | Total Due Amounts in Checkout VS Manage Sales and Payments don't always match | Significant | Internal | Inprogress | Development

## GGO 7.16.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.16.0 | GGO-13795 | Sathiyabharathi | Defect | Manually added Convenience Fee sales not counted as 'Convenience Fee Applied' | Significant | Internal | Closed | Development
2 | GGO 7.16.0 | /GGO-13804 | Sathiyabharathi | Defect | Charge Batch Grid height not limited to 400px | Minor | Internal | Closed | Development

## GGO 7.16.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.16.0 | Saranya | GGO-13143 | Send Group to OB for bidders | 2 | 2 | Saranya | Priya | No Comments | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7229 | 2024-01-18 | 20-Jan-0202 | Rajesh | No Comments | Mike Wall,Loan | 2024-01-20 | No Comments | No Comments | No Comments | Closed
2 | GGO 7.16.0 | Saranya | GGO-13735 | Update Legacy Go Time Mobile Reader Options image | 3 | 3 | Saranya | Sathiyabharathi and Priya | No Comments | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7279 | 2024-02-02 | 2024-02-02 | Rajesh | No Comments | Mike Wall,Loan | 2024-01-20 | No Comments | No Comments | No Comments | Closed
3 | GGO 7.16.0 | Priya-QA | GGO-13740 | GGO 7.15.0 CRT Release & Regression Testing | 2 | 2 | Priya | Priya | No Defects | Rajesh | No | NA | NA | NA | NA | No Comments | NA | NA | NA | NA | NA | Closed
4 | GGO 7.16.0 | Rajesh | GGO-13770 | AGG-07 Reports missing from PRD | 2 | 2 | Rajesh | Rajesh and Priya | No Comments | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7264 | 2024-01-28 | 2024-01-31 | Mike Wall,Loan | No Comments | NA | NA | NA | No Comments | No Comments | Closed
5 | GGO 7.16.0 | Sathiyabharathi | GGO-13696 | Add option to supporter record | 3 | 3 | Sathiyabharathi | Priya | No Comments | Rajesh | create new file in Library project and move the convenience fee releated changes to that file | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7285 | 2024-02-06 | 2024-02-06 | Rajesh | No Comments | Mike Wall | 2024-02-02 | No Comments | No Comments | No Comments | Inprogress
6 | GGO 7.16.0 | Saranya | GGO-13736 | Hide card reader popup for mobile pilot users | 3 | 3 | Saranya | Priya | No Comments | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7273 | 2024-02-01 | 2024-02-02 | Rajesh | No Comments | Mike Wall,Loan | 2024-02-02 | No Comments | No Comments | No Comments | Closed
7 | GGO 7.16.0 | Rajesh | GGO-13774 | Escalation Support | 2 | 2 | Rajesh | Rajesh | NA | Rajesh | No | NA | NA | NA | Rajesh | No Comments | NA | NA | NA | NA | NA | Closed
8 | GGO 7.16.0 | Sathiyabharathi / Saranya | GGO-13702 | Supporter Advanced Search Update* | 3 | 3 | Sathiyabharathi | Saranya and Priya | No Comments | Rajesh | No |  |  |  | Rajesh | No LLBLGen file changes should be made manually. You need to run LLBLGen using powershell tool. If you have problem with license, let me know. | [5 empty] | Inprogress

## GGO 7.16.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.16.0 Sprint 1 | https://greatergiving.atlassian.net/browse/GGO-13775 | Saranya Namachivayam | Defect | GGO code card entry dialogue is still showing behind the new Popup from GGO Mobile | Significant | Internal | Closed | Development
2 | GGO 7.16.0 Sprint 1 | https://greatergiving.atlassian.net/browse/GGO-13780 | Sathiya | Defect | Negative values are getting updated under Total sales when we have deleted the normal sale and convenience sale from the checkout | Significant | Internal | Inprogress | Development

## GGO 7.15.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.15.0 Sprint 4 | Saranya Namachivayam/Sathiyabharathi Paramasivam | GGO-13143 | Send Group to OB for bidders | 3 | 3 | Completed | Rajesh | No comments | Rajesh | No comments | https://greatergiving.visualstudio .com/Greater%20Giving/_git/ GGO/pullrequest/7252 | 25-01-2024 | 25-01-2024 | Rajesh | No Comments | Michael Wall | 25-01-2024 | No Comments | No Comments | No Comments | Closed | Took more time to cover all scenario's, failed with 1 scenario at the end of sprint, so it got carry forwarded to next sprint
2 | Mobile Sprint 4 | Saranya Namachivayam | GGOM-832 | user gets error if users login is shared in multiple orgs | 1 | 1 | Completed | Rajesh | No comments | Rajesh | No comments | https://greatergiving.visualstudio. com/Greater%20Giving/_git/ GGO/pullrequest/7224 | 17-01-2024 | 18-01-2024 | Rajesh | No Comments | Michael Wall | 18-01-2024 | No Comments | No Comments | No Comments | Closed
3 | GGO 7.15.0 Sprint 4 | Sathiyabharathi Paramasivam | GGO-13695 | Add Conv fee flag to backend of supporter | 3 | 3 | Completed | Rajesh | No comments | Rajesh | No comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7231 | 19-01-2024 | 19-01-2024 | Rajesh | No Comments | Loan,Mike Wall,Mike Horihan | 19-01-2024 | why we choose varchar(250) for the Email column | No Comments | No Comments | Closed | Changed [EmailAddress] column datatype and length as([nvarchar] (127) NULL)
4 | GGO 7.15.0 Sprint 4 | Sathiyabharathi Paramasivam | GGO-13756 | CRT Regression Issue-AGG-23X Report loading issue | 2 | 2 | Completed | Rajesh | No comments | Rajesh | No comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7248 | 23-01-2024 | 23-01-2024 | Rajesh | No Comments | Loan | 23-01-2024 | No Comments | No Comments | we frequently faced AsyncPageTime out issue while Running AGG-03 ,AGG-25, AGG-23x reports.PO decided to revert the changes . | Closed | Reverted SQLCLR 7 story changes, we frequently faced AsyncPageTime out issue while Running AGG-03 ,AGG-25, AGG-23x reports.PO decided to revert the changes .
5 | GGO 7.15.0 Sprint 4 | Saranya Namachivayam | GGO-13742 | Project Website Creation error for returning clients* | 2 | 2 | Completed | Rajesh | No comments | Rajesh | No comments |  |  |  | Rajesh | No Comments | MikeH | Migration Script Updated in ChangeLog | No Comments | No Comments | No Comments | Closed
6 | GGO 7.15.0 Sprint 4 | Rajesh | GGO-13752 | Set IsBluetoothPilot Flag in browser cookies for Legacy Mobile App* | 1 | 1 | Completed | Rajesh | No comments | Loan | No comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7216 | 13-01-2024 | 13-01-202 | Loan | No Comments | Loan | 13-01-2024 | No Comments | No Comments | No Comments | Closed
7 | GGO 7.15.0 Sprint 4 | Rajesh | GGO-13753 | Set isBluetoothFlag in Switch Project functionality for Legacy Mobile App | 1 | 1 | Completed | Rajesh | No comments | Loan, MikeW | No |  |  |  | Rajesh | No Comments | MikeW | 18-01-2024 | No Comments | No Comments | No Comments | Closed
| GGO 7.15.0 Sprint 4 | Priya-QA | GGO-13462 | Identify and update the non-data table 4 | 2 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Testing completed on this sprint
9 | GGO 7.15.0 Sprint 4 | Priya-QA | GGO-13694 | Project Builder Updates | 2 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Testing completed on this sprint

## GGO 7.15.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.15.0 Sprint 4 | GGO-13758 | Saranya Namachivayam | Defect | Adding new admissions from the existing supporter and Save it- Getting "An Error has occurred" | Significant | Internal | Closed | Development

## Checklist (hidden)
Code Review Comments received from Client for 2.5 Sprint |  | S No | Execution Steps | Status
1 | index.tsx /AugustWeb/Features/ContactMaintenance/Components/index.tsx Search doesn't work on the details page. Please remove the search component from the header. | 1 | Code conflict | FALSE
2 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs If the admin doesn't set up any of the new options, then the system rejects every registration. | 2 | Coding Standard | FALSE
3 | PickEnrollmentPlanView.tsx /ParentWeb/ClientApp/src/pages/Registration/PickEnrollmentPlanView.tsx This should be filtered before this ternary statement so the "No enrollment plans" message could be shown if all plans are at capacity and closed. | 3 | Existing Functionality | FALSE
4 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs Could we add a TermEnrollmentPlanId query parameter and query for it directly instead of pulling all the plans for the term? | 4 | Acceptance Criteria coverage | FALSE
|  | 5 | Code execute | FALSE
|  | 6 | Code Performance | FALSE
|  | 7 | Code cleanup | FALSE
|  | 8 | Understandable code comments | FALSE

## Details
Root Cause category
Enhancements
Existing_Issues
Requirements
QA
Design
Documentation
Development
Project_Management
Environment_Related

## Settings
Refinement
Ready
Being Developed
Peer Review
Verify
Ready for testing
Being Tested
Completed

## ExportData
1 | GGO Donor Wave | 46044 | 46058 | GGO 7.21.0 Sprint 4 | SathyaBharathi/Rajesh Kannan | GGO-14325 | Rewrite and Update BID-06 (Invoice) using RDLC Part 1 | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan/Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8075 | 45643 | 45643 | Rajesh |  | Michael Wall | 45643 |  |  |  | Tested in the Dev environment - Informed few issues to the Team.12/17/202410:48 PM. Tested in the TST Env- 12/18/2024 7:20 PM.
2 | GGO Donor Wave | 46044 | 46058 | GGO 7.21.0 Sprint 4 | SathyaBharathi/Rajesh Kannan | GGO-14426 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 2 (Sales Only) | Completed | 5 | 5 |  |  | Priya |  | Rajesh Kannan | [11 empty] | Rolling over remaining testing to this story - GGO-14427
3 | GGO Donor Wave | 46044 | 46058 | GGO 7.21.0 Sprint 4 | Saranya | GGO-14418 | Modify GGO SFDC Webservice | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8079 | 45639 | 45643 | Rajesh |  | Michael Wall | 45643 |  |  |  | Coordinated with saranya and Tested in Local -12/16/2024 8:56 PM.
4 | GGO Donor Wave | 46044 | 46058 | GGO 7.21.0 Sprint 4 | Saranya | GGO-14445 | Project Website - Remove Deprecated Share Functionality | Completed | 2 | 2 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8080 | 45639 | 45642 | Rajesh |  | Loan Troung | 45642 |  |  |  | Tested in the Dev environment - 12/16/2024 8:57 PM. Tested in the TST env. Working well. 12/17/2024 10:47 PM
5 | GGO Donor Wave | 46044 | 46058 | GGO 7.21.0 Sprint 4 | Rajesh Kannan | GGO-14419 | Duplicate EventXcode updated when GGO sync with SF | Completed | 3 | 3 |  |  | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8092 | 45653 | 45656 | Rajesh |  | Michael Wall | 45656
6 | GGO Donor Wave | 46044 | 46058 | GGO 7.21.0 Sprint 4 | Saranya/Rajesh Kannan | GGO-14375 | Pop-up warning on batch process with unapplied convenience fees | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8096 | 45657 | 45657 | Rajesh |  | Michael Wall | 45657 |  |  |  | Tested in the TST env. Working well 1/3/2025 8:13 PM
7 | GGO Donor Wave | 46044 | 46058 | GGO 7.21.0 Sprint 4 | Sathiyabharathi/Rajesh Kannan | GGO-14427 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 3 (Sales & Payments) | Being Tested | 5 | 5 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8097 | 45657 | 37621 | Rajesh |  | Michael Wall | 45657 |  |  |  | Tested in the TST env. And it is In Progress 1/3/2025 8:13 PM. Tested in the Dev as well as in TST Env- 8:28 PM 1/6/2025. Testing is still in progress. 1/8/2025 8:10 PM
1 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 2 | Saranya | GGO-12487 | Adjust Admission Functionality - sale details | Completed | 5 | 5 | 23 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8184 | 45687 | 45687 | Rajesh |  | Loan Troung | 45687 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025. Priya - Testing in dev env is in progress 4:48 PM 1/30/2025
2 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 2 | Sathiyabharathi | GGO-14503 | Adjust Admission Functionality - add/remove | Ready for Testing | 5 | 5 |  | Sathiya |  |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8189 | 45691 | 45692 | Rajesh |  | Loan Troung | 45692 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025 Deletion of attendee row if supporter chosen showed the popup confirmation, working on Adjusted amount calculation [1/29/2025] Did developer testing in TST environment no issues found [02/04/2025] Onsite QA testing pending since [02/04/2025]
3 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 2 | RajeshKannan | GGO-14514 | Update remaining admission allocated attendee count in GGO webserivce to OP | Completed | 1 | 1 |  | Rajesh | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8174 | 45681 | 45681 | Rajesh |  | Loan Troung | 45681 |  |  |  | Completed Testing in the TST env. 8:31 PM 1/29/2025
4 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 2 | Sathiyabharathi | GGO-14477 | BID-06 Header Settings Update | Completed | 2 | 2 |  | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8170 | 45680 | 45681 | Rajesh |  | Michael Wall | 45681 |  | This is QA automation which comes under Infrastructure improvement |  | Picked on 01/22/2025.Development in progress 23/01/2025 Deployed in dev and completed developer testing. Priya - Completed Testing in Dev. Working well 5:07 PM 1/24/2025. Completed Testing in TST 5:02 PM 1/27/2025
5 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 2 | RajeshKannan | GGO-14450 | GGO Image Thumbnail Creation error | Ready for Testing | 2 | 2 |  | Rajesh | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8197 | 45692 | 45693 | Rajesh |  | Loan Troung | 45693 |  |  |  | It is completed and given for testing 3 days prior to Sprint end, Offshore QA doesn't got any access to test in TST, only MikeH and Nate got access to test it.
6 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 2 | Priya-QA | GGO-14511 | GoTime SF Tap card generate Null Ref Error | Completed | 2 | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Priya- Did one round of Payment Regression Testing since we dont have access to Tap cards. 5:01 PM 1/27/2025
7 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 2 | Priya-QA | PAPI-794 | Add Tag 9F6E to List of Acceptable Tags in ParseC3XJsonDataToTLV* | Completed | 1` | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Priya- Did one round of Payment Regression Testing since we dont have access to Tap cards. 8:00 PM1/28/2025
1 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14503 | Adjust Admission Functionality - add/remove | Completed | 2 | 2 | 23 | Sathiya | Priya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8189 | 45691 | 45692 | Rajesh |  | Loan Troung | 45692 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025 Deletion of attendee row if supporter chosen showed the popup confirmation, working on Adjusted amount calculation [1/29/2025] Did developer testing in dev environment no issues found [02/05/2025] Automation is pending[02/19/2025]. Nathan Closed the Automation Ticket
2 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 3 | RajeshKannan | GGO-14450 | GGO Image Thumbnail Creation error | Completed | 2 | 2 | 2 | Rajesh | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8197 | 45692 | 45693 | Rajesh |  | Loan Troung | 45693
3 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 3 | Rajesh/Saranya | GGO-14529 | Invoice Timeout Fix | Completed | 1 | 1 | 7.5 |  | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8204
4 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 3 | Saranya | GGO-14070 | Rewrite BID-15 to a new report toolset | Peer Review | 5 | 5 | 84.5 |  | Priya | [13 empty] | Test Case Prepartion is done 5:48 PM 2/7/2025. Tested in dev env. 7:30 PM 2/19/2025 Carry forwarded to next sprint : Saranya worked on the RDLC report and own the full task took some time for her to learn and implement
6 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14530 | Image Manager Fix | Completed | 1 | 1 | 25.5 | Rajesh | Priya |  | Priya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8218 | 45695 | 45695 | Rajesh |  | Loan Troung | 45695 |  |  |  | 02/08/2025: This issue was Identitfied by CS and this is not a development or QA miss, this happens because the Javascript [DOM] component was deprecated and the code need to be updated accordingly.
7 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14504 | Adjust Admission Functionality - graph updates | Ready for Testing | 5 | 5 | 60 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8228 | 45700 | 45706 | Rajesh |  | Loan Troung | 45706 | GO PRINT N'Drop Procedure [dbo].[sp_GetAdjustedAdmissionCount]' GO IF OBJECT_ID('[dbo].[sp_GetAdjustedAdmissionCount]') IS NOT NULL DROP PROCEDURE [dbo].[sp_GetAdjustedAdmissionCount]; GO It is not necessary, but we do usually add PRINT statement. |  |  | Tested in the Dev env. 5:09 PM 2/17/2025. Completed testing the TST env. 8:27 PM 2/18/2025 Onsite QA Logged bug on last day of sprint, we fixed it deployed before sprint prep, QA didn't get time to complete it.
8 | GGO Donor Wave | 46044 | 46058 | GGO 7.22.0 Sprint 3 | Priya-QA | GGO-14071 | Rewrite BID-19 to a new report toolset | Completed | 1 | 1 | 22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Test Case Prepartion is done 5:48 PM 2/7/2025. Testing in dev env. 8:41 PM 2/13/2025. Completed Testing in the TST env.
1 | GGO Donor Wave | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Saranya | GGO-14070 | Rewrite BID-15 to a new report toolset | Completed | 2 | 2 | 15.5 | Saranya | Priya | Alignment Issues/ Design Issues | [12 empty] | Test Case Prepartion is done 5:48 PM 2/7/2025. Tested in dev env. 7:30 PM 2/19/2025 Carry forwarded to next sprint : Saranya worked on the RDLC report and own the full task took some time for her to learn and implement. Bug GGO-14564 was created on 20/02/2025. Pull request created on 20/02/2025 and Closed on 21 February 2025 at 03:41
3 | GGO Donor Wave | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Sathiyabharathi | GGO-14547 | Edit Package Image Display Issue | Completed | 2 | 1 | 9 | Sathiya | Priya | NA |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8265 | 45709 |  | Rajesh | [6 empty] | Peer testing N/A for this bug it's required DB update. Priya: Verified in TST env.8:56 PM 2/24/2025
4 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Sathiyabharathi | GGO-14545 | Move the Azure Storage Settings in to Redis/IIS cache to avoid multiple DB calls | Completed | 2 | 3 | 40.25 | Sathiya | Priya | NA |  |  | http://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8272 | 45714 | 45714 | Rajesh | [6 empty] | [02/25/2025]-Created draft PR. Dev Testing in Progress. Tested in the TST env. Working well 7:47 PM2/27/2025
5 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Loan/Sathiyabharathi | GGO-14510 | High - BDSA-2024-4305 - bootstrap/4.6.2 | Being Tested | 5 | 3 | 75.25 | Sathiya |  | NA | [7 empty] | Loan Troung | 45714 |  |  |  | This story is developed by an onsite developer (Loan). After a Bootstrap version update, we’re facing some UI issues. Offshore developer (Sathiya) is assisting with that. Tested this in the TST env. Raised a bug under this. 5:51 PM 3/5/2025. Nathan Comments: Got some Errors in Automation. So It require automation code updates or app code fix.
6 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Saranya | GGO-14567 | Bypass Verify on 3X Storefront swipe | Completed | 2 | 2 | 34.5 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8281 | 45716 | 45720 | Rajesh |  | Loan Troung | 45721 |  |  |  | We dont have access to test EMV transactions. Did Payment Regression Testing using manual cards. Since Portico is down, we were not able to verify swipe transactions. Portico is UP on last day of sprint, Verified and Completed.
7 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Saranya | PAPI-811 | Bypass Verify on 3X Storefront swipe | Completed | 2 | 2 | 35.75 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8282 | 45716 | 45720 | Rajesh |  | Loan Troung | 45721 |  |  |  | We dont have access to test EMV transactions. Did Payment Regression Testing using manual cards. Since Portico is down, we were not able to verify swipe transactions. Portico is UP on last day of sprint, Verified and Completed.
8 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4-[Stretch] | Saranya | GGO-14535 | OPStats.GetRsvpCount not being cached correctly | Being Developed | 2 | 2 | 31 | [15 empty] | Stretch story taken 1 day before sprint end, so got carry forwarded to next sprint.
8 | GGO Donor Wave | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14546 | Automation Maintenance | Completed | 1 | 1 | 10 | [15 empty] | Coding is still in progress 8:55 PM 2/24/2025. Completed almost all the files. Execution is in Progress 8:33 PM 3/3/2025 Execution Completed on 3/5/2025.
9 | GGO Donor Wave | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Priya-QA | PAPI-797 | Ensure Credit Card Last 4 is stored in Payers and Payments tables for 3X tap/dip | Completed | 1 | 1 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only. Testing blocked (since yesterday) by partial Portico outage – cannot generate successful EMV transactions.
10 | GGO Donor Wave | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14566 | 25 Feb GGO 7.22.0 CRT Release & Regression Testing | Completed | 1 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | CRT Regression Testing is in Progress. 8:31 PM 3/3/2025.Partially blocked by Portico transaction failures in CRT.Completed Remaining scenario from our end
11 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14509 | Critical - Privacy Violation | Completed | 1 | 1 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in TST env. 8:31 PM 3/3/2025
1 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Rajesh | GGO-14535 | OPStats.GetRsvpCount not being cached correctly | Completed | 2 | 2 | 22 | Rajesh | Priya | NIL |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8288 | 45722 | 45723 | Rajesh |  | Michael Wall | 45723 |  |  |  | Completed Testing 3/11/2025 7:40 PM
2 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Rajesh | PAPI-822 | Handle SystemError Response From Portico SOAP Call | Completed | 2 | 2 | 2.25 | Rajesh |  |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8291 | 45723 | 45724 | Rajesh |  | Michael Wall, Loan Troung | 45724
3 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | SathiyaBharathi | GGO-13890 | Rewrite and Update SLS-10 | Completed | 3 | 3 | 45.5 | Sathiya/Rajesh | Priya | NIL | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8300 | 45727 | 45727 | Rajesh |  | Michael Wall | 45727 |  |  |  | Completed Testing in the TST env 8:00 PM 3/12/2025
4 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Saranya | PAPI-816 | Investigate Check-In not storing Card or Payer record for Go-Time Enter Card on EMV TAP when flag Portico_TestingNeverSendToProcessor=true | Completed | 2 | 2 | 14.25 | Saranya | Sathiya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8293 | 45723 | 45726 | Rajesh |  | Michael Wall | 45727 |  |  |  | Completed Testing in the TST env. 3/11/2025 7:40 PM
5 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Rajesh | GGO-14576 | Investigate Card Verify Failure Message | Completed | 2 | 2 | 2.25 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8292 | 45723 | 45724 | Rajesh |  | Michael Wall, Loan Troung | 45724
6 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Saranya | PAPI-809 | HIGH - jQuery/2.0.0 in PapiAdmin | Completed | 2 | 2 | 33.75 | Saranya | Rajesh |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8314 | 45730 | 45730 | Rajesh |  | Michael Wall, Loan Troung | 45730 |  |  |  | Did one round of Payment Regression Testing in the TST env
7 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Rajesh | PAPI-808 | HIGH - CVE-2024-43485 System.Text.Json 8.0.4 | Completed | 2 | 2 | 11.75 | Rajesh | Saranya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8312 | 45729 | 45730 | Rajesh |  | Michael Wall, Loan Troung | 45730 |  |  |  | Did one round of Payment Regression Testing in the TST env
8 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1-[Stretch] | SathiyaBharathi/ Saranya/Rajesh | GGO-14586 | At Least 3 Card Brands Can Have Up to 19 Digit PAN* | Ready For Testing | 5 | 5 | 72 | Saranya/Rajesh | Priya | NIL | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8320 | 45734 | 45735 | Rajesh |  | Michael Wall | 45735 |  |  |  | Development has been completed and partially completed testing in dev environment[03/19/2025]. Did one round of payment Regression for this story in the TST env.
9 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1-[Stretch] | SathiyaBharathi/Rajesh | PAPI-829 | At Least 3 Card Brands Can Have Up to 19 Digit PAN* | Ready For Testing | 2 | 2 | 11.5 | Sathiya/Rajesh | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8318 | 45734 | 45735 | Rajesh |  | Michael Wall | 45735 |  |  |  | Development has been completed and partially completed testing in dev environment. [03/19/2025]
10 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1-[Stretch] | Rajesh | GGO-14587 | Invoice is not importing or clearing from import area* | Being Developed | 3 |  | 14.5
11 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Priya-QA | GGO-14584 | Resolve new issues introduced to automation | Completed | 1 | 1 | 22 | [15 empty] | Dev completed. Testing in Progress. Facing Mailinator Issues in the TST env. Completed Coding and Execution and Raised PR
12 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Priya-QA/ Sathiyabharathi/ Rajesh | PAPI-820 | Update the Portico Batch delayed interval | Completed | 1 | 1 | 18 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
13 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Priya-QA/ Rajesh | GGO-14596 | Add 3X SWIPE card payment method type* | Completed | 1 | 1 | 2 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
1 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Rajesh | GGO-14594 | Invoice Payment Pages are calculating unapplied convenience fees | Completed | 2 | 2 | 22.5 | Rajesh | Saranya/Priya | NA |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8336 | 45740 | 45740 | Rajesh |  | Loan Troung | 45740 |  |  |  | Email Queues and Quartz job issue blocked us to test this. Verified this story in the TST env. 3/28/2025. But still Quartz job issue exists.
2 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14621 | Email queues in TST repeatedly disabling* | Completed | 1 | 1 | 9 |  |  | NIL | [12 empty] | Email Queues issue got fixed. But still Quartz job issue exists in the TST env.
3 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14626 | Quartz Job not sending email in TST environment* | Completed | 1 | 1 | 2 |  |  | NIL | [12 empty] | Quartz job issue exists in the TST env.
4 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Sathiya | GGO-14589 | New clients don't have Invoicing capabilities | Completed | 2 | 2 | 13 | Sathya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8330 | 45737 | 45737 | Rajesh |  | Mike Horihan | 45738 |  |  |  | Completed Testing in the TST env. 3/25/2025
5 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Sathiya | GGO-14606 | Duplicate EventXCode's are Being Created | Completed | 3 | 3 | 71 | Sathya | Rajesh,Priya | NIL |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8355 | 45743 | 45744 | Rajesh |  | Loan Troung,Michael Wall | 45744 |  |  |  | Testing in progres 7:17 PM 3/28/2025
6 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Saranya | GGO-14587 | Invoice is not importing or clearing from import area | Completed | 2 | 2 | 32 | Saranya | Sathya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8338 | 45740 | 45741 | Rajesh |  | Loan Troung | 45741 |  |  |  | Completed Testing in the TST env. 3/28/2025
7 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Saranya | GGO-14573 | OP to GGO import timeouts | Being Developed | 3 | 5 | 97 | [15 empty] | We have reproduced this issue in DEV and TST environments but are still unable to reproduce it locally. Based on our analysis, GetClosedMatches method seems to be causing the issue. This method is used to find the closest matched names for the given input names and utilizes the Jaro-Winkler algorithm
8 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Priya-QA | GGO-14161 | Rewrite AGG-13 to a new report toolset | Completed | 1 | 1 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/25/2025
9 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14597 | Deprecated "DOMNodeInserted" & "DOMSubtreeModified" event throwing error in multiple places * | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/28/2025
10 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | PAPI-807 | Not all Credit Card Last 4 being added to payments table after hotfix PAPI-795* | Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
11 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14592 | Not all Credit Card Last 4 being added to payments table after hotfix PAPI-795* | Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
12 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14473 | Remove equipment banner* | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/25/2025
13 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | PAPI-839 | Ensure all Portico calls use the client's API Key* | Being Tested | 1 | 1 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test Client API Key's. Offshore QA did payment Regression Testing only.
14 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh,Sathiya | GGO-14602 | Handle message for 3X Reader Wi-Fi connection failed - StoreFront* | Completed | 2 | 2 | 1 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8362 | 45748 | 45748 | Rajesh | NA | Loan
1 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Sathiya | GGO-14573 | OP to GGO import timeouts | Completed | 3 | 3 | 42 | Sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8370 | 45754 | 45755 | Rajesh |  | Mike Wall and Loan | 45755
2 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Rajesh | GGO-14633 | Allow Household Share on RSVP Imported Cards | Completed | 3 | 3 | 53 | Rajesh | Priya | Nill
3 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Sathiya | GGO-14457 | Allow Multiple RSVP Import from OP | Completed | 5 | 5 | 83 | sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8380 | 45761 | 45762 | Rajesh |  | Mike Wall and Loan | 45762
4 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3-[Stretch] | Saranya/Sathiya | GGO-14620 | BID-19 Admissions Count issue* | Completed | 3 | 3 | 13.5 | Sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8407 | 45763 | 45763 | Rajesh |  | Mike Wall | 45763
5 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3-[Stretch] | Priya-QA,Rajesh | PAPI-839 | Ensure all Portico calls use the client's API Key* | Completed | 1 | 1 | 13.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
6 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Priya-QA | GGO-14617 | HIGH & MEDIUM-Serilog.Sinks.File:4.0.0 | Completed | 1 | 1 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed 'testing in the TST env. 11:19 PM 4/7/2025
7 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Priya-QA,Rajesh | PAPI-842 | Fix issue where Payer Records CreditCardStatus are being set to Invalid | Completed | 2 | 2 | 17.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rajesh - Supported to analyze the root cause. Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario
8 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Saranya | PAPI-840 | Remove the use of StringHashTable | Peer Review | 8 | 5 | 90.5 | Sathiya | Priya | Nill | [12 empty] | Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario. The story was left in Peer Review upon completion, per the client's request to hold it and maintain this branch separately from the CERT branch. Dependency on Onsite QA now
1 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Saranya | PAPI-840 | Remove the use of StringHashTable | Completed | 3 | 3 | 23.5
2 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Rajesh, Saranya | GGO-14644 | Remove Hash table in PAPI - GGO need to pass Bluetooth Swipe data on StoreFront scenario* | Completed | 1 | 1 | 14.5 | [15 empty] | Completed One round of Payment Regression
3 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Rajesh | GGO-14614 | HIGH - Microsoft.AspNetCore.Http.Connections.Client:1.0.0 | Completed | 2 | 2 | 19.5 | Rajesh | Sathish,Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8431 | 45770 | 45770 | Rajesh |  | Loan Troung | 45770 |  |  |  | Completed One round of Standard Regression
4 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Sathya | GGO-14613 | HIGH - Cross-Site Scripting: DOM - MaintenanceNotification.js: 22 & 25 | Completed | 2 | 2 | 34.5 | Sathiya | Rajesh,Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8434 | 45771 | 45775 | Rajesh |  | Michael Wall, Loan Troung | 45775
5 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4[Stretch] | Sathya | GGO-14658 | CRITICAL - CVE-2021-43569 - starkbank-ecdsa/1.3.1* | Completed | 1 | 1 | 14 | Sathiya | Rajesh,Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8436 | 45772 | 45775 | Rajesh |  | Michael Wall | 45775 |  |  |  | Development has been completed and tested in local and Dev enviroment[28-April-2025] Completed One round of Standard Regression
6 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Sathiya, Rajesh | GGO-13722 | High - Weak Encryption: Insecure Mode of Operation - Cryptography.cs: 56 | Peer review | 1 | 0.5 | 12.5 | Sathiya | Rajesh |  |  |  | NA
7 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Saranya | GGO-14615 | HIGH - Microsoft.Bcl.Async:1.0.168 | Completed | 2 | 2 | 10.5 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8427 | 45769 | 45769 | Rajesh |  | Loan Troung | 45769 |  |  |  | Completed One round of Standard Regression
8 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Saranya | GGO-13723 | High - Weak Encryption: Insecure Mode of Operation - SymmetricAlgorithmProvider.cs: 35 | Peer review | 1 | 0.5 | 22 | [5 empty] | NA
9 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4[Stretch] | MikeW, Rajesh, Saranya | GGO-14651 | Pass New IsFallback Swipe Flag from GoTime to PAPI | Completed | 2 | 2 | 36 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8440 | 45775 | 45775 | Rajesh |  | Michael Wall | 45775
10 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | MikeW, Rajesh, Saranya | PAPI-846 | EMV Fallback Requires <EMVChipCondition> Tag along with Swipe Data* | Completed | 3 | 3 | 48 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8441 | 45775 | 45775 | Rajesh |  | Michael Wall | 45775
11 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Priya-QA | GGO-14649 | 22 APR GGO 7.23.0 CRT Release & Regression Testing | Completed | 5 | 5 | 35.5 | [15 empty] | CRT Regression Testing in Progress
12 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Priya-QA | PAPI-851 | 22 APR PAPI 7.18.0 CRT Release & Regression Testing | Completed | 3 | 3 | 22 | [15 empty] | CRT Regression Testing in Progress
1 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-13722 | High - Weak Encryption: Insecure Mode of Operation - Cryptography.cs: 56 | Completed | 1 | 1 | 15 | Sathiya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8458 | 45779 | 45779 | Rajesh |  | Michael Wall | 45780 |  |  |  | Verified in the TST env.5 May 2025 at 08:36
2 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-13723 | High - Weak Encryption: Insecure Mode of Operation - SymmetricAlgorithmProvider.cs: 35 | Completed | 1 | 1 | 34.5 | Sathiya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8457 | 45779 | 45783 | Rajesh |  | Michael Wall, Loan Troung | 45784 |  |  |  | Tested in the TST env 7 May 2025 at 09:20
3 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-14618 | MEDIUM - BDSA-2024-4605 - System.IdentityModel.Tokens.Jwt/5.5.0 | Completed | 2 | 2 | 10.25 | Sathiya | Rajesh |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8474 | 45784 | 45785 | Rajesh |  | Michael Wall | 45785 |  |  |  | Tested in the Dev env 8:09 PM 5/7/2025
4 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Rajesh/Saranya | PAPI-841 | Fix ValidateAndGetPorticoToken calls to handle when Token or CardBrandTransactionId exists | Completed | 2 | 2 | 18 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8477 | 45785 | 45786 | Rajesh |  | Michael Wall | 45786 |  |  |  | Did one round of Payment Regression Testing for this story in the TST env.9 May 2025 at 09:19
5 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Saranya | GGO-14601 | Project UI accepting Invalid Email address results in error on GGO to SF sync | Completed | 2 | 2 | 35 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8463 | 45782 | 45783 | Rajesh |  | Michael Wall | 45783 |  |  |  | Test Cycle executed Successfully in the TST env.7 May 2025 at 07:30
6 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Saranya | GGO-14652 | Enable Online Bidding - Blocked when users mistakenly generate Display Board | Completed | 5 | 5 | 49.5 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8476 | 45785 | 45787 | Rajesh |  | Michael Wall | 45789 |  |  |  | Tested in the TST env 13 May 2025 at 09:16
7 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1[Stretch] | Rajesh | GGO-14678 | Unable to Export Sales* | Completed | 2 | 2 | 19 | Rajesh | Sathiya,Priya |  |  |  | NA | NA | NA | NA |  | NA | NA
8 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 | 0 | 50.5 | [15 empty] | Issue not reproduceable in Dev and TST.Need to check query execution CRT
9 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Rajesh/ Sathiya | GGO-14656 | Nav Bar Update | Being Developed | 3 | 0 | 64.5 | [15 empty] | Reskin-V2 is a complete overhaul of the existing Master Page, focusing on delivering a fully responsive design. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness.
1 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 |  | 27.5 | [15 empty] | Issue not reproduceable in Dev and TST.Need to check query execution CRT The work around has been provided and ticket has been put on hold for now as it only impacts only one client/org and is of low priority
2 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Rajesh/ Sathiya | GGO-14656 | Nav Bar Update | Completed | 5 | 5 | 107 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8525 | 45805 | 45805 | Rajesh |  | Michael Wall | 45805 |  |  |  | Testing this in the Dev. In Progress 4:32 PM 5/27/2025
3 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Saranya | GGO-14679 | Sales Grid and Details Update for old Convenience Fee assets | Completed | 3 | 3 | 19 | Saranya | Rajesh |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8496 | 45793 | 45797 | Rajesh |  | Michael Wall | 45797 |  |  |  | Verified in the TST env successfully. 20 May 2025 at 05:52
4 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Saranya | GGO-9991 | "Purchaser Company Name" column causes error when the "Export" link is selected | Completed | 2 | 2 | 11.5 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8502 | 45796 | 45797 | Rajesh |  | Michael Wall | 45796 |  |  |  | Verified this in the TST env. 21 May 2025 at 09:23
5 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Rajesh | GGO-14708 | Remove Pivotal WebApi Project from GGO Repo - Unused project and it is using .Net Core 6 (deprecated version)* | Completed | 2 | 2 | 33 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8498 | 45794 | 45796 | Saranya |  | Michael Wall | 45797 |  |  |  | Offshore QA Verified this in the TST env. 21 May 2025 at 09:23
6 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Mike Wall/Rajesh/Saranya | GGO-14701 | Update Implementation of Flag to Disable Card Types in select Organizations | Completed | 2 | 2 | 23.75 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8508 | 45798 | 45798 | Rajesh |  | Michael Wall | 45798 |  |  |  | Verified in the TST env. 22 May 2025 at 08:01
7 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Mike Wall/Rajesh/Saranya | PAPI-858 | Update Flag to Disable Amex in select Organizations With Pre-Token Check* | Completed | 2 | 2 | 38 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8518 | 45799 | 45800 | Rajesh |  | Mike H | 45800 |  |  |  | Verified in the TST env. 22 May 2025 at 08:01
8 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Rajesh/Saranya | GGO-14684 | Implement Pendo for GGO | Completed | 5 | 5 | 41.75 | Rajesh | Priya |  | Saranyas |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8523 | 45804 | 45806 | Rajesh | 1. Let's add the following to the account metadata Environment: pendoEnvironment, 2. PendoUserID should be prefixed with PendoEnvironment so that UserID is unique across all environments 3. Dev and local should not fall under the same environment label | Mike H | 45806 |  |  |  | Testing this in the Dev. In Progress 4:32 PM 5/27/2025
1 | GGO Donor Wave | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Kannan | GDON-4 | GGO Donor Api Project Setup (WebApi Project in GGO Repo) | Completed | 3 | 3 | 25 | Vishnu | Rajesh |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8547 | 45813 | 45817 | Rajesh |  | Mccarty, Mike | 45817
2 | GGO Donor Wave | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Vishnu | GDON-5 | Create a Integration Test Project to unit test WebApi calls | Completed | 3 | 3 | 39 | Vishnu | Kannan |  | Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8553 | 45814 | 45818 | Rajesh |  | Mccarty,Mike Wall | 45818
3 | GGO Donor Wave | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Ubaithullah | GDON-6 | GGO Donor Api Authentication | Completed | 3 | 3 | 60 | Ubaithullah | Rajesh |  | Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8566 | 45818 | 45819 | Rajesh |  | Mccarty | 45936 | If we hardcode password, even temporarily as a placeholder, macroscope will flag it as a critical issue
1 | GGO Donor Wave | 45820 | 45834 | GGO 7.24.0 Sprint 4 | Kannan, Ubaithullah | GDON-9 | Donor API - Get/Create/Update/Delete Account Information | Completed | 5 |  |  | Kannan | Charles |  | Rajesh |  | Pull Request 8592: [GDON-9] Donor API - Get/Create/Update/Delete Account Information | 45828 | 45832 | Rajesh |  | Wall-Iannarelli, Michael | 45828 |  |  |  | Tested in the Dev. Completed 4:45 PM 06/25/2025
2 | GGO Donor Wave | 45820 | 45834 | GGO 7.24.0 Sprint 3[Stretch] | Vishnu | GDON-7 | GGO Donor Api Project Pipeline and Release setup | Completed | 2 |  | 8 | Vishnu | Rajesh |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8573 | 45819 | 45825 | Rajesh |  | Horihan, Mike | 45825
3 | GGO Donor Wave | 45820 | 45834 | GGO 7.24.0 Sprint 4 | Vishnu | GDON-10 | Donor API - Get/Create/Update/Delete Profile Information | Completed | 5 |  | 36 | Vishnu | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8593 | 45828 | 45829 | Rajesh |  | Wall-Iannarelli, Michael | 45829 | Suggestion can we rename Phones to PhoneNumbers ? "Phones" by itself implies the hardware |  |  | Tested in the Dev. Completed 5:30 PM 06/24/2025
1 | GGO Donor Wave | 45835 | 45848 | GGO 7.25.0 Sprint 1 | Kannan, Ubaithullah | GDON-11 | Donor API - Get/Create/Update/Delete OnlineBiddingActivity | Completed | 5 |  |  |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8621 | 45845 | 45846 | Rajesh |  | Wall-Iannarelli, Michael | 45846 |  |  |  | Tested in the Dev. Completed 5:30 PM 07/08/2025
2 | GGO Donor Wave | 45835 | 45848 | GGO 7.25.0 Sprint 1 | Vishnu | GDON-15 | Donor API - Get/Create/Update/Delete AddressBookEntry | Completed | 3 |  |  |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8615 | 45840 | 45846 | Rajesh |  | Wall-Iannarelli, Michael | 45846 |  |  | do we need to make sure error type matches operation type for all these methods ? | Tested in the Dev. Completed 12:30 PM 07/10/2025
3 | GGO Donor Wave | 45835 | 45848 | GGO 7.25.0 Sprint 1 [Stretch] | Kannan, Ubaithullah | GDON-14 | Donor API - Get/Create/Update/Delete CreditCardInfo | Completed | 3 |  |  |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8627 | 45846 | 45846 | Rajesh |  | Wall-Iannarelli, Michael | 45846 |  |  |  | Tested in the Dev. Completed 3:30 PM 07/09/2025
4 | GGO Donor Wave | 45835 | 45848 | GGO 7.25.0 Sprint 1 [Stretch] | Ubaithullah | GDON-12 | Donor API - Get/Create/Update/Delete ElectronicContactInfo | Verify | 2 |  |  |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8632 | 45847 | 45848 | Rajesh |  | Wall-Iannarelli, Michael | 45848 |  |  |  | Tested in the Dev. Completed 12:30 PM 07/15/2025
5 | GGO Donor Wave | 45835 | 45848 | GGO 7.25.0 Sprint 1 [Stretch] | Vishnu | GDON-13 | Donor API - Get/Create/Update/Delete AddressInfo | Being Developed | 2 |  |  |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8645 | 45852 | 45852 | Rajesh |  | Wall-Iannarelli, Michael | 45852 |  |  |  | Tested in the Dev. Completed 2:00 PM 07/15/2025
1 | GGO Donor Wave | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Kannan, Ubaithullah | GDON-25 | Donor APi - Create/Update Fundraising Page | Completed | 5 |  |  | 45848 | 45858 |  | Charles |  | Rajesh, Vishnu |  | Pull Request 8665: [GDON-25] Donor API - Create/Update Fundraising_Page | 45859 | 45859 | Rajesh |  | Wall-Iannarelli, Michael | 45859
2 | GGO Donor Wave | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Ubaithullah | GDON-26 | Donor API - Delete Fundraising Page | Rejected | 2
3 | GGO Donor Wave | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Ubaithullah | GDON-16 | Donor API - Get FundraisingPage | Completed | 5 |  |  | 45853 | 45860 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8673 | 45860 | 45860 | Rajesh |  | Wall-Iannarelli, Michael | 45860
4 | GGO Donor Wave | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Charles | GDON-12 | Donor API - Get/Create/Update/Delete ElectronicContactInfo | Completed | 2 | [5 empty] | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8632
5 | GGO Donor Wave | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Vishnu | GDON-13 | Donor API - Get/Create/Update/Delete AddressInfo | Completed | 2 |  |  | 45848 | 45849 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8645 | 45852 | 45852 | Rajesh |  | Wall-Iannarelli, Michael | 45852
6 | GGO Donor Wave | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Vishnu | GDON-20 | Donor API - GetImage for Fundraising Page | Completed | 2 |  |  | 45852 | 45856 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8666 | 45859 | 45859 | Rajesh |  | Wall-Iannarelli, Michael | 45859
7 | GGO Donor Wave | 45848 | 45862 | GGO 7.25.0 Sprint 2 [Strech] | Kannan, Ubaithullah | GDON-28 | Upload image for Fundraising Page | Being Developed | 3 |  |  | 45861
1 | GGO Donor Wave | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Kannan | GDON-29 | Create API to send info from GGO to Donor Platform - Organizations | Completed | 3 |  |  | 45863 | 45866 |  | Charles |  | Rajesh |  | Pull Request 8692: GDON-29 Create API to send info from GGO to Donor Platform - Organizations | 45866 | 45868 | Rajesh |  | Wall-Iannarelli, Michael | 45868
2 | GGO Donor Wave | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Ubaithullah, Kannan | GDON-28 | Upload Image for Fundraising pages * | Completed | 2 |  |  | 45861 | 45866 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8696 | 45866 | 45867 | Rajesh |  | Wall-Iannarelli, Michael | 45867
3 | GGO Donor Wave | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Ubaithullah, Kannan | GDON-19 | Donor API - Get/Send Email | Completed | 5 |  |  | 45867 | 45874 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8713 | 45874 | 45874 | Rajesh |  | Wall-Iannarelli, Michael | 45874
4 | GGO Donor Wave | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Vishnu | GDON-30 | Create GGO API for Donor Platform - Events | Completed | 3 |  |  | 45863 | 45874 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8704 | 45873 | 45874 | Rajesh |  | Wall-Iannarelli, Michael | 45874
5 | GGO Donor Wave | 45862 | 45876 | GGO 7.25.0 Sprint 3[Strech] | Kannan | GDON-21 | Donor API - Delete FundraisingActivity | Completed | 2 |  |  | 45874 | 45874 |  | Charles |  | Rajesh |  | Pull Request 8708: [GDON-21] Donor API - Delete Fundraising Activity | 45874 | 45874 | Rajesh |  | Wall-Iannarelli, Michael | 45874
6 | GGO Donor Wave | 45862 | 45876 | GGO 7.25.0 Sprint 3[Strech] | Vishnu | GDON-32 | Donor API - GetOfflineDonation | Being Developed | 2 |  |  | 45874
7 | GGO Donor Wave | 45862 | 45876 | GGO 7.25.0 Sprint 3[Strech] | Ubaithullah, Kannan | GDON-33 | Donor API - EditOfflineDonation | Being Developed | 3 |  |  | 45875
1 | GGO Donor Wave | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Kannan,Ubaithullah | GDON-17 | Donor API - Get/Create/Update/Delete FundraisingTeamMember | Completed | 5 | 5 |  | 45877 | 45882 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8736 | 45882 | 45883 | Rajesh |  | Wall-Iannarelli, Michael | 45883 | Remove Semicolon
2 | GGO Donor Wave | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Vishnu | GDON-18 | Donor API - Get/Create/Update/Delete FundraisingTeamCoordinator | Completed | 5 | 4 | 85.25 | 45880 | 45888 |  | Charles |  | Prabhu |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8754 | 45888 | 45889 | Prabhu | 1. Correct the params here 2. Correct the param here 3. Don't we have to check teamCoordinator is not null here before accessing its property 4. correct the param name here 5. Why are we keeping empty class here? remove it if not needed Suggestion 1. rather than generic description like 'response' , why don't we use actual description 2. rather than generic description like 'response' , why don't we use actual description (i.e FundraisingTeamCoordinator) 3. You could use else or else if here Does there any edge case of equals 0 here 4. Consider renaming this variable here? to be more descriptive | Wall-Iannarelli, Michael | 45889
3 | GGO Donor Wave | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Vishnu | GDON-32 | Donor API - GetOfflineDonation | Completed | 2 | 2 | 22.75 | 45874 | 45877 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8724 | 45878 | 45878 | Rajesh |  | Wall-Iannarelli, Michael | 45878
4 | GGO Donor Wave | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Ubaithullah, Kannan | GDON-33 | Donor API - EditOfflineDonation | Completed | 3 | 3 | 26 | 45875 | 45877 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8724 | 45878 | 45878 | Rajesh |  | Wall-Iannarelli, Michael | 45878
5 | GGO Donor Wave | 45876 | 45890 | GGO 7.25.0 Sprint 4 [Strech] | Ubaithullah, Kannan | GDON-36 | Donor API - Update Profile Image | Verify | 3 |  | 33.75 | 45882 | 45888 |  | Charles |  | Prabhu | Comment/ Suggestions: 1. does the method name is descriptive enough to explain the functionality? 2. Why are we duplicating the if check here? 3. Avoid the Naming rule violation here by start with uppercase | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8753 | 45888 | 45889 | Prabhu | 1. does the method name is descriptive enough to explain the functionality? 2. Why are we duplicating the if check here? 3. Avoid the Naming rule violation here by start with uppercase 4. Does there any references also needs to be updated? | Wall-Iannarelli, Michael | 45889
6 | GGO Donor Wave | 45876 | 45890 | GGO 7.25.0 Sprint 4 [Strech] | Ubaithullah, Kannan | GDON-37 | API Request - Pull Organization and Events at the same time | Completed | 3 |  | 18 | 45889
7 | GGO Donor Wave | 45876 | 45890 | GGO 7.25.0 Sprint 4 [Strech] | Vishnu | GDON-34 | Donor API - GetCoordinatorProgress | Completed | 5 |  | 17.5 | 45889
1 | GGO Donor Wave | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Ubaithullah, Kannan | GDON-36 | Donor API - Update Profile Image | Completed | 2 |  |  | 45882 | 45888 |  | Charles |  | Prabhu | Provided some internal comments, which has been fixed mentioned in previous Sprint GGO 7.25.0 Sprint 4 | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8753 | 45888 | 45889 | Prabhu |  | Wall-Iannarelli, Michael | 45889
2 | GGO Donor Wave | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Ubaithullah, Kannan | GDON-37 | API Request - Pull Organization and Events at the same time | Completed | 2 |  |  | 45889 | 45895 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8757 | 45895 | 45876 | Rajesh |  | Wall-Iannarelli, Michael | 45896
3 | GGO Donor Wave | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Vishnu , Ubaithullah | GDON-34 | Donor API - GetCoordinatorProgress | Completed | 2 |  |  | 45889 |  |  | Rajesh |  | Rajesh | I did analysis on the Team Coordinator display in GGAM and PROD data, noticed that functionality is disabled for all projects by default and also I verified the PROD data, that the last allowed Team Coordinator data is 2018. So I don’t want to spent much time on this Team Coordinator logic if it is not used in PROD. We will work on implementing new API’s once Donor team decide to add a new UI for this Teams Coordinator functionality in future. I would suggest to reduce the points to 2 and close this ticket.
4 | GGO Donor Wave | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Kannan | GDON-35 | Donor API - ContactsUpload | Completed | 3 |  |  | 45889 | 45895 |  | Charles |  | Rajesh | Client Suggestion 1: Do we have this regEx in a common place so that we aren't duplicating code? | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8771 | 45895 | 45899 | Rajesh |  | Wall-Iannarelli, Michael | 45899
5 | GGO Donor Wave | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Vishnu | GDON-18 | Donor API - Get/Create/Update/Delete FundraisingTeamCoordinator | Completed | 1 |  |  | 45880 | 45888 |  | Charles |  | Prabhu | Provided some internal comments, which has been fixed mentioned in previous Sprint GGO 7.25.0 Sprint 4 | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8754 | 45888 | 45889 | Prabhu |  | Wall-Iannarelli, Michael | 45889
6 | GGO Donor Wave | 45890 | 45904 | GGO 8.0.0 Sprint 1 [Strech] | Vishnu | GDON-42 | Donor API - GetFundraisingInfo | Completed | 2 |  |  | 45897 | 45903 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8801 | 45903 | 45903 | Rajesh |  | Wall-Iannarelli, Michael | 45903
7 | GGO Donor Wave | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Ubaithullah, Kannan | GDON-39 | Donor API - Logging | Completed | 5 |  |  | 45901 | 45903 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8793 | 45903 | 45903 | Rajesh |  | Wall-Iannarelli, Michael | 45903
1 | GGO Donor Wave | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Kannan | GDON-31 | Donor API - GetCreditCards for Account/Profile | Completed | 3 |  |  | 45910 | 45915 |  | Charles |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8840 | 45915 | 45916 | Rajesh |  | Wall-Iannarelli, Michael | 45916
2 | GGO Donor Wave | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Kannan | GDON-43 | Donor API - Save Credit Card for Account/Profile | Completed | 3 |  |  | 45905 | 45910 |  | Charles |  | Rajesh |  | Pull Request 8836: [GDON-43] Save Credit Card for Profile | 45911 | 45911 | Rajesh |  | Wall-Iannarelli, Michael | 45911
3 | GGO Donor Wave | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Vishnu | GDON-44 | Donor API - UpdateCreditCard for Account/Profile (Update only Primary and Billing address) | Completed | 3 |  |  | 45912 | 45917 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8842 | 45917 | 45917 | Rajesh |  | Wall-Iannarelli, Michael | 45917
4 | GGO Donor Wave | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Ubaithullah | GDON-40 | Donor API - Exception Handling | Completed | 3 |  |  | 45905 | 45912 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8819 | 45912 | 45912 | Rajesh |  | Wall-Iannarelli, Michael | 45912
| GGO Donor Wave | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Vishnu | GDON-41 | Donor API - Create Profile - Send Email to user after creating profile | Completed | 3 |  |  | 45904 | 45917 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8824 (edited) | 45910 | 45917 | Rajesh |  | Wall-Iannarelli, Michael | 45917
1 | GGO Donor Wave | 45919 | 45932 | GGO 8.0.0 Sprint 3 | Vishnu | GDON-46 | Donor API - Update ApAdmin settings for Donor App | Completed | 5 |  |  | 45922 | 45926 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8866 | 45925 | 45926 | Rajesh |  | Mccarty, Joseph | 45926
2 | GGO Donor Wave | 45919 | 45932 | GGO 8.0.0 Sprint 3 | Vishnu | GDON-47 | Donor API - Get ApAdmin settings for Donor App | Completed | 2 |  |  | 45919 | 45924 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8866 | 45923 | 45926 | Rajesh |  | Mccarty, Joseph | 45926
1 | GGO Donor Wave | 45933 | 45946 | GGO 8.0.0 Sprint 4 | Vishnu | GDON-50 | Donor API - Add Address Type for profile | Completed | 2 |  |  | 45933 | 45936 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8901 | 45936 | 45936 | Rajesh |  | Horihan, Mike | 45936
2 | GGO Donor Wave | 45933 | 45946 | GGO 8.0.0 Sprint 4 | Vishnu | GDON-51 | Donor API - Modify Create Account API to validate email and return profile Info | Completed | 5 |  |  | 45938 | 45943 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8914 | 45939 | 45943 | Rajesh |  | Mccarty, Joseph | 45943
1 | GGO Donor Wave | 45947 | 45960 | GGO 8.1.0 Sprint 1 | Vishnu | GDON-53 | Donor API - Add Company Name for the Business address type | Completed | 2 |  |  | 45947 | 45951 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8936 | 45951 | 45951 | Rajesh |  | Mccarty, Joseph | 45951
2 | GGO Donor Wave | 45947 | 45960 | GGO 8.1.0 Sprint 1 | Vishnu | GDON-54 | Validate User Profile - Check Bidder/Supporter has got GGAM User Profile or not using "BidderKey" | Completed | 2 |  |  | 45952 | 45953 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8948 | 45953 | 45954 | Rajesh |  | Mccarty, Joseph | 45954
3 | GGO Donor Wave | 45947 | 45960 | GGO 8.1.0 Sprint 1 | Vishnu | GDON-55 | Create OnlineBiddingActivity to accept multiple Credit Card and transfer default ClientXid to respective Org clientxid | Completed | 3 |  |  | 45954 | 45958 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8964 | 45958 | 45958 | Rajesh |  | Mccarty, Joseph | 45954
1 | GGO Donor Wave | 45960 | 45974 | GGO 8.1.0 Sprint 2 [Strech] | Vishnu | GDON-56 | Update Account Creation to include Online Bidding Activity creation if user login via OB | Completed | 2 |  |  | 45959 | 45964 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8976 | 45964 | 45965 | Rajesh |  | Mccarty, Joseph | 45965
2 | GGO Donor Wave | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Vishnu | GDON-57 | Donor API - Update GGO Card reference in SaveCreditCard | Ready for Testing | 2 |  |  | 45971 | 45973 |  | Charles |  | Rajesh |  |  | 45972 | 45973 | Rajesh |  | Mccarty, Joseph | 45973
1 | GGO Donor Wave | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Vishnu | GDON-59 | Donor API - Update the Response code for all the donor API based | Completed | 3 |  |  | 45982 | 45986 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9048 | 45986 | 45986 | Rajesh |  | Mccarty, Joseph | 45986
2 | GGO Donor Wave | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Vishnu | GDON-61 | Donor API - Delete Credit Card in donor app should also delete from GGO if no charge is made | Completed | 3 |  |  | 45974 | 45979 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9018 | 45978 | 45978 | Rajesh |  | Mccarty, Joseph | 45978
1 | GGO Donor Wave | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Vishnu | GDON-63 | Create Donor Admin Page | Completed | 5 | 5 |  | 45988 | 45994 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9066 | 45994 | 45994 | Rajesh |  | Mccarty, Joseph | 45994
2 | GGO Donor Wave | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Vishnu | GDON-65 | Donor API - Validate Online Bidding activity and Card address before creating OB activity | Completed | 2 | 2 |  | 45994 | 45995 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9076 | 45995 | 45996 | Rajesh |  | Mccarty, Joseph | 45996
1 | GGO Donor Wave | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Vishnu | GDON-66 | Donor API - Create Online Bidding Activity without Credit Card Info* | Completed | 5 | 5 | 66.5 | 45996 | 46009 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9104 | 46006 | 46014 | Rajesh |  | Mccarty, Joseph | 46014
2 | GGO Donor Wave | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Vishnu | GDON-67 | Disabled the Online Bidding activity creation process and hide the display of OB activities in GGAM based on flag | Completed | 5 | 5 | 105 | 46010 | 46024 |  | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9133 | 46015 | 46029 | Rajesh |  | Mccarty, Joseph | 46029
1 | GGO Donor Wave | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Vishnu | GDON-68 | Donor API - Include AddressTypeId and CompanyName in the GetProfileCreditCards API * | Completed | 1 | 1 | 12.5 | 46027 | 46030 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9155 | 46030 | 46030 | Rajesh |  | Mccarty, Joseph | 46030
2 | GGO Donor Wave | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Vishnu | GDON-73 | Create GG API to send Checkout information to Donor Platform | Completed | 5 | 5 | 53.5 | 46031 | 46038 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9178 | 46038 | 46041 | Rajesh |  | Mccarty, Joseph | 46041
3 | GGO Donor Wave | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Vishnu | GDON-75 | Donor API - Add Donation Sale for Donor | Completed | 3 | 3 | 33.5 | 46038 | 46042 | Done | Charles |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9188 | 46042 | 46042 | Rajesh |  | Mccarty, Joseph | 46042