## Dashboard
Current Sprint | GGO 8.4.0 Sprint 4 | Current Sprint Sheet | GGO 8.4.0 Sprint 4-Status | Sprint Start Date | 2026-05-14 | Sprint End Date | 2026-05-28 | Application Name | GGO Web | Users | jennifer.anthony@relevantz.com;saranya.namachivayam@relevantz.com;sathiyabharathi.paramasivam@relevantz.com;priyadharshini.ravichandran@relevantz.com;rajeshkannan.subramanian@relevantz.com;satarupa.mohanty@relevantz.com | Teams Name(GP-GGO.Web) | 19:ac26c2f1541e4a10bdec732dd7eb2936@thread.v2
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story points introduced/removed | Sprint Summary | Accomplishments | Remarks | Retro Points (Internal & External) | Data sanity Audit Status | AuditDate | Planned Leaves | Availed Leaves | Backlog Health
NA | GGO 7.15.0 Sprint 4 | 2024-01-12 | 2024-01-25 | 17 | 15 | 7 |  |  | Completed all the introduced story in the mid of the sprint | Internal: External:
NA | GGO 7.16.0 Sprint 1 | 2024-01-26 | 2024-02-08 | 17 | 14 | 3 |  |  | Actual estimated stories (17pts) got completed from our end with Development and Testing, From Onsite QA (Nate) took time for testing 3 point story because of PRD release and he took half day leave and he got only 4 hrs of time. So from this I would like to say, we should plan to complete the estimated stories 2 days prior, else Nate won't close on the last day of sprint. Introduced Story - 3 point is Development completed, only Testing pending. | Internal: External:
NA | GGO 7.16.0 Sprint 2 | 2024-02-09 | 2024-02-22 | 23 | 22 | 2 |  |  | Completed all the stories on time, but we noticed one minor issue in GGO-13703 Bid-18 report on xls and xlsx formats. the column header occupying some aditional column . It require an report engine code changes.verified some other reports also having the same issue and it's an existing issue.completed introduced story as well | Internal: External:
NA | GGO 7.16.0 Sprint 3 | 2024-02-23 | 2024-03-07 | 27 | 23 | 7 |  |  | GGO-13801-onsite QA(Nathan) raised one bug , we tried to reproduce the issue on rounding but we are not able to do that. We have asked for the steps to reproduce the issue. GGO-13738 -Development has been completed on this story, it require's IT team support to complete the testing. Introduced Story - 7 points (Except GGO-13738 testing) all completed | Internal: External:
NA | GGO 7.16.0 Sprint 4 | 2024-03-08 | 2024-03-21 | 20 | 16 | 5 |  |  | GGO-13796 and GGO-13773 development has been completed.testing requires IT team support to complete,currently salesforce team doing some changes at their side we can't test salesforce api's .Introduced Story - 5 points Develpment has been completed for that. | Internal: External:
NA | GGO 7.17.0 Sprint 1 | 2024-03-22 | 2024-04-04 | 14 | 11 | 3 |  |  | Since we need support from sales force team for testing GGO -13773 ,PAPI-702 saranya supported Mike wall for testing We got info from Doug about the 4 PROD issues in planning meeting 1. Convenience Fee Issue - Not able to reproduce by our team and Onsite QA in DEV, TST & CRT, it is occurring only in PRD, finding a way to check the values, settings in PROD to replicate in lower envrionment 2. Package Tax Issue - Round off to whole number instead of 2 decimal, this is our mistake that has got in to PRD 3 months before, when fixing old code to replace SQL CLR to C# method. 3. Item tax added to Package - This was old issue, but many clients started to raise concern about this issue now, because of our new implementation for Convenience Fee. 4. Payment show error when Actually it is success in PAPI for Few Clients in PRD - Still don't know the reason, analysing the root cause of this issue. | Internal: External:
NA | GGO 7.17.0 Sprint 2 | 2024-04-05 | 2024-04-18 | 19 | 17 | 0 |  |  | This sprint we fixed production issues and macroscope security issues . PAPI-702 carried because card details need to verified with PAPI database, we don't have required permission for that, only onsite QA need to be verified. | Internal: External:
NA | GGO 7.17.0 Sprint 3 | 2024-04-19 | 2024-05-02 | 18 | 11 | 0 |  |  | 2 stories got carried. 1. Due to salesforce team confirmed they can't do any changes. 2. Onshore Testing is pending | Internal: External:
NA | GGO 7.17.0 Sprint 4 | 2024-05-03 | 2024-05-16 | 14 | 4 | 0 |  |  | CRT Regression Testing is still in Progress. 3 stores are blocked and carried because of IT dependencey (Certificate Issue and Permission issue for Report Instance folder in DEV & TST Environments), all the development and testing works are done from our end. | Internal: External:
NA | GGO 7.18.0 Sprint 1 | 2024-05-17 | 2024-05-30 | 15 | 14 | 0 |  |  | Testing blocked due to certificate issue | Internal: External:
NA | GGO 7.18.0 Sprint 2 | 2024-05-31 | 2024-06-13 | 20 | 16 | 0 |  |  |  | Internal: External:
NA | GGO 7.18.0 Sprint 3 | 2024-06-14 | 2024-06-27 | 17 | 15 | 2 |  |  |  | Internal: External:
NA | GGO 7.18.0 Sprint 4 | 2024-06-28 | 2024-07-11 | 20 | 20 | 0 |  |  |  | Internal: External:
NA | GGO 7.19.0 Sprint 1 | 2024-07-12 | 2024-07-25 | 15 | 15 | 5 |  |  | Two stretch stories got carried to next sprint. | Internal: External:
NA | GGO 7.19.0 Sprint 2 | 2024-07-26 | 2024-08-07 | 6 | 6 | 7 |  |  | Two stretch stories got carried to next sprint. | Internal: External:
NA | GGO 7.19.0 Sprint 3 | 2024-08-08 | 2024-08-22 | 16 | 16 | 2 |  |  |  | Internal: External:
NA | GGO 7.19.0 Sprint 4 | 2024-08-23 | 2024-09-05 | 17 | 14 | 2 |  |  | Automation Regression story got carried over as it was new for Offshore QA and there was some learning curve involved. | Internal: External:
NA | GGO 7.20.0 Sprint 1 | 2024-09-05 | 2024-09-19 | 15 | 13 | 2 |  |  | 2 point carry forwarded to next sprint, development and testing completed from our end, but onsite QA didn't complete it. | Internal: External:
NA | GGO 7.20.0 Sprint 2 | 2024-09-20 | 2024-10-03 | 19 | 14 | 2 |  |  | GGO-14067 got carried, We are migrating Bid-03 report to new RDLC framework, there is lot of existing logic present in RPT file. we need to exactly replicate same logic in SQL stored procedure for new RDLC format.understanding .rpt file logic is complication involved Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 | Internal: External:
NA | GGO 7.20.0 Sprint 3 | 2024-10-04 | 2024-10-17 | 17 | 12 |  |  |  | GGO-14067 got carried, Getting Timeout issue for large records,Suporterwise page breakup and some functionlity in spreadsheetlayout is pending Onsite CRC: 0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 | Internal: External:
NA | GGO 7.20.0 Sprint 4 | 2024-10-18 | 2024-10-31 | 16 | 13 |  |  | 1. Login Page Privacy policy update in MFA login page of GGO application 2. Paymen Receipt in new RDLC replacing form display helps users to download receipt as PDF and send email with attachment. | GGO-14067 got carried, Getting Timeout issue for large records Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 | Internal: External:
NA | GGO 7.21.0 Sprint 1 | 2024-11-01 | 2024-11-14 | 18 | 17 | 3/0 |  | 1.Fixed Timeout issue on Bid-03 RDLC report generation. 2.Completed two tickets introduced in the mid of the sprint | Completed all story points on time Onsite CRC: 0 Client CRC: 0 Internal Defects: 2 External Defects: 0 | Internal: External:
NA | GGO 7.21.0 Sprint 2 | 2024-11-15 | 2024-11-25 | 14 | 11 |  |  | 1. Fixed Grid selection issue on Bid-03 RDLC report generation. 2. Fixed Azure Images issue replacing content server url with azure url 3. Investigated GGO to OB Queue flow to replace it with Quartz Job. 4. Allow GGO to validate and support different card card types (JCB, Diners club & Discover Debit) | GGO-13319 story got rolled over due to Azure image access issue and a ticket with Microsoft has been opened​ by IT Onsite CRC: 0 Client CRC: 1 Internal Defects: 0 External Defects: 0 | Internal: External:Rajesh and offshore for continued work on reports Priya, Nathan and Conor for testing a lot of stories and completing them
NA | GGO 7.21.0 Sprint 3 | 2024-11-26 | 2024-12-12 | 14 | 14 | 7/0 |  | 1. Application images moved in Azure , previously we stored the images in DB as bytes 2. 7.20.1 Successfully deployed to PRD 3. EMV Implementation -completed most of the cardreader functionality | GGO-14325 - BID-06 story is a huge effort and cannot be completed in one sprint, hence it was taken as a strech goal Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 | Internal: External:
NA | GGO 7.21.0 Sprint 4 | 2024-12-13 | 2025-01-09 | 24 | 19 | 3/0 |  | 1. Fixed Duplicate Event X Code issue that was a PROD bug for more than 5 years. 2. Good progress on Bid-06 RDLC update and feel confident in completing it next sprint 3. Popup warning for Convenience fee validation implemented 4. Quartz Job implemented for Bid-06 email flow with our own effort and stored the PDF in Azure. | GGO-14427 - BID-06 - Part-3 story is a huge effort, this has got more than 100 scenario's, so it took more time for testing left out with 2 bugs at the end of sprint (development done for the bugs) only testing pending. Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 8 External Defects: 0 | Internal: External: Offshore team made great progress on Bid-06 report
NA | GGO 7.22.0 Sprint 1 | 2025-01-10 | 2025-01-23 | 21 | 17 | 4/0 |  | 1.GGO-14484 Jan 21 Prod Release 2. Successfully completed Bid-06 with new report tool set 3. CRT regression testing completed | GGO-14427 - BID-06 - Part-3 during the CRT testing noticed package item enabled scenario taking too long to complete the report - immediately addressed this Issue. GGO-14483 Completed CRT Release & Regression Testing Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 6 External Defects: 0 Reason for pending: GGO-14422, PAPI-789 - Development and Testing completed from our end, Pending testing from Nate (Onsite QA) because he was focusing more in CRT regression. GGO-14447 - Automation story completed from our end, pending review from Nate GGO-14450 - A.C change one day prior to Sprint end date, so it got carry forward to next sprint
NA | GGO 7.22.0 Sprint 2 | 2025-01-24 | 2025-02-06 | 18 | 11 | 2/0 |  | 1.Enhance RSVP Functionality with key features to enable better data gathering and management of attendee info. 2.Azure Thumbnail image creation issue fix - Add this project as part of GGO Solution and build it via Build pipeline and add it to GGO Artifact | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 1 Testing is pending by Onsite QA and we completed the stories (GGO-14503, GGO-14450) and deployed to TST 2 days prior Sprint end, that's the reason these stories got rolled over to next sprint.
NA | GGO 7.22.0 Sprint 3 | 2025-02-07 | 2025-02-20 | 18 | 8 |  |  | 1.Adjust Admission Functionality and Infrastructure(Graph) update 2.Bid-19 and Bid-15 Report Updates | Peer CRC:0 Onsite CRC: 0 Client CRC: 4 Internal Defects: 4 External Defects: 1 Reason for pending: GGO-14504 - The story was given Onisite QA for testing 3 days before the end of Sprint but Onsite QA logged bug on the last day of Thesprint. It was fixed and deployed before sprint prep, QA didn't get time to complete it. GGO-14070 - Development took a lot of time and got completed only on 1 day before Sprint end, the offshore QA logged a minor bug on the last day of sprint, fixed the bug and PR created for review. (Saranya worked on the RDLC report for the first time and there was a learning curve involved which took time)
NA | GGO 7.22.0 Sprint 4 | 2025-02-21 | 2025-03-06 | 20 | 15 | 2/0 |  | CRT Release & Regression testing for GGO 7.22.0 and PAPI 7.17.0 | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 4 External Defects: 0 Reason for pending: GGO-14510 - Bootstrap update - Development and Testing from Offshore got completed, the automation flow broken with this bootstrap update, so Nate created a automation change ticket under this story and this got carry forwarded to next sprint.
NA | GGO 7.23.0 Sprint 1 | 2025-03-07 | 2025-03-20 | 19 | 19 | 7/0 |  | Continued EMV Implementation and Infrastructure updates Allowed 19 digit card entry in GGAM, GGO and PAPI Cleared some Macroscope issues in PAPI Fixed cache issue in GGO Accomplishments: Addiitionally completed Developemnt for stretch goal stories | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 | Internal Retro 1. Sathiya/ Rajesh and Saranya for providing help to Priya testing the stories 2. Team for completing all the story points
NA | GGO 7.23.0 Sprint 2 | 2025-03-20 | 2025-04-03 | 13 | 19 | 10/0 |  | Completed Duplicate even code story and Invoice import and Invoice Payment Pages story Fixed Quartz Job access issues and Email Queue Issues. Accomplishments: Completing the development and testing for lot of stretch goal stories on the current sprint | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 2 External Defects: 0 Pending Story: 2 Stories has been carried forward 1.GGO-14573 -Hard to reproduce in the lower environements. The offshore developers made several attempts to reproduce the issue, but because it’s related to performance, it took a considerable amount of time to replicate. That’s why it got carried over. 2.PAPI-839(Stretch Goal) -Dependency on Onsite QA to complete it(Offshore QA has already completed testing for this story) | Retro: 1.Rajesh for supporting multiple escalation issues 2.Sathiya/ Rajesh and Saranya for covering such a wide spread of stories 3.Priya for completing the testing for the planned as well as lot of stretch jiras
NA | GGO 7.23.0 Sprint 3 | 2025-04-04 | 2025-04-17 | 22 | 24 | 6/0 |  | Completed Multiple RSVP Imports Accomplishments: Did some Redis changes which was very challenging and OP to GGO import timeouts(which is a esclation ticket) Completing the development for the stretch goal stories on the current sprint | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 Pending Story: 2 stories has been carried forward which includes 1 stretch PAPI-840(8spt)and GGO-14644[Stretch] -Development for this story was completed three days ahead of the sprint deadline. However, a last-minute AC request from the client required code modifications, which were implemented the timeline.The story was left in Peer Review upon completion, per the client's request to hold it and maintain this branch separately from the CERT branch.Offshore QA has completed verification in the lower environment. The story is now pending validation from Onsite QA. | Rajesh and offshore for taking the redis changes which was very challenging
NA | GGO 7.23.0 Sprint 4 | 2025-04-18 | 2025-05-01 | 23 | 27 | 5/0 |  | Accomplishments: Completed CRT testing Completed all planned stories and more Okta 1 Proof of concept Completed more macroscopic stories | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 Pending Story: 2 stories has been carried forward GGO-13722 ->we documented the alternative encryption change, client wanted to add new feature flag based on that need to follow the old and new encryption flow GGO-13723 ->we documented the alternative encryption change, client wanted to add new feature flag based on that need to follow the old and new encryption flow | To the whole team for helping remove all the blockers for testing Rajesh and offshore for helping with the fallback cases Rajesh for assisting with integrating the Okta proof-of-concept
NA | GGO 7.24.0 Sprint 1 | 2025-05-02 | 2025-05-15 | 19 | 16 | 2/0 |  | Accomplishments: Old Amex certification testing Nav Bar Updation Fixed Dashboard generation Issue and Enabled Online Bidding for the same Fixed Export Sales issue Completed more macroscopic stories | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending Story: 2 stories has been carried forward GGO-14628->Hard to reproduce in the lower environements. The offshore developers and QA's made several attempts to reproduce the issue, However, on the last day of the sprint,we found one way to reproduce it. But team need to ensure this after providing the solutions and to check whether this the cause of this issue. Team is still working on it.That’s why it got carried over. GGO-14656->Reskin-V2 is a complete overhaul of the existing Master Page. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness. Its taking more time to complete this story | Rajesh and Sathiyabharathi for working on the Nav bar update. Rajesh for helping with the Escalation issue
NA | GGO 7.24.0 Sprint 2 | 2025-05-16 | 2025-05-29 | 26 | 23 |  |  | Accomplishments: Completed Pendo Implementation Completed Nav Bar Implementation Fixed Amex card disable for select organizations Fixed Sale Grid Export issue | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending Story: 1 story has been carried forward GGO-14628->Hard to reproduce in the lower environements. The offshore developers and QA's made several attempts to reproduce the issue. Team is still working on it.That’s why it was put on hold as it is of low priority | Rajesh and Sathiyabharathi for the Nav bar update. Rajesh and offshore team on the quick implementation of pendo. Mike Horihan gave Kudos for the quick Pendo implementation
NA | GGO 7.24.0 Sprint 3 | 2025-05-29 | 2025-06-12 | 14 | 6 | 5-removed |  | Accomplishments: Completed Reskin User Profile Development | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 3 External Defects: 0 Pending Story: 2 stories has been carried forward GGO-14682 and GGO-14683 - Reskin-V2 is a complete overhaul of the existing Master Page. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness. Its taking more time to complete this since UI design work is new to the development team and it is bit challenging too.Also for GGO-14682 ->Development took a lot of time and got completed only on 1 day before Sprint end, the offshore QA logged a bug on the last day of sprint | 1.Sathiyabharathi and Saranya for implementing most the design changes and making sure the existing workflow is in in place +2 2.Priya for testing all the changes before sending to the PR to onsite and identifying the bugs early. 3.Rajesh for helping multiple offshore teams and get them all set up and going
NA | GGO 7.24.0 Sprint 4 | 2025-06-12 | 2025-06-26 | 22 | 22 |  |  | Accomplishments: completed Reskin User Profile and Profject home. CRT Regression Completed for the release | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | Great job Team on completing all planned stories and more! It was well appreciated by everyone here at onsite. Sathiyabharathi and Saranya for focussing on project reskin Priya for completing CRT Regression and the sprint story testing Rajesh for managing all the different projects at the same time
NA | GGO 7.25.0 Sprint 1 | 2025-06-26 | 2025-07-10 | 20 | 10 |  |  | Accomplishments:Project home page and great progress in Supporter reskin design | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending :GGO-14687 and GGO-14802: 2 stories has been carried forward as we are currently working on the reskinning of the grid component. Once this is completed, the remaining stories for the upcoming sprints are expected to progress quickly. Informed to client as well | GGO Dev offshore team for reskin progress Rajesh for figuring out the SalesForce production issue Priya for doing a thorough testing before sending to Dev and TST
NA | GGO 7.25.0 Sprint 2 | 2025-07-10 | 2025-07-24 | 22 | 9 |  |  | Accompolishment : Supporter Grid Page and great progress in Common controls and Filters | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 3 External Defects: 0 Pending: 3 stories carried forward GGO-14688 - Can't able to complete the task as planned due to changes in the new layout design, which introduced additional controls and complexity. Also, another story GGO-14687 required more time than anticipated, which impacted the overall timeline." GGO-14802 - Development is completed. During testing,tester found 3 defects. 2 defects and this story also got carried forward. GGO-14724: Client requested to add few more things in the same story at the end of the sprint end. | What went well? Progress on OneTrust Closed several MacroScope Issues Kudos QA for testing so many stories Offsore developers for the supporter grid Development
NA | GGO 7.25.0 Sprint 3 | 2025-07-24 | 2025-08-07 | 24 | 14 |  |  |  | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 Pending: 2 stories carried forward GGO-14712 and GGO-14851- The design challenges in this story prevent us from reusing existing user controls in every controls
NA | GGO 7.25.0 Sprint 4 | 2025-08-07 | 2025-08-21 | 14 | 14 | Stretch - 6 |  | Accomplishments: Completed Advanced filter search(Sales & Payments) for View Supporters page | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 3 External Defects: 0 Pending: 2 stretch stories carried forward GGO-14858 - Development part is completed. Testing is in progress. GGO-14863 - Onetrust cookies are not deleting properly to reopen the onetrsut consent popup again when clicking Privacy option under User Profile | What went well? Finished all the BTT tests Kudos Offshore team for the reskin stuff is very complicated Prabhu for filling in for Rajesh
NA | GGO 8.0.0 Sprint 1 | 2025-08-21 | 2025-09-04 | 15 | 14 | Stretch - 5 Stretch Completed - 4 |  | Accomplishments: Completed the existing design layout issues with reskin enabled. Completed Advanced filter search(Bidders and Attendees, Staffs, Contributors and Fundaraisers) for View Supporters Page | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 Pending: 1 assigned story and 1 stretch story carried forward GGO-14875 - Onsite Dev-Mike Wall picked this story earlier did some basic changes due to design difficulties hand overed the story to offshore on 1-sep-25 and also So far, we’ve worked on implementing grid controls across all modules. The team is currently focused on the Create Pages as part of the redesign effort, which is taking additional time due to the complexity of the UI work. GGO - 14854 - Stretch stories - Development and Dev env testing completed from our QA. Pending for Review. | What went well? Completed more than planned Good progress on Filter and Item page Kudos Rajesh to cover the Demo today Offshore for progress on the create item ticket Offshore Donor team for completing all planned and more stories Praveen and Sathiyabharati for fixing the existing design layout issues with reskin enabled
NA | GGO 8.0.0 Sprint 2 | 2025-09-04 | 2025-09-18 | 12 | 11 | Stretch - 2 |  | Accomplishment: Completed the Item Page with the new UI design, conditional on reskin being enabled. | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 1 External Defects: 0 Pending: 1 assigned story carried forward Due to complications involving multiple user controls on the filter page, some functions within the new user control are not triggering as expected. Additionally, new controls were added which require further integration and testing to ensure smooth functionality. | What went well? Donor Api work went well Items page got done Pendo and one trust deployed to prod Kudos Praveen and Sathiyabharthi for finishing the Item story +1 Rajesh and Donor offshore team for the Donor API progress+1
NA | GGO 8.0.0 Sprint 3 | 2025-09-18 | 2025-10-02 | 15 | 15 | Stretch -2 |  | Accomplishment: Completed Saved Search and more than planned story points | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Completed more than planned story points Kudos Rajesh e for picking up the slack and working on the credit card stuff Conor for doing all the testing related to Carlos changing storage account settings in all Environments Offshore team booth GGO and GDONOr for completing all the planned stories and more Saranya and Sathiyabharti for completing the save search
NA | GGO 8.0.0 Sprint 4 | 2025-10-02 | 2025-10-16 | 13 | 13 | Stretch - 1 |  | Accomplishment: Completed Rich Text editor and Image Control (Multi Image chooser) | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Met the Sprint goal Kudos Rajesh for finding the needle in the hay stack, finding the root cause for Go time error GGO team for meeting the goal +1 Jennifer for keeping up with all the UI changes +1
NA | GGO 8.1.0 Sprint 1 | 2025-10-16 | 2025-10-30 | 17 | 12 |  |  | Accomplishment: Completed Group by Household functionality and fixed variuos issue in View Supporters Filter | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending: 1 assigned story carried forward GGO-14901 - Since the design is more complex for the manage images popup and focused on group items by household functionality in the view supporters filter | What went well? The team was able to respond to the Azure outage very fast Kudos Mike H: Rajesh for figuring out the Pendo One trust thing and RDLC receipt problem Rajesh: Offshore for implementing the household in the supporter grid +1 Conor for keeping up with everything on 2 teams +1 Priya for doing multiple round of testing household and CRT +1
NA | GGO 8.1.0 Sprint 2 | 2025-10-30 | 2025-11-13 | 23 | 23 | Stretch -1 |  | Accomplishment: Completed Manage pop up design changes and completed all planned and more | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Completed all planned and more Good feedback from CS, customers and Kisa during the Sprint review Kudos Conor Kudos to Rajesh for getting the hotfixes out quickly Mike H: The team for going over and beyond and the extra late nights Rajesh: Kudos to Conor and Priya for testing the hotfixes in all the environments Sathiya and Saranaya for the Manage pop up design changes.
NA | GGO 8.1.0 Sprint 3 | 2025-11-13 | 2025-11-27 | 19 | 24 | Stretch -3 2 stretch stories are completed. Development is completed for 1 story |  | Accomplishment: Completed all planned stories and more | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Completed all planned stories and more Kudos Conor Mike H: The whole team for another impressive Sprint especially Dev Rajesh: Offshore for completing the overall Sprint goal Priya and Conor for testing all kind of scenarios for current sprint stories Doug Thank you for the super quick turn around on the RSVP escalation Great work team!
NA | GGO 8.1.0 Sprint 4 | 2025-11-27 | 2025-12-11 | 21 | 21 | Stretch -2 GGO-15068 - Development completed. Testing is in progress GGO-15086 Development is in progress |  | Accomplishment: Completed more than planned and Create/Edit Package Page | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Completed more than planned Kudos Conor Priya for helping out with current sprint story testing Mike H: Rajesh for keeping up with everything and making sure the team is successful Conor and Priya for CRT regression and current sprint stories Keep up the good work!
NA | GGO 8.2.0 Sprint 1 | 2025-12-11 | 2026-01-08 | 30 | 39 | Stretch -5 4 Stretch stories completed 1 story is pending GGO-15123 - Development is completed |  | Accomplishment: Completed more than planned story points Completed Online Bidding Settings View/Edit Design Updated Supporter API for NextGen Completed no negative search for Sales and Payments | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Completed all planned and more stories even through the holidays Kudos Conor Mike H: Offshore is on autopilot Rajesh: Sathiyabharathi for the Online bidding settings Priya for general testing of all stories through the holidays(+1 Conor) Charles and Vishnu for completing the GGAM online activity story
NA | GGO 8.2.0 Sprint 3 | 2026-01-08 | 2026-01-22 | 22 | 19 |  |  | Accomplishment: Completed Duplicate EventXCode Completed Jscramber Implementation | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending: 2 assigned stories carried forward GGO-14628 Hard to reproduce the the Print invoice/receipt page issue in lower environment GGO-15135 Development and testing is completed by our end. Settings to be updated by Jscramber IT team | What went well? Sizable commit Completed Kudos Mike H: Team for getting sizable commit done Rajesh and Conor for managing 2 teams Rajesh: Kudos to GGO and GDON team for completing all the committed work
NA | GGO 8.2.0 Sprint 4 | 2026-01-22 | 2026-02-05 | 19 | 23 | 5 |  | Accomplishment: Refined Supporter Query | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending: 2 assigned stories carried forward GGO-14628 - For this issue, a temporary fix has been provided by the offshore development team. However, the client has requested a permanent fix with a different approach, so the story has been carried forward GGO-15140 - CRT regression testing has been completed by the offshore QA team. The onsite QA requested that this story be put on hold, as WAF testing is still pending on his side. Therefore, the story has been carried forward | What went well? Sizable commit completed Kudos Mike H: Rajesh for the refining the supporter query Rajesh: Offshore GGO and GDOn team for completing all the stories |  |  | 1 | 0.5
NA | GGO 8.3.0 Sprint 1 | 2026-02-05 | 2026-02-19 | 23 | 28 | 7 |  | Accomplishment: 1. Achieved a 20% usability improvement with the Reskin project, enhancing user experience and efficiency. 2. Successfully met the planned commit targets and seamlessly integrated additional patch work mid-sprint. 3. Thoroughly tested all report scenarios, ensuring quality and reliability. 4. Completed most of the report changes, driving progress forward. | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending: 1 story carried forward GGO-14628 - Development has been completed. Since we planned to provide a permanent fix, instead of calculating the mostRecentDate at the time of generating invoices or receipts, we decided to pre-calculate and update the relevant tables when associating sales with the corresponding payments. Initially, this logic was implemented in code, but later we moved it to triggers. As this is a major change, the testing effort required is significant, so the work has been carried forward. | What went well? Met the planned commit commit along with the patch work which was added mid sprint Kudos Mike H: The whole team for meeting the allocated story points Rajesh: Sathiyabharathi for fixing all the report bugs(+1 Jennifer) Conor and Priya for testing all the scenarios for the Report Saranya for the working on the Print email timeout issue GDON team for completing the planned stories Doug Finished most of the Report changes 20% improvement in usability with the Reskin project |  |  | 1 | 1
NA | GGO 8.3.0 Sprint 2 | 2026-02-19 | 2026-03-05 | 22 | 29 | 7 |  | Accomplishment: 1. Successfully met the planned commit targets 2. Successfully completed Print/Email invoice or receipts issue | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Met the planned commit Kudos Mike H: Rajesh for handling multiple teams here, handling the super difficult stories Rajesh: Offshore team for achieving the sprint goal |  |  | 1 | 1
NA | GGO 8.3.0 Sprint 3 | 2026-03-05 | 2026-03-19 | 23 | 26 | 4 |  | Accomplishment: 1. Successfully met the planned commit targets 2. Successfully completed RSVP Dashboard | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Completed all planned stories and more Kudos Mike H: Rajesh for getting the receipt print and duplicate bidder key tickets completed Conor for doing double duty and keep the operation afloat (+1 Rajesh) Rajesh for triple duty Rajesh: Whole GGo offshore team for achieving the goal(+1Mike H) Sathiyabharathi Paramasivam [C] for working on the RSVP functionality Jennifer Anthony Bosco [C] for always supporting the team and clarifying any question that the team has |  |  | 1 | 2
NA | GGO 8.3.0 Sprint 4 | 2026-03-19 | 2026-04-02 | 20 | 21 | 4 |  | Accomplishment: 1. Most of the planned sprint stories were successfully delivered. 2. Rajesh ensured smooth handling of LLBGen setup challenges, addressing edge cases and performance issues 3. Team members supported each other, with kudos highlighting individual and collective efforts. | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Pending: 1 stretch story carried forward GGO-12244 - Development was delayed because we received the setup file only on the last day of the sprint. | What went well? Completed most of the stories Kudos Mike H: Rajesh for keep it all coordinated specially the LLBGen files tones of edge cases fixed, performance Rajesh: Offshore team for completing the stories in the sprint |  |  | 4 | 4
NA | GGO 8.4.0 Sprint 1 | 2026-04-02 | 2026-04-16 | 20 | 28 | 10 | Successfully implemented Reskin design for Sales Page. Successfully implemented the Text Template and SMS request once the checkout is done , and implemented a new Donor API - CheckBidderHouseHold for both Individual and Household supported and Implemented the GetCreditCards API which was always returning as 2 - while updating the AddressTypeId | Accomplishment: 1. The team achieved timely completion of the majority of planned sprint stories, ensuring consistent progress toward project goals. 2. Fixed some synk vulnerability issues 3. API Support for mobile team | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories | What went well? Completed all the stories and some stretch Kudos Mike H: Rajesh and Conor for pulling double duty on teams Rajesh: Whole GGO and GDON offshore team for completing all the tickets Conor, Priya and Charles for completing the testing for all the stories |  |  | 4 | 4 | 1357
NA | GGO 8.4.0 Sprint 2 | 2026-04-16 | 2026-04-30 | 21 | 22 | 3 | This sprint's focus is to further develop the GGO Reskin for the Sales and Payments pages, which includes the Create/Edit Sales & Payments, Common Controls, and Advanced search functionalities. It also covers the page functionalities for Non-Admin users. Moreover, there are plans to work on the APIs for Donor Check-out and Check-in. Furthermore, the Username will be updated for receipt generation when requests are received from NextGen for the Mobile team. | Accomplishment: 1. Finished all the designated stories 2. Effectively executed the Reskin design for the Sales and Payments Page 3. Provided API support for the Mobile and Donor Team | Peer CRC:0 Onsite CRC: 1 1. Is there a common JavaScript file with this function in it to include instead of the inline javascript? Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories. | What went well? Rajesh and Conor did double duty as always and still managed to complete more than forecast Completed all the stories and some stretch Kudos Rajesh: Offshore GGO and GDon for completing all the stories Sathiyabharathi for completing the sales stories, as it was complex Priya for testing all the sales stories |  |  | 4 | 4 | 1330
NA | GGO 8.4.0 Sprint 3 | 2026-04-30 | 2026-05-14 | 20 | 21 | 3 | In this Sprint, we are continuing our efforts on the GGO Reskin for the Sales and Payments pages, which includes addressing some outstanding items concerning Manage Charge Batches. Additionally, we are implementing fixes for Priority defects, improving Infrastructure, and offering support for APIs associated with Donor Check-out. | Accomplishment: 1. Successfully achieved the Sprint objective 2. Completed the development of the Create Refund page - Edit Payments 3. Executed the implementation of the Manage Charge Batch pages within Sales & Payments 4. Certain Donor Check-in and API functionalities have been developed 5. A number of priority bugs have been fixed 6. Lastly, worked on some of the Synk findings | Peer CRC:0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 0 External Defects: 0 Completed all the assigned stories. | Well Done team in maintaining consistent Delivery! What went well? Completed all planned stories and more Kudos Mike H: Rajesh for supporting 3 teams and Conor for supporting 2 teams Rajesh: GGO and GDON offshore team for achieving the sprint goal (+1 Mike) |  |  |  |  | 1334
NA | GGO 8.4.0 Sprint 4 | 2026-05-14 | 2026-05-28 | 23

## Unplanned Leaves
Resource Name
Sprint Name | Priyadharshini Ravichandran | Saranya Namachivayam | Jennifer | Sathiyabharathi | Rajesh | Total Planned Leaves | Remarks
GGO 8.3.0 Sprint 1 (05-Feb-26 to 19-Feb-26) | 1 | 0 | 0 | 0 | 0 | 1
GGO 8.3.0 Sprint 2 (19-Feb-26 to 05-Mar-26) | 0 | 0 | 0 | 0 | 0 | 0
GGO 8.3.0 Sprint 3 (05-Mar-26 to 19-Mar-26) | 0 | 1 | 0.5 | 0 | 0 | 1.5
GGO 8.3.0 Sprint 4 (19-Mar-26 to 02-Apr-26) | 1 | 2 | 0 | 1 | 1 | 5
GGO 8.4.0 Sprint 1 (02-Apr-26 to 16-Apr-26) | 1 | 0 | 1 | 1 | 0 | 3
GGO 8.4.0 Sprint 2 (16-Apr-26 to 30-Apr-26) | 0 | 0 | 0 | 0 | 0 | 0
GGO 8.4.0 Sprint 3 (30-Apr-26 to 14-May-26) | 0 | 0 | 0.5 | 1 | 3 | 4.5
]

## GGO 8.4.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Saranya | GGO-15245 | Snyk Finding - Microsoft.AspNetCore.Server.Kestrel@2.2.0 update to 2.3.6 | Being Developed | 2 |  |  | 2026-05-15
2 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 |  | GGO-15170 | Employee Controls for Reports | Refinement | 5
3 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Saranya | GGO-14513 | Log Quartz Job errors in Elmah log | Being Developed | 2 |  |  | 2026-05-15
4 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Rajesh | PAPI-291 | PAPI is using an old version of LLBGEN i.e. 2.5. We need to upgrade to the latest LLBGen i.e. 5.8 | Being Developed | 3 |  |  | 2026-05-15
5 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 |  | GGO-15251 | Project Builder - Feature Flag to turn off/on the changes | Refinement | 2
6 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Sathiya | GGO-15219 | Project Builder - Create Project - Getting Started section | Being Developed | 5 |  |  | 2026-05-15
7 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Priya-QA | GGO-15242 | 19 May GGO 8.4.0 CRT Release & Regression testing | Refinement | 3
8 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 8.4.0 Sprint 4 | Priya-QA | PAPI-898 | 19 May PAPI 8.2.0 CRT Release & Regression testing | Refinement | 1

## GGO 8.4.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.4.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Saranya | GGO-15229 | Edit Payments - Create Refund page | Completed | 2 | 2 | 14 | 2026-04-04 | 2026-05-05 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9520 | 2026-04-29 | 2026-05-05 | Rajesh |  | Mike Horihan | 2026-05-06 |  |  |  | Created a enhanced refund page on 04/29/2026 Unit testing done and Created a PR on 04/30/2026. Testing Completed in the TST env
2 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Rajesh | GGO-15230 | Validate Sales Force Invoice Posted Items API flow with real data | Completed | 2 | 2 | 12 | 2026-05-01 | 2026-05-13 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9562 | 2026-05-13 | NA | NA |  | Mike Horihan | 2026-05-13 |  |  |  | Testing Completed in the TST env
3 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Rajesh | GGO-15216 | Online Bidding setup opens Old UI instead of New Online Bidding UI | Completed | 1 | 1 | 11 | 2026-05-01 | 2026-05-01 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9532 | 2026-05-05 | NA | NA |  | Mike Horihan | 2026-05-05 |  |  |  | Testing Completed in the TST env
4 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Rajesh | GGO-15218 | New GGO Clients are not setup with bluetooth | Completed | 2 | 2 | 5 | 2026-05-01 | 2026-05-05 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9533 | 2026-05-05 | NA | NA |  | Mike Horihan | 2026-05-05 |  |  |  | Testing Completed in the TST env
5 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Sathiya | GGO-14911 | Sales & Payments - Manage Charge Batches | Completed | 5 | 5 | 44.5 | 2026-05-04 | 2026-05-06 | Done | Priya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9535 | 2026-05-06 | 2026-05-06 | NA |  | Mike Horihan | 2026-05-06 |  |  |  | Copied all the necessary files from oldl ayout 05/04/2026 Created an enhanced charge batch page 05/05/2026 Unit testing done and Created a PR on 05/06/2026. Testing Completed in the TST env
6 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Saranya | GGO-14912 | Sales & Payments - View Charge Batch Page | Completed | 5 | 5 | 54.5 | 2026-05-04 | 2026-05-08 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9550 | 2026-05-08 | NA | NA |  | Mike Horihan | 2026-05-11 |  |  |  | Copied all the necessary files from old ayout 05/04/2026 Created an enhanced charge batch page 05/05/2026 Created an enhanced declined page on 05/06/2026 Incorporated UI changes suggested by Jennifer on 05/07/2026 Unit testing done and Created a PR on 05/08/2026. Testing Completed in the TST env
7 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Rajesh | GGO-15150 | BID-10 report not showing image | Completed | 2 | 2 | 5 | 2026-05-04 | 2026-05-06 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9537 | 2026-05-06 | NA | NA |  | Mike Horihan | 2026-05-06 |  |  |  | Testing Completed in the TST env
8 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 | Saranya | GGO-15157 | Lack of ConvenienceFeeRate in sectionGridSettings causes error | Completed | 1 | 1 | 9 | 2026-05-11 | 2026-05-11 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9556 | 2026-05-11 |  | Rajesh |  | Mike Horihan |  |  |  |  | Fixed ConvenienceFeeRate issue in SectionGrid Settings, Unit testing done and Created a PR on 05/11/2026. Testing Completed in the TST env
9 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 [STRETCH] | Sathiya | GGO-15247 | Snyk Finding - System.Security.Cryptography.Xml@8.0.2 update to 8.0.3 | Completed | 1 | 1 | 28 | 2026-05-12 | 2026-05-12 | Done | Priya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9560 | 2026-05-12 | 2026-05-12 | Rajesh |  | Mike Horihan | 2026-05-12 | Also seeing the reference in GreaterGiving.Online.Website.Reskin |  |  | Updated package version did dev testing PR created 05/12/2026 Addressed code review comments . Updated package across all the solution did dev testing PR updated 05/13/2026. Testing Completed in the TST env
10 | GGO Web | 2026-04-30 | 2026-05-14 | GGO 8.4.0 Sprint 3 [STRETCH] | Saranya | GGO-15245 | Snyk Finding - Microsoft.AspNetCore.Server.Kestrel@2.2.0 update to 2.3.6 | Being Developed | 2 | 0 | 12 | 2026-05-13

## GGO 8.4.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.4.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Saranya | GGO-14792 | View Payments Page | Completed | 1 | 1 | 13 | NA | NA | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio .com/Greater%20Giving/_git/GGO/ pullrequest/9464 | 2026-04-13 | 2026-04-17 | Rajesh |  | Mike Horihan | 2026-04-18 | No concerns have been noted up to this point; it will be rolled over. |  |  | Payments Grid new reskin design implementation started on 04/10/2026 Developement and testing completed. Created a PR on 04/13/2026
2 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Saranya | GGO-14818 | View Payments Common controls | Completed | 1 | 1 | 12 | NA | NA | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio .com/Greater%20Giving/_git/GGO/ pullrequest/9464 | 2026-04-13 | 2026-04-17 | Rajesh |  | Mike Horihan | 2026-04-18 | No concerns have been noted up to this point; |  |  | Implemented Payments Grid common controls and testing completed. Created a PR on 04/13/2026
3 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Saranya | GGO-14820 | View Payments Advanced search | Completed | 2 | 2 | 29 | 2026-04-17 | 2026-04-22 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9485 | 2026-04-17 | 2026-04-22 | Rajesh |  | Mike Horihan | 2026-04-22 | Is there a common JavaScript file with this function in it to include instead of the inline javascript? |  |  | Implemented Payment Advanced search filters and Unit Testing done on 04/17/2026 Moved Payment Reference # serach into Advanced Search Filter and tested on 04/21/2026 Incorporated code review comments given by MikeH and tested on 04/22/2026
4 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Sathiya | GGO-14791 | Create/Edit Sales page | Completed | 5 | 5 | 52 | 2026-04-17 | 2026-04-23 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9501 | 2026-04-23 | 2026-04-28 | Rajesh |  | Mike Horihan | 2026-04-28 |  |  |  | Started implementing Create/Edit Sales Page on 04/17/2026 Started to implement details tab on 04/20/2026. Started to implement purchaser tab on 04/21/2026. Started to implement admission tab on 04/22/2026 Admisson tab grid design update on 04/23/2026 Details tab rsvp url design update on 04/24/2026 Completed Testing
5 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Sathiya | GGO-15209 | View Sales page for Non-Admin users | Completed | 3 | 3 | 21 | 2026-04-27 | 2026-04-28 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9516 | 2026-04-28 | 2026-04-29 | Rajesh |  | Mike Horihan | 2026-04-29 |  |  |  | Design update for non-admin users on 04/28/2026 Jennifer gave some inputs changing the control design applied the design on 04/28/2026
6 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Saranya | GGO-14793 | Create/Edit Payment page | Completed | 5 | 5 | 33 | 2026-04-20 | 2026-04-27 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9512 | 2026-04-27 | 2026-04-28 | Rajesh |  | Mike Horihan | 2026-04-29 |  |  |  | Started implementing Create/Edit Payment Page on 04/20/2026. Worked on Grid changes on 04/23/2026 Worked on alignment issues and new Datepicker on 04/24/2026 Implemented indeterminate checkbox on 04/27/2026 Verified in the Dev env. 4/28/2026 3:54 PM
7 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Saranya | GGO-15210 | View Payments page for Non-Admin users | Completed | 3 | 3 | 12 | 2026-04-27 | 2026-04-28 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9512 | 2026-04-27 | 2026-04-28 | Rajesh |  | Mike Horihan | 2026-04-29 |  |  |  | Started implementing view payments for non-admin user on 04/27/2026 Unit testing done and created a PR on 04/28/2026
8 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 | Rajesh | GGO-15215 | Update Username for receipt generation when receiving the request from NextGen | Completed | 1 | 1 | 10 | 2026-04-20 | 2026-04-23 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9503 | 2026-04-23 | NA | NA |  | Patterson, Scott | 2026-04-24 |  |  |  | Implemented passing username as a parameter in cookie header from nextgen API instead of using AesopSession username on 04/20/2026 Fixed invoice generation error on 04/21/2026 Unit testing done and Created a PR on 04/23/06
9 | GGO Web | 2026-04-16 | 2026-04-30 | GGO 8.4.0 Sprint 2 [STRETCH] | Saranya | GGO-15229 | Edit Payments - Create Refund page | Being Developed | 3 | 1 | 12 | 2026-04-29 | 2026-04-30 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9520 | 2026-04-29 |  | Rajesh |  | Mike Horihan |  |  |  |  | Created a enhanced refund page on 04/29/2026 Unit testing done and Created a PR on 04/30/2026

## GGO 8.4.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.4.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Rajesh | GGO-12244 | LLBGen Upgrade to the latest version | Completed | 2 | 2 | 18 | 2026-03-20 | 2026-04-01 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9424 | 2026-04-01 | 2026-04-01 | Rajesh |  | Mike Horihan | 2026-04-02 |  |  |  | Got LLBLGen 5.10.1 setup file and started to work on it on 03/30/2026 Completed development, PR created and sent it to Approval on 04/01/2026 Testing completed in the TST env.
2 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Saranya | GGO-15169 | API update to provide card expiration date to next gen | Completed | 1 | 1 | 6 | 2026-04-01 | 2026-04-01 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9426 | 2026-04-02 | 2026-04-04 | Rajesh |  | Mike Horihan | 2026-04-06 |  |  |  | Development is completed in previous sprint itself. Testing completed in the TST env.
3 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Rajesh | GGO-15174 | Remove Deleted Package from ap_OnlineBiddingSettings featuredPackageIDs Column | Completed | 2 | 2 | 4 | 2026-04-03 | 2026-04-03 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9431 | 2026-04-03 | NA | Na |  | Mike Horihan | 2026-04-03 |  |  |  | Development is completed. Unit testing is done and Created a PR on 04/03/2026. Testing completed in the TST env.
4 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Saranya | GGO-15186 | Snyk Findings - form-data@4.0.0 | Completed | 2 | 2 | 12 | 2026-04-03 | 2026-04-06 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9440 | 2026-04-06 |  | Rajesh |  | Mike Horihan | 2026-04-07 |  |  |  | Started upgrading form-data package from 4.0.0 to 4.0.4 for angular project and facing some issues on 04/03/2026 Fixed issue. Testing is done and Created PR on 04/06/2026. Testing completed in the TST env.
5 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Saranya | GGO-15187 | Snyk Finding - ajv@8.12.0 | Completed | 2 | 2 | 7 | 2026-04-03 | 2026-04-03 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9436 | 2026-04-03 | NA | NA |  | Mike Horihan | 2026-04-06 |  |  |  | Upgraded ajv package from 8.8.0 to 8.18.0 for angular project. Testing is done and Created PR on 04/03/2026. Testing completed in the TST env.
6 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Sathiya | GGO-14790 | View Sales page | Completed | 3 | 3 | 38.5 | 2026-04-03 | 2026-04-06 | Done | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9433 | 2026-04-06 | 2026-04-10 | Rajesh |  | Mike Horihan | 2026-04-10 | There was an issue with the text alignment that has been addressed and completed. |  |  | Need to verify in local and dev since implementation is completed on 04/03/2026 Verified in DEV environment. Published the PR on 04/06/2026. Testing completed in the TST env.
7 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Sathiya | GGO-14819 | View Sales Advanced search | Completed | 5 | 5 | 29 | 2026-04-06 | 2026-04-08 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9450 | 2026-04-08 | 2026-04-14 | Rajesh |  | Mike Horihan | 2026-04-14 | Detected a few problems and rectified some; the remaining issues will be addressed in the forthcoming story. |  |  | Started View sales advanced search on 04/06/2026 Fixed issues in Frozen column on 04/09/2026 PackageNumber and BidderNumber search make confusion on grid result Asked PO for the clarification on 04/10/2026 Moved package search to advanced search section on 04/14/2026 Testing completed in the TST env.
8 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 | Sathiya | GGO-14817 | View Sales common controls | Completed | 3 | 3 | 28 | 2026-04-03 | 2026-04-06 | Done | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9433 | 2026-04-06 | 2026-04-10 | Rajesh |  | Mike Horihan | 2026-04-10 | Implemented successfully |  |  | Need to verify in local and dev since implementation is completed on 04/03/2026 Verified in DEV environment. Published the PR on 04/06/2026. Testing completed in the TST env.
9 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 [STRETCH] | Sathiya | GGO-15201 | Investigate Snyk Finding - @angular/compiler-cli@16.2.8 | Completed | 2 | 2 | 7.5 | 2026-04-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Snyk fix require to update angular version from 8 to 19+ and Updated comments in Jira on 04/14/2026
10 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 [STRETCH] | Saranya | GGO-15145 | Error on Merge with proccessedInvoice | Completed | 2 | 2 | 14 | 2026-04-08 | 2026-04-10 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com /Greater%20Giving/_git/GGO/ pullrequest/9455 | 2026-04-09 | 2026-04-11 | Rajesh |  | Mike Horihan | 2026-04-11 |  |  |  | Started analyzing the issue and tried to reprduce the issue in TST ENV on 04/09/2026 Fixed the issue wih replacing target SupporterId with Source SupporterId while megring two supporters on 04/10/2026 Unit Testing is done on 04/11/2026
11 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 [STRETCH] | Saranya | GGO-14792 | View Payments Page | Being Developed | 3 | 2 | 26 | 2026-04-10 | 2026-04-13 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio .com/Greater%20Giving/_git/GGO/ pullrequest/9464 | 2026-04-13 |  | Rajesh |  | Mike Horihan |  | No concerns have been noted up to this point; it will be rolled over. |  |  | Payments Grid new reskin design implementation started on 04/10/2026 Developement and testing completed. Created a PR on 04/13/2026
12 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 [STRETCH] | Saranya | GGO-14818 | View Payments Common controls | Being Developed | 1 | 0 | 15 | 2026-04-13 | 2026-04-13 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio .com/Greater%20Giving/_git/GGO/ pullrequest/9464 | 2026-04-13 |  | Rajesh |  | Mike Horihan |  | No concerns have been noted up to this point; |  |  | Implemented Payments Grid common controls and testing completed. Created a PR on 04/13/2026
13 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 [STRETCH] | Rajesh | GGO-15204 | Fundraising Signup Issue - Could not load file or assembly 'System.ValueTuple, Version=4.0.0.0, Culture=neutral, PublicKeyToken=cc7b13ffcd2ddd51' or one of its dependencies. The system cannot find the file specified. | Completed | 1 | 1 | 7 | 2026-04-15 | 2026-04-15 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9471 | 2026-04-15 | NA | Rajesh |  | Mike Horihan | 2026-04-15
14 | GGO Web | 2026-04-02 | 2026-04-16 | GGO 8.4.0 Sprint 1 [STRETCH] | Rajesh | GGO-15206 | Add Index to OnlineBidderKey for ap_OnlineBidder table | Completed | 1 | 1 | 1 | 2026-04-15 | 2026-04-15 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9478 | 2026-04-16 | NA | NA |  | Mike Horihan | 2026-04-16 |  |  |  | Migration script added for creating index for ap_OnlineBidder table for this issue and Unit testing done on 04/15/2026

## GGO 8.4.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.3.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Tester Comments | Developer Comments
1 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Saranya | GGO-15048 | API Update for Next Gen - Invoicing Email | Completed | 1 | 1 | 22.5 | NA | NA | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9387 | 2026-03-18 | 2026-03-20 | Rajesh |  | Mike Horihan | 2026-03-21 |  |  |  | Testing completed in the TST env
2 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Sathiya | GGO-15185 | OB Edit Image Upload issue | Completed | 1 | 1 | 8 | NA | NA | Done | Priya |  | Rajesh | NA | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9393 | 2026-03-20 | 2026-03-20 | Rajesh | NA | NA | NA | NA | NA | NA+ | Testing completed in the TST env | Fixed the issue and created the PR on 03/20/26
3 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Rajesh | GGO-12244 | LLBGen Upgrade to the latest version | Ready for Testing | 5 | 3 | 28 | 2026-03-20 | 2026-04-01 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9424 | 2026-04-01 | 2026-04-01 | Rajesh |  | Mike Horihan | 2026-04-02 |  |  |  |  | Got LLBLGen 5.10.1 setup file and started to work on it on 03/30/26 Completed development, PR created and sent it to Approval on 04/01/2026
4 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Sathiya | GGO-15167 | OB Settings - Donation Bar | Completed | 3 | 3 | 25.5 | 2026-03-23 | 2026-03-25 | Done | Priya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9402 | 2026-03-24 | 2026-03-25 | Rajesh |  | Mike Horihan | 2026-03-26 |  |  |  |  | Verified in dev flag value pushed to the OB queue correctly and created PR on 03/25/26
5 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Saranya | GGO-12200 | Consolidate Nuget Packages | Completed | 3 | 3 | 52.5 | 2026-03-20 | 2026-03-30 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9413 | 2026-03-30 | 2026-03-31 | Rajesh |  | Mike Horihan | 2026-03-31
6 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Rajesh | GGO-13962 | Update NuGet Authenticate in Azure Pipeline | Completed | 2 | 2 | 6 | 2026-03-20 | 2026-03-24 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9400 | 2026-03-24 | NA | NA |  | Mike Horihan | 2026-03-25 |  |  |  |  | Started development on 03/20/26 Completed development and created PR on 03/24/26
7 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Sathiya | GGO-12282 | Replace DLL direct references with NuGet packages | Completed | 2 | 2 | 15.5 | 2026-03-25 | 2026-03-25 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9412 | 2026-03-30 | 2026-03-30 | Rajesh |  | Mike Horihan | 2026-03-31 |  |  |  |  | [26-Mar-26] Except Nevron.dll we can't remove other dll's for above reason. all are third party dll's can't find in NuGet
8 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 | Priya-QAa | GGO-15182 | 24 Mar GGO 8.3.0 CRT Release & Regression testing | Completed | 3 | 3 | 36 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Testing completed in the CRT env
9 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 [STRETCH] | Saranya | GGO-15173 | API Update for Card Entry Permissions in Go Time | Completed | 2 | 2 | 8 | 2026-03-31 | 2026-03-31 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9422 | 2026-03-31 | 2026-03-31 | Rajesh |  | Mike Horihan | 2026-04-01 |  |  |  |  | Analyzing existing GetCards API and added additional property(EditCreditCards) for NextGen and Testing completed in Local and Dev Env on 03/31/2026
10 | GGO Web | 2026-03-19 | 2026-04-02 | GGO 8.3.0 Sprint 4 [STRETCH] | Saranya | GGO-15169 | API update to provide card expiration date to next gen | Being Developed | 2 | 1 | 8 | 2026-04-01 | 2026-04-01 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9426 | 2026-04-02 |  | Rajesh |  | Mike Horihan | [5 empty] | Analyzing existing GetCards API and added additional property(CardExpirationDate) for NextGen and Testing completed in Local and Dev Env on 04/01/2026

## GGO 8.3.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.3.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Tester Comments | Developer Comments
1 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Rajesh | GGO-15147 | RSVP - Special Characters During Import for Apostrophe and Ampersand | Completed | 1 | 1 | 11 | 2026-03-09 | 2026-03-10 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9360 | 2026-03-11 | NA | NA |  | Mike Horihan | 2026-03-11 |  |  |  |  | Fixed RSVP Special charcters issue during import on 03/09/2026 Tested and Created a PR on 03/10/2026
2 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Rajesh | GGO-15165 | Unicode Characters in Item Descriptions | Completed | 2 | 2 | 6 | 2026-03-06 | 2026-03-06 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9348 | 2026-03-06 | NA | NA |  | Mike Horihan | 2026-03-07 |  |  |  |  | Reproduced issue in TST environment, development completed by handling the Unicode char for the item and package description. 100% development completed and shared PR to client on 03/06/2026
3 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Rajesh | GGO-15047 | API Update for Next Gen - Invoicing Available | Completed | 2 | 2 | 11 | 2026-03-06 | 2026-03-06 | Done | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9351 | 2026-03-09 | NA | NA |  | Mike Horihan | 2026-03-09 |  |  |  |  | Created new GoTime API to check the invoicing status and return response to Mobile Team. 100% development completed and shared PR to client on 03/06/2026
4 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Sathiya | GGO-14809 | Manage Project - RSVP Dashboard - Admission, Admission by Package and Meal Types grids | Completed | 3 | 3 | 25 | 2026-03-06 | 2026-03-10 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9359 | 2026-03-10 | 2026-03-11 | Rajesh |  | Mike Horihan | 2026-03-11 |  |  |  |  | Development started on 03/10/2026 Did local and dev testing and created PR on 03/10/2026
5 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Sathiya | GGO-14812 | Manage Project - RSVP Dashboard | Completed | 5 | 5 | 47.25 | 2026-03-10 | 2026-03-16 | Done | Priya |  | Saranya/Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9380 | 2026-03-16 | 2026-03-17 | Rajesh |  | Mike Horihan | 2026-03-17 |  |  |  |  | Implemented rsvp grid on 03/13/2026 Develoment completed fixing minor UI issues on 03/16/2026
6 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Rajesh | GGO-15162 | Scroll bar issue in PRD - View Packages | Completed | 2 | 2 | 6 | 2026-03-12 | 2026-03-13 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9371 | 2026-03-13 | NA | Rajesh |  | Mike Horihan | 2026-03-13 |  |  |  |  | Reproduced issue in TST environment with help of customer service team took some time to fix this issue. 100 % development completed and shared PR to client on 03/13/2026
7 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Saranya | GGO-15038 | Data not importing in from OP RSVP | Completed | 2 | 2 | 23 | 2026-03-06 | 2026-03-12 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9368 | 2026-03-12 | 2026-03-12 | Rajesh |  | Mike Horihan | 2026-03-13 |  |  |  |  | Trying to reproduce this issue. But unable to reproduce in Local, Dev, TST and CRT on 03/06//2026
8 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Saranya | GGO-15160 | Streamline Support Redirect from Equipment Express | Completed | 3 | 3 | 23 | 2026-03-10 | 2026-03-12 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9358 | 2026-03-10 | 2026-03-12 | Rajesh |  | Mike Horihan | 2026-03-12 |  |  |  |  | Development 90% Completed. Created Banner and Popup to redirect Streamline support from Equipment Express. Testing is inprogress on 03/10/2026
9 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 | Sathiya | GGO-14810 | Manage Project - RSVP Dashboard - Search field and Send Letters & Emails button | Completed | 3 | 3 | 16.5 | 2026-03-10 | 2026-03-16 | Done | Priya |  | Saranya/Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9380 | 2026-03-16 | 2026-03-17 | Rajesh |  | Mike Horihan | 2026-03-17 |  |  |  |  | Implemented search functionality on 03/13/2026 Develoment completed fixing minor UI issues on 03/16/2026
10 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 [STRETCH] | Rajesh | GGO-15178 | Un-hide PKG-06en | Completed | 1 | 1 | 3 | 2026-03-18 | 2026-03-18 | Done | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9384 | 2026-03-18 | NA | NA |  | Mike Horihan | 2026-03-18 |  |  |  |  | Fixed unhide PGK report and testing completed and Created PR on 03/18/2026
11 | GGO Web | 2026-03-05 | 2026-03-19 | GGO 8.3.0 Sprint 3 [STRETCH] | Saranya/Sathiya | GGO-15048 | API Update for Next Gen - Invoicing Email | Being Developed | 3 | 2 | 47.5 | 2026-03-16 | 2026-03-19 | Done | [15 empty] | Analyzing existig Email functionality to create new API for NextGen on 03/16/2026 Created a new API to Send Email Invoice for nextgen on 03/18/2026 Testing in Local and Dev Env on 03/19/2026

## GGO 8.3.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.3.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Tester Comments | Developer Comments
1 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Rajesh/Saranya | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Completed | 2 | 2 | 41 | 2026-02-06 | 2026-02-18 | Done | Priya | No Defects | Rajesh | NA | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9303 | 2026-02-19 | 2026-02-20 | Rajesh |  | Mike Horihan | 2026-02-20 | Is this change related to the Timeout Issue? | NA | NA | Testing Completed in the TST env | 23/2/2026 - Testing is inprogress in TST. Found one issue 24/2/2026 - Fixed the issue and deployed in DEV env and Testing is inprogress
2 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Sathiya/Praveen | GGO-14874 | Reports and Exports - View Report Page | Completed | 3 | 3 | 31.5 | 2026-02-20 | 2026-02-23 | Done | Priya | GGO-15163 | Rajesh | NA | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9312 | 2026-02-23 | 2026-02-24 | Rajesh |  | Mike Horihan | 2026-02-25 |  | NA | NA | Testing Completed in the TST env | 20/2/2026 - Sorting order changed on search 23/2/2026 - Loaded all the reports section and created PR
3 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Saranya | GGO-15076 | API Update for Next Gen - Checkout | Completed | 5 | 5 | 38 | 2026-02-20 | 2026-02-26 | Done | Priya |  | Rajesh | NA | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9334 | 2026-02-28 | 2026-02-28 | Rajesh |  | Mike Horihan | 2026-02-28 |  | NA | NA | Raised bug 9:00 PM 3/3/2026 | 20/2/2026 - Analysing checkout recorded against the admission- similar to check-in 23/2/2026 - Analysing the existing functionality of checkin and checkout API's 24/2/2026 - Implemented code 20% 25/2/2026 - Added new API to update attendee's chekout info and fetch the same info in GetCheckinDetails API 26/2/2026 - Dev testing is completed and Created a PR
4 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Rajesh | GGO-15105 | Update to GGO GPPostedInvoiceItems Data | Completed | 5 | 5 | 19 | [7 empty] | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9325 | 2026-02-27 | 2026-02-27 | Rajesh |  | Mike Horihan | 2026-02-28 |  |  |  | Testing Completed in the TST env
5 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Saranya | PAPI-893 | Investigation into PAPI Client & Settlement Data | Completed | 2 | 2 | 22 | 2026-02-26 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 26/2/2026 - Started analysing PAPIClients from OPSStaging Database 27/2/2026 - Documentaion preparation
6 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Sathiya | GGO-11918 | Sponsor imgs not updating for non ob projects on displays | Completed | 3 | 3 | 14.5 | 2026-02-25 | 2026-02-25 | Done | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9320 | 2026-02-25 | 2026-02-26 | Rajesh |  | Mike Horihan | 2026-02-26 |  | NA | NA | Testing Completed in the TST env | 25/2/2026 did SP changes verified in dev environment
7 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Sathiya/Rajesh | GGO-15152 | Telerik Shared Library Issue | Completed | 1 | 1 | 6.5 | 2026-02-26 | 2026-02-26 | Done |  |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9326 | 2026-02-27 | 2026-02-27 | Rajesh |  | Mike Horihan | 2026-02-27 |  | NA | NA | Testing Completed in the TST env | 26/02/2026 Fixed mentioned CSP issue by adding data: in the iframe src now facing new CORS issue on Jscrambler 27/02/2026 Created PR
8 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 | Rajesh | GGO-15149 | Update SkiSharp to version 2.88.6 in GGOImageTransferApp | Completed | 1 | 1 |  |  |  | Done |  |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9314 | 2026-02-23 | 2026-02-27 | Rajesh |  | Mike Horihan | 2026-02-27 |  | NA | NA | Testing Completed in the TST env
9 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 [STRETCH] | Sathiya | GGO-14561 | Bidder was assigned reused URL that led to another org | Completed | 5 | 5 | 55 | 2026-02-27 | 2026-03-05 | Done | NA | NA | NA |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9339 | 2026-03-03 | 2026-03-04 | Rajesh |  | Mike Horihan | 2026-03-04 |  | NA | NA | Testing Completed in the Dev env. 9:00 PM 3/3/2026 | 27/02/2026 - created the new function and calling old function in it 02/03/2026 - WITH EXECUTE AS CALLER and UNIQUE KEY constraint is necessary to add 03/03/2026 - Provided the script to checking the duplicates and updated verified locally 04/03/2026 - Rajesh maodified the script and updated OnlineBidding Script 05/03/2026 - Change log created and updated script verified in local
10 | GGO Web | 2026-02-19 | 2026-03-05 | GGO 8.3.0 Sprint 2 [STRETCH] | Saranya | GGO-11722 | Discount code not able to update when set to fixed type | Completed | 2 | 2 | 8 | 2026-03-03 | 2026-03-04 | Done | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9343 | 2026-03-04 | 2026-03-04 | Rajesh |  | Mike Horihan | 2026-03-04 |  | NA | NA | Testing Completed in the TST env | 3/3/2026 - Started analyzing about Dicount Codes 4/3/2026 - Fixed this issue and Unit testing is done. Created PR

## GGO 8.3.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 8.3.0 Sprint 2 | GGO-15163 | GGO-14874 | Sathiya | Bounceback/Sub-Defect | View Report- Text Does Not Highlight in Blue After Generating Report | Minor | Manual | Internal | Closed | Design | Priya | Minor UI issues
| GGO 8.3.0 Sprint 2 | GGO-15166 | GGO-15076 | Saranya | Bounceback/Sub-Defect | isCheckedOut flag is required for household members in API response | Significant | Manual | Internal | Closed | Design | Priya | Requested by the Mobile team to add a flag
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.3.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Tester Comments | Developer Comments
1 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Sathiya | GGO-15103 | Optout.aspx.cs Exception | Completed | 1 | 1 | 6.5 | 2026-02-05 | 2026-02-05 | Done | Priya | No Defects |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9260 | 2026-02-05 | [8 empty] | Testing completed in the TST env | 2/5/2026 - Fixed decryption issue and verified in DEV. Created PR
2 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Priya-QA | GGO-15140 | 27 Jan GGO 8.2.0 CRT Release & Regression Testing | Completed | 1 | 1 | 16 | NA | NA | Done | Priya | No Defects | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in CRT env. | CRT regression testing has been completed by the offshore QA team. The onsite QA requested that this story be put on hold, as WAF testing is still pending on his side. Therefore, the story has been carried forward
3 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Saranya | GGO-13847 | Disable/Hide the Reports | Completed | 5 | 5 | 10 | 2026-02-06 | 2026-02-06 | Done | Priya | The migration script missed one report name in the delete statement. | Rajesh | NA | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9263 | 2026-02-07 | 2026-02-07 | Rajesh | NA | Mike Horihan | 2026-02-07 | NA | NA | NA | Testing completed in the TST env | 2/6/2026 - Created migration script to delete the reports which was mentioned in the story. Unit testing is done and Created PR
4 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Sathiya/Praveen | GGO-14865 | Reports and Exports page - Left nav and Header section | Completed | 3 | 3 | 18.5 | 2026-02-06 | 2026-02-10 | Done | Priya | No Defects | Rajesh | NA | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9269 | 2026-02-10 | 2026-02-12 | Rajesh | NA | Mike Horihan | 2026-02-12 | NA | NA | NA | Testing completed in the TST env | 06/02/2026 - Applied Praveen changes to to current branch Implemented new card design for the reports 10/02/2026 - Unit testing , PO verfication and fixed UI Issues 11/02/2026 - Deployed in dev and fixed minor UI issues
5 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Sathiya/Praveen | GGO-14866 | Reports and Exports - Search bar | Completed | 3 | 3 | 9.5 | 2026-02-06 | 2026-02-10 | Done | Priya | No Defects | Rajesh | NA | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9269 | 2026-02-10 | 2026-02-12 | Rajesh | NA | Mike Horihan | 2026-02-12 | NA | NA | NA | Testing completed in the TST env | 09/02/2026 - Implemented search functionality on the reports 10/02/2026 - Unit testing , PO verfication and fixed UI Issues 11/02/2026 - Deployed in dev and fixed minor UI issues
6 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Sathiya/Praveen | GGO-14867 | Reports and Exports - Favorite Reports section | Completed | 5 | 5 | 13.5 | 2026-02-06 | 2026-02-10 | Done | Priya | No Defects | Rajesh | NA | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9269 | 2026-02-10 | 2026-02-12 | Rajesh | NA | Mike Horihan | 2026-02-12 | NA | NA | NA | Testing completed in the TST env | 10/02/2026 - Unit testing , PO verfication and fixed UI Issues 11/02/2026 - Deployed in dev and fixed minor UI issues
7 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 | Rajesh/Saranya | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Peer review | 5 | 3 | 94.5 | 2026-02-06 | 2026-02-18 | Done | Priya | No Defects | Rajesh | NA | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9303 | 2026-02-19 | 2026-02-20 | Rajesh |  |  |  |  | NA | NA | Testing completed in the Dev env | Development has been completed. Since we planned to provide a permanent fix, instead of calculating the mostRecentDate at the time of generating invoices or receipts, we decided to pre-calculate and update the relevant tables when associating sales with the corresponding payments. Initially, this logic was implemented in code, but later we moved it to triggers. As this is a major change, the testing effort required is significant, so the work has been carried forward.
8 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 [STRETCH] | Sathiya/Praveen | GGO-14868 | Reports and Exports - Recommended Reports section | Completed | 1 | 1 | 11.5 | 2026-02-12 | 2026-02-12 | Done | Priya | No Defects | Rajesh | NA | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9281 | 2026-02-12 | 2026-02-13 | Rajesh | NA | Mike Horihan | 2026-02-13 |  | NA | NA | Testing completed in the TST env | [02/12/2026]-did design changes for recommended reportes and created PR
9 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 [STRETCH] | Sathiya/Praveen | GGO-14869 | Reports and Exports - All Reports Section | Completed | 3 | 3 |  | 2026-02-12 | 2026-02-13 | Done | Priya | No Defects | Rajesh | NA | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9284 | 2026-02-13 | 2026-02-14 | Rajesh | NA | Mike Horihan | 2026-02-14 |  | NA | NA | Testing completed in the TST env | 02/13/2026]-did design changes for all reports and exports and created PR
10 | GGO Web | 2026-02-05 | 2026-02-19 | GGO 8.3.0 Sprint 1 [STRETCH] | Sathiya/Praveen | GGO-14872 | Reports and Exports - Standard and Advanced Settings Page | Completed | 3 | 3 | 18 | 2026-02-16 | 2026-02-18 | Done | Priya | No Defects | Rajesh | NA | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9302 | 2026-02-18 | 2026-02-18 | Rajesh | Na | Mike Horihan | 2026-02-18 |  | NA | NA | Testing completed in the TST env | 02/13/2026]-did design changes for all reports and exports and created PR

## GGO 8.3.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.2.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Tester Comments | Developer Comments
1 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Sathiya/Saranya/Rajesh | GGO-15135 | Jscrambler for GGO & GGAM & GO Time | Completed | 3 | 3 | 16 | 2026-01-22 | 2026-01-22 | Done | Priya | No Defects |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9201 | 2026-01-21 | 2026-01-22 | Rajesh |  | Mike Horihan | 2026-01-23 |  |  |  | Dev Testing Completed. Testing completed in TST env. | Development is completed in last sprint itself
2 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Rajesh | GGO-15138 | Online Bidding Settings Embed Video Settings | Completed | 1 | 1 | 2 | 2026-01-23 | 2026-01-23 | Done | Priya | No Defects |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9209 | 2026-01-23 | 2026-01-23 |  |  | Mike Horihan | 2026-01-23 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 01/23/2026 - Development 100% completed. Dev testing completed and Created PR
3 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Sathiya | GGO-15137 | Implement ReCaptcha in Supporter | Completed | 2 | 2 | 35.5 | 2026-01-23 | 2026-01-28 | Done | Priya | No Defects |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9211 | 2026-01-28 | 2026-01-28 | Rajesh |  | Mike Horihan | 2026-01-28 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 01/27/2026 - Implemented Recaptcha for Fundraising Activity page 01/27/2026 - Development 50% completed 01/28/2026 - Fixed recaptcha error message clearing issue Removed unused reference of CSP from the controllers Local Unit testing and Created PR
4 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Saranya/Rajesh | GGO-15108 | Equipment Express Update | Completed | 1 | 1 | 15 | 2026-01-23 | 2026-01-23 | Done | Priya | No Defects | Rajesh | Method repeated multiple times. Move to common service and call it. | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9213 | 2026-01-23 | 2026-01-24 | Rajesh |  | Mccarty Joseph | 2026-01-24 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 01/23/2026 - Remove the bullet point about Android Compatibility when the bluetooth option is enabled for a client. Development 100% completed Dev testing completed and Created PR
5 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Rajesh | GGO-13585 | Update to fix LLBLgen generated code | Completed | 1 | 1 | 12 | 2026-01-23 | 2026-01-29 | Done | Priya | No Defects |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9229 | 2026-01-28 | 2026-01-29 | Rajesh |  | Mike Horihan | 2026-01-29 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 01/23/2026 - Some LLBLGen Work is completed by Rajesh 01/28/2026 - Fixed code issue. Dev testing is completed
6 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Saranya/Rajesh | GGO-15109 | Upgrade the Telerik to its latest version | Completed | 5 | 5 | 17 | 2026-01-29 |  | Done | Priya | No Defects | [12 empty] | Dev Testing Completed. Testing completed in TST env. | 01/29/2026 - Upgraded Latest Telerik.Licensig Package 01/30/2026 - Analyzing how to implement licensing environmental wise for Telerik.Licensing package
7 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Saranya | GGO-15142 | API Update for Next Gen - Checkout part 1 | Completed | 1 | 1 | 10 | 2026-01-28 | 2026-01-28 | Done | Priya | No Defects |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9235 | 2026-01-29 | 2026-01-29 | Rajesh |  | Mike Horihan | 2026-01-30 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 01/28/2026 - GetCheckinDetails API Updated with some additional info for NextGen. Development 100% completed 01/29/2026 - Dev testing completed. Created PR
8 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Rajesh | PAPI-883 | Upgrade the Polly NuGet Package | Completed | 2 | 2 | 2 | 2026-01-30 | 2026-01-31 | Done | Priya | No Defects |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/9242 | 2026-01-31 | 2026-01-31 | Rajesh |  | Mike Horihan | 2026-01-31 |  |  |  | Dev Testing Completed. Testing completed in TST env.
9 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 [Stretch] | Saranya | GGO-15084 | Report Timestamps in UTC | Completed | 2 | 2 | 10 | 2026-02-04 | 2026-02-05 | Done | Priya | No Defects | [12 empty] | Dev Testing Completed. Testing completed in TST env. Pending with Onsite QA | 02/04/2026 - Implemented report run time based on Project timezone for rpf reports
10 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 [Stretch] | Rajesh | GGO-15143 | Update the Apigee domain for Azure B2C OIDC endpoints. | Completed | 1 | 1 | 1 | 2026-02-04 | 2026-02-05 | Done | Priya | No Defects | [12 empty] | Dev Testing Completed. Testing completed in TST env. Pending with Onsite QA
11 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 [Stretch] | Sathiya | GGO-15103 | Optout.aspx.cs Exception | Verfiy | 2 | 1 | 10.5 | 2026-02-05 | 2026-02-05 | Done |  |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9260 | 2026-02-05 | [9 empty] | 2/5/2026 -Fixed decryption issue verified in dev. PR created
12 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Sathiya/Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 |  | 64.5 | 2026-01-23 | [6 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9220 | 2026-01-27 | NA | NA |  | Mike Horihan |  |  |  |  | 0 | 01/28/2026 - Identified query part which taking more time 01/29/2026 - Writing new sp for calculating most recent association date Added migration script for the new SPCreated LLBLGen for the SP call definition
13 | GGO Web | 2026-01-22 | 2026-02-05 | GGO 8.2.0 Sprint 4 | Priya-QA | GGO-15140 | 27 Jan GGO 8.2.0 CRT Release & Regression Testing | Being Tested | 3 | 3 | 22 | 2026-02-04 | 2026-02-05 | Done | Priya | No Defects | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in CRT env. Pending with Onsite QA

## GGO 8.2.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.2.0 Sprint3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.2.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Tester Comments | Developer Comments
1 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Saranya | GGO-15123 | package item search | Completed | 1 | 1 | 14 | 2026-01-13 | 2026-01-09 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9159 | 2026-01-09 | 2026-01-09 | Rajesh |  | Mike Horihan | 2026-01-10 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 8/1/2026 - Item name search functionality implemented in View Packages search 9/1/2026 - Unit and Dev testing is completed. Created PR
2 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Rajesh | GGO-14843 | GGO is Creating Duplicate Event Codes | Completed | 5 | 5 | 28 | 2026-01-13 | 2026-01-19 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9183 | 2026-01-17 | NA | NA |  | Mike Horihan | 2026-01-21 |  |  |  | Dev Testing Completed. Testing completed in TST env. Pending with Onsite QA
3 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Sathiya | GGO-15125 | View Items - Reposition the buttons | Completed | 1 | 1 | 16.5 | 2026-01-09 | 2026-01-09 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9158 | 2026-01-09 | 2026-01-10 | Rajesh |  | Mike Horihan | 2026-01-10 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 1/9/2026 - Development 100% completed. Dev testing is completed and Created a PR
4 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Saranya | GGO-15126 | Create/Edit Item - Update the options within Image Description, Restriction and Images | Completed | 1 | 1 | 9 | 2026-01-09 | 2026-01-09 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9167 | 2026-01-12 | 2026-01-13 | Rajesh |  | Mike Horihan | 2026-01-13 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 1/9/2026 - Development 100% completed. Dev testing is completed and Created a PR
5 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Saranya | GGO-15127 | View Items/Packages - Remove Merge option | Completed | 1 | 1 | 13 | 2026-01-09 | 2026-01-09 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9167 | 2026-01-12 | 2026-01-13 | Rajesh |  | Mike Horihan | 2026-01-13 | the exclamation point is not necessary |  |  | Dev Testing Completed. Testing completed in TST env. | 1/9/2026 - Development 100% completed. Merge option removed from Actons dropdown in View Item and View Packages pages. Dev testing is completed and Created a PR
6 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Rajesh | GGO-15079 | Do not allow OB Donation package as a featured package | Completed | 3 | 3 | 25 | 2026-01-16 | 2026-01-19 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9191 | 2026-01-21 | 2026-01-21 | Rajesh |  | Mike Horihan | 2026-01-21 |  |  |  | Dev Testing Completed. Testing completed in TST env. Pending with Onsite QA | 1/16/2026 - Analysis completed 1/17/2026 - Development is 80% completed 1/18/2026 - Development is 100% completed 1/19/2026 - Unit and Dev testing is completed and created a PR
7 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Saranya | GGO-15128 | Image File Size not getting set | Completed | 2 | 2 | 16 | 2026-01-12 | 2026-01-13 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9172 | 2026-01-13 | 2026-01-14 | Rajesh |  | Mike Horihan | 2026-01-14 |  |  |  | Dev Testing Completed. Testing completed in TST env. | 1/12/2026 - Development 80% completed 1/13/2026 - LLBLGen created for stored procedure and Dev testing is completed and created a PR
8 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Rajesh | GGO-15104 | Guides & Analytics toggle won't save | Completed | 2 | 2 | 2 | 2026-01-09 | 2026-01-09 |  | NA |  |  |  | NA | NA | NA | NA |  | NA | NA |  |  |  |  | Development is completed by our end. Pending from Pendo side
9 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Sathiya/Saranya/Rajesh | GGO-15135 | Jscrambler for GGO & GGAM & GO Time | Peer review | 3 | 3 | 30.5 | 2026-01-19 | 2026-01-21 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9201 | 2026-01-21 | 2026-01-22 | Rajesh |  | Mike Horihan | [5 empty] | 1/19/2026 - Completed analysis & Implemented Jscramber in ManageSalesAndPayements and GoTime 1/20/2026 - Implemented Jscramber in GGAM Page 1/21/2026 - Refactored code. Unit testing and peer review done. Created Pull request for review. Development and unit testing is done by our end. Settings to be updated by Jcramber Side
10 | GGO Web | 2026-01-08 | 2026-01-22 | GGO 8.2.0 Sprint 3 | Sathiya | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 |  | 56 | 2026-01-09 | [17 empty] | Unable to reproduce in TST env. Mike will confirm with backend team whether we need to close this ticket or provide the steps to reproduce

## GGO 8.2.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15068 | Print or Email Invoices/Receipts - Add a loading Pop-up | Completed | 1 |  | 4 | 2025-12-09 | 2025-12-09 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9094 | 2025-12-10 | 2025-12-10 | Rajesh |  | Mike Horihan | 2025-12-10 |  |  |  | Completed Testing in the TST env
2 | GGO Web | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15124 | Item Name field allows more than 127 characters, causing error on save in the Create Item Page | Completed | 2 |  | 1 | 2025-12-16 | 2025-12-16 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9109 | 2025-12-16 | 2025-12-16 | Rajesh |  | Mike Horihan | 2025-12-16 |  |  |  | Completed Testing in the TST env
3 | GGO Web | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Rajesh | GGO-15052 | API Update for Next Gen - Supporter Search | Completed | 3 |  | 31 | 2025-12-12 | 2026-01-19 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9105 | 2025-12-15 | 2025-12-16 | Rajesh |  | Mike Horihan | 2025-12-16 |  |  |  | Completed Testing in the TST env
4 | GGO Web | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15086 | no negative search for sales and payments | Completed | 5 |  | 53 | 2025-12-12 | 2026-01-19 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9126 | 2025-12-20 | 2025-12-20 | Rajesh |  | Mike Horihan | 2025-12-20 |  |  |  | Completed Testing in the TST env
5 | GGO Web | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-14956 | Online Bidding settings page - Section 1 | Completed | 5 |  | 82 | 2025-12-15 | 2025-12-31 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9136 | 2025-12-26 | 2026-01-01 | Rajesh |  | Mccarty, Joseph | 2026-01-01 |  |  |  | Completed Testing in the TST env
5 | GGO Web | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-14919 | Online Bidding settings page - Section 2 | Completed | 5 |  | 44 | 2025-12-16 | 2025-12-31 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9136 | 2025-12-26 | 2026-01-01 | Rajesh |  | Mccarty, Joseph | 2026-01-01 |  |  |  | Completed Testing in the TST env
6 | GGO Web | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-14957 | Online Bidding settings page - Section 3 | Completed | 5 |  | 37 | 2025-12-17 | 2025-12-31 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9136 | 2025-12-26 | 2026-01-01 | Rajesh |  | Mccarty, Joseph | 2026-01-01 |  |  |  | Completed Testing in the TST env
7 | GGO Web | 2025-12-12 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Rajesh | GGO-15094 | Fallback plan for OB changes | Completed | 1 |  | 6 | NA | NA | NA | Priya |  | NA |  | NA | NA | NA | NA |  | NA | NA |  |  |  | Completed Testing in the TST env
8 | GGO Web | 2025-12-12 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Rajesh/Saranya | GGO-15080 | API update for Next Gen - supporter badges | Completed | 3 |  | 7 | 2025-12-22 | 2025-12-23 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9140 | 2025-12-30 | 2025-12-31 | Rajesh |  | Mccarty, Joseph | 2025-12-31 |  |  |  | Completed Testing in the TST env
9 | GGO Web | 2025-12-11 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15117 | View Package for for Non-Admin User* | Completed | 2 |  | 18 | 2025-12-02 | 2026-01-05 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9149 | 2026-01-05 | 2026-01-06 | Rajesh |  | Mike Horihan | 2026-01-06 |  |  |  | Completed Testing in the TST env
10 | GGO Web | 2025-12-12 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-15132 | Online Bidding Settings - Edit or Change Phase* | Completed | 2 |  | 12.5 | 2025-12-31 | 2026-01-02 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9146 | 2026-01-02 | 2026-01-03 | Rajesh |  | Mike Horihan | 2026-01-05 |  |  |  | Completed Testing in the TST env
11 | GGO Web | 2025-12-12 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-15111 | Revise Create/Edit Package design* | Completed | 3 |  | 22 | 2026-01-07 | 2026-01-07 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9150 | 2026-01-07 | 2026-01-07 | Rajesh |  | Mike Horihan | 2026-01-07
12 | GGO Web | 2025-12-12 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Sathiya/Saranya | GGO-15112 | Update the grids - Supporter, Items and Packages pages* | Completed | 2 |  | 29 | 2026-01-06 | 2026-01-07 | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9151 | 2026-01-07 | 2026-01-08 | Rajesh |  | Mike Horihan | 2026-01-08
13 | GGO Web | 2025-12-12 | 2026-01-08 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15123 | package item search* | Being Developed | 2 |  | 9 | 2025-12-08

## GGO 8.2.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
NO Defects
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.1.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Rajesh | GGO-14932 | Pop-up Dialogs in View Packages page | Completed | 1 |  | 12 | 2025-11-26 | 2025-11-26 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9053 | 2025-11-26 | 2025-11-26 | Rajesh |  | Mike Horihan | 2025-11-26
2 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Sathiya | GGO-15091 | Image Manager Missing in New UI for Edit Package Image while creating New Items | Completed | 1 |  | 18 | 2025-11-27 | 2025-11-27 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9052 | 2025-11-26 | 2025-11-27 | Rajesh |  | Mike Horihan | 2025-11-27
3 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15085 | package search update | Completed | 3 |  | 28 | 2025-11-27 | 2025-12-02 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9068 | 2025-12-03 | 2025-12-03 | Rajesh |  | Mike Horihan | 2025-12-03
4 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Rajesh | GGO-15095 | Nuget Package updates | Completed | 3 |  | 10 | 2025-11-27 |  | Rajesh | Priya |  | Priya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9087 | 2025-12-06 | 2025-12-06 | Rajesh |  | Mike Horihan | 2025-12-06
5 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Sathiya | GGO-14876 | Create/Edit Package Page | Completed | 8 |  | 85.25 | 2025-11-28 | 2025-12-09 | Sathya | Priya |  | Saranya/Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9084 | 2025-12-05 | 2025-12-09 | Rajesh |  | Mike Horihan | 2025-12-09
6 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15071 | Image Manager - Folder Rename Issue | Completed | 3 |  | 40 | 2025-12-01 |  | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9086 | 2025-12-05 | 2025-12-05 | Rajesh |  | Mccarty, Joseph | 2025-12-06
7 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Rajesh | GGO-15072 | Project Home Update - Non OB Clients | Completed | 2 |  | 8 | 2025-11-27 |  | Rajesh | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9063 | 2025-12-02 | 2025-12-02 | Rajesh |  | Mike Horihan | 2025-12-02
8 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15106 | All radio buttons appear selected by default on the Edit Invoice and GoTime Settings page | Completed | NA |  | 2 | 2025-12-04 | 2025-12-04 | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9078 | 2025-12-04 | 2025-12-04 | Rajesh |  | Mike Horihan | 2025-12-04
9 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Rajesh/Saranya | GGO-15110 | Edit Package - Change Type and UI issue | Completed | NA |  | 15.5 | 2025-12-09 | 2025-12-09 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9095 | 2025-12-10 | 2025-12-10 | Rajesh |  | Mike Horihan | 2025-12-10
10 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15068 | Print or Email Invoices/Receipts - Add a loading Pop-up* | Being Tested | 1 |  | 4 | 2025-12-09 | 2025-12-09 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9094 | 2025-12-10 | 2025-12-10 | Rajesh |  | Mike Horihan | 2025-12-10
11 | GGO Web | 2025-11-27 | 2025-12-11 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15086 | no negative search for sales and payments* | Being Developed | 5 |  | 8 | 2025-12-11

## GGO 8.1.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 8.1.0 Sprint 4 | GGO-15106 | GGO-15014 | Saranya | Defect | All radio buttons appear selected by default on the Edit Invoice and GoTime Settings page | Significant | Manual | Internal | Closed | Design | Priya
| GGO 8.1.0 Sprint 4 | GGO-15110 | GGO-14876 | Saranya | Defect | Edit Package - Change Type and UI issue | Significant | Manual | Internal | Closed | Design | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.1.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Rajesh | GGO-14931 | View Items Advanced Search | Completed | 2 |  | 14 | 2025-11-06 | 2025-11-13 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9004 | 2025-11-12 | 2025-11-13 | Rajesh |  | Mike Horihan | 2025-11-13 |  |  |  | Completed Testing in the TST env
2 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Rajesh | GGO-15075 | Supporter and Item Search advanced syntax | Completed | 1 |  | 24 | 2025-11-13 | 2025-11-13 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9008 | 2025-11-13 | 2025-11-14 | Rajesh |  | Mike Horihan | 2025-11-14 |  |  |  | Completed Testing in the TST env
3 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Sathya | GGO-15065 | Cancel Button Hidden in Popups on Package Page Across All Environments - UI Issues | Completed | 2 |  | 42.5 | 2025-11-14 | 2025-11-18 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9017 | 2025-11-18 | 2025-11-18 | Rajesh |  | Mike Horihan | 2025-11-18 |  |  |  | Completed Testing in the TST env
4 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Sathya | GGO-15058 | Login Page Update - Expiring Privacy Policy Message v2 | Completed | 3 |  | 23 | 2025-11-18 | 2025-11-20 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9031 | 2025-11-19 | 2025-11-21 | Rajesh |  | Mike Horihan | 2025-11-21 | the whole div should be removed, right? Are we also hiding the B2C Batch Migration setting? this div is the end div that was surrounding the B2C Batch Migration, right? |  |  | Completed Testing in the TST env
5 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Rajesh | GGO-15067 | Nav Bar - Maintain consistent behavior throughout the application | Completed | 3 |  | 13 | 2025-11-14 | 2025-11-17 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9019 | 2025-11-17 | 2025-11-18 | Rajesh |  | Mike Horihan | 2025-11-18 |  |  |  | Completed Testing in the TST env
6 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Saranya | GGO-14933 | View Packages Advanced Search | Completed | 5 |  | 26 | 2025-11-17 | 2025-11-19 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9028 | 2025-11-18 | 2025-11-18 | Rajesh |  | Mike Horihan | 2025-11-19 |  |  |  | Completed Testing in the TST env
7 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Saranya / Rajesh | PAPI-891 | GoTime Check-in with EMV is missing PAPI Payment record for CardVerify | Completed | 3 |  | 6 | 2025-11-17 | 2025-11-18 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/9029 | 2025-11-19 | 2025-11-19 | Rajesh |  | Mike Horihan | 2025-11-19 |  |  |  | Completed Testing in the TST env
8 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Saranya | GGO-15081 | Create Items - Update Hyperlink Manager pop-up* | Completed | 2 |  | 34 | 2025-11-20 | 2025-11-26 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9040 | 2025-11-25 | 2025-11-25 | Rajesh |  | Mike Horihan | 2025-11-25 |  |  |  | Completed Testing in the Dev env
9 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Saranya | GGO-15082 | Rename popup UI shrinks and require multiple clicks in Global Search to apply changes | Completed | NA |  | 6 | 2025-11-20 | 2025-11-20 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9038 | 2025-11-20 | 2025-11-20 | Rajesh |  | Mike Horihan | 2025-11-21 |  |  |  | Completed Testing in the TST env
10 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Rajesh | GGO-15089 | RSVP Import Delays / Slowness* | Completed | 2 |  | 6 |  |  | Rajesh | Priya |  | 0 |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9050 | 2025-11-26 | 2025-11-26 | Rajesh |  | Mike Horihan | 2025-11-26
11 | GGO Web | 2025-11-13 | 2025-11-27 | GGO 8.1.0 Sprint 3 | Saranya / Rajesh | GGO-14932 | Pop-up Dialogs in View Packages page | Verify | 2 |  | 3 | 2025-11-26 | 2025-11-26 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9053 | 2025-11-26 | 2025-11-26 | Rajesh |  | Mike Horihan | 2025-11-26

## GGO 8.1.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 8.1.0 Sprint 3 | GGO-14933 | GGO-15802 | Saranya | Defect | Rename popup UI shrinks and require multiple clicks in Global Search to apply changes | Significant | Manual | Internal | Closed | Design | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.1.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Sathiya/Saranya | GGO-14901 | Manage Images - Popup | Completed | 5 |  | 52 | 2025-10-31 | 2025-11-10 | Sathiya | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8963 | 2025-10-28 | 2025-11-07 | Rajesh |  | Mike Horihan | 2025-11-07 |  |  |  | Completed Testing in the TST env
2 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Rajesh | GGO-10698 | Item solicitor doesn't import when added during Import Online Item Donation process | Completed | 3 |  | 22 | 2025-10-31 | 2025-11-04 | Rajesh | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8980 | 2025-11-04 | 2025-11-04 | Saranya |  | Mike Horihan | 2025-11-04 |  |  |  | Completed Testing in the TST env
3 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Rajesh | GGO-15054 | Supporters - Filters - Retain Radio buttons value in Saved Search | Completed | 3 |  | 19 | 2025-10-31 | 2025-10-31 | Rajesh | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8971 | 2025-10-31 | 2025-10-31 | Sathya |  | Mike Horihan | 2025-10-31 |  |  |  | Completed Testing in the TST env
4 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Sathya | GGO-15060 | View Items page for Non-Admin User | Completed | 3 |  | 16 | 2025-11-06 | 2025-11-10 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8990 | 2025-11-07 | 2025-11-07 | Rajesh |  | Mike Horihan | 2025-11-08 |  |  |  | Completed Testing in the TST env
5 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Saranya | GGO-15055 | View Items - Actions - Copy Items from other Projects | Completed | 3 |  | 29 | 2025-11-03 | 2025-11-06 | Saranya | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8987 | 2025-11-06 | 2025-11-06 | Rajesh |  | Mike Horihan | 2025-11-07 |  |  |  | Completed Testing in the TST env
6 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Rajesh/Saranya/Sathya | GGO-14931 | View Items Advanced Search* | Being Tested | 5 |  | 40 | 2025-11-06 | 2025-11-13 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9004 | 2025-11-12 | 2025-11-13 | Rajesh |  | Mike Horihan | 2025-11-13
7 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Rajesh/Saranya/Sathya | GGO-15066 | Equipment Needed banner is missing after the GGO UI refresh released to Production | Completed | 2 |  | 4 | 2025-11-11 | 2025-11-13 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8998 | 2025-11-11 | 2025-11-11 | Rajesh |  | Mike Horihan | 2025-11-11 |  |  |  | Completed Testing in the TST env
8 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Rajesh/Saranya/Sathya | GGO-15070 | View Supporters no cards on file search filter is not working | Completed | 2 |  | 10 | 2025-11-11 | 2025-11-13 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9002 | 2025-11-11 | 2025-11-11 | Rajesh |  | Mike Horihan | 2025-11-11 |  |  |  | Completed Testing in the TST env
9 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Rajesh/Saranya/Sathya | GGO-15073 | Activate OB Link isn't on the New GGO Home Page | Completed | 2 |  | 13.5 | 2025-11-11 | 2025-11-13 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9000 | 2025-11-11 | 2025-11-12 | Rajesh |  | Mike Horihan | 2025-11-12 |  |  |  | Completed Testing in the TST env
10 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Sathiya/Saranya | GGO-15069 | UI Issues | Completed |  |  | 6.5 | 2025-11-07 | 2025-11-07 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8994 | 2025-11-08 | 2025-11-08 | Rajesh |  | Mike Horihan | 2025-11-08 |  |  |  | Completed Testing in the TST env
11 | GGO Web | 2025-10-30 | 2025-11-13 | GGO 8.1.0 Sprint 2 | Saranya | GGO-15075 | Supporter and Item Search advanced syntax | Verify |  |  | 14 | 2025-11-13 | 2025-11-13 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9008 | 2025-11-13 | 2025-11-14 | Rajesh |  | Mike Horihan | 2025-11-14 |  |  |  | Completed Testing in the TST env

## GGO 8.1.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-10-16 | 2025-10-30 | GGO 8.1.0 Sprint 1 | Saranya | GGO-15042 | Re-introduce Group by Household to Supporter Grid* | Completed | 3 |  |  | 2025-10-17 |  | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8944 | 2025-10-23 | 2025-10-23 | Rajesh |  | Mike Horihan | 2025-10-23 |  |  |  | Testing completed in the TST env.
2 | GGO Web | 2025-10-16 | 2025-10-30 | GGO 8.1.0 Sprint 1 | Rajesh | GG0-15041 | Household Investigation | Completed | 3 |  | 9 | 2025-10-17 | [6 empty] | NA | NA | NA | NA |  | NA | NA |  |  |  | NA
3 | GGO Web | 2025-10-16 | 2025-10-30 | GGO 8.1.0 Sprint 1 | Rajesh | GGO-15020 | OneTrust implementation issue | Completed | 3 |  |  | 2025-10-17 |  | Rajesh | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8954 | 2025-10-25 | 2025-10-25 | Rajesh |  | Mike Horihan | 2025-10-27 |  |  |  | Testing completed in the TST env.
4 | GGO Web | 2025-10-16 | 2025-10-30 | GGO 8.1.0 Sprint 1 | Sathiya | GGO-14901 | Manage Images - Popup | Completed | 5 |  |  | 2025-10-17 | [16 empty] | Since the design is more complex and focused on group items by household functionality in the view supporters filter
5 | GGO Web | 2025-10-16 | 2025-10-30 | GGO 8.1.0 Sprint 1 | Saranya/Sathya | GGO-14930 | Pop-up Dialogs in View Items page | Completed | 3 |  |  | 2025-10-17 |  | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8960 | 2025-10-28 | 2025-10-28 | Rajesh |  | Mike Horihan | 2025-10-28 | Selecting 2 items, click Package from Actions, Click cancel causes the page to refresh and items selected become unselected. |  |  | Testing completed in the TST env.

## GGO 8.1.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 8.1.0 Sprint 1 | GGO-15069 | GGO-14901 | Sathiya/Rajesh/Saranya | Defect | UI Issues | Significant | Manual | Internal | Closed | Design | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.1.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 8.1.0 Sprint 1 | GGO-15042 | GGO-15050 | Sathiya/Rajesh/Saranya | Defect | Search filter and design issues | Significant | Manual | Internal | Closed | Design | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.0.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 | Praveen/Sathiya | GGO-15015 | Create Item - Update the Rich Text editor | Completed | 2 |  | 32 | 2025-10-03 |  | Sathiya | Priya |  | Praveen |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8918 | 2025-10-11 | 2025-10-11 | Rajesh |  | Mike Horihon | 2025-10-13 |  |  |  | Verified in the TST env. Working well
2 | GGO Web | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 | Saranya | GGO-14966 | item package updates | Completed | 2 |  | 13 | 2025-10-03 |  | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8902 | 2025-10-06 | 2025-10-07 | Rajesh |  | Mike Horihon | 2025-10-07 |  |  |  | Verified in the TST env. Working well
3 | GGO Web | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 | Praveen/Sathiya | GGO-14877 | Create Item - Image Control (Multi-image chooser) | Completed | 5 |  | 36 | 2025-10-03 |  | Sathiya | Priya |  | Praveen |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8922 | 2025-10-14 | 2025-10-15 | Rajesh |  | Mike Horihon | 2025-10-15 |  |  |  | Verified in the TST env. Working well
4 | GGO Web | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 | Rajesh | GGO-15037 | Error clicking cancel in Email Verify and Password Reset | Completed | 1 |  | 3 | 2025-10-03 |  | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8893 | 2025-10-03 | 2025-10-03 | NA |  | Mike Horihon | 2025-10-03 |  |  |  | Verified in the TST env. Working well
5 | GGO Web | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 | Sathiya/Rajesh | GGO-15029 | Gotime-Error | Completed | 3 |  | 43.5 | 2025-10-03 |  | NA | NA |  | NA |  | NA | NA | NA | NA |  | NA | NA |  |  |  | Verified from client side.
6 | GGO Web | 2025-10-03 | 2025-10-16 | GGO 8.0.0 Sprint 4 | Saranya | GGO-15042 | Re-introduce Group by Household to Supporter Grid* | Being Developed | 5 |  | 47 | 2025-10-13 | [16 empty] | Testing in Dev env.

## GGO 8.0.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Sathiya/Rajesh/Saranya | GGO-14980 | View Supporter Page Filter - Save Search | Completed | 3 |  | 106 | 2025-09-05 | 2025-09-29 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8872 | 2025-09-25 | 2025-09-27 | Rajesh |  | Mike Horihan | 2025-09-27 |  |  |  | Due to complications involving multiple user controls on the filter page, some functions within the new user control are not triggering as expected. Additionally, new controls were added which require further integration and testing to ensure smooth functionality.
2 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Saranya | GGO-14822 | Update Email validation on Project Builder | Completed | 2 |  | 18 | 2025-09-22 | 2025-09-24 | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8860 | 2025-09-23 | 2025-09-24 | Rajesh |  | Mccarty, Joseph | 2025-09-24 |  |  |  | Testing Completed in the TST env
3 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Praveen | GGO-15013 | Remove G logo from side nav | Completed | 2 |  | 8 | 2025-09-19 |  | Praveen | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8853 | 2025-09-22 | 2025-09-22 | Rajesh |  | Michael Wall | 2025-09-22 |  |  |  | Testing Completed in the TST env
4 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Rajesh | GGO-14661 | Reskin Feature flag for new clients | Completed | 3 |  | 9 | 2025-09-19 |  | Rajesh | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8850 | 2025-09-22 | 2025-09-23 | Rajesh |  | Michael Wall | 2025-09-23 |  |  |  | Testing Completed in the TST env
5 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Saranya/Praveen | GGO-15010 | Reskin Project Home Update Issue | Completed | 2 |  | 13 | 2025-09-23 | 2025-09-26 | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8873 | 2025-09-25 | 2025-09-25 | Rajesh |  | Michael Wall | 2025-09-26 |  |  |  | Testing Completed in the TST env
6 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Rajesh/Sathiya | GGO-14960 | Macroscope - High - Prevent URL Redirector Abuse on Logout | Completed | 2 |  | 17.5 | 2025-09-23 |  | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8876 | 2025-09-26 | 2025-09-26 | Rajesh |  | Mike Horihan | 2025-09-26 |  |  |  | Testing Completed in the TST env
7 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Saranya/Rajesh | PAPI-882 | Ensure All Card Types can be added as CoF when amount = $0.01 is set by Mobile Team | Completed | 1 |  | 11 | 2025-09-29 |  | Saranya | Rajesh |  | Rajesh |  | NA | NA | NA | NA |  | NA | NA |  |  |  | Testing Completed in the TST env
8 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Praveen/Sathiya | GGO-15015 | Create Item - Update the Rich Text editor* | Being Developed | 2 |  | 5 | 2025-09-29
9 | GGO Web | 2025-09-18 | 2025-10-02 | GGO 8.0.0 Sprint 3 | Saranya | GGO-14966 | item package updates* | Being Developed | 3 |  | 8 | 2025-09-30 | [9 empty] | Rajesh |  | Mike Horihan

## GGO 8.0.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 8.0.0 Sprint 3 | GGO-15030 | GGO-14980 | Sathiya/Rajesh/Saranya | Defect | Create sales page UI impact | Significant | Manual | Internal | Closed | Design | Sathiya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.0.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Saranya | GGO-14854 | View Supporter Page Filter - Staff and Fundraisers* | Completed | 1 | 2 |  | 2025-09-05 |  | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8810 | 2025-09-05 | 2025-09-05 | Rajesh |  | Mike Horihan | 2025-09-06 |  |  |  | Testing completed in the Dev env. 4:30 PM 9/4/2025
2 | GGO Web | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Sathya / Praveen | GGO-14875 | Create Item Page | Completed | 5 | 5 |  | 2025-09-05 |  | Sathiya | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8744 | 2025-09-16 | 2025-09-16 | Rajesh |  | Mike Wall | 2025-09-16 |  |  |  | Testing completed in the TST env.
3 | GGO Web | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Saranya | GGO-14979 | View Supporter Page Filter - Supporters | Completed | 3 | 3 |  | 2025-09-05 |  | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8822 | 2025-09-10 | 2025-09-10 | Rajesh |  | Mike Horihan | 2025-09-11 |  |  |  | Testing completed in the TST env.
4 | GGO Web | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Rajesh/Saranya | GGO-14980 | View Supporter Page Filter - Save Search | Being Developed | 3 |  |  | 2025-09-05 | [16 empty] | Due to complications involving multiple user controls on the filter page, some functions within the new user control are not triggering as expected. Additionally, new controls were added which require further integration and testing to ensure smooth functionality.
5 | GGO Web | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Rajesh | GGO-14984 | Content Security Policy Update for Pendo * | Completed | 2 | 2 |  | 2025-09-05 |  | Rajesh | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8820 | 2025-09-09 | 2025-09-09 |  |  | Mike Horihan | 2025-09-09 |  |  |  | Testing completed in the TST env.
6 | GGO Web | 2025-09-04 | 2025-09-18 | GGO 8.0.0 Sprint 2 | Priya-QA | GGO-15009 | sub field creation links to classic page | Completed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## GGO 8.0.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 8.0.0 Sprint 2 | GGO-15009 | GGO-14875 | Sathiya | Defect | sub field creation links to classic page | Significant | Manual | Internal | Closed | Enhancements | Conor | We found the same kind of issue in the dev env while testing the create item page. Onsite QA found the same issue while editing the items in the TST env
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 8.0.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Praveen / Sathiya | GGO-14858 | Retain the overall design of the application | Completed | 2 | 2 |  | 2025-08-19 | 2025-08-20 | Praveen/Sathiya | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8756 | 2025-08-20 | 2025-08-20 | Prabhu |  | Michael Wall | 2025-08-20 |  |  |  | It is stretched story development and testing completed by offshore , onsite QA testing not yet completed.[22-Aug-25]. Testing completed
2 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Rajesh/Saranya/Sathya | GGO-14863 | OneTrust Privacy Center in profile | Completed | 2 | 2 |  |  |  | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8779 | 2025-08-27 | 2025-08-27 | Sathiya |  | Michael Wall | 2025-08-27 |  |  |  | Testing completed in the TST env,
3 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Sathya / Praveen | GGO-14852 | View Supporter Page Filter - Bidders & Attendees | Completed | 3 | 3 |  |  |  | Sathya/Praveen | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8786 | 2025-08-28 | 2025-08-30 | Rajesh |  | Mccarty, Joseph | 2025-08-30 |  |  |  | Testing completed in the TST env,
4 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Rajesh / Saranya / Sathya | GGO-14853 | View Supporter Page Filter - Sponsors and Donors | Completed | 3 | 3 |  |  |  | Sathya/Praveen | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8786 | 2025-08-28 | 2025-08-30 | Rajesh |  | Mccarty, Joseph | 2025-08-30 |  |  |  | Testing completed in the TST env,
5 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 - [Stretch] | Saranya | GGO-14854 | View Supporter Page Filter - Staff and Fundraisers* | Being Developed | 3 | 2 |  |  |  | Saranya | Priya |  | Sathya | [11 empty] | Testing completed in the Dev env. 4:30 PM 9/4/2025
6 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 - [Stretch] | Rajesh | GGO-14971 | Pendo Content Security Policy * | Completed | 2 | 2 |  |  |  | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8799 | 2025-09-03 | NA | NA |  | Michael Wall | 2025-09-03 |  |  |  | Testing completed by Client. Offshore QA doesnt have access to do the testing for this
7 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Rajesh | GGO-14972 | org mail templates error | Completed | NA | NA | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8773 | NA | NA | NA |  | Michael Wall | 2025-08-27 |  |  |  | Carry forward CRT bug
8 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Rajesh | GGO-14970 | jquery update issues | Completed | NA | NA |  | 2025-09-02 | 2025-09-02 | [10 empty] | Michael Wall | 2025-08-26 |  |  |  | Carry forward CRT bug
9 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Sathya / Praveen | GGO-14875 | Create Item Page | Being Developed | 5 | [19 empty] | Onsite Dev-Mike Wall picked this story earlier did some basic changes due to design difficulties handovered the story to offshore on 1-sep-25
10 | GGO Web | 2025-08-21 | 2025-09-04 | GGO 8.0.0 Sprint 1 | Priya-QA | GGO-14981 | Date Picker Positioning Breaks After Scrolling the Page | Completed | NA | NA | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8791 | 2025-09-02 | 2025-09-03 | Rajesh |  | Michael Wall | 2025-09-03 |  |  |  | Carry forward CRT bug

## GGO 8.0.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 8.0.0 Sprint 1 | GGO-14981 | GGO-14852 | Sathiya | Defect | Date Picker Positioning Breaks After Scrolling the Page | Significant | Manual | Internal | Closed | Enhancements | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.25.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Rajesh/Sathya/Saranya | GGO-14851 | Filter pages - Sales & Payments (with Payments on) and Supporters | Completed | 5 | 5 | 52.25 | 2025-08-12 | 2025-08-15 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8742 | 2025-08-15 | 2025-08-15 | Rajesh |  | Michael Wall | 2025-08-15 |  |  |  | Testing completed in the TST env.
2 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Rajesh/Sathya/Saranya | GGO-14712 | View Supporter Filter and Sales & Payments (with Sales on) page | Completed | 5 | 5 | 54.75 | 2025-08-07 | 2025-08-11 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8725 | 2025-08-11 | 2025-08-13 | Rajesh |  | Michael Wall | 2025-08-13 |  |  |  | Testing completed in the TST env.
3 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Rajesh/Saranya | GGO-14863 | OneTrust Privacy Center in profile* | Being Developed | 3 |  | 37.75 | 2025-08-18
4 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Praveen/Sathiya | GGO-14858 | Retain the overall design of the application* | Ready for testing | 3 |  | 21 | 2025-08-19 | 2025-08-20 | Praveen/Sathiya | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8756 | 2025-08-20 | 2025-08-20 | Prabhu |  | Michael Wall | 2025-08-20 |  |  |  | It is stretched story development and testing completed by offshore , onsite QA testing not yet completed.[22-Aug-25]
5 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14954 | Filter Not Reset When Sales Is Disabled | Completed | NA | NA | 9.5 | 2025-08-13 | 2025-08-13 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8738 | 2025-08-13 | 2025-08-14 | Rajesh |  | Michael Wall | 2025-08-14 |  |  |  | Testing completed in the TST env.
6 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14961 | Supporter Records Not Filtering Correctly When "Has Payment" is Toggled On | Completed | NA | NA | 1 | 2025-08-13 | 2025-08-13 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8738 | 2025-08-13 | 2025-08-14 | Rajesh |  | Michael Wall | 2025-08-14 |  |  |  | Testing completed in the TST env.
7 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14691 | View Packages page | Completed | 1 | 1 | 2.25 | NA | NA | [15 empty] | Testing completed in the TST env.
8 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14689 | View Items page | Completed | 1 | 1 | 10 | NA | NA | [5 empty] | NA | NA | NA | NA |  | NA | NA |  |  |  | Testing completed in the TST env.
9 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14962 | Old Icon Displayed for "Type" in View Packages Page | Completed | NA | NA | 1 | NA | NA | [5 empty] | NA | NA | NA | NA |  | NA | NA |  |  |  | Testing completed in the TST env.
10 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14927 | Macroscope - High - Microsoft.VSSDK.BuildTools:15.8.3252 | Completed | 1 | 1 | 2 |  | NA | [5 empty] | NA | NA | NA | NA |  | NA | NA |  |  |  | Testing completed in the TST env.
11 | GGO Web | 2025-08-07 | 2025-08-21 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14955 | MacroScope - Medium - BDSA-2022-2259 - System.Security.Cryptography.Xml/4.5.0 | Completed | 1 | 1 | 2 | NA | NA | [5 empty] | NA | NA | NA | NA |  | NA | NA |  |  |  | Testing completed in the TST env.

## GGO 7.25.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 7.25.0 Sprint 4 | GGO-14954 | GGO-14712 | Sathiya/Rajesh/Saranya | Defect | Filter Not Reset When Sales Is Disabled | Significant | Manual | Internal | Closed | Enhancements | Priya
| GGO 7.25.0 Sprint 4 | GGO-14961 | GGO-14851 | Sathiya/Rajesh/Saranya | Defect | Supporter Records Not Filtering Correctly When "Has Payment" is Toggled On | Significant | Manual | Internal | Closed | Enhancements | Priya
| GGO 7.25.0 Sprint 4 | GGO-14962 | GGO-14691 | Mike Wall | Defect | Old Icon Displayed for "Type" in View Packages Page | Significant | Manual | Internal | Closed | Enhancements | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.25.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14802 | GGO Reskin - Implement the View Supporter common controls | Completed | 3 | 3 |  | 2025-07-14 | 2025-07-28 |  | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8677 | 2025-07-23 | 2025-07-23 | Rajesh |  | Michael Wall | 2025-07-23 |  |  |  | 28 July 2025 at 09:13 Verified in the TST env.
2 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Rajesh | GGO-14724 | Implement OneTrust | Completed | 2 | 2 |  | 2025-07-14 | 2025-07-28 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8667 | 2025-07-21 | 2025-07-21 | Rajesh |  | Michael Wall | 2025-07-22 |  |  |  | Verified in the TST env. Working well
3 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14840 | Pop-up Dialogs in Supporters page | Completed | 5 | 5 |  | 2025-07-25 | [6 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8706 | 2025-08-05 | 2025-08-05 | Rajesh |  | Michael Wall | 2025-08-05
4 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14855 | when saved search is selected no new search can be done | Completed |  |  |  | 2025-07-24 | 2025-07-28 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8691 | 2025-07-25 | 2025-07-25 | Rajesh |  | Michael Wall | 2025-07-25 |  |  |  | 28 July 2025 at 09:13 Except for the 1st scenario, Everything is working as expected. As discussed with Jennifer, greying out the other action dropdowns except import will be fixed in the Popup story. Hence, closing the defect.
5 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14851 | Filter pages - Sales & Payments (with Payments on) and Supporters | Being Developed | 5 | [19 empty] | The design challenges in this story prevent us from reusing existing user controls in every context.
6 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14712 | View Supporter Filter and Sales & Payments (with Sales on) page | Being Developed | 5 | [19 empty] | We didn’t work on this story due to story GGO-14840 taking more time than anticipated due to its complexity
7 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Rajesh | GGO-14794 | GGO Reskin - Implement the View Catalog page | Completed | 3 | 3 | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8687 | 2025-07-25 | 2025-08-01 |  |  | Rajesh | 2025-08-01 |  |  |  | 4 August 2025 at 09:14 Verified in the TST env. Working well
8 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Priya-QA | GGO-14900 | Update Manage Columns in Catalog Grid | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Verified in the TST env. Working well
9 | GGO Web | 2025-07-24 | 2025-08-07 | GGO 7.25.0 Sprint 3 | Priya-QA | GGO-14906 | checkbox Alignment Issues and Missed to implement Bottom Border Opacity and Title panel Aligns | Completed | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Verified in the TST env. Working well

## GGO 7.25.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Rajesh/Sathya/Saranya | GGO-14687 | GGO Reskin - Implement the View Supporter page | Completed | 3 | 3 |  | 2025-07-11 | 2025-07-14 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8649 | 2025-07-16 | 2025-07-16 | Rajesh |  | Michael Wall | 2025-07-16 |  |  |  | Testing is still in progress in the TST env 8:52 PM 7/16/2025. Testing completed in the TST env. 7/21/2025
2 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Rajesh/Sathya/Saranya | GGO-14802 | GGO Reskin - Implement the View Supporter common controls | Being Developed | 5 |  |  | 2025-07-14 | 2025-07-23 |  | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8677 | 2025-07-23 | 2025-07-23 | Rajesh |  | Michael Wall | 2025-07-23 |  |  |  | Did Testing in TST Env. Found a bug.Created a defect under this story
3 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Rajesh | GGO-14724 | Implement OneTrust | Being Developed | 5 |  |  | 2025-07-14 | 2025-07-24 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8667 | 2025-07-21 | 2025-07-21 | Rajesh |  | Michael Wall | 2025-07-22 |  |  |  | Development part is completed. OneTrust website is not yet available in the TST environment
4 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Rajesh/Sathya/Saranya | GGO-14688 | GGO Reskin - Implement the Edit Supporter details page - Top Section | Being Developed | 3 | [19 empty] | Can't able to complete the task as planned due to changes in the new layout design, which introduced additional controls and complexity. Also, another story GGO-14687 required more time than anticipated, which impacted the overall timeline."
5 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14831 | MacroScope - High - Microsoft.Owin.Security.OpenIdConnect:4.2.2 | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of Regression Testing in the TST env.
6 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14835 | MacroScope - High - BDSA-2024-7402 - jQuery.UI.Combined/1.12.1 | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of Regression Testing in the TST env.
7 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14832 | MacroScope - High - CVE-2021-24112 - System.Drawing.Common | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of Regression Testing in the TST env.
8 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14829 | MacroScope - High - Manual HTML Sanitization | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of Regression Testing in the TST env.
9 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14837 | MacroScope - High - DomPurify.js Unsanitized HTML | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of Regression Testing in the TST env.
9 | GGO Web | 2025-07-10 | 2025-07-24 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14829 | MacroScope - High - Manual HTML Sanitization | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of Regression Testing in the TST env.

## GGO 7.25.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 7.25.0 Sprint 3 | GGO-14906 | GGO-14840 | Sathiya | Defect | checkbox Alignment Issues and Missed to implement Bottom Border Opacity and Title panel Aligns | Significant | Manual | Internal | Closed | Enhancements | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.25.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 7.25.0 Sprint 2 | GGO-14850 | GGO-14802 | Rajesh/Saranya/Sathiya | Defect | Display warning popup when only one supporter is selected for household creation | Minor | Manual | Internal | Closed | Development | Saranya | Developer missed handling this negative scenario. | Moving forward, Developers will also do proper Unit testing before pushing this to TST env
| GGO 7.25.0 Sprint 2 | GGO-14855 | GGO-14802 | Rajesh/Saranya/Sathiya | Defect | Dropdown under Actions is disabled when searching for supporters and no records are found, and also few UI Alignment issues | Significant | Manual | Internal | Inprogress | Development | Priya | Developer missed handling this negative scenario. | Moving forward, Developers will also do proper Unit testing before pushing this to TST env
| GGO 7.25.0 Sprint 2 | GGO-14856 | GGO-14802 | Rajesh/Saranya/Sathiya | Defect | when saved search is selected no new search can be done | Significant | Manual | Internal | Rejected | Development | Conor | Developer missed handling this negative scenario. | Moving forward, Developers will also do proper Unit testing before pushing this to TST env
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.25.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-06-26 | 2025-07-10 | GGO 7.25.0 Sprint 1 | Saranya | GGO-14799 | API update for next gen section times | Completed | 2 | 2 |  | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8619 | 2025-07-03 | 2025-07-03 | Rajesh |  | Michael Wall | 2025-07-03 |  |  |  | 3 July 2025 at 09:11 Verified in the TST env.Working fine
2 | GGO Web | 2025-06-26 | 2025-07-10 | GGO 7.25.0 Sprint 1 | Sathiya | GGO-14699 | GGO Reskin - Update for the Project Home for Total sales grid | Completed | 3 | 3 |  | Sathiya | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8606 | 2025-06-30 | 2025-07-01 | Rajesh |  | Michael Wall | 2025-07-01 |  |  |  | 3 July 2025 at 08:03 Verified in the TST env.
3 | GGO Web | 2025-06-26 | 2025-07-10 | GGO 7.25.0 Sprint 1 | Saranya | GGO-14700 | GGO Reskin - Update for the Project Home for the Total Payments grid | Completed | 3 | 3 |  | Saranya | Sathya |  | Sathiya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8612 | 2025-07-01 | 2025-07-02 | Rajesh |  | Michael Wall | 2025-07-02 |  |  |  | 3 July 2025 at 08:06 Verified in the TST env.
4 | GGO Web | 2025-06-26 | 2025-07-10 | GGO 7.25.0 Sprint 1 | Rajesh/Sathya/Saranya | GGO-14687 | GGO Reskin - Implement the View Supporter page | Being Developed | 5
5 | GGO Web | 2025-06-26 | 2025-07-10 | GGO 7.25.0 Sprint 1 | Rajesh | https://greatergiving.atlassian.net/browse/GGO-14798 | Go Time Script Update | Completed | 2 | 2
6 | GGO Web | 2025-06-26 | 2025-07-10 | GGO 7.25.0 Sprint 1 | Rajesh/Sathya/Saranya | GGO-14802 | GGO Reskin - Implement the View Supporter common controls | Being Developed | 5

## GGO 7.24.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Saranya | GGO-14682 | Reskin update for the User profile | Completed | 5 | 5 |  | Priya | Priya | NA |  |  | NA | [9 empty] | Tested in the Dev and TST env. Few issues found. Testing completed in the TST env.
2 | GGO Web | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Rajesh/Sathiya/Saranya | GGO-14683 | Reskin update for the Project Home | Completed | 8 | 8 |  | Saranya/Sathiya/Rajesh | Priya | NA | Rajesh |  | http://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8598 | 2025-06-24 | 2025-06-25 | Rajesh |  | Michael Wall | 2025-06-25 |  |  |  | Testing completed in the TST env
3 | GGO Web | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Saranya/Sathiya | GGO-14763 | UI Issues | Completed |  |  |  | Saranya/Priya | Sathiya/Priya | NA | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8581 | 2025-06-14 | 2025-06-14 | Rajesh |  | Mike Horihan | 2025-06-14 |  |  |  | Tested in the TST env directly.Still one issues exists 5:25 PM 6/16/2025 Testing completed in the TST env
4 | GGO Web | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Priya-QA | GGO-14765 | GGO 7.24.0 CRT Release & Regression Testing | Completed | 3 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in the CRT env
5 | GGO Web | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Priya-QA | PAPI-866 | PAPI 7.19.0 CRT Release & Regression Testing | Completed | 3 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in the CRT env
6 | GGO Web | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Priya-QA | https://greatergiving.atlassian.net/browse/GGO-14732 | Update MFA physical address & other old addresses | Completed | 1 | 1 |  | NA | NA | NA |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in the TST env
7 | GGO Web | 2025-06-12 | 2025-06-26 | GGO 7.24.0 Sprint 4 | Saranya | https://greatergiving.atlassian.net/browse/GGO-14766 | Update Pendo Implementation | Completed | 2 | 2 |  |  | Priya | NA | [12 empty] | Testing completed in the TST env

## GGO 7.24.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Rajesh | GGO-14721 | GoTime - NextGen API Update - Changing to a new project doesn't persist on next login if user changed their home organization | Completed | 1 | 1 | [6 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8562 | 2025-06-10 | 2025-06-11 |  |  | Mike Horihan | 2025-06-11 |  |  |  | Completed
2 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Saranya | GGO-14682 | Reskin update for the User profile | Being Developed | 5 | 86 |  | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8576 | 2025-06-12 | 2025-06-12 | Rajesh |  | Michael Wall | 2025-06-12 |  |  |  | Raised bug under this story in the TST env.
3 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | SathiyaBharathi | GGO-14657 | Reskin for the TopBar | Completed | 3 | 3 | 74 | Sathiya | Priya | UI issues | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8531 | 2025-05-30 | 2025-06-10 | Rajesh |  | Michael Wall | 2025-06-10 |  |  |  | Testing completed in the TST env.
4 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Saranya | GGO-14724 | Implement OneTrust | Being Developed | 5 | [17 empty] | We do not have access to OneTrust Privay Policy Center and discussions are still ongoing on the client side. So Client has been moved this stroy to the backlog
5 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Rajesh | GGO-14683 | Reskin update for the Project Home | Being Developed | 5 | 18.5 | [16 empty] | Reskin-V2 is a complete overhaul of the existing Master Page. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness. Its taking more time to complete this since UI design work is new to the development team and it is bit challenging too
6 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Priya-QA | GGO-14722 | Stop checking expiration dates | Completed | 1 | 1 | 3 | [15 empty] | Did one round of Payment Regression Testing in the TST env
7 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Priya-QA | https://greatergiving.atlassian.net/browse/PAPI-864 | Stop checking expiration dates | Completed | 1 | 1 | [16 empty] | Did one round of Payment Regression Testing in the TST env
8 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | SathiyaBharathi | GGO-14744 | UI Issues | Completed | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8564 | 2025-06-10 | 2025-06-10 | Rajesh |  | Michael Wall | 2025-06-10 |  |  |  | Testing completed in the TST env.
9 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Rajesh | GGO-14748 | Update Hamburger Menu matching figma only with 3 lines, remove border | Completed | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8569 | 2025-06-11 | 2025-06-11 | Rajesh |  | Mike Horihan | 2025-06-11 |  |  |  | Testing completed in the TST env.
10 | GGO Web | 2025-05-29 | 2025-06-12 | GGO 7.24.0 Sprint 3 | Saranya / Sathiya | GGO-14763 | UI Issues | Being Developed

## GGO 7.24.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 7.24.0 Sprint 3 | GGO-14744 | GGO-14657 | Sathiya | Defect | UI Issues | Significant | Manual | Internal | Closed | Enhancements | Priya
| GGO 7.24.0 Sprint 3 | GGO-14748 | GGO-14657 | Rajesh | Defect | Update Hamburger Menu matching figma only with 3 lines, remove border | Significant | Manual | Internal | Closed | Enhancements | Rajesh
| GGO 7.24.0 Sprint 3 | GGO-14763 | GGO-14682 | Saranya/Sathiya | Defect | UI Issues | Significant | Manual | Internal | Inprogress | Enhancements | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.24.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 |  | 27.5 | [15 empty] | Issue not reproduceable in Dev and TST.Need to check query execution CRT The work around has been provided and ticket has been put on hold for now as it only impacts only one client/org and is of low priority
2 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Rajesh/ Sathiya | GGO-14656 | Nav Bar Update | Completed | 5 | 5 | 107 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8525 | 2025-05-28 | 2025-05-28 | Rajesh |  | Michael Wall | 2025-05-28 |  |  |  | Testing this in the Dev. In Progress 4:32 PM 5/27/2025
3 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Saranya | GGO-14679 | Sales Grid and Details Update for old Convenience Fee assets | Completed | 3 | 3 | 19 | Saranya | Rajesh |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8496 | 2025-05-16 | 2025-05-20 | Rajesh |  | Michael Wall | 2025-05-20 |  |  |  | Verified in the TST env successfully. 20 May 2025 at 05:52
4 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Saranya | GGO-9991 | "Purchaser Company Name" column causes error when the "Export" link is selected | Completed | 2 | 2 | 11.5 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8502 | 2025-05-19 | 2025-05-20 | Rajesh |  | Michael Wall | 2025-05-19 |  |  |  | Verified this in the TST env. 21 May 2025 at 09:23
5 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Rajesh | GGO-14708 | Remove Pivotal WebApi Project from GGO Repo - Unused project and it is using .Net Core 6 (deprecated version)* | Completed | 2 | 2 | 33 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8498 | 2025-05-17 | 2025-05-19 | Saranya |  | Michael Wall | 2025-05-20 |  |  |  | Offshore QA Verified this in the TST env. 21 May 2025 at 09:23
6 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Mike Wall/Rajesh/Saranya | GGO-14701 | Update Implementation of Flag to Disable Card Types in select Organizations | Completed | 2 | 2 | 23.75 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8508 | 2025-05-21 | 2025-05-21 | Rajesh |  | Michael Wall | 2025-05-21 |  |  |  | Verified in the TST env. 22 May 2025 at 08:01
7 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Mike Wall/Rajesh/Saranya | PAPI-858 | Update Flag to Disable Amex in select Organizations With Pre-Token Check* | Completed | 2 | 2 | 38 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8518 | 2025-05-22 | 2025-05-23 | Rajesh |  | Mike H | 2025-05-23 |  |  |  | Verified in the TST env. 22 May 2025 at 08:01
8 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Rajesh/Saranya | GGO-14684 | Implement Pendo for GGO | Completed | 5 | 5 | 41.75 | Rajesh | Priya |  | Saranyas |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8523 | 2025-05-27 | 2025-05-29 | Rajesh | 1. Let's add the following to the account metadata Environment: pendoEnvironment, 2. PendoUserID should be prefixed with PendoEnvironment so that UserID is unique across all environments 3. Dev and local should not fall under the same environment label | Mike H | 2025-05-29 |  |  |  | Testing this in the Dev. In Progress 4:32 PM 5/27/2025
9 | GGO Web | 2025-05-16 | 2025-05-29 | GGO 7.24.0 Sprint 2 | Saranya | GGO-14313 | HIGH- Usage of Manual HTML Sanitization (XSS) | Completed | 2 | 2 | 20.5 | Saranya | Rajesh |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8524 | 2025-05-27 | 2025-05-28 | Rajesh |  | Michael Wall | 2025-05-28

## GGO 7.24.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.24.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-13722 | High - Weak Encryption: Insecure Mode of Operation - Cryptography.cs: 56 | Completed | 1 | 1 | 15 | Sathiya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8458 | 2025-05-02 | 2025-05-02 | Rajesh |  | Michael Wall | 2025-05-03 |  |  |  | Verified in the TST env.5 May 2025 at 08:36
2 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-13723 | High - Weak Encryption: Insecure Mode of Operation - SymmetricAlgorithmProvider.cs: 35 | Completed | 1 | 1 | 34.5 | Sathiya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8457 | 2025-05-02 | 2025-05-06 | Rajesh |  | Michael Wall, Loan Troung | 2025-05-07 |  |  |  | Tested in the TST env 7 May 2025 at 09:20
3 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-14618 | MEDIUM - BDSA-2024-4605 - System.IdentityModel.Tokens.Jwt/5.5.0 | Completed | 2 | 2 | 10.25 | Sathiya | Rajesh |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8474 | 2025-05-07 | 2025-05-08 | Rajesh |  | Michael Wall | 2025-05-08 |  |  |  | Tested in the Dev env 8:09 PM 5/7/2025
4 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Rajesh/Saranya | PAPI-841 | Fix ValidateAndGetPorticoToken calls to handle when Token or CardBrandTransactionId exists | Completed | 2 | 2 | 18 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8477 | 2025-05-08 | 2025-05-09 | Rajesh |  | Michael Wall | 2025-05-09 |  |  |  | Did one round of Payment Regression Testing for this story in the TST env.9 May 2025 at 09:19
5 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Saranya | GGO-14601 | Project UI accepting Invalid Email address results in error on GGO to SF sync | Completed | 2 | 2 | 35 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8463 | 2025-05-05 | 2025-05-06 | Rajesh |  | Michael Wall | 2025-05-06 |  |  |  | Test Cycle executed Successfully in the TST env.7 May 2025 at 07:30
6 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Saranya | GGO-14652 | Enable Online Bidding - Blocked when users mistakenly generate Display Board | Completed | 5 | 5 | 49.5 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8476 | 2025-05-08 | 2025-05-10 | Rajesh |  | Michael Wall | 2025-05-12 |  |  |  | Tested in the TST env 13 May 2025 at 09:16
7 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1[Stretch] | Rajesh | GGO-14678 | Unable to Export Sales* | Completed | 2 | 2 | 19 | Rajesh | Sathiya,Priya |  |  |  | NA | NA | NA | NA |  | NA | NA
8 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 | 0 | 50.5 | [15 empty] | Issue not reproduceable in Dev and TST.Need to check query execution CRT
9 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Rajesh/ Sathiya | GGO-14656 | Nav Bar Update | Being Developed | 3 | 0 | 64.5 | [15 empty] | Reskin-V2 is a complete overhaul of the existing Master Page, focusing on delivering a fully responsive design. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness.
10 | GGO Web | 2025-05-02 | 2025-05-15 | GGO 7.24.0 Sprint 1 | Priya-QA | GGO-14619 | MEDIUM - CVE-2024-43485 - System.Text.Json/8.0.4 | Completed | 1 | 1 | 29 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env.

## GGO 7.24.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO 7.24.0 Sprint 1 | GGO-14678 | GGO-13890 | Rajesh | Defect | Unable to Export Sales* | Major | Manual | External | Closed | Enhancements | End User | This is a production issue. The export sale grid functionality broke due to changes in the SLS report | For every small change implemented, a complete regression testing cycle must be performed to ensure system stability. This includes updating both automation and manual test cases to reflect any new or impacted scenarios. Additionally, thorough verification of all buttons across all application pages must be included, and corresponding scenarios should be documented and maintained in the manual test cases to ensure comprehensive coverage.
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.23.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Saranya | PAPI-840 | Remove the use of StringHashTable | Completed | 3 | 3 | 23.5
2 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Rajesh, Saranya | GGO-14644 | Remove Hash table in PAPI - GGO need to pass Bluetooth Swipe data on StoreFront scenario* | Completed | 1 | 1 | 14.5 | [15 empty] | Completed One round of Payment Regression
3 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Rajesh | GGO-14614 | HIGH - Microsoft.AspNetCore.Http.Connections.Client:1.0.0 | Completed | 2 | 2 | 19.5 | Rajesh | Sathish,Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8431 | 2025-04-23 | 2025-04-23 | Rajesh |  | Loan Troung | 2025-04-23 |  |  |  | Completed One round of Standard Regression
4 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Sathya | GGO-14613 | HIGH - Cross-Site Scripting: DOM - MaintenanceNotification.js: 22 & 25 | Completed | 2 | 2 | 34.5 | Sathiya | Rajesh,Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8434 | 2025-04-24 | 2025-04-28 | Rajesh |  | Michael Wall, Loan Troung | 2025-04-28
5 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4[Stretch] | Sathya | GGO-14658 | CRITICAL - CVE-2021-43569 - starkbank-ecdsa/1.3.1* | Completed | 1 | 1 | 14 | Sathiya | Rajesh,Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8436 | 2025-04-25 | 2025-04-28 | Rajesh |  | Michael Wall | 2025-04-28 |  |  |  | Development has been completed and tested in local and Dev enviroment[28-April-2025] Completed One round of Standard Regression
6 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Sathiya, Rajesh | GGO-13722 | High - Weak Encryption: Insecure Mode of Operation - Cryptography.cs: 56 | Peer review | 1 | 0.5 | 12.5 | Sathiya | Rajesh |  |  |  | NA
7 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Saranya | GGO-14615 | HIGH - Microsoft.Bcl.Async:1.0.168 | Completed | 2 | 2 | 10.5 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8427 | 2025-04-22 | 2025-04-22 | Rajesh |  | Loan Troung | 2025-04-22 |  |  |  | Completed One round of Standard Regression
8 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Saranya | GGO-13723 | High - Weak Encryption: Insecure Mode of Operation - SymmetricAlgorithmProvider.cs: 35 | Peer review | 1 | 0.5 | 22 | [5 empty] | NA
9 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4[Stretch] | MikeW, Rajesh, Saranya | GGO-14651 | Pass New IsFallback Swipe Flag from GoTime to PAPI | Completed | 2 | 2 | 36 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8440 | 2025-04-28 | 2025-04-28 | Rajesh |  | Michael Wall | 2025-04-28
10 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | MikeW, Rajesh, Saranya | PAPI-846 | EMV Fallback Requires <EMVChipCondition> Tag along with Swipe Data* | Completed | 3 | 3 | 48 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8441 | 2025-04-28 | 2025-04-28 | Rajesh |  | Michael Wall | 2025-04-28
11 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Priya-QA | GGO-14649 | 22 APR GGO 7.23.0 CRT Release & Regression Testing | Completed | 5 | 5 | 35.5 | [15 empty] | CRT Regression Testing in Progress
12 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4 | Priya-QA | PAPI-851 | 22 APR PAPI 7.18.0 CRT Release & Regression Testing | Completed | 3 | 3 | 22 | [15 empty] | CRT Regression Testing in Progress
13 | GGO Web | 2025-04-17 | 2025-05-01 | GGO 7.23.0 Sprint 4[Stretch] | Sathiya | GGO-14616 | HIGH & MEDIUM - Microsoft.Owin.Security.OpenIdConnect:4.2.2 | Completed | 2 | 2 | 5.5 | N/A | N/A | N/A | Rajesh |  | N/A | [9 empty] | Since we can't move Reskin Project from .net framework to .netcore update the comments in the story [04/30/2025]

## GGO 7.23.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO Web | GGO-14614 | GGO-14662 | Sathiya | Defect | Section Times Page Fails to Load After Launch – 500 Internal Server Error in Console | Significant | Manual | Internal | Closed | Development | Priya/Rajesh |  | As we updated Microsoft.AspNetCore.Http.Connections.Client:1.0.0 package to latest version 6.0.0.0 but it's dependent package Microsoft.Azure.SignalR.Asp.Net not updated by default Visual Studio and Pipeline doesn't show any exception
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.23.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Sathiya | GGO-14573 | OP to GGO import timeouts | Completed | 3 | 3 | 42 | Sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8370 | 2025-04-07 | 2025-04-08 | Rajesh |  | Mike Wall and Loan | 2025-04-08
2 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Rajesh | GGO-14633 | Allow Household Share on RSVP Imported Cards | Completed | 3 | 3 | 53 | Rajesh | Priya | Nill
3 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Sathiya | GGO-14457 | Allow Multiple RSVP Import from OP | Completed | 5 | 5 | 83 | sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8380 | 2025-04-14 | 2025-04-15 | Rajesh |  | Mike Wall and Loan | 2025-04-15
4 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3-[Stretch] | Saranya/Sathiya | GGO-14620 | BID-19 Admissions Count issue* | Completed | 3 | 3 | 13.5 | Sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8407 | 2025-04-16 | 2025-04-16 | Rajesh |  | Mike Wall | 2025-04-16
5 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3-[Stretch] | Priya-QA,Rajesh | PAPI-839 | Ensure all Portico calls use the client's API Key* | Completed | 1 | 1 | 13.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
6 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Priya-QA | GGO-14617 | HIGH & MEDIUM-Serilog.Sinks.File:4.0.0 | Completed | 1 | 1 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed 'testing in the TST env. 11:19 PM 4/7/2025
7 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Priya-QA,Rajesh | PAPI-842 | Fix issue where Payer Records CreditCardStatus are being set to Invalid | Completed | 2 | 2 | 17.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rajesh - Supported to analyze the root cause. Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario
8 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3 | Saranya | PAPI-840 | Remove the use of StringHashTable | Peer Review | 8 | 5 | 90.5 | Sathiya | Priya | Nill | [12 empty] | Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario. The story was left in Peer Review upon completion, per the client's request to hold it and maintain this branch separately from the CERT branch. Dependency on Onsite QA now
9 | GGO Web | 2025-04-03 | 2025-04-17 | GGO 7.23.0 Sprint 3-[Stretch] | Saranya,Rajesh | GGO-14644 | Remove Hash table in PAPI - GGO need to pass Bluetooth Swipe data on StoreFront scenario* | Peer Review | 2 | 1 | 19.5 | Sathiya | Priya | Nill | [12 empty] | Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario. The story was left in Peer Review upon completion, per the client's request to hold it and maintain this branch separately from the CERT branch. Dependency on Onsite QA now

## GGO 7.23.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | Comment | RCA Comment
| GGO Web | GGO-14646 | GGO-14457 | Rajesh | Defect | Code mistakenly overwritten for GGO-14457 | Significant | Manual | Internal | Closed | Development | Rajesh | GGO-14633 Code mistakenly overwritten for GGO-14457. TThe team addressed the issue promptly, and the defect was resolved and closed on the same day. | Going forward team will make sure these kinds of overwrites will not be repeated and will do the review process accordingly
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?
Note on O1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.23.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Rajesh | GGO-14594 | Invoice Payment Pages are calculating unapplied convenience fees | Completed | 2 | 2 | 22.5 | Rajesh | Saranya/Priya | NA |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8336 | 2025-03-24 | 2025-03-24 | Rajesh |  | Loan Troung | 2025-03-24 |  |  |  | Email Queues and Quartz job issue blocked us to test this. Verified this story in the TST env. 3/28/2025. But still Quartz job issue exists.
2 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14621 | Email queues in TST repeatedly disabling* | Completed | 1 | 1 | 9 |  |  | NIL | [12 empty] | Email Queues issue got fixed. But still Quartz job issue exists in the TST env.
3 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14626 | Quartz Job not sending email in TST environment* | Completed | 1 | 1 | 2 |  |  | NIL | [12 empty] | Quartz job issue exists in the TST env.
4 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Sathiya | GGO-14589 | New clients don't have Invoicing capabilities | Completed | 2 | 2 | 13 | Sathya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8330 | 2025-03-21 | 2025-03-21 | Rajesh |  | Mike Horihan | 2025-03-22 |  |  |  | Completed Testing in the TST env. 3/25/2025
5 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Sathiya | GGO-14606 | Duplicate EventXCode's are Being Created | Completed | 3 | 3 | 71 | Sathya | Rajesh,Priya | NIL |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8355 | 2025-03-27 | 2025-03-28 | Rajesh |  | Loan Troung,Michael Wall | 2025-03-28 |  |  |  | Testing in progres 7:17 PM 3/28/2025
6 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Saranya | GGO-14587 | Invoice is not importing or clearing from import area | Completed | 2 | 2 | 32 | Saranya | Sathya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8338 | 2025-03-24 | 2025-03-25 | Rajesh |  | Loan Troung | 2025-03-25 |  |  |  | Completed Testing in the TST env. 3/28/2025
7 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Saranya | GGO-14573 | OP to GGO import timeouts | Being Developed | 3 | 5 | 97 | [15 empty] | We have reproduced this issue in DEV and TST environments but are still unable to reproduce it locally. Based on our analysis, GetClosedMatches method seems to be causing the issue. This method is used to find the closest matched names for the given input names and utilizes the Jaro-Winkler algorithm
8 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2 | Priya-QA | GGO-14161 | Rewrite AGG-13 to a new report toolset | Completed | 1 | 1 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/25/2025
9 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14597 | Deprecated "DOMNodeInserted" & "DOMSubtreeModified" event throwing error in multiple places * | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/28/2025
10 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | PAPI-807 | Not all Credit Card Last 4 being added to payments table after hotfix PAPI-795* | Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
11 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14592 | Not all Credit Card Last 4 being added to payments table after hotfix PAPI-795* | Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
12 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14473 | Remove equipment banner* | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/25/2025
13 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | PAPI-839 | Ensure all Portico calls use the client's API Key* | Being Tested | 1 | 1 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test Client API Key's. Offshore QA did payment Regression Testing only.
14 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh,Sathiya | GGO-14602 | Handle message for 3X Reader Wi-Fi connection failed - StoreFront* | Completed | 2 | 2 | 1 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8362 | 2025-04-01 | 2025-04-01 | Rajesh | NA | Loan
14 | GGO Web | 2025-03-20 | 2025-04-03 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14624 | Previous/Next Month buttons not displaying in apAdmin* | Completed | 1 | 1 | 1 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8363 | 2025-04-01 | 2025-04-01 | Rajesh | NA | MikeWall |  |  |  |  | Supported Loan for this story

## GGO 7.23.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | RCA Comment
| GGO 7.23.0 Sprint 2 | GGO-14626 | NA | Rajesh | Defect | Quartz Job not sending email in TST environment* | Significant | Manual | Internal | Closed | Environment_Related | Priya | Deops team did setup new access rule for Azure Image Storage, missed to include Quartz Job server that results in failure of Quartz Job, finally fixed it by giving access for Quartz job server.
| GGO 7.23.0 Sprint 2 | GGO-14621 | NA | Rajesh | Defect | Email queues in TST repeatedly disabling* | Significant | Manual | Internal | Closed | Environment_Related | Priya,Nathan | This was issue related to Aesop Service bounce email not validated in Send Grid, removing the bounce email from Queue fixed this issue.
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.23.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Rajesh | GGO-14535 | OPStats.GetRsvpCount not being cached correctly | Completed | 2 | 2 | 22 | Rajesh | Priya | NIL |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8288 | 2025-03-06 | 2025-03-07 | Rajesh |  | Michael Wall | 2025-03-07 |  |  |  | Completed Testing 3/11/2025 7:40 PM
2 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Rajesh | PAPI-822 | Handle SystemError Response From Portico SOAP Call | Completed | 2 | 2 | 2.25 | Rajesh |  |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8291 | 2025-03-07 | 2025-03-08 | Rajesh |  | Michael Wall, Loan Troung | 2025-03-08
3 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | SathiyaBharathi | GGO-13890 | Rewrite and Update SLS-10 | Completed | 3 | 3 | 45.5 | Sathiya/Rajesh | Priya | NIL | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8300 | 2025-03-11 | 2025-03-11 | Rajesh |  | Michael Wall | 2025-03-11 |  |  |  | Completed Testing in the TST env 8:00 PM 3/12/2025
4 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Saranya | PAPI-816 | Investigate Check-In not storing Card or Payer record for Go-Time Enter Card on EMV TAP when flag Portico_TestingNeverSendToProcessor=true | Completed | 2 | 2 | 14.25 | Saranya | Sathiya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8293 | 2025-03-07 | 2025-03-10 | Rajesh |  | Michael Wall | 2025-03-11 |  |  |  | Completed Testing in the TST env. 3/11/2025 7:40 PM
5 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Rajesh | GGO-14576 | Investigate Card Verify Failure Message | Completed | 2 | 2 | 2.25 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8292 | 2025-03-07 | 2025-03-08 | Rajesh |  | Michael Wall, Loan Troung | 2025-03-08
6 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Saranya | PAPI-809 | HIGH - jQuery/2.0.0 in PapiAdmin | Completed | 2 | 2 | 33.75 | Saranya | Rajesh |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8314 | 2025-03-14 | 2025-03-14 | Rajesh |  | Michael Wall, Loan Troung | 2025-03-14 |  |  |  | Did one round of Payment Regression Testing in the TST env
7 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Rajesh | PAPI-808 | HIGH - CVE-2024-43485 System.Text.Json 8.0.4 | Completed | 2 | 2 | 11.75 | Rajesh | Saranya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8312 | 2025-03-13 | 2025-03-14 | Rajesh |  | Michael Wall, Loan Troung | 2025-03-14 |  |  |  | Did one round of Payment Regression Testing in the TST env
8 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1-[Stretch] | SathiyaBharathi/ Saranya/Rajesh | GGO-14586 | At Least 3 Card Brands Can Have Up to 19 Digit PAN* | Ready For Testing | 5 | 5 | 72 | Saranya/Rajesh | Priya | NIL | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8320 | 2025-03-18 | 2025-03-19 | Rajesh |  | Michael Wall | 2025-03-19 |  |  |  | Development has been completed and partially completed testing in dev environment[03/19/2025]. Did one round of payment Regression for this story in the TST env.
9 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1-[Stretch] | SathiyaBharathi/Rajesh | PAPI-829 | At Least 3 Card Brands Can Have Up to 19 Digit PAN* | Ready For Testing | 2 | 2 | 11.5 | Sathiya/Rajesh | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8318 | 2025-03-18 | 2025-03-19 | Rajesh |  | Michael Wall | 2025-03-19 |  |  |  | Development has been completed and partially completed testing in dev environment. [03/19/2025]
10 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1-[Stretch] | Rajesh | GGO-14587 | Invoice is not importing or clearing from import area* | Being Developed | 3 |  | 14.5
11 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Priya-QA | GGO-14584 | Resolve new issues introduced to automation | Completed | 1 | 1 | 22 | [15 empty] | Dev completed. Testing in Progress. Facing Mailinator Issues in the TST env. Completed Coding and Execution and Raised PR
12 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Priya-QA/ Sathiyabharathi/ Rajesh | PAPI-820 | Update the Portico Batch delayed interval | Completed | 1 | 1 | 18 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
13 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Priya-QA/ Rajesh | GGO-14596 | Add 3X SWIPE card payment method type* | Completed | 1 | 1 | 2 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
14 | GGO Web | 2025-03-07 | 2025-03-20 | GGO 7.23.0 Sprint 1 | Priya-QA | PAPI-819 | Fix 3X Swipe not Storing CCN Last4 GoTime ¦ Checkin ¦ Enter Card, & StoreFront | Completed | 1 | 1 | 1 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.

## GGO 7.23.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | RCA Comment
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.22.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Saranya | GGO-14070 | Rewrite BID-15 to a new report toolset | Completed | 2 | 2 | 15.5 | Saranya | Priya | Alignment Issues/ Design Issues | [12 empty] | Test Case Prepartion is done 5:48 PM 2/7/2025. Tested in dev env. 7:30 PM 2/19/2025 Carry forwarded to next sprint : Saranya worked on the RDLC report and own the full task took some time for her to learn and implement. Bug GGO-14564 was created on 20/02/2025. Pull request created on 20/02/2025 and Closed on 21 February 2025 at 03:41
3 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Sathiyabharathi | GGO-14547 | Edit Package Image Display Issue | Completed | 2 | 1 | 9 | Sathiya | Priya | NA |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8265 | 2025-02-21 |  | Rajesh | [6 empty] | Peer testing N/A for this bug it's required DB update. Priya: Verified in TST env.8:56 PM 2/24/2025
4 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Sathiyabharathi | GGO-14545 | Move the Azure Storage Settings in to Redis/IIS cache to avoid multiple DB calls | Completed | 2 | 3 | 40.25 | Sathiya | Priya | NA |  |  | http://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8272 | 2025-02-26 | 2025-02-26 | Rajesh | [6 empty] | [02/25/2025]-Created draft PR. Dev Testing in Progress. Tested in the TST env. Working well 7:47 PM2/27/2025
5 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Loan/Sathiyabharathi | GGO-14510 | High - BDSA-2024-4305 - bootstrap/4.6.2 | Being Tested | 5 | 3 | 75.25 | Sathiya |  | NA | [7 empty] | Loan Troung | 2025-02-26 |  |  |  | This story is developed by an onsite developer (Loan). After a Bootstrap version update, we’re facing some UI issues. Offshore developer (Sathiya) is assisting with that. Tested this in the TST env. Raised a bug under this. 5:51 PM 3/5/2025. Nathan Comments: Got some Errors in Automation. So It require automation code updates or app code fix.
6 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Saranya | GGO-14567 | Bypass Verify on 3X Storefront swipe | Completed | 2 | 2 | 34.5 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8281 | 2025-02-28 | 2025-03-04 | Rajesh |  | Loan Troung | 2025-03-05 |  |  |  | We dont have access to test EMV transactions. Did Payment Regression Testing using manual cards. Since Portico is down, we were not able to verify swipe transactions. Portico is UP on last day of sprint, Verified and Completed.
7 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Saranya | PAPI-811 | Bypass Verify on 3X Storefront swipe | Completed | 2 | 2 | 35.75 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8282 | 2025-02-28 | 2025-03-04 | Rajesh |  | Loan Troung | 2025-03-05 |  |  |  | We dont have access to test EMV transactions. Did Payment Regression Testing using manual cards. Since Portico is down, we were not able to verify swipe transactions. Portico is UP on last day of sprint, Verified and Completed.
8 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4-[Stretch] | Saranya | GGO-14535 | OPStats.GetRsvpCount not being cached correctly | Being Developed | 2 | 2 | 31 | [15 empty] | Stretch story taken 1 day before sprint end, so got carry forwarded to next sprint.
8 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14546 | Automation Maintenance | Completed | 1 | 1 | 10 | [15 empty] | Coding is still in progress 8:55 PM 2/24/2025. Completed almost all the files. Execution is in Progress 8:33 PM 3/3/2025 Execution Completed on 3/5/2025.
9 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | PAPI-797 | Ensure Credit Card Last 4 is stored in Payers and Payments tables for 3X tap/dip | Completed | 1 | 1 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only. Testing blocked (since yesterday) by partial Portico outage – cannot generate successful EMV transactions.
10 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14566 | 25 Feb GGO 7.22.0 CRT Release & Regression Testing | Completed | 1 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | CRT Regression Testing is in Progress. 8:31 PM 3/3/2025.Partially blocked by Portico transaction failures in CRT.Completed Remaining scenario from our end
11 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14509 | Critical - Privacy Violation | Completed | 1 | 1 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in TST env. 8:31 PM 3/3/2025
12 | GGO Web | 2025-02-21 | 2025-03-06 | GGO 7.22.0 Sprint 4 | Priya-QA | PAPI-812 | 25 Feb PAPI 7.17.0 CRT Release & Regression Testing | Completed | 1 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | CRT Regression Testing is in Progress. 8:31 PM 3/3/2025.Partially blocked by Portico transaction failures in CRT. Completed Remaining scenario from our end

## GGO 7.22.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Found By | RCA Comment
| GGO 7.22.0 Sprint 4 | GGO-14563 | GGO-14504 | Sathiyabharathi | Defect | If Adjusted Admissions purchased by one supporter 'even out,' Supporter Form -> Sales Summary does not show asterisk | Significant | Manual | Internal | Closed | Development | Nathan
| GGO 7.22.0 Sprint 4 | GGO-14564 | GGO-14070 | Saranya | Defect | Negative Price Amounts Not Displaying Correctly | Significant | Manual | Internal | Closed | Development | Priya
| GGO 7.22.0 Sprint 4 | GGO-14571 | GGO-14070 | Rajesh | Defect | Extra line appears after the Package Name in few scenario's | Significant | Manual | Internal | Closed | Development | Priya
| GGO 7.22.0 Sprint 4 | GGO-14510 | GGO-14579 | Loan/Sathiyabharathi | Defect | Alignment Issues in GGO-apAdmin Page | Significant | Manual | Internal | Closed | Development | Priya
Note on N1: Preethi Rajasekaran: 1. Whether it is Production Issue? 2. Issue found during? 3. Whether it was Escalation? 4. Who worked this?

## GGO 7.22.0 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14503 | Adjust Admission Functionality - add/remove | Completed | 2 | 2 | 23 | Sathiya | Priya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8189 | 2025-02-03 | 2025-02-04 | Rajesh |  | Loan Troung | 2025-02-04 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025 Deletion of attendee row if supporter chosen showed the popup confirmation, working on Adjusted amount calculation [1/29/2025] Did developer testing in dev environment no issues found [02/05/2025] Automation is pending[02/19/2025]. Nathan Closed the Automation Ticket
2 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | RajeshKannan | GGO-14450 | GGO Image Thumbnail Creation error | Completed | 2 | 2 | 2 | Rajesh | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8197 | 2025-02-04 | 2025-02-05 | Rajesh |  | Loan Troung | 2025-02-05
3 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Rajesh/Saranya | GGO-14529 | Invoice Timeout Fix | Completed | 1 | 1 | 7.5 |  | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8204
4 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Saranya | GGO-14070 | Rewrite BID-15 to a new report toolset | Peer Review | 5 | 5 | 84.5 |  | Priya | [13 empty] | Test Case Prepartion is done 5:48 PM 2/7/2025. Tested in dev env. 7:30 PM 2/19/2025 Carry forwarded to next sprint : Saranya worked on the RDLC report and own the full task took some time for her to learn and implement
6 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14530 | Image Manager Fix | Completed | 1 | 1 | 25.5 | Rajesh | Priya |  | Priya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8218 | 2025-02-07 | 2025-02-07 | Rajesh |  | Loan Troung | 2025-02-07 |  |  |  | 02/08/2025: This issue was Identitfied by CS and this is not a development or QA miss, this happens because the Javascript [DOM] component was deprecated and the code need to be updated accordingly.
7 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14504 | Adjust Admission Functionality - graph updates | Ready for Testing | 5 | 5 | 60 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8228 | 2025-02-12 | 2025-02-18 | Rajesh |  | Loan Troung | 2025-02-18 | GO PRINT N'Drop Procedure [dbo].[sp_GetAdjustedAdmissionCount]' GO IF OBJECT_ID('[dbo].[sp_GetAdjustedAdmissionCount]') IS NOT NULL DROP PROCEDURE [dbo].[sp_GetAdjustedAdmissionCount]; GO It is not necessary, but we do usually add PRINT statement. |  |  | Tested in the Dev env. 5:09 PM 2/17/2025. Completed testing the TST env. 8:27 PM 2/18/2025 Onsite QA Logged bug on last day of sprint, we fixed it deployed before sprint prep, QA didn't get time to complete it.
8 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Priya-QA | GGO-14071 | Rewrite BID-19 to a new report toolset | Completed | 1 | 1 | 22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Test Case Prepartion is done 5:48 PM 2/7/2025. Testing in dev env. 8:41 PM 2/13/2025. Completed Testing in the TST env.
9 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 3 | Priya-QA | PAPI-758 | Add support for additional Card Types | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. Verified all the cards 8:26 PM2/18/2025

## GGO 7.22.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| GGO 7.22.0 Sprint 3 | GGO-14542 | GGO-14503 | Sathiyabharathi | Bounceback/Sub-Defect | Admission UI should display even after saving sale with admissions adjusted to 0 | Significant | Manual | Internal | Closed/Rejected | Development
| GGO 7.22.0 Sprint 3 | GGO-14544 | GGO-14503 | Sathiyabharathi | Bounceback/Sub-Defect | Fix for GGO-1077 no longer working (allocation deleted via supporter) | Significant | Manual | Internal | Closed/Rejected | Development
| GGO 7.22.0 Sprint 3 | GGO-14563 | GGO-14504 | Sathiyabharathi | Bounceback/Sub-Defect | If Adjusted Admissions purchased by one supporter 'even out,' Supporter Form -> Sales Summary does not show asterisk | Significant | Manual | Internal | Inprogress | Development
| GGO 7.22.0 Sprint 3 | GGO-14564 | GGO-14070 | Sathiyabharathi | Bounceback/Sub-Defect | Negative Price Amounts Not Displaying Correctly | Significant | Manual | Internal | Inprogress | Development
| GGO 7.22.0 Sprint 3 | GGO-14530 |  |  | Defect | Image Manager Fix - the Scroll was not working so the CS was only able to see the 1st set of records and nothing beyond that | Significant | Manual | External | Closed/Rejected | Enhancements | This issue was Identitfied by CS and this is not a development or QA miss, this happens because the Javascript [DOM] component was deprecated and the code need to be updated accordingly.

## GGO 7.22.0 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Saranya | GGO-12487 | Adjust Admission Functionality - sale details | Completed | 5 | 5 | 23 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8184 | 2025-01-30 | 2025-01-30 | Rajesh |  | Loan Troung | 2025-01-30 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025. Priya - Testing in dev env is in progress 4:48 PM 1/30/2025
2 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Sathiyabharathi | GGO-14503 | Adjust Admission Functionality - add/remove | Ready for Testing | 5 | 5 |  | Sathiya |  |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8189 | 2025-02-03 | 2025-02-04 | Rajesh |  | Loan Troung | 2025-02-04 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025 Deletion of attendee row if supporter chosen showed the popup confirmation, working on Adjusted amount calculation [1/29/2025] Did developer testing in TST environment no issues found [02/04/2025] Onsite QA testing pending since [02/04/2025]
3 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | RajeshKannan | GGO-14514 | Update remaining admission allocated attendee count in GGO webserivce to OP | Completed | 1 | 1 |  | Rajesh | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8174 | 2025-01-24 | 2025-01-24 | Rajesh |  | Loan Troung | 2025-01-24 |  |  |  | Completed Testing in the TST env. 8:31 PM 1/29/2025
4 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Sathiyabharathi | GGO-14477 | BID-06 Header Settings Update | Completed | 2 | 2 |  | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8170 | 2025-01-23 | 2025-01-24 | Rajesh |  | Michael Wall | 2025-01-24 |  | This is QA automation which comes under Infrastructure improvement |  | Picked on 01/22/2025.Development in progress 23/01/2025 Deployed in dev and completed developer testing. Priya - Completed Testing in Dev. Working well 5:07 PM 1/24/2025. Completed Testing in TST 5:02 PM 1/27/2025
5 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | RajeshKannan | GGO-14450 | GGO Image Thumbnail Creation error | Ready for Testing | 2 | 2 |  | Rajesh | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8197 | 2025-02-04 | 2025-02-05 | Rajesh |  | Loan Troung | 2025-02-05 |  |  |  | It is completed and given for testing 3 days prior to Sprint end, Offshore QA doesn't got any access to test in TST, only MikeH and Nate got access to test it.
6 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Priya-QA | GGO-14511 | GoTime SF Tap card generate Null Ref Error | Completed | 2 | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Priya- Did one round of Payment Regression Testing since we dont have access to Tap cards. 5:01 PM 1/27/2025
7 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Priya-QA | PAPI-794 | Add Tag 9F6E to List of Acceptable Tags in ParseC3XJsonDataToTLV* | Completed | 1` | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Priya- Did one round of Payment Regression Testing since we dont have access to Tap cards. 8:00 PM1/28/2025
8 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 2 | Saranya | GGO-14529 | Stretch --Invoice Timeout Fix* | Peer Review | 2 | 2 | 12 | [5 empty] | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8204

## GGO 7.22.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| GGO 7.22.0 Sprint 2 | GGO-14529 | Production bug |  | Defect | Invoice timeout fix | Major | Manual | External | Open | Development | A miss from both Onsite and Offshore QA and Onsite and offshore developemnt because the old report generation handled it but the new report didn't so a miss on both testing and developement end. Extended testing needs to be done with a lot more combination of data which could be infinite combination.Moving forward this type of complex reports must be tested by all the team members including onsite lead before pushing to TST environment.

## GGO 7.22.0 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Sathiyabharathi/Rajesh Kannan | GGO-14427 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 3 (Sales & Payments) | Completed | 2 | 2 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8097 | 2024-12-31 | 2002-12-31 | Rajesh |  | Michael Wall | 2024-12-31 |  |  |  | Tested in the TST env. And it is In Progress 1/3/2025 8:13 PM. Tested in the Dev as well as in TST Env- 8:28 PM 1/6/2025. Testing is still in progress. 1/8/2025 8:10 PM
2 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Sathiyabharathi | GGO-14474 | Mismatch between the net invoice count and the report being generated. | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8112 | 2025-01-07 | 2025-01-08 | Rajesh |  | Loan Troung | 2025-01-08 |  |  |  | Tested in the Dev env. Looks good. 5:01 PM 1/21/2025.Tested in the TST env. Working well. 6:18 PM 1/22/2025
3 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Saranya | PAPI-790 | Insecure Transport: Database - App.config: 5 | Completed | 1 | 1 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8136 | 2025-01-11 | 2025-01-11 | Rajesh |  | Loan Troung | 2025-01-11 |  |  |  | Did one round of payment related regression Testing in the TST env. Looks good. 7:13 PM 1/16/2025
4 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Saranya/Rajesh Kannan | GGO-14450 | GGO Image Thumbnail Creation error | Being Developed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8158 | 2025-01-17 | 2025-01-21 | Rajesh |  | Loan Troung | 2025-01-21
5 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | GGO-14422 | Storefront Implement Signature Workflow in legacy go time code | Ready for Testing | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of payment Regression Testing in the TST env and checked cash and Check flow only(since I dont have EMV acces) Working well. 1/16/2025. 7:13 PM.
6 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA/Rajesh Kannan | GGO-14483 | 9 Jan CRT Release & Regression Testing | Completed | 5 | 5 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing in the progress CRT env.1/17/2025 4:37 PM. Testing is still in progress in CRT env. 1/20/2025 8:12 PM
7 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Saranya | PAPI-791 | Privacy Violation - PorticoSoapXmlBuilder.cs: 290 | Completed | 2 | 2 | [6 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | attempted to encrypt the entire XML section, but this failed during XML loading and saving. I observed this same privacy policy violation in two files: PorticoSoapXMLBuilder.cs and PorticoAdminBase.cs We chose PorticoAdminBase.cs for debugging and testing, this file SOAP envelope contains a username and password for Portico access. I encrypted only the username and password. However, I received a 'remote server returned 500 error' upon execution. Since the necessary data is encrypted, marking this as a false positive.
8 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | GGO-14469 | EMV Storefront - Implement Success Message for Card Entry flow | Completed | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of payment Regression Testing in the TST env. Working well. 1/17/2025 4:36 PM
9 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | GGO-14468 | EMV Checkin - Implement Success Message for Card Entry flow | Completed | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of payment Regression Testing in the TST env. Working well. 1/17/2025 4:36 PM
10 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | GGO-14447 | QA Automation - update EquipmentExpressVerification to account for date changes | Being Developed | 1 | 1 |  |  |  | NA |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGAutomation/pullrequest/8157 | 2025-01-17
11 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Priya-QA | PAPI-789 | refactor apConstants.EMV_SUCCESS_CODE and apConstants.EMV_FAILURE_CODE usage | Ready for Testing | 1 | 1 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Did one round of payment Regression Testing in the TST env. Working well. 4:35 PM 1/18/2025
12 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Saranya | GGO-14471 | Stretch --Update UI for Receipt Dialogue* | Completed | 2 | 2 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8166 | 2025-01-21 | 2025-01-22 | Rajesh |  | Loan Troung | 2025-01-22 |  |  |  | Tested in the TST env. Looks good. 6:17 PM 1/22/2025
13 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.22.0 Sprint 1 | Sathiyabharathi | GGO-14477 | Stretch -- BID-06 Header Settings Update.* | Being Developed | 2 | 2 | [16 empty] | Picked on 01/22/2025.Development in progress 23/01/2025 Deployed in dev and completed developer testing

## GGO 7.22.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| GGO 7.22.0 Sprint 1 | GGO-14489 | GGO-14427 | Sathiya | Defect | When the package number is entered under "omit sales and payments," it applies to all supporters, preventing the individual package values from being displayed for each supporter | Significant | Manual | Internal | Closed | Development
| GGO 7.22.0 Sprint 1 | GGO-14490 | GGO-14427 | Rajesh | Defect | Invoice link in email appearing twice when triggered from "Print/Email batch" | Significant | Manual | Internal | Closed | Development
| GGO 7.22.0 Sprint 1 | GGO-14500 | GGO-14483 | Rajesh | Defect | Print or Email Invoices - Over ride setting for "Show Invoice Page Link" & "Invoice Page Link Label" is not reflecting for a new email batch | Significant | Manual | Internal | Closed | Development | Verified in TST.Working well. 7:15 PM 1/16/2025
| GGO 7.22.0 Sprint 1 | GGO-14499 | GGO-14483 | Rajesh | Defect | implement quartz retry logic for invoice emails | Significant | Manual | Internal | Closed | Development | Unable to reproduce this issue in TST. Email sent successfully within few secs without getting any failures 7:18 PM 1/16/2025
| GGO 7.22.0 Sprint 1 | GGO-14512 | GGO-14483 | Rajesh | Defect | Report Bid-06 taking more time when selecting "View Items" in "Edit Invoice & Receipts settings" | Significant | Manual | Internal | Closed | Development | Tested in TST env. Working well. 8:11 PM 1/20/2025.

## GGO 7.21.0 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | SathyaBharathi/Rajesh Kannan | GGO-14325 | Rewrite and Update BID-06 (Invoice) using RDLC Part 1 | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan/Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8075 | 2024-12-17 | 2024-12-17 | Rajesh |  | Michael Wall | 2024-12-17 |  |  |  | Tested in the Dev environment - Informed few issues to the Team.12/17/202410:48 PM. Tested in the TST Env- 12/18/2024 7:20 PM.
2 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | SathyaBharathi/Rajesh Kannan | GGO-14426 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 2 (Sales Only) | Completed | 5 | 5 |  |  | Priya |  | Rajesh Kannan | [11 empty] | Rolling over remaining testing to this story - GGO-14427
3 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Saranya | GGO-14418 | Modify GGO SFDC Webservice | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8079 | 2024-12-13 | 2024-12-17 | Rajesh |  | Michael Wall | 2024-12-17 |  |  |  | Coordinated with saranya and Tested in Local -12/16/2024 8:56 PM.
4 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Saranya | GGO-14445 | Project Website - Remove Deprecated Share Functionality | Completed | 2 | 2 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8080 | 2024-12-13 | 2024-12-16 | Rajesh |  | Loan Troung | 2024-12-16 |  |  |  | Tested in the Dev environment - 12/16/2024 8:57 PM. Tested in the TST env. Working well. 12/17/2024 10:47 PM
5 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Rajesh Kannan | GGO-14419 | Duplicate EventXcode updated when GGO sync with SF | Completed | 3 | 3 |  |  | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8092 | 2024-12-27 | 2024-12-30 | Rajesh |  | Michael Wall | 2024-12-30
6 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Saranya/Rajesh Kannan | GGO-14375 | Pop-up warning on batch process with unapplied convenience fees | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8096 | 2024-12-31 | 2024-12-31 | Rajesh |  | Michael Wall | 2024-12-31 |  |  |  | Tested in the TST env. Working well 1/3/2025 8:13 PM
7 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Sathiyabharathi/Rajesh Kannan | GGO-14427 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 3 (Sales & Payments) | Being Tested | 5 | 5 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8097 | 2024-12-31 | 2002-12-31 | Rajesh |  | Michael Wall | 2024-12-31 |  |  |  | Tested in the TST env. And it is In Progress 1/3/2025 8:13 PM. Tested in the Dev as well as in TST Env- 8:28 PM 1/6/2025. Testing is still in progress. 1/8/2025 8:10 PM
8 | GGO Web | 2026-05-14 | 2026-05-28 | GGO 7.21.0 Sprint 4 | Sathiyabharathi | GGO-14474 | Stretch -- Mismatch between the net invoice count and the report being generated.* | Ready For Testing | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8112 | 2025-01-07 | 2025-01-08 | Rajesh |  | Loan | 2025-01-08

## GGO 7.21.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
| GGO 7.21.0 Sprint 4 | GGO-14479 | Sathiya | Defect | Design issues | Minor | Internal | Closed | Design
| GGO 7.21.0 Sprint 4 | GGO-14480 | Rajesh | Defect | Express indicator displaying on Top right in compact scenario even the Supporter is not marked as "Express Checkout" | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14481 | Sathiya | Defect | When the "Only Show Sales That Are Paid" option is enabled in the invoice settings, the "Total Due" field should not be displayed in the Bid 06 report but it is still visible | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14486 | Rajesh | Defect | Font not changing in Bid-06 RDLC report based on "General Accounts & Settings" | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14488 | Rajesh | Defect | Receipt Settings Override while sending Invoice email is not working | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14476 | Saranya | Defect | When the convenience fee is disabled, clicking on "Start New Batch" does not navigate to the next page. | Significant | Internal | Closed | Development
| GGO 7.21.0 Sprint 4 | GGO-14489 | Sathiya | Defect | When the package number is entered under "omit sales and payments," it applies to all supporters, preventing the individual package values from being displayed for each supporter | Significant | Internal | Inprogress | Development
| GGO 7.21.0 Sprint 4 | GGO-14490 | Rajesh | Defect | Invoice link in email appearing twice when triggered from "Print/Email batch" | Significant | Internal | Closed | Development

## GGO 7.21.0 Sprint 3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO 7.21.0 Sprint 3 | SathyaBharathi/Rajesh Kannan | GGO-14325 | Strech--Rewrite and Update BID-06 (Invoice) using RDLC | Inprogress | 5 | 5 | [15 empty] | It will get carry forward to next sprint, due to requirement change by MikeH. 2.[12/12/2024] Invoice Email Failed becuase of Quratz service required DB permission
2 | GGO 7.21.0 Sprint 3 | Saranya | PAPI-725 | High - Weak Encryption: Insecure Mode of Operation - Dukpt.cs: 102 | Completed | 3 | 3 | [15 empty] | Waiting for macroscope result 12/12 : Was marked out of Scope by Mike Horihan
3 | GGO 7.21.0 Sprint 3 | Saranya | GGO-12835 | Update to event date range fields and logic in GGO Project Builder* | Completed | 3 | 3 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8056 | 2024-12-04 | 2024-12-06 | Rajesh |  | Loan Troung, Michael Wall | 6-Dec-024
4 | GGO 7.21.0 Sprint 3 | Rajesh Kannan | GGO-14414 | Investigate GGO Client create/update API to handle Client sync process with SF* | Completed | 2 | 2 | [15 empty] | Investigation completed
5 | GGO 7.21.0 Sprint 3 | Priya | GGO-13319 | Azure Images CRT Testing | Completed | 1 | 1 | [15 empty] | Completed from our end
6 | GGO 7.21.0 Sprint 3 | Priya | GGO-14402 | 03 DEC GGO 7.20.1 CRT Release | Completed | 2 | 2
7 | GGO 7.21.0 Sprint 3 | Saranya | GGO-14383 | Stretch --Refund Reference Number Not Generating* | Completed | 2 | 2 | [5 empty] | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8071 | 2024-12-10 | 2024-12-11 | Rajesh |  | Loan Troung, Michael Wall | 2024-12-11 |  |  |  | Completed from our end
8 | GGO 7.21.0 Sprint 3 | Priya | PAPI-773 | Update to PAPI TLV response for success / fail Verify (Check-In) if not included | Ready for Testing | 1 | 1 | [15 empty] | Did one Round of Payment Regression Testing, Final testing pending for onsite QA
9 | GGO 7.21.0 Sprint 3 | Priya | PAPI-781 | Required Zip Code Problems with EMV Verify (AMEX Only) | Ready for Testing | 1 | 1 | [15 empty] | Did one Round of Payment Regression Testing, Final testing pending for onsite QA
10 | GGO 7.21.0 Sprint 3 | Priya | GGO-14425 | Remove "Transaction was Successful!" pop-up at the right corner of screen for EMV (Storefront & CheckInOut)* | Completed | 1 | 1 | [15 empty] | Did one Round of Payment Regression Testing

## GGO 7.21.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No Defects

## GGO 7.21.0 Sprint 2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | GGO 7.21.0 Sprint 2 | SathyaBharathi | GGO-14386 | BID-03 RDLC version ignoring grid selection for output | Completed | 3 | 3 | Sathiyabharathi | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8003 | 2024-11-18 | 2024-11-19 | Rajesh |  |  |  |  | Bug fix - Completed
2 | GGO 7.21.0 Sprint 2 | Saranya | GGO-14355 | Update Help Center URLS | Completed | 2 | 2 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8000 | 2024-11-15 | 2024-11-16 | Rajesh |  | Loan Troung | 2024-11-16 | The target has been assigned with a "_blank" but we still keep this button and ID. Where/which file is this ID being used? Looks like you removed the popup properties for it in file "GoTime.ts" line: 533 | Updated New helpcenter content - Completed
3 | GGO 7.21.0 Sprint 2 | Priya-QA | GGO-14361 | Add support for additional Card Types | Completed | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | GGO 7.21.0 Sprint 2 | Priya-QA | GGO-13319 | Azure Images CRT Testing | InProgress | 3 | 3 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | GGO 7.21.0 Sprint 2 | Saranya | GGO-14395 | Unable to add Discover cards in orgs enabled for Discover | Completed | 1 | 1 | Saranya | Priya | No | Sathiya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8022 | 2024-11-22 | 2024-11-22 | Rajesh | No | Mike Wall | 2024-11-22 | No | Defect story for GGO-14361 - Completed | No
6 | GGO 7.21.0 Sprint 2 | Rajesh | GGO-14397 | Image is not being retrieved from Azure after saving the Project or settings, even though Azure configuration is enabled | Completed | 2 | 2 | Rajesh | Priya | No | Sathiya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8022 | 2024-11-22 | 2024-11-22 | Sathiya | No | Mike Wall | 2024-11-22 | No | Bug fix - Completed | No
7 | GGO 7.21.0 Sprint 2 | SathyaBharathi/Rajesh | GGO-14385 | Investigate New App Svc for OB Queue Replacement | Completed | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Investigation - Completed | NA | It's an investingation story we prepared document and attached the jira ticket

## GGO 7.21.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments

## GGO 7.21.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.21.0 Sprint 1 | Rajesh/SathyaBharathi | GGO-14067 | Rewrite BID-03 to a new report toolset | 5 | 5 | Sathiyabharathi/Rajesh | Priya | GGO-14353 Alignment Issues and GGO-14378 Throwing 504 Gateway Timeout error while rendering Bid-03 report | Saranya | No | NA | NA | NA | NA |  | NA |  |  | Moving report to new toolset - Completed |  | Completed | Cretaed bugs under this story (GGO-14353 and GGO-14378) PR created and completed under those bugs
2 | GGO 7.21.0 Sprint 1 | Rajesh | GGO-14244 | Error when trying to create project website | 3 | 3 | Rajesh | Priya | No | Sathiya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7961 | 2024-11-06 | 2024-11-06 | Loan | I think if we are going to catch it, then we should log it. Log "info". |  | 2024-11-06 |  | Bug fix - Completed |  | Completed
3 | GGO 7.21.0 Sprint 1 | Sathiyabharathi | GGO-14353 | Alignment Issues | NA | NA | Sathiyabharathi | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7949 | 2024-11-08 | 2024-11-08 |  | No Comments | Michael Wall/Loan | 2024-11-08 | No Comments |  |  | Completed
4 | GGO 7.21.0 Sprint 1 | Sathiyabharathi | GGO-14378 | Throwing 504 Gateway Timeout error while rendering Bid-03 report | NA | NA | Sathiyabharathi | Priya |  | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7981 | 2024-11-12 | 2024-11-12 | Rajesh | No Comments | Michael Wall/Loan | 2024-11-12 | 1.is this variable name a typo ? "foud" vs "found" 2.Could we move all these spacing into a variable/constant before using? The variable naming provides meaning to why all these spacing are used. | Defect story for GGO-14067 - Completed |  | Completed
5 | GGO 7.21.0 Sprint 1 | Saranya | GGO-14295 | Handle Deleted User Session | 3 | 3 | Saranya | Priya |  | Sathiya | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7983 | 2024-11-13 | 2024-11-13 | Rajesh |  | Michael Wall | 2024-11-13 |  | Rolled over |  | InProgress | Trying to reproduce the issue in local
6 | GGO 7.21.0 Sprint 1 | Rajesh | GGO-14373 | ManageSalesAndPayments Error* | 2 | 2 | Rajesh | Priya | No | Sathiya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7968 | 2024-11-07 | 2024-11-08 | Loan | No Comments |  |  |  | Bug fix - Completed |  | Completed
6 | GGO 7.21.0 Sprint 1 | Saranya | GGO-14355 | Update Help Center URLS* | 3 | 2 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7988 | 2024-11-13 |  | Rajesh |  |  |  |  | Rolled over |  | InProgress | Development completed
7 | GGO 7.21.0 Sprint 1 | Priya-QA | PAPI-774 | Refunds failing to process | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | completed
8 | GGO 7.21.0 Sprint 1 | Priya-QA | GGO-14361 | Add support for additional Card Types | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | InProgress
9 | GGO 7.21.0 Sprint 1 | Priya-QA | GGO-14373 | ManageSalesAndPayments Error* | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed
10 | GGO 7.21.0 Sprint 1 | Priya-QA | GGO-14244 | Error when trying to create project website | 1 | 1 | NA | Priya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed

## GGO 7.21.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
| GGO 7.21.0 Sprint 1 | GGO-14244 | Rajesh | Defect | Error when trying to create project website | Major | Internal | Closed
| GGO 7.21.0 Sprint 1 | GGO-14378 | Sathiya | Defect | Throwing 504 Gateway Timeout error while rendering Bid-03 report | Significant | Internal | Closed
| GGO 7.21.0 Sprint 1 | GGO-14373 | OP Team | Defect | ManageSalesAndPayments Error | Major | External | Closed |  | Production Bug missed by OP Client team and fixed by GGO team . It is a defect which needs to be documented on OP team sheet but was fixed by GGO team

## GGO 7.20.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.20.0 Sprint 4 | Rajesh/SathyaBharathi | GGO-14067 | Rewrite BID-03 to a new report toolset | 5 |  |  | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7869 | 2024-10-24 | 2024-10-24 | Rajesh | No | Michael Wall | 2024-10-24 | can we have a folder for each report ? | Moving the report to new toolset - Rolled over |  | InProgress | We got an timeout issue while running the report in dev enviroment.
2 | GGO 7.20.0 Sprint 4 | Saranya | GGO-14340 | Login Page Update - Expiring Privacy Policy Message | 3 | 3 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7916 | 2024-10-23 | 2024-10-25 | Rajesh |  | Michael Wall | 2024-10-25 |  | To implement an expiring message with a url informing customers of an updated privacy policy on the GGO login page, to maintain compliance with corporate legal - Completed |  | completed
3 | GGO 7.20.0 Sprint 4 | Saranya | GGO-14244 | Error when trying to create project website* | 3 | 3 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7945 | 2024-10-30 | 2024-10-30 | Rajesh | No | Michael Wall | 2024-10-30 |  | Priority defect fix - Rolled over |  | InProgress
4 | GGO 7.20.0 Sprint 4 | Rajesh | GGO-14352] | Update Report Path in Publish XML | NA | NA |  | NA |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7930 | 2024-10-24 | 2024-10-24 |  |  | Michael Wall | 2024-10-24 | No |  |  | completed
5 | GGO 7.20.0 Sprint 4 | Priya-QA | GGO-13860 | GGO - handle emv dip/tap in check in/out | 1 | 1 | Loan | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | Rolled over | NA | completed
6 | GGO 7.20.0 Sprint 4 | Rajesh | PAPI-769 | PAPI-769 Update PAPI Web References* | 2 | 2 | Rajesh | Priya | No | NA | NA | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7934 | 2024-10-25 | 2024-10-25 | Mike Wall | No | NA | NA | No | Bug fix - Completed |  | completed
7 | GGO 7.20.0 Sprint 4 | Rajesh | GGO-14347 | Update the format of amount in payment receipt* | 1 | 1 | Sathiya | Priya | [11 empty] | Bug fix - Completed |  | Completed
8 | GGO 7.20.0 Sprint 4 | Saranya | GGO-14356 | Footer statement appears in the middle of the report instead of at the bottom when a footer is included. | 1 | 1 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7945 | [9 empty] | Completed

## GGO 7.20.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
| GGO 7.20.0 Sprint 4 | GGO-14353 | Sathiya | Defect | Alignment Issues | Minor | Internal | Open

## GGO 7.20.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.20.0 Sprint 3 | Rajesh/SathyaBharathi/Saranya | GGO-14067 | Rewrite BID-03 to a new report toolset | 5 | [14 empty] | Rewriting all the reports to new toolset and BID-03 is the Proof of Concept. Rolled over and team is still working on it.In a single report, multiple layouts are there |  | Inprogress
2 | GGO 7.20.0 Sprint 3 | Rajesh/Saranya | GGO-14079 | Rewrite BID-06 (Payment Receipt) using RDLC | 5 | 5 | Rajesh/Saranya | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7892 | 2024-10-12 | 2024-10-12 | Rajesh | No | Loan Troung, Michael Wall | 2024-10-12 | No | Similar to BID-03 |  | Closed
3 | GGO 7.20.0 Sprint 3 | Saranya | PAPI-751 | High - jQuery.UI.Combined/1.12.1 | 2 | 2 | Saranya | Rajesh |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7894 | 2024-10-15 | 2024-10-15 | Rajesh | No | Loan Troung, Michael Wall | 2024-10-15 | No | Part of Macroscope scanning epic |  | Closed
4 | GGO 7.20.0 Sprint 3 | Rajesh | GGO-14323 | Adding new GG Build Server for GGO Pipeline build replacing Azure Build server | 1 | 1 | Rajesh | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7873 | 2024-10-05 | 2024-10-05 | NA | No | Loan Troung, Michael Wall,Mike Horihan | 2024-10-05 | No |  |  | Closed
5 | GGO 7.20.0 Sprint 3 | Rajesh | GGO-14324 | Send PDF for email payment receipt | 3 | 3 | Rajesh/Saranya | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7892 | 2024-10-12 | 2024-10-12 |  | No | Loan Troung, Michael Wall | 2024-10-12 | No |  |  | Closed
6 | GGO 7.20.0 Sprint 3 | Priya-QA | GGO-14199 | Fix Deleted Credit Card Online Payment Pop-up Message / Function | 1 | 1 | Loan | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
7 | GGO 7.20.0 Sprint 3 | Rajesh/Saranya | GGO-14332 | Unable to view the Header and Footer Statement in the Payment Receipt even though they have already been added to the payment receipt settings |  |  | Rajesh/Saranya | Sathya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7896 | 2024-10-16 | 2024-10-16 | Rajesh | No | Michael Wall | 2024-10-16 | No | Bug for the Story GGO-14079 |  | Closed

## GGO 7.20.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
| GGO 7.20.0 Sprint 3 | GGO-14332 | Rajesh/Saranya | Defect | Unable to view the Header and Footer Statement in the Payment Receipt even though they have already been added to the payment receipt settings | Major | Internal | Closed | Enhancements

## GGO 7.20.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.20.0 Sprint 2 | Sathiyabharathi | GGO-14002 | Update AGG-03 | 3 | 3 | sathiya | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7840 | 2024-09-23 | 2024-09-26 | Rajesh | No | Loan Troung | 2024-09-26 | No | Concept of moving all the reports to new toolset | No | Closed
2 | GGO 7.20.0 Sprint 2 | Rajesh/SathyaBharathi/Saranya | GGO-14067 | Rewrite BID-03 to a new report toolset | 5 | [14 empty] | Concept of moving all the reports to new toolset |  | Inprogress
3 | GGO 7.20.0 Sprint 2 | Saranya | GGO-14300 | GetAdmissionInfo API update for mobile team | 3 | 3 |  | Priya | Yes(Found one Issue while testing this in Dev Env) | SathiyaBharathi | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7842 | 2024-09-23 | 2024-09-24 | Rajesh | No | Loan Troung, Michael Wall | 2024-09-24 | No | No | No | Closed
4 | GGO 7.20.0 Sprint 2 | Saranya | GGO-14302 | SFDC Release Support | 2 | 2 |  | Priya |  | SathyaBharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7835 | 2024-09-20 | 2024-09-20 | Rajesh | No | MikeH,Loan Troung | 2024-09-20 | No |  |  | Closed
5 | GGO 7.20.0 Sprint 2 | Sathiyabharathi | GGO-14255 | API update for nextgen search* | 1 | 1 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7817 | 2024-09-13 | 2024-09-19 | Rajesh | No | Loan Troung | 2024-09-19 | No | No | No | Closed
5 | GGO 7.20.0 Sprint 2 | Priya-QA | GGO-14267 | GGO Image Server | 2 | 2 | Loan | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
6 | GGO 7.20.0 Sprint 2 | Rajesh | GGO-13842 | Fallback Strategy for Report Migration | 2 | 2 | Rajesh | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7838 | 2024-09-20 | 2024-09-23 | Loan | No | Mike Wall | 2024-09-23 | No | This is for the new reporting toolset | No | Closed
7 | GGO 7.20.0 Sprint 2 | Priya-QA | PAPI-750 | Portico SOAP - Token and CardBrandTxnId* | 1 | 1 | Mike Wall | Priya | No | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed

## GGO 7.20.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments

## GGO 7.20.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.20.0 Sprint 1 | Sathiyabharathi | GGO-14287 | Renew localtest Certificate | 1 | 1 | Rajesh | Rajesh | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7791 | 2024-09-09 | 2024-09-09 | Rajesh |  | MikeH | 2024-09-09 | No | No | No | Closed
2 | GGO 7.20.0 Sprint 1 | Rajesh | GGO-14293 | Event payments processed under wrong event name, GGO and SF not synced correctly* | 1 | 1 | Rajesh | Rajesh | No | Rajesh |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
3 | GGO 7.20.0 Sprint 1 | Saranya | GGO-14218 | High - CVE-2024-30105 - System.Text.Json/4.7.2 & CVE-2024-30105 - System.Text.Json/4.6.0 | 2 | 2 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7702 | 2024-09-11 | 2024-09-11 | Rajesh | No | Michael Wall | 2024-09-11 | No | Macroscope scanning - fixed | No | Closed
4 | GGO 7.20.0 Sprint 1 | Sathiyabharathi | GGO-14215 | Cannot create/update Project Template in PROD | 2 | 2 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7800 | 2024-09-12 | 2024-09-12 | Rajesh | No | Loan Troung | 2024-09-12 | No | Priority defect - Fixed | No | Closed
5 | GGO 7.20.0 Sprint 1 | Sathiyabharathi/Saranya | GGO-14255 | API update for nextgen search* | 2 | 2 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7817 | 2024-09-13 | 2024-09-19 | Rajesh | No | Loan Troung | 2024-09-19 | No | No | No | Inprogress
6 | GGO 7.20.0 Sprint 1 | Priya-QA | GGO-14275 | Add Edit Remove User Test Case* - Automation | 2 | 2 | Priya | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGAutomation/pullrequest/7822 | 2024-09-18 | 2024-09-19 | Owen | 1. All Console.Writelines can be removed. Only should be used for debugging purposes. 2. This function should be moved into SeleniumActions. that file is in alphabetical order. 3. We have a function called VerifyCheckBoxInner. that should be used and this one removed. | Owen | 2024-09-19 | No | No | No | Closed
7 | GGO 7.20.0 Sprint 1 | Saranya | PAPI-733 | Refactor Polly Retry code for Portico to have "Try" block inside "Polly.Execute" block | 5 | 5 | Priya | Sathiya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7820 | 2024-09-16 | 2024-09-16 | Rajesh | No | Loan Troung, MikeW | 2024-09-16 | No | No | No | Closed

## GGO 7.20.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.19.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.19.0 Sprint 4 | Sathiyabharathi/Saranya | GGO-14269 | Project builder to pull images from the Azure CDN instead of Content server url if Azure setting is enabled | 2 | 2 |  | Sathiyabharathi/Saranya | No | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7766 | 2024-08-23 | 2024-09-03 | Rajesh |  | Michael Wall | 2024-09-03 | No | No | No | Closed
2 | GGO 7.19.0 Sprint 4 | Priya-QA | https://greatergiving.atlGGO-14270 | GGO 7.19.0 CRT Release & Regression Testing | 3 |  | Priya | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
3 | GGO 7.19.0 Sprint 4 | Priya-QA | PAPI-734 | PAPI 7.14.0 CRT Release & Regression Testing | 1 | 1 | Priya | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
4 | GGO 7.19.0 Sprint 4 | Saranya | GGO-14216 | High - ASP.NET MVC Bad Practices: Model With Required Non-Nullable Property - ProjectDto.cs* | 1 | 1 | Priya |  |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7770 | 2024-08-23 | 2024-08-23 | Rajesh | No | Loan Troung | 2024-08-23 | No |  |  | Closed
5 | GGO 7.19.0 Sprint 4 | Sathiya/Rajesh | GGO-14264 | Duplicate Supporters that are imported in through sales does not trigger check for duplicate* | 3 | 3 | Priya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7780 | 2024-08-29 | 2024-08-30 | Rajesh | No | Michael Wall | 2024-08-30 | No |  |  | Closed
6 | GGO 7.19.0 Sprint 4 | Sathiyabharathi/Saranya | GGO-14255 | API update for nextgen search* | 2 | 1 | Priya | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7817 | [9 empty] | Inprogress
7 | GGO 7.19.0 Sprint 4 | Saranya | GGO-14240 | NextGen API update for supporter card on file status | 2 | 2 | Saranya | Priya |  | SathiyaBharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7765 | 2024-08-23 | 2024-08-23 | Rajesh | No | Loan Troung | 2024-08-23 | No | No | No | Closed
8 | GGO 7.19.0 Sprint 4 | Priya-QA | GGO-14275 | Add Edit Remove User Test Case* - Automation | 3 |  | Priya | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress

## GGO 7.19.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.19.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status
1 | GGO 7.19.0 Sprint 3 | Saranya/Rajesh/Sathiya | GGO-14232 | PRD Issue with Recalculate Name Fields is timing out | 2 | 1 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7758 | 2024-08-20 | 2024-08-20 | Rajesh | NA | Mike W | 2024-08-20 | NVARCHAR(MAX) should not be used with Split. | Prod issue - Fixed | NA | Closed
2 | GGO 7.19.0 Sprint 3 | Sathiyabharathi | GGO-14236 | Convert asp.net core | 5 | 5 | Sathiyabharathi | Priya | No | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7753 | 2024-08-13 | 2024-08-19 | Rajesh | NA | Loan | 2024-08-19 | No | NA | NA | Closed
3 | GGO 7.19.0 Sprint 3 | Saranya | GGO-14225 | Update the left nav menu | 2 | 2 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7746 | 2024-08-07 | 2024-08-07 | Rajesh |  | Mike Horihan | 2024-08-13 |  | Part of Invoicing epic - Completed |  | Closed
4 | GGO 7.19.0 Sprint 3 | Priya-QA | GGO-14253 | CRT Release Support GGO 7.18.2 | 3 |  | Priya | Priya |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
5 | GGO 7.19.0 Sprint 3 | Saranya | GGO-14216 | High - ASP.NET MVC Bad Practices: Model With Required Non-Nullable Property - ProjectDto.cs* | 2 | 1 | Saranya | Priya |  | Rajesh |  | NA | [7 empty] | Macroscope scanning - Rolled oved |  | Closed | Macroscope error should be resoved by our changes.But it takes 3 days. once it is done we have to check whether the issue is resolved or not
6 | GGO 7.19.0 Sprint 3 | Sathiyabharathi | GGO-14262 | Investigation - RSVP Page cannot be edited or deleted; leads to an error* | 2 | 2 | Sathiyabharathi | NA | NA | Rajesh |  | NA | NA | NA | Rajesh | NA | NA | NA | NA | Priority defect - Fixed | NA | Closed | It is an investigation story, we found that some of the RSVP pages in PROD is marked as “IsRsvp = 0” in “ap_WebsiteRegistrationPage” table instead of “IsRsvp=1“.

## GGO 7.19.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.19.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.19.0 Sprint 2 | Sathiyabharathi | GGO-14204 | High & Medium - BDSA-2023-3833 - jQuery.Validation/1.19.5 & BDSA-2021-3651 - jQuery/3.5.1 | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7691 | 2024-07-16 | 2024-07-18 | Rajesh | No | Loan | 2024-07-18 | Query is part of the BundleConfig for Reskin. Is this reference necessary? | Part of macroscope scanning - Completed |  | Closed | Instead of using JQuery reference directly in User control or content pages, we can use Script Manager proxy to define Jquery. So i have removed jquery reference link and used ScriptManagerProxy. In our application some of the pages(ClientView.aspx) we have used script manager proxy. It is used to add scripts and services to content pages and to user controls if the master page or host page already contains a ScriptManager control. We are not used any master pages in PreMfaLanding.aspx page but still this file handling click events so retains Jquery reference link in this file alone. (edited)
2 | GGO 7.19.0 Sprint 2 | Priya-QA | GGO-14233 | Landing page "admissionsChart" and "totalSalesChart" Throwing Console Error* | 1 | 1 | NA | Priya | Yes - Found one issue while testing this bug in Dev env | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Part of Quality of life epic | NA | Closed
3 | GGO 7.19.0 Sprint 2 | Priya-QA | GGO-14247 | Users unable to set/reset GGO password in Chrome & Edge* | 3 | 2 | NA | Priya |  | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Priority defect - Fixed | NA | Closed
4 | GGO 7.19.0 Sprint 2 [STRETCH] | Saranya | GGO-14232 | PRD Issue with Recalculate Name Fields is timing out | 2 | 1 |  | Priya |  | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | Rolled over | NA | Inprogress | Unable to reproduce this issue in lower environments. Team is still finding out the way to fix this issue.
5 | GGO 7.19.0 Sprint 2 [STRETCH] | Sathiyabharathi | GGO-14236 | Convert asp.net core | 5 | 5 |  | NA | [11 empty] | Rolled over |  | Inprogress

## GGO 7.19.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.19.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.19.0 Sprint 1 | Rajesh | GGO-14197 | issue with Template List not appearing on Project Creator | 3 | 3 | Rajesh | N/A | N/A | N/A | N/A | N/A | [7 empty] | Prod issue - Fixed and closed |  | Closed | Rajesh coordianted with Carlos and found the root cause.user deleted the project that is associated with project template
2 | GGO 7.19.0 Sprint 1 [STRETCH] | Sathiyabharathi | GGO-14204 | High & Medium - BDSA-2023-3833 - jQuery.Validation/1.19.5 & BDSA-2021-3651 - jQuery/3.5.1 | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7691 | 2024-07-16 | [6 empty] | Part of macroscope scanning - Rolled over |  | Inprogress
3 | GGO 7.19.0 Sprint 1 | Saranya | GGO-14308 | Update Replace Tokens Task version in GGO-VMSS Release Pipeline | 1 | 1 | Saranya | Priya | No | Sathiyabharathi | No | NA | [7 empty] | Version upgrade - Completed |  | Closed | Version of the task is deprecated in release Pipelines. So we upgraded task version 3 to 6 in GGO_VMSS and PAPI_VMSS pipelines.
4 | GGO 7.19.0 Sprint 1 | Saranya | PAPI-724 | Critical: Insecure Transport: Database - App.config: 5* | 1 | 1 | Saranya | Sathiyabharathi and Priya | No | Sathiyabharathi | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/7692 | 2024-07-16 | 2024-07-16 | Rajesh | No | Loan Troung | 2024-07-17 | No | Part of macroscope scanning - completed |  | Closed
5 | GGO 7.19.0 Sprint 1 [STRETCH] | Sathiyabharathi | GGO-14210 | High - Investigate Projects using Microsoft.AspNetCore* | 3 | [14 empty] | Part of macroscope scanning - completed |  | Inprogress
6 | GGO 7.19.0 Sprint 1 | Priya-QA | GGO-14185 | GGO 7.18.0 CRT Release & Regression Testing | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
7 | GGO 7.19.0 Sprint 1 | Priya-QA | PAPI-721 | PAPI 7.13.0 CRT Release & Regression testing | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
8 | GGO 7.19.0 Sprint 1 | Sathiyabharathi | GGO-14200 | Updated Aspose.Cells license* | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7665 | 2024-07-05 | 2024-07-08 | Rajesh | No Comments | Loan | 2024-07-08 | No Comments |  |  | Closed
9 | GGO 7.19.0 Sprint 1 | Saranya | GGO-13995 | Update AddSalesAndPayments call from OB to handle duplicate calls* | 2 | 2 | Sathiyabharathi | Priya | No | Sathiya | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7669 | 2024-07-04 | 2024-07-09 | Rajesh | No Comments | Loan | 2024-07-09 | No Comments | Part of infrastructure improvement - Completed |  | Closed
10 | GGO 7.19.0 Sprint 1 | Rajesh | GGO-14223 | Transfer Special instruction information to SF on Project creation before equipment order update* | 2 | 2 | Rajesh | Priya | [11 empty] | Salesforce update |  | Closed
11 | GGO 7.19.0 Sprint 1 | Rajesh | GGO-14201 | Throwing Error while uploading the new images when Azure Image setting enabled in DEV environment* | 1 | 1 | Rajesh | Priya | [11 empty] | Part of macroscope scanning - completed |  | Closed
12 | GGO 7.19.0 Sprint 1 | Priya-QA | PAPI-726 | High & Medium - CVE-2024-30105 System.Text.Json 8.0.0 * | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed

## GGO 7.19.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.18.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.18.0 Sprint 4 | Saranya | GGO-13995 | Update AddSalesAndPayments call from OB to handle duplicate calls* | 2 | 2 | Sathiyabharathi | Priya | No | Sathiya | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7669 | 2024-07-04 | 2024-07-09 | Rajesh | No Comments | Loan | 2024-07-09 | No Comments | Stretch story on Infrasturcture epic - Rolled over |  | Closed
2 | GGO 7.18.0 Sprint 4 | Sathiyabharathi | GGO-14200 | Updated Aspose.Cells license* | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7665 | 2024-07-05 | 2024-07-08 | Rajesh | No Comments | Loan | 2024-07-08 | No Comments |  |  | Closed
3 | GGO 7.18.0 Sprint 4 | Saranya/Sathiyabharathi | GGO-14004 | Error when attempting to edit users | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7663 | 2024-07-03 | 2024-07-04 | Rajesh | No Comments | Loan | 2024-07-04 | Replace "" with string.Empty | Part of infrastructure epic - Completed |  | Closed
4 | GGO 7.18.0 Sprint 4 | Sathiyabharathi/Rajesh | GGO-14187 | Analyze impact of .net update | 3 | 3 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Loan |  |  |  |  | Closed | Investingation story
5 | GGO 7.18.0 Sprint 4 | Rajesh | GGO-14193 | console app udpate* | 2 | 2 | Rajesh | Sathiya | No | Sathiya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7658 | 2024-06-28 | 2024-06-29 | Sathiya | No Comments | Loan | 2024-06-29 | No Comments |  |  | Closed
6 | GGO 7.18.0 Sprint 4 | Saranya/Rajesh | GGO-13999 | Quartz Service - Replace hard coded Application Insights key* | 2 | 2
7 | GGO 7.18.0 Sprint 4 | Priya-QA | GGO-13947 | Medium - CVE-2022-30187 - Azure.Storage.Blobs/12.10.0 & 12.15.0 | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Part of macroscope scanning - Completed | NA | Closed
8 | GGO 7.18.0 Sprint 4 | Priya-QA | GGO-13982 | Console errors, blank output when printing shipping labels from Firefox | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Priority defect - Implemented successfully | NA | Closed
9 | GGO 7.18.0 Sprint 4 | Priya-QA | GGO-13993 | Supporter - Handle MaxRequestLength* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
10 | GGO 7.18.0 Sprint 4 | Priya-QA | GGO-14185 | GGO 7.18.0 CRT Release & Regression Testing | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
11 | GGO 7.18.0 Sprint 4 | Rajesh | GGO-14201 | Throwing Error while uploading the new images when Azure Image setting enabled in DEV environment* | 1 | 1 | Rajesh | Priya | [13 empty] | Closed
12 | GGO 7.18.0 Sprint 4 | Priya-QA | PAPI-721 | PAPI 7.13.0 CRT Release & Regression testing | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed

## GGO 7.18.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.18.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.18.0 Sprint 3 | Sathiyabharathi | GGO-14003 | Recalculate Name Fields times out every time | 3 | 3 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7628 | 2024-06-24 | 2024-06-24 | Rajesh | No | Loan Troung | 2024-06-24 | No | Bug fix - Implemented successfully | No | Closed | Mike Wall did the script level changes but the issue occued for the org which is having more supporters we updated the name fields by Batch processing and it worked as expected
2 | GGO 7.18.0 Sprint 3 | Rajesh/Sathiyabharathi | GGO-13655 | Enable CDC for GGO | 3 | 3 | Sathiyabharathi | N/A | N/A | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7629 | 2024-06-18 | 2024-06-24 | Rajesh | No | Loan Troung | 2024-06-24 | Fix typo/misspell privilege. | Rolled over | No | Closed | Completed the implementation and tested in local and Dev environment.verification in TST is pending.it is script changes.Onsite QA confirmation is pending.
3 | GGO 7.18.0 Sprint 3 | Priya-QA | PAPI-716 | PAPI 7.12.0 CRT Release | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
4 | GGO 7.18.0 Sprint 3 | Priya-QA | GGO-14062 | GGO 7.17.0 CRT Release and Regression Testing | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
5 | GGO 7.18.0 Sprint 3 | Priya-QA | GGO-13856 | Medium - Microsoft.IdentityModel.JsonWebTokens:5.5.0 & Microsoft.IdentityModel.JsonWebTokens:6.10.0* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
6 | GGO 7.18.0 Sprint 3 |  | GGO-13998 | Can not permanently delete projects from APAdmin | 2 | 2 |  | Priya | [13 empty] | Closed
7 | GGO 7.18.0 Sprint 3 | Priya-QA | GGO-14169 | MSR Certification test - iOS | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Swipe certification tests for iOS from Self testing portal | NA | Closed
8 | GGO 7.18.0 Sprint 3 | Saranya | PAPI-710 | Remove apConstants.PORTICO_TESTING_TOKEN* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
10 | GGO 7.18.0 Sprint 3 STRETCH | Sathiyabharathi | GGO-13947 | Medium - CVE-2022-30187 - Azure.Storage.Blobs/12.10.0 & 12.15.0* | 2 | 2 | Sathiyabharathi | Priya | No | N/A | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7641 | 2024-06-24 | [6 empty] | Macroscope scanning - Rolled over |  | Inprogress
11 | GGO 7.18.0 Sprint 3 | Saranya | GGO-14004 | Error when attempting to edit users | 2 | 2 |  | Priya | [11 empty] | Part of infrastructure epic - Rolled over |  | Inprogress | It is a production issue. Reproduced in local and it should be fixed

## GGO 7.18.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.18.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.18.0 Sprint 2 | Sathiyabharathi | GGO-13691 | Issue with ClearExpiredTrialUsers | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7599 | 2024-06-04 | 2024-06-05 | Rajesh | No Comments | Loan | 2024-06-05 | No Comments | Implemented successfully |  | Closed
2 | GGO 7.18.0 Sprint 2 | Sathiyabharathi | GGO-13994 | Update Capital letter tagging validation for Bidder and Supporter welcome SMS | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7592 | 2024-05-31 | 2024-06-01 | Rajesh | No Comments | Loan | 2024-06-01 | No Comments | Implemented successfully |  | Closed
3 | GGO 7.18.0 Sprint 2 | Sathiyabharathi | GGO-14037 | MSR Certification test - Manually Keyed Transaction (Purchase/Full Reversal-V1 01 & M1 03) | 5 | 4 | Sathiyabharathi | [12 empty] | This has been added a flag in ApAdmin to toggle the card present setting for GoTime>Storefront - Rolled over |  | Closed | Development has been completed. Client dependency (Portico side test cases required some additional params)
4 | GGO 7.18.0 Sprint 2 | Saranya | PAPI-714 | MSR Certification test - Manually Keyed Transaction (Purchase/Full Reversal-V1 01 & M1 03) | 3 | 2 | Saranya | Priya |  | Sathya | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/7613 | 2024-10-06 | 2024-12-06 | Rajesh |  | Loan Troung |  |  | This has also been rolled over |  | Closed | Development has been completed. Client dependency (Portico side test cases required some additional params)
5 | GGO 7.18.0 Sprint 2 | Saranya | PAPI-712 | High - jquery-ui-1-11-4/1.11.4 | 3 | 3 | Saranya | Priya |  | Rajesh | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/7598 | 2024-04-06 | 2024-04-06 | Rajesh | No Comments | Loan Troung | 2024-04-06 | No Comments | This is a part of macroscope - completed |  | Closed
6 | GGO 7.18.0 Sprint 2 | Priya-QA | PAPI-713 | Bluetooth Swipe Refund Transactions are Processed as Credit Sale* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
7 | GGO 7.18.0 Sprint 2 | Priya-QA | PAPI-716 | PAPI 7.12.0 CRT Release | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Deployement happened at the end of the sprint. Testing is still in progress
8 | GGO 7.18.0 Sprint 2 | Priya-QA | GGO-14062 | GGO 7.17.0 CRT Release and Regression Testing | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Deployement happened at the end of the sprint. Testing is still in progress

## GGO 7.18.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.18.0 Sprint 1 | Sathiyabharathi/Rajesh | GGO-13819 | Migrate Reporting to Quartz | 5 | 5 | Sathiyabharathi |  |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7553 | 2024-05-24 | [8 empty] | Closed | Development has been completed for this story and did local testing need to test in Dev environment is pending it requires client IT team support
2 | GGO 7.18.0 Sprint 1 | Sathiyabharathi | PAPI-711 | Critical - Secret Detected in Source/config/apCalcSolution/cacl | 2 | 2 | Sathiyabharathi |  |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7584 | 2024-05-28 | [8 empty] | Closed
3 | GGO 7.18.0 Sprint 1 | Rajesh | GGO-14039 | Legacy iOS - Login button for some reason is listed as Update* | 1 | 1 | Rajesh | [14 empty] | Closed
4 | GGO 7.18.0 Sprint 1 | Priya-QA | GGO-13985 | GGO 7.16.2 CRT Release & Regression Testing | 2 | 2 | Saranya | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
5 | GGO 7.18.0 Sprint 1 | Saranya | GGO-13954 | AGG-07 Report not pull LY numbers | 3 | [5 empty] | NA | NA | NA | NA | [7 empty] | Closed | Analyzed and found out the rootcause and updated required details in that story's comment section. That info is shared to Customer Service
6 | GGO 7.18.0 Sprint 1 | Priya-QA | GGO-14005 | Wrong Credit Card Method Type Assignment | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Testing is Blocked due to Certificate Issues.
7 | GGO 7.18.0 Sprint 1 | Saranya | GGO-14006 | Shipping label generation not working in CRT | 1 | 1 | NA | NA | NA | NA | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7567 | 2024-05-20 | 2024-05-21 | Rajesh | No | Mike Horihan | 2024-05-21 | it looks like we need to remove a hyphen from zip code before we check the length and truncate | No | No | Closed

## GGO 7.18.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.18.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.17.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.17.0 Sprint 4 | Rajesh | GGO-13981 | Remove Bluetooth Data logging from GoTime.AddCreditCard* | 1 | 1 | Rajesh | Priya | No | Sathiyabharathi | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7521 | [9 empty] | Closed
2 | GGO 7.17.0 Sprint 4 | Sathiyabharathi | GGO-13948 | Value uneditable when splitting a sale | 2 | 2 | Sathiyabharathi | Priya | No | Rajesh | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7516 | 2024-04-30 | 2024-05-01 | Rajesh | NA | Loan | 2024-05-01 | No | No | No | Closed
3 | GGO 7.17.0 Sprint 4 | Saranya | GGO-13939 | Thumbnail images are not scaled proportionately by Quartz Job | 3 | 2 | Saranya | Priya | No | Rajesh | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7527 | 2024-05-03 | 2024-05-07 | Rajesh | NA | Michael Wall | 2024-05-07 | No | No | No | Inprogress | Development completed and marked this one as Impediment. Client IT team has to do some configuration.
4 | GGO 7.17.0 Sprint 4 | Priya-QA | GGO-13985 | GGO 7.16.2 CRT Release & Regression Testing | 3 | 2 | Saranya | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Testing completed. Client IT team has to do some configuration to resolve Shipping label generation.
5 | GGO 7.17.0 Sprint 4 | Rajesh | GGO-13983 | Move GGO Websvcs to its own application | 5 | 3 | [15 empty] | Inprogress | Marked this one as Impediment. Client IT team has to do some configuration.

## GGO 7.17.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.17.0 Sprint 3 | Saranya Namachivayam | GGO-13760 | UPS Oauth Credentials | 3 | 3 | Saranya | Priya | No | Sathiya | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7498 | 2024-04-24 | 2024-04-24 | Rajesh | NO | Michael Wall | 2024-04-26 | No | NA | NA | Closed
2 | GGO 7.17.0 Sprint 3 | Priya-QA | GGO-13836 | API call for testing card readers | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.
3 | GGO 7.17.0 Sprint 3 | Saranya Namachivayam | GGO-13940 | Length Validation for Bidder and Supporter SMS | 2 | 2 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7501 | 2024-04-24 | 2024-04-24 | Rajesh | No | Michael Wall | 2024-04-24 | NA | NA | NA | Closed
4 | GGO 7.17.0 Sprint 3 | Priya-QA | PAPI-708 | Allow CardVerify Response Code 91 and store CardBrandTransactionID | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Mike Wall and we tested it and updated the comments in JIRA.
5 | GGO 7.17.0 Sprint 3 | Priya-QA | PAPI-702 | GGAM & All Client Apps: Test to determine if they are saving Tokens instead of encrypted CCN/PAN | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Mike Wall and we tested it and updated the comments in JIRA.
6 | GGO 7.17.0 Sprint 3 | Rajesh | GGO-13981 | Remove Bluetooth Data logging from GoTime.AddCreditCard* | 1 | 1 | Rajesh | Priya | No | Sathiyabharathi | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7521 | [9 empty] | Closed
7 | GGO 7.17.0 Sprint 3 | Sathiyabharathi | GGO-13948 | Value uneditable when splitting a sale | 2 | 1 | Sathiyabharathi | Priya | No | Rajesh | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7516 | 2024-04-30 | 2024-05-01 | Rajesh | NA | Loan | 2024-05-01 | No | No | No | Inprogress | We offshore tested and provided the comments. And Informed one existing issue. Nathan raised an new issue for the same and also testing is still pending from his side.
8 | GGO 7.17.0 Sprint 3 | Sathiyabharathi | GGO-13773 | create method for running pivotal and sfdc event sync simultaneously | 5 | 4 | Sathiyabharathi | N/A | No | Rajesh | No Comments | N/A | [9 empty] | Inprogress | salesforce team confirmed they can't do any changes

## GGO 7.17.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.17.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.17.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.17.0 Sprint 2 | Saranya Namachivayam | GGO-13877 | Tax rate in view packages cuts off decimal amounts of percentage | 3 | 3 | Saranya | Priya | No | SathiyaBharathi | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7453 | 2024-04-05 | 2024-04-08 | Rajesh | No | Loan Truong | 2024-04-08 | No | No | No | Closed
2 | GGO 7.17.0 Sprint 2 | Sathiyabharathi Paramasivam | GGO-13878 | Issues with convenience fee rounding | 3 | 3 | Sathiyabharathi | Rajesh | No | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7465 | 2024-04-10 | 2024-04-11 | Rajesh | No | Mike Wall | 2024-04-11 | No | No | No | Closed
3 | GGO 7.17.0 Sprint 2 | Saranya Namachivayam | GGO-13879 | Payments shown in GGO as Error actually processed | 3 | 3 | Saranya | Priya | No | Rajesh | No | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7469 | 2024-04-10 | 2024-04-11 | Rajesh | No | Loan Truong | 2024-04-11 | No | No | No | Closed
4 | GGO 7.17.0 Sprint 2 | Rajesh | GGO-13925 | Tax Rate on Create Sale inaccurate | 2 | 2 | Rajesh | Priya | No | SathiyaBharathi | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7466 | 2024-04-10 | 2024-04-10 | Loan | No | Mike Wall | 2024-04-10 | No | No | No | Closed
5 | GGO 7.17.0 Sprint 2 | Rajesh | GGO-13917 | ManageSalesAndPayments Nullable object must have a value | 2 | 2 | Rajesh | Priya | No | SathiyaBharathi | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7454 | 2024-04-05 | 2024-04-05 | Sathiyabharathi | No | Loan Truong | 2024-04-06 | No | No | No | Closed
6 | GGO 7.17.0 Sprint 2 | Priya-QA | PAPI-702 | GGAM & All Client Apps: Test to determine if they are saving Tokens instead of encrypted CCN/PAN | 2 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Scope of the Story is only testing.And this is Fully Developed by Mike Wall and we tested and updated the comments in JIRA.card details need to verified with PAPI database, we don't have required permission for that only onsite QA need to be verified.
7 | GGO 7.17.0 Sprint 2 | Priya-QA | GGO-13834 | Tax Rate on Packages showing as 0 | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.
8 | GGO 7.17.0 Sprint 2 | Priya-QA | GGO-13938 | High - CVE-2024-0056 - System.Data.SqlClient/4.5.1* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.
9 | GGO 7.17.0 Sprint 2 | Priya-QA | GGO-13927 | High - Detector AzureStorage Found Result* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.
10 | GGO 7.17.0 Sprint 2 | Priya-QA | GGO-13857 | (High & Medium) - BDSA-2018-5195 - Newtonsoft.Json/9.0.1 & BDSA-2018-5195 - Newtonsoft.Json/12.0.2 & Newtonsoft.Json:11.0.2* | 1 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.And this is Fully Developed by Loan and we tested it and updated the comments in JIRA.

## GGO 7.17.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## GGO 7.17.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.17.0 Sprint 1 | Sathiyabharathi | GGO-13843 | High - MessagePack:1.7.3.4 ¦ MessagePack for C# and Unity Before Version 1.9.11 and 2.1.90 Has a Vulnerability | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7422 | 2024-03-27 | 2024-03-28 | Prabhu | No | Loan | 2024-03-28 | No | No | No | Closed
2 | GGO 7.17.0 Sprint 1 [Stretch] | Sathiyabharathi | GGO-13844 | create method for running pivotal and sfdc event sync simultaneously* | 3 | 3 | Sathiyabharathi | N/A | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7442 | 2024-04-02 |  | Rajesh | No | [5 empty] | Inprogress | Development has been completed , require salesforce team support to test
3 | GGO 7.17.0 Sprint 1 | Saranya Namachivayam | GGO-13854 | Critical - Insecure Transport: Database - App.config: 5 | 3 | 3 | Saranya | Priya | No | SathiyaBharathi | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7439 | 2024-04-01 | 2024-04-01 | Rajesh | No | Mike Wall | 2024-04-01 | No | No | No | Closed
4 | GGO 7.17.0 Sprint 1 | Saranya Namachivayam / Mike Wall | PAPI-702 | GGAM & All Client Apps: Test to determine if they are saving Tokens instead of encrypted CCN/PAN | 2 | 2 | Saranya | Priya, Saranya | No | Rajesh | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/7437 | 2024-03-30 | 2024-03-30 | Loan Truong | No | Rajesh | 2024-04-03 | No | No | No | Closed | Scope of the Story is only testing. We are doing testing support to onsite resource
5 | GGO 7.17.0 Sprint 1 | Priya-QA | GGO-13816 | GGO 7.16.0 CRT Release & Regression Testing | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
6 | GGO 7.17.0 Sprint 1 | Priya-QA | GGO-13785 | Go Time Card Entry update for old readers | 2 | 2 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Scope of the Story is only testing.(Fully Developed by Loan and we tested and updated the comments in JIRA)

## GGO 7.17.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.17.0 Sprint 1 | GGO-13893 | Saranya | Defect | CancelledDate' from SF always saved as 1969-12-31 in GGO database | Significant | Internal | Closed | Development

## GGO 7.16.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.16.0 Sprint 4 | Saranya Namachivayam | GGO-13815 | When importing Online Registrations & Purchases, Sale/Payment Association Status will be Partial | 5 | 5 | Saranya | Priya | No | SathiyaBharathi | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7370 | 2024-03-09 | 2024-03-08 | Rajesh | No | Mike Wall | 2024-03-12 | No | The bug was fixed successfully | No | Closed
2 | GGO 7.16.0 Sprint 4 | Sathiyabharathi | GGO-13801 | Supporter Details household behavior | 2 | 2 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7366 | 2024-03-08 | 2024-03-08 | Rajesh | No | Loan | 2024-03-08 | No | Implemented as per AC | No | Closed
3 | GGO 7.16.0 Sprint 4 | Sathiyabharathi | GGO-13773 | create method for running pivotal and sfdc event sync simultaneously* | 5 | 5 | [13 empty] | Got some issue with GGOApi user for transfer of data from GGO to SF - Rolled over |  | Inprogress | Development has been completed , require salesforce team support to test
4 | GGO 7.16.0 Sprint 4 | Saranya Namachivayam | GGO-13738 | Coordinate with IT to add Bluetooth hardware column in SF | 1 | 1 | Saranya | Priya | No | SathiyaBharathi | No Comments | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7364 | 2024-03-07 | 2024-03-14 | Rajesh | No | Mike Wall | 2024-03-14 | No | Implemented as per AC | No | Closed
5 | GGO 7.16.0 Sprint 4 | Saranya Namachivayam | GGO-13796 | TST verification for SFDC Enhancements | 3 |  | Saranya | Priya | No | SathiyaBharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7383 | 2024-03-13 |  | Rajesh |  |  |  |  | In Progress - Rolled over |  | Inprogress
6 | GGO 7.16.0 Sprint 4 | Priya-QA | GGO-13816 | GGO 7.16.0 CRT Release & Regression Testing | 3 | 3 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Rolled Over | NA | Inprogress
6 | GGO 7.16.0 Sprint 4 | Priya-QA | GGO-13737 | GGO Storefront handle Mobile Transaction card data for swipe | 3 | 1 | NA | Priya | No | NA | No Comments | NA | NA | NA | NA | NA | NA | NA | NA | Implemented as per AC | NA | Inprogress | This story was developed by Loan and I have tested this and updated my comments

## GGO 7.16.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.16.0 Sprint 4 | GGO-13837 | Saranya | Defect | Package you have chosen is not a multisale package and it is already sold. Getting error while trying to add another sale of this package | Significant | Internal | Closed | Development
2 | GGO 7.16.0 Sprint 4 | GGO-13838 | Saranya | Defect | Supporter Grid display issues in Fundraiser-only projects | Significant | Internal | Closed | Development
3 | GGO 7.16.0 Sprint 4 | GGO-13835 | Loan | Defect | GoTime-Storefront - Web- Getting Error while making the payment through Cash | Significant | Internal | Closed | Development

## GGO 7.16.0 Sprint 3-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.16.0 Sprint 3 | SathiyaBharathi | GGO-13733 | Go time checkin update | 3 | 3 | Sathiyabharathi | Saranya,Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7344 | 2024-02-26 | 2024-02-26 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-02-27 | No Comments | Implemented as per AC, no issues found. |  | Closed
2 | GGO 7.16.0 Sprint 3 | SathiyaBharathi / Saranya Namachivayam | GGO-13699 | Go time checkout update | 5 | 5 | Sathiyabharathi/Saranya | Saranya,Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7345 | 2024-03-01 | 2024-03-01 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-03-01 | No Comments | Implemented as per AC. |  | Closed
3 | GGO 7.16.0 Sprint 3 | Saranya | GGO-13807 | Apply Fees Logic Update | 5 | 5 | Sathiyabharathi | Sathiyabharathi,Priya |  | Sathiyabharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7347 | 2024-02-28 | 2024-02-28 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-02-29 | No Comments | No comments |  | Closed
4 | GGO 7.16.0 Sprint 3 | Saranya/SathiyaBharathi | GGO-13801 | Supporter Details household behavior | 3 | 3 | Sathiyabharathi/Saranya | Saranya,Sathiyabharathi,Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7352 | 2024-03-01 | 2024-03-02 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-03-02 | No Comments | Found a new defect. Still in progress |  | Inprogress
5 | GGO 7.16.0 Sprint 3 | Rajesh | GGO-13744 | Convenience Fee Enabled Setting Persistence across templates and copied projects | 2 | 2 | Rajesh | Priya |  | Sathiyabharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7346 | 2024-02-27 | 2024-02-27 | SathiyaBharathi | No Comments | Loan Truong | 2024-02-28 | No Comments | Implemented as per AC. |  | Closed
6 | GGO 7.16.0 Sprint 3 | Saranya | GGO-13738 | Coordinate with IT to add Bluetooth hardware column in SF* | 3 |  | Saranya | Sathiyabharathi |  | Sathiyabharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7364 | 2024-03-07 |  | Rajesh |  |  |  |  | Still in progress |  | Inprogress | Development is completed. Testing is pending. It requires IT team support
7 | GGO 7.16.0 Sprint 3 | SathiyaBharathi | GGO-13824 | When updating equipment orders, it will only update one card reader field at a time.* | 3 | 3 | Sathiyabharathi | Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7358 | 2024-03-05 | 2024-03-05 | Rajesh | No Comments | Loan Truong/Mike Wall | 2024-03-05 | No Comments | This bug was fixed |  | Closed
8 | GGO 7.16.0 Sprint 3 | Priya-QA | GGO-13703 | Bid-18 Update | 2 | 2 | Saranya | Priya | No Defects | Sathiyabharathi,Rajesh | No | NA | NA | NA | NA | No Comments | NA | NA | NA | No comments | NA | Closed
9 | GGO 7.16.0 Sprint 4 | Rajesh | GGO-13820 | Salesforce Support* | 1 | 1 | Rajesh | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | No comments | N/A | Closed

## GGO 7.16.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.16.0 | Saranya Namachivayam / Rajesh | GGO-13612 | Update Redis Cache Clearing on Release | 5 | 5 |  | SathiyaBharathi,Priya |  | SathiyaBharathi |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/7317 | 2024-02-15 | 2024-02-16 | Rajesh |  | Loan Truong | 2024-02-16 |  | No comments |  | Closed
2 | GGO 7.16.0 | SathiyaBharathi / Saranya Namachivayam | GGO-13703 | Bid-18 Update | 3 | 2 |  | Priya |  | Saranya | [9 empty] | The column header was occupying additional column for the report BID-18, however it’s look like an existing issue. |  | Inprogress
3 | GGO 7.16.0 | Priya-QA | GGO-13696 | Add option to supporter record | 1 | 1 | Sathiyabharathi/Rajesh | Saranya,Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7316 | 2024-02-14 | 2024-02-15 | Rajesh | Move constant variable to common file convenienceFee.cs | Loan Truong | 2024-02-15 | No Comments | Implemented as per AC | No Comments | Closed
4 | GGO 7.16.0 | SathiyaBharathi | GGO-13701 | Charge Batch Update | 5 | 5 | Sathiyabharathi | Saranya,Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7306 | 2024-02-12 | 2024-02-15 | Rajesh |  | Loan Truong | 2024-02-15 | move methods to common place | One Defect Sub-task has been created to update the window height based on AC. It was fixed and the story was completed. | No Comments | Closed
5 | GGO 7.16.0 | SathiyaBharathi/Rajesh | GGO-13795 | Manually added Convenience Fee sales not counted as 'Convenience Fee Applied' | 2 | 2 | Sathiyabharathi/Rajesh | Saranya,Priya | No | Saranya | No Comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7316 | 2024-02-14 | 2024-02-15 | Rajesh | No Comments | Loan Truong | 2024-02-15 | No Comments | No Comments | No Comments | Closed | Parent story-GGO-13702
6 | GGO 7.16.0 | SathiyaBharathi | GGO-13771 | Update label on supporter record* | 2 | 2 | Sathiyabharathi | N/A | N/A | N/A | N/A | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7330 | 2024-02-21 | 2024-02-21 | Rajesh | Move variable declaration to common file convenienceFee.cs | Loan Truong | 2024-02-21 | No Comments | Implemented as per AC | No Comments | Closed
7 | GGO 7.16.0 | Priya- QA | GGO-13702 | Supporter Advanced Search update | 3 | 3 | Sathiyabharathi | Priya | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Implemented as per AC | N/A | Closed | Testing completed in this sprint
8 | GGO 7.16.0 | Priya- QA | GGO-13783 | Go Time Card Entry Interface for new readers | 2 | 2 | Rajesh | Priya | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Implemented as per AC | N/A | Closed | Worked and Tested with the Mobile team to check the new popup doesn't affect any existing flow.

## GGO 7.16.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.16.0 Sprint 3 | GGO-13821 | Saranya | Defect | Manually created negative Conv fee sale is displayed in both Total sales and Conv fee applied and the total due is calculated based on these two values... | Significant | Internal | Closed | Development
2 | GGO 7.16.0 Sprint 3 | GGO-13825 | Sathiya | Defect | Negative convenience amount is calculated in the report Bid- 18 if the supporter has a negative due and covering conv fee is enabled | Significant | Internal | Closed | Development
3 | GGO 7.16.0 Sprint 3 | GGO-13828 | Sathiya | Defect | Total Due Amounts in Checkout VS Manage Sales and Payments don't always match | Significant | Internal | Inprogress | Development

## GGO 7.16.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.16.0 | GGO-13795 | Sathiyabharathi | Defect | Manually added Convenience Fee sales not counted as 'Convenience Fee Applied' | Significant | Internal | Closed | Development
2 | GGO 7.16.0 | /GGO-13804 | Sathiyabharathi | Defect | Charge Batch Grid height not limited to 400px | Minor | Internal | Closed | Development

## GGO 7.16.0 Sprint 1-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.16.0 | Saranya | GGO-13143 | Send Group to OB for bidders | 2 | 2 | Saranya | Priya | No Comments | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7229 | 2024-01-18 | 20-Jan-0202 | Rajesh | No Comments | Mike Wall,Loan | 2024-01-20 | No Comments | No Comments | No Comments | Closed
2 | GGO 7.16.0 | Saranya | GGO-13735 | Update Legacy Go Time Mobile Reader Options image | 3 | 3 | Saranya | Sathiyabharathi and Priya | No Comments | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7279 | 2024-02-02 | 2024-02-02 | Rajesh | No Comments | Mike Wall,Loan | 2024-01-20 | No Comments | No Comments | No Comments | Closed
3 | GGO 7.16.0 | Priya-QA | GGO-13740 | GGO 7.15.0 CRT Release & Regression Testing | 2 | 2 | Priya | Priya | No Defects | Rajesh | No | NA | NA | NA | NA | No Comments | NA | NA | NA | NA | NA | Closed
4 | GGO 7.16.0 | Rajesh | GGO-13770 | AGG-07 Reports missing from PRD | 2 | 2 | Rajesh | Rajesh and Priya | No Comments | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7264 | 2024-01-28 | 2024-01-31 | Mike Wall,Loan | No Comments | NA | NA | NA | No Comments | No Comments | Closed
5 | GGO 7.16.0 | Sathiyabharathi | GGO-13696 | Add option to supporter record | 3 | 3 | Sathiyabharathi | Priya | No Comments | Rajesh | create new file in Library project and move the convenience fee releated changes to that file | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7285 | 2024-02-06 | 2024-02-06 | Rajesh | No Comments | Mike Wall | 2024-02-02 | No Comments | No Comments | No Comments | Inprogress
6 | GGO 7.16.0 | Saranya | GGO-13736 | Hide card reader popup for mobile pilot users | 3 | 3 | Saranya | Priya | No Comments | Rajesh | No | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7273 | 2024-02-01 | 2024-02-02 | Rajesh | No Comments | Mike Wall,Loan | 2024-02-02 | No Comments | No Comments | No Comments | Closed
7 | GGO 7.16.0 | Rajesh | GGO-13774 | Escalation Support | 2 | 2 | Rajesh | Rajesh | NA | Rajesh | No | NA | NA | NA | Rajesh | No Comments | NA | NA | NA | NA | NA | Closed
8 | GGO 7.16.0 | Sathiyabharathi / Saranya | GGO-13702 | Supporter Advanced Search Update* | 3 | 3 | Sathiyabharathi | Saranya and Priya | No Comments | Rajesh | No |  |  |  | Rajesh | No LLBLGen file changes should be made manually. You need to run LLBLGen using powershell tool. If you have problem with license, let me know. | [5 empty] | Inprogress

## GGO 7.16.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.16.0 Sprint 1 | https://greatergiving.atlassian.net/browse/GGO-13775 | Saranya Namachivayam | Defect | GGO code card entry dialogue is still showing behind the new Popup from GGO Mobile | Significant | Internal | Closed | Development
2 | GGO 7.16.0 Sprint 1 | https://greatergiving.atlassian.net/browse/GGO-13780 | Sathiya | Defect | Negative values are getting updated under Total sales when we have deleted the normal sale and convenience sale from the checkout | Significant | Internal | Inprogress | Development

## GGO 7.15.0 Sprint 4-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | GGO 7.15.0 Sprint 4 | Saranya Namachivayam/Sathiyabharathi Paramasivam | GGO-13143 | Send Group to OB for bidders | 3 | 3 | Completed | Rajesh | No comments | Rajesh | No comments | https://greatergiving.visualstudio .com/Greater%20Giving/_git/ GGO/pullrequest/7252 | 25-01-2024 | 25-01-2024 | Rajesh | No Comments | Michael Wall | 25-01-2024 | No Comments | No Comments | No Comments | Closed | Took more time to cover all scenario's, failed with 1 scenario at the end of sprint, so it got carry forwarded to next sprint
2 | Mobile Sprint 4 | Saranya Namachivayam | GGOM-832 | user gets error if users login is shared in multiple orgs | 1 | 1 | Completed | Rajesh | No comments | Rajesh | No comments | https://greatergiving.visualstudio. com/Greater%20Giving/_git/ GGO/pullrequest/7224 | 17-01-2024 | 18-01-2024 | Rajesh | No Comments | Michael Wall | 18-01-2024 | No Comments | No Comments | No Comments | Closed
3 | GGO 7.15.0 Sprint 4 | Sathiyabharathi Paramasivam | GGO-13695 | Add Conv fee flag to backend of supporter | 3 | 3 | Completed | Rajesh | No comments | Rajesh | No comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7231 | 19-01-2024 | 19-01-2024 | Rajesh | No Comments | Loan,Mike Wall,Mike Horihan | 19-01-2024 | why we choose varchar(250) for the Email column | No Comments | No Comments | Closed | Changed [EmailAddress] column datatype and length as([nvarchar] (127) NULL)
4 | GGO 7.15.0 Sprint 4 | Sathiyabharathi Paramasivam | GGO-13756 | CRT Regression Issue-AGG-23X Report loading issue | 2 | 2 | Completed | Rajesh | No comments | Rajesh | No comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7248 | 23-01-2024 | 23-01-2024 | Rajesh | No Comments | Loan | 23-01-2024 | No Comments | No Comments | we frequently faced AsyncPageTime out issue while Running AGG-03 ,AGG-25, AGG-23x reports.PO decided to revert the changes . | Closed | Reverted SQLCLR 7 story changes, we frequently faced AsyncPageTime out issue while Running AGG-03 ,AGG-25, AGG-23x reports.PO decided to revert the changes .
5 | GGO 7.15.0 Sprint 4 | Saranya Namachivayam | GGO-13742 | Project Website Creation error for returning clients* | 2 | 2 | Completed | Rajesh | No comments | Rajesh | No comments |  |  |  | Rajesh | No Comments | MikeH | Migration Script Updated in ChangeLog | No Comments | No Comments | No Comments | Closed
6 | GGO 7.15.0 Sprint 4 | Rajesh | GGO-13752 | Set IsBluetoothPilot Flag in browser cookies for Legacy Mobile App* | 1 | 1 | Completed | Rajesh | No comments | Loan | No comments | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/7216 | 13-01-2024 | 13-01-202 | Loan | No Comments | Loan | 13-01-2024 | No Comments | No Comments | No Comments | Closed
7 | GGO 7.15.0 Sprint 4 | Rajesh | GGO-13753 | Set isBluetoothFlag in Switch Project functionality for Legacy Mobile App | 1 | 1 | Completed | Rajesh | No comments | Loan, MikeW | No |  |  |  | Rajesh | No Comments | MikeW | 18-01-2024 | No Comments | No Comments | No Comments | Closed
| GGO 7.15.0 Sprint 4 | Priya-QA | GGO-13462 | Identify and update the non-data table 4 | 2 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Testing completed on this sprint
9 | GGO 7.15.0 Sprint 4 | Priya-QA | GGO-13694 | Project Builder Updates | 2 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Testing completed on this sprint

## GGO 7.15.0 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | GGO 7.15.0 Sprint 4 | GGO-13758 | Saranya Namachivayam | Defect | Adding new admissions from the existing supporter and Save it- Getting "An Error has occurred" | Significant | Internal | Closed | Development

## Checklist (hidden)
Code Review Comments received from Client for 2.5 Sprint |  | S No | Execution Steps | Status
1 | index.tsx /AugustWeb/Features/ContactMaintenance/Components/index.tsx Search doesn't work on the details page. Please remove the search component from the header. | 1 | Code conflict | FALSE
2 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs If the admin doesn't set up any of the new options, then the system rejects every registration. | 2 | Coding Standard | FALSE
3 | PickEnrollmentPlanView.tsx /ParentWeb/ClientApp/src/pages/Registration/PickEnrollmentPlanView.tsx This should be filtered before this ternary statement so the "No enrollment plans" message could be shown if all plans are at capacity and closed. | 3 | Existing Functionality | FALSE
4 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs Could we add a TermEnrollmentPlanId query parameter and query for it directly instead of pulling all the plans for the term? | 4 | Acceptance Criteria coverage | FALSE
|  | 5 | Code execute | FALSE
|  | 6 | Code Performance | FALSE
|  | 7 | Code cleanup | FALSE
|  | 8 | Understandable code comments | FALSE

## Details
Root Cause category
Enhancements
Existing_Issues
Requirements
QA
Design
Documentation
Development
Project_Management
Environment_Related

## Settings
Refinement
Ready
Being Developed
Peer Review
Verify
Ready for testing
Being Tested
Completed

## ExportData
1 | GGO Web | 46058 | 46072 | GGO 7.21.0 Sprint 4 | SathyaBharathi/Rajesh Kannan | GGO-14325 | Rewrite and Update BID-06 (Invoice) using RDLC Part 1 | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan/Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8075 | 45643 | 45643 | Rajesh |  | Michael Wall | 45643 |  |  |  | Tested in the Dev environment - Informed few issues to the Team.12/17/202410:48 PM. Tested in the TST Env- 12/18/2024 7:20 PM.
2 | GGO Web | 46058 | 46072 | GGO 7.21.0 Sprint 4 | SathyaBharathi/Rajesh Kannan | GGO-14426 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 2 (Sales Only) | Completed | 5 | 5 |  |  | Priya |  | Rajesh Kannan | [11 empty] | Rolling over remaining testing to this story - GGO-14427
3 | GGO Web | 46058 | 46072 | GGO 7.21.0 Sprint 4 | Saranya | GGO-14418 | Modify GGO SFDC Webservice | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8079 | 45639 | 45643 | Rajesh |  | Michael Wall | 45643 |  |  |  | Coordinated with saranya and Tested in Local -12/16/2024 8:56 PM.
4 | GGO Web | 46058 | 46072 | GGO 7.21.0 Sprint 4 | Saranya | GGO-14445 | Project Website - Remove Deprecated Share Functionality | Completed | 2 | 2 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8080 | 45639 | 45642 | Rajesh |  | Loan Troung | 45642 |  |  |  | Tested in the Dev environment - 12/16/2024 8:57 PM. Tested in the TST env. Working well. 12/17/2024 10:47 PM
5 | GGO Web | 46058 | 46072 | GGO 7.21.0 Sprint 4 | Rajesh Kannan | GGO-14419 | Duplicate EventXcode updated when GGO sync with SF | Completed | 3 | 3 |  |  | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8092 | 45653 | 45656 | Rajesh |  | Michael Wall | 45656
6 | GGO Web | 46058 | 46072 | GGO 7.21.0 Sprint 4 | Saranya/Rajesh Kannan | GGO-14375 | Pop-up warning on batch process with unapplied convenience fees | Completed | 3 | 3 |  |  | Priya |  | Rajesh Kannan |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8096 | 45657 | 45657 | Rajesh |  | Michael Wall | 45657 |  |  |  | Tested in the TST env. Working well 1/3/2025 8:13 PM
7 | GGO Web | 46058 | 46072 | GGO 7.21.0 Sprint 4 | Sathiyabharathi/Rajesh Kannan | GGO-14427 | Rewrite and Update BID-06 (Invoice) using RDLC - Part 3 (Sales & Payments) | Being Tested | 5 | 5 |  |  | Priya |  | Rajesh Kannan |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8097 | 45657 | 37621 | Rajesh |  | Michael Wall | 45657 |  |  |  | Tested in the TST env. And it is In Progress 1/3/2025 8:13 PM. Tested in the Dev as well as in TST Env- 8:28 PM 1/6/2025. Testing is still in progress. 1/8/2025 8:10 PM
1 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 2 | Saranya | GGO-12487 | Adjust Admission Functionality - sale details | Completed | 5 | 5 | 23 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8184 | 45687 | 45687 | Rajesh |  | Loan Troung | 45687 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025. Priya - Testing in dev env is in progress 4:48 PM 1/30/2025
2 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 2 | Sathiyabharathi | GGO-14503 | Adjust Admission Functionality - add/remove | Ready for Testing | 5 | 5 |  | Sathiya |  |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8189 | 45691 | 45692 | Rajesh |  | Loan Troung | 45692 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025 Deletion of attendee row if supporter chosen showed the popup confirmation, working on Adjusted amount calculation [1/29/2025] Did developer testing in TST environment no issues found [02/04/2025] Onsite QA testing pending since [02/04/2025]
3 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 2 | RajeshKannan | GGO-14514 | Update remaining admission allocated attendee count in GGO webserivce to OP | Completed | 1 | 1 |  | Rajesh | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8174 | 45681 | 45681 | Rajesh |  | Loan Troung | 45681 |  |  |  | Completed Testing in the TST env. 8:31 PM 1/29/2025
4 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 2 | Sathiyabharathi | GGO-14477 | BID-06 Header Settings Update | Completed | 2 | 2 |  | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8170 | 45680 | 45681 | Rajesh |  | Michael Wall | 45681 |  | This is QA automation which comes under Infrastructure improvement |  | Picked on 01/22/2025.Development in progress 23/01/2025 Deployed in dev and completed developer testing. Priya - Completed Testing in Dev. Working well 5:07 PM 1/24/2025. Completed Testing in TST 5:02 PM 1/27/2025
5 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 2 | RajeshKannan | GGO-14450 | GGO Image Thumbnail Creation error | Ready for Testing | 2 | 2 |  | Rajesh | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8197 | 45692 | 45693 | Rajesh |  | Loan Troung | 45693 |  |  |  | It is completed and given for testing 3 days prior to Sprint end, Offshore QA doesn't got any access to test in TST, only MikeH and Nate got access to test it.
6 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 2 | Priya-QA | GGO-14511 | GoTime SF Tap card generate Null Ref Error | Completed | 2 | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Priya- Did one round of Payment Regression Testing since we dont have access to Tap cards. 5:01 PM 1/27/2025
7 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 2 | Priya-QA | PAPI-794 | Add Tag 9F6E to List of Acceptable Tags in ParseC3XJsonDataToTLV* | Completed | 1` | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Priya- Did one round of Payment Regression Testing since we dont have access to Tap cards. 8:00 PM1/28/2025
1 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14503 | Adjust Admission Functionality - add/remove | Completed | 2 | 2 | 23 | Sathiya | Priya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8189 | 45691 | 45692 | Rajesh |  | Loan Troung | 45692 |  |  |  | Story Analysis and Test Case preparation is on progress 5:07 PM 1/24/2025 Deletion of attendee row if supporter chosen showed the popup confirmation, working on Adjusted amount calculation [1/29/2025] Did developer testing in dev environment no issues found [02/05/2025] Automation is pending[02/19/2025]. Nathan Closed the Automation Ticket
2 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 3 | RajeshKannan | GGO-14450 | GGO Image Thumbnail Creation error | Completed | 2 | 2 | 2 | Rajesh | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8197 | 45692 | 45693 | Rajesh |  | Loan Troung | 45693
3 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 3 | Rajesh/Saranya | GGO-14529 | Invoice Timeout Fix | Completed | 1 | 1 | 7.5 |  | Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8204
4 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 3 | Saranya | GGO-14070 | Rewrite BID-15 to a new report toolset | Peer Review | 5 | 5 | 84.5 |  | Priya | [13 empty] | Test Case Prepartion is done 5:48 PM 2/7/2025. Tested in dev env. 7:30 PM 2/19/2025 Carry forwarded to next sprint : Saranya worked on the RDLC report and own the full task took some time for her to learn and implement
6 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14530 | Image Manager Fix | Completed | 1 | 1 | 25.5 | Rajesh | Priya |  | Priya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8218 | 45695 | 45695 | Rajesh |  | Loan Troung | 45695 |  |  |  | 02/08/2025: This issue was Identitfied by CS and this is not a development or QA miss, this happens because the Javascript [DOM] component was deprecated and the code need to be updated accordingly.
7 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 3 | Sathiyabharathi | GGO-14504 | Adjust Admission Functionality - graph updates | Ready for Testing | 5 | 5 | 60 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8228 | 45700 | 45706 | Rajesh |  | Loan Troung | 45706 | GO PRINT N'Drop Procedure [dbo].[sp_GetAdjustedAdmissionCount]' GO IF OBJECT_ID('[dbo].[sp_GetAdjustedAdmissionCount]') IS NOT NULL DROP PROCEDURE [dbo].[sp_GetAdjustedAdmissionCount]; GO It is not necessary, but we do usually add PRINT statement. |  |  | Tested in the Dev env. 5:09 PM 2/17/2025. Completed testing the TST env. 8:27 PM 2/18/2025 Onsite QA Logged bug on last day of sprint, we fixed it deployed before sprint prep, QA didn't get time to complete it.
8 | GGO Web | 46058 | 46072 | GGO 7.22.0 Sprint 3 | Priya-QA | GGO-14071 | Rewrite BID-19 to a new report toolset | Completed | 1 | 1 | 22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Test Case Prepartion is done 5:48 PM 2/7/2025. Testing in dev env. 8:41 PM 2/13/2025. Completed Testing in the TST env.
1 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Saranya | GGO-14070 | Rewrite BID-15 to a new report toolset | Completed | 2 | 2 | 15.5 | Saranya | Priya | Alignment Issues/ Design Issues | [12 empty] | Test Case Prepartion is done 5:48 PM 2/7/2025. Tested in dev env. 7:30 PM 2/19/2025 Carry forwarded to next sprint : Saranya worked on the RDLC report and own the full task took some time for her to learn and implement. Bug GGO-14564 was created on 20/02/2025. Pull request created on 20/02/2025 and Closed on 21 February 2025 at 03:41
3 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Sathiyabharathi | GGO-14547 | Edit Package Image Display Issue | Completed | 2 | 1 | 9 | Sathiya | Priya | NA |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8265 | 45709 |  | Rajesh | [6 empty] | Peer testing N/A for this bug it's required DB update. Priya: Verified in TST env.8:56 PM 2/24/2025
4 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Sathiyabharathi | GGO-14545 | Move the Azure Storage Settings in to Redis/IIS cache to avoid multiple DB calls | Completed | 2 | 3 | 40.25 | Sathiya | Priya | NA |  |  | http://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8272 | 45714 | 45714 | Rajesh | [6 empty] | [02/25/2025]-Created draft PR. Dev Testing in Progress. Tested in the TST env. Working well 7:47 PM2/27/2025
5 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Loan/Sathiyabharathi | GGO-14510 | High - BDSA-2024-4305 - bootstrap/4.6.2 | Being Tested | 5 | 3 | 75.25 | Sathiya |  | NA | [7 empty] | Loan Troung | 45714 |  |  |  | This story is developed by an onsite developer (Loan). After a Bootstrap version update, we’re facing some UI issues. Offshore developer (Sathiya) is assisting with that. Tested this in the TST env. Raised a bug under this. 5:51 PM 3/5/2025. Nathan Comments: Got some Errors in Automation. So It require automation code updates or app code fix.
6 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Saranya | GGO-14567 | Bypass Verify on 3X Storefront swipe | Completed | 2 | 2 | 34.5 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8281 | 45716 | 45720 | Rajesh |  | Loan Troung | 45721 |  |  |  | We dont have access to test EMV transactions. Did Payment Regression Testing using manual cards. Since Portico is down, we were not able to verify swipe transactions. Portico is UP on last day of sprint, Verified and Completed.
7 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Saranya | PAPI-811 | Bypass Verify on 3X Storefront swipe | Completed | 2 | 2 | 35.75 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8282 | 45716 | 45720 | Rajesh |  | Loan Troung | 45721 |  |  |  | We dont have access to test EMV transactions. Did Payment Regression Testing using manual cards. Since Portico is down, we were not able to verify swipe transactions. Portico is UP on last day of sprint, Verified and Completed.
8 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4-[Stretch] | Saranya | GGO-14535 | OPStats.GetRsvpCount not being cached correctly | Being Developed | 2 | 2 | 31 | [15 empty] | Stretch story taken 1 day before sprint end, so got carry forwarded to next sprint.
8 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14546 | Automation Maintenance | Completed | 1 | 1 | 10 | [15 empty] | Coding is still in progress 8:55 PM 2/24/2025. Completed almost all the files. Execution is in Progress 8:33 PM 3/3/2025 Execution Completed on 3/5/2025.
9 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Priya-QA | PAPI-797 | Ensure Credit Card Last 4 is stored in Payers and Payments tables for 3X tap/dip | Completed | 1 | 1 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only. Testing blocked (since yesterday) by partial Portico outage – cannot generate successful EMV transactions.
10 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14566 | 25 Feb GGO 7.22.0 CRT Release & Regression Testing | Completed | 1 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | CRT Regression Testing is in Progress. 8:31 PM 3/3/2025.Partially blocked by Portico transaction failures in CRT.Completed Remaining scenario from our end
11 | GGO Web | 45709 | 45722 | GGO 7.22.0 Sprint 4 | Priya-QA | GGO-14509 | Critical - Privacy Violation | Completed | 1 | 1 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in TST env. 8:31 PM 3/3/2025
1 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Rajesh | GGO-14535 | OPStats.GetRsvpCount not being cached correctly | Completed | 2 | 2 | 22 | Rajesh | Priya | NIL |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8288 | 45722 | 45723 | Rajesh |  | Michael Wall | 45723 |  |  |  | Completed Testing 3/11/2025 7:40 PM
2 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Rajesh | PAPI-822 | Handle SystemError Response From Portico SOAP Call | Completed | 2 | 2 | 2.25 | Rajesh |  |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8291 | 45723 | 45724 | Rajesh |  | Michael Wall, Loan Troung | 45724
3 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | SathiyaBharathi | GGO-13890 | Rewrite and Update SLS-10 | Completed | 3 | 3 | 45.5 | Sathiya/Rajesh | Priya | NIL | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8300 | 45727 | 45727 | Rajesh |  | Michael Wall | 45727 |  |  |  | Completed Testing in the TST env 8:00 PM 3/12/2025
4 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Saranya | PAPI-816 | Investigate Check-In not storing Card or Payer record for Go-Time Enter Card on EMV TAP when flag Portico_TestingNeverSendToProcessor=true | Completed | 2 | 2 | 14.25 | Saranya | Sathiya |  | Rajesh |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8293 | 45723 | 45726 | Rajesh |  | Michael Wall | 45727 |  |  |  | Completed Testing in the TST env. 3/11/2025 7:40 PM
5 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Rajesh | GGO-14576 | Investigate Card Verify Failure Message | Completed | 2 | 2 | 2.25 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8292 | 45723 | 45724 | Rajesh |  | Michael Wall, Loan Troung | 45724
6 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Saranya | PAPI-809 | HIGH - jQuery/2.0.0 in PapiAdmin | Completed | 2 | 2 | 33.75 | Saranya | Rajesh |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8314 | 45730 | 45730 | Rajesh |  | Michael Wall, Loan Troung | 45730 |  |  |  | Did one round of Payment Regression Testing in the TST env
7 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Rajesh | PAPI-808 | HIGH - CVE-2024-43485 System.Text.Json 8.0.4 | Completed | 2 | 2 | 11.75 | Rajesh | Saranya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8312 | 45729 | 45730 | Rajesh |  | Michael Wall, Loan Troung | 45730 |  |  |  | Did one round of Payment Regression Testing in the TST env
8 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1-[Stretch] | SathiyaBharathi/ Saranya/Rajesh | GGO-14586 | At Least 3 Card Brands Can Have Up to 19 Digit PAN* | Ready For Testing | 5 | 5 | 72 | Saranya/Rajesh | Priya | NIL | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8320 | 45734 | 45735 | Rajesh |  | Michael Wall | 45735 |  |  |  | Development has been completed and partially completed testing in dev environment[03/19/2025]. Did one round of payment Regression for this story in the TST env.
9 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1-[Stretch] | SathiyaBharathi/Rajesh | PAPI-829 | At Least 3 Card Brands Can Have Up to 19 Digit PAN* | Ready For Testing | 2 | 2 | 11.5 | Sathiya/Rajesh | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/8318 | 45734 | 45735 | Rajesh |  | Michael Wall | 45735 |  |  |  | Development has been completed and partially completed testing in dev environment. [03/19/2025]
10 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1-[Stretch] | Rajesh | GGO-14587 | Invoice is not importing or clearing from import area* | Being Developed | 3 |  | 14.5
11 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Priya-QA | GGO-14584 | Resolve new issues introduced to automation | Completed | 1 | 1 | 22 | [15 empty] | Dev completed. Testing in Progress. Facing Mailinator Issues in the TST env. Completed Coding and Execution and Raised PR
12 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Priya-QA/ Sathiyabharathi/ Rajesh | PAPI-820 | Update the Portico Batch delayed interval | Completed | 1 | 1 | 18 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
13 | GGO Web | 45723 | 45736 | GGO 7.23.0 Sprint 1 | Priya-QA/ Rajesh | GGO-14596 | Add 3X SWIPE card payment method type* | Completed | 1 | 1 | 2 | [15 empty] | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
1 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Rajesh | GGO-14594 | Invoice Payment Pages are calculating unapplied convenience fees | Completed | 2 | 2 | 22.5 | Rajesh | Saranya/Priya | NA |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8336 | 45740 | 45740 | Rajesh |  | Loan Troung | 45740 |  |  |  | Email Queues and Quartz job issue blocked us to test this. Verified this story in the TST env. 3/28/2025. But still Quartz job issue exists.
2 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14621 | Email queues in TST repeatedly disabling* | Completed | 1 | 1 | 9 |  |  | NIL | [12 empty] | Email Queues issue got fixed. But still Quartz job issue exists in the TST env.
3 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh | GGO-14626 | Quartz Job not sending email in TST environment* | Completed | 1 | 1 | 2 |  |  | NIL | [12 empty] | Quartz job issue exists in the TST env.
4 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Sathiya | GGO-14589 | New clients don't have Invoicing capabilities | Completed | 2 | 2 | 13 | Sathya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8330 | 45737 | 45737 | Rajesh |  | Mike Horihan | 45738 |  |  |  | Completed Testing in the TST env. 3/25/2025
5 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Sathiya | GGO-14606 | Duplicate EventXCode's are Being Created | Completed | 3 | 3 | 71 | Sathya | Rajesh,Priya | NIL |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8355 | 45743 | 45744 | Rajesh |  | Loan Troung,Michael Wall | 45744 |  |  |  | Testing in progres 7:17 PM 3/28/2025
6 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Saranya | GGO-14587 | Invoice is not importing or clearing from import area | Completed | 2 | 2 | 32 | Saranya | Sathya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8338 | 45740 | 45741 | Rajesh |  | Loan Troung | 45741 |  |  |  | Completed Testing in the TST env. 3/28/2025
7 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Saranya | GGO-14573 | OP to GGO import timeouts | Being Developed | 3 | 5 | 97 | [15 empty] | We have reproduced this issue in DEV and TST environments but are still unable to reproduce it locally. Based on our analysis, GetClosedMatches method seems to be causing the issue. This method is used to find the closest matched names for the given input names and utilizes the Jaro-Winkler algorithm
8 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2 | Priya-QA | GGO-14161 | Rewrite AGG-13 to a new report toolset | Completed | 1 | 1 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/25/2025
9 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14597 | Deprecated "DOMNodeInserted" & "DOMSubtreeModified" event throwing error in multiple places * | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/28/2025
10 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | PAPI-807 | Not all Credit Card Last 4 being added to payments table after hotfix PAPI-795* | Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
11 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14592 | Not all Credit Card Last 4 being added to payments table after hotfix PAPI-795* | Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
12 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | GGO-14473 | Remove equipment banner* | Completed | 1 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed Testing in the TST env. 3/25/2025
13 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Priya-QA | PAPI-839 | Ensure all Portico calls use the client's API Key* | Being Tested | 1 | 1 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test Client API Key's. Offshore QA did payment Regression Testing only.
14 | GGO Web | 45736 | 45750 | GGO 7.23.0 Sprint 2-[Stretch] | Rajesh,Sathiya | GGO-14602 | Handle message for 3X Reader Wi-Fi connection failed - StoreFront* | Completed | 2 | 2 | 1 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8362 | 45748 | 45748 | Rajesh | NA | Loan
1 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Sathiya | GGO-14573 | OP to GGO import timeouts | Completed | 3 | 3 | 42 | Sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8370 | 45754 | 45755 | Rajesh |  | Mike Wall and Loan | 45755
2 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Rajesh | GGO-14633 | Allow Household Share on RSVP Imported Cards | Completed | 3 | 3 | 53 | Rajesh | Priya | Nill
3 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Sathiya | GGO-14457 | Allow Multiple RSVP Import from OP | Completed | 5 | 5 | 83 | sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8380 | 45761 | 45762 | Rajesh |  | Mike Wall and Loan | 45762
4 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3-[Stretch] | Saranya/Sathiya | GGO-14620 | BID-19 Admissions Count issue* | Completed | 3 | 3 | 13.5 | Sathiya | Priya | Nill |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8407 | 45763 | 45763 | Rajesh |  | Mike Wall | 45763
5 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3-[Stretch] | Priya-QA,Rajesh | PAPI-839 | Ensure all Portico calls use the client's API Key* | Completed | 1 | 1 | 13.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We dont have access to test EMV transactions. Offshore QA did payment Regression Testing only.
6 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Priya-QA | GGO-14617 | HIGH & MEDIUM-Serilog.Sinks.File:4.0.0 | Completed | 1 | 1 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed 'testing in the TST env. 11:19 PM 4/7/2025
7 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Priya-QA,Rajesh | PAPI-842 | Fix issue where Payer Records CreditCardStatus are being set to Invalid | Completed | 2 | 2 | 17.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rajesh - Supported to analyze the root cause. Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario
8 | GGO Web | 45750 | 45764 | GGO 7.23.0 Sprint 3 | Saranya | PAPI-840 | Remove the use of StringHashTable | Peer Review | 8 | 5 | 90.5 | Sathiya | Priya | Nill | [12 empty] | Priya- Did Payment Regression Testing along with the void transaction from OP and Refund scenario. The story was left in Peer Review upon completion, per the client's request to hold it and maintain this branch separately from the CERT branch. Dependency on Onsite QA now
1 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Saranya | PAPI-840 | Remove the use of StringHashTable | Completed | 3 | 3 | 23.5
2 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Rajesh, Saranya | GGO-14644 | Remove Hash table in PAPI - GGO need to pass Bluetooth Swipe data on StoreFront scenario* | Completed | 1 | 1 | 14.5 | [15 empty] | Completed One round of Payment Regression
3 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Rajesh | GGO-14614 | HIGH - Microsoft.AspNetCore.Http.Connections.Client:1.0.0 | Completed | 2 | 2 | 19.5 | Rajesh | Sathish,Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8431 | 45770 | 45770 | Rajesh |  | Loan Troung | 45770 |  |  |  | Completed One round of Standard Regression
4 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Sathya | GGO-14613 | HIGH - Cross-Site Scripting: DOM - MaintenanceNotification.js: 22 & 25 | Completed | 2 | 2 | 34.5 | Sathiya | Rajesh,Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8434 | 45771 | 45775 | Rajesh |  | Michael Wall, Loan Troung | 45775
5 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4[Stretch] | Sathya | GGO-14658 | CRITICAL - CVE-2021-43569 - starkbank-ecdsa/1.3.1* | Completed | 1 | 1 | 14 | Sathiya | Rajesh,Priya |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8436 | 45772 | 45775 | Rajesh |  | Michael Wall | 45775 |  |  |  | Development has been completed and tested in local and Dev enviroment[28-April-2025] Completed One round of Standard Regression
6 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Sathiya, Rajesh | GGO-13722 | High - Weak Encryption: Insecure Mode of Operation - Cryptography.cs: 56 | Peer review | 1 | 0.5 | 12.5 | Sathiya | Rajesh |  |  |  | NA
7 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Saranya | GGO-14615 | HIGH - Microsoft.Bcl.Async:1.0.168 | Completed | 2 | 2 | 10.5 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8427 | 45769 | 45769 | Rajesh |  | Loan Troung | 45769 |  |  |  | Completed One round of Standard Regression
8 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Saranya | GGO-13723 | High - Weak Encryption: Insecure Mode of Operation - SymmetricAlgorithmProvider.cs: 35 | Peer review | 1 | 0.5 | 22 | [5 empty] | NA
9 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4[Stretch] | MikeW, Rajesh, Saranya | GGO-14651 | Pass New IsFallback Swipe Flag from GoTime to PAPI | Completed | 2 | 2 | 36 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8440 | 45775 | 45775 | Rajesh |  | Michael Wall | 45775
10 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | MikeW, Rajesh, Saranya | PAPI-846 | EMV Fallback Requires <EMVChipCondition> Tag along with Swipe Data* | Completed | 3 | 3 | 48 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8441 | 45775 | 45775 | Rajesh |  | Michael Wall | 45775
11 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Priya-QA | GGO-14649 | 22 APR GGO 7.23.0 CRT Release & Regression Testing | Completed | 5 | 5 | 35.5 | [15 empty] | CRT Regression Testing in Progress
12 | GGO Web | 45764 | 45778 | GGO 7.23.0 Sprint 4 | Priya-QA | PAPI-851 | 22 APR PAPI 7.18.0 CRT Release & Regression Testing | Completed | 3 | 3 | 22 | [15 empty] | CRT Regression Testing in Progress
1 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-13722 | High - Weak Encryption: Insecure Mode of Operation - Cryptography.cs: 56 | Completed | 1 | 1 | 15 | Sathiya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8458 | 45779 | 45779 | Rajesh |  | Michael Wall | 45780 |  |  |  | Verified in the TST env.5 May 2025 at 08:36
2 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-13723 | High - Weak Encryption: Insecure Mode of Operation - SymmetricAlgorithmProvider.cs: 35 | Completed | 1 | 1 | 34.5 | Sathiya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8457 | 45779 | 45783 | Rajesh |  | Michael Wall, Loan Troung | 45784 |  |  |  | Tested in the TST env 7 May 2025 at 09:20
3 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Sathiya | GGO-14618 | MEDIUM - BDSA-2024-4605 - System.IdentityModel.Tokens.Jwt/5.5.0 | Completed | 2 | 2 | 10.25 | Sathiya | Rajesh |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8474 | 45784 | 45785 | Rajesh |  | Michael Wall | 45785 |  |  |  | Tested in the Dev env 8:09 PM 5/7/2025
4 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Rajesh/Saranya | PAPI-841 | Fix ValidateAndGetPorticoToken calls to handle when Token or CardBrandTransactionId exists | Completed | 2 | 2 | 18 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8477 | 45785 | 45786 | Rajesh |  | Michael Wall | 45786 |  |  |  | Did one round of Payment Regression Testing for this story in the TST env.9 May 2025 at 09:19
5 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Saranya | GGO-14601 | Project UI accepting Invalid Email address results in error on GGO to SF sync | Completed | 2 | 2 | 35 | Saranya | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8463 | 45782 | 45783 | Rajesh |  | Michael Wall | 45783 |  |  |  | Test Cycle executed Successfully in the TST env.7 May 2025 at 07:30
6 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Saranya | GGO-14652 | Enable Online Bidding - Blocked when users mistakenly generate Display Board | Completed | 5 | 5 | 49.5 | Saranya | Rajesh |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8476 | 45785 | 45787 | Rajesh |  | Michael Wall | 45789 |  |  |  | Tested in the TST env 13 May 2025 at 09:16
7 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1[Stretch] | Rajesh | GGO-14678 | Unable to Export Sales* | Completed | 2 | 2 | 19 | Rajesh | Sathiya,Priya |  |  |  | NA | NA | NA | NA |  | NA | NA
8 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 | 0 | 50.5 | [15 empty] | Issue not reproduceable in Dev and TST.Need to check query execution CRT
9 | GGO Web | 45779 | 45792 | GGO 7.24.0 Sprint 1 | Rajesh/ Sathiya | GGO-14656 | Nav Bar Update | Being Developed | 3 | 0 | 64.5 | [15 empty] | Reskin-V2 is a complete overhaul of the existing Master Page, focusing on delivering a fully responsive design. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness.
1 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 |  | 27.5 | [15 empty] | Issue not reproduceable in Dev and TST.Need to check query execution CRT The work around has been provided and ticket has been put on hold for now as it only impacts only one client/org and is of low priority
2 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Rajesh/ Sathiya | GGO-14656 | Nav Bar Update | Completed | 5 | 5 | 107 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8525 | 45805 | 45805 | Rajesh |  | Michael Wall | 45805 |  |  |  | Testing this in the Dev. In Progress 4:32 PM 5/27/2025
3 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Saranya | GGO-14679 | Sales Grid and Details Update for old Convenience Fee assets | Completed | 3 | 3 | 19 | Saranya | Rajesh |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8496 | 45793 | 45797 | Rajesh |  | Michael Wall | 45797 |  |  |  | Verified in the TST env successfully. 20 May 2025 at 05:52
4 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Saranya | GGO-9991 | "Purchaser Company Name" column causes error when the "Export" link is selected | Completed | 2 | 2 | 11.5 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8502 | 45796 | 45797 | Rajesh |  | Michael Wall | 45796 |  |  |  | Verified this in the TST env. 21 May 2025 at 09:23
5 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Rajesh | GGO-14708 | Remove Pivotal WebApi Project from GGO Repo - Unused project and it is using .Net Core 6 (deprecated version)* | Completed | 2 | 2 | 33 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8498 | 45794 | 45796 | Saranya |  | Michael Wall | 45797 |  |  |  | Offshore QA Verified this in the TST env. 21 May 2025 at 09:23
6 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Mike Wall/Rajesh/Saranya | GGO-14701 | Update Implementation of Flag to Disable Card Types in select Organizations | Completed | 2 | 2 | 23.75 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8508 | 45798 | 45798 | Rajesh |  | Michael Wall | 45798 |  |  |  | Verified in the TST env. 22 May 2025 at 08:01
7 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Mike Wall/Rajesh/Saranya | PAPI-858 | Update Flag to Disable Amex in select Organizations With Pre-Token Check* | Completed | 2 | 2 | 38 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/8518 | 45799 | 45800 | Rajesh |  | Mike H | 45800 |  |  |  | Verified in the TST env. 22 May 2025 at 08:01
8 | GGO Web | 45793 | 45806 | GGO 7.24.0 Sprint 2 | Rajesh/Saranya | GGO-14684 | Implement Pendo for GGO | Completed | 5 | 5 | 41.75 | Rajesh | Priya |  | Saranyas |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8523 | 45804 | 45806 | Rajesh | 1. Let's add the following to the account metadata Environment: pendoEnvironment, 2. PendoUserID should be prefixed with PendoEnvironment so that UserID is unique across all environments 3. Dev and local should not fall under the same environment label | Mike H | 45806 |  |  |  | Testing this in the Dev. In Progress 4:32 PM 5/27/2025
1 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Rajesh | GGO-14721 | GoTime - NextGen API Update - Changing to a new project doesn't persist on next login if user changed their home organization | Completed | 1 | 1 | [6 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8562 | 45818 | 45819 |  |  | Mike Horihan | 45819 |  |  |  | Completed
2 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Saranya | GGO-14682 | Reskin update for the User profile | Being Developed | 5 | 86 |  | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8576 | 45820 | 45820 | Rajesh |  | Michael Wall | 45820 |  |  |  | Raised bug under this story in the TST env.
3 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | SathiyaBharathi | GGO-14657 | Reskin for the TopBar | Completed | 3 | 3 | 74 | Sathiya | Priya | UI issues | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8531 | 45807 | 45818 | Rajesh |  | Michael Wall | 45818 |  |  |  | Testing completed in the TST env.
4 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Saranya | GGO-14724 | Implement OneTrust | Being Developed | 5 | [17 empty] | We do not have access to OneTrust Privay Policy Center and discussions are still ongoing on the client side. So Client has been moved this stroy to the backlog
5 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Rajesh | GGO-14683 | Reskin update for the Project Home | Being Developed | 5 | 18.5 | [16 empty] | Reskin-V2 is a complete overhaul of the existing Master Page. The new layout seamlessly integrates Telerik controls, Bootstrap, and Kendo UI CSS, ensuring an optimized, modern, and adaptive user experience across all devices. As part of this redesign, we need to explore which Telerik control is best suited for the requested layout to achieve the desired functionality and responsiveness. Its taking more time to complete this since UI design work is new to the development team and it is bit challenging too
6 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Priya-QA | GGO-14722 | Stop checking expiration dates | Completed | 1 | 1 | 3 | [15 empty] | Did one round of Payment Regression Testing in the TST env
7 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Priya-QA | https://greatergiving.atlassian.net/browse/PAPI-864 | Stop checking expiration dates | Completed | 1 | 1 | [16 empty] | Did one round of Payment Regression Testing in the TST env
8 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | SathiyaBharathi | GGO-14744 | UI Issues | Completed | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8564 | 45818 | 45818 | Rajesh |  | Michael Wall | 45818 |  |  |  | Testing completed in the TST env.
9 | GGO Web | 45806 | 45820 | GGO 7.24.0 Sprint 3 | Rajesh | GGO-14748 | Update Hamburger Menu matching figma only with 3 lines, remove border | Completed | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8569 | 45819 | 45819 | Rajesh |  | Mike Horihan | 45819 |  |  |  | Testing completed in the TST env.
1 | GGO Web | 45820 | 45834 | GGO 7.24.0 Sprint 4 | Saranya | GGO-14682 | Reskin update for the User profile | Completed | 5 | 5 |  | Priya | Priya | NA |  |  | NA | [9 empty] | Tested in the Dev and TST env. Few issues found. Testing completed in the TST env.
2 | GGO Web | 45820 | 45834 | GGO 7.24.0 Sprint 4 | Rajesh/Sathiya/Saranya | GGO-14683 | Reskin update for the Project Home | Completed | 8 | 8 |  | Saranya/Sathiya/Rajesh | Priya | NA | Rajesh |  | http://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8598 | 45832 | 45833 | Rajesh |  | Michael Wall | 45833 |  |  |  | Testing completed in the TST env
3 | GGO Web | 45820 | 45834 | GGO 7.24.0 Sprint 4 | Saranya/Sathiya | GGO-14763 | UI Issues | Completed |  |  |  | Saranya/Priya | Sathiya/Priya | NA | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8581 | 45822 | 45822 | Rajesh |  | Mike Horihan | 45822 |  |  |  | Tested in the TST env directly.Still one issues exists 5:25 PM 6/16/2025 Testing completed in the TST env
4 | GGO Web | 45820 | 45834 | GGO 7.24.0 Sprint 4 | Priya-QA | GGO-14765 | GGO 7.24.0 CRT Release & Regression Testing | Completed | 3 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in the CRT env
5 | GGO Web | 45820 | 45834 | GGO 7.24.0 Sprint 4 | Priya-QA | PAPI-866 | PAPI 7.19.0 CRT Release & Regression Testing | Completed | 3 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in the CRT env
6 | GGO Web | 45820 | 45834 | GGO 7.24.0 Sprint 4 | Priya-QA | https://greatergiving.atlassian.net/browse/GGO-14732 | Update MFA physical address & other old addresses | Completed | 1 | 1 |  | NA | NA | NA |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed in the TST env
1 | GGO Web | 45834 | 45848 | GGO 7.25.0 Sprint 1 | Saranya | GGO-14799 | API update for next gen section times | Completed | 2 | 2 |  | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8619 | 45841 | 45841 | Rajesh |  | Michael Wall | 45841 |  |  |  | 3 July 2025 at 09:11 Verified in the TST env.Working fine
2 | GGO Web | 45834 | 45848 | GGO 7.25.0 Sprint 1 | Sathiya | GGO-14699 | GGO Reskin - Update for the Project Home for Total sales grid | Completed | 3 | 3 |  | Sathiya | Saranya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8606 | 45838 | 45839 | Rajesh |  | Michael Wall | 45839 |  |  |  | 3 July 2025 at 08:03 Verified in the TST env.
3 | GGO Web | 45834 | 45848 | GGO 7.25.0 Sprint 1 | Saranya | GGO-14700 | GGO Reskin - Update for the Project Home for the Total Payments grid | Completed | 3 | 3 |  | Saranya | Sathya |  | Sathiya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8612 | 45839 | 45840 | Rajesh |  | Michael Wall | 45840 |  |  |  | 3 July 2025 at 08:06 Verified in the TST env.
4 | GGO Web | 45834 | 45848 | GGO 7.25.0 Sprint 1 | Rajesh/Sathya/Saranya | GGO-14687 | GGO Reskin - Implement the View Supporter page | Being Developed | 5
5 | GGO Web | 45834 | 45848 | GGO 7.25.0 Sprint 1 | Rajesh | https://greatergiving.atlassian.net/browse/GGO-14798 | Go Time Script Update | Completed | 2 | 2
1 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Rajesh/Sathya/Saranya | GGO-14687 | GGO Reskin - Implement the View Supporter page | Completed | 3 | 3 |  | 45849 | 45852 |  | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8649 | 45854 | 45854 | Rajesh |  | Michael Wall | 45854
2 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Rajesh/Sathya/Saranya | GGO-14802 | GGO Reskin - Implement the View Supporter common controls | Being Developed | 5 |  |  | 45852 | 45861 |  | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8677 | 45861 | 45861 | Rajesh |  | Michael Wall | 45861
3 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Rajesh | GGO-14724 | Implement OneTrust | Being Developed | 5 |  |  | 45852 | 45862 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8667 | 45859 | 45859 | Rajesh |  | Michael Wall | 45860
4 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Rajesh/Sathya/Saranya | GGO-14688 | GGO Reskin - Implement the Edit Supporter details page - Top Section | Being Developed | 3
5 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14831 | MacroScope - High - Microsoft.Owin.Security.OpenIdConnect:4.2.2 | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14835 | MacroScope - High - BDSA-2024-7402 - jQuery.UI.Combined/1.12.1 | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14832 | MacroScope - High - CVE-2021-24112 - System.Drawing.Common | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14829 | MacroScope - High - Manual HTML Sanitization | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | GGO Web | 45848 | 45862 | GGO 7.25.0 Sprint 2 | Priya-QA | GGO-14837 | MacroScope - High - DomPurify.js Unsanitized HTML | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | GGO Web | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14802 | GGO Reskin - Implement the View Supporter common controls | Completed | 3 | 3 |  | 45852 | 45866 |  | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8677 | 45861 | 45861 | Rajesh |  | Michael Wall | 45861
2 | GGO Web | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Rajesh | GGO-14724 | Implement OneTrust | Completed | 2 | 2 |  | 45852 | 45866 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8667 | 45859 | 45859 | Rajesh |  | Michael Wall | 45860
3 | GGO Web | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14840 | Pop-up Dialogs in Supporters page | Completed | 5 | 5 |  | 45863 | [6 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8706 | 45874 | 45874 | Rajesh |  | Michael Wall | 45874
4 | GGO Web | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14855 | when saved search is selected no new search can be done | Completed |  |  |  | 45862 | 45866 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8691 | 45863 | 45863 | Rajesh |  | Michael Wall | 45863
5 | GGO Web | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14851 | Filter pages - Sales & Payments (with Payments on) and Supporters | Being Developed | 5
6 | GGO Web | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Rajesh/Sathya/Saranya | GGO-14712 | View Supporter Filter and Sales & Payments (with Sales on) page | Being Developed | 5
7 | GGO Web | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Rajesh | GGO-14794 | GGO Reskin - Implement the View Catalog page | Completed | 3 | 3 | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8687 | 45863 | 45870 |  |  | Rajesh | 45870
8 | GGO Web | 45862 | 45876 | GGO 7.25.0 Sprint 3 | Priya-QA | GGO-14900 | Update Manage Columns in Catalog Grid | Completed | 1 | 1 |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Rajesh/Sathya/Saranya | GGO-14851 | Filter pages - Sales & Payments (with Payments on) and Supporters | Completed | 5 | 5 | 52.25 | 45881 | 45884 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8742 | 45884 | 45884 | Rajesh |  | Michael Wall | 45884
2 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Rajesh/Sathya/Saranya | GGO-14712 | View Supporter Filter and Sales & Payments (with Sales on) page | Completed | 5 | 5 | 54.75 | 45876 | 45880 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8725 | 45880 | 45882 | Rajesh |  | Michael Wall | 45882
3 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Rajesh/Saranya | GGO-14863 | OneTrust Privacy Center in profile* | Being Developed | 3 |  | 37.75 | 45887
4 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Praveen/Sathiya | GGO-14858 | Retain the overall design of the application* | Ready for testing | 3 |  | 21 | 45888 | 45889 | Praveen/Sathiya | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8756 | 45889 | 45889 | Prabhu |  | Michael Wall | 45889
5 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14954 | Filter Not Reset When Sales Is Disabled | Completed | NA | NA | 9.5 | 45882 | 45882 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8738 | 45882 | 45883 | Rajesh |  | Michael Wall | 45883
6 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14961 | Supporter Records Not Filtering Correctly When "Has Payment" is Toggled On | Completed | NA | NA | 1 | 45882 | 45882 | [5 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8738 | 45882 | 45883 | Rajesh |  | Michael Wall | 45883
7 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14691 | View Packages page | Completed | 1 | 1 | 2.25 | NA | NA
8 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14689 | View Items page | Completed | 1 | 1 | 10 | NA | NA | [5 empty] | NA | NA | NA | NA |  | NA | NA
9 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14962 | Old Icon Displayed for "Type" in View Packages Page | Completed | NA | NA | 1 | NA | NA | [5 empty] | NA | NA | NA | NA |  | NA | NA
10 | GGO Web | 45876 | 45890 | GGO 7.25.0 Sprint 4 | Priya-QA | GGO-14927 | Macroscope - High - Microsoft.VSSDK.BuildTools:15.8.3252 | Completed | 1 | 1 | 2 |  | NA | [5 empty] | NA | NA | NA | NA |  | NA | NA
1 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Praveen / Sathiya | GGO-14858 | Retain the overall design of the application | Completed | 2 | 2 |  | 45888 | 45889 | Praveen/Sathiya | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8756 | 45889 | 45889 | Prabhu |  | Michael Wall | 45889
2 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Rajesh/Saranya/Sathya | GGO-14863 | OneTrust Privacy Center in profile | Completed | 2 | 2 |  |  |  | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8779 | 45896 | 45896 | Sathiya |  | Michael Wall | 45896
3 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Sathya / Praveen | GGO-14852 | View Supporter Page Filter - Bidders & Attendees | Completed | 3 | 3 |  |  |  | Sathya/Praveen | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8786 | 45897 | 45899 | Rajesh |  | Mccarty, Joseph | 45899
4 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Rajesh / Saranya / Sathya | GGO-14853 | View Supporter Page Filter - Sponsors and Donors | Completed | 3 | 3 |  |  |  | Sathya/Praveen | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8786 | 45897 | 45899 | Rajesh |  | Mccarty, Joseph | 45899
5 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 - [Stretch] | Saranya | GGO-14854 | View Supporter Page Filter - Staff and Fundraisers* | Being Developed | 3 | 2 |  |  |  | Saranya | Priya |  | Sathya
6 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 - [Stretch] | Rajesh | GGO-14971 | Pendo Content Security Policy * | Completed | 2 | 2 |  |  |  | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8799 | 45903 | NA | NA |  | Michael Wall | 45903
7 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Rajesh | GGO-14972 | org mail templates error | Completed | NA | NA | [8 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8773 | NA | NA | NA |  | Michael Wall | 45896
8 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Rajesh | GGO-14970 | jquery update issues | Completed | NA | NA |  | 45902 | 45902 | [10 empty] | Michael Wall | 45895
9 | GGO Web | 45890 | 45904 | GGO 8.0.0 Sprint 1 | Sathya / Praveen | GGO-14875 | Create Item Page | Being Developed | 5
1 | GGO Web | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Saranya | GGO-14854 | View Supporter Page Filter - Staff and Fundraisers* | Completed | 1 | 2 |  | 45905 |  | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8810 | 45905 | 45905 | Rajesh |  | Mike Horihan | 45906
2 | GGO Web | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Sathya / Praveen | GGO-14875 | Create Item Page | Completed | 5 | 5 |  | 45905 |  | Sathiya | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8744 | 45916 | 45916 | Rajesh |  | Mike Wall | 45916
3 | GGO Web | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Saranya | GGO-14979 | View Supporter Page Filter - Supporters | Completed | 3 | 3 |  | 45905 |  | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8822 | 45910 | 45910 | Rajesh |  | Mike Horihan | 45911
4 | GGO Web | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Rajesh/Saranya | GGO-14980 | View Supporter Page Filter - Save Search | Being Developed | 3 |  |  | 45905
5 | GGO Web | 45904 | 45918 | GGO 8.0.0 Sprint 2 | Rajesh | GGO-14984 | Content Security Policy Update for Pendo * | Completed | 2 | 2 |  | 45905 |  | Rajesh | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8820 | 45909 | 45909 |  |  | Mike Horihan | 45909
1 | GGO Web | 45918 | 45932 | GGO 8.0.0 Sprint 3 | Sathiya/Rajesh/Saranya | GGO-14980 | View Supporter Page Filter - Save Search | Completed | 3 |  | 106 | 45905 | 45929 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8872 | 45925 | 45927 | Rajesh |  | Mike Horihan | 45927
2 | GGO Web | 45918 | 45932 | GGO 8.0.0 Sprint 3 | Saranya | GGO-14822 | Update Email validation on Project Builder | Completed | 2 |  | 18 | 45922 | 45924 | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8860 | 45923 | 45924 | Rajesh |  | Mccarty, Joseph | 45924
3 | GGO Web | 45918 | 45932 | GGO 8.0.0 Sprint 3 | Praveen | GGO-15013 | Remove G logo from side nav | Completed | 2 |  | 8 | 45919 |  | Praveen | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8853 | 45922 | 45922 | Rajesh |  | Michael Wall | 45922
4 | GGO Web | 45918 | 45932 | GGO 8.0.0 Sprint 3 | Rajesh | GGO-14661 | Reskin Feature flag for new clients | Completed | 3 |  | 9 | 45919 |  | Rajesh | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8850 | 45922 | 45923 | Rajesh |  | Michael Wall | 45923
5 | GGO Web | 45918 | 45932 | GGO 8.0.0 Sprint 3 | Saranya/Praveen | GGO-15010 | Reskin Project Home Update Issue | Completed | 2 |  | 13 | 45923 | 45926 | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8873 | 45925 | 45925 | Rajesh |  | Michael Wall | 45926
6 | GGO Web | 45918 | 45932 | GGO 8.0.0 Sprint 3 | Rajesh/Sathiya | GGO-14960 | Macroscope - High - Prevent URL Redirector Abuse on Logout | Completed | 2 |  | 17.5 | 45923 |  | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8876 | 45926 | 45926 | Rajesh |  | Mike Horihan | 45926
7 | GGO Web | 45918 | 45932 | GGO 8.0.0 Sprint 3 | Saranya/Rajesh | PAPI-882 | Ensure All Card Types can be added as CoF when amount = $0.01 is set by Mobile Team | Completed | 1 |  | 11 | 45929 |  | Saranya | Rajesh |  | Rajesh |  | NA | NA | NA | NA |  | NA | NA
8 | GGO Web | 45918 | 45932 | GGO 8.0.0 Sprint 3 | Praveen/Sathiya | GGO-15015 | Create Item - Update the Rich Text editor* | Being Developed | 2 |  | 5 | 45929
1 | GGO Web | 45933 | 45946 | GGO 8.0.0 Sprint 4 | Praveen/Sathiya | GGO-15015 | Create Item - Update the Rich Text editor | Completed | 2 |  | 32 | 45933 |  | Sathiya | Priya |  | Praveen |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8918 | 45941 | 45941 | Rajesh |  | Mike Horihon | 45943
2 | GGO Web | 45933 | 45946 | GGO 8.0.0 Sprint 4 | Saranya | GGO-14966 | item package updates | Completed | 2 |  | 13 | 45933 |  | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8902 | 45936 | 45937 | Rajesh |  | Mike Horihon | 45937
3 | GGO Web | 45933 | 45946 | GGO 8.0.0 Sprint 4 | Praveen/Sathiya | GGO-14877 | Create Item - Image Control (Multi-image chooser) | Completed | 5 |  | 36 | 45933 |  | Sathiya | Priya |  | Praveen |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8922 | 45944 | 45945 | Rajesh |  | Mike Horihon | 45945
4 | GGO Web | 45933 | 45946 | GGO 8.0.0 Sprint 4 | Rajesh | GGO-15037 | Error clicking cancel in Email Verify and Password Reset | Completed | 1 |  | 3 | 45933 |  | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8893 | 45933 | 45933 | NA |  | Mike Horihon | 45933
5 | GGO Web | 45933 | 45946 | GGO 8.0.0 Sprint 4 | Sathiya/Rajesh | GGO-15029 | Gotime-Error | Completed | 3 |  | 43.5 | 45933 |  | NA | NA |  | NA |  | NA | NA | NA | NA |  | NA | NA
1 | GGO Web | 45946 | 45960 | GGO 8.1.0 Sprint 1 | Saranya | GGO-15042 | Re-introduce Group by Household to Supporter Grid* | Completed | 3 |  |  | 45947 |  | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8944 | 45953 | 45953 | Rajesh |  | Mike Horihan | 45953
2 | GGO Web | 45946 | 45960 | GGO 8.1.0 Sprint 1 | Rajesh | GG0-15041 | Household Investigation | Completed | 3 |  | 9 | 45947 | [6 empty] | NA | NA | NA | NA |  | NA | NA
3 | GGO Web | 45946 | 45960 | GGO 8.1.0 Sprint 1 | Rajesh | GGO-15020 | OneTrust implementation issue | Completed | 3 |  |  | 45947 |  | Rajesh | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8954 | 45955 | 45955 | Rajesh |  | Mike Horihan | 45957
4 | GGO Web | 45946 | 45960 | GGO 8.1.0 Sprint 1 | Sathiya | GGO-14901 | Manage Images - Popup | Completed | 5 |  |  | 45947
1 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Sathiya/Saranya | GGO-14901 | Manage Images - Popup | Completed | 5 |  | 52 | 45961 | 45971 | Sathiya | Priya |  | Saranya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8963 | 45958 | 45968 | Rajesh |  | Mike Horihan | 45968
2 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Rajesh | GGO-10698 | Item solicitor doesn't import when added during Import Online Item Donation process | Completed | 3 |  | 22 | 45961 | 45965 | Rajesh | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8980 | 45965 | 45965 | Saranya |  | Mike Horihan | 45965
3 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Rajesh | GGO-15054 | Supporters - Filters - Retain Radio buttons value in Saved Search | Completed | 3 |  | 19 | 45961 | 45961 | Rajesh | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8971 | 45961 | 45961 | Sathya |  | Mike Horihan | 45961
4 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Sathya | GGO-15060 | View Items page for Non-Admin User | Completed | 3 |  | 16 | 45967 | 45971 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8990 | 45968 | 45968 | Rajesh |  | Mike Horihan | 45969
5 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Saranya | GGO-15055 | View Items - Actions - Copy Items from other Projects | Completed | 3 |  | 29 | 45964 | 45967 | Saranya | Priya |  | Sathya |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/8987 | 45967 | 45967 | Rajesh |  | Mike Horihan | 45968
6 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Rajesh/Saranya/Sathya | GGO-14931 | View Items Advanced Search* | Being Tested | 5 |  | 40 | 45967 | 45974 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9004 | 45973 | 45974 | Rajesh |  | Mike Horihan | 45974
7 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Rajesh/Saranya/Sathya | GGO-15066 | Equipment Needed banner is missing after the GGO UI refresh released to Production | Completed | 2 |  | 4 | 45972 | 45974 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8998 | 45972 | 45972 | Rajesh |  | Mike Horihan | 45972
8 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Rajesh/Saranya/Sathya | GGO-15070 | View Supporters no cards on file search filter is not working | Completed | 2 |  | 10 | 45972 | 45974 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9002 | 45972 | 45972 | Rajesh |  | Mike Horihan | 45972
9 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Rajesh/Saranya/Sathya | GGO-15073 | Activate OB Link isn't on the New GGO Home Page | Completed | 2 |  | 13.5 | 45972 | 45974 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9000 | 45972 | 45973 | Rajesh |  | Mike Horihan | 45973
10 | GGO Web | 45960 | 45974 | GGO 8.1.0 Sprint 2 | Sathiya/Saranya | GGO-15069 | UI Issues | Completed |  |  | 6.5 | 45968 | 45968 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/8994 | 45969 | 45969 | Rajesh |  | Mike Horihan | 45969
1 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Rajesh | GGO-14931 | View Items Advanced Search | Completed | 2 |  | 14 | 45967 | 45974 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9004 | 45973 | 45974 | Rajesh |  | Mike Horihan | 45974
2 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Rajesh | GGO-15075 | Supporter and Item Search advanced syntax | Completed | 1 |  | 24 | 45974 | 45974 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9008 | 45974 | 45975 | Rajesh |  | Mike Horihan | 45975
3 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Sathya | GGO-15065 | Cancel Button Hidden in Popups on Package Page Across All Environments - UI Issues | Completed | 2 |  | 42.5 | 45975 | 45979 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9017 | 45979 | 45979 | Rajesh |  | Mike Horihan | 45979
4 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Sathya | GGO-15058 | Login Page Update - Expiring Privacy Policy Message v2 | Completed | 3 |  | 23 | 45979 | 45981 | Sathya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9031 | 45980 | 45982 | Rajesh |  | Mike Horihan | 45982 | the whole div should be removed, right? Are we also hiding the B2C Batch Migration setting? this div is the end div that was surrounding the B2C Batch Migration, right?
5 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Rajesh | GGO-15067 | Nav Bar - Maintain consistent behavior throughout the application | Completed | 3 |  | 13 | 45975 | 45978 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9019 | 45978 | 45979 | Rajesh |  | Mike Horihan | 45979
6 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Saranya | GGO-14933 | View Packages Advanced Search | Completed | 5 |  | 26 | 45978 | 45980 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9028 | 45979 | 45979 | Rajesh |  | Mike Horihan | 45980
7 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Saranya / Rajesh | PAPI-891 | GoTime Check-in with EMV is missing PAPI Payment record for CardVerify | Completed | 3 |  | 6 | 45978 | 45979 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/PAPI/pullrequest/9029 | 45980 | 45980 | Rajesh |  | Mike Horihan | 45980
8 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Saranya | GGO-15081 | Create Items - Update Hyperlink Manager pop-up* | Completed | 2 |  | 34 | 45981 | 45987 | Saranya | Priya |  | Sathya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9040 | 45986 | 45986 | Rajesh |  | Mike Horihan | 45986
9 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Saranya | GGO-15082 | Rename popup UI shrinks and require multiple clicks in Global Search to apply changes | Completed | NA |  | 6 | 45981 | 45981 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9038 | 45981 | 45981 | Rajesh |  | Mike Horihan | 45982
10 | GGO Web | 45974 | 45988 | GGO 8.1.0 Sprint 3 | Rajesh | GGO-15089 | RSVP Import Delays / Slowness* | Completed | 2 |  | 6 |  |  | Rajesh | Priya |  | 0 |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9050 | 45987 | 45987 | Rajesh |  | Mike Horihan | 45987
1 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Rajesh | GGO-14932 | Pop-up Dialogs in View Packages page | Completed | 1 |  | 12 | 45987 | 45987 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9053 | 45987 | 45987 | Rajesh |  | Mike Horihan | 45987
2 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Sathiya | GGO-15091 | Image Manager Missing in New UI for Edit Package Image while creating New Items | Completed | 1 |  | 18 | 45988 | 45988 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9052 | 45987 | 45988 | Rajesh |  | Mike Horihan | 45988
3 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15085 | package search update | Completed | 3 |  | 28 | 45988 | 45993 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9068 | 45994 | 45994 | Rajesh |  | Mike Horihan | 45994
4 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Rajesh | GGO-15095 | Nuget Package updates | Completed | 3 |  | 10 | 45988 |  | Rajesh | Priya |  | Priya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9087 | 45997 | 45997 | Rajesh |  | Mike Horihan | 45997
5 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Sathiya | GGO-14876 | Create/Edit Package Page | Completed | 8 |  | 85.25 | 45989 | 46000 | Sathya | Priya |  | Saranya/Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9084 | 45996 | 46000 | Rajesh |  | Mike Horihan | 46000
6 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15071 | Image Manager - Folder Rename Issue | Completed | 3 |  | 40 | 45992 |  | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9086 | 45996 | 45996 | Rajesh |  | Mccarty, Joseph | 45997
7 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Rajesh | GGO-15072 | Project Home Update - Non OB Clients | Completed | 2 |  | 8 | 45988 |  | Rajesh | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9063 | 45993 | 45993 | Rajesh |  | Mike Horihan | 45993
8 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15106 | All radio buttons appear selected by default on the Edit Invoice and GoTime Settings page | Completed | NA |  | 2 | 45995 | 45995 | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9078 | 45995 | 45995 | Rajesh |  | Mike Horihan | 45995
9 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Rajesh/Saranya | GGO-15110 | Edit Package - Change Type and UI issue | Completed | NA |  | 15.5 | 46000 | 46000 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9095 | 46001 | 46001 | Rajesh |  | Mike Horihan | 46001
10 | GGO Web | 45988 | 46002 | GGO 8.1.0 Sprint 4 | Saranya | GGO-15068 | Print or Email Invoices/Receipts - Add a loading Pop-up* | Being Tested | 1 |  | 4 | 46000 | 46000 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9094 | 46001 | 46001 | Rajesh |  | Mike Horihan | 46001
1 | GGO Web | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15068 | Print or Email Invoices/Receipts - Add a loading Pop-up | Completed | 1 |  | 4 | 46000 | 46000 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9094 | 46001 | 46001 | Rajesh |  | Mike Horihan | 46001
2 | GGO Web | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15124 | Item Name field allows more than 127 characters, causing error on save in the Create Item Page | Completed | 2 |  | 1 | 46007 | 46007 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9109 | 46007 | 46007 | Rajesh |  | Mike Horihan | 46007
3 | GGO Web | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Rajesh | GGO-15052 | API Update for Next Gen - Supporter Search | Completed | 3 |  | 31 | 46003 | 46041 | Rajesh | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9105 | 46006 | 46007 | Rajesh |  | Mike Horihan | 46007
4 | GGO Web | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15086 | no negative search for sales and payments | Completed | 5 |  | 53 | 46003 | 46041 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9126 | 46011 | 46011 | Rajesh |  | Mike Horihan | 46011
5 | GGO Web | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-14956 | Online Bidding settings page - Section 1 | Completed | 5 |  | 82 | 46006 | 46022 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9136 | 46017 | 46023 | Rajesh |  | Mccarty, Joseph | 46023
5 | GGO Web | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-14919 | Online Bidding settings page - Section 2 | Completed | 5 |  | 44 | 46007 | 46022 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9136 | 46017 | 46023 | Rajesh |  | Mccarty, Joseph | 46023
6 | GGO Web | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-14957 | Online Bidding settings page - Section 3 | Completed | 5 |  | 37 | 46008 | 46022 | Sathiya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9136 | 46017 | 46023 | Rajesh |  | Mccarty, Joseph | 46023
7 | GGO Web | 46003 | 46030 | GGO 8.2.0 Sprint 1 | Rajesh | GGO-15094 | Fallback plan for OB changes | Completed | 1 |  | 6 | NA | NA | NA | Priya |  | NA |  | NA | NA | NA | NA |  | NA | NA
8 | GGO Web | 46003 | 46030 | GGO 8.2.0 Sprint 1 | Rajesh/Saranya | GGO-15080 | API update for Next Gen - supporter badges | Completed | 3 |  | 7 | 46013 | 46014 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9140 | 46021 | 46022 | Rajesh |  | Mccarty, Joseph | 46022
9 | GGO Web | 46002 | 46030 | GGO 8.2.0 Sprint 1 | Saranya | GGO-15117 | View Package for for Non-Admin User* | Completed | 2 |  | 18 | 45993 | 46027 | Saranya | Priya |  | Rajesh |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9149 | 46027 | 46028 | Rajesh |  | Mike Horihan | 46028
10 | GGO Web | 46003 | 46030 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-15132 | Online Bidding Settings - Edit or Change Phase* | Completed | 2 |  | 12.5 | 46022 | 46024 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9146 | 46024 | 46025 | Rajesh |  | Mike Horihan | 46027
11 | GGO Web | 46003 | 46030 | GGO 8.2.0 Sprint 1 | Sathiya | GGO-15111 | Revise Create/Edit Package design* | Completed | 3 |  | 22 | 46029 | 46029 | Sathiya | Priya |  | Saranya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9150 | 46029 | 46029 | Rajesh |  | Mike Horihan | 46029
12 | GGO Web | 46003 | 46030 | GGO 8.2.0 Sprint 1 | Sathiya/Saranya | GGO-15112 | Update the grids - Supporter, Items and Packages pages* | Completed | 2 |  | 29 | 46028 | 46029 | Saranya | Priya |  | Sathiya |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9151 | 46029 | 46030 | Rajesh |  | Mike Horihan | 46030
1 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Saranya | GGO-15123 | package item search | Completed | 1 | 1 | 14 | 46035 | 46031 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9159 | 46031 | 46031 | Rajesh |  | Mike Horihan | 46032
2 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Rajesh | GGO-14843 | GGO is Creating Duplicate Event Codes | Completed | 5 | 5 | 28 | 46035 | 46041 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9183 | 46039 | NA | NA |  | Mike Horihan | 46043
3 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Sathiya | GGO-15125 | View Items - Reposition the buttons | Completed | 1 | 1 | 16.5 | 46031 | 46031 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9158 | 46031 | 46032 | Rajesh |  | Mike Horihan | 46032
4 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Saranya | GGO-15126 | Create/Edit Item - Update the options within Image Description, Restriction and Images | Completed | 1 | 1 | 9 | 46031 | 46031 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9167 | 46034 | 46035 | Rajesh |  | Mike Horihan | 46035
5 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Saranya | GGO-15127 | View Items/Packages - Remove Merge option | Completed | 1 | 1 | 13 | 46031 | 46031 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9167 | 46034 | 46035 | Rajesh |  | Mike Horihan | 46035 | the exclamation point is not necessary
6 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Rajesh | GGO-15079 | Do not allow OB Donation package as a featured package | Completed | 3 | 3 | 25 | 46038 | 46041 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9191 | 46043 | 46043 | Rajesh |  | Mike Horihan | 46043
7 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Saranya | GGO-15128 | Image File Size not getting set | Completed | 2 | 2 | 16 | 46034 | 46035 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9172 | 46035 | 46036 | Rajesh |  | Mike Horihan | 46036
8 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Rajesh | GGO-15104 | Guides & Analytics toggle won't save | Completed | 2 | 2 | 2 | 46031 | 46031 |  | NA |  |  |  | NA | NA | NA | NA |  | NA | NA
9 | GGO Web | 46030 | 46044 | GGO 8.2.0 Sprint 3 | Sathiya/Saranya/Rajesh | GGO-15135 | Jscrambler for GGO & GGAM & GO Time | Peer review | 3 | 3 | 30.5 | 46041 | 46043 | Done | Priya |  |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9201 | 46043 | 46044 | Rajesh |  | Mike Horihan
1 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Sathiya/Saranya/Rajesh | GGO-15135 | Jscrambler for GGO & GGAM & GO Time | Completed | 3 | 3 | 16 | 46044 | 46044 | Done | Priya | No Defects |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9201 | 46043 | 46044 | Rajesh |  | Mike Horihan | 46045
2 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Rajesh | GGO-15138 | Online Bidding Settings Embed Video Settings | Completed | 1 | 1 | 2 | 46045 | 46045 | Done | Priya | No Defects |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9209 | 46045 | 46045 |  |  | Mike Horihan | 46045
3 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Sathiya | GGO-15137 | Implement ReCaptcha in Supporter | Completed | 2 | 2 | 35.5 | 46045 | 46050 | Done | Priya | No Defects |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9211 | 46050 | 46050 | Rajesh |  | Mike Horihan | 46050
4 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Saranya/Rajesh | GGO-15108 | Equipment Express Update | Completed | 1 | 1 | 15 | 46045 | 46045 | Done | Priya | No Defects | Rajesh | Method repeated multiple times. Move to common service and call it. | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9213 | 46045 | 46046 | Rajesh |  | Mccarty Joseph | 46046
5 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Rajesh | GGO-13585 | Update to fix LLBLgen generated code | Completed | 1 | 1 | 12 | 46045 | 46051 | Done | Priya | No Defects |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9229 | 46050 | 46051 | Rajesh |  | Mike Horihan | 46051
6 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Saranya/Rajesh | GGO-15109 | Upgrade the Telerik to its latest version | Completed | 5 | 5 | 17 | 46051 |  | Done | Priya | No Defects
7 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Saranya | GGO-15142 | API Update for Next Gen - Checkout part 1 | Completed | 1 | 1 | 10 | 46050 | 46050 | Done | Priya | No Defects |  |  | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9235 | 46051 | 46051 | Rajesh |  | Mike Horihan | 46052
8 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Rajesh | PAPI-883 | Upgrade the Polly NuGet Package | Completed | 2 | 2 | 2 | 46052 | 46053 | Done | Priya | No Defects |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/PAPI/pullrequest/9242 | 46053 | 46053 | Rajesh |  | Mike Horihan | 46053
9 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 [Stretch] | Saranya | GGO-15084 | Report Timestamps in UTC | Completed | 2 | 2 | 10 | 46057 | 46058 | Done | Priya | No Defects
10 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 [Stretch] | Rajesh | GGO-15143 | Update the Apigee domain for Azure B2C OIDC endpoints. | Completed | 1 | 1 | 1 | 46057 | 46058 | Done | Priya | No Defects
11 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 [Stretch] | Sathiya | GGO-15103 | Optout.aspx.cs Exception | Verfiy | 2 | 1 | 10.5 | 46058 | 46058 | Done |  |  |  |  | https://dev.azure.com/greatergiving/Greater%20Giving/_git/GGO/pullrequest/9260 | 46058
12 | GGO Web | 46044 | 46058 | GGO 8.2.0 Sprint 4 | Sathiya/Rajesh | GGO-14628 | Print Invoice/Receipts page - Timeout when Omit Sales and payment option selected with both Before and After date options | Being Developed | 3 |  | 64.5 | 46045 | [6 empty] | https://greatergiving.visualstudio.com/Greater%20Giving/_git/GGO/pullrequest/9220 | 46049 | NA | NA |  | Mike Horihan