## Dashboard
Current Sprint | MCS 26 Sprint 9 | Current Sprint Sheet | MCS 26 Sprint 9-Status | Sprint Start Date | 2026-05-08 | Sprint End Date | 2026-05-21 | Application Name | MCS Wave | Users | kalaivani.vijaya@relevantz.com;sathishkumar.velusamy@relevantz.com;srinivasu.ponnaganti@relevantz.com;jayapriya.suresh@relevantz.com | Teams Name(GP-HSS_MCS Product) | 19:3b0279a924ab4f35985570b471228dd7@thread.v2
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story points introduced/removed | Stretch Completed | Accomplishments | Remarks | Retro Points (Internal & External) | Data sanity Audit Status | AuditDate | Backlog Health
NA | MCS 24 Sprint 17 | 2024-08-16 | 2024-08-29 | 3 | 3 | Nil | 0 | 1.Change Cafe Enterprise application export image format to JPG 2. UserName Length issue in the MCS Tool fixed | Onboarding Sprint - Worked on access related items. Hariharan and BoobalaKrishnan has only got the access. Dinesh has not got access to the Client Tools. | Internal: External:
NA | MCS 24 Sprint 18 | 2024-08-30 | 2024-09-12 | 19 | 13 | 45689 and 45690 tasks has been moved to the next sprint (6SP) | 0 | 1. Meal Pattern Flexibility. 2. SFTP sent to orders method. | Dinesh has not still got the access to the code repo hence no points picked by him. | Internal: External:
NA | MCS 24 Sprint 19 | 2024-09-13 | 2024-09-26 | 12 | 12 | New ACs were added for #45900 - 1SP | 0 | 1. New ACs for Meal Pattern Flexibility. 2. MCS - FR - Add "Test Email" button to SMTP settings 3. 2 user defect were closed. | #45900(New ACs) is Moved to Sprint Stretch. #45444 is moved to Sprint Stretch | Internal: External:
NA | MCS 24 Sprint 20 | 2024-09-27 | 2024-10-10 | 18 | 18 | 6 (Assigned from Sprint Strech) Carry forwarded to next sprint | 0 | 1. Report Layout Overrides. 2. Total Sugar Vaidation across application | #45539 - Product Expiration Report. #45908 - MCS - ED - Inventory On Hand report. Pulled from the sprint strech, will move to sprint 20 | Internal: External: Relevanz team for quickly becoming comfortable in the codebase and the quality work we did for this sprint
NA | MCS 24 Sprint 21 | 2024-10-11 | 2024-10-24 | 11 | 11 | 3 (Assigned from Sprint Strech) | 0 | 1. Report Layout Override - Group by. 2. Product Expiration Report. 3. Inventory On-hand Report | #46255 - Pulled from the sprint strech, will move to sprint 22 | Internal: External:Relevantz team members contributions & ramp up going well
NA | MCS 24 - Sprint 22 | 2024-10-25 | 2024-11-07 | 11 | 11 | Nil | 0 | 1. FOH/BOH Integration calculation issues 2. Cafeteria Filter Dashboard Refresh. 3. Balance Recolination Discripency | Completed as planned. This Sprint Involved tasks with More analysis. | External : Good Team Work
NA | MCS 24 Sprint 23 | 2024-11-08 | 2024-11-21 | 13 | 7 |  | 0 | 1. Layout Override for Student Rooster Report 2. Newton Dashboard loading faster 3. Permissions for Employee and Special Adult key in Newton POS 4. Leftover calculations fixed in Edison report | Internal CRC - 0 External CRC - 2 QA Defects - 1 Escaped Defects - 1 | Internal: External:
NA | MCS 24 Sprint 24 | 2024-11-22 | 2024-12-10 | 25 (9 +16) | 12 | 1+8+8 | 0 | 1. POS - Function Keys Enable or Disable. 2. Production Escalation - Breakfast POS Hotfix. | 1. POV is delayed due to unavailabilty of PO- Josh. 2. Since only one QA was available for this sprint, stories for this sprint was backloged in testing. (Milan - Client QA is on Vacation) 3. Introduced new stories in the last few of days of sprint closure (client) Internal CRC - 0 External CRC - 4 QA Defects - 0 Escaped Defects - 0 | Internal: External: Relevanz team for quickly becoming comfortable in the codebase and the quality work we did for this sprint
NA | MCS 24 Sprint 25 | 2024-12-11 | 2025-01-02 | 30 (25+5) | 12 | 5 | 0 | 1. Completed the Production Escalation Task for Item Importers. 2.Completed Grouping and Sorting for Layout Overrides in Student Roster and Student Barcode Roster Report. 3. Price Contract Import UI part was completed. 4. Oauth2.0 R&D was completed successfully. 5. Analysis for POS Optimization. | FYI SRX25080 - was introduced as a new production escalation task from Josh. Requested to Prioritize and release it as a HotFix. Client was out for last week hence PR approval and confirmation for any blockers were on-hold. Since Client QA(Milan) was on leave for the entire month. Only 1 QA - Andrews was available for testing. He was Involved in testing Client DEV stories as well. Internal CRC - 0 External CRC - 4 QA Defects - 2 Escaped Defects - 0 | Internal: External: Relevantz team was very productive during holidays.
NA | MCS 25 Sprint 1 | 2025-01-03 | 2025-01-16 | 22 (17 +5) | 9 | 5 | 0 | 1.Completed the role importers. 2.Completed the GSDN Item importer. | OAuth integration has dependency on SMTP approval from Relevantz for dev testing to be done. Import proce contracts - UI has been completed after initial POV approval and working on backend for the same Optiomazation of cafeteria permission - Need to combine the cafeteria category based user role permissions into the fetch query while login Internal CRC - 0 External CRC - 4 QA Defects - 0 Escaped Defects - 0 | Internal: Andrews for handling testing effort on his plate External: Relevantz team provided Good dev support this sprint
NA | MCS 25 Sprint 2 | 2025-01-17 | 2025-01-30 | 9 | 9 | 5 | 0 | 1. Optimized Cafeteria Cache Permissions: Improved efficiency and security of the cafeteria system by optimizing cache permissions, ensuring smoother operations. 2. Implemented OAuth2.0: Successfully integrated OAuth2.0 for secure and seamless authentication, which was demonstrated effectively, showcasing our system's enhanced security measures. 3. Developed Import Price Contracts: Completed development changes for the implementation of import price contracts, paving the way for streamlined contract management. A Proof of Value (POV) has been scheduled to demonstrate the impact and effectiveness of these changes. | Not able to close the stories within the sprint as planned since we have less bandwidth in testing New AC's were introduced at mid of the sprint that caused delay in executing the stories.(#45301 and #46563) Internal CRC - 1 External CRC - 2 QA Defects - 0 Escaped Defects - 0 | Internal: Onboarded wave team successfully. Completed business KT sessions for all applications in MCS. External: Appreciation received from client team(Andrea, Rudy, Milan and Patrick) for Hari for Oauth implemention.
NA | MCS 25 Sprint 3 | 2025-01-31 | 2025-02-13 | 26 | 23 | 4 | 0 | 1. Bootstrap Migration Research: Completed the research and documented the findings. Identified the affected pages from this migration and created stories to fix the layout issues to complete the migration. 2. New ACs for Oauth2.0 Integration: New ACs for the Oauth2.0 Integration for the FRANKLIN application is completed. 3. New AC Developed Import Price Contracts: Completed development changes for the implementation of import price contracts, paving the way for streamlined contract management. 4. New Field for Item Importer: New field "Generate Recipe" for item importer has added. 5. Wave Team completed the analysis on SQLite Migration. | Two Storieds #45301 and #46563 has its testign effort of 3SP carry forwarded to next sprint. #47119 and #21529 was was picked from the Sprint Stretch. Internal CRC - 0 External CRC - 1 QA Defects - 1 Escaped Defects - 0 | Internal: Overall Team Collabration was good. External: Patrick mentioned in the retro that wave Team Ramp-up was good
NA | MCS 25 Sprint 4 | 2025-02-14 | 2025-02-27 | 34 | 29 | 2 | 0 | 1. Bootstrap Migration: Completed the implementations of the bootstrap changes for the following pages. Home, Application Pages (8 sub modules) 2. New ACs for Oauth2.0 Integration: New ACs for the Oauth2.0 Integration for the FRANKLIN application is completed. 3.Named Site Filter Defect: Script fix for the defect named side filter is completed. 4. New Field for Item Importer: New field "Generate Recipe" for item importer has been completed. which was demonstrated successfully. 5. Wave Team completed the SQLite Task as planned for this sprint. 6.Accessability Fix: Identified the places where we need to fix WCAG2.2 issues on MSA Web using Wave and AC Lite plugin | Story #47120 has its testing pending so carry forwarded to next sprint. Story #46563 has its testing pending so carry forwarded to next sprint. Internal CRC - 1 External CRC - 1 QA Defects - 0 Escaped Defects - 1 | Internal: Overall Team Collabration was good. Sprint went well as we were able to complete assigned tasks. External: Clients mentioned Sprint went well as we were able to complete assigned tasks.
NA | MCS 25 Sprint 5 | 2025-02-28 | 2025-03-13 | 38 | 35 | 5 | 0 | 1. Bootstrap Migration: Completed the implementations of the bootstrap changes for the following pages. Home, Application Pages (8 sub modules) 2.New Item Importing to price contract: New item adding to price contract has been completed. which was demonstrated successfully. 3. New Field for Item Importer: New field "Generate Recipe" for item importer has been completed. which was demonstrated successfully. 4. Wave Team completed the SQLite Task as planned for this sprint. | "Story #47120 has its testing pending so carry forwarded to next sprint. Story #46563 has its testing pending so carry forwarded to next sprint. Hari had a laptop replacement which took 3 days and had to setup the entire environment from the scratch. Internal CRC - 1 External CRC - 5 QA Defects - 0 Escaped Defects - 1 | Internal: Overall Team Collabration was good. Sprint went well as we were able to complete assigned tasks. External: Clients mentioned Sprint went well as we were able to complete assigned tasks.
NA | MCS 25 Sprint 6 | 2025-03-14 | 2025-03-27 | 54 | 40 | 3 | 0 | 1. Wave Team completed the Unit testing in xUnit (unit testing frameworks) for the Admin colsole and MCS Application Server and Started to analyze and create the Approach Document for the Newtom POS 2. Boostrap Migration changes completed for Admin Pages. 3. Price Contracts Import Implementation is completed. 4. Oauth 2.0 Integration for SMTP in POS is completed. | Internal CRC - 1 External CRC - 1 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good. Transition for Shriveni and Rajesh was smooth. External: Testing team has to sync-up with DEV for task inputs. Patrick Mentioned Wave Team shows good Progress. Andrea Mentioned Bootstrap Migration by Krish is going excellent
NA | MCS 25 Sprint 7 | 2025-03-28 | 2025-04-10 | 36 | 31 | 8 | 0 | 1. Wave Team completed the Development for Admin console and MCS Application server for Sqlite Migration. 2. Boostrap Migration changes completed for - Admin - Audit Logs and WCAG related changes have been done. 3. Production Defect for Production Bulk editor is fixed. | Internal CRC - 0 External CRC - 1 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: Patrick Mentioned Overall Relevantz team shows good progress.
NA | MCS 25 Sprint 8 | 2025-04-11 | 2025-04-24 | 12 | 25 | 34 | 0 | 1. Wave Team Started Newton POS i Started working on the Newton POS application and the development is inprogress . DB has been completed for writting the scripts for SQLite for Newtom POS 2. Boostrap Migration changes completed for Admin Pages 3. Price Contracts Import Implementation is completed. 4. Oauth 2.0 Integration for SMTP in POS is completed. | Internal CRC - 0 External CRC - 1 QA Defects - 2 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: Patrick Mentioned Overall Relevantz team shows good progress. And RJ has mentioned the Wave team has the visibility of what they are working
NA | MCS 25 Sprint 9 | 2025-04-25 | 2025-05-08 | 13 | 13 | 8 | 0 | 1. Wave team has completed the stories what ever Assigned in the current sprint 2. 70 % of the Newton POS development has been completed in the last 2 sprints. | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: 1. The build was delayed due to our dependency on Patrick, who was on PTO for five working days. 2. Patrick has a positive impression of the Wave team, as we successfully demonstrated the project upon his return.
NA | MCS 25 Sprint 10 | 2025-05-09 | 2025-05-22 | 16 | 21 | 13 | 0 | 1. Wave team has completed most of the stories Assigned in the current sprint and completed the streach stories also. 2. The Newton POS development has been completed and moved the application to Code Review and started the Newton Application Today. | Internal CRC - 0 External CRC - 3 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: 1. Patrick wants to give More attention on Wave and Wave stories till it get completes
NA | MCS 25 Sprint 11 | 2025-05-23 | 2025-06-05 | 7 | 7 | 16 | 0 | 1. Wave team has completed most of the stories Assigned in the current sprint 2. The Newton POS development Analysis has been completed and approach document and Database Schema has been completed | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: Clean Architecture has been followed
NA | MCS 25 Sprint 12 | 2025-06-06 | 2025-06-20 | 16 | 16 | 8 | 0 | 1. Wave team has completed most of the stories Assigned in the current sprint and one story has been carry forwarded to next sprint as its a big functionaity 2. The Newton development 50% of the code has been completed and working on the Architecture development. | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: Clean Architecture has been followed Newton Architecture Demo has been provided
NA | MCS 25 Sprint 13 | 2025-06-21 | 2025-07-03 | 24 | 24 | 0 | 0 | 1. Wave team has completed all the three application Admin Console, Newton and Newton POS.Unit test methods has been completed for newton POS | Internal CRC - 0 External CRC - 1 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: Patrick gave kudos during the retrospective for our recent work—here’s what he shared: "Good job adapting swiftly to the recent unit testing code changes. You not only picked it up quickly, but also delivered code that’s clean, polished, and steadily improving in quality. The incremental progress is clearly visible—keep the momentum going. Kudos to the whole team"
NA | MCS 25 Sprint 14 | 2025-07-04 | 2025-07-17 | 16 | 24 | 13 | 0 | 1. We have completed the Development for Newton and Newton POS Application and currently working on creating the unit test method for the entire applicationalong with the report generation. | Internal CRC - 9 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: Patrick gave kudos during the retrospective for our recent work and claimed that the wave team is progressing good.
NA | MCS 25 Sprint 15 | 2025-07-18 | 2025-07-31 | 24 | 24 | 0 | 0 | We've completed writing unit test methods for the Newton application, covering both the Provider implementation and the files within the Common folder. Test methods written: 60 for Provider implementation 207 for Common folder files Total written: 267 test methods Resulting test executions: 414 run test methods for the Common folder | Internal CRC - 3 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: Patrick is feeling good with the team and the team gonna start working on the API related task from the next sprint.
NA | MCS 25 Sprint 16 | 2025-08-01 | 2025-08-14 | 26 | 26 | 0 | 0 | Contributed to the initial setup of APIs for a DataCenter application and performed analysis on database folder files, including SaveBuilder and Reader modules, to support RPC method implementation | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.. External: Patrick is feeling good with the team and the team is working on the API related task.
NA | MCS 25 Sprint 17 | 2025-08-15 | 2025-08-28 | 32 | 32 | 0 | 0 | Worked for DataCenter application Database folder files changed linear sql queris into Rpc methods implementation | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good. External: Patrick is feeling good with the team and the team gonna start working on the API related task from the next sprint.
NA | MCS 25 Sprint 18 | 2025-08-29 | 2025-09-11 | 18 | 18 | 0 | 0 | Worked for MSAClient application Database folder files changed linear sql queris into Rpc methods implementation | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good. External: Patrick commended the Wave team, describing them as fantastic and highly effective. He gave a special shout-out to Kalai for her outstanding contributions in resolving build issues.
NA | MCS 25 Sprint 19 | 2025-09-12 | 2025-09-24 | 20 | 20 | 0 | 0 | 2 members are working for MSA Client API Testing for Linear queries implemenation and 2 others working on Frankling setup and started API Implemenation | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good. External: Patrick commended the Wave team, Team progressing well for API implemenation.
NA | MCS 25 Sprint 20 | 2025-09-25 | 2025-10-09 | 20 | 20 | 0 | 0 | 4 members are working for Franklin API Calls Implementation | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good.
NA | MCS 25 Sprint 21 | 2025-10-10 | 2025-10-23 | 17 | 17 | 0 | 0 | Newton and Newton POS Code Review comments has been Completed. And along with that, Franklin application Testing has been completed for all the 70 Files. | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: Overall Team Collabration was good. Patrick : Significant Progress is seen in the Wave team.
NA | MCS 25 Sprint 22 | 2025-10-24 | 2025-11-06 | 20 | 20 | 0 | 0 | We have completed 2 Bounceback tickets, by analyzing it we found that it was an configuration issues and cancelled the bounceback. We have also given 2 builds on this sprint, Named, Newton and Newton POS , MCS Application Server along with SQLCipher Implementation We have also completed the datacenter Reader Implementation. | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 2 | Internal: Overall Team Collabration was good. Patrick : Had a good communication with kalai and Hari, and Worked on some of the tickets to clear the blocker.
NA | MCS 25 Sprint 23 | 2025-11-07 | 2025-11-20 | 10 | 28 | 18 | 0 | We Have completed the Newton and Newton POS SqlCipher Implementation and gave the build to the QA Team to perform the QA testing for the application. Also, We completed the Datacenter Application Reader and Builder Files along with testing and gave the application to the Patrick for the Code Review. | Internal CRC - 0 External CRC - 0 QA Defects - 1 Escaped Defects - 0 | Internal: Overall Team Collabration was good. Patrick : Had a good communication with all the MCS Wave team in the sync up calls And, Wave Team is progressing.
NA | MCS 25 Sprint 24 | 2025-11-21 | 2025-12-18 | 42 | 42 | 18 | 0 | We have completed the MSAClient API Implemenation including with Reader/Builder changes and currently doing the code review internally. We have closed three bounce backs Newton/NewtonPOS. | Internal CRC - 0 External CRC - 0 QA Defects - 4 Escaped Defects - 0 | Internal: Overall Team Collabration was good. Patrick : Need to review the MSA Client and Datacenter code.Had a good communication with all the MCS Wave team.
NA | MCS 25 Sprint 25 | 2025-12-19 | 2026-01-15 | 26 | 26 | 18 | 0 | We are currently working on the Franklin application Out of 153 Files we have completed around 73 Files. | Internal CRC - 4 External CRC - 0 QA Defects - 1 Escaped Defects - 0 | Internal: Overall Team Collabration was good. Patrick : Need to review Datacenter Code, The Wave team is progressing well.Had a good communication with all the MCS Wave team.
NA | MCS 26 Sprint 1 | 2026-01-16 | 2026-01-29 | 15 | 15 | 18 | 0 | We are currently working on the Franklin application Out of 153 Files we have completed around 110 Files and planning to work on the Newton Application from next Sprint. Given the Build for Newton & Newton POS Bouncebacks and Admin Console Defect | Internal CRC - 1 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: In this Retro every one shared their thoughts on this current sprint and Shriveni Thanked Patrick for helping us while needed to clarify our doubts and Clarifications. Patrick : In this sprint Patrick has created a ticket for Datacenter to review for himself / Rudy. Also, the message from Richard is - "Wave team kudos; have gotten faster & more accurate this sprint. "
NA | MCS 26 Sprint 2 | 2026-01-30 | 2026-02-12 | 21 | 16 | 18 | 0 | This sprint we have completed the franklin API Implementation for 153 Files and started to work on the Newton API Migration Files. In Newton we have around 242 Files, and these were segregated for each one in the team. | Internal CRC - 7 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: In this Retro every one shared their thoughts on this current sprint. Andrea: Good communication with Milan, Josh, Kalai Andrea – Code review for Data Center ... not clearly defined so branch is so far from Master. Made outline on which to use. Andrea – Some files moved; git history was removed. 1st commit file moved & 2nd file including changes Also, One ticket was carry forwarded to next sprint as we dont have time to take the ticket.
NA | MCS 26 Sprint 3 | 2026-02-13 | 2026-02-26 | 17 | 17 | 17 | 0 | This sprint we have completed the franklin API Implementation for 153 Files and started to work on the Newton API Migration Files. In Newton we have around 242 Files, and these were segregated for each one in the team. | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: In this Retro every one shared their thoughts on this current sprint. Andrea: Good communication with Milan, Josh, Kalai Andrea – Code review for Data Center ... not clearly defined so branch is so far from Master. Made outline on which to use. Andrea – Some files moved; git history was removed. 1st commit file moved & 2nd file including changes Also, One ticket was carry forwarded to next sprint as we dont have time to take the ticket.
NA | MCS 26 Sprint 4 | 2026-02-27 | 2026-03-12 | 20 | 24 | 17 | 4 | This sprint we are currently working on Newton API Implementation for 243 Files and we have completed around 160 files. Also, along with this we have completed around 2 Bouncebacks and 1 defect. | Internal CRC - 0 External CRC - 0 QA Defects - 1 Escaped Defects - 0 | Internal: In this Retro every one shared their thoughts on this current sprint. Andrea – Code review for Data Center ... Patrick : Bounceback review this round helped QA narrow testing scope & saved time
NA | MCS 26 Sprint 5 | 2026-03-13 | 2026-03-26 | 20 | 20 | 13 | 0 | This sprint we have completed the Newton API Migration for all the 243 files and created a ticket to clean up the files and doing the code review. Also int his sprint we have taken the Edison Application to do the API Migration. | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | Internal: In this Retro every one shared their thoughts on this current sprint. Andrea & Rudy – Code review for Data Center has been completed and the build is got ready to test datacenter for QA. Patrick : He concenterated on custom reports this and upcomming sprint and trying to complete it before he leave the company before Apr 17.
NA | MCS 26 Sprint 6 | 2026-03-27 | 2026-04-09 | 20 | 20 | 13 | 8 | This sprint we have started the Edison API Migration for Reader Files for 205 Files. We split the files for all four of us to wok. Also, In this sprint from Development team one of the resourses "Shriveni" Worked for QA to help them complete the SQL Cipher Testing for ewton and Newton POS. | Internal CRC - 0 External CRC - 0 QA Defects - 0 Escaped Defects - 0 | What went well: In this Retro every one shared their thoughts on this current sprint. Andrea & Rudy – Code review for Data Center has been completed and created a ticket to test the datacenter project Patrick : He concenterated on custom reports this sprint to complete before leaving. The Next point of contact was choosed to be "Rudy". What Didn't go well: - NA Improvements - As Patrick is moving needs to discuss the code with Rudy as he gonna be the point of contact.
NA | MCS 26 Sprint 7 | 2026-04-10 | 2026-04-23 | 20 | 25 | 10 | 5 | In this sprint we have completed the Edison Reader files as planned. We have totally 205 Reader files and we have completed all the reader files in this sprint and planned to take the main files to proceed the intermediate queries to migrate to RPC layer. This sprint the team has coordinated wellto complete their task along with bouncebacks. | Internal CRC - 1 External CRC - 0 QA Defects - 1 Escaped Defects - 0 | What went well: In this Retro every one shared their thoughts on this current sprint. Rudy – Code review for Franklin is in progress with rudy and the upgrade changes needs to be merged with the current branch. Patrick has shared his knowledge to hari what we needs to be carried away and whats needs to be accomplished for wave team as he is leaving the company What Didn't go well: - Patrick left the company which creates a void space in wave team. Improvements - NA
NA | MCS 26 Sprint 8 | 2026-04-24 | 2026-05-07 | 20 | 20 | 0 | 0 | In this sprint we were working on the Intermediate querries migrationwhen already reader files are completed. Also, 2 Bouncebacks were raised and completed by the development team by proving the build to QA for the 2 bouncebacks. This sprint the team has coordinated wellto complete their task along with bouncebacks. | Internal CRC - 0 External CRC - 0 QA Defects - 1 Escaped Defects - 0 | What went well: In this Retro every one shared their thoughts on this current sprint. Rudy – Code review for Franklin is in progress with rudy and the upgrade changes needs to be merged with the current branch, Also working along with the wave team for code review.. What Didn't go well: - NA Improvements - NA
NA | MCS 26 Sprint 9 | 2026-05-08 | 2026-05-21 | 20 | 0 | 0 | 0

## Defect-template
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## ExportData
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MCS Wave | 2025-08-01 | 2025-08-14 | MCS Wave 25 Sprint 16 | Kalai | 49404 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API Part 2 | Story Completed | 8
2 | MCS Wave | 2025-08-01 | 2025-08-14 | MCS Wave 25 Sprint 16 | Srini | 49403 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API Part 1 | Story Completed | 8
3 | MCS Wave | 2025-08-01 | 2025-08-14 | MCS Wave 25 Sprint 16 | Sathish | 49434 | MCS - Cloud - (WAVE #68527) Modernize MCS : Wrapping up SQL Lite Stories including comprehensive unit testing for Newton Final Part | Story Completed | 5
4 | MCS Wave | 2025-08-01 | 2025-08-14 | MCS Wave 25 Sprint 16 | Shriveni | 49405 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API Part 3 | Story Completed | 5

## Unplanned Leaves
Total Unplanned Leaves | 1
Resource Name
Sprint Name | Kalaivani Vijaya Pandian | Shriveni Baskarn | Srinivasulu Ponngatti | Sathish Kumar | Jayapriya Suresh | Remarks
MCS 26 Sprint 2 (30-Jan-26 to 12-Feb-26)
MCS 26 Sprint 3 (13-Feb-26 to 26-Feb-26) | 0.5
MCS 26 Sprint 4 (27-Feb-26 to 12-Mar-26)
MCS 26 Sprint 5 (13-Mar-26 to 26-Mar-26)
MCS 26 Sprint 6 (27-Mar-26 to 09-Apr-26)
MCS 26 Sprint 7 (10-Apr-26 to 23-Apr-26) |  | 0.5
MCS 26 Sprint 8 (24-Apr-26 to 07-May-26)
Total | 0.5 | 0.5 | 0 |  | 0

## MCS 26 Sprint 9-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Mitigation
1 | MCS Wave | 2026-05-08 | 2026-05-21 | MCS Wave 26 Sprint 09 | Srini | 53151 | Modernize MCS: Edison – Migrate DB calls to API with basic and intermediate - Part 9 | Story Being Developed | 5 |  |  | 2026-05-08 | 2026-05-21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2026-05-08 | 2026-05-21 | MCS Wave 26 Sprint 09 | Sathish | 53152 | Modernize MCS: Edison – Migrate DB calls to API with basic and intermediate - Part 10 | Story Being Developed | 5 |  |  | 2026-05-08 | 2026-05-21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2026-05-08 | 2026-05-21 | MCS Wave 26 Sprint 09 | Shriveni | 53153 | Modernize MCS: Edison – Migrate DB calls to API with basic and intermediate - Part 11 | Story Being Developed | 5 |  |  | 2026-05-08 | 2026-05-21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MCS Wave | 2026-05-08 | 2026-05-21 | MCS Wave 26 Sprint 09 | kalai | 53154 | Modernize MCS: Edison – Migrate DB calls to API with basic and intermediate - Part 12 | Story Being Developed | 5 |  |  | 2026-05-08 | 2026-05-21 | Yes | NA | Nil | Kalai | Nil | NA |  | Nil | Nil | Nil | Nil |  | Nil | NA | NA |  | NA

## MCS 26 Sprint 9-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 26 Sprint 09 | 27357 | MCS - APP Server - Loosing data when upgrading SQLite to another SQLite version | Sathish | Defect | Loosing data when upgrading SQLite to another SQLite version | Significant | Manual | Internal | Story Peer Review | Internal |  | 2

## MCS 26 Sprint 8-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Mitigation
1 | MCS Wave | 2026-04-24 | 2026-05-07 | MCS Wave 26 Sprint 08 | Kalai | 52952 | Modernize MCS: Newton Code Review | Story Being Developed | 5 | 54 | 10.8 | 2026-04-24 | 2026-05-07 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA
2 | MCS Wave | 2026-04-24 | 2026-05-07 | MCS Wave 26 Sprint 08 | Srini | 52949 | Edison – Migrate DB calls to API with basic and intermediate - Part 6 | Story Being Developed | 5 | 48 | 9.6 | 2026-04-24 | 2026-05-07 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This Edison Applicaition is currently in development phase and the development is in progress we are planning to complete the development on May End. | NA
3 | MCS Wave | 2026-04-24 | 2026-05-07 | MCS Wave 26 Sprint 08 | Sathish | 52950 | Edison – Migrate DB calls to API with basic and intermediate - Part 7 | Story Being Developed | 5 | 54 | 10.8 | 2026-04-24 | 2026-05-07 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This Edison Applicaition is currently in development phase and the development is in progress we are planning to complete the development on May End. | NA
4 | MCS Wave | 2026-04-24 | 2026-05-07 | MCS Wave 26 Sprint 08 | Shriveni | 52951 | Edison – Migrate DB calls to API with basic and intermediate - Part 8 | Story Being Developed | 5 | 60 | 12 | 2026-04-24 | 2026-05-07 | Yes | NA | Nil | Kalai | Nil | NA |  | Nil | Nil | Nil | Nil |  | Nil | NA | NA | This Edison Applicaition is currently in development phase and the development is in progress we are planning to complete the development on May End. | NA

## MCS 26 Sprint 8-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 26 Sprint 08 | 27357 | MCS - APP Server - Loosing data when upgrading SQLite to another SQLite version | Sathish | Defect | Loosing data when upgrading SQLite to another SQLite version | Significant | Manual | Internal | Story Peer Review | Internal | As this defect was raised in the end of this sprint we could not complete this story. | 2

## MCS 26 Sprint 7-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Mitigation
1 | MCS Wave | 2026-04-10 | 2026-04-23 | MCS Wave 26 Sprint 07 | Kalai | 52820 | Modernize MCS: Franklin Code Review & Testing | Story Completed | 5 | 7.5 | 30 | 2026-04-10 | 2026-04-23 | NA | Srini | SQl Injection and for some thods needs to add the validation | Hari | NA | Pull request 48465: [axof:52820] - Franklin API Code Changes - Repos | 16/04/2026 | Rudy | NA | In progress | NA | NA | NA | NA | NA | Client Developer is actually reviewing our code and writting his code on toop of the application. | NA
2 | MCS Wave | 2026-04-10 | 2026-04-23 | MCS Wave 26 Sprint 07 | Srini | 52733 | Edison – Migrate DB calls to API with basic and intermediate Part 3 | Story Completed | 5 | 15 | 60 | 2026-04-10 | 2026-04-23 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This Edison Applicaition is currently in development phase and the development is in progress we are planning to complete the development on May End. | NA
3 | MCS Wave | 2026-04-10 | 2026-04-23 | MCS Wave 26 Sprint 07 | Sathish | 52734 | Edison – Migrate DB calls to API with basic and intermediate Part 4 | Story Completed | 5 | 7.5 | 30 | 2026-04-10 | 2026-04-23 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This Edison Applicaition is currently in development phase and the development is in progress we are planning to complete the development on May End. | NA
4 | MCS Wave | 2026-04-10 | 2026-04-23 | MCS Wave - Sprint 07 Stretch | Shriveni | 52735 | Edison – Migrate DB calls to API with basic and intermediate Part 5 | Story Completed | 5 | 15 | 60 | 2026-04-10 | 2026-04-23 | Yes | NA | Nil | Kalai | Nil | NA |  | Nil | Nil | Nil | Nil |  | Nil | NA | NA | This Edison Applicaition is currently in development phase and the development is in progress we are planning to complete the development on May End. | NA
5 | MCS Wave | 2026-04-10 | 2026-04-23 | MCS Wave - Sprint 07 | kalai | 50401 | Modernize MCS : Implement SQLCipher for Newton POS with end-to-end testing | Story Completed | 5 | 7.5 | 30 | 2026-04-10 | 2026-04-23 | Yes | NA | Nil | Kalai | Nil | NA |  | Nil | Nil | Nil | Nil |  | Nil | NA | NA |  | NA
6 | MCS Wave | 2026-04-10 | 2026-04-23 | MCS Wave - Sprint 07 Stretch | Sathish | 52818 | Modernize MCS: DataCenter Previous Year Database Support [Timebox] | Story Ready For Testing | 5 | 7.5 | 30 | 2026-04-10 | 2026-04-23 | Yes | NA | Nil | Kalai | Nil | NA |  | Nil | Nil | Nil | Nil |  | Nil | NA | NA |  | NA

## MCS 26 Sprint 7-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 26 Sprint 07 | 27201 | MCS - Cloud - DC-API testing one or more error occured | Sathish | Defect | While sync the Datacenter from franklin application the error pop up throws "One more error occoured" | Significant | Manual | Internal | Story Being Developed | Internal | This Defect was added | 2

## MCS 26 Sprint 6-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Mitigation
1 | MCS Wave | 2026-03-27 | 2026-04-09 | MCS Wave 26 Sprint 06 | Kalai | 52509 | Modernize MCS: Franklin Code Review & Newton Testing | Story Completed | 5 | 7.5 | 30 | 2026-03-27 | 2026-04-09 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | As this sprint was completely into the development we havnt created any PR's and Code Review for it. | NA
2 | MCS Wave | 2026-03-27 | 2026-04-09 | MCS Wave 26 Sprint 06 | Srini | 52510 | Edison – Migrate DB calls to API with basic and intermediate setup | Story Completed | 5 | 15 | 60 | 2026-03-27 | 2026-04-09 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | As this sprint was completely into the development we havnt created any PR's and Code Review for it. | NA
3 | MCS Wave | 2026-03-27 | 2026-04-09 | MCS Wave 26 Sprint 06 | Sathish | 52511 | Edison – Migrate DB calls to API with basic and intermediate Part 1 | Story Completed | 5 | 13.5 | 54 | 2026-03-27 | 2026-04-09 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | As this sprint was completely into the development we havnt created any PR's and Code Review for it. | NA
4 | MCS Wave | 2026-03-27 | 2026-04-09 | MCS Wave - Sprint 06 Stretch | Shriveni | 52512 | Edison – Migrate DB calls to API with basic and intermediate Part 2 | Story Completed | 5 | 13.5 | 54 | 2026-03-27 | 2026-04-09 | Yes | NA | Nil | Kalai | Nil | NA |  | Nil | Nil | Nil | Nil |  | Nil | NA | NA | As this sprint was completely into the development we havnt created any PR's and Code Review for it. | NA
5 | MCS Wave | 2026-03-27 | 2026-04-09 | MCS Wave - Sprint 05 Stretch | kalai | 50401 | Modernize MCS : Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 13 | 6 | 24 | 2026-03-27 | 2026-04-09 | Yes | Srini | Nil | Srini | Nil | Pull request 42964: Newton - WIP - Repos | 2026-04-01 | Hari | 2026-04-01 | Nil | 2026-04-01 | Rudy | 2026-04-01 | NA | NA | On of the bounce back has been raised by QA in Newton related to Cast conversion and it was resolved and given the fix to QA team | NA

## MCS 26 Sprint 6-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point

## MCS 26 Sprint 5-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Mitigation
1 | MCS Wave | 2026-03-13 | 2026-03-26 | MCS Wave 26 Sprint 05 | Kalai | 52080 | Franklin – Code Review Migrate DB calls to API Part 2 | Story Completed | 5 | 12.5 | 50 | 2026-03-13 | 2026-03-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | As this sprint was completely into the development we havnt created any PR's and Code Review for it. | NA
2 | MCS Wave | 2026-03-13 | 2026-03-26 | MCS Wave 26 Sprint 05 | Srini | 52310 | Newton – Migrate DB calls to API with basic and intermediate queries Part 8 | Story Completed | 5 | 15 | 60 | 2026-03-13 | 2026-03-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | As this sprint was completely into the development we havnt created any PR's and Code Review for it. | NA
3 | MCS Wave | 2026-03-13 | 2026-03-26 | MCS Wave 26 Sprint 05 | Shriveni | 52312 | Newton – Migrate DB calls to API with basic and intermediate queries Part 9 | Story Completed | 5 | 15 | 60 | 2026-03-13 | 2026-03-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | As this sprint was completely into the development we havnt created any PR's and Code Review for it. | NA
4 | MCS Wave | 2026-03-13 | 2026-03-26 | MCS Wave 26 Sprint 05 | Sathish | 52311 | Newton – Migrate DB calls to API with basic and intermediate queries Part 10 | Story Completed | 5 | 15 | 60 | 2026-03-13 | 2026-03-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | As this sprint was completely into the development we havnt created any PR's and Code Review for it. | NA
5 | MCS Wave | 2026-03-13 | 2026-03-26 | MCS Wave - Sprint 05 Stretch | kalai | 50401 | Modernize MCS : Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 13 | 2.5 | 10 | 2026-03-13 | 2026-03-26 | Yes | Yes | Nil | Kalai | Nil | NA | NA | Nil | Nil | Nil | Nil |  | Nil | NA | NA |  | NA

## MCS 26 Sprint 5-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point

## MCS 26 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | data | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Mitigation
1 | MCS Wave | 2026-02-27 | 2026-03-12 | MCS Wave 26 Sprint 04 | Kalai | 52080 | Franklin – Code Review Migrate DB calls to API | Story Completed | 5 | 6 | 30 | 2026-02-27 | 2026-03-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2026-02-27 | 2026-03-12 | MCS Wave 26 Sprint 04 | Srini | 52077 | Newton – Migrate DB calls to API with basic and intermediate queries Part 5 | Story Completed | 5 | 10.8 | 54 | 2026-02-27 | 2026-03-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2026-02-27 | 2026-03-12 | MCS Wave 26 Sprint 04 | Shriveni | 52079 | Migrate DB calls to API with basic and intermediate queries Newton Part 7 | Story Completed | 5 | 12 | 60 | 2026-02-27 | 2026-03-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MCS Wave | 2026-02-27 | 2026-03-12 | MCS Wave 26 Sprint 04 | Sathish | 52078 | Migrate DB calls to API with basic and intermediate queries Newton Part 6 | Story Completed | 5 | 12 | 60 | 2026-02-27 | 2026-03-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MCS Wave | 2026-02-27 | 2026-03-12 | MCS Wave - Sprint 04 Stretch | Sathish | 50400 | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Story Completed | 4 | 3.75 | 15 | 2026-02-27 | 2026-03-12 | Yes | Srini | Nil | Hari | Functionality code has been modified | Pull request 44601: Newton/POS SQLite - Repos | 17/09/2025 | Patrick | Mar 4 2026 | Nil | Nil | Mar 4 2026 | Nil | NA | NA | The Bounceback 5 & 6 has been fixed and provided the build to the QA Team on 4 Mar | NA
6 | MCS Wave | 2026-02-27 | 2026-03-12 | MCS Wave - Sprint 04 Stretch | Sathish | 50401 | Modernize MCS : Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 13 | 1.1538 | 15 | 2026-02-27 | 2026-03-12 | Yes | Sathish | Nil | Hari | Functionality code has been modified | Pull request 44601: Newton/POS SQLite - Repos | 17/09/2025 | Patrick | Mar 4 2026 | Nil | Nil | Mar 4 2026 | Nil | NA | NA | The Bounceback 5 & 6 has been fixed and provided the build to the QA Team on 4 Mar | NA

## MCS 26 Sprint 4-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 26 Sprint 04 | 26858 | 50400 | kalai | Defect | MCS - (WAVE #68527) Cloud - Newton POS- Path is not a legal form | Significant | Manual | Internal | Defect Rejected | Existing Issue | The defect was raised as it was occuring in SQLite Implemented application and it was raised as defect, but later found out it was an existing behaviour and need some set up to clear the error pop up. | 2

## MCS 26 Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2026-02-13 | 2026-02-26 | MCS Wave 26 Sprint 03 | Kalai | 51906 | Migrate DB calls to API with basic and intermediate queries Part 4 for Newton | Story Completed | 5 | 20 | 64.5 | 2026-02-13 | 2026-02-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2026-02-13 | 2026-02-26 | MCS Wave 26 Sprint 03 | Srini | 51690 | Newton – Migrate DB calls to API with basic and intermediate queries Part 2 | Story Completed | 5 | 20 | 54 | 2026-02-13 | 2026-02-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2026-02-13 | 2026-02-26 | MCS Wave 26 Sprint 03 | Shriveni | 51907 | Migrate DB calls to API for Reader and Builder Files Part 10 for Franklin | Story Completed | 2 | 8 | 24 | 2026-02-13 | 2026-02-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MCS Wave | 2026-02-13 | 2026-02-26 | MCS Wave 26 Sprint 03 | Sathish | 51905 | Migrate DB calls to API with basic and intermediate queries Newton Part 3 | Story Completed | 5 | 20 | 46 | 2026-02-13 | 2026-02-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MCS Wave | 2026-02-13 | 2026-02-26 | MCS Wave - Sprint 03 Stretch | Sathish | 50400 | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Story Ready For Testing | 4 | 16 | 18 | 2026-02-13 | 2026-02-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MCS Wave | 2026-02-13 | 2026-02-26 | MCS Wave - Sprint 03 Stretch | Sathish | 50401 | Modernize MCS : Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 13 | 0 |  |  |  | Yes | NA | Nil | Kalai | Nil | Pipelines - Run Install MCSApplicationServer 4.0.6.16921 | 2026-01-19 | Nil | Nil | Nil | Nil | 2026-01-27 | Nil | NA | NA | The Build Number has been provided to QA and QA testing is in Progress | NA

## MCS 26 Sprint 3-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 25 Sprint 24 - Stretch | 50401 |  | Sathish | Bounceback/Sub-Defect | The sqlcipher.dll gets currupted and missing | Significant | Manual | Internal | Story Being Developed | Internal | The Entire Newton / Newton POS Migration has been moved to QA and they are finding the defects / Bouncebacs | 5
| MCS Wave 25 Sprint 24 - Stretch | 50400 |  | Sathish | Bounceback/Sub-Defect | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Significant | Manual | Internal | Defect Fixed | Internal | The Entire Newton / Newton POS Migration has been moved to QA and they are finding the defects / Bouncebacs

## MCS 26 Sprint 2-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point

## MCS 26 Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Mitigation Plan
1 | MCS Wave | 2026-01-30 | 2026-02-12 | MCS Wave 26 Sprint 02 | Srini | 51689 | Modernize MCS: Newton – Migrate DB calls to API with basic and intermediate queries Part 1 | Story Completed | 5 | 5 | 20 | 2026-02-06 | 2026-02-10 | yes | Kalai | NA | NA | NA | Pull request 46858: MSA Client - PR - Repos | 2026-01-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2026-01-30 | 2026-02-12 | MCS Wave 26 Sprint 02 | Srini | 51687 | Modernize MCS: Newton – Migrate DB calls to API with basic and intermediate queries Part 2 | Story Approved | 5 | 0 | 0 | 2026-01-30 | 2026-02-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | We havnt taken this story as we worked on the other bounce backs and extending the current developments with modifications | In future ticket planning, we must ensure that resource availability (including planned leaves) is accounted for, and that the number of tickets scheduled allows for sufficient backup or slack time to handle unforeseen issues.
3 | MCS Wave | 2026-01-30 | 2026-02-12 | MCS Wave 26 Sprint 02 | Kalai | 51691 | Modernize MCS: MSA Client– Migrate DB calls to API for Reader and Builder Files Code Review -1 | Story Completed | 5 | 6.25 | 25 | 2026-01-30 | 2026-02-05 | yes | Kalai | Yes | Srini | Nil | Pull request 46858: MSA Client - PR - Repos | NA | NA | NA | Why file name DBRejectedApplication.cachedreader.cs is matched as RPC reason reader? - No We dont RpcStudents.cs - Line 75 ⚠️ - Double santization - valid RpcApplicationTracking.cs - AppendTracking() - Checked No harm in this method Remove dead code - Delete unused static helpers in RpcDBApplications.cs - This is an invalid file RPCEndofYear.cs - SetDatabaseRecoveryModeSimple() manual bracketsstring sql = "ALTER DATABASE [" + dbLib.BrackIdentifier(databaseName) + "] SET RECOVERY SIMPLE"; // ^^ ^^ // MANUAL BRACKET + BrackIdentifier() = DOUBLE BRACKETS – Done Valid RPCLogin: "SELECT " + dbLib.CSql(sqlResultVarName) + " = CASE WHEN ..." // ^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^^ // ❌ WRONG! This treats SQL variable name as a VALUE "WHERE " + sql.RecID + " = " + dbLib.CSql(sqlLoginId) // ^^^^^^^^^^^^^^^^^^^^^^^^^ // ❌ WRONG! sqlLoginId is a SQL variable name, not a value – Done Valid why are we migrating Rejectionapplicationreasonreader? - Need Clarification Schoolquerybuilder is migrated from which file? And savehelperbase as well? For studentuploaded.cs - SubmitData() for (int i = 1; i < dto.FieldNames.Count && i < row.Values.Count; ++i) { if (i > 1) sqlUpdate.Append(", "); sqlUpdate.Append(dto.FieldNames[i]); // ^^^^^^^^^^^^^^^^^^^ // ⚠️ FIELD NAME FROM DTO (must verify it's safe) sqlUpdate.Append(" = "); - Done And MINOR INCONSISTENCY: • Line 518: [STUDENT].[" + sqlFieldName + "] - Manual bracketing (not using BrackIdentifier) • Other lines use dbLib.BrackIdentifier(sqlFieldName) - Done SqlExtensionFieldDifferent() Helper • Line 529: Extra ] after [STUDENT_EXTENSION]. + BrackIdentifier(sqlFieldName) • This would cause SQL syntax error - Done RPCWOrklogs: AppendSqlAddStudentWorkLogMultiStudent() public static StringBuilder AppendSqlAddStudentWorkLogMultiStudent(StringBuilder addStudentWorkLogMultiStudentQry, string sqlSelectStudentId, string sqlSelectActionDate, string sqlSelectLoginId, string sqlSelectWorkLogTypeId, string sqlSelectComments, string sqlFrom, string sqlWhere) { addStudentWorkLogMultiStudentQry.AppendLine("INSERT INTO [STUDENT_WORKLOG] ([StudentID], [ActionDate], [LoginID], [WorkLog_TypeID], [Comments])"); addStudentWorkLogMultiStudentQry.AppendLine(" SELECT " + sqlSelectStudentId + ", " + sqlSelectActionDate + ", " + sqlSelectLoginId + ", " + sqlSelectWorkLogTypeId + ", " + sqlSelectComments); // ^^^^^^^^^^^^^^^^^^^ ^^^^^^^^^^^^^^^^^^^^ ^^^^^^^^^^^^^^^^^^ ^^^^^^^^^^^^^^^^^^^^^^^ ^^^^^^^^^^^^^^^^^^ // ⚠️ FROM CALLER ⚠️ FROM CALLER ⚠️ FROM CALLER ⚠️ FROM CALLER ⚠️ FROM CALLER addStudentWorkLogMultiStudentQry.AppendLine(" FROM " + sqlFrom); // ^^^^^^^^ // ⚠️ FROM CALLER if (!string.IsNullOrEmpty(sqlWhere)) addStudentWorkLogMultiStudentQry.AppendLine(" WHERE " + sqlWhere); // ^^^^^^^^ // ⚠️ FROM CALLER addStudentWorkLogMultiStudentQry.AppendLine(dbLib.SQLErrorHandler()); return addStudentWorkLogMultiStudentQry; } • All SQL fragments passed as strings from caller • NO SANITIZATION WITHIN THIS METHOD DBTestDatabases.cs: ISSUE: SQL injection via database name "ALTER DATABASE [" + dbLib.CSql(databaseName) + "] SET RECOVERY SIMPLE" Problem: dbLib.CSql() adds quotes around the value, but the brackets [ ] are outside the quotes. This creates: Correct approach should use dbLib.BrackIdentifier() or not use brackets at all: | NA | NA | NA | NA | NA | Shared the Branch to patrick after completing the Code review comments by Hari. | NA
4 | MCS Wave | 2026-01-30 | 2026-02-12 | MCS Wave 26 Sprint 02 | Shriveni | 51688 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 9 | Story Completed | 3 | 15 | 60 | 2026-01-30 | 2026-02-12 | yes | Kalai | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MCS Wave | 2026-01-30 | 2026-02-12 | MCS Wave 26 Sprint 02 | Sathish | 51687 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 8 | Story Completed | 3 | 7.5 | 30 | 2026-01-30 | 2026-02-12 | yes | Kalai | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MCS Wave | 2026-01-30 | 2026-02-12 | MCS Wave - Sprint 02 Stretch | Sathish | 50400 | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Story Ready For Testing | 4 | 6.25 | 25 | 2026-02-10 | 2026-02-12 | yes | yes | Nil | Srini | Nil | Pull request 42964: Newton - WIP - Repos | 15/06/2025 | Patrick | Nil | Nil | Nil | Pipelines - Run Newton 16.1.0.17992 | Nil | Nil | NA | BounceBack #6 was raised by the QA team and we worked on that and gave the build to QA team. | NA
7 | MCS Wave | 2026-01-30 | 2026-02-12 | MCS Wave - Sprint 02 Stretch | Sathish | 50401 | Modernize MCS : Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 13 | 3.5 | 14 | 2026-02-10 | 2026-02-12 | Yes | Kalai | Nil | Kalai | Nil | Pipelines - Run Install MCSApplicationServer 4.0.6.16921 | 2026-01-19 | Nil | Nil | Nil | Nil | 2026-01-27 | Nil | NA | NA | The Build Number has been provided to QA and QA testing is in Progress | NA

## MCS 26 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2026-01-16 | 2026-01-29 | MCS Wave 26 Sprint 01 | Kalai | 51520 | Modernize MCS: MSA Client– Migrate DB calls to API for Reader and Builder Files Code Review | Story Completed | 3 | 6.5 | 26 | yes | Kalai | NA | NA | NA | Pull request 46858: MSA Client - PR - Repos | 2026-01-26 | Hari | NA | Don't remove unused the references as it leads to the confusion, will take this a tech debt story in later point. | NA | NA | NA | NA | NA | Review Comments are being addressing for the MSA Client | NA
2 | MCS Wave | 2026-01-16 | 2026-01-29 | MCS Wave 26 Sprint 01 | Sathish | 26604 | Modernize MCS: Admin Console Vista Upgrade | Story Completed | 2 | 4.25 | 17 | Yes | Kalai | Nil | Kalai | Nil | Pipelines - Run Install MCSApplicationServer 4.0.6.16921 | 2026-01-19 | Nil | Nil | Nil | Nil | 2026-01-27 | Nil | NA | NA | The Build Number has been provided to QA and QA testing is in Progress | NA
3 | MCS Wave | 2026-01-16 | 2026-01-29 | MCS Wave - Sprint 01 Stretch | Sathish | 50401 | Modernize MCS : Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 13 | 5.25 | 21 | yes | Kalai | NA | NA | NA | Pull requests - Repos | 2026-01-19 | Patrick | NA | NA | NA | 2026-01-27 | NA | NA | NA | Bounceback : The sqlcipher.dll gets currupted and missing , the bounceback has been addressed and provided the fix in the same sprint. | NA
4 | MCS Wave | 2026-01-16 | 2026-01-29 | MCS Wave - Sprint 01 Stretch | Sathish | 50400 | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Story Ready For Testing | 5 | 7 | 28 | yes | Kalai | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | The Entire Newton / Newton POS Migration has been moved to QA and they are finding the defects / Bouncebacs | NA
5 | MCS Wave | 2026-01-16 | 2026-01-29 | MCS Wave 26 Sprint 01 | Shriveni | 51522 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 7 | Story Completed | 5 | 12 | 48 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MCS Wave | 2026-01-16 | 2026-01-29 | MCS Wave 26 Sprint 01 | Srini | 51521 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 6 | Story Completed | 5 | 9 | 36 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## MCS 26 Sprint 1-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 25 Sprint 24 - Stretch | 50400 |  | Sathish | Bounceback/Sub-Defect | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Significant | Manual | Internal | Defect Fixed | Internal | The Entire Newton / Newton POS Migration has been moved to QA and they are finding the defects / Bouncebacs

## MCS 25 Sprint 25-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-12-19 | 2026-01-15 | MCS Wave 25 Sprint 25 | Kalai | 501295 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 5 | Story Completed | 5 | 8.5 | 34 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2025-12-19 | 2026-01-15 | MCS Wave 25 Sprint 25 | Shriveni | 501293 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 3 | Story Completed | 5 | 22.5 | 90 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2025-12-19 | 2026-01-15 | MCS Wave 25 Sprint 25 | Srini | 501291 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 2 | Story Completed | 5 | 23.5 | 94 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MCS Wave | 2025-12-19 | 2026-01-15 | MCS Wave 25 Sprint 25 - Stretch | Sathish | 50401 | Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 5 | 5.75 | 23 | Yes | Kalai | Nil | Kalai | Nil | Pipelines - Run Newton 16.0.9.17005 | Nil | NA | NA | NA | NA | NA | NA | NA | NA | For the Newton BounceBacks the build has been provided to QA team | NA
5 | MCS Wave | 2025-12-19 | 2026-01-15 | MCS Wave 25 Sprint 25 | Sathish | 501294 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 4 | Story Completed | 5 | 8 | 32 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MCS Wave | 2025-12-19 | 2026-01-15 | MCS Wave 25 Sprint 25 - Stretch | Sathish | 50400 | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Defect Ready For Testing | 13 | 10 | 40 | Yes | Kalai | Nil | Kalai | Nil | Pipelines - Run Newton 16.0.9.17005 | Nil | NA | NA | NA | NA | NA | NA | NA | NA | For the NewtonPOS BounceBacks the Build has been provided to the QA team for Testing | NA
7 | MCS Wave | 2025-12-19 | 2026-01-15 | MCS Wave 25 Sprint 25 | Kalai | 51292 | Modernize MCS: MSA Client– Migrate DB calls to API for Reader and Builder Files Code Review | Story Completed | 3 | 6.25 | 25 | NA | Hari | NA | Srini | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MCS Wave | 2025-12-19 | 2026-01-15 | MCS Wave 25 Sprint 25 | Kalai | 51299 | Modernize MCS: Datacenter– Migrate DB calls to API for Reader and Builder Files Code Review | Story Completed | 3 | 6.25 | 25 | NA | Hari | NA | Srini | NA | Pull request 46429: [axof:51299] - MCSDatacenter API Implementation for DB calls - Repos | 2026-01-06 | Hari | 2026-01-13 | MCSDataCenter.DbRpcLib\RpcDatabase\RpcWinFSFRUploads.Reader.cs Using RpcDB.UploadStatus instead of local UploadStatus enum (defined at line 14). File: MCSDataCenter.DbRpcLib\RpcDatabase\RpcDB.cs (Line 22) PROBLEM: DOUBLE ESCAPING - Using both CSql() and BrackIdentifier() together is incorrect! • dbLib.CSql(databaseName) returns: 'DatabaseName' (string literal with quotes) • dbLib.BrackIdentifier('DatabaseName') returns: ['DatabaseName'] (bracket-escaped identifier) • Combined result: [''DatabaseName''] ❌ INVALID SQL! | Patrick | NA | NA | NA | NA | NA | NA

## MCS 25 Sprint 25-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 25 Sprint 24 - Stretch | 50401 | 50401 | Sathish | Bounceback/Sub-Defect | Implement SQLCipher for Newton POS with end-to-end testing | Significant | Manual | Internal | Defect Fixed | Internal | The Entire Newton / Newton POS Migration has been moved to QA and they are finding the defects / Bouncebacs
| MCS Wave 25 Sprint 24 - Stretch | 50400 | 50400 | Sathish | Bounceback/Sub-Defect | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Significant | Manual | Internal | Defect Fixed | Internal | The Entire Newton / Newton POS Migration has been moved to QA and they are finding the defects / Bouncebacs

## MCS 25 Sprint 24-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-11-21 | 2025-12-18 | MCS Wave 25 Sprint 24 | Kalai | 50936 | Modernize MSA Client – Migrate DB calls to API for Reader and Builder Files Part 3 | Story Completed | 8 | 32 | 120 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2025-11-21 | 2025-12-18 | MCS Wave 25 Sprint 24 | Shriveni | 50727 | Modernize MCS: MSA Client – Migrate DB calls to API for Reader and Builder Files Part 2 [Timebox] | Story Completed | 13 | 52 | 90 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MCS Wave | 2025-11-21 | 2025-12-18 | MCS Wave 25 Sprint 24 | Srini | 50726 | Modernize MCS: MSA Client – Migrate DB calls to API for Reader and Builder Files Part 1 [Timebox] | Story Completed | 13 | 52 | 114 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2025-11-21 | 2025-12-18 | MCS Wave 25 Sprint 24 - Stretch | Sathish | 50401 | Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 5 | 20 | 36 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MCS Wave | 2025-11-21 | 2025-12-18 | MCS Wave 25 Sprint 24 | Sathish | 50935 | Modernize MCS: Franklin – Migrate DB calls to API for Reader and Builder Files Part 1 | Story Completed | 8 | 32 | 57 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MCS Wave | 2025-11-21 | 2025-12-18 | MCS Wave 25 Sprint 24 - Stretch | Sathish | 50400 | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Story Being Developed | 13 | 52 | 26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## MCS 25 Sprint 24-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 25 Sprint 24 - Stretch | 50401 |  | Sathish | Bounceback/Sub-Defect | Implement SQLCipher for Newton POS with end-to-end testing | Significant | Manual | Internal | Defect Fixed | Internal | The Entire Newton / Newton POS Migration has been moved to QA and they are finding the defects / Bouncebacs
| MCS Wave 25 Sprint 24 - Stretch | 50400 |  | Sathish | Bounceback/Sub-Defect | Modernize MCS : Implement SQLCipher for Newton with end-to-end testing | Significant | Manual | Internal | Defect Fixed | Internal | The Entire Newton / Newton POS Migration has been moved to QA and they are finding the defects / Bouncebacs

## MCS 25 Sprint 23-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-11-07 | 2025-11-20 | MCS Wave 25 Sprint 23 | Kalai / Shriveni | 50724 | Datacenter – Migrate DB calls to API for Reader Files Part 1 – Testing | Story Being Developed | 5 | 54 | 13.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2025-11-07 | 2025-11-20 | MCS Wave 25 Sprint 23 | Srini / Satish | 50725 | Datacenter – Migrate DB calls to API for Reader Files Part 2 – Testing | Story Being Developed | 5 | 60 | 15 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2025-11-07 | 2025-11-20 | MCS Wave 25 Sprint 23 - Stretch | Kalai | 50400 | Implement SQLCipher for Newton with end-to-end testing | Story Ready For Testing | 13 | 56 | 14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MCS Wave | 2025-11-07 | 2025-11-20 | MCS Wave 25 Sprint 23 - Stretch | Kalai | 50401 | Implement SQLCipher for Newton POS with end-to-end testing | Story Ready For Testing | 5 | 35 | 8.75 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## MCS 25 Sprint 23-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 25 Sprint 23 | 26336 |  | Kalai | Defect | (WAVE #68527) Application Server - After upgrade to SQLite Connection Methods for some applications are lost | Minor | Manual | External | Defect Being Tested | Existing Issue | The issue was related to the DB end and it was fixed and gave the build to QA team. | 3

## MCS 25 Sprint 22-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-10-24 | 2025-11-06 | MCS Wave 25 Sprint 22 | Kalai | 50014 | Modernize MCS : Newton and POS Code Review | Story Completed | 2 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2025-10-24 | 2025-11-06 | MCS Wave 25 Sprint 22 | kalai | 50387 | Implement SQLCipher for Application Server with end-to-end testing | Story Completed | 3 | 6.25 | 25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2025-10-24 | 2025-11-06 | MCS Wave 25 Sprint 22 | Srini | 50525 | DataCenter Application Rpc Reader Implementation Part 1 | Story Completed | 5 | 13.75 | 55 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MCS Wave | 2025-10-24 | 2025-11-06 | MCS Wave 25 Sprint 22 | shriveni | 50526 | DataCenter Application Rpc Reader Implementation Part 2 | Story Completed | 5 | 12.5 | 50 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MCS Wave | 2025-10-24 | 2025-11-06 | MCS Wave 25 Sprint 22 - Stretch | Kalai | 50370 | Datacenter - Migrate DB calls to API for Reader Files | Story Completed | 5 | 12.5 | 50 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## MCS 25 Sprint 22-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Story Point
| MCS Wave 25 Sprint 21 | 47530 |  | Sathish Kumar | Bounceback/Sub-Defect | MCS - Cloud - (WAVE #68527) Modernize MCS : Testing - Migrate to SQLite ¦ Security Tab | Major | Manual | Internal | Defect Found | Internal | The Bounce back has been analysed and found the issue was from the configuration which we needs to be done in the QA system. The QA closed this bounceback after tested. | 5

## MCS 25 Sprint 21-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-10-10 | 2025-10-23 | MCS Wave 25 Sprint 21 | Kalai | 50014 | Newton and POS Code Review | Story Completed | 2 | 7.5 | 30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2025-10-10 | 2025-10-23 | MCS Wave 25 Sprint 21 | Srini | 50368 | Franklin - Migrate DB calls to API with Testing Part 2 | Story Completed | 5 | 11.25 | 45 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2025-10-10 | 2025-10-23 | MCS Wave 25 Sprint 21 | Sathish | 50367 | Franklin - Migrate DB calls to API with Testing Part 1 | Story Completed | 5 | 12 | 48 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MCS Wave | 2025-10-10 | 2025-10-23 | MCS Wave 25 Sprint 21 | Shriveni | 50369 | Franklin - Migrate DB calls to API with Testing Part 3 | Story Completed | 5 | 12 | 48 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## MCS 25 Sprint 21-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 20-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-09-25 | 2025-10-09 | MCS Wave 25 Sprint 20 | Kalai | 50192 | Franklin - Migrate DB calls to API with Testing Part 2 | Story Completed | 5 | 20 | 48 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
2 | MCS Wave | 2025-09-25 | 2025-10-09 | MCS Wave 25 Sprint 20 | Srini | 50193 | Franklin - Migrate DB calls to API with Testing Part 3 | Story Completed | 5 | 20 | 47 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
3 | MCS Wave | 2025-09-25 | 2025-10-09 | MCS Wave 25 Sprint 20 | Sathish | 50194 | Franklin - Migrate DB calls to API with Testing Part 4 | Story Completed | 5 | 20 | 53 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
4 | MCS Wave | 2025-09-25 | 2025-10-09 | MCS Wave 25 Sprint 20 | Shriveni | 50195 | Franklin - Migrate DB calls to API with Testing Part 5 | Story Completed | 5 | 20 | 46.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A

## MCS 25 Sprint 20-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 19-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-09-12 | 2025-09-24 | MCS Wave 25 Sprint 19 | Kalai | 50012 | Franklin - Migrate DB calls to API with Testing Part 1 | Story Completed | 5 | 20 | 54 | Nil | Srini | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
2 | MCS Wave | 2025-09-12 | 2025-09-24 | MCS Wave 25 Sprint 19 | Srini | 50013 | Franklin - Migrate DB calls to API with Testing Part 2 | Story Completed | 5 | 20 | 54 | Nil | Satish | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
3 | MCS Wave | 2025-09-12 | 2025-09-24 | MCS Wave 25 Sprint 19 | Sathish | 50010 | MSA Client - Migrate DB calls to API with Testing Part 5 | Story Completed | 5 | 20 | 54 | Nil | Shriveni | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
4 | MCS Wave | 2025-09-12 | 2025-09-24 | MCS Wave 25 Sprint 19 | Shriveni | 50011 | MSA Client - Migrate DB calls to API with Testing Part 6 | Story Completed | 5 | 20 | 54 | Nil | Kalai | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil

## MCS 25 Sprint 19-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| MCS Wave 25 Sprint 19 | 49650 | MCS - Cloud - (WAVE #68527) DataCenter Import Error | Kalai | Defect | Pre conditions: - Application Server and Admin Console are installed with installers which contains SQLite implentation. - Any Datacenter dataset is restored - Datacenter is installed | Significant | Manual | Internal | Story Completed | Internal

## MCS 25 Sprint 18-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-08-29 | 2025-09-11 | MCS Wave 25 Sprint 18 | Kalai | 49821 | MSA Client - Migrate DB calls to API with Testing Part 1 | Story Being Developed | 5 | 20 | 24 | Partially Completed |  | Nil | Srini | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
2 | MCS Wave | 2025-08-29 | 2025-09-11 | MCS Wave 25 Sprint 18 | Srini | 49822 | MSA Client - Migrate DB calls to API with Testing Part 2 | Story Completed | 5 | 20 | 60 | Partially Completed |  | Nil | Satish | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
3 | MCS Wave | 2025-08-29 | 2025-09-11 | MCS Wave 25 Sprint 18 | Sathish | 49823 | MSA Client - Migrate DB calls to API with Testing Part 3 | Story Completed | 5 | 20 | 54 | Partially Completed |  | Nil | Shriveni | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
4 | MCS Wave | 2025-08-29 | 2025-09-11 | MCS Wave 25 Sprint 18 | Shriveni | 49824 | MSA Client - Migrate DB calls to API with Testing Part 4 | Story Being Developed | 3 | 12 | 48 | Partially Completed |  | Nil | Kalai | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil

## MCS 25 Sprint 18-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 17-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-08-15 | 2025-08-28 | MCS Wave 25 Sprint 17 | Kalai | 49647 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API with Testing Part 4 | Story Completed | 3 | 12 | 14 | Done | Nil | Nil | Shriveni | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
2 | MCS Wave | 2025-08-15 | 2025-08-28 | MCS Wave 25 Sprint 17 | Srini | 49644 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API with Testing Part 5 | Story Completed | 8 | 32 | 48 | Done | Nil | Nil | Kalai | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
3 | MCS Wave | 2025-08-15 | 2025-08-28 | MCS Wave 25 Sprint 17 | Sathish | 49645 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API with Testing Part 6 | Story Completed | 8 | 32 | 42 | Done | Nil | Nil | Srinivasu | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
4 | MCS Wave | 2025-08-15 | 2025-08-28 | MCS Wave 25 Sprint 17 | Shriveni | 49646 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API with Testing Part 7 | Story Completed | 8 | 32 | 48 | Done | Nil | Nil | Sathish | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
5 | MCS Wave | 2025-08-15 | 2025-08-28 | MCS Wave 25 Sprint 17 | Kalai | 49649 | MCS - Cloud - (WAVE #68527) Incorrect usernames in the SQLite Default Database, specifically in the Application table | Story Completed | 2 | 8 | 14 | Done | Nil | Nil | Patrick | Nil | https://dev.azure.com/heartlandschools/MCS/_git/MCSApplicationServer/pullrequest/41173 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil
6 | MCS Wave | 2025-08-15 | 2025-08-28 | MCS Wave 25 Sprint 17 | Kalai | 49650 | MCS - Cloud - (WAVE #68527) DataCenter Import Error | Story Peer Review | 3 | 12 | 14 | Done | Nil | Nil | Patrick | Nil | https://dev.azure.com/heartlandschools/MCS/_git/MCSLib/pullrequest/42091 | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil | Nil

## MCS 25 Sprint 17-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 16-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-08-01 | 2025-08-14 | MCS Wave 25 Sprint 16 | Kalai | 49404 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API Part 2 | Story Completed | 8 | 8 | 60
2 | MCS Wave | 2025-08-01 | 2025-08-14 | MCS Wave 25 Sprint 16 | Srini | 49403 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API Part 1 | Story Completed | 8 | 8 | 60
3 | MCS Wave | 2025-08-01 | 2025-08-14 | MCS Wave 25 Sprint 16 | Sathish | 49434 | MCS - Cloud - (WAVE #68527) Modernize MCS : Wrapping up SQL Lite Stories including comprehensive unit testing for Newton Final Part | Story Completed | 5 | 5 | 54
4 | MCS Wave | 2025-08-01 | 2025-08-14 | MCS Wave 25 Sprint 16 | Shriveni | 49405 | MCS - Cloud - (WAVE #68527) Modernize MCS : Datacenter - Migrate DB calls to API Part 3 | Story Completed | 5 | 5 | 60

## MCS 25 Sprint 16-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 15-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-07-18 | 2025-07-31 | MCS Wave 25 Sprint 15 | Kalai | 49053 | MCS - Cloud - (WAVE #68527) Modernize MCS : Newton Application (Unit Test Framework) | Story Completed | 5 | 15 | 60 | Yes | Sathish | Remove Unnessary namespace | Sathish | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | In this sprint we are creating the unit test method for the Newton Application
2 | MCS Wave | 2025-07-18 | 2025-07-31 | MCS Wave 25 Sprint 15 | Srini | 49193 | MCS - Cloud - (WAVE #68527) Modernize MCS : Wrapping up SQL Lite Stories including comprehensive unit testing for Newton Part 2 | Story Completed | 8 | 15 | 60 | Yes | Shriveni |  | Shriveni | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | In this sprint we are creating the unit test method for the Newton Application
3 | MCS Wave | 2025-07-18 | 2025-07-31 | MCS Wave 25 Sprint 15 | Sathish | 49192 | MCS - Cloud - (WAVE #68527) Modernize MCS : Wrapping up SQL Lite Stories including comprehensive unit testing for Newton Part 1 | Story Completed | 8 | 12 | 48 | Yes | Kalai | proper naming conventions, detection of unused variables, and opportunities for code optimization. Provide suggestions to improve readability, maintainability, and performance where applicable. | Kalai | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | In this sprint we are creating the unit test method for the Newton Application
4 | MCS Wave | 2025-07-18 | 2025-07-31 | MCS Wave 25 Sprint 15 | Shriveni | 49194 | MCS - Cloud - (WAVE #68527) Modernize MCS : Wrapping up SQL Lite Stories including comprehensive unit testing for Newton Part 3 | Story Completed | 3 | 13.5 | 54 | Yes | Srini | Please provide the review comments wt we needs to use, I am providing these only "proper naming conventions, detection of unused variables, and opportunities for code optimization. Provide suggestions to improve readability, maintainability, and performance where applicable." | Srini | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | In this sprint we are creating the unit test method for the Newton Application

## MCS 25 Sprint 15-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 14-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-07-04 | 2025-07-17 | MCS Wave 25 Sprint 14 | Kalai | 49053 | MCS - Cloud - (WAVE #68527) Modernize MCS : Newton Application (Unit Test Framework) | Story Being Developed | 5 | 7.5 | 30 | 2025-07-04 |  | Done | Srini | Nil | Srini | Complete SQLite Unit Tests First Focus on implementing all test cases using SQLite as the backend. Utilize the helper class for DB setup, seeding, and teardown. Extend Solution to VistaDB Once SQLite tests are completed, begin integrating VistaDB as the alternate provider. Investigate differences in behavior, connection setup, and schema management. Write VistaDB Connection Setup Document the theory behind setting up a VistaDB connection. Create a reusable method inside the helper to configure and return a VistaDB instance. | NA
2 | MCS Wave | 2025-07-04 | 2025-07-17 | MCS Wave 25 Sprint 14 Stretch | Srini | 49009 | MCS - Cloud - (WAVE #68527) Modernize MCS : Wrapping up SQL Lite Stories including comprehensive unit testing -1 [Time Box] | Story Completed | 13 | 22.5 | 90 | 2025-07-04 |  | Done | Shriveni | Nil | Shriveni | Pass DB Instances into Tests Refactor your test methods to accept the database instance as a parameter. This helps support both SQLite and VistaDB dynamically through test configuration. Merge Common Functionality Write all common functionalities for SQLite and VistaDB into the helper class. Separate provider-specific logic into nested methods or use conditional branching if needed. | NA
3 | MCS Wave | 2025-07-04 | 2025-07-17 | MCS Wave 25 Sprint 14 | Sathish | 49010 | MCS - Cloud - (WAVE #68527) Modernize MCS : Wrapping up SQL Lite Stories including testing - 2 | Story Completed | 8 | 15 | 60 | 2025-07-04 |  | Done | Kalai | Nil | Kalai | Create a Common Helper File Add a new helper class (e.g., DbTestHelper.cs) under your unit test project to manage shared database logic. This file should provide access to the properties and utilities of the db.cs implementation. Centralize Shared Methods Move all frequently used or pre-set functions (initialization, disposal, seeding) into the helper class. Ensure the helper class is static or singleton if needed, to maintain a clean API. Include Master Tables in Helper Define and initialize master tables like Items, Categories, or other static lookup data within the helper. This allows consistent seeding for both SQLite and VistaDB tests. | NA
4 | MCS Wave | 2025-07-04 | 2025-07-17 | MCS Wave 25 Sprint 14 | Shriveni | 49066 | MCS - Cloud - (WAVE #68527) Modernize MCS : Wrapping up SQL Lite Stories including comprehensive unit testing - 3 | Story Completed | 3 | 9.25 | 37 | 2025-07-04 |  | Done | Sathish | Nil | Sathish | Write the unit test methods by taking the reference of the previoues completed file. | NA

## MCS 25 Sprint 14-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 13-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1 | Column2
1 | MCS Wave | 2025-06-23 | 2025-07-03 | MCS Wave 25 Sprint 13 | Kalai | 48479 | MCS - Cloud - (WAVE #68527) Modernize MCS : Newton Architecture Implementation | Story Completed | 8 | 8 | 56 | Done | Srini | Remove Unnessary References dont use * in select statements | Srini | NIL | https://dev.azure.com/heartlandschools/MCS/_git/Newton/pullrequest/42964 | NIL | NIL | NIL | 1.Add "LockDB" as the reference is already added." 2.Remove unused References | Hari | NIL | NIL | NIL | NIL
2 | MCS Wave | 2025-06-23 | 2025-07-03 | MCS25 - Sprint 13 Stretch | Srini | 48441 | MCS - Cloud - (WAVE #68527) Modernize MCS : Newton POS Application (Unit Test Framework) | Story Completed | 8 | 8 | 60 | Done | Sathish | Arrange the code accordingly like Arrange, Act and Assert don't use temp file to create a database for SQLite create the temp database inside test project | Sathish | NIL | Pull request 42964: Newton - WIP - Repos | NIL | NIL | NIL | Mocking is meant to simplify the complex behavior of Dependencies to the concrete class being tested. Things like, if the class wants to send an email, but we're not validating that emails are being sent, then the email sender class should be mocked. | Patrick | NIL | NIL | NIL | NIL
3 | MCS Wave | 2025-06-23 | 2025-07-03 | MCS Wave 25 Sprint 13 | Sathish | 48595 | MCS - Cloud - (WAVE #68527) Modernize MCS : Add SQLite Db in Newton Application | Story Completed | 8 | 8 | 60 | Done | Kalai | Don't use * in select statement don't use object instead use var datatype | Kalai | NIL | Pull request 42964: Newton - WIP - Repos | NIL | NIL | NIL |  | NIL | NIL | NIL | NIL | NIL

## MCS 25 Sprint 13-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 12-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-06-06 | 2025-06-20 | MCS Wave 25 Sprint 12 | Kalai | 48439 | MCS - Cloud - (WAVE #68527) Modernize MCS : Segregate Vista Db from Newton Application | Story Completed | 5 | 5 | 42 | Srini | Srini | NA | Srini | Architectre would be done as like Newton POS
2 | MCS Wave | 2025-06-06 | 2025-06-20 | MCS Wave 25 Sprint 12 | Srini | 48438 | MCS - Cloud - (WAVE #68527) Modernize MCS : Create SQLite ¦ Newton Database Creation: Build SQLite DB with Schema | Story Completed | 3 | 3 | 28 | Sathish | Sathish | NA | [12 empty] | The unit test has been completed with the earlier architecture and when the architecture has been modifies we has a plan to carry forward this to next sprint.
3 | MCS Wave | 2025-06-06 | 2025-06-20 | MCS Wave 25 Sprint 12 | Sathish | 48595 | MCS - Cloud - (WAVE #68527) Modernize MCS : Add SQLite Db in Newton Application [Timebox] | Story Completed | 8 | 8 | 60 | Kalai | Kalai | NA | Kalai | Please follow the code for newton as donr by NewtonPOS

## MCS 25 Sprint 12-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 11-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-05-23 | 2025-06-05 | MCS Wave 25 Sprint 11 | Srini | 48438 | MCS - Cloud - (WAVE #68527) Modernize MCS : Create SQLite ¦ Newton Database Creation: Build SQLite DB with Schema | Story Completed | 2
2 | MCS Wave | 2025-05-23 | 2025-06-05 | MCS Wave 25 Sprint 11 | Sathish | 48437 | MCS - Cloud - (WAVE #68527) Modernize MCS : Refined Approach for Newton | Story Completed | 3
3 | MCS Wave | 2025-05-23 | 2025-06-05 | MCS Wave 25 Sprint 11 | Kalai | 48197 | MCS - Cloud - (WAVE #68527) Modernize MCS : System - Migrate to SQLite ¦ Query conversion from VistaDB to SQLite Part 1.5 | Story Completed | 2
4 | MCS Wave | 2025-05-23 | 2025-06-05 | MCS Wave 25 Sprint 11 Stretch | Kalai | 48439 | MCS - Cloud - (WAVE #68527) Modernize MCS : Segregate Vista Db from Newton Application | Story Being Developed | 8
5 | MCS Wave | 2025-05-23 | 2025-06-05 | MCS Wave 25 Sprint 11 Stretch | Srini | 48442 | MCS - Cloud - (WAVE #68527) Modernize MCS : Newton POS (Unit Test Framework) | Story Peer Review | 8

## MCS 25 Sprint 11-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 10-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-05-09 | 2025-05-22 | MCS Wave 25 Sprint 10 | Kalai | 48197 | MCS - Cloud - (WAVE #68527) Modernize MCS : Migrate to SQLite ¦ Query conversion from VistaDB to SQLite Part 1.5 | Story Peer Review | 8 | 15 | 60 | NA | NA | NA | srini | [11 empty] | The Reson i took long time is, The Architecture has been changed at the mid of the sprint as we have completed 90 % of the code. And we put out effort to complete the development on time along with the architecture change. Also, in this sprint we face some build issues for Admin Console and it took our time.
2 | MCS Wave | 2025-05-09 | 2025-05-22 | MCS Wave 25 Sprint 10 | Srini | 48191 | MCS - Cloud - (WAVE #68527) Modernize MCS : Migrate to SQLite ¦ Query conversion from VistaDB to SQLite Part 3 | Story Completed | 8 | 12 | 48 | NA | NA | NA | sathish
3 | MCS Wave | 2025-05-09 | 2025-05-22 | MCS Wave 25 - Sprint 10 Stretch | Sathish | 48029 | MCS - Cloud - (WAVE #68527) Modernize MCS : Migrate to SQLite ¦ Query conversion from VistaDB to SQLite Part 2 | Story Completed | 13 | 15 | 60 | NA | NA | NA | kalai | Nil | Pull request 42135: [axof: 47881] Migrate to SQLite - Repos | 14/05/2025 | Patrick |  | 1. The Variable needs to be named better 2.There is no need to create a sqlite version of this object. It has nothing to do with the database. 3. since prmreturn is no longer used. Actually prmreturn should be removed entirely to avoid confusion like this. | [5 empty] | Got an Escalation for this current sprint from Patrick, As the development Quality is not par to the standard. So, We had a call with the entire team and set the stage to do the peer Review and assigned an Architect to do the code Review before moving it to patrick.

## MCS 25 Sprint 10-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 25 Sprint 9-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours (Worklog) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Column1
1 | MCS Wave | 2025-04-25 | 2025-05-08 | MCS 25 Sprint 9 | Sathish | 47881 | MCS - Cloud - (WAVE #68527) Modernize MCS : Migrate to SQLite ¦ Transition to SQLite with Offline Database Creation Replacing Vista DB | Story Completed | 8 | 13.25 | 53 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MCS Wave | 2025-04-25 | 2025-05-08 | MCS 25 Sprint 9 | Srini | 48021 | MCS - Cloud - (WAVE #68527) Modernize MCS : Migrate to SQLite ¦ Creating Offline photo db | Story Completed | 5 | 11.25 | 45 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MCS Wave | 2025-04-25 | 2025-05-08 | MCS25 - Sprint 9 Stretch | Kalai | 48022 | MCS - Cloud - (WAVE #68527) Modernize MCS : Migrate to SQLite ¦ Query conversion from VistaDB to SQLite Part 1 [Time Box] | Story Being Developed | 8 | 12 | 48 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 4 | NA | NA

## MCS 25 Sprint 9-Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## MCS 24 - Sprint 25-Status_Old
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Code Review | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Client Code Review Comments | Approved Date | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MCS24 Sprint 25 | Dineshkumar Sathasivam | 46337 | MCS - POS - Role importer - Map cafeteria roles to categories | Inprogress | 1 | 1 | Done | Boobalakrishnan | Nil | Boobalakrishnan | Nil | https://dev.azure.com/heartlandschools/MCS/_git/Newton/pullrequest/39972 | 2024-12-05 | 2024-12-17 | Boobalakrishnan | Nil | Patrick | Nil | 2024-12-17 | ACs met the expectations and POV verified successfully. | ACs met the expectations and POV verified successfully. | Task development is completed and PR is approved. QA requested additional testing effort and hence it is in testing stage.
2 | MCS24 Sprint 25 | Boobalakrishnan Ramasamy | 24266 | MCS - POS - Fix Grouping and Sorting for Layout Overrides in Student Roster and Student Barcode Roster Report | Inprogress | 2 | 2 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/MCS/_git/Newton/pullrequest/39981 | 2024-12-10 |  | Patrick |  | Patrick | Performing the sort here does not guarantee that the data will be sorted correctly after it is grouped in the devexpress report. This field should be selected as a column named [SORT_KEY], just like the [GROUP_*] columns, and then sorting should be performed in the report. |  | ACs met the expectations and POV verified successfully. | ACs met the expectations and POV verified successfully. | 12/10 - POV is done and created PR. This will be carried over to next sprint Rudy is fine with the implementation. Dev and unit testing is done. Need to go for POV 11/22 - Based on the discussion(11/22) with Patrick and Rudy we need to implement this feature based on InventoryOnHand report layout. GroupBy layout will be modified according to that. Defect was introduced by client. Analysis only completed. When analyzed, we found there is no functionality related to this issue, so we are going to implement a new feature that will oversee the future complications related to this defect. 12/10 - PR has been raised for this defect. Waiting for PR approval from Patrick. Carry forwarded to next sprint.
3 | MCS24 Sprint 25 | Dineshkumar Sathasivam | 45301 | MCS - ED - Import Price Contracts | Inprogress | 8 | [16 empty] | Analysis for this story completed in the current sprint. Development task will be carry forwarded to Sprint 25.
4 | MCS24 Sprint 25 | Hariharan Dhandapani | 46563 | MCS - FR - Replace System.Net.Mail with MailKit and enable OAuth2 for email | Inprogress | 8 | [16 empty] | Analysis for this story completed in the current sprint. Development task will be carry forwarded to Sprint 25.
5 | MCS24 Sprint 25 | Boobalakrishnan Ramasamy | 46636 | MCS - POS - Optimization - Cache all cafeteria permissions from a single reader query during login | Inprogress | 3

## Checklist (hidden)
Code Review Comments received from Client for 2.5 Sprint |  | S No | Execution Steps | Status
1 | index.tsx /AugustWeb/Features/ContactMaintenance/Components/index.tsx Search doesn't work on the details page. Please remove the search component from the header. | 1 | Code conflict | FALSE
2 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs If the admin doesn't set up any of the new options, then the system rejects every registration. | 2 | Coding Standard | FALSE
3 | PickEnrollmentPlanView.tsx /ParentWeb/ClientApp/src/pages/Registration/PickEnrollmentPlanView.tsx This should be filtered before this ternary statement so the "No enrollment plans" message could be shown if all plans are at capacity and closed. | 3 | Existing Functionality | FALSE
4 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs Could we add a TermEnrollmentPlanId query parameter and query for it directly instead of pulling all the plans for the term? | 4 | Acceptance Criteria coverage | FALSE
|  | 5 | Code execute | FALSE
|  | 6 | Code Performance | FALSE
|  | 7 | Code cleanup | FALSE
|  | 8 | Understandable code comments | FALSE

## Details
Root Cause category
Enhancements
Existing_Issues
Requirements
QA
Design
Documentation
Development
Project_Management
Environment_Related

## Settings
Story Completed
Story Being Tested
Story Ready For Testing
Story Peer Review
Product Owner - Verify
Story Being Developed
Story Approved
Defect Found
Defect Verified
Defect Being Fixed
Defect Peer Review
Product Owner - Verify
Defect Ready For Testing
Defect Being Tested
Defect Fixed
Defect Rejected
Defect Needs More Info
Defect Blocked