## Dashboard
Current Sprint | 26.6 Sprint S1 | Current Sprint Sheet | 26.6 Sprint S1-Status | Sprint Start Date | 2026-05-06 | Sprint End Date | 2026-05-19 | Application Name | MSB Activities | Users | allen.xavier@relevantz.com;kanchanamala.umakanthan@relevantz.com;manjunathan.dharman@relevantz.com;athinarayanan.ramar@relevantz.com;ramprabu.sakthivel@relevantz.com | Teams Name(GP- MSB Activities) | 19:1e38c92221534f43aaff617f2f44a82e@thread.v2
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story points introduced/removed | Sprint Summary | Accomplishments | Remarks | Client Appreciations | Retro Points (Internal & External) | Unplanned Leaves | Data sanity Audit Status | AuditDate | Backlog Health
#REF! | 2.9 Sprint S1 | 2024-01-03 | 2024-01-16 | 9 (47 sp - assigned) | 9 - Development completed 4 - Testing completed 2 - Testing in progress 3 - Peer review (23 sp - completed) |  |  |  | 42924, 42923, 42989 - Story peer review, 22646, 37677, 22653, 22655 - Testing completed , 22642, 42917 - Testing in progress. |  | Internal: External:
#REF! | 2.9 Sprint S2 | 2024-01-17 | 2024-01-30 | 5 (31 sp - assigned) | 4 - Testing completed [22682, 22676, 22657,43155] 2 - defect/story carried from last sprint for testing [22642, 42917] - Testing Completed (19 sp - completed) |  |  |  | 2 - client peer review [42924, 42923], 2 - Testing [22642, 42917] - Carried from last sprint [2.9 sprint s1] 5 - Development [22682, 22676, 22657,43155, 43149- timeboxed] - Current sprint [2.9 sprint s2] |  | Internal: External:
#REF! | 2.9 Sprint S3 | 2024-01-31 | 2024-02-13 | 9 (31 sp - assigned) | Development completed (8) -22756, 43550, 43336,43335,43334,43388, 43536,43486 Development inprogress -42874 |  |  |  | 2 - Testing pending [42924, 42923], 1- stretch [ 43313 ] - Testing pending - Carried from last sprint [2.9 sprint s2] Total 9 - [43334 (Main -1), [Stretch -22756, 43486, 43336,43335,43550,43388, 42874,43536=8] This Regressin sprint,team worked on stretch stories |  | Internal: External:
#REF! | 2.9.5 Sprint S1 | 2024-02-14 | 2024-02-27 | 5 Total - 46 Sp (7+5) | 21 Sp | 2 sp |  |  | Carried from last sprint for client Peer review and Testing: 43633,22756,43550,43586,43335,43336,43486 = 7 Current Sprint stories assigned Main :42874,43531,43659; Stretch: 43629,43582 Total:5 Introduced story in stretch - 43208 |  | Internal: External:
#REF! | 2.9.5 Sprint S2 | 2024-02-28 | 2024-03-12 | 9 [50 Sp] | 53 sp |  |  |  | Carried from last sprint for client Peer review and Testing: =3 Current Sprint stories assigned Main and stretch : 9 Total: 9+3 = 12 |  | Internal: External:
#REF! | 2.9.5 Sprint S3 | 2024-03-13 | 2024-03-26 | 7 [ 33 Sp] | 26.5 Sp |  |  |  | Regression Sprint |  | Internal: External:
#REF! | 3.0 Sprint S1 | 2024-03-27 | 2024-04-09 | 14 | 9 |  |  |  | One of the offshore developer is on planned leave for the entire Sprint. Development completed for all 4 committed stories. (3 - Closed, 1 - Client POV pending) Development completed for 3 out of 4 stretch stories. (3 - PR approval pending from client, 1 - Development in progress) |  | Internal: External:
#REF! | 3.0 Sprint S2 | 2024-04-10 | 2024-04-23 | 9 [37 Sp] | 22 Sp |  |  |  | 2 development story 1 Automation and 6 - testing =9 |  | Internal: External:
#REF! | 3.0 Sprint S3 | 2024-04-24 | 2024-05-07 | 31 sp | 31 Sp |  |  |  | Regression Sprint |  | Internal: External:
#REF! | 3.1 Sprint S1 | 2024-05-08 | 2024-05-21 | 29 Sp | 16 Sp | [5 empty] | Internal: External:
#REF! | 3.1 Sprint S2 | 2024-05-22 | 2024-06-04 | 23 Sp | 23 Sp |  |  |  | Testing will be covered in next sprint for 3 stories. |  | Internal: External:
#REF! | 3.1 Sprint S3 | 2024-06-05 | 2024-06-18 | 29 Sp | 29 Sp |  |  |  | Regression Sprint |  | Internal: External:
#REF! | 3.2 Sprint S1 | 2024-06-19 | 2024-07-02 | 30 Sp | 14 sp | [5 empty] | Internal: External:
#REF! | 3.2 Sprint S2 | 2024-07-03 | 2024-07-16 | 26 Sp | 26 Sp |  |  |  | Completed all committed stories with testing and 45114 and 45203 took more efforts than the initial estimation in closing out along with testing. | 3.2 Sprint S2 Retro Appreciation : Assignees: Kristy MacCheyne - Client PO Kudos to everyone on the team. This was an awesome sprint. Allen - Leadership ensuring the team is all on the same page working toward our goals, helping out with getting stories completed to make 3.2 even better. His research for upcoming efforts and suggestions for how to best handle everything. Hari - Always extremely grateful for all of Hari's efforts. I can always trust that anything Hari takes on will be great. Kanchana - Kanchana continuously does an incredible job in this role ensuring we are all communicating effectively and that if/when there are questions we are able to discuss them to get on the same page. Her efforts to ensure we have stories written up for Refinements based on prioritized efforts is greatly appreciated. I also appreciate her collaboration with my new Business Analyst for my other team, Kanchana models how helpful her role can be to Product Management and I appreciate her willingness to provide guidance to my other team's BA. Kaliammal - Great work on wrapping up her first stories since getting access figured out. Manjunathan - Attention to detail and catching impressive finds while testing stories (ie: the final bounceback on 44444), ensuring testing wrapped up on everything heading into Planning for Regression. | Internal: External:
#REF! | 3.2 Sprint S3 | 2024-07-17 | 2024-07-30 | 29 Sp | 29 Sp | 14 |  |  | Regression Sprint |  | Internal: External:
#REF! | 3.3 Sprint S1 | 2024-07-31 | 2024-08-13 | 24 Sp | 24 |  |  |  |  | 3.3 Sprint S1 Retro Appreciation : Assignees: Kristy MacCheyne - Client PO Manjunathan - Did a great job at staying on top of the large testing effort we had for Sprint 1. Manjunathan and Jeff both made this sprint look easy despite a lot of work being on their shoulders. Kaliammal - Kaliammal is doing a great job getting up to speed, she did great work on the No Cost Retainer Fee story. Hari - Thank you Hari for always doing an exceptional job with whatever story you take on. You are always ready to take on stories/epics for our Release Goals and I really appreciate it. Kanchana - I appreciate all of Kanchana's efforts. She does an exceptional job in this role and allows me to jump back and forth between teams and spend time supporting my other team when they had escalations coming up. Kanchana is always extremely thoughtful, detail oriented, and a true team player Allen - Thank you for your incredible ideas and suggestions for approach, Allen really helped me ahead of our last Planning meeting to ensure we were setting QA up for success with a large number of stories ready for testing. Allen's leadership is always greatly appreciated. . | Internal: External:
#REF! | 3.3 Sprint S2 | 2024-08-14 | 2024-08-27 | 32 Sp | 19 Sp |  |  |  | Completed most of the committed stories with one story 45116 in QA which will be carry forwarded to next sprint for QA. |  | Internal: External:
#REF! | 3.3 Sprint S3 | 2024-08-28 | 2024-09-10 | 21 Sp | 19 Sp |  |  |  | 23905, 44143 - Client moved to next release 10-Sep-2024 Peer CRC: 0 Onsite CRC: 0 Client CRC: 2 Internal Defects: 5 External Defects: 1 |  |  |  | Completed
#REF! | 3.4 Sprint S1 | 2024-09-11 | 2024-09-24 | 23 Sp | 23 Sp | 18 Sp |  |  | 24-Sep-2024 Peer CRC: 0 Onsite CRC: 0 Client CRC: 1 Internal Defects: 2 External Defects: 0 |  |  |  | Completed
#REF! | 3.4 Sprint S2 | 2024-09-25 | 2024-10-08 | 22 Sp | 21 Sp |  |  |  | 09-Oct-2024 Peer CRC: 2 Onsite CRC: 0 Client CRC: 2 Internal Defects: 3 External Defects: 0
#REF! | 3.4 Sprint S3 | 2024-10-09 | 2024-10-22 | 14 Sp | 22 Sp | Introduced - 8 |  |  | Regression Sprint 23-Oct-2024 Peer CRC: 0 Onsite CRC: 1 Client CRC: 0 Internal Defects: 0 External Defects: 0
#REF! | 3.5 Sprint S1 | 2024-10-23 | 2024-11-05 | 24 Sp | 11 Sp |  |  | Completed 46329 - Bulk Copy Enrollment Common component creation which is pre-requisite for two other stories | Reason for not Completing the Story Points --- 46323 - Testing not completed due to PTO of both offshore and client QA 46336 - PR delayed due to existing issues in related component Regression Sprint 46355 - Timebox story 46032 - Stretch story Peer CRC: 0 Onsite CRC: 1 Client CRC: 0 Internal Defects: 0 External Defects: 0 | Client PO Appreciations for the team : Kanchana - Partnering with Kanchana also brings me joy - she has a desire to learn, grow, and take on whatever task comes up. She inspires me with her organization skills and attention to detail and helps make everything much smoother and easier for me (and the team)! Hari - I appreciate your thoroughness, great questions, and agility. You're always ready to take on challenging efforts. Kaliammal - I appreciate that you are always ready to take on whatever story/defect requires attention. You're a great addition to our team! Manjunathan - I appreciate seeing your growth on this team! Your attention to detail and thoughtfulness in testing is really appreciated as well! Jeff always speaks highly of you and both of you collaborating on testing efforts! Allen - I appreciate your dedication, steadiness, and thoughtful approach to solving problems. You always have great ideas, and it helps with each effort we take on (especially ones that have been hanging out in the backlog without a clear path for us).
#REF! | 3.5 Sprint S2 | 2024-11-06 | 2024-11-19 | 29 | 37 | Story points introduced in the mid of the sprint : 46499 -3sp 46511 - 5sp 46557 - 8 sp Defect points introduced : 24286 - 1sp 24301 - 1sp Total Introduced - 18 Total Completed - 8 |  | Completed Enrollment Plans - Selected Actions Bulk Edit (Seminole) and Capacity Report - Dropdown Tree for Activity and EP Filters (Seminole) | Peer CRC: 0 Onsite CRC: 0 Client CRC: 0 Internal Defects: 2 External Defects: 1 (Production Issue - Minor) | Excellent communication skills, frequent check-ins, excellent collaboration, and always working to build an environment where we can share ideas to work towards common goals! The great discussions, sharing of ideas, collaboration, and identifying new paths to solve problems that have left us stuck in the past. Hearing positivity from internal stakeholders and customers (and then sharing with the team) about how our work has helped product growth and quality of life.
#REF! | 3.5 Sprint S3 | 2024-11-20 | 2024-12-03 | 21 Sp | 39 sp | Stories Introduced Introduced - 5sp Defects Introduced Introduced - 3sp Total Introduced - 8 Total Completed - 8 |  | 1.Completed Enrollment Plan Maintenance - Limit number for Selected Actions & Config Prop, 2.Capacity Report - Total "All Enrollment Plans" count in Excel Output Format, 3.Attendance Report - Group By Grade, 4.Update "Description" to Item Name [UI Labels Only](PR & QA) | Peer CRC: 1 Onsite CRC:1 Client CRC: 2 Internal Defects: 6 External Defects: 0 | The team continues to do a great job and accomplish everything they set out to do despite any disruptions. This sprint we had a ton of Client PTO and difficult timing to work around and the team still managed to close out the commit and make some progress in the stretch despite all of that. It's exciting to see the team continuing to knock it out of the park. I’m just so proud of this team! Keep up the great work!
#REF! | 3.5 Sprint S4 | 2024-12-04 | 2025-01-02 | 24 | 55 | Total Introduced: 31 |  | 1.Completed the development work for React conversion stories for Users, Home page and District level. 2.Completed the development work for Enrollment Plan/Activity - Update "Description" to Item Name in SQL Tables (SYSTEM). 3. Completed the development work for Spilt billing audit log and Term Capture Attendance Calendar modifications in Audit Log | Peer CRC: 6 Onsite CRC:0 Client CRC: 0 Internal Defects: 7 External Defects: 0 | Keep up the great work and continue efforts we started in 3.5 Sprint 4 (with the intention of holding for 3.6)
#REF! | 3.6 Sprint S1 | 2025-01-03 | 2025-01-14 | 14 | 32 |  |  | 1.Modified the common component Date Selector to Display as an Expanded Calendar Overlay 2.Fixed production defect regarding the billing Prepaid Billing Used Instead of Drop In - Logic defect fixed 3.Admin Home Page has been converted to react 4.Students page to Server Side sorting | Few Stories are moved to 3.7 that Contains DataBase Column Name Changes - Slated for 3.7 release. One Story is On hold by Client QA Peer CRC: 1 Onsite CRC:1 Client CRC: 1 Internal Defects: 2 External Defects: 2
#REF! | 3.6 Sprint S2 | 2025-01-15 | 2025-01-28 | 43 | 50 | Introduced - 10 |  | 1.Completion of District level view of Open Operating Days 2.Completion of React conversion for Tenant and Heartland Staff users 3.Fixed Production defect regarding Operating day checkout errors 4.Updated Enrollment Plan - Update "Required Forms" page with Sorting and Pagination. 5 Updated the.MSB Invoice Profile - Remove filter by Provider for GL Codes | Peer CRC: 0 Onsite CRC:0 Client CRC: 2 Internal Defects: 7 External Defects: 2 | Feedback from Beth Boyack, Payments Account Specialist after using this for the first time: "Hey! I'm using the copy enrollment plan for the first time. Yay!! Definitely helps!" & "I was only copying 4 plans and the performance was good, no lag or anything". Great feedback on the new Selected Actions effort! | Kristy MacCheyne Product Manager - MSB Activities & MSB Tickets - "I think we have great commitment to our team, as well as to our sprint goals. If we are struggling on one story/defect, we communicate with each other and identify a path forward. I think the strong individual commitment to the sprint is a side effect of our commitment to our team and collective goals."
#REF! | 3.6 Sprint S3 | 2025-01-29 | 2025-02-11 | 20 | 31 |  |  | 1.Completed Filter By Registration status for Custom Registration with highlighting updated fields for Updated Registrations 2.Completion of Performance improvement to reduce the time taken to copy large number of Enrollment plans which required Framework level changes. 3.Completed converting Description Table column to Name for SecurityGroup, Kiosk, District, Custom Fields and Dynamic Report 4.Fixed existing production defect in Custom Registration Report | Peer CRC: 0 Onsite CRC:1 Client CRC: 0 Internal Defects: 7 External Defects:1 |  | Kristy MacCheyne Product Manager - MSB Activities & MSB Tickets - "The team did an excellent job at working through Regression testing, identifying and resolving defects, making progress on some Performance Improvements, updating description to item names in SQL tables, Automation, and had some great discussions for some upcoming larger efforts. I think we also have been doing a great job at communicating and relaying concerns/needs to re-estimate certain efforts as we learn more and have been able to reforecast as needed to ensure we are capturing as much of the full picture of these efforts as we can.Also, we are seeing things pick up on the sales side for Activities and I have been working closely with the new dedicated sales rep for Activities (Ed), we are partnering for an upcoming webinar that I am really excited about."
#REF! | 3.7 Sprint S1 | 2025-02-12 | 2025-02-25 | 23 | 37 | Introduced - 5 Removed - 8 |  | 1.Completed Customizable column headers for the Datatable in Parent Accounts. 2.Completed Description change to Item Name for Activity, Enrollment plan, Security Group, Kiosk and District Maintenance. 3.Development completed to Improve performance for Bulk edit of Enrollment plans. | Peer CRC: 0 Onsite CRC:0 Client CRC: 2 Internal Defects:2 External Defects:1 | Feedback from Ramsey Whitley, Implementation Coordinator Ramsey's comment was towards the customizable parent table column headers in the sprint demo review, like this is a wonderful feature. | Kristy MacCheyne Product Manager - MSB Activities & MSB Tickets - Dedication, determination, and collaboration from the team! We had some great discussions to ensure we are all on the same page. We also got some really great new features added this Sprint. I loved Hari's approach for displaying Students in the Student column (Customizable Columns for Parents). Shoutout to Andy for his patience and determination as we made various changes to the District view of Terms. Jeff and Manjunathan did a great job at getting things over the finish line this sprint. Brian Newby, Senior Manager, Software Development Mentioned: "The team is communicating well and doing great work".
#REF! | 3.7 Sprint S2 | 2025-02-26 | 2025-03-11 | 23 | 38 | Introduced - 7 |  | 1.Completed the Other Contacts Customizable column Header. 2.Completed updating Setup icons, text position, order for tiles and, page headers. 3.Completed the Custom Registration Report - Include Student Number for Output Format. 4.Completed Description change to Item Name for Term and Site. 5.Completed the Performance Improvements for Enrollment Plan for Bulk Edit. 6. Fixed existing PROD defects. | Peer CRC: 0 Onsite CRC:1 Client CRC:5 Internal Defects:2 External Defects:3 | Feedback from Beth Boyack, Payments Account Specialist "OMG I just used the Dynamic Report Generator for Updated Student Counts and it's AMAZING!! I don't think I can thank you enough for this!" Feedback from Kristy MacCheyne Product Manager - MSB Activities & MSB Tickets @Allen Xavier : all the time you have spent on the dynamic report generator is paying off! | Kristy MacCheyne Product Manager - MSB Activities & MSB Tickets - I think the number 1 thing we do that we do well/should continue doing is communicating with each other. This team does an exceptional job at communicating progress, challenges, etc. I think the team's collaborative approach helps ensure we are successful each sprint - we discuss problems/challenges as a team, share ideas to fix/improve, and work together each step of the way to make it happen. I find the discussions with the team the most fulfilling for my day to day.
#REF! | 3.7 Sprint S3 | 2025-03-12 | 2025-03-25 | 15 | 25 |  |  | 1.Completed Research for Split billing improvements to upload invoices by MSB UserId 2.Development completion of Next set of Description changes for Fees,FormTypes,Discounts,Custom Fields and Dynamic Report. 3.Development completion of enhancement in the Datatable to show total Entries | Peer CRC: 0 Onsite CRC:0 Client CRC:1 Internal Defects:0 External Defects:0
#REF! | 3.8 Sprint S1 | 2025-03-26 | 2025-04-08 | 36 | 28 |  |  | 1.Development completion of Split billing improvements to invoice by MSB User ID 2.UI Enhancement - Ability to select multiple fields of Student, Parent and Contact fields in Enrollment plan 3.Reports - Improve Student Filter Multi-Select dropdowns | Peer CRC: 5 Onsite CRC:1 Client CRC:0 Internal Defects:3 External Defects:0 | Feedback from Kristy MacCheyne about the team Product Manager - MSB Activities & MSB Tickets Ganapathi Sent: Hello team, I just got off a call with Kristy where in she was so happy with the team's transformation and progress. I've no words to express the excitement that she expressed talking about everyone on the team under Allen's leadership. Kudos to your hardwork and commitment | Kristy MacCheyne: Product Manager - MSB Activities & MSB Tickets Kanchana's attention to detail always helps us be prepared. I also think our Refinements and discussions at standups helped us keep momentum. I also think that the new process for Pendo guides worked well this sprint. Jeff Dean - QA Team collaboration is always a great line for success with this team. Each strand in our team does great work in completing and making sure we are successful.
#REF! | 3.8 Sprint S2 | 2025-04-09 | 2025-04-22 | 29 | 27 | Introduced - 22 |  | 1.Student Filter Improvements in Report 2.Enhancement in Field Selection in EnrollmentPlan 3.Split Billing Updates 4.Tile Icon updates in Registration Page 5.New SearchableSelect Component creation to be reused across the application | Peer CRC: 2 Onsite CRC:0 Client CRC:2 Internal Defects:0 External Defects:2 |  | Kristy MacCheyne: Product Manager - MSB Activities & MSB Tickets Kudos to the entire team! Everyone did really great work this sprint from Allen cruising through the split billing story, Hari providing great ideas for UI and calling out scenarios we may not think of, Kaliammal also did great work and showcased that getting quick feedback during POVs in 2nd rounds. Manjunathan did a great job working with Jeff to get through a LOT of testing efforts, Kanchana always does a fantastic job at supporting the team, her attention to detail is great - catching some defects that we have been able to fix before anyone notices, and keeping things moving.
#REF! | 3.8 Sprint S3 | 2025-04-23 | 2025-05-06 | 9 | 19 | 16 |  | 1.Completed Regression testing with no regression defect 2.Completed Research to display Split billing invoices under purchases 3.Completed Research on tracking split billing changes in Audit log 4.Completed Research on Custom registration report to support multiple enrollmentplans | Peer CRC: 2 Onsite CRC:1 Client CRC:1 Internal Defects:0 External Defects:0 | NIL | NIL
#REF! | 3.9 Sprint S1 | 2025-05-07 | 2025-05-20 | 26 | 23 | 9 |  | Conversion of Auditlog view into a Grid with search,sort and customisable column header functionality, Improvements in Add tenant Page, Split Billing settings which was displayed as a Popup/Modal has been converted in to a separate page for ease of access. | Peer CRC: 1 Onsite CRC:1 Client CRC:2 Internal Defects:4 External Defects:0 | We have implemented the existing audit log in a table grid format for student maintenance. Feedback from Jeff Dean - QA This makes me happy: I'm sure our support members will LOVE it as much as I am, if not more! makes it SO MUCH easier to find information Feedback from Brian Newby:Senior Manager Good stuff. Sometimes its hard to step back and see the impact that our work is having. Thanks for all you you guys do. | Kristy MacCheyne: Product Manager - MSB Activities & MSB Tickets We made great progress on updating the display of audit logging for student maintenance - the new grid view looks great! We also made excellent progress on split billing updates for audit logging, displaying split billing as a separate tab from the Student record (instead of needing to drill into editing the student details to find the split billing setup), improving and expediting the add district/tenant process, automation, and tech debt. Overall, it was a great sprint for the team with great communication. Excellent communication, trust, determination, and Kanchana 😂 (I don’t think I need to say much more than her name - she helps lock in on our goal and help guide everyone forward).
#REF! | 3.9 Sprint S2 | 2025-05-21 | 2025-06-03 | 24 | 29 | Introduced - 20 |  | 1.Inclusion of Splitbilling invoices in Purchases, 2.Relocation of Splitbilling settings to a separate tab with readonly and edit view 3.Additional fields in Tenant Add/Edit page | Peer CRC: 5 Onsite CRC:0 Client CRC:0 Internal Defects:3 External Defects:3 | NIL | Jeff Dean - QA Analyst: Manjunathan and Kanchana’s attention to detail, Allens willingness to go above and beyond (and check in late at night lol). Being ourselves. Kristy MacCheyne: : Product Manager - MSB Activities & MSB Tickets The team is always great at working together and providing support in whatever area needs it most. This sprint I had to take some unexpected time off for my health and the team did a great job at filling in and keeping everything moving in the right direction. Shout out to Kanchana!
#REF! | 3.9 Sprint S3 | 2025-06-04 | 2025-06-17 | 32 | 52 | Introduced - 20 |  | 1.Regression went well. 2.Fixed Regression Split Billing Defects. 3.Completed People - Update Icons and Tile Layout 4.Split Billing Audit Log changes and UI Changes. 5.Converted Tile layout pages, Admin Header & Left Navigation Menu to React. 6.Good Progress on Vega UI updates on Admin Header and Left Navigation Menu 7.Completed few discovery stories like Notification Hub & Registration - Specific URLs 8.Conversion of Functional Components | Peer CRC:0 Onsite CRC:0 Client CRC:0 Internal Defects:2 External Defects:2 | NIL | Kristy MacCheyne: : Product Manager - MSB Activities & MSB Tickets The team had some great conversations this sprint during standups, refinement, and planning prep calls. The team also made great progress on converting the admin header and left nav to React, and getting a start on implementing the new vega components with the new designs (exceeded my expectations for where I thought we would be)! The team also did a great job with regression (as usual). The team has done a great job at focusing on what is within our control though, and providing great feedback to help make the designs better for everyone (not just our team). Shoutout to Allen for his attention to detail/eye for the customer UX in pointing out risks with the District/Site dropdown placement within the new design.Shoutout to Kanchana for her great ideas of upcoming improvements to the Parent UX.
#REF! | 4.0 Sprint S1 | 2025-06-18 | 2025-07-01 | 13 | 13 | Introduced - 5 |  | 1. Completed development for Multi Selection Enrollment Plan Filter in Custom Registration Report. 2. Completed Split Billing - Partial Invoice Upload Failures 3. Completed updating Tile Layout Pages to React 4. Added a new "State" column in Districts maintenance table grid page. | Peer CRC:2 Onsite CRC:0 Client CRC:1 Internal Defects:0 External Defects:0 | NIL | Brian Newby: Senior Manager, Software Development Making progress on Azure AD group and Notification Hub integration. Vega stuff looks good. Kristy MacCheyne: Product Manager - MSB Activities & MSB Tickets Great progress on the Kaleida designs, worked together as a team to identify the best path forward for our District/Site selector (despite it being different from the initial designs, I feel that we are making the right decision and the design team and platform PM are aligned on our approach.
#REF! | 4.0 Sprint S2 | 2025-07-02 | 2025-07-15 | 15 | 17 | Introduced -2 |  | 1. Implemented Multi Selection Enrollment Plan Filter in Custom Registration Report. 2. Completed Setup Tile Reorder. 3. Completed URL Update for react converted page. 4. Completed Retain Historical Split Billing Invoice By Value. | Peer CRC:0 Onsite CRC:0 Client CRC:2 Internal Defects:2 External Defects:0 | Joe: Sr. Product Specialist for MealViewer, MSB Activities & Tickets Mentioned in the Sprint Review Demo: I just want to add that you ALL do great work. | Jeff Dean - QA Analyst : Manjunathan and Siva did great work vetting our new features, so much so that I got to do some dev work! "Kristy MacCheyne: Product Manager - MSB Activities & MSB Tickets The team wrapped up everything in the main commit and made great progress in stretch. It was a great team effort towards the end of the sprint getting everything closed out. Shout out to Kanchana for taking on more ownership of enhancement requests from internal stakeholders! Also shout out to the whole team for the collaborative and platform centric energy brought to the table for the Kaleida efforts - great questions, concerns, and suggestions have been brought up that I think have helped guide the design process for the entire platform. And us keeping an eye on progress in MSB and Meal Orders has helped keep us aligned and even helped identify defects for others"
#REF! | 4.0 Sprint S3 | 2025-07-16 | 2025-07-29 | 16 | 11 | Introduced -1 |  | 1.Completed the development of converting the CSHTML pages to React a) Record-Not-Found b) Tenant mismatch c) Site mismatch 2.Removed unused CSHTML pages. 3.Completed the enhancement of adding MSB District ID to Job Request Queue page. 4.Good progress on implementing the Integrating Notification Hub to MSB Activities. 5.Completion of Regression Testing within the sprint. | Peer CRC:0 Onsite CRC:0 Client CRC:0 Internal Defects:0 External Defects:0 Note: Story# 48830 Activities - Integrating Notification Hub to MSB Activities [4.1] - Development Completed and the story is carried to next sprint for PR & QA. | NIL | Received retro appreciations from each team member from - Kristy MacCheyne Product Manager - MSB Activities & MSB Tickets: Kanchana (always Kanchana deserving a shoutout for all she does!) for her dedication to supporting the team, asking great questions, and being an expert at juggling whenever we find ourselves in that position. Manjunathan did an incredible job this entire release but definitely this sprint. Allen - doing an incredible job at juggling everything, getting our newer team members up to speed, and still finding time to make progress towards our goals Kaliammal - Making sure we are making great progress towards BAU efforts while we take on Kaleida updates. Sivaraja - Doing a great job getting up to speed!
#REF! | 4.1 Sprint S1 | 2025-07-30 | 2025-08-12 | 20 | 17 | Introduced-0 | Discovery for Site Registration URL, Implemented View All[Registrations] page to Server Side sorting, Converting the CSHTML pages to React (Records not found, Tenant and Site mismatch), Integrating Notification Hub for Parent Admin. | 1. Completed View All[Registrations] page to Server Side sorting. 2. Completed converting the CSHTML pages to React. 3. Completed converting the Record-Not-FoundL pages to React. 4. Completed converting the Tenant mismatch pages to React. 5. Completed converting the Site mismatch pages to React. 6. Completed the analysis of Site Registrations URL (discovery). 7. Defect fixes and bouncebacks fixed. | Peer CRC:2 Onsite CRC:0 Client CRC:1 Internal Defects:4 External Defects:1 Note: Story# 48830 Activities - Parent- Integrating Notification Hub to MSB Activities [4.1] - Reason :Story carried to next sprint for testing.The notification hub story was carried over to the next sprint to allow for integration with the existing email template, thorough testing in the development environment to ensure compatibility with our NuGet package, and to address additional peer and PR reviews.This approach ensures seamless integration and robust unit test coverage. |  | Good Sprint and appreciated the team for great communication and collaboration.
#REF! | 4.1 Sprint S2 | 2025-08-13 | 2025-08-26 | 18 | 14 | Introduced- 4 | 4.1 Sprint 2 delivered key outcomes, including defect resolutions for student selection in Reports and fees icon alignment in Admin Accounting. The team completed integration of the Notification Hub for both Parent and Admin users, enhanced the Site Home Page user experience, and advanced the Site Registrations URL update through peer review. Progress also continued on the Job Request Queue Tree component and improvements to the Admin Reports multiselect functionality. | 1. Resolved the issue where unselected students were being chosen from the student dropdown list in Reports. 2. Completed integration of the Notification Hub with MSB Activities for Parent users. 3. Fixed the vertical scroll bar on the Site Home Page to enhance user experience. 4. Completed integration of the Notification Hub with MSB Activities for Admin users. 5. Corrected the fees icon mismatch in the page header of the Fees Page in Admin Accounting. 6. Completed the development of Site Registrations URL. | Peer CRC:0 Onsite CRC:0 Client CRC:1 Internal Defects:0 External Defects:3 Note: Story# 49407-"Site Registration Url" development has been completed, and the story is carried to the next sprint by client for client code review. The client team mentioned that this will not be part of this release 4.1 and will be pushed to the 4.2 release for QA efforts. | Nil | What slowed us down or caused friction this sprint? Jeff Dean - QA: Didn’t have the best communication this sprint and Perhaps we prioritized incorrectly, underestimated, upon further review we realized our approach changed. Andy Ritzman - Developer-We had a few stories that were underestimated in this sprint. I think in some cases like the Site URLs and React conversion they just ended up having more complexity than we expected. In the case of the NotificationHub integration we adjusted our approach mid sprint, which I believe was the right call but it slowed us down a bit. We also estimated the stories for just the work to tie the new library into activities without considering this was the first real review of the new library and it may need updating as well. Kristy MacCheyne-Product Manager- There were some things that came up that caused us to change our approach for the NH stories, additional fixes needed for the update admin login page to react, and the Site Registrations URL effort potentially being larger than anticipated. I think the team did a great job at communicating the concerns, we then prioritized discussion and getting on the same page about each main commit item at refinement, and worked together to reset/refocus. I think the team did a great job at figuring out how we should pivot to make sure we are focusing on the right things with the remaining time left in the sprint.
#REF! | 4.1 Sprint S3 | 2025-08-27 | 2025-09-09 | 11 | 11 | Introduced - 0 | 4.1 Sprint 3 delivered key outcomes, including regression testing went well, completed the development of the job request queue page changes, and Multi-student component selection Defect. | 1. Completed Regression Sprint. 2. Completed development and unit testing for the Job Request Queue screen with features below. a)Multi selection dropdown for Districts, and Request Kind b)Pagination, Sorting and Search c)New filter for Status | Peer CRC:5 Onsite CRC:0 Client CRC:0 Internal Defects:1 External Defects:0 Note: Defect has been blocked by Client # :25807, 25853, 25859 Three defects are currently blocked because multiple issues exist in the same component, which impact component selection. Fixing one defect causes another to appear. As comprehensive unit testing is required for all scenarios, we have decided to revamp the component. Therefore, this defect will remain blocked in the current sprint, and a new story will be created for the new implementation in the next sprint. | NIL | Andy Ritzman - Developer Kristy MacCheyne-Product Manager Finished regression without major findings. Finding additional issues with the tree component (and planned to have a separate story to address those defects - its a good approach), and we made strategic decisions while completing regression and worked on research/discovery.
#REF! | 4.2 Sprint S1 | 2025-09-10 | 2025-09-23 | 9 | 9 | Introduced - 0 | 4.2 Sprint 1 delivered key outcomes, including the completion of Site-Registrations URL feature for New-Parent flow, enhanced the Job Request Queue page and fixed bounce back for SiteRegistration URL and Job Request Queue screen. | 1. Completed the feature Site-Registrations URL for New-Parent flow. 2. Enhanced the Job Request Queue Page for the HSS Users. 3. Completed fixing the Bounce back for Site-Registrations URL and Job Request Queue. | Peer CRC:1 Onsite CRC:0 Client CRC:0 Internal Defects:4 External Defects:0 | NIL | Jeff Dean - QA Closed out the main commit, Was able to integrate our notifications into notification hub. Great steps with the Site URL stories to eventually get us to a point that anyone can be registered for an activity.
#REF! | 4.2 Sprint S2 | 2025-09-24 | 2025-10-07 | 8 | 6 | Introduced - 0 | 4.2 Sprint 2 delivered key outcomes, the analysis was completed for new term Enrollment-registration-url changes. | 1. Completed development for the issues in the Multi-Tree component Search & Selection. 2. Analyzed the changes for the new' Term Enrollment-registration-url' | Peer CRC:0 Onsite CRC:0 Client CRC:0 Internal Defects:0 External Defects:0 Note:This Story # 49964 Activities - Reports - Multi Tree Select Component (Search & Selection) - Development is completed and unit testing in-progress and carried to next sprint for [PR ,POV and QA] and focused for 4.3 release. Reason: Initially, we attempted multi-student to handle it with the common tree select component, but it wasn't feasible, so we moved it to separate component. This approach took a lot of effort and additional time. Unit testing also required time to validate multiple scenarios. | NIL | Team took a step back to review big picture, found several issues early on, created Stories,fixed all initial issues. Team then discovered prod issues as part of Stories (existing issues)
#REF! | 4.2 Sprint S3 | 2025-10-08 | 2025-10-21 | 10 | 11 | Introduced - 9 | 4.2 Sprint 3 delivered key outcomes, the analysis and inital development is completed for Term-Enrollment plan registrations url changes. Multi Tree component issues are fixed. Also an issue sprlit billing is fixed. Initial development is completed to handle the error scenarios in Site-Registrations url. Changes made in to Districts page to hide the Advanced tools button for Customer support role. | 1.Initial development is completed for Term Enrollment Registrations url. 2.Multi Tree Select - component changes are completed. | Peer CRC:0 Onsite CRC:0 Client CRC:1 Internal Defects:0 External Defects:0
#REF! | 4.3 Sprint S1 | 2025-10-22 | 2025-11-04 | 20 | 22 | Introduced - 2 | 4.3 sprint 1 Implemented new verbiage for Parent Term Enrollment Plan URLs and addressed related registration scenarios.Resolved server errors in admin search functionality caused by special character inputs.Completed quality assurance for the Multi Tree Select Component in Reports (v4.3). Enhanced user access by updating district and parent views, including advanced tool restrictions and role-based button visibility for HSS Customer Support. | 1.Integrated new verbiage for Parent Term Enrollment Plan URLs. 2.Resolved server errors caused by special characters in admin search criteria. 3.Completed QA for Multi Tree Select Component in Reports (v4.3). 4.Addressed registration and site URL issues for inactive sites, sites without EPs, and Term Enrollment Plan URLs. 5.Updated district and parent views to hide advanced tools and restricted 'Add'/'Edit' buttons for HSS Customer Support roles. | Peer CRC:8 Onsite CRC:1 Client CRC:4 Internal Defects:0 External Defects:0 |  | Kristy MacCheyne-Product Manager Really strong first sprint of the release completing almost everything in the main, and a bunch in stretch. We wrapped up a couple of efforts that we have been working on for a while (multi-tree select component fixes, term EP URL, and are very close to being wrapped up with the admin manual registration for the non student/guest registration work!). 4.2 is live. Shoutouts Everyone. Kanchana’s efforts to ensure the team is supported. Allen’s guidance and forward thinking with efforts he takes on with the team. Everyone who worked on documents for discovery stories. QA for staying on top of everything as we closed out a ton of stories this sprint.
#REF! | 4.3 Sprint S2 | 2025-11-05 | 2025-11-18 | 15 | 18 | Introduced - 4 | In 4.3 sprint 2, The team successfully delivered all planned work items plus two additional stretch goals, demonstrating strong execution and exceptional productivity throughout the sprint. Additionally, the team proactively addressed external defects and peer review comments, maintaining high quality standards. Enhanced the Enrollments screen with improved error prevention of payment method ,added 'Actions' Dropdown in Term Maintenance for Activities & Enrollment Plan Tab, upgraded the Audit Log to a table grid for Form Types, and resolved issues with prompt closure and manual registration errors. Stretch Stories Completion The team exceeded sprint goals by successfully delivering stretch stories which are development is completed: 1.Enrollment plan field validation 2.Discovery story for Term Enrollment plan capacity. | 1. Implemented prevention of Payment Method errors on the Enrollments screen. 2. Added a new feature 'Actions' Dropdown in Term Maintenance for Activities & Enrollment Plan Tab. 3. Completed existing Audit Log to a Table Grid for Form Types Maintenance. 4. Resolved the issue where the Enrollment Plan Capacity Reached prompt was not closing properly. 5. Resolved the issue in Manual Registration where a null Student Info caused an error. | Peer CRC:5 Onsite CRC:0 Client CRC:0 Internal Defects:0 External Defects:2 | NIL | Good Sprint and appreciated the team for great communication and collaboration.
#REF! | 4.3 Sprint S3 | 2025-11-19 | 2025-12-02 | 9 | 19 | Introduced - 0 | In this 4.3 sprint S3 was primarily focused on regression testing, which was successfully completed. All stories addressed during the sprint were development-only items. The team prioritized stretch stories and technical improvements, ensuring stability and readiness for future releases. | 1. Successfully completed full regression testing, ensuring system stability and readiness for release. 2. Delivered a universal search feature for the Students page, improving user experience and data accessibility as Discovery. 3. Enhanced field validation in the Enrollment Plan administration, addressing technical debt and improving data quality. 4. Implemented validation to prevent starting a registration for students with a null student number in the development environment. 5. Removed obsolete "Original Description" columns from the system, streamlining data structures and supporting future maintainability. | Peer CRC:0 Onsite CRC:0 Client CRC:0 Internal Defects:0 External Defects:0 | NIL | NIL [Retro meeting was not held]
#REF! | 26.2 Sprint S1 | 2025-12-03 | 2025-12-16 | 12 | 19 | Introduced - 16 | In Sprint 26.2 S1 we completed field validation for Form Type and Term, implemented new Universal Search and Datagrid components, and removed the Original Description column to simplify the data model. | 1.Strengthened validation for Form Type and Term to address technical debt and improve data quality. 2.Completed reusable Universal Search component for cross‑context lookups. 3.Implemented the Datagrid component and updated pagination design for a cleaner, more responsive UX. 4.Removed the Original Description column to simplify data structures and make future maintenance easier. 5.Added a check that prevents starting a registration for students with a null studentNumber. | Peer CRC:4 Onsite CRC:0 Client CRC:0 Internal Defects:2 External Defects:3 | NIL | NIL
#REF! | 26.2 Sprint S2 | 2025-12-17 | 2026-01-13 | 35 | 43 | Introduced - 8 | In Sprint 26.2 S2 we completed customizable columns for Enrollment Plans,universal search for Student Maintenance, Upgraded audit log to table grid for Activities and Custom Fields,added a spinning loader on the Purchases & Fees tab,Completed discovery work for Activity Pricing under prepaid Enrollment Plans, Added a new “No Students” screen, Fixed the capacity modal popup issue development completed for custom grid implementation across Enrollment Plans, Activities, Discounts, and Terms . | 1.Implemented the Enrollment Plan grid with configurable/customizable columns. 2.Upgraded the existing Activities audit log to use the new table grid. 3.Upgraded the existing Custom Fields audit log to use the new table grid. 4.Implemented universal search for Student Maintenance. 5.Replaced the message-based indicator with a spinning loader on the Purchases & Fees tab. 6.Completed discovery for Activity Pricing for prepaid Enrollment Plans. 7. Added a new “No Students” screen and a provision to manually add students even when no MSB students exist. 8.Fixed the capacity modal popup issue. 9.Completed development of the custom grid for Enrollment Plans, Activities, Discounts, and Terms. | Peer CRC:0 Onsite CRC:0 Client CRC:2 Internal Defects:3 External Defects:0 Note:This Story # 51138 - Activities - Non Student Registration - Update validation for checking for students in the msb household - Development is completed and pending for client approval Note :Reason – There were dependencies on MSB APIs, which became blockers for this story. The blockers were identified one after another and discussed with Allen and the client developer, Andy, for confirmation. The PR has been approved by Allen and is currently pending approval from the client developer, Andy. | Nil | Good Sprint and appreciated to completed main as well stretch items. Continue excellent communication, collaboration, and open-minded reflection/retrospectives.
#REF! | 26.2 Sprint S3 | 2026-01-14 | 2026-01-27 | 9 | 7 |  | In this 26.2 sprint S3 was primarily focused on regression testing, which was successfully completed. We are completed Editable data grid chanes and UI updates for HSS menu, etc. | Completed the following stories: 1.Activities - Non Student Registration: Updated validation to check for students in the MSB household. 2.Activities - Kaleida: Updated table grid design for Term Maintenance [26.3]. 3.Activities - Kaleida: Admin - Created component for Editable Grid Table with updated design [26.3]. 4.Activities - Kaleida: Updated table grid design for HSS Maintenance. 5.All regression tests passed successfully, ensuring stability for release. | Peer CRC:0 Onsite CRC:0 Client CRC:0 Internal Defects:0 External Defects:0 Note:This Story # 51367 Activities - Kaleida - Update table grid design for Enrollment Plans/ Activities/ Discounts [26.3] - Development is completed and pending QA testing Reason – During the regression sprint, we completed development and Product Owner verification. The pull request will be merged only after the regression sprint ends. Note: As informed by the client, this story will be carried over to the next sprint for PR merging and testing efforts. | Nil | Good Sprint and appreciated to completed main as well stretch items.
#REF! | 26.3 Sprint S1 | 2026-01-28 | 2026-02-10 | 26 | 39 | 13 | In this 26.3 sprint S1, We have successfully completed all main stories and stretch stories for this sprint. The primary focus was on data table conversion, migrating legacy components to the new CustomDataGrid with improved sorting and filtering capabilities. We also completed comprehensive parent UI updates to enhance the overall user experience and component consistency. Additionally, we addressed various general updates and bug fixes across the system. This sprint demonstrates strong execution with all planned work delivered on schedule. | 1.Data Table Conversion - Successfully migrated 12+ admin modules to the new CustomDataGrid architecture with improved sorting and filtering. 2.Parent UI Updates - Completed Payment History, Kiosk PIN, and loading experience redesigns to enhance user interface consistency. 3.Shared Component Framework - Established shared folder structure for parent components to reduce code duplication and improve maintainability. 4.Universal Search Implementation - Replaced legacy global search with new Universal Search backend functionality. 5.Bug Fixes & Refinements - Addressed action menu alignment, breadcrumb navigation, and general system improvements across all modules. | Peer CRC:0 Onsite CRC:0 Client CRC:1 Internal Defects:5 External Defects:0 | Nil | Overrall a good Sprint and appreciated to completed main as well stretch items. Andy Onsite Developer – Wave team’s last day during this Sprint, the team pushed through and it was a smooth transition. Kristy Client PO - Great communication and collaboration pushed us forward. | 0
#REF! | 26.3 Sprint S2 | 2026-02-11 | 2026-02-24 | 25 | 35 | 6 | In this 26.3 sprint S2, we successfully completed all main and stretch stories as planned. The primary focus was on updating and standardizing data tables, including migrating legacy components to the new CustomDataGrid with enhanced sorting and filtering features. Significant progress was made on parent UI improvements, delivering a more consistent and user-friendly experience across key areas. We also implemented important component upgrades such as updating to the latest Vega version and converting class components to functional ones. In addition, several general updates and critical bug fixes were addressed, ensuring improved stability and performance throughout the system. This sprint reflects strong execution, with all objectives delivered on schedule. | 1. UI/UX Enhancements: Updated table grid designs for Students, Contacts, Enrollment Plan tabs, People > Documents, and Registrations > Enrollments in Kaleida. Implemented new Parent Breadcrumb UI and updated Parent Footer with Kiosk PIN & Payment History Report. 2. Component Improvements: Converted Student Info Class Components to Functional Components. Created Student Info Card Component for Parent Registration. Updated Vega component to the latest version. 3.Admin Features & Fixes: Added filter for "Completed with Errors" in JobRequest DataGrid. Improved App Switcher initialization for HSSAppTray (26.2.1 dot release). 4.Defect Resolutions: Hid inactive districts from parent selection in Kaleida. Fixed calendar display issues in transfer/withdraw modal. Corrected status column in Parent Accounts to display proper values. Resolved universal search freezing when returning ":" from query. | Peer CRC:0 Onsite CRC:0 Client CRC:1 Internal Defects:5 External Defects:2 | Nil | Overrall a good Sprint and appreciated to completed main as well and few stretch items. Great communication (as always). | 0
#REF! | 26.3 Sprint S3 | 2026-02-25 | 2026-03-10 | 6 | 12 | 1 | Sprint 26.3 S3 was successfully completed with all regression tests and related defect fixes. Development was finalized for the App Switcher button visibility enhancement. Timeboxed work on Kaleida Admin Breadcrumbs [26.5] was completed. Stretch stories, including updates to Parent Registration, Admin UI improvements, Universal Search, and API token handling, were also delivered for 26.5. All planned and stretch objectives for this sprint were achieved on schedule. | Accomplishments for Sprint 26.3 S3: Completed all regression testing and resolved related defects. Delivered the App Switcher enhancement to hide the button until the script loads. Finished timeboxed development for Kaleida Admin Breadcrumbs [26.5]. Completed stretch stories: Parent Registration updates, Admin UI improvements, Universal Search for Student Purchases, and API token session handling [26.5]. Achieved all planned and stretch sprint objectives on time. | Peer CRC:0 Onsite CRC:0 Client CRC:2 Internal Defects:1 External Defects:3 | Nil | Shoutout to offshore team, engaged, great communication to Vega team. I think we made the most of our refinement, standups, and planning prep call had a great discussions! The collaboration and communication is always top-notch. | 0
#REF! | 26.5 Sprint S1 | 2026-03-11 | 2026-03-24 | 28 | 23 |  | Sprint 26.5 S1 was successfully Completed key Kaleida Parent Registration updates, including Student Info, Your Info design, Schedule Landing updates, and Admin Breadcrumbs,Fixed multiple Admin issues, including Bulk Copy/Edit selector defects, Enhanced Registrations Table Grid header text, and Preview EP Forms errors, Completed Parent Accounts registration status navigation so Pending and Waitlisted statuses route correctly to the Review page, Delivered Admin search improvements with Universal Search for Student Purchases,Finished discovery work for the Admin calendar display issue and system-level config props access. | - Completed Add/Edit Student Info updates for Kaleida Parent Registration in 26.5. - Completed the Your Info design updates for Kaleida Parent Registration. - Completed development and internal POV for Schedule Landing updates in Kaleida Parent Registration. - Fixed the Bulk Copy/Edit Selector defect in Admin. - Completed removal of header text from the Registrations Table Grid in 26.5. - Completed navigation from Parent Accounts Registration statuses like Pending and Waitlisted to the Review page in 26.5. - Completed fixes for Preview EP Forms errors in Admin. - Completed Universal Search for Student Purchases in Admin. - Completed discovery for the Admin calendar display issue. - Completed Admin Breadcrumbs updates for Kaleida. - Completed stretch discovery for system-level access to config props | Peer CRC:0 Onsite CRC:0 Client CRC:8 Internal Defects:2 External Defects:0 Note: This #52259 story is being carried forward to the testing phase only due to a last-minute design change request that modified the originally accepted design specifications and acceptance criteria.The client stakeholder has been informed and acknowledges the current status and the revised scope resulting from the design change | Nil | Overrall a good Sprint and Great communication (as always). | 0
#REF! | 26.5 Sprint S2 | 2026-03-25 | 2026-04-07 | 35 | 28 | 0 | Sprint 26.5 S2 successfully completed key development work across Kaleida and Parent experiences, including Parent Withdraw/Transferred UI verbiage cutoff updates, the Physician's Name field spacing fix, Admin Breadcrumbs [V1], Parent Registration Design updates for Contacts, and Schedule-related enhancements. The sprint also delivered system-level improvements by enabling the App Switcher for HSS users and adding access to configuration properties at the system level, while resolving the Admin calendar display issue. In addition, development was completed for stretch items such as Preview EP Forms Errors, post-submission navigation to the Enrollments page, and redirect button updates to return users to previous screens. Development was also completed for the Schedule Status Indicator and Schedule Landing Updates; however, testing for these items has been carried forward due to a 2.5-day outage across lower environments, including Dev, QA, and Integration. Throughout the sprint, the team maintained strong communication and kept stakeholders informed of the blocker and its impact. | 1. Successfully completed all planned main stories, including Parent Withdraw/Transferred UI verbiage updates, the Physician's Name field spacing fix, Admin Breadcrumbs [V1], Parent Registration Design updates for Contacts, and the Admin calendar display fix. 2. Delivered key system-level enhancements by enabling the App Switcher for HSS users and adding access to configuration properties at the system level. 3. Completed development for stretch stories, including Preview EP Forms error handling, post-submission navigation to the Enrollments page, and redirect button updates to previous screens. 4. Finished development for Schedule Status Indicator and Schedule Landing Updates as part of the Parent Registration enhancements. | Peer CRC:0 Onsite CRC:0 Client CRC:3 Internal Defects:2 External Defects:1 Notes :Stories #52259 and #52461 are deferred pending testing. A 2.5-day blocker affecting all lower environments (Development, Quality Assurance, and Integration) prevented the team from conducting peer code reviews, peer testing, and quality assurance testing. The client is fully aware of this issue. | Nil | What went well: strong communication, good use of meeting times, great attention to detail from the team. What didn't go well : Lower Environments being down delayed being able to test | 0
#REF! | 26.5 Sprint S3 | 2026-04-08 | 2026-04-21 | 16 | 22 | 9 | Sprint 26.5 S3 was a mini regression sprint focused on strengthening the Activities experience across Parent, Admin, and Kaleida workflows. The team completed key updates including Schedule Landing Updates, Schedule Status Indicator development, parent registration usability improvements, Admin redirect and search enhancements, and Enrollments page navigation updates. Several regression and defect fixes were also completed, including the haspendingUpdates refresh error, incorrect modified field indicators, calendar header spacing, and withdrawn student enrollment counts. Stretch progress included preview handling for manually added student sources, past registration interaction prevention, Admin calendar modal fixes, and Dynamic Reports student count corrections. A small number of items remain in peer review or Product Owner verification. | 1.Successfully completed the planned Sprint 26.5 S3 work across Parent, Admin, and Kaleida experiences, including Schedule Landing Updates, Schedule Status Indicator development, parent registration UI improvements, redirect button updates, and Enrollments page navigation updates. 2.Delivered important usability and stability improvements by enhancing special character support in Universal and Global Search, improving enrollment count visibility, and strengthening the overall registration experience. 3.Resolved key regression and defect items, including the haspendingUpdates refresh issue, incorrect modified field indicators for DOB, School, and Grade, calendar header spacing issues, and Admin calendar modal behavior. 4.Completed stretch development items, including manually added student source preview handling, prevention of interaction with past program registrations, and Dynamic Reports student count fixes, while carrying a small number of items into verification and peer review. | Peer CRC:0 Onsite CRC:0 Client CRC:1 Internal Defects:6 External Defects:2 Notes: Regression defect #27238 was identified at the end of the sprint and has been classified as low priority. Development has been completed, and the related testing effort will be carried forward to the next sprint. | Nil | What Went Well : The team did an incredible job getting almost all of the main commit closed out as well as a bunch in stretch. Carryover is limited to a regression defect, some NotificationHub wrap up, and stretch work. A tremendous amount of work was wrapped up including some finishing touches on the parent redesign V1 What didn't go well : We lost some time to the secret expiring in lower environments blocking us from deploying newer builds as they became available (lost roughly 0.5-1 day of planned work with this). Inconsistency on the environments between non prod and prod. Which made the analysis time a bit longer. | 0 |  |  | 62 sp
#REF! | 26.5 Sprint S4 | 2026-04-22 | 2026-05-05 | 9 | 9 |  | Sprint 26.5 S4 was successfully completed with all regression tests and related defect fixes. Stretch stories, including updates to Parent Registration, Admin UI improvements, Universal Search , All planned and stretch objectives for this sprint were achieved on time. | Accomplishments for Sprint 26.5 S4: 1.Completed all regression testing and resolved related defects. 2. Adjust registration status chip display. 3. Disable Next button when no eligible students. 4. Pendo - Registration Student Source Event Tagging 5. Achieved all planned and stretch sprint objectives on time. | Peer CRC:0 Onsite CRC:0 Client CRC:1 Internal Defects:9 External Defects:0 | Nil | What Went Well : Allen assigned offshore to regression, more issues identified, manju assisted “the star”, huge undertaking this regression sprint, Team showed the good communication What didn't go well : MSB being down/login issue which delayed Unit testing and PR. | 0 |  |  | 75 sp
#REF! | 26.6 Sprint S1 | 2026-05-06 | 2026-05-19 | 22 |  |  |  |  | Peer CRC:0 Onsite CRC:0 Client CRC:0 Internal Defects:1 External Defects:4 |  |  | 0 |  |  | 84 sp
Note on G2: Sivaraja Muthurajan:

## Defect-template
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## Unplanned Leaves
Total Leaves | 0
Resource Name
Sprint | Allen Xavier | Athinarayanana Ramar | Ramprabhu Sakthivel | Manjunathan Dharaman | Kanchana Umakanthan | Remarks
26.3 Sprint S1(26-Jan-2026 to 10-Feb-2026)
26.3 Sprint S2(11-Feb-2026 to 24-Feb-2026)
26.3 Sprint S3(25-Feb-2026 to 10-Mar-2026)
26.5 Sprint S1(11-Mar-2026 to 24-Mar-2026)
26.5 Sprint S2(25-Mar-2026 to 07-Apr-2026)
26.5 Sprint S3( 08-Apr-2026 to 21-Apr-2026
26.5 Sprint S4( 22-Apr-2026 to 05-May-2026)
Total | 0 | 0 | 0 | 0 | 0

## 26.6 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
0
1 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 | Athi | 27161 | Activities - Admin - Pending Registration not showing updated weeks | Defect Fixed | 5 | 3 | 12 | 2026-05-07 | 2026-05-11 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48962 | 2026-05-11 | 2026-05-11 | Allen | Nil | Ethan | 2026-05-11 | Nil | NA | NA | NA | Meets Expectation
2 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 | Allen | 52738 | Activities - Admin - Place cursor in search box for expanded Site selector | Story Completed | 2 | 2 | 8 | 2026-05-11 | 2026-05-11 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/49000 | 2026-05-12 | 2026-05-12 | Allen | Nil | Ethan | 2026-05-12 | Nil | Approved | Approved |  | Meets Expectation
3 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 | Athi | 53146 | Activities - Parent - Hide download/print schedule from Enrollments page [26.5] | Story Completed | 2 | 1 | 4 | 2026-05-06 | 2026-05-06 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48873 | 2026-05-06 | 2026-05-06 | Allen | Nil | Andy | 2026-05-06 | Nil | Approved | Approved |  | Meets Expectation
4 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 | Allen | 27358 | Activities - Fake parent login is not working | Defect Being Fixed | 1 |  |  | 2026-05-06 | 2026-05-11 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48794 | 2026-05-11 | [6 empty] | NA | NA | Its not release canditate | Meets Expectation
5 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 | Allen | 52940 | Activities - Pendo - Move Pendo into global config prop settings so that it can be accessed prior to a tenant being selected | Story Completed | 1 |  |  | 2026-05-01 | 2026-05-04 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/49068 | 2026-05-15 | 2026-05-15 | Allen | Nil | Andy | 2026-05-15 | Nil | NA | NA |  | Meets Expectation
6 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 | Ram | 52700 | Activities - Kaleida - Update Parent Registration Design (Forms) | Story Being Tested | 8 | 4 | 21 | 2026-05-06 | 2026-05-11 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48987 | 2026-05-12 | 2026-05-12 | Allen | Nil | Andy | 2026-05-12 | Nil | Approved | Approved |  | Meets Expectation
7 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 | Athi | 52689 | Activities - Kaleida - Update delete registration confirmation modals (Parent) | Story Completed | 2 | 1 | 4 | 2026-05-12 | 2026-05-12 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48997 | 2026-05-12 | 2026-05-12 | Allen | Nil | Ethan | 2026-05-12 | Nil | Approved | Approved |  | Meets Expectation
8 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 | Allen | 27298 | Activities - Admin - District Settings - Edit screen save validation when Provider ID blank is not working | Defect Fixed | 1 | 1 | 4 | 2026-05-05 | 2026-05-06 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48835 | 2026-05-06 | 2026-05-06 | Allen | Nil | Andy |  | What if both the password and providerid are blank, wouldn't this hide the validation about the password? We are going to circle back on this discussion - it seems like perhaps the actual solution here is to just remove the X (unselect) option from the dropdown and never allow this to be unset | NA | NA |  | Meets Expectation
9 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 Stretch | Allen | 53123 | Activities - Pendo - Registration Student Source Event Tagging | Story Completed | 2 |  |  | 2026-05-06 | 2026-05-11 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48834 | 2026-05-14 | 2026-05-14 | Allen | Nil | Andy | 2026-05-14 | Nil | NA | NA |  | Meets Expectation
10 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 Stretch | Ram | 52786 | Activities - Parent - Place cursor in search box for District & Site selector | Story Completed | 2 | 1 | 4 | 2026-05-13 | 2026-05-13 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/49049 | 2026-05-14 | 2026-05-14 | Allen | Nil | Ethan | 2026-05-14 | Nil | Approved | Approved |  | Meets Expectation
11 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 Stretch | Ram | 52455 | Activities - Parent - Update Default Relationship Field Selection to "Parent" | Story Being Tested | 3 | 1 | 6 | 2026-05-12 | 2026-05-12 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/49050 | 2026-05-14 | 2026-05-14 | Allen | Nil | Ethan | 2026-05-14 | Nil | Approved | Approved |  | Meets Expectation
12 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 Stretch | Athi | 27410 | Activities - Reject Updated Registration modal is formatted poorly | Defect Fixed | 1 | 1 | 2 | 2026-05-14 | 2026-05-14 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/49057 | 2026-05-14 | 2026-05-14 | Allen | Nil | Ethan | 2026-05-14 | Nil | NA | NA |  | Meets Expectation
13 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 Stretch | Athi | 27416 | Activities - Admin - Clear Discount Modal triggering when no discount exists | Defect Fixed | 1 | 1 | 4 | 2026-05-15 | 2026-05-15 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/49082 | 2026-05-15 | 2026-05-15 | Allen | Nil | Ethan | 2026-05-15 | Nil | NA | NA |  | Meets Expectation
14 | MSB Activities | 2026-05-06 | 2026-05-19 | 26.6 Sprint S1 Stretch | Athi | 52834 | Activities - SYSTEM - TECH DEBT - Database - Investigate usage of LOCKs in DB queries [26.6] | Story Being Developed | 8 | 0 | 2 | 2026-05-14 | [14 empty] | NA | NA |  | Meets Expectation

## 26.6 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.6 Sprint S1 | 27298 Activities - Admin - District Settings - Edit screen save validation when Provider ID blank is not working |  | Allen | Defect | If you go into a district in Hss Staff - Districts and proceed to the edit screen, remove the MSB Provider Id (setting it to not set) then try to save. The button does nothing and there is no validation messaging. |  | Minor | Manual | External | Defect Fixed | Existing_Issues |  | Offshore PO - Kanchana
2 | 26.6 Sprint S1 | 27161 Activities - Admin - Pending Registration not showing updated weeks |  | Athi | Defect | Defect: 1 - When using the weekly calendar. If you update the weeks on a pending registration and then navigate to that registration in Admin. We are not showing the update. Defect: 2 - I verified in the integration environment that in the parent, I scheduled only for one week (weekly calendar) and submitted my registration. When I viewed it as an admin on the pending/waitlist/View all/ Student enrollment pages, it showed all the weeks as selected. |  | Major | Manual | External | Defect Fixed | Existing_Issues |  | Offshore PO - Kanchana
3 | 26.6 Sprint S1 | 27358 Activities - Fake parent login is not working |  | Allen | Defect | The fake parent login is not working |  | Minor | Manual | Internal | Defect Being Fixed | Development |  | Onshore Manager - Ethan
4 | 26.6 Sprint S1 Stretch | 27410 - Activities - Reject Updated Registration modal is formatted poorly |  | Athi | Defect | The Reject Updated Registration modal formatting could be improved. |  | Minor | Manual | External | Defect Fixed | Existing_Issues |  | Onsite QA - Jeff
5 | 26.6 Sprint S1 Stretch | 27416 Activities - Admin - Clear Discount Modal triggering when no discount exists |  | Athi | Defect | In admin, it looks like once a discount is set, and then removed. If you change the pricing of the enrollment plan, it triggers the "Clear Discounts" modal, even though a discount does not exist. Most likely we are not updating the state of the prop once a discount has been set. |  | Significant | Manual | External | Defect Fixed | Existing_Issues |  | Onsite QA - Jeff

## 26.5 Sprint S4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
0
1 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Athi | 27238 | Activities - Regression - Parent - Not able to see Screen "No Student Yet" when no student are available for a parent. | Defect Fixed | 0 | 1 | 3 | 2026-04-20 | 2026-04-21 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48541 | 2026-04-21 | 2026-04-22 | Allen | Nil | Andy | 2026-04-22 | Nil | NA | NA | Carried from last sprint - Testing effort only:This defect found on end of the sprint, its low priority, and development effort is completed in the last sprint. | Meets Expectation
2 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Ram | 27267 | Activities - Regression - Student Card - The data-testid field is displaying the UID instead of the Student Name | Defect Fixed | 0 | 1 | 2 | 2026-04-22 | 2026-04-22 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48574 | 2026-04-22 | 2026-04-22 | Allen | Nil | Ethan | 2026-04-22 | Nil | NA | NA |  | Meets Expectation
3 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Ram | 27266 | Activities - Regression - Site Selector - The data-testid field is displaying the UID instead of the Site Name | Defect Fixed | 0 | 1 | 2 | 2026-04-22 | 2026-04-22 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48573 | 2026-04-22 | 2026-04-22 | Allen | Nil | Ethan | 2026-04-22 | Nil | NA | NA |  | Meets Expectation
4 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Ram | 52882 | Activities - Parent - Disable Next button when no eligible students | Story Completed | 2 | 2 | 2 | 2026-04-17 | 2026-04-20 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48583 | 2026-04-22 | 2026-04-22 | Allen | Nil | Ethan | 2026-04-22 | Nil | Approved | Approved |  | Meets Expectation
5 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Athi | 52883 | Activities - Parent - Adjust registration status chip display [26.5?] | Story Completed | 2 | 2 | 2 | 2026-04-16 | 2026-04-20 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48579 | 2026-04-22 | 2026-04-22 | Allen | Nil | Ethan | 2026-04-22 | Nil | Approved | Approved |  | Meets Expectation
6 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Allen | 52939 | Activities - Pendo - Registration Student Source Event Tagging (Discovery) | Story Completed | 5 | 5 | 5 | 2026-04-22 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Its Discovery story | Meets Expectation
7 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Athi | 27272 | Activities - REGRESSION - Admin - Missing breadcrumb link in Config Props - Add and Roles – Edit | Defect Fixed | 0 | 1 | 3 | 2026-04-23 | 2026-04-23 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48610 | 2026-04-23 | 2026-04-23 | Allen | Nil | Ethan | 2026-04-23 | Very minor, but this should be an "else if" | NA | NA | Minor suggestion in CRC | Meets Expectation
8 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Athi | 27306 | Activities - Regression - Admin - Universal search is not filtering when we provide invalid date and Amount Field. | Defect Fixed | 0 | 1 | 3 | 2026-04-28 | 2026-04-28 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48689 | 2026-04-30 | 2026-05-01 | Allen | Nil | Andy | 2026-05-01 | Nil | NA | NA |  | Meets Expectation
9 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Athi | 27311 | Activities - REGRESSION - Parent - Removed day still showing in parent after removing it from the schedule | Defect Fixed | 0 | 1 | 3 | 2026-04-29 | 2026-04-29 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48716 | 2026-04-29 | 2026-04-29 | Allen | Nil | Andy | 2026-04-29 | Nil | NA | NA |  | Meets Expectation
10 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Ram | 27308 | Activities - Regression - Parent - Custom Field Email Validation is not working | Defect Fixed | 0 | 1 | 3 | 2026-04-28 | 2026-04-28 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48680 | 2026-04-28 | 2026-04-28 | Allen | Nil | Ethan | 2026-04-28 | Nil | Nil | Nil |  | Meets Expectation
11 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Athi | 27317 | Activities - Regression - Parent - Incorrect display of Download & Print schedule data on Enrollments page card details | Defect Fixed | 0 | 1 | 3 | 2026-04-30 | 2026-04-30 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48772 | 2026-04-30 | 2026-05-01 | Allen | Nil | Andy | 2026-05-01 | Nil | NA | NA |  | Meets Expectation
12 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 | Ram | 27325 | Activities - Regression - Parent - Page is not responding while changing the custom field Radio button values. | Defect Fixed | 0 | 1 | 4 | 2026-04-30 | 2026-04-30 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48768 | 2026-04-30 | 2026-04-30 | Allen | Nil | Andy | 2026-04-30 | Nil | NA | NA |  | Meets Expectation
13 | MSB Activities | 2026-04-22 | 2026-05-05 | 26.5 Sprint S4 Stretch | Athi | 52834 | Activities - SYSTEM - TECH DEBT - Database - Investigate usage of LOCKs in DB queries [26.6] | Story Being Developed | 8 | 1 | 6 | 2026-04-22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Its Tech debt story | Meets Expectation
17
18

## 26.5 Sprint 4 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.5 Sprint S4 | Activities - Regression - Site Selector - The data-testid field is displaying the UID instead of the Site Name |  | Ram | Defect | In the Site Selector, the data-testid field is displaying the UID instead of the Site Name | Datatest Id renamed in the UI compenent which is used for automation test | Minor | Manual | Internal | Defect Fixed | Existing_Issues |  | Onshore - QA - Jeff
2 | 26.5 Sprint S4 | 27267 Activities - Regression - Student Card - The data-testid field is displaying the UID instead of the Student Name |  | Ram | Defect | On the updated Student Cart, the data-testid field is displaying the UID instead of the Student Name | Datatest Id renamed in the UI compenent which is used for automation test | Minor | Manual | Internal | Defect Fixed | Existing_Issues |  | Onshore - Manager - Ethan
3 | 26.5 Sprint S4 | 27272 Activities - REGRESSION - Admin - Missing breadcrumb link in Config Props - Add and Roles – Edit |  | Athinarayanan | Defect | Missing breadcrumb link issue in Config Props Add and Roles – Edit Config Props > Add (Home> Heartland Staff ) Roles > Edit. (Home > Setup > Roles) | This breadcrumb path is missed in the AC point. | Minor | Manual | Internal | Defect Fixed | QA |  | Ram - Offshore Developer
4 | 26.5 Sprint S4 | 27238 - Activities - Regression - Parent - Not able to see Screen "No Student Yet" when no student are available for a parent. |  | Athinarayanan | Defect | Not able to see Screen "No Student Yet" when no student are available for a parent. | Student count validation is missed | Minor | Manual | Internal | Defect Fixed | Development | Carried from last sprint - Testing effort only:This defect found on end of the sprint, its low priority, and development effort is completed in the last sprint. | Athinarayanan - Offshore Developer
5 | 26.5 Sprint S4 | 27311 Activities - REGRESSION - Parent - Removed day still showing in parent after removing it from the schedule |  | Athinarayanan | Defect | In parent with daily calendar on, if you put in that you will be attending everyday. Then deselect all of a specific day (remove Mondays by deselecting it). In the Schedules section it still shows Monday as being part of the schedule. This is occurring with updating an accepted registration as well. | Model Validation is missed | Minor | Manual | Internal | Defect Fixed | Development | . | Offshore QA - manjunath
6 | 26.5 Sprint S4 | 27308 Activities - Regression - Parent - Custom Field Email Validation is not working |  | Ram | Defect | Custom Field Email Validation is not working Custom Field Email Validation is missing for students Info screen, Contacts screen and parent info Screen. | Email validation for custom field is missed. | Minor | Manual | Internal | Defect Fixed | Development | . | Offshore QA - manjunath
7 | 26.5 Sprint S4 | 27325 Activities - Regression - Parent - Page is not responding while changing the custom field Radio button values. |  | Ram | Defect | Page is not responding while changing the Radio button values. This happens for Student info, parent Info and contacts info screen. | Sync event handling which affected the performance of the page. | Significant | Manual | Internal | Defect Fixed | Development | . | Offshore QA - manjunath
8 | 26.5 Sprint S4 | 27306 Activities - Regression - Admin - Purchases Universal search is not filtering when we provide invalid date and Amount Field |  | Athinarayanan | Defect | Universal search is not filtering when we provide invalid date and Amount Field | Invalid or edge case validation are missed in the query builder. | Significant | Manual | Internal | Defect Fixed | Development |  | Ram - Offshore Developer
9 | 26.5 Sprint S4 | 27317 Activities - Regression - Parent - Incorrect display of Download & Print schedule data on Enrollments page card details |  |  | Defect | Defect:1 Validation message persists after clearing To Date in Payment History Report In the Payment History Report, when a user enters a From Date later than the To Date (e.g., From Date: 05/02/2026, To Date: 04/28/2026), the system correctly displays a validation message indicating the invalid date range. However, after clearing the To Date field, the validation message continues to persist even though the input is now valid. This suggests that the validation logic is not being reset when the To Date field is cleared. Defect: 2: Incorrect display of Download and Print schedule data on Enrollments & Registration page card details On the Enrollments & Registration page, the enrollment card details section is showing incorrect data for the Download and Print schedule options. The information displayed does not match the actual schedule data, leading to inconsistencies between what is downloaded/printed and what is shown on the schedule page. | Clearing error message was missed after proper date.Updated scheduled date are not printed in the sheet. | Significant | Manual | Internal | Defect Fixed | Development |  | Kanchana - Offshore PO

## 26.5 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
0
1 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Athi | 52259 | Activities - Kaleida - Update Parent Registration - Schedule Landing Updates | Story Completed | 2 | 1 | 1 | 2026-03-11 | 2026-03-23 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47981 | 2026-03-24 | 2026-03-24 | Allen | Nil | Ethan | 2026-03-25 | Nil | Approved. POV Comments: When two different calendar activities are scheduled, the system displays similar data for both, instead of distinct activity details. Download - Empty PDF is downloading | Approved. During POV additional scope is added to the story |  | Meets Expectation
2 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Athi | 52461 | Activities - Kaleida - Update Parent Registration - Schedule Status indicator | Story Completed | 1 | 1 | 1 | 2026-03-26 | 2026-03-30 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48198 | 2026-04-02 | 2026-04-02 | Allen | Nil | Ethan | 2026-04-02 | Nil | POV comment: Incomplete and Complete status showing at the same time. Approved | Approved |  | Meets Expectation
3 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Ram | 52686 | Activities - Parent - Hide unselected students and checkboxes for submitted registrations | Story Completed | 5 | 3 | 10 | 2026-04-08 | 2026-04-08 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48328 | 2026-04-09 | 2026-04-09 | Allen | Nil | Ethan | 2026-04-09 | Nil | Approved. | Approved |  | Meets Expectation
4 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Ram | 52687 | Activities - Parent - Hide pencil/edit icon for students not selected | Story Completed | 2 | 2 | 5 | 2026-04-10 | 2026-04-10 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48354 | 2026-04-10 | 2026-04-10 | Allen | Nil | Ethan | 2026-04-10 | Nil | Approved. | Approved. |  | Meets Expectation
5 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Athi | 52048 | Activities - Admin - Redirect buttons to previous screens | Story Completed | 1 | 1 | 1 | 2026-03-31 | 2026-04-02 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48318 | 2026-04-09 | 2026-04-10 | Allen | Nil | Ethan | 2026-04-10 |  | Approved. | Approved |  | Meets Expectation
6 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Allen | 52480 | Activities - Parent - Land on Enrollments page after interacting with a registration | Story Completed | 1 |  |  | 2026-04-01 | 2026-04-01 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48250 | 2026-04-06 | 2026-04-06 | Allen | Nil | Ethan | 2026-04-06 | Nil | Approved. | Approved. |  | Meets Expectation
7 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Athi | 52528 | Activities - Admin - Universal & Global Search – Support for Special Characters | Story Completed | 3 | 1 | 2 | 2026-04-08 | 2026-04-09 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48353 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48500 | 2026-04-10 | 2026-04-20 | Allen | Nil | Andy | 2026-04-20 | Nil | Approved. | Approved |  | Meets Expectation
8 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Allen | 26974 | Activities - Parent - Enrollments count including withdrawn [26.5] | Defect Fixed | 1 | 1 | 1 | 2026-04-07 | 2026-04-07 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48277 | 2026-04-07 | 2026-04-07 | Allen | Nil | Ethan | 2026-04-07 | Nil | NA | NA |  | Meets Expectation
9 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Athi | 27171 | Activities - REGRESSION - Parent - Facing "haspendingUpdates" error while refreshing the screen | Defect Fixed |  | 1 | 2 | 2026-04-13 | 2026-04-13 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48427 | 2026-04-15 | 2026-04-15 | Allen | Nil | Ethan | 2026-04-15 | Nil | NA | NA |  | Meets Expectation
10 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Ram | 27211 | Activities - REGRESSION - Parent - DOB,School and Grade fields shown as modified while updating the registration | Defect Fixed |  | 2 | 4 | 2026-04-17 | 2026-04-17 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48497 | 2026-04-17 | 2026-04-20 | Allen | Nil | Andy | 2026-04-20 | Nil | NA | NA |  | Meets Expectation
11 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Athi | 27217 | Activities - REGRESSION - Parent - Calendar showing space above header | Defect Fixed |  | 1 | 2 | 2026-04-17 | 2026-04-17 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48512 | 2026-04-20 | 2026-04-20 | Allen | Nil | Andy | 2026-04-20 | Nil | NA | NA |  | Meets Expectation
12 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 | Athi | 27238 | Activities - Regression - Parent - Not able to see Screen "No Student Yet" when no student are available for a parent. | Defect Peer Review |  | 1 | 2 | 2026-04-20 | 2026-04-21 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48541 | 2026-04-21 | NA | NA | NA | NA | NA | NA | NA | NA | This Regression defect found in end-of-sprint. May be Test effort will be carry forward to the next sprint. | Meets Expectation
13 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 Stretch | Allen\Athi | 52709 | Activities - Enrollment Plans - Handle Preview tab for manually added student source | Story Completed | 2 | 1 | 2 | 2026-04-08 | 2026-04-09 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48351 | 2026-04-10 | 2026-04-10 | Allen | Nil | Ethan | 2026-04-13 | What is the purpose of this iVBORw0KG check? | Given POV Comments: PNG File format is not worked | Approved | CRC: Request clarificatin and explain. There is no code change | Meets Expectation
14 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 Stretch | Allen | 27160 | Activities - Admin - Calendar Modal is not working properly, when we select year or month and then use scroll bar | Defect Fixed | 1 |  |  | 2026-04-08 | 2026-04-09 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48338 | 2026-04-08 | 2026-04-08 | Allen | Nil | Ethan | 2026-04-08 | Nil | NA | NA |  | Meets Expectation
15 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 Stretch | Athi | 52885 | Activities - Parent - Prevent parent from interacting with past program registrations | Story Completed | 2 | 1 | 4 | 2026-04-16 | 2026-04-16 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48501 | 2026-04-17 | 2026-04-17 | Allen | Nil | Ethan | 2026-04-17 | Nil | Approved | Approved |  | Meets Expectation
16 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 Stretch | Ram | 52882 | Activities - Parent - Disable Next button when no eligible students | Product Owner - Verify | 5 | 1 | 4 | 2026-04-17 | 2026-04-20 | Done | Athi | Nil | Athi | Nil | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Meets Expectation
17 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 Stretch | Allen | 27212 | Activities - Error running the Update Student Counts in the Dynamic Reports | Defect Fixed | 1 |  |  | 2026-04-16 | 2026-04-16 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48472 | 2026-04-16 | 2026-04-16 | Allen | Nil | Ethan | 2026-04-16 | Nil | NA | NA |  | Meets Expectation
18 | MSB Activities | 2026-04-08 | 2026-04-21 | 26.5 Sprint S3 Stretch | Athi | 52883 | Activities - Parent - Adjust registration status chip display [26.5?] | Product Owner - Verify | 3 |  | 2 | 2026-04-16 | 2026-04-20 | Done | Ram | Nil | Ram | Nil | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation

## 26.5 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.5 Sprint S3 | 26974 Activities - Parent - Enrollments count including withdrawn [26.5] |  | Allen | Defect | As a parent, when I log in I am seeing programs my student was withdrawn from counted in the number of Enrollments on the landing page. | Enrollment count is not showing accuretly , incorrect SQL query logic | Minor | Manual | External | Defect Fixed | Existing_Issues |  | Stakeholder
2 | 26.5 Sprint S3 | 52528 Activities - Admin - Universal & Global Search – Support for Special Characters |  | Athinarayanan | Bounceback/Sub-Defect | Special Character [ ] brackets are not working for District Maintenance and FormType Screens, | ] is not considered as escape literal in sql query | Minor | Manual | Internal | Defect Fixed | Development |  | Offshore QA - Manjunath
3 | 26.5 Sprint S3 | 27211 Activities - REGRESSION - Parent - DOB,School and Grade fields shown as modified while updating the registration |  | Ramkumar | Defect | Defect:1 DOB, School, and Grade fields shown as modified while updating the registration. Defect 2: When we enter the text and place the cursor at the beginning of the text cursor automatically go to end of the text. So Couldn't enter the text continuously. | Defect1 : Model validation , Defect 2 : Issue caused by text onchange event | Minor | Manual | Internal | Defect Fixed | Development |  | Offshore QA - Manjunath
4 | 26.5 Sprint S3 | 27171 - Activities - REGRESSION - Parent - Facing "haspendingUpdates" error while refreshing the screen |  | Athinarayanan | Defect | Issue: Facing "haspendingUpdates" error while refreshing the screen. Issue2: When the ‘From Date’ field is cleared, the ‘To Date’ field is automatically populated with a date in Payment History Page. | Null check is not handled | Minor | Manual | Internal | Defect Fixed | Development |  | Offshore QA - Manjunath
5 | 26.5 Sprint S3 | 27160 - Activities - Admin - Calendar Modal is not working properly, when we select year or month and then use scroll bar |  | Allen | Defect | Calendar modal is not working properly, when we select year or month and then use the scroll bar the dropdown closes. This happens throughout the application where Calendar modal is applicable. (see video) | Onchange event is not handled | Minor | Manual | Internal | Defect Fixed | Development |  | Offshore QA - Manjunath
6 | 26.5 Sprint S3 | 27217 Activities - REGRESSION - Parent - Calendar showing space above header |  | Athinarayanan | Defect | With calendar turned on for parent. We are getting a space between the top of the container and the top of the SMTWTFS header. | UI alignment is mismatch while scorll | Minor | Manual | Internal | Defect Fixed | Development |  | Onshore QA - Jeff
7 | 26.5 Sprint S3 | 27212 Activities - Error running the Update Student Counts in the Dynamic Reports |  | Allen | Defect | The query needs to be updated after we changed the description column. This one was missed, and it now errors when running. | Database upgrade | Minor | Manual | External | Defect Fixed | Development |  | Stakeholder
8 | 26.5 Sprint S3 | 27238 - Activities - Regression - Parent - Not able to see Screen "No Student Yet" when no student are available for a parent. |  | Athinarayanan | Defect | Not able to see Screen "No Student Yet" when no student are available for a parent. | Student count validation is missed | Minor | Manual | Internal | Defect Peer Review | Development | This defect found on end of the sprint, its low priority, and development effort is completed, test effort will be carry forward. | Developer- Athinarayanan

## 26.5 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Athi | 52259 | Activities - Kaleida - Update Parent Registration - Schedule Landing Updates | Story Being Tested | 5 | 1 | 2 | 2026-03-11 | 2026-03-23 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47981 | 2026-03-24 | 2026-03-24 | Allen | Nil | Ethan | 2026-03-25 | Nil | Approved. POV Comments: When two different calendar activities are scheduled, the system displays similar data for both, instead of distinct activity details. Download - Empty PDF is downloading | Approved. During POV additional scope is added to the story | This story is carry forward to next sprint due to team got blocker as all lower environment were down for two days during this sprint. So Test effort will be carry forward. | Meets Expectation
2 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Ram | 27042 | Activities - Kaleida - Parent Withdraw/Transferred UI - Verbiage Cutoff | Defect Fixed | 3 | 1 | 4 | 2026-03-25 | 2026-03-25 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48020 | 2026-03-25 | 2026-03-25 | Allen | Nil | Ethan | 2026-03-25 | Nil | NA | NA |  | Meets Expectation
3 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Allen | 27051 | Activities - Parent - Physician's Name field not allowing spaces | Defect Fixed | 2 | 2 | 4 | 2026-03-25 | 2026-03-25 | Done | Athi | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48027 | 2026-03-25 | 2026-03-25 | Allen | Nil | Ethan | 2026-03-25 | Nil | NA | NA |  | Meets Expectation
4 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Athi | 52475 | Activities - Kaleida - Admin Breadcrumbs [V1] | Story Completed | 3 | 2 | 6 | 2026-03-25 | 2026-03-25 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48088 | 2026-03-27 | 2026-03-30 | Allen | Nil | Ethan | 2026-03-30 | Nil | POV Comments: Breadcrumb is displaying wrongly 1. Activities > Edit > Displays Details 2. Enrollment Plan> Edit > EP name is missing 3. Roles> Edit > Role name missing 4.Security Groups> Edit> Display Details Suggestions: Include District Name for District Breadcrumb and Include View Job Request Queue and View Config props - Breadcrumb links. Approved | Approved |  | Meets Expectation
5 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Ram | 52049 | Activities - Kaleida - Update Parent Registration Design (Contacts) | Story Completed | 8 | 7 | 29 | 2026-03-26 | 2026-03-31 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48196 | 2026-04-02 | 2026-04-02 | Allen | Nil | Ethan | 2026-04-02 | Nil | POV comment: The delete modal popup is animated when clicking the delete contact icon. Approved | Approved |  | Meets Expectation
6 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Allen | 52284 | Activities - App Switcher - Show for HSS users at system level | Story Completed | 1 | 1 | 2 | 2026-03-25 | 2026-03-26 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48213 | 2026-04-02 | 2026-04-02 | Allen | Nil | Ethan | 2026-04-02 | Nil | Approved. | Approved. |  | Meets Expectation
7 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Allen | 52432 | Activities - Config Props - Add the ability to access config props at the system level | Story Completed | 3 | 2 | 9 | 2026-03-25 | 2026-03-27 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48213 | 2026-04-02 | 2026-04-02 | Allen | Nil | Ethan | 2026-04-03 | Should this be updated to use the GetGlobalConfigPropValue/GetConfigPropValue methods instead of the Tenant.ConfigPropCache.GetConfigPropValue method? Are there other areas within the application that need to be updated? Per the above suggestion, I don't think there is a reason to do the user check. I believe we should just be able to call to the GetGlobalConfigPropValue method regardless | POV comment: App switcher config props not working for following cases: 1. I haven’t configured the App Switcher in Config Props at both the system level and the tenant level , but the app tray icon is still showing for HSS User . 2. Set the config prop App Switcher false at district level, and true at system level and Log in as an HSS user, do not select any districts, go directly to HSS > Configprops page, and click the App Switcher icon — the app tray does not open. 3. Set the config prop App Switcher to true at both the system level and the tenant level for my Kanchana sandbox district. I could not see the App Switcher icon for the tenant-level. | Approved | We got sugesstion as CRC to add cache for system level config and remove the user check validation and call the mentioned methods | Meets Expectation
8 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Athi | 52461 | Activities - Kaleida - Update Parent Registration - Schedule Status indicator | Story Being Tested | 5 | 3 | 12 | 2026-03-26 | 2026-03-30 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48198 | 2026-04-02 | 2026-04-02 | Allen | Nil | Ethan | 2026-04-02 | Nil | POV comment: Incomplete and Complete status showing at the same time. Approved | Approved | This story is carry forward to next sprint due to team got blocker as all lower environment were down for two days during this sprint. So Test effort will be carry forward. | Meets Expectation
9 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 | Allen | 52431 | Activities - Admin - Calendar not displaying properly | Story Completed | 5 | 3 | 13 | 2026-03-25 | 2026-03-27 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48173 | 2026-04-01 | 2026-04-01 | Allen | Nil | Ethan | 2026-04-02 | Nil | POV comment: Opening the calendar does not close it when switching tabs. Approved | Approved |  | Meets Expectation
10 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 Stretch | Ram | 52410 | Activities - Admin - Preview EP Forms Errors | Story Completed | 3 | 1 | 4 | 2026-04-02 | 2026-04-03 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48219 | 2026-04-03 | 2026-04-03 | Allen | Nil | Ethan | 2026-04-03 | Nil | NA | NA |  | Meets Expectation
11 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 Stretch | Allen | 52480 | Activities - Parent - Land on Enrollments page after submitting a registration | Story Being Tested | 2 | 1 | 1 | 2026-04-01 | 2026-04-01 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/48250 | 2026-04-06 | 2026-04-06 | Allen | Nil | Ethan | 2026-04-06 | Nil | Approved. | Approved. |  | Meets Expectation
12 | MSB Activities | 2026-03-25 | 2026-04-07 | 26.5 Sprint S2 Stretch | Athi | 52048 | Activities - Admin - Redirect buttons to previous screens | Product Owner - Verify | 5 | 3 | 12.5 | 2026-03-31 | 2026-04-02 | Done | Ram | Nil | Ram | Nil | NA | NA | NA | NA | NA | NA | NA | NA | Pending | Pending |  | Meets Expectation

## 26.5 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.5 Sprint S2 | 27051 Activities - Parent - Physician's Name field not allowing spaces |  | Ram | Defect | As a logged in parent registering their student for an Enrollment Plan with the Physician's Name Stock Custom Field set as required, I am unable to enter a full name (First and Last Names) because I am not able to use spaces. | We removed the space in the entered text to handle the field validations in the UI | Minor | Manual | Internal | Defect Fixed | Development |  | Onshore PO - Kristy
2 | 26.5 Sprint S2 | 27042 Activities - Kaleida - Parent Withdraw/Transferred UI - Verbiage Cutoff |  | Ram | Defect | Withdraw/Transferred - Displayed in the new design, but the verbiage cutoff; needs to be greyed out, and the checkbox should either be disabled or hidden. | This verbiage text needs to remove and use the vegachip . Its UI change request. | Minor | Manual | Internal | Defect Fixed | Development |  | Offshore PO - Kanchana
3 | 26.5 Sprint S3 | 26974 Activities - Parent - Enrollments count including withdrawn [26.5] |  | Allen | Defect | As a parent, when I log in I am seeing programs my student was withdrawn from counted in the number of Enrollments on the landing page. | Enrollment count is not showing accuretly , incorrect SQL query logic | Minor | Manual | External | Defect Verified | Existing_Issues | This defect is added on stretch with low priority, which is carry forwarded to next sprint main commit | Stakeholder

## 26.5 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
0
1 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Ram | 51885 | Activities - Kaleida - Update Parent Registration - Add/Edit Student Info [26.5] | Story Completed | 2 | 2 | 7 | 2026-02-25 | 2026-03-03 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47558 | 2026-03-05 | 2026-03-06 | Allen | Nil | Ethan | 2026-03-09 | Remove unused imports | Approved. | Approved. | CRC Suggestion : Which requested to remove unused imports | Meets Expectation
2 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Ram | 51671 | Activities - Kaleida - Update Parent Registration Design (Your Info) | Story Completed | 5 | 4 | 17.5 | 2026-03-13 | 2026-03-16 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47829 | 2026-03-16 | 2026-03-16 | Allen | Nil | Ethan | 2026-03-16 | Nil | Nil | Nil | Nil | Meets Expectation
3 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Athi | 52259 | Activities - Kaleida - Update Parent Registration - Schedule Landing Updates | Story Peer Review | 8 | 7 | 28 | 2026-03-11 | 2026-03-23 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47981 | 2026-03-24 | NA | NA | NA | NA | NA | NA | Approved. POV Comments: When two different calendar activities are scheduled, the system displays similar data for both, instead of distinct activity details. Download - Empty PDF is downloading | Approved. During POV additional scope is added to the story | This story is being carried forward to the testing phase only due to a last-minute design change request that modified the originally accepted design specifications and acceptance criteria.The client stakeholder has been informed and acknowledges the current status and the revised scope resulting from the design change | Meets Expectation
4 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Allen | 26946 | Activites - Admin - Bulk Copy/Edit Selector issues | Defect Fixed | 1 | 1 | 0.5 | 2026-03-09 | 2026-03-09 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47708 | 2026-03-09 | 2026-03-10 | Allen | Nil | Ethan | 2026-03-10 | Nil | NA | NA |  | Meets Expectation
5 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Allen | 51918 | Activities - Admin - Remove Header Text from Registrations Table Grid [26.5] | Story Completed | 1 | 1 | 4 | 2026-02-25 | 2026-02-25 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47545 | 2026-03-02 | 2026-03-02 | Allen | Nil | Andy | 2026-03-03 | Nil | Approved | Approved |  | Meets Expectation
6 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Allen | 52010 | Activities - Admin - Parent Accounts - Registrations Tab > Status (Pending, Waitlisted) Navigate to the Review page [26.5] | Story Completed | 1 | 1 | 4 | 2026-02-25 | 2026-02-26 | Done | Athi | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47566 | 2026-03-02 | 2026-03-02 | Allen | Nil | Andy | 2026-03-03 | 1. Both sides of the result of this conditional operator look the same outside of casing, IsActiveTerm (uppercase i) and isActiveTerm (lowercase i). Looking at the model it seems like we should be using isActiveTerm, is there a reason I'm not considering that we need this check? If we're getting the incorrect casing coming back from the API we may need to add [JsonProperty("isActiveTerm") to the property declaration or otherwise correct the issue from the server. 2. Similar question here as above, were you seeing inconsistent casing from the server? I think we're missing the [JsonProperty(...) attribute on the server side model declaration if that is the case | If the term is inactive but the registration is still pending or waitlisted, should we redirect to the Registrations Review page, or continue redirecting to the View All page (as per our current behavior)? Approved | Include: "This Registration is no longer valid, as it is not associated with an active program." | Both observations from the CRC are hereby noted as suggestive improvements. The recommendations encompass: (i) case sensitivity validation, and (ii) JSON attribute integration within the Modal component. This user story is designated for delivery in Release 26.5. | Meets Expectation
7 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Allen | 26913 | Activities - Admin - Preview EP Forms Errors | Defect Rejected | 2 | 2 | 8 | 2026-03-12 | 2026-03-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This defect will be consider as new feature in next sprint as a story based on our analysis. So this defect is rejected now. | Meets Expectation
8 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Athi | 43597 | Activities - Admin - Universal Search for Student Purchases | Story Completed | 2 |  |  | 2026-03-02 | 2026-03-06 | Done | Ram | NA | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47858 | 2026-03-17 | 2026-03-17 | Allen | Nil | Andy | 2026-03-17 | Nil | The drop-down list shows ‘Loading...’ when there is no data for Purchase and Student universal search. However, in the Staging/PROD environments, this issue does not occur in Universal Search for Student. I can see it in DEV and QA. Common search is only retrieving data for the enrollment plan & Amount column and not for other columns (Purchase Date, Period). I am getting a ‘Forbidden’ error when I search using Start Date and End Date in the dev environment. | update placeholder text to "Search Purchases" (capitalize the P in purchases) | This Internal POV comment will not covered in the story scope, will be addressed in another story | Meets Expectation
9 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Allen | 52069 | Activities - Admin - Calendar not displaying properly (DISCOVERY) | Story Completed | 3 | 3 | 15 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This is discovery story | Meets Expectation
10 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 | Athi | 52248 | Activities - Kaleida - Admin Breadcrumbs | Story Completed | 3 |  |  | 2026-02-25 | 2026-02-26 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47574 | 2026-03-05 | 2026-03-09 | Allen | Nil | Ethan | 2026-03-09 | Should this have a breadcrumbCaption? Could you change the caption value as well? Curiosity question: Are we displaying the text "EnrollmentName" to end users? If so, is there a reason it is that format instead of "Enrollment Name" (space between the words)? Is this the correct breadcrumbCaption? Most have been shorter/same length as the caption, but this one is longer? Is this the correct breadcrumbCaption? Most have been shorter/same length as the caption, but this one is longer? | Given POV comments for few section . Approved | Approved | Ethan, as a new member of the team, inquired about these changes, and we provided him with a detailed explanation of the requirements. | Meets Expectation
11 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 Stretch | Ram | 52049 | Activities - Kaleida - Update Parent Registration Design (Contacts) | Story Being Developed | 8 | 1 | 2 | 2026-03-19 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Activities | 2026-03-11 | 2026-03-24 | 26.5 Sprint S1 Stretch | Allen | 52353 | Activities - Config Props - Add the ability to access config props at the system level (DISCOVERY) | Story Completed | 3 |  |  | 2026-02-23 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This is discovery story

## 26.5 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.5 Sprint S1 | 43597 Activities - Admin - Universal Search for Student Purchases | 43597 | Athinarayanan | Bounceback/Sub-Defect | Numeric values are not searchable for student purchases. | Numeric values considered for amount feild by conditional, now its optimized to support all feild | Significant | Manual | Internal | Defect Fixed | Development |  | OffShore QA - Manjunath
2 | 26.5 Sprint S1 | 43597 Activities - Admin - Universal Search for Student Purchases | 43597 | Athinarayanan | Bounceback/Sub-Defect | Able to see JSON format if we search with start date and end date. | JSON Format as Searhc keyword | Minor | Manual | Internal | Defect Fixed | Development |  | OffShore QA - Manjunath

## 26.3 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
0
1 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 | Allen | 52039 | Activities - App Switcher - Hide button until script loads | Story Completed | 1 | 1 | 2 | 2026-02-25 | 2026-02-25 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47470 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47440 | 2026-02-25 | 2026-02-25 | Allen | Nil | Andy | 2026-02-25 | Nil | NA | NA |  | Meets Expectation
2 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 | Athi | 51662 | Activities - Kaleida - Admin Breadcrumbs [26.5] (Timeboxed) | Story Completed | 5 | 5 | 20 | 2026-02-25 | 2026-02-26 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47574 | 2026-03-05 | 2026-03-09 | Allen | Nil | Ethan | 2026-03-09 | Nil | Given POV comments for few section . | Approved | Hold for 26.5 Release and it is regression sprint | Meets Expectation
3 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 | Allen | 26866 | Activities - Regression - Admin - Facing an error in the Converted Table Grid Audit Log | Defect Fixed | 0 | 1 | 4 | 2026-02-27 | 2026-03-27 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47536 | 2026-02-27 | 2026-02-27 | Allen | Nil | Andy | 2026-02-27 | Nil | NA | NA |  | Meets Expectation
4 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 | Allen/Ram | 26875 | Activities - Regression - Admin - Open operating days default sort, sorting incorrectly | Defect Fixed | 0 | 1 | 1 | 2026-03-04 | 2026-03-04 | Done | Athi | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47601 | 2026-03-04 | 2026-03-04 | Allen | Nil | Ethan | 2026-03-04 | Nil | NA | NA |  | Meets Expectation
5 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 | Allen | 26914 | Activities - Regression - Admin > Setup - Some of the icons are off center | Defect Fixed | 0 | 1 | 2 | 2026-03-06 | 2026-03-06 | Done | Athi | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47659 | 2026-03-06 | 2026-03-06 | Allen | Nil | Ethan | 2026-03-07 | Nil | NA | NA |  | Meets Expectation
6 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 Stretch | Ram | 51885 | Activities - Kaleida - Update Parent Registration - Add/Edit Student Info [26.5] | Story Ready For Testing | 8 | 7 | 30 | 2026-02-25 | 2026-03-03 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47558 | 2026-03-05 | 2026-03-06 | Allen | Nil | Ethan | 2026-03-09 | Remove unused imports | Nil | Nil | CRC Suggestion : Which requested to remove unused imports Hold for 26.5 Release | Meets Expectation
7 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 Stretch | Allen | 51918 | Activities - Admin - Remove Header Text from Registrations Table Grid [26.5] | Story Ready For Testing | 1 | 1 | 2 | 2026-02-25 | 2026-02-25 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47545 | 2026-03-02 | 2026-03-02 | Allen | Nil | Andy | 2026-03-03 | Nil | Approved | Approved | Hold for 26.5 Release | Meets Expectation
8 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 Stretch | Allen | 52010 | Activities - Admin - Parent Accounts - Registrations Tab > Status (Pending, Waitlisted) Navigate to the Review page [26.5] | Story Ready For Testing | 5 | 2 | 8 | 2026-02-25 | 2026-02-26 | Done | Athi | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47566 | 2026-03-02 | 2026-03-02 | Allen | Nil | Andy | 2026-03-03 | 1. Both sides of the result of this conditional operator look the same outside of casing, IsActiveTerm (uppercase i) and isActiveTerm (lowercase i). Looking at the model it seems like we should be using isActiveTerm, is there a reason I'm not considering that we need this check? If we're getting the incorrect casing coming back from the API we may need to add [JsonProperty("isActiveTerm") to the property declaration or otherwise correct the issue from the server. 2. Similar question here as above, were you seeing inconsistent casing from the server? I think we're missing the [JsonProperty(...) attribute on the server side model declaration if that is the case | If the term is inactive but the registration is still pending or waitlisted, should we redirect to the Registrations Review page, or continue redirecting to the View All page (as per our current behavior)? Approved | Include: "This Registration is no longer valid, as it is not associated with an active program." | Both observations from the CRC are hereby noted as suggestive improvements. The recommendations encompass: (i) case sensitivity validation, and (ii) JSON attribute integration within the Modal component. This user story is designated for delivery in Release 26.5. | Meets Expectation
9 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 Stretch | Athi | 43597 | Activities - Admin - Universal Search for Student Purchases [26.5] | Product Owner - Verify | 5 | 5 | 20 | 2026-03-02 | 2026-03-06 | Done | Ram | NA | Ram | Nil | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | POV and QA will be carry forward to next sprint.Target to 26.5 Release | Meets Expectation
10 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 Stretch | Allen | 52070 | Activities - Parent - API token expiring before user session [26.5] | Story Completed | 5 | 3 | 12 | 2026-02-25 | 2026-03-03 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This issue could not be reproduced in the QA environment or other environments, with the issue observed only in the development environment. Consequently, this story will be closed. | Meets Expectation
11 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 Stretch | Athi | 52219 | Activities - Kaleida - Parent Registration Design Schedule w/o Calendar Updates (DISCOVERY) [Timebox] | Story Completed | 1 | 1 | 4 | 2026-03-10 | 2026-03-10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | The Discovery document and points added in the story note section
12 | MSB Activities | 2026-02-25 | 2026-03-10 | 26.3 Sprint S3 Stretch | Allen | 26946 | Activites - Admin - Bulk Copy/Edit Selector issues | Defect Being Fixed | 1 | 1 | 0.5 | 2026-03-09 | 2026-03-09 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47708 | 2026-03-09 | 2026-03-10 | Allen | Nil | Ethan | NA | NA | NA | NA | Carried to next sprint Main commit

## 26.3 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.3 Sprint S3 | 26866 Activities - Regression - Admin - Facing an error in the Converted Table Grid Audit Log |  | Allen | Defect | Facing an error while clicking on the audit log for the converted table grid . Following are the pages 1.Activities. 2.Form type. 3.Student maintenance. 4.Custom Field Maintenance. | Missed the Data test id in the custom data grid component | Significant | Manual | Internal | Defect Fixed | Development |  | OffShore Dev - Athinarayanan
2 | 26.3 Sprint S3 | 26875 Activities - Regression - Admin - Open operating days default sort, sorting incorrectly |  | Athinarayanan | Defect | The default sorting for the district level open operating days should by default sort by the newest day to the oldest day | We had primary sorting initially and now we are implementing secondary sorting as well | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing PROD Issue. | OffShore PO- Kanchana
3 | 26.3 Sprint S3 | 26914 Activities - Regression - Admin > Setup - Some of the icons are off center |  | Allen | Defect | On the Admin > Setup page, some of the icons are slightly off center. Specifically, the Fee Items, Custom Fields, and Kiosk Maintenance icons have this issue. | Tiles Icons is not aligned centerly. | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing PROD Issue. | Onsite Manager - Ethan Coggin
4 | 26.3 Sprint S3 Stretch | 26946 - Activites - Admin - Bulk Copy/Edit Selector issues |  | Allen | Defect | We Internally found a couple issues with the selector for bulk copy/edit (see videos) | Existing production issue | Minor | Manual | External | Defect Being Fixed | Existing_Issues | Existing PROD Issue. Carry to next sprint | Onsite lead - Allen Xavier

## 26.3 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
0
1 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Allen | 51752 | Activities - Admin - Filter Completed with Errors in JobRequest DataGrid | Story Completed | 1 | 2.5 | 9 | 2026-02-02 | 2026-02-05 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47285 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47405 | 2026-02-17 | 2026-02-17 | Allen | Nil | Andy | 2026-02-18 | Nil | Approved | Approved |  | Meets Expectation
2 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Ram | 51787 | Activities - SYSTEM - Update Vega component to Latest Version | Story Completed | 1 | 1 | 4 | 2026-02-11 | 2026-02-11 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47174 | 2026-02-10 | 2026-02-11 | Allen | Nil | Andy | 2026-02-11 | Nil | NA | NA |  | Meets Expectation
3 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Allen | 51847 | Activities - Kaleida - Update table grid design for Students & Contacts >Missing Tabs | Story Completed | 1 | 1 | 4 | 2026-02-10 | 2026-02-11 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47211 | 2026-02-12 | 2026-02-12 | Allen | Nil | Andy | 2026-02-12 | Nil | Given POV comments | Approved |  | Meets Expectation
4 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Allen | 51849 | Activities - Kaleida - Update table grid design for Enrollment Plan tabs (Required Forms,Discount & Activity Prices) | Story Completed | 1 | 1 | 4 | 2026-02-10 | 2026-02-11 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47208 | 2026-02-12 | 2026-02-12 | Allen | Nil | Andy | 2026-02-12 | Nil | Approved | Approved |  | Meets Expectation
5 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Allen | 51886 | Activities - Kaleida - Update New design for Registrations> Enrollments | Story Completed | 1 | 1 | 4 | 2026-02-10 | 2026-02-11 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47211 | 2026-02-12 | 2026-02-12 | Allen | Nil | Andy | 2026-02-12 | Nil | Given POV comments | Approved |  | Meets Expectation
6 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Allen | 51887 | Activities - Kaleida - Update table grid design for People > Documents Tab | Story Completed | 1 | 1 | 4 | 2026-02-10 | 2026-02-11 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47211 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47246 | 2026-02-12 | 2026-02-12 | Allen | Nil | Andy | 2026-02-12 | Nil | Given POV comments | Approved |  | Meets Expectation
7 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Athi | 51807 | Activities - Kaleida - Parent Breadcrumb UI | Story Completed | 2 | 1 | 1.5 | 2026-01-28 | 2026-02-05 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47228 | 2026-02-13 | 2026-02-13 | Allen | Nil | Andy | 2026-02-13 | Nil | Given POV comments | Approved |  | Meets Expectation
8 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Athi | 51256 | Activities - Kaleida - Update Parent Footer (Kiosk PIN & Payment History Report) | Story Completed | 3 | 1 | 4 | 2026-02-11 | 2026-02-11 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47229 | 2026-02-13 | 2026-02-13 | Allen | Nil | Andy | 2026-02-13 | Nil | Given POV comments | Approved |  | Meets Expectation
9 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Ram | 51809 | Activities - Kaleida - Convert Class Components → Functional Components for Student Info | Story Completed | 1 | 1 | 4 | 2026-02-11 | 2026-02-11 | Done | Athi | Nil | Athi | Nil | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Development completed , PR will addressed with Parent Story 51670 Activities - Kaleida - Update Parent Registration - Student Info Card Component Creation | Meets Expectation
10 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Allen | 51837 | Activities - Admin App Switcher - Updates to initializing HSSAppTray [26.2.1 dot Release] | Story Completed | 5 | 1 | 3 | 2026-02-10 | 2026-02-11 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47200 | 2026-02-12 | 2026-02-12 | Allen | Nil | Andy | 2026-02-12 | Nil | NA | NA |  | Meets Expectation
11 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 | Ram | 51670 | Activities - Kaleida - Update Parent Registration - Student Info Card Component Creation | Story Completed | 8 | 7 | 28 | 2026-02-12 | 2026-02-17 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47378 | 2026-02-19 | 2026-02-20 | Allen | Nil | Andy | 2026-02-23 | Nil | Nil | Nil |  | Meets Expectation
12 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 Stretch | Ram | 51885 | Activities - Kaleida - Update Parent Registration - Add/Edit Student Info | Story Being Developed | 8 | 1 | 4 | 2026-02-23 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Meets Expectation
13 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 Stretch | Athi | 51662 | Activities - Kaleida - Admin Breadcrumbs | Story Being Developed | 8 | 4 | 16 | 2026-02-12 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Meets Expectation
14 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 Stretch | Allen | 51753 | Activities - Kaleida - Hide Inactive Districts from Parent Selection | Story Completed | 5 | 4 | 16 | 2026-02-16 | 2026-02-18 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47429 | 2026-02-21 | 2026-02-21 | Allen | Nil | Andy | 2026-02-23 | Nil | Given POV comments - Not handled for Single tenant | Approved |  | Meets Expectation
15 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 Stretch | Athi | 26810 | Activities - Admin - Calendar not displaying properly for transfer/withdraw modal | Defect Fixed | 1 | 1 | 2 | 2026-02-17 | 2026-02-17 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47300 | 2026-02-17 | 2026-02-17 | Allen | Nil | Andy | 2026-02-17 | Nil | NA | NA |  | Meets Expectation
16 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 Stretch | Allen | 26788 | Activities - Admin - Status column in the Parent Accounts of the Registrations tab displays numeric values. | Defect Fixed | 2 | 2 | 6 | 2026-02-17 | 2026-02-19 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47246 | 2026-02-17 | 2026-02-17 | Allen | Nil | Andy | 2026-02-18 | Nil | NA | NA |  | Meets Expectation
17 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 Stretch | Allen | 26811 | Activities - Parent - API token expiring before user session | Defect Being Fixed | 1 |  |  | 2026-02-23 | 2026-02-24 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | During planning discussions, we decided to convert it into a story and move it to the next sprint stretch.
18 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 Stretch | Allen/Ram | 26824 | Activities - Admin - Universal search freezing when returning : from query | Defect Fixed | 2 | 1 | 2 | 2026-02-18 | 2026-02-19 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47382 | 2026-02-19 | 2026-02-19 | Allen | Nil | Andy | 2026-02-19 | Can you add a comment to each of the regex replaces to explain what they are looking for to make this easier if we ever have to modify them, or move these into helper functions similar to the escape SQL characters one and comment the function? | NA | NA | Suggestions from client to add comments in code for future understanding | Meets Expectation
19 | MSB Activities | 2026-02-11 | 2026-02-24 | 26.3 Sprint S2 Stretch | Allen | 52039 | Activities - App Switcher - Hide button until script loads | Story Being Developed | 1 | 1 | 2 | 2026-02-23 | 2026-02-23 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47440 | 2026-02-23 | 2026-02-23 | Allen | Nil | Andy | 2026-02-23 | Nil | NA | NA | Moved to Next sprint Main | Meets Expectation

## 26.3 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.3 Sprint S2 | 51887 Activities - Kaleida - Update table grid design for People > Documents Tab | 51887 | Allen | Bounceback/Sub-Defect | View icon is only working for pdf files and not working for photo | During the process of resolving a merge conflict, an issue was introduced due to incorrect or incomplete integration of code changes from different branches. | Significant | Manual | Internal | Story Completed | Development |  | Offshore QA - Manjunath
2 | 26.3 Sprint S2 Stretch | 26788 Activities - Admin - Status column in the Parent Accounts of the Registrations tab displays numeric values. |  | Allen | Defect | The Status column in the Parent Accounts of the Registrations tab displays numeric values, such as 3 or 5. | The mapping between the enum value and its corresponding display string was not implemented or was incorrectly handled. | Significant | Manual | Internal | Defect Fixed | Development |  | Offshore PO - Kanchana
3 | 26.3 Sprint S2 Stretch | 26810 Activities - Admin - Calendar not displaying properly for transfer/withdraw modal. |  | Athinarayanan | Defect | A recent CSS change is causing the calendar modal to not display properly | Date picker is not displayed properly in Modal popup | Significant | Manual | External | Defect Fixed | Existing_Issues | PROD Issue: This issue was raised due to the fix for adjusting padding and spacing in the modal pop-up during an earlier sprint. | Offshore PO - Kanchana
4 | 26.3 Sprint S2 Stretch | 26824 Activities - Admin - Universal search freezing when returning : from query |  | Allen | Defect | In admin if you perform a search with the character : the input box freezes and the grid does not refresh with the filtered data. It looks to only occur when the grid actually contains the character : (so the EP name has 1:00 it would cause the search to not function properly) | The search query lacked proper input validation, allowing invalid or unexpected values to be processed, which led to invalid results. | Minor | Manual | Internal | Defect Fixed | Development |  | Onsite QA - Jeff
5 | 26.3 Sprint S2 Stretch | 26811 Activities - Parent - API token expiring before user session |  | Allen | Defect | After logging into parent, after 15 minutes expires, the get district modal is not being retrieved. It looks to be an issue with the API token to MSB expiring before the users session | Access token is getting expired | Significant | Manual | External | Defect Being Fixed | Existing_Issues | PROD Issue: Existing Issue from MSB Token and converted as Story in next sprint | Onsite QA - Jeff
6 | 26.3 Sprint S2 | 51752 - Activities - Admin - Filter Completed with Errors in JobRequest DataGrid | 51752 | Athinarayanan | Bounceback/Sub-Defect | Search is not getting retained, while we go to next page and get back | The data table was not refreshed appropriately after executing the search query, resulting in outdated or incorrect data being displayed to the user. | Significant | Manual | Internal | Defect Fixed | Development |  | Offshore QA - Manjunath
7 | 26.3 Sprint S2 | 51752 - Activities - Admin - Filter Completed with Errors in JobRequest DataGrid | 51752 | Athinarayanan | Bounceback/Sub-Defect | Completed with error status records also shown in the table grid even if we are not selected in the status filter | The logic used to compare the filter keyword in the data table was incorrect, resulting in improper filtering and inaccurate search results being displayed to the user | Significant | Manual | Internal | Defect Fixed | Development |  | Offshore QA - Manjunath

## 26.3 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
0
1 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 | Allen | 26675 | Activities - Term Enrollment Plans - Action menu text alignment | Defect Fixed | 1 | 1 | 3 | 2026-01-28 | 2026-02-05 | Done | Athi | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46894 | 2026-01-28 | 2026-01-29 | Allen | Nil | Andy | 2026-01-29 | Nil | NA | NA |  | Meets Expectation
2 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 | Athi | 51254 | Activities - Kaleida - Update Parent Payment History Design [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-16 | 2026-01-21 | Done | Kaliammal/Sivaraja | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46835 | 2026-01-23 | 2026-01-28 | Allen | Nil | Andy | 2026-01-29 | Suggestion, Remove the scorllbar | Given POV comments. Approved | Approved | Dev is completed in Last Sprint , it just carry forward for testing only | Meets Expectation
3 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 | Nathiya | 51255 | Activities - Kaleida - Update Parent Kiosk PIN Design [26.3] | Story Completed | 1 | 1 | 4 | 2025-12-24 | 2025-12-31 | Done | Ram,Kaliammal | Nil | Ram,Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46513 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46972 | 2026-01-08 | 2026-01-28 | Allen | Nil | Andy | 2026-01-29 | Nil | Nil | Approved | Dev is completed in Last Sprint , it just carry forward for testing only | Meets Expectation
4 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 | Kaliammal | 51367 | Activities - Kaleida - Update table grid design for Enrollment Plans/ Activities/ Discounts [26.3] | Story Completed | 2 | 1 | 3 | 2026-01-01 | 2026-01-14 | Done | Ram,Nathiya | Nil | Ram,Nathiya | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46619 | 2026-01-23 | 2026-01-28 | Allen | Nil | Andy | 2026-01-28 | Nil | Nil | Nil | Dev is completed in Last Sprint , it just carry forward for testing only | Meets Expectation
5 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 | Ram | 51667 | Activities - Tech Debt - Create Shared Folder for Parent Shared Component | Story Completed | 2 | 1 | 3 | 2026-01-16 | 2026-01-27 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46872 | 2026-01-27 | 2026-01-28 | Allen | Nil | Andy | 2026-01-28 | Nil | NA | NA | Dev is completed in Last Sprint , it just carry forward for testing only | Meets Expectation
6 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 | Nathiya | 51178 | Activities - Kaleida - Parent - Remove "Loading message" with New Spinning Loader Design[26.3] | Story Completed | 3 | 2 | 8 | 2026-01-28 | 2026-01-29 | Done | Sivaraj | Nil | SivaRaja,Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46937 | 2026-01-30 | 2026-01-31 | Allen | Nil | Andy | 2026-01-31 | Nil | Approved | Approved |  | Meets Expectation
7 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 | Athi | 51167 | Activities - Kaleida - Breadcrumb in the Parent UI (DISCOVERY & DEV) | Story Completed | 8 | 8 | 32 | 2026-01-28 | 2026-02-05 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Discovery and Dev work is completed | Meets Expectation
8 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 | Ram | 51659 | Activities - Kaleida - Update Parent Registration Design (DISCOVERY) | Story Completed | 8 | 8 | 32 | 2026-01-28 | 2026-02-05 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Discovery completed and document updated in Axosoft | Meets Expectation
9 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Nathiya | 51472 | Activities - Admin - Implement the Existing Global Search to be Replaced with Universal Search (Backend) | Story Completed | 3 |  | 1 | 2026-01-19 | 2026-01-23 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46912 | 2026-02-02 | 2026-02-02 | Allen | Nil | Andy | 2026-02-02 | Nil |  |  |  | Meets Expectation
10 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51573 | Activities - Kaleida - Update table grid design for Roles/Users/Security Groups/District ACL [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-30 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46969 | 2026-01-30 | 2026-01-30 | Allen | Nil | Andy | 2026-01-30 | Nil |  |  |  | Meets Expectation
11 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51574 | Activities - Kaleida - Update table grid design for Form Types/Kiosk/PIN Maintenance [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-30 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46970 | 2026-01-30 | 2026-01-30 | Allen | Nil | Andy | 2026-01-30 | NIl |  |  |  | Meets Expectation
12 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51488 | Activities - Kaleida - Update table grid design for Student Maintenance [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-02-02 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46912 | 2026-02-02 | 2026-02-02 | Allen | Nil | Andy | 2026-02-02 | Nil |  |  |  | Meets Expectation
13 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen/Athi | 51752 | Activities - Admin - Filter Completed with Errors in JobRequest DataGrid | Story Peer Review | 5 | 3 | 11 | 2026-02-02 | 2026-02-05 | Done | Ram | Nil | Ram | Nil | [11 empty] | Meets Expectation
14 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51596 | Activities - Kaleida - Update table grid design for Parent Accounts (People) [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-28 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46829 | 2026-02-03 | 2026-02-03 | Allen | Nil | Andy | 2026-02-03 | Nil | Nil | Nil |  | Meets Expectation
15 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51597 | Activities - Kaleida - Update table grid design for Others Contacts (People) [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-28 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46792 | 2026-02-03 | 2026-02-03 | Allen | Nil | Andy | 2026-02-03 | Nil | Nil | Nil |  | Meets Expectation
16 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51618 | Activities - Kaleida - Update table grid design for Accounting [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-28 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47024 | 2026-02-03 | 2026-02-03 | Allen | Nil | Andy | 2026-02-03 | Nil | Nil | Nil |  | Meets Expectation
17 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51646 | Activities - Kaleida - Update table grid design for Registrations [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-28 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47019 | 2026-02-03 | 2026-02-03 | Allen | Nil | Andy | 2026-02-03 | Nil | Nil | Nil |  | Meets Expectation
18 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51656 | Activities - Kaleida - Update table grid design for Home Screen(District/Site)/Events [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-28 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47026 | 2026-02-03 | 2026-02-03 | Allen | Nil | Andy | 2026-02-04 | Nil | Nil | Nil |  | Meets Expectation
19 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51657 | Activities - Kaleida - Update table grid design for Operating Days [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-28 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/47021 | 2026-02-03 | 2026-02-03 | Allen | Nil | Andy | 2026-02-03 | Nil | Nil | Nil |  | Meets Expectation
20 | MSB Activities | 2026-01-28 | 2026-02-10 | 26.3 Sprint S1 Stretch | Allen | 51572 | Activities - Kaleida - Update table grid design for Fee Items/Custom Fields/Sites [26.3] | Story Completed | 1 | 1 | 1 | 2026-01-28 | 2026-01-28 | Done | Ram | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46791 | 2026-02-03 | 2026-02-03 | Allen | Nil | Andy | 2026-02-03 | Nil | Nil | Nil

## 26.3 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.3 Sprint S1 | 26675 | 26675 | Allen | Defect | 26675 - Activities - Term Enrollment Plans - Action menu text alignment | UI Changes caused Alignmant issue | Minor | Manual | Internal | Story Completed | Design |  | Offshore - Kanchana
2 | 26.3 Sprint S1 | 51255 | 51255 | Nathiya | Bounceback/Sub-Defect | 51255 - Activities - Kaleida - Update Parent Kiosk PIN Design [26.3] | UI Changes caused Alignmant issue | Minor | Manual | Internal | Story Completed | Design |  | Offshore QA - SivaMohan
3 | 26.3 Sprint S1 | 51574 | 51574 | Allen | Bounceback/Sub-Defect | We are able to checkin for past date, Even if have have tooltip notification. |  | Significant | Manual | Internal | Story Completed | Development |  | Offshore QA - Manjunath
4 | 26.3 Sprint S1 | 51597 | 51597 | Allen | Bounceback/Sub-Defect | We are able to see two search field in the screen |  | Significant | Manual | Internal | Story Completed | Development |  | Offshore QA - Manjunath
5 | 26.3 Sprint S1 | 51646 | 51646 | Allen | Bounceback/Sub-Defect | Facing No record found issue when we click on table grid record |  | Significant | Manual | Internal | Story Completed | Development |  | Offshore QA - Manjunath

## 26.2 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2026-01-14 | 2026-01-27 | 26.2 Sprint S3 | Sivaraja | 51138 | Activities - Non Student Registration - Update validation for checking for students in the msb household | Story Completed | 2 | 1 | 4 | 2025-12-18 | 2026-01-06 | Done | Ram,Kaliammal | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46602 | 2026-01-12 | 2026-01-12 | Allen | Nil | Done | 2026-01-13 | Nil | Nil | Nil | Nil | Meets Expectation
2 | MSB Activities | 2026-01-14 | 2026-01-27 | 26.2 Sprint S3 | Allen | 51279 | Activities - Kaleida - Update table grid design for Term Maintenance [26.3] | Story Completed | 2 | 2 | 8 | 2025-12-12 | 2025-12-14 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46584 | 2026-01-14 | 2026-01-15 | Allen | Nil | Andy | 2026-01-15 | Nil | Nil | Nil |  | Meets Expectation
3 | MSB Activities | 2026-01-14 | 2026-01-27 | 26.2 Sprint S3 | Allen | 51332 | Activities - Kaleida - Admin - Component Creation for Editable Grid Table with Updated Design [26.3] | Story Completed | 2 | 1 | 2 | 2025-12-12 | 2025-12-14 | Done | Ram,Nathiya | NIl | Ram,Nathiya | NIl | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46625 | 2026-01-14 | 2026-01-14 | Allen | Nil | Andy | 2026-01-14 | Nil | Nil | NIl |  | Meets Expectation
4 | MSB Activities | 2026-01-14 | 2026-01-27 | 26.2 Sprint S3 | Kaliammal | 51367 | Activities - Kaleida - Update table grid design for Enrollment Plans/ Activities/ Discounts [26.3] | Story Peer Review | 3 | 5 | 20 | 2026-01-01 | 2026-01-14 | Done | Ram,Nathiya | Nil | Ram,Nathiya | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46619 | 2026-01-23 | NA | NA | NA | NA | NA | NA | Given POV Comments. | Nil | During the regression sprint, we completed development and Product Owner verification. The pull request will be merged only after the regression sprint ends. Note: As informed by the client, this story will be carried over to the next sprint for PR merging and testing efforts. | Meets Expectation
5 | MSB Activities | 2026-01-14 | 2026-01-27 | 26.2 Sprint S3 Stretch | Allen | 51489 | Activities - Kaleida - Update table grid design for HSS Maintenance | Story Completed | 3 | 3 | 12 | 2026-01-14 | 2026-01-16 | Done | Ram,Nathiya | Nil | Ram,Nathiya | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46671 | 2026-01-14 | 2026-01-16 | Allen | Nil | Andy | 2026-01-16 | Nil | Nil | Nil |  | Meets Expectation
6 | MSB Activities | 2026-01-14 | 2026-01-27 | 26.2 Sprint S3 Stretch | Nathiya | 51472 | Activities - Admin - Implement the Existing Global Search to be Replaced with Universal Search (Backend) | Story Peer Review | 5 | 5 | 20 | 2026-01-19 | 2026-01-23 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46885 | 2026-01-27 | NA | NA | NA | NA | NA | NA | NA | NA | During the regression sprint, we completed development and Product Owner verification. The pull request will be merged only after the regression sprint ends. Note: As informed by the client, this story will be carried over to the next sprint for PR merging and testing efforts. | Meets Expectation

## 26.2 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised

## 26.2 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 | Sivaraja | 51138 | Activities - Non Student Registration - Update validation for checking for students in the msb household | Story Ready For Testing | 3 | 3 | 12 | 2025-12-17 | 2026-01-06 | Done | Ram, Kaliammal | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46602 | 2026-01-12 | 2026-01-12 | Allen | Nil | Done | 2026-01-13 | Nil | Approved | Approved | Reason – There were dependencies on MSB APIs, which became blockers for this story. The blockers were identified one after another and discussed with Allen and the client developer, Andy, for confirmation. The PR has been approved by Allen and is currently pending approval from the client developer, Andy. Carried to Next Sprint for QA | Meets Expectation
2 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 | Sivaraja | 26419 | Activities - Admin - Validation is missing the start and end time when editing a term activity | Defect Fixed | 1 | 1 | 4 | 2025-12-11 | 2025-12-12 | Done | Ram, Kaliammal | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46261 | 2025-12-11 | 2025-12-19 | Done | Nil | Done | 2025-12-22 | Nil | NA | NA | NA | Meets Expectation
3 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 | Kaliammal | 47253 | Activities - Enrollment Plans - Customizable Column Headers | Story Completed | 5 | 6 | 26 | 2025-12-17 | 2026-01-06 | Done | Sivaraja | Nil | Sivaraja,Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46437 | 2026-01-06 | 2026-01-06 | Done | Nil | Done | 2026-01-08 | Nil | Need to check copy/Edit . | Remove SorBy for regitration Start and End.Status alignment to center | NA | Meets Expectation
4 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 | Kaliammal | 26460 | Activities - Admin - Pending Registrations - Capacity modal appearing when approving non-capacity registrations | Defect Fixed | 1 | 1 | 10 | 2025-12-12 | 2025-12-15 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46263 | 2025-12-17 | 2025-12-20 | Done | Nil | Done | 2025-12-22 | Nil | NA | NA | NA | Meets Expectation
5 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 | Sivaraja | 51079 | Activities - Admin - Upgrade Existing Audit Log to a Table Grid for 'Activities' | Story Completed | 2 | 1 | 3 | 2025-12-04 | 2025-12-05 | Done | Ram | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46162 | 2025-12-11 | 2025-12-11 | Done | Nil | Done | 2025-12-17 | I don't know if we have the ability to do any better, but this would show us the current name of the custom field, not what it was named when it was added, correct? This could cause confusion if fields have been renamed. Is the name not stored as a part of the audit log? | Approved | Approved | NA | Meets Expectation
6 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 | Kaliammal | 51093 | Activities - Admin - Upgrade Existing Audit Log to a Table Grid for 'Custom Fields' | Story Completed | 2 | 1 | 4 | 2025-12-04 | 2025-12-09 | Done | Sivaraja | Nil | Athi,Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46163 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46355 | 2025-12-11 | 2025-12-11 | Done | Nil | Done | 2025-12-10 | I don't know if we have the ability to do any better, but this would show us the current name of the custom field, not what it was named when it was added, correct? This could cause confusion if fields have been renamed. Is the name not stored as a part of the audit log? | Approved | Approved | NA | Meets Expectation
7 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 | Nathiya | 51175 | Activities - Admin - Integrate the Data into Universal Search for Student Maintenanace | Story Completed | 8 | 5.5 | 22 | 2025-12-17 | 2025-12-22 | Done | Sivaraja | Nil | Athi,Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46417 | 2026-01-05 | 2026-01-06 | Allen | Nil | Andy | 2026-01-07 | Nil | Given POV comments. | Approved | NA | Meets Expectation
8 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 | Manju/Siva | 51217 | Activities - SYSTEM - Automation [Timeboxed] | Story Completed | 13 | 13 | 16 | 2025-12-22 | 2026-01-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
9 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 Stretch | Nathiya | 51186 | Activities - Admin - Display a Spinning Loader instead of Message for (Purchases & Fees) Tab | Story Completed | 2 | 1 | 4 | 2025-12-23 | 2025-12-23 | Done | Ram | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46213 | 2025-12-15 | 2026-01-08 | Allen | Nil | Andy | 2026-01-08 | Nil | Approved | Approved |  | Meets Expectation
10 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 Stretch | Allen | 51279 | Activities - Kaleida - Update table grid design for Term Maintenance | Story Peer Review | 8 | 6 | 24 | 2025-12-17 | 2025-12-23 | Done | Ram | Nil | Ram | NIL | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Development has been completed, but the PR is delayed due to pending confirmation from the client. As discussed with the client, we planned to merge the data table grid changes into a separate branch instead of Master. Today, the client developer created a new branch to merge these changes. The testing effort may be carried out after the regression sprint. | Meets Expectation
11 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 Stretch | Nathiya | 51335 | Activities - Students - Update Nickname column label | Story Completed | 1 | 0.5 | 2 | 2025-12-22 | 2025-12-22 | Done | Sivaraja | Nil | Athi,Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46417 | 2026-01-05 | 2026-01-06 | Allen | Nil | Andy | 2026-01-07 | Nil | Approved | Approved | NA | Meets Expectation
12 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 Stretch | Sivaraja | 47410 | Activities - DISCOVERY - Activity Pricing for Prepaid Enrollment Plans | Story Completed | 8 | 6.5 | 26 | 2025-12-29 | 2026-01-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
13 | MSB Activities | 2025-12-17 | 2026-01-13 | 26.2 Sprint S2 Stretch | Kaliammal | 51367 | Activities - Kaleida - Update table grid design for Enrollment Plans/ Activities/ Discounts | Story Peer Review | 8 | 5 | 20 | 2025-12-31 | 2026-01-12 | Done | Sivaraja,Nathiya | Nil | Sivaraja,Nathiya | Nil | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Development has been completed, but the PR is delayed due to pending confirmation from the client. As discussed with the client, we planned to merge the data table grid changes into a separate branch instead of Master. Today, the client developer created a new branch to merge these changes. The testing effort may be carried out after the regression sprint. | Meets Expectation

## 26.2 Sprint 2- Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.2 Sprint S2 | 51093 | 51093 | Kaliammal | Bounceback/Sub-Defect | First column should be field Column in table grid and in custom column header, But when we apply custom column header order changes. | NA | Significant | Manual | Internal | Story Completed | Development | Story Bounceback | Manjunath - Offshore QA
2 | 26.2 Sprint S2 | 51079 | 51079 | Kaliammal | Bounceback/Sub-Defect | First column should be field Column in table grid and in custom column header, But when we apply custom column header order changes. | NA | Significant | Manual | Internal | Story Completed | Development | Story Bounceback | Manjunath - Offshore QA
3 | 26.2 Sprint S2 | 47253 | 47253 | Kaliammal | Bounceback/Sub-Defect | when selecting columns and then navigating away and back, the selector no longer shows the columns selected (but columns do show)(see image) | NA | Minor | Manual | Internal | Story Completed | Development | Story Bounceback | Jeff - Onshore QA

## 26.2 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 | Sivaraja | 45772 | Activities - Admin - Term - Tech Debt Field Validation | Story Completed | 1 | 0.5 | 2.5 | 2025-12-03 | 2025-12-03 | Done | Ram, Kaliammal | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46062 | 2025-12-04 | 2025-12-04 | Done | Nil | Done | 2025-12-05 | Nil | Approved | Approved | NA | Meets Expectation
2 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 | Kaliammal | 51052 | Activities - SYSTEM - Removing the Original Description Columns [PR & QA] | Story Completed | 1 | 1 | 6 | 2025-11-19 | 2025-11-28 | Done | Sivaraja,Athi | Include Report Changes | Sivaraja,Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45981 | 2025-12-01 | 2025-12-02 | Done | Nil | Done | 2025-12-05 | Nil | NA | NA | NA | Meets Expectation
3 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 | Sivaraja | 51038 | Activities - Registration - Prevent starting a registration for a student with a null student number [PR &QA] | Story Completed | 1 | 1 | 4 | 2025-11-19 | 2025-11-26 | Done | Ram, Kaliammal | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46016 Bounce Back: https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46111 Bounce Back: https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46187 | 2025-12-02 | 2025-12-04 | Done | Nil | Done | 2025-12-05 | Nil | Nil | Nil | NA | Meets Expectation
4 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 | Kaliammal | 45765 | Activities - Admin - Form Types -Tech Debt Field Validation | Story Completed | 1 | 0.5 | 2.5 | 2025-12-03 | 2025-12-03 | Done | Sivaraja | Nil | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46052 | 2025-12-04 | 2025-12-04 | Done | Nil | Done | 2025-12-05 | Nil | Approved | Approved | NA | Meets Expectation
5 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 | Nathiya | 51078 | Activities - Admin - Component Creation for Universal Search | Story Completed | 8 | 8 | 34 | 2025-12-03 | 2025-12-08 | Done | Athi,Sivaraja | Nil | Athi,Sivaraja | 1. Remove Unused import 2. Check Null condition for Date Picker 3. To remove the same logic used twice in setTimeout. 4. Suggestion to add keypress event when we click outside of the search panel | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46150 | 2025-12-10 | 2025-12-12 | Done | Nil | Done | 2025-12-15 | Nil | Approved | Approved | NA | Meets Expectation
6 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 Stretch | Sivaraja | 51079 | Activities - Admin - Upgrade Existing Audit Log to a Table Grid for 'Activities' | Story Peer Review | 5 | 3 | 12 | 2025-12-04 | 2025-12-05 | Done | Ram | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46162 | 2025-12-11 | 2025-12-11 | Done | Nil | NA | NA | NA | Approved | Approved | NA | Meets Expectation
7 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 Stretch | Allen | 51076 | Activities - Kaleida - Admin - Component Creation for DataGrid with Updated Design | Story Completed | 5 | 5 | 20 | 2025-12-03 | 2025-12-05 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46092 | 2025-12-05 | 2025-12-09 | Done | Nil | Done | 2025-12-09 | Nil | NA | NA | NA | Meets Expectation
8 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 Stretch | Kaliammal | 51093 | Activities - Admin - Upgrade Existing Audit Log to a Table Grid for 'Custom Fields' | Story Peer Review | 5 | 3 | 14 | 2025-12-04 | 2025-12-09 | Done | Sivaraja | Nil | Athi,Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46163 | 2025-12-11 | 2025-12-11 | Done | Nil | NA | NA | NA | Approved | Approved | NA | Meets Expectation
9 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 Stretch | Sivaraja | 26419 | Activities - Admin - Validation is missing the start and end time when editing a term activity | Defect Peer Review | 2 | 2 | 8 | 2025-12-11 | 2025-12-12 | Done | Ram, Kaliammal | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46162 | 2025-12-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
10 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 Stretch | Kaliammal | 26460 | Activities - Admin - Pending Registrations - Capacity modal appearing when approving non-capacity registrations | Defect Peer Review | 2 | 1 | 4 | 2025-12-12 | 2025-12-15 | Done | Sivaraja |  | Athi | Nil | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
11 | MSB Activities | 2025-12-03 | 2025-12-16 | 26.2 Sprint S1 Stretch | Allen/Athi | 26461 | Activities - Admin - Custom Field - Delete/Add button on dropdown options routing to details screen on first click | Defect Fixed | 2 | 0.5 | 2 | 2025-12-15 | 2025-12-15 | Done | Kaliammal | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46220 | 2025-12-15 | 2025-12-15 | Done | Nil | Done | 2025-12-16 | Nil | NA | NA | NA | Meets Expectation

## 26.2 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 26.2 Sprint S1 | 50138 | 50138 | Sivaraja | Bounceback/Sub-Defect | When we are editing any field in student maintenance screen facing error. | When we modify the split billing, we only pass the modified fields.The Student # is not passed to the backend.So, we get the validation message | Significant | Manual | Internal | Story Completed | Development | Story Bounceback | Manjunath - Offshore QA
2 | 26.2 Sprint S1 | 50138 | 50138 | Sivaraja | Bounceback/Sub-Defect | When we found another instance of the Student ID number throwing a bad validation, this is when editing split billing details editing any field in student maintenance screen facing error. | When we modify the split billing, we only pass the modified fields.The Student # is not passed to the backend.So, we get the validation message | Significant | Manual | Internal | Story Completed | Development | Story Bounceback | Jeff- Offshore QA
3 | 26.2 Sprint S1 Stretch | 26419 |  | Sivaraja | Defect | The validation does not include start and end times when editing a term activity. | Existing behaviour added validation for Start time and End Time. We have validation for Start date and End date. | Significant | Manual | External | Defect Peer Review | Existing_Issues | Existing PROD Issue | Kanchana - PO
4 | 26.2 Sprint S1 Stretch | 26460 |  | Kaliammal | Defect | The capacity modal is popping up randomly when approving non-capacity registrations. | Existing registration information maintain next registration also, so it affect with / without capacity. | Significant | Manual | Internal | Defect Peer Review | Existing_Issues | Existing PROD Issue | Jeff- Offshore QA
5 | 26.2 Sprint S1 Stretch | 26461 |  | Athi | Defect | On the first time you navigate to the Custom Fields section, if you open a drop down custom field, then hit the add option/delete on the top option it re-routes to the details screen for that custom field. This appears to only happen once per login, once it has happened once it does not replicate, unless you log out and then log back in. So seems to be session based. | Existing issue identified and raised defect. | Significant | Manual | Internal | Defect Fixed | Existing_Issues | Existing PROD Issue | Kanchana - PO

## 4.3 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-11-19 | 2025-12-02 | 4.3 Sprint S3 | Allen/Nathiya | 45848 | Activities - DISCOVERY - Universal Search for Students Page | Story Completed | 8 | 6 | 24 | 2025-11-19 | 2025-12-02 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
2 | MSB Activities | 2025-11-19 | 2025-12-02 | 4.3 Sprint S3 | Kaliammal | 45756 | Activities - Admin - Enrollment Plan - Tech Debt Field Validation | Story Completed | 1 | 1 | 2 | 2025-11-17 | 2025-11-17 | Done | Athi,Sivaraja | Nil | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45761 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45841 | 2025-11-18 | 2025-11-18 | Done | Nil | Done | 2025-11-18 | Nil | Approved | Approved | Carried from last sprint stretch for this sprint main commit for QA and part of 4.3 release. | Meets Expectation
3 | MSB Activities | 2025-11-19 | 2025-12-02 | 4.3 Sprint S3 Stretch | Sivaraja | 50741 | Activities - Registration - Prevent starting a registration for a student with a null student number [20.1] DEV only | Story Completed | 5 | 5.75 | 23 | 2025-11-19 | 2025-11-26 | Done | Ram, Kaliammal | Nil | Ram, Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/46016 | 2025-12-02 | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
4 | MSB Activities | 2025-11-19 | 2025-12-02 | 4.3 Sprint S3 Stretch | Kaliammal | 47588 | Activities - SYSTEM - Removing the Original Description Columns [20.1] DEV only | Story Completed | 5 | 6 | 24 | 2025-11-19 | 2025-11-28 | Done | Sivaraja,Athi | Include Report Changes | Sivaraja,Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45981 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation

## 4.3 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised

## 4.3 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-11-05 | 2025-11-18 | 4.3 Sprint S2 | Kaliammal | 50340 | Activities - Admin - Prevent Payment Method Errors | Story Completed | 5 | 3 | 12 | 2025-11-05 | 2025-11-11 | Done | Ram,Athi | Nil | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45640 | 2025-11-13 | 2025-11-13 | 2025-11-13 | Nil | Done | 2025-11-13 | Nil | Change Error Message. | Approved | Nil | Meets Expectation
2 | MSB Activities | 2025-11-05 | 2025-11-18 | 4.3 Sprint S2 | Sivaraja | 50583 | Activities - Admin - Add 'Actions' Dropdown in Term Maintenance for Activities & Enrollment Plan Tab | Story Completed | 3 | 1.75 | 7 | 2025-11-05 | 2025-11-07 | Done | Ram, Kaliammal | Nil | Ram, Athi, Kaliammal | useCallBack' can be used for better performance | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45602 | 2025-11-10 | 2025-11-10 | Done | Nil | Done | 2025-11-11 | Nil | UI Suggestions Given: We need to highlight the color of each action item when selected (similar to the selected actions in the dropdown list). Currently, the hover message does not clearly indicate which button it refers to. Suggestions: If needed, we can use an icon similar to the one used in the selected actions. Drop-down list arrow icon - shall we use the consistent drop-down throughout the application. Approved | It looks good, however the gray icon on the blue background is really difficult to see. Approved | Nil | Meets Expectation
3 | MSB Activities | 2025-11-05 | 2025-11-18 | 4.3 Sprint S2 | Kaliammal | 26189 | Activities - Admin - Registrations - Enrollment Plan Capacity Reached Prompt is not getting closed | Defect Fixed | 2 | 1 | 2 | 2025-10-29 | 2025-11-04 | Done | Sivaraja | Nil | Ram,Sivaraja | 1.Rename var name. | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45502 | 2025-11-05 | 2025-11-05 | Done | Nil | Done | 2025-11-05 | Nil | NA | NA | Nil | Meets Expectation
4 | MSB Activities | 2025-11-05 | 2025-11-18 | 4.3 Sprint S2 | Kaliammal | 50559 | Activities - Admin - Upgrade Existing Audit Log to a Table Grid for Form Types Maintenance | Story Completed | 3 | 3 | 12 | 2025-10-28 | 2025-11-03 | Done | Sivaraja | 1.Getting duplicate entries in logs while creating new form and while updating Form-Type-Name 2.Custom colum header to formtype specific | Ram.Athi | 1.Add null check and add description 2.Remove unused namespace | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45635 | 2025-11-11 | 2025-11-13 | Done | Nil | Done | 2025-11-13 | Nil | Approved | Approved | Nil | Meets Expectation
5 | MSB Activities | 2025-11-05 | 2025-11-18 | 4.3 Sprint S2 | Sivaraja | 26178 | Activities - Admin - Manual Registration Null Student Info error | Defect Fixed | 2 | 2 | 9 | 2025-10-30 | 2025-10-31 | Done | Kaliammal | Nil | Ram, Athi, Kaliammal | Remove the duplicate code | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45415 | 2025-11-06 | 2025-11-07 | Done | Nil | Done | 2025-11-10 | Nil | NA | NA | Nil | Meets Expectation
6 | MSB Activities | 2025-11-05 | 2025-11-18 | 4.3 Sprint S2 Stretch | Kaliammal | 45756 | Activities - Admin - Enrollment Plan - Tech Debt Field Validation | Story Peer Review | 1 | 1 | 4 | 2025-11-17 | 2025-11-17 | Done | Athi,Sivaraj | Nil | Sivaraj | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45761 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
7 | MSB Activities | 2025-11-05 | 2025-11-18 | 4.3 Sprint S2 Stretch | Sivaraja | 50692 | Activities - Admin - Term - Enrollment Plan Capacity Limit (Discovery) | Story Completed | 3 | 2.75 | 10.5 | 2025-11-17 | 2025-11-18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation

## 4.3 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 4.3 Sprint S2 | 26178 - Activities - Admin - Manual Registration Null Student Info error | 26178 | Sivaraja | Defect | If an admin performs a manual registration all the way to the end, then uses the bread crumb to start another registration we get a render error due to a null in the student info (see video) | Browser memory is cleared after the registration is completed. So the requested object is null when we start the new registration. | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing PROD Issue | Jeff - Onshore QA
2 | 4.3 Sprint S2 | 26189 - Activities - Admin - Registrations - Enrollment Plan Capacity Reached Prompt is not getting closed | 26189 | Kaliammal | Defect | Enrollment plan capacity reached prompt (modal popup) is still showing even by clicking the OK button (even capacity is reached, there is no registrations to waitlist/reject, the modal popup is still showing) Happening for Waitlist and Rejected. | Existing issue. Close event is not handled properly. | Significant | Manual | External | Defect Fixed | Existing_Issues | Existing PROD Issue | Kanchana -PO

## 4.3 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 | Sivaraja | 50489 | Activities - Registration - Integrate the "New Verbiage" to Parent Term Enrollment Plan specific URL | Story Completed | 5 | 4.25 | 17 | 2025-10-22 | 2025-10-27 | Done | Ram,Athi,Kaliammal | Nil | Ram,Athi,Kaliammal | Use constant variable "AllTerms" instead of using hardcoded value -1. | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45342 | 2025-10-28 | 2025-10-30 | Done | Nil | Done | 2025-10-30 | Nil | Given feedback on functional scenarios | Approved | NA | Meets Expectation
2 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 | Allen | 26099 | Activities - Admin - Search criteria with special characters causing server error | Defect Fixed | 2 | 1 | 4 | 2025-10-22 | 2025-10-24 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45236 | 2025-10-24 | 2025-10-24 | Done | Nil | Done | 2025-10-24 | Nil | NA | NA | NA | Meets Expectation
3 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 | Kaliammal | 50347 | Activities - Reports - Multi Tree Select Component (Search & Selection) (qa only) [4.3] | Story Completed | 5 | 3 | 9 | 2025-10-13 | 2025-10-13 | Done | Ram,Athi | Nil | Ram,Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45070 Bounceback PR https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45361 | 2025-10-10 | 2025-10-13 | Done | Nil | Done | 2025-10-23 | Nil | NA | NA | NA | Meets Expectation
4 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 | Kaliammal | 50160 | Activities - Parent - Site Registration URL for Inactive Site and Tenant | Story Completed | 1 | 1 | 3 | 2025-10-13 | 2025-10-22 | Done | Ram,Athi | 1.Redirect page is loaded background | Ram,Athi | 1.Rename NorecordsFound to NorecordFoundMessage. 2.Change buttton to button 3. Change Null check | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45304 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45370 | 2025-10-23 | 2025-10-27 | Done | Nil | Done | 2025-10-28 | Nil | 1. Message is showing at the time of reloading the screen. 2. Mentioned few URL that is still shows not found on the page instead of No results found. | Approved | NA | Meets Expectation
5 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 | Kaliammal | 50161 | Activities - Parent - Site Registration URL for Site without EPs | Story Completed | 3 | 3 | 13 | 2025-10-15 | 2025-10-22 | Done | Ram,Sivaraja | Nil | Ram,Sivaraja | 1.Error message change for EnrollmentPlan | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45304 | 2025-10-23 | 2025-10-27 | Done | Nil | Done | 2025-10-28 | Nil | Approved | Approved | NA | Meets Expectation
6 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 | Sivaraja | 50488 | Activities - Registration - Term Enrollment Plan specific URLS (POV, PR and QA) | Story Completed | 3 | 1 | 4 | 2025-10-08 | 2025-10-21 | Done | Ram, Kaliammal | Nil | Ram, Athi, Kaliammal | 1.AddEnrollmentPlanFields.tsx - remove the empty spaces in that file 2.Remove unused code from UrlHelper.tsx 3.Here used const var but not used in url creation , you directly added | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45280 | 2025-10-24 | 2025-10-28 | Done | Remove the feature specific logic from Utils class and added to the specific class in the term controller. | Done | 2025-10-30 | 1.Move this GetEnrollmentRegistrationsURL() to UrlHelper.cs 2.Build TermEnrollment URL in the constructor of DetailsModel.cs instead of Database response model 3.Use IsActiveTerm property instead of creating another. | Given UI Suggestions for better user experience. | Approved | Client PR Comments : Suggestion to refactor and organize the code . | Meets Expectation
7 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 | Allen | 50159 | Activities - View Districts - Hide Advanced Tools for HSS CustomerSupport [PR & QA] | Story Completed | 1 | 1 | 4 | 2025-10-22 | 2025-10-22 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45049 | 2025-10-09 | 2025-10-24 | Done | Nil | Done | 2025-10-24 | Can we update this to instead check for a match against the allowed roles? something like AppContext.systemRole == SystemRoleID.Admin ¦¦ AppContext.systemRole == SystemRoleID.Support so that if systemRole is ever not set correctly or we add another role they aren't given access accidentally | Approved | Approved | NA | Meets Expectation
8 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 Stretch | Allen | 50393 | Activities - District - Hide 'Add' and 'Edit' button for HSS Customer Support Role | Story Completed | 2 | 1 | 4 | 2025-10-22 | 2025-10-22 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45320 | 2025-10-28 | 2025-10-28 | Done | Nil | Done | 2025-10-28 | Nil | Approved | Approved | NA | Meets Expectation
9 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 Stretch | Kaliammal | 26189 | Activities - Admin - Registrations - Enrollment Plan Capacity Reached Prompt is not getting closed | Defect Peer Review | 2 | 2 | 8 | 2025-10-29 | 2025-11-04 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
10 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 Stretch | Kaliammal | 50559 | Activities - Admin - Upgrade Existing Audit Log to a Table Grid for Form Types Maintenance | Product Owner - Verify | 3 | 3 | 12 | 2025-10-28 | 2025-11-03 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
11 | MSB Activities | 2025-10-22 | 2025-11-04 | 4.3 Sprint S1 Stretch | Sivaraja | 26178 | Activities - Admin - Manual Registration Null Student Info error | Story Peer Review | 2 | 2 | 8 | 2025-10-30 | 2025-10-31 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation

## 4.3 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised

## 4.2 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-10-08 | 2025-10-21 | 4.2 Sprint S3 | Sivaraja | 50339 | Activities - Registration - Term Enrollment Plan specific URLS [4.3] (Discovery/ Dev only) | Story Completed | 5 | 7 | 29 | 2025-10-08 | 2025-10-21 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Meets Expectation
2 | MSB Activities | 2025-10-08 | 2025-10-21 | 4.2 Sprint S3 | Kaliammal | 49964 | Activities - Reports - Multi Tree Select Component (Search & Selection) (Dev & PR, POV only) [4.3] | Story Completed | 5 | 3 | 14 | 2025-09-10 | 2025-09-10 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45070 | 2025-10-10 | 2025-10-13 | Allen | Nil | NA | NA | NA | NA | NA | waiting for client review | Meets Expectation
3 | MSB Activities | 2025-10-08 | 2025-10-21 | 4.2 Sprint S3 | Allen | 26142 | Activities - Regression - Admin - Split Billing Input deleting after 3rd character | Defect Fixed | 1 | 1 | 4 | 2025-10-15 | 2025-10-16 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45170 | 2025-10-16 | 2025-10-16 | Allen | Nil | Done | 2025-10-16 | Nil | NA | NA |  | Meets Expectation
4 | MSB Activities | 2025-10-08 | 2025-10-21 | 4.2 Sprint S3 Stretch | Allen | 50159 | Activities - View Districts - Hide Advanced Tools for HSS CustomerSupport [4.3] | Story Peer Review | 2 | 1 | 4 | 2025-10-08 | 2025-10-09 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45049 | 2025-10-09 | 2025-10-09 | Allen | Nil | Done |  | Can we update this to instead check for a match against the allowed roles? something like AppContext.systemRole == SystemRoleID.Admin ¦¦ AppContext.systemRole == SystemRoleID.Support so that if systemRole is ever not set correctly or we add another role they aren't given access accidentally |  | Nil | Suggestion: Consider checking for negative scenarios in the if condition rather than positive scenarios | Meets Expectation
5 | MSB Activities | 2025-10-08 | 2025-10-21 | 4.2 Sprint S3 Stretch | Kaliammal | 50160 | Activities - Parent - Site Registration URL for Inactive Site and Tenant | Story Being Developed | 3 | 2 | 8 | 2025-10-13 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Activities | 2025-10-08 | 2025-10-21 | 4.2 Sprint S3 Stretch | Kaliammal | 50161 | 50161 Activities - Parent - Site Registration URL for Site without EPs | Story Being Developed | 5 | 2 | 8 | 2025-10-14 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 4.2 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 46142 | Activities - Regression - Admin - Split Billing Input deleting after 3rd character | 46142 | Allen | Defect | In the split billing section, the percent input will delete after the third character is inputed |  | Minor | Manual | Internal | Defect Fixed | Development |  | Ramprabu - Developer

## 4.2 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-09-24 | 2025-10-07 | 4.2 Sprint S2 | Sivaraja | 50066 | Activities - Admin - Prevent 'Admin' from Deleting Activities in Enrollment Plan if used in Operating Days | Story Completed | 3 | 2.5 | 10 | 2025-09-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | As discussed with Jeff, the fix provided in the story is not feasible. So created another story:50302 to analyze further and closing this story. | Meets Expectation
2 | MSB Activities | 2025-09-24 | 2025-10-07 | 4.2 Sprint S2 | Kaliamal | 49964 | Activities - Reports - Multi Tree Select Component (Search & Selection) | Story Being Developed | 5 | 5 | 20 | 2025-09-10 | 2025-10-07 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Development is completed and unit testing in-progress and carried to next sprint for [PR ,POV and QA] and focused for 4.3 release. Reason: Initially, we attempted multi-student to handle it with the common tree select component, but it wasn't feasible, so we moved it to separate component. This approach took a lot of effort and additional time. Unit testing also required time to validate multiple scenarios. | Meets Expectation
3 | MSB Activities | 2025-09-24 | 2025-10-07 | 4.2 Sprint S2 Stretch | Allen | 49748 | Activities - Registration - Term Enrollment Plan specific URLS (Discovery) | Story Completed | 3 | 3 | 12 | 2025-09-25 | 2025-10-07 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Meets Expectation

## 4.2 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised

## 4.2 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 4.2 Sprint S1 | 49849 - Activities - Registration - Site Registrations URL (QA) | 49849 | Allen | Bounceback/Sub-Defect | When we update from inactive site to active site and save the site, Site registration URL field is empty in site maintenance screen and when we refresh the screen we are able to see the site registration URL |  | Significant | Manual | Internal | Story Completed | Development |  | Manjunath - QA Offshore
2 | 4.2 Sprint S1 | 49848 Activities - Admin - Implement Tree component for Job Request Queue(PR &QA) | 49848 | Sivaraja | Bounceback/Sub-Defect | Records are not properly fetched for failed status, when we select multiple district |  | Significant | Manual | Internal | Story Completed | Development |  | Manjunath - QA Offshore
3 | 4.2 Sprint S1 | 49848 Activities - Admin - Implement Tree component for Job Request Queue(PR &QA) | 49848 | Sivaraja | Bounceback/Sub-Defect | If we have a district selected at the top, then go to the job request page and do a select all we do not get the district column of data |  | Significant | Manual | Internal | Story Completed | Development |  | Jeff- QA Onshore
4 | 4.2 Sprint S1 | 49848 Activities - Admin - Implement Tree component for Job Request Queue(PR &QA) | 49848 | Sivaraja | Bounceback/Sub-Defect | when we search on results, the record count is not updating based on the records returned in the search |  | Significant | Manual | Internal | Story Completed | Development |  | Manjunath- QA Onshore

## 4.2 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-09-10 | 2025-09-23 | 4.2 Sprint S1 | Sivaraja | 49796 | Activities - Registration - New Parent Account for Site Registration URL | Story Completed | 3 | 3 | 12 | 2025-09-10 | 2025-09-12 | Done | Ram | Nil | Ram/Athi | Minor change != to !== in loginreturn.tsx | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44575 | 2025-09-17 | 2025-09-17 | Done | Nil | Done | 2025-09-18 | Nil | Approved | Approved |  | Meets Expectation
2 | MSB Activities | 2025-09-10 | 2025-09-23 | 4.2 Sprint S1 | Sivaraja | 49848 | Activities - Admin - Implement Tree component for Job Request Queue (PR &QA) | Story Completed | 3 | 3 | 15 | 2025-08-07 | 2025-09-09 | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44529 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44675 | 2025-09-12 | 2025-09-15 | Done | Nil | Done | 2025-09-15 | Nil | Approved. Given one pov comment: 1. If the multi select dropdown (have more data it extended below the footer at the bottom and showing extra space) - Addressed with cllient - We plan to have a separate story. | Approved |  | Meets Expectation
3 | MSB Activities | 2025-09-10 | 2025-09-23 | 4.2 Sprint S1 | Allen | 49849 | Activities - Registration - Site Registrations URL (QA) | Story Completed | 3 | 3 | 15 | 2025-08-14 | 2025-08-22 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44172 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44208 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44610 | 2025-08-26 | 2025-08-26 | Done | Nil | Done | 2025-09-02 | Nil | Below points are not working as per AC: 1.URL redirection is navigating wrongly after selecting an students (again redirecting to a Site selection page to select a site). 2.If no Enrollment Plans are open for registration, we should show a message "No Enrollment Plans currently open for registration" 3.If no students in their household, we should route them to the current parent-facing page that gives a redirect to MSB option to add students to their household. 4.If the parent has students in their household, but no students in their household for the particular district associated with the site registration URL, we should show the following message "Your account does not currently have any students associated with this district, please select this district and add students to your account to continue" 5.Once the site is inactive in the admin, do we still give access to the site registration URL from the parents? Currently, in parents, we usually show only the active site to register. No, we don't need to give access to the Site registration URL if the Site is inactive. We can hide the URL at that time. We can do that in a separate story next release if needed. 6.If the parent knows the active site registration URL link and then the site is inactive, what message do we need to show to the parent admin if they access the URL again? We could keep it simple with "No results found" for now if that works. 6. New Registration is not working. | Approved |  | Meets Expectation
4 | MSB Activities | 2025-09-10 | 2025-09-23 | 4.2 Sprint S1 Stretch | Kaliamal | 49964 | Activities - Reports - Multi Tree Select Component (Search & Selection) | Story Being Developed | 8 | 6 | 24 | 2025-09-10

## 4.1 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-08-27 | 2025-09-09 | 4.1 Sprint S3 | Kaliammal | 25807 | Activities - Admin - Reports - Multiselect component selection not working for the first time selection. | Defect Blocked | 3 | 3 | 19 | 2025-08-28 | 2025-08-29 | Done | SivaRaja Athi | Nil | SivaRaja Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44276 | 2025-08-29 | 2025-08-29 | Done | Nil | Done | 2025-09-02 | Nil | NA | NA | The defect is currently blocked because multiple issues exist in the same component , which impact component selction .Fixing one defect causes another to appear. As comprehensive unit testing is required for all scanarios, we have decided to revamp the component.Therefore , this defect will remain blocked in current sprint, and a new story will create for new implementation.
2 | MSB Activities | 2025-08-27 | 2025-09-09 | 4.1 Sprint S3 | Sivaraja | 49280 | Activities - Admin - Implement Tree component for Job Request Queue [4.2] (timeboxed) | Story Completed | 5 | 6 | 24 | 2025-08-07 | 2025-09-09 | Done | Ram/Athi | Nil | Ram/Athi | 1. use Count instead of .Count() 2. Remove unused variables 3. Simplify the GetTenants() 4. Simplify the useEffect in MultiTreeSelect Component 5. Found some of spelling mistake 6.Instead of using any use Number 7. Consolidate useEffect method in single call | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
3 | MSB Activities | 2025-08-27 | 2025-09-09 | 4.1 Sprint S3 | Allen | 49407 | Activities - Registration - Site Registrations URL [4.2] (timeboxed) | Story Completed | 3 | 3 | 3 | 2025-08-14 | 2025-08-22 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44172 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44208 | 2025-08-26 | 2025-08-26 | Done | Nil | Done | Hold for next release | Can we move the styling into a class in the site.scss file instead of using inline styling | Below points are not working as per AC: 1.URL redirection is navigating wrongly after selecting an students (again redirecting to a Site selection page to select a site). 2.If no Enrollment Plans are open for registration, we should show a message "No Enrollment Plans currently open for registration" 3.If no students in their household, we should route them to the current parent-facing page that gives a redirect to MSB option to add students to their household. 4.If the parent has students in their household, but no students in their household for the particular district associated with the site registration URL, we should show the following message "Your account does not currently have any students associated with this district, please select this district and add students to your account to continue" 5.Once the site is inactive in the admin, do we still give access to the site registration URL from the parents? Currently, in parents, we usually show only the active site to register. No, we don't need to give access to the Site registration URL if the Site is inactive. We can hide the URL at that time. We can do that in a separate story next release if needed. 6.If the parent knows the active site registration URL link and then the site is inactive, what message do we need to show to the parent admin if they access the URL again? We could keep it simple with "No results found" for now if that works. 6. New Registration is not working. | Approved | Today we discussed potentially holding this for the 4.2 Release since it has not yet made it into testing. Note - We did not touch the login API as a part of this story. Instead we are focusing on updating the routing after login instead of changing core API logic. Allen is going to deploy the changes to the dev environment for Jeff to take a look at, then we can make the final determination of if we are going to include this in 4.1 or save for 4.2. | Meets Expectation
4 | MSB Activities | 2025-08-27 | 2025-09-09 | 4.1 Sprint S3 | Kaliammal | 25890 | Activities - Admin - Regression - Facing validation "The EnrollmentplanId field is required" even if we select enrollment plan | Defect Fixed | 3 | 3 | 3 | 2025-09-05 | 2025-09-05 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44400 | 2025-09-05 | 2025-09-05 | Done | Nil | Done | 2025-09-08 | Nil | NA | NA | NA
5 | MSB Activities | 2025-08-27 | 2025-09-09 | 4.1 Sprint S3 Stretch | NA | 49748 | Activities - Registration - Term Enrollment Plan specific URLS (Discovery) | Story Approved | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Activities | 2025-08-27 | 2025-09-09 | 4.1 Sprint S3 Stretch | Kaliammal | 25853 | Activities - Reports - Student Filter Tree Select Component issue in Search/Selection | Defect Blocked | NA | 2 | 10 | 2025-09-01 | 2025-09-02 | Done | Athi | Nil | Ram/Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44326 | 2025-09-03 | NA | NA | NA | NA | NA | NA | NA | NA | The defect is currently blocked because multiple issues exist in the same component , which impact component selction .Fixing one defect causes another to appear. As comprehensive unit testing is required for all scanarios, we have decided to revamp the component.Therefore , this defect will remain blocked in current sprint, and a new story will create for new implementation.
7 | MSB Activities | 2025-08-27 | 2025-09-09 | 4.1 Sprint S3 Stretch | Kaliammal | 25859 | Activities - Reports - Student Filter Tree Select Component Search issue [4.2] | Defect Blocked | NA | 1 | 4 | 2025-09-03 | 2025-09-03 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | The defect is currently blocked because multiple issues exist in the same component , which impact component selction .Fixing one defect causes another to appear. As comprehensive unit testing is required for all scanarios, we have decided to revamp the component.Therefore , this defect will remain blocked in current sprint, and a new story will create for new implementation.

## 4.1 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 4.1 Sprint S3 | 25890 - Activities - Admin - Regression - Facing validation "The EnrollmentplanId field is required" even if we select enrollment plan. |  | Kaliammal | Defect | Facing validation "The EnrollmentplanId field is required" even if we select enrollment plan. | This issue occured while fixing defect 25807, Code broke caused this issue. Identified and reverted the code. | Significant | Manual | Internal | Defect Fixed | QA | Regression Defect | Manjunathan - QA
2 | 4.1 Sprint S3 | 25807 - Activities - Admin - Reports - Multiselect component selection not working for the first time selection. |  | Kaliammal | Defect | Defect 1: Multiselect component selection not working for the first selection.(Refer Repo steps) Defect 2: Even all the students are selected it is not showing all selected instead it is displaying each students in the student filter. Defect 3: Performing select and unselect of students multiple times clearing the previous selections as well. | This issue occurred while fixing another issue. If we have more than 50 plus records that are not loaded into the first set of 50 records. | Minor | Manual | Internal | Defect Blocked | QA | Existing PROD Issue | Manjunathan and Siva Mohan - QA
3 | 4.1 Sprint S3 Stretch | 25853 - Activities - Reports - Student Filter Tree Select Component issue in Search/Selection |  | Kaliammal | Defect | Defect 1: When selecting "All Students" from the student filter and then search for any student and uncheck the searched student. Defect 2: When changing the activity filter after selecting the student list, it still retains the students list which are selected exists. But when you select the "select the activity", the selected list are getting cleared properly. | This issue occurred while fixing another issue. If we have more than 50 plus records that are not loaded into the first set of 50 records. | Minor | Manual | Internal | Defect Blocked | QA | Existing PROD Issue | Dev Team Unit Testing
4 | 4.1 Sprint S3 Stretch | 25859 - Activities - Reports - Student Filter Tree Select Component Search issue [4.2] |  | Kaliammal | Defect | When selecting "All Students" from the student filter and search any student name that is not listed in the filter, we see a message like No Students Are Available. | This issue occurred while fixing another issue. If we have more than 50 plus records that are not loaded into the first set of 50 records. | Minor | Manual | Internal | Defect Blocked | QA | Existing PROD Issue | Dev Team Unit Testing

## 4.1 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-08-13 | 2025-08-26 | 4.1 Sprint S2 | Kaliammal | 25741 | Activities - Reports - Unselected Students are being selected from the Student dropdown list | Defect Fixed | 3 | 3 | 16.5 | 2025-08-13 | 2025-08-20 | Done | Sivaraja | 1. 'Unselected student appears when we search & unselect the user 2.Selected students not appears when we search & select the user | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44053 | 2025-08-20 | 2025-08-22 | Done | Nil | Done | 2025-08-22 | Nil | NA | NA |  | Meets Expectation
2 | MSB Activities | 2025-08-13 | 2025-08-26 | 4.1 Sprint S2 | Kaliammal | 48830 | Activities - Parent - Integrating Notification Hub to MSB Activities | Story Completed | 2 | 2 | 16 | 2025-08-14 | 2025-08-21 | Done | Athi | Nil | Athi | Nil | NA | 2025-08-20 |  | Done | Nil | Done |  | Nil | NA | NA | Kristy MacCheyne: We ended up updating our approach for this update so that it is less invasive (it should not change how we queue, send, or render emails). We should be able to flip from the old method to the new method. With this approach (changing the email service only), if we merge these changes we would also get the admin NH update for free with this change. | Meets Expectation
3 | MSB Activities | 2025-08-13 | 2025-08-26 | 4.1 Sprint S2 | Allen | 49407 | Activities - Registration - Site Registrations URL | Story Peer Review | 8 | 7 | 28.5 | 2025-08-14 | 2025-08-22 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44172 | 2025-08-26 | 2025-08-26 | Done | Nil | Done |  |  | Below points are not working as per AC: 1.URL redirection is navigating wrongly after selecting an students (again redirecting to a Site selection page to select a site). 2.If no Enrollment Plans are open for registration, we should show a message "No Enrollment Plans currently open for registration" 3.If no students in their household, we should route them to the current parent-facing page that gives a redirect to MSB option to add students to their household. 4.If the parent has students in their household, but no students in their household for the particular district associated with the site registration URL, we should show the following message "Your account does not currently have any students associated with this district, please select this district and add students to your account to continue" 5.Once the site is inactive in the admin, do we still give access to the site registration URL from the parents? Currently, in parents, we usually show only the active site to register. No, we don't need to give access to the Site registration URL if the Site is inactive. We can hide the URL at that time. We can do that in a separate story next release if needed. 6.If the parent knows the active site registration URL link and then the site is inactive, what message do we need to show to the parent admin if they access the URL again? We could keep it simple with "No results found" for now if that works. 6. New Registration is not working. | Approved | Today we discussed potentially holding this for the 4.2 Release since it has not yet made it into testing. Note - We did not touch the login API as a part of this story. Instead we are focusing on updating the routing after login instead of changing core API logic. Allen is going to deploy the changes to the dev environment for Jeff to take a look at, then we can make the final determination of if we are going to include this in 4.1 or save for 4.2. | Meets Expectation
4 | MSB Activities | 2025-08-13 | 2025-08-26 | 4.1 Sprint S2 | Sivaraja | 49578 | Activities - Site Home Page - Fix the Vertical Scroll Bar | Story Completed | 5 | 5 | 21.5 | 2025-08-13 | 2025-08-19 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44062 | 2025-08-20 | 2025-08-21 | Done | Nil | Done | 2025-08-21 | typo: change 'secreen' to 'screen' | Given suggestion, to align the verbiage in the center. Approved | Approved |  | Meets Expectation
5 | MSB Activities | 2025-08-13 | 2025-08-26 | 4.1 Sprint S2 Stretch | Sivaraja | 49280 | Activities - Admin - Implement Tree component for Job Request Queue [4.2] | Story Being Developed | 8 | 3.75 | 15 | 2025-08-07 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Meets Expectation
6 | MSB Activities | 2025-08-13 | 2025-08-26 | 4.1 Sprint S2 Stretch | Allen | 49604 | Activities - Admin - Integrating Notification Hub to MSB Activities | Story Completed | 3 | 3 | 10 | 2025-08-14 | 2025-08-21 | Done | Athi | Nil | Athi | Nil | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Kristy MacCheyne: We ended up updating our approach for this update so that it is less invasive (it should not change how we queue, send, or render emails). We should be able to flip from the old method to the new method. With this approach (changing the email service only), if we merge these changes we would also get the admin NH update for free with this change. | Meets Expectation
7 | MSB Activities | 2025-08-13 | 2025-08-26 | 4.1 Sprint S2 Stretch | Kaliammal | 25686 | Activities - Admin - Accounting - Fees Icon mismatch in Page header of the Fees Page | Defect Fixed | 1 | 1 | 2 | 2025-08-21 | 2025-08-21 | Done | Sivaraja | Nil | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44084 | 2025-08-22 | 2025-08-25 | Done | Nil | Done | 2025-08-25 | Nil | NA | NA
8 | MSB Activities | 2025-08-13 | 2025-08-26 | 4.1 Sprint S2 Stretch | Kaliammal | 25807 | Activities - Admin - Reports - Multiselect component selection not working for the first time selection. | Defect Being Fixed | 3 | 2 | 8 | 2025-08-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 4.1 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Root Cause Analysis | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 4.1 Sprint S2 | 25741 - Activities - Reports - Unselected Students are being selected from the Student dropdown list. |  | Kaliammal | Defect | In the reports, Students who were previously unselected are being selected from the student dropdown list. | This same issue was identified early and fixed by developers. This issue reoccurred while fixing another issue. If we have more than 50 plus records that are not loaded in the first set of 50 records. | Major | Manual | External | Defect Fixed | QA | Existing PROD Issue | Internal Stakeholder
2 | 4.1 Sprint S2 Stretch | 25686 - Activities - Admin - Accounting - Fees Icon mismatch in Page header of the Fees Page. |  | Kaliammal | Defect | Fees Icon mismatch in the Page header of the Fees Page. | Requirement Gap. We believe this could have been there for a long time, and we identified while testing tile page changes across the application (React conversion). | Minor | Manual | External | Defect Fixed | QA | Existing PROD Issue | Siva Mohan - QA
3 | 4.1 Sprint S2 Stretch | 25807 - Activities - Admin - Reports - Multiselect component selection not working for the first time selection. | 25741 | Kaliammal | Defect | Defect 1: Multiselect component selection not working for the first selection.(Refer Repo steps) Defect 2: Even all the students are selected it is not showing all selected instead it is displaying each students in the student filter. | This issue occurred while fixing another issue. If we have more than 50 plus records that are not loaded into the first set of 50 records. | Minor | Manual | External | Defect Being Fixed | QA | Existing PROD Issue Carried to next sprint for dev work | Manjunathan and Siva Mohan - QA

## 4.1 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-07-30 | 2025-08-12 | 4.1 Sprint S1 | Allen Xavier | 44086 | Activities - Admin - Update View All[Registrations] page to Server Side sorting [PR&QA] | Story Completed | 1 | 2 | 9 | NA | NA | Done | Sivaraja | 1. 'Update Search' button does not fetch the records based on the Registrations-Status selected 2.Status column is not sorted properly | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43488 BounceBack PR Link https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43774 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43841 | 2025-07-30 | 2025-07-30 | Done | Nil | Done | 2025-07-31 | Nil | Approved | Approved |  | Meets Expectation
3 | MSB Activities | 2025-07-30 | 2025-08-12 | 4.1 Sprint S1 | Sivaraja | 49199 | Activities - SYSTEM - Update ' Record you requested was not found' page to React [PR &QA] | Story Completed | 5 | 3.25 | 13 | NA | NA | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43500 Bounceback PR Link: https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43844 | 2025-07-30 | 2025-07-31 | Done | Nil | Done | 2025-07-31 | Nil | NA | NA |  | Meets Expectation
3 | MSB Activities | 2025-07-30 | 2025-08-12 | 4.1 Sprint S1 | Kaliammal | 49201 | Activities - SYSTEM - Update 'Site & Tenant Mismatch' Page to React [PR &QA ] | Story Completed | 3 | 3 | 13.5 | NA | NA | Done | Sivaraja | 1.SiteMismatch need to handle in Kiosk | Sivaraja | 1.MisMatchExceptionController.cs (string MisMatchType) Change Variable to CamelCase 2.ControllerApp.tsx window.location.href : use this only one time by reusing TenantId and SiteId variable | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43579 Bounceback PR Link: https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43836 | 2025-07-30 | 2025-07-31 | Done | Nil | Done | 2025-08-04 | There are a number of places where Mismatch is spelled with both M's capitalized MisMatch, for consistencies sake can we make it Mismatch everywhere? | NA | NA |  | Meets Expectation
4 | MSB Activities | 2025-07-30 | 2025-08-12 | 4.1 Sprint S1 | Sivaraja | 49202 | Activities - SYSTEM - Remove CSHTML Pages For REACT Conversions [PR & QA] | Story Completed | 1 | 1 | 4 | NA | NA | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43670 | 2025-07-30 | 2025-08-11 | Done | Nil | Done | 2025-08-11 | Nil | NA | NA |  | Meets Expectation
5 | MSB Activities | 2025-07-30 | 2025-08-12 | 4.1 Sprint S1 | Sivaraja | 25685 | Activities - Admin - Modal popup 'Override Site Settings' Shown incorrectly when saving unrelated fields | Defect Fixed | 2 | 2 | 8 | 2025-07-30 | 2025-07-31 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43710 | 2025-08-01 | 2025-08-07 | Done | Nil | Done | 2025-08-08 | Nil | Nil | Nil
6 | MSB Activities | 2025-07-30 | 2025-08-12 | 4.1 Sprint S1 | Allen Xavier | 48830 | Activities - Integrating Notification Hub to MSB Activities [4.1] | Story Peer Review | 3 | 5 | 19 | NA | NA | Done | Sivaraja | Nil | Sivaraja | Nil | [10 empty] | The notification hub story was carried over to the next sprint to allow for integration with the existing email template, thorough testing in the development environment to ensure compatibility with our NuGet package, and to address additional peer and PR reviews. This approach ensures seamless integration and robust unit test coverage.If any problem with this integration, we can revert our integration with configuration as well. We are working towards on that.
7 | MSB Activities | 2025-07-30 | 2025-08-12 | 4.1 Sprint S1 | Kaliammal | 49397 | Activities - Registration - Site Registrations URL [Discovery ] | Story Completed | 5 | 3 | 12 | 2025-07-30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
8 | MSB Activities | 2025-07-30 | 2025-08-12 | 4.1 Sprint S1 Stretch | Sivaraja | 49280 | Activities - Admin - Implement Tree component for Job Request Queue | Story Being Developed | 8 | 3 | 12 | 2025-08-07 | [16 empty] | Carried to next sprint stretch for Development work

## 4.1 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 4.1 Sprint S1 | 25685 Activities - Admin - Modal popup 'Override Site Settings' Shown incorrectly when saving unrelated fields |  | Sivaraja | Defect | When saving the Registration Status Message (Accepted/Waitlist/Rejected) fields. And then save any fields other than the registration status message, the 'Override Site settings' modal popup is still being triggered. | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing PROD Issue | Kanchana - Offshore PO
2 | 4.1 Sprint S1 | 44086 - Activities - Admin - Update View All[Registrations] page to Server Side sorting [PR&QA] | 44086 | Kaliammal | Bounceback/Sub-Defect | Search is not working in view all registration. | Minor | Manual | Internal | Story Completed | Development |  | Manjunathan - QA
3 | 4.1 Sprint S1 | 44086 - Activities - Admin - Update View All[Registrations] page to Server Side sorting [PR&QA] | 44086 | Kaliammal | Bounceback/Sub-Defect | Search is no longer searching the full date, it looks to only be searching on the month | Significant | Manual | Internal | Story Completed | Development |  | Jeff Onsite - QA
4 | 4.1 Sprint S1 | 49199 - Activities - SYSTEM - Update ' Record you requested was not found' page to React [PR &QA] | 49199 | Sivaraja | Bounceback/Sub-Defect | showing BAD Gateway error message instead of "Record not Requested was not found". | Minor | Manual | Internal | Story Completed | Development |  | Manjunathan - QA
5 | 4.1 Sprint S1 | 49201 - Activities - SYSTEM - Update 'Site & Tenant Mismatch' Page to React [PR &QA ] | 49201 | Kaliammal | Bounceback/Sub-Defect | Facing server error for admin user. | Significant | Manual | Internal | Story Completed | Development |  | Manjunathan - QA

## 4.0 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-07-16 | 2025-07-29 | 4.0 Sprint S3 | Allen Xavier | 49188 | Activities - Admin - Add MSB District ID to Job Request Queue | Story Completed | 1 | 1 | 4 | 2025-07-16 | 2025-07-16 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43425 | 2025-07-16 | 2025-07-16 | Done | Nil | Done | 2025-07-16 | Nil | Approved | Approved
2 | MSB Activities | 2025-07-16 | 2025-07-29 | 4.0 Sprint S3 | Allen Xavier | 48830 | Activities - Integrating Notification Hub to MSB Activities [4.1] | Story Peer Review | 5 | 5 | 20 | 2025-07-17 | 2025-07-29 | Done | Sivaraja | Nil | Sivaraja | Nil | [8 empty] | NA | NA | It's a Development story (Dev work completed) and the Onsite DEV Manager needs to confirm this same story to PUSH for PR Creation & Testing in the next sprint (need to discuss in the planning) Based on the feedback: Moved to next sprint
3 | MSB Activities | 2025-07-16 | 2025-07-29 | 4.0 Sprint S3 | Sivaraja | 49151 | Activities - SYSTEM - Update ' Record you requested was not found' page to React [4.1] dev only | Story Completed | 5 | 5 | 19 | 2025-07-16 | 2025-07-22 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Dev only story. We have a separate story for PR & QA on the next sprint commit.
4 | MSB Activities | 2025-07-16 | 2025-07-29 | 4.0 Sprint S3 | Kaliammal | 49152 | Activities - SYSTEM - Update 'Site & Tenant Mismatch' Page to React [4.1] - dev only | Story Completed | 5 | 5 | 20 | 2025-07-16 | 2025-07-22 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Dev only story. We have a separate story for PR & QA on the next sprint commit.
5 | MSB Activities | 2025-07-16 | 2025-07-29 | 4.0 Sprint S3 Stretch | Sivaraja | 49202 | Activities - SYSTEM - Remove CSHTML Pages For REACT Conversions | Story Peer Review | 1 | 1 | 4 | 2025-07-25 | 2025-07-28 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Dev only story. We have a separate story for PR & QA on the next sprint commit.
6 | MSB Activities | 2025-07-16 | 2025-07-29 | 4.0 Sprint S3 Stretch | Kaliammal | 25604 | Activities - Reports - All term, enrollment fields are selected automatically, when we modify site filter by adding new site. | Defect Rejected | 5 |  | 6 | 2025-07-24 | 2025-07-29 | [15 empty] | Onsite PO - Fine with existing functionality and we have rejected the defect.

## 4.0 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 4.0 Sprint S3 Stretch | 25604 - Activities - Reports - All term, enrollment fields are selected automatically, when we modify site filter by adding new site. | 25604 | Kaliammal | Defect | All term, enrollment fields are selected automatically, when we modify site filter by adding new site. | Minor | Manual | Internal | Defect Rejected | Development | Onsite PO - Fine with existing functionality and we have rejected the defect. | Manjunathan - Offshore QA

## 4.0 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-07-02 | 2025-07-15 | 4.0 Sprint S2 | Kaliammal | 48805 | Activities - Reports - Add "Multi-Selection" for Enrollment Plan Filter on Custom Registration Report [PR & QA] | Story Completed | 2 | 2 | 8.5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43068 | 2025-06-30 | 2025-07-04 | Done | Nil | Done | 2025-07-08 | Can we update this name to be more fitting, GetByQueryAsync or something along those lines? | Approved | Approved | Waiting for Onsite QA approval to mark it complete
2 | MSB Activities | 2025-07-02 | 2025-07-15 | 4.0 Sprint S2 | Kaliammal | 48831 | Activities - Admin - Add a column for "State" to the Districts Page | Story Completed | 1 | 2 | 7.5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43069 | 2025-06-30 | 2025-06-30 | Done | NIl | Done | 2025-06-30 | Nil | Approved | Approved | Carried from previous sprint to this sprint for onsite QA to test
3 | MSB Activities | 2025-07-02 | 2025-07-15 | 4.0 Sprint S2 | Allen | 48653 | Activities - Admin - Reorder Program Setup Tile Order | Story Completed | 2 | 2 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43106 | 2025-07-01 | 2025-07-01 | Done | NIl | Done | 2025-07-01 | Nil | Approved | Approved
4 | MSB Activities | 2025-07-02 | 2025-07-15 | 4.0 Sprint S2 | Kaliammal | 48970 | Activities - SYSTEM - URL Update for React Converted Pages | Story Completed | 5 | 6 | 24.5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43236 | 2025-07-09 | 2025-07-09 | Done | NIl | Done | 2025-07-09 | Remove TenantId string in returnURL | NA | NA
5 | MSB Activities | 2025-07-02 | 2025-07-15 | 4.0 Sprint S2 | Hari | 49001 | Activities - Accounting - Retain Historical Split Billing Invoice By Value | Story Completed | 5 | 7 | 27.5 | Done | Kaliammal | Nil | Kaliammal | NIl | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43291 | 2025-07-10 | 2025-07-10 | Done | NIl |  | 2025-07-10 | Nil | NA | NA
6 | MSB Activities | 2025-07-02 | 2025-07-15 | 4.0 Sprint S2 Stretch | Sivaraja | 25529 | Activities - Admin - Operating days page UI overlay with "One or more students are not scheduled for attendance" notification message" | Defect Fixed | 2 | 2 | 6.5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43318 | 2025-07-11 | 2025-07-11 | Done | Nil | Done | 2025-07-11 | Nil | NA | NA
7 | MSB Activities | 2025-07-02 | 2025-07-15 | 4.0 Sprint S2 Stretch | Kaliammal | 44086 | Activities - Admin - Update View All[Registrations] page to Server Side sorting [4.1] Dev only | Story Peer Review | 5 | 3.5 | 14 | Done | Sivaraja | 1. 'Update Search' button does not fetch the records based on the Registrations-Status selected 2.Status column is not sorted properly | Sivaraja | Nil | [10 empty] | This story is not part of the release (4.0) and will be part of the next release (4.1)

## 4.0 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 4.0 Sprint S2 | 48805 - Activities - Reports - Add "Multi-Selection" for Enrollment Plan Filter on Custom Registration Report [PR & QA] | 48805 | Kaliammal | Bounceback/Sub-Defect | When we select multiple enrollment plans and have multiple stock fields, district custom and enrollment plan custom fields for each enrollment plans, Only one stock, District and enrollment plan custom fields are visible in the filter info sheet for excel format, Works fine for pdf | Significant | Manual | Internal | Defect Fixed | Development |  | Manjunathan - Offshore QA
2 | 4.0 Sprint S2 Stretch | 25529 - Activities - Admin - Operating days page UI overlay with "One or more students are not scheduled for attendance" notification message" | 25529 | Sivaraja | Defect | Operating days page UI overlay with "One or more students are not scheduled for attendance" notification message" | Minor | Manual | Internal | Defect Fixed | Development |  | Manjunathan - Offshore QA

## 4.0 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-06-18 | 2025-07-01 | 4.0 Sprint S1 | Kaliammal | 48126 | Activities - Reports - Add "Multi-Selection" for Enrollment Plan Filter on Custom Registration Report [SYSTEM] [DEV Only] | Story Completed | 5 | 7 | 27.5 | Done | Hari | 1) Select All not working | Hari | 1) Add column name instead of index 2) Add Break | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43068 | 2025-06-30 | [6 empty] | Approved | Approved
2 | MSB Activities | 2025-06-18 | 2025-07-01 | 4.0 Sprint S1 | Hari | 48725 | Activities - Split Billing - Partial Invoice Upload Failures | Story Completed | 5 | 8 | 31.5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43007 | 2025-06-26 | 2025-06-26 | Done | Nil | Done | 2025-06-26 | 1.isInvalidContact appears to be set to false when being initialized and isn't ever updated, so I believe this will never be true. Should this be using isValidContacts instead which is set by the ValidateSplitbillingContacts function? | NA | NA
3 | MSB Activities | 2025-06-18 | 2025-07-01 | 4.0 Sprint S1 | Hari | 48718 | Activities - SYSTEM - Update Tile Layout Pages to React [PR & QA] | Story Completed | 3 | 3 | 12 | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42890 | 2025-06-17 | 2025-06-18 | Done | NIL | Done | 2025-06-20 | Nil | 1.When I click the Heartland Staff bread crumb link, getting server error. 2.Bread crumb Setup link is missing for District settings page 3.Bread crumb Setup link is missing for Security Groups Name | NA
4 | MSB Activities | 2025-06-18 | 2025-07-01 | 4.0 Sprint S1 Stretch | Kaliammal | 48831 | Activities - Admin - Add a column for "State" to the Districts Page | Story Being Tested | 2 | 1.5 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43069 | 2025-06-30 | 2025-06-30 | Done | NIl | Done | 2025-06-30 | Nil | Approved | Approved | Testing was completed by offshore QA. Onsite QA is not available in this sprint waiting for his approval for completion.
5 | MSB Activities | 2025-06-18 | 2025-07-01 | 4.0 Sprint S1 Stretch | Kaliammal | 48970 | Activities - SYSTEM - URL Update for React Converted Pages | Story Being Developed | 3 | 1.5 | 6 | [15 empty] | Carried to Next Sprint for Dev & Testing

## 4.0 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised

## 3.9 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Kaliammal | 25123 | Activities - Admin - Total Record Count is showing wrongly in Roles Page | Defect Fixed | 1 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42284 | 2025-05-20 | 2025-05-21 | Done | Nil | Done | 2025-05-21 | Nil | NA | NA
2 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Kaliammal | 25330 | Activities - Admin - Contacts - Getting "Model state invalid" error if we remove the E-mail Address[3.9] | Defect Fixed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42569 | 2025-06-03 | 2025-06-05 | Done | Nil | Done | 2025-06-05 | Nil | NA | NA | Carried from last sprint stretch for testing
3 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Kaliammal | 47956 | Activities - Admin - People - Update Icons and Tile Layout [3.9] | Story Completed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42528 | 2025-06-02 | 2025-06-02 | Done | Nil | Done | 2025-06-03 | Nil | Approved | Approved | Carried from last sprint stretch for testing
4 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Hari | 48281 | Activities - Accounting - Retain Grid Records in Fees Page[3.9] | Story Completed | 1 | 1 | 4 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42530 | 2025-06-02 | 2025-06-02 | Done | Nil | Done | 2025-06-03 | Nil | If we select all the fees from the drop-down (All Selected) and click the search, the fee record is not displaying. | NA | Carried from last sprint stretch for testing
5 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Hari | 48400 | Activities - Students - Audit Log - Capture Updated Contact User ID for New Split Billing [3.9] | Story Completed | 1 | 1 | 4 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42531 | 2025-06-02 | 2025-06-02 | Done | Nil | Done | 2025-06-03 | Nil | Approved | Approved | Carried from last sprint stretch for testing
6 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Hari | 48567 | Activities - Accounting - Payments - Formatting Split Billing Contacts UI [3.9] | Story Completed | 2 | 2 | 5 | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42576?_a=files | 2025-06-03 | 2025-06-03 | Done | Nil | Done | 2025-06-03 | Nil | Approved | Approved
7 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Allen | 25337 | Activities - Admin - Failed uploads due to "glAcctID" not matched for District or Login [3.9] | Defect Fixed | 2 | 2 | 7 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42566 | 2025-06-03 | 2025-06-03 | Done | Nil | Done | 2025-06-03 | Nil | NA | NA
8 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Ram | 48529 | Activities - SYSTEM - Update Admin Header to React & Start Vega UI Updates [Timebox] | Story Completed | 8 | 8 | 32 | [13 empty] | NA | NA
9 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Bala/Athi | 48528 | Activities - SYSTEM - Update Admin Left Nav to React & Start Vega UI Updates [Timebox] | Story Completed | 13 | 16 | 64 | [13 empty] | NA | NA
10 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 | Kaliammal | 25389 | Activities - Admin - Regression Defect - MSB Invoice Details tab is missing, When we enable Split billing toggle. | Defect Fixed | 3 | 5 | 20 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42750 | 2025-06-11 | 2025-06-11 | Done | Nil | Done | 2025-06-11 | Nil | NA | NA
11 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 Stretch | Allen | 25369 | Activities - Admin - Accounting Payments - Dynamically showing split billing yes/no instead of historically | Defect Fixed | 2 | 4 | 16 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42673 | 2025-06-06 | 2025-06-06 | Done | Nil | Done | 2025-06-09 | Nil | NA | NA
12 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 Stretch | Allen | 48576 | Activities - SYSTEM - Convert to Functional Components [Dev] | Story Completed | 5 | 5 | 18 | [13 empty] | NA | NA
13 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 Stretch | Allen | 45713 | Activities - Integrate with NotificationHub (Discovery) | Story Completed | 5 | 5 | 18 | [13 empty] | NA | NA
14 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 Stretch | Hari | 48672 | Activities - SYSTEM - Update Tile Layout Pages to React [DEV Only] | Story Completed | 5 | 4 | 16 | [13 empty] | NA | NA
15 | MSB Activities | 2025-06-04 | 2025-06-17 | 3.9 Sprint S3 Stretch | Hari | 48717 | Activities - Registration - Specific URLs Discovery | Story Completed | 3 | 2 | 8 | [13 empty] | NA | NA

## 3.9 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 3.9 Sprint S3 | 25330 Activities - Admin - Contacts - Getting "Model state invalid" error if we remove the E-mail Address | 25330 | Kaliammal | Defect | If we remove the email address field and save the contact, getting this error "Model state invalid" | Significant | Manual | External | Defect Fixed | QA | PROD Issue [Carried from previous sprint for testing] | Kaliammal - Offshore Dev
2 | 3.9 Sprint S3 | 48281 Activities - Accounting - Retain Grid Records in Fees Page [3.9] | 48281 | Hari | Bounceback/Sub-Defect | Scenario the previous selection it doesnt load data anymore for split billing | Significant | Manual | Internal | Story Completed | Development |  | Jeff - Onsite QA
3 | 3.9 Sprint S3 | 25389 Activities - Admin - Regression Defect - MSB Invoice Details tab is missing, When we enable Split billing toggle. | 48377 | Kaliammal | Defect | MSB Invoice Details tab is missing, When we enable Split billing toggle | Significant | Manual | Internal | Defect Fixed | QA |  | Manjunathan - Offshore QA
4 | 3.9 Sprint S3 Stretch | 25369 Activities - Admin - Accounting Payments - Dynamically showing split billing yes/no instead of historically |  | Allen | Defect | On the payments grid we are showing split billing yes/no reflected from student maintenance. We should be showing it based on the purchase details screen | Significant | Manual | External | Defect Fixed | Existing_Issues | PROD Issue | Jeff - Onsite QA

## 3.9 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 | Allen | 25219 | Activities - Dynamic Report Generator - Duplicates on Report (Volusia) | Defect Fixed | 3 | 3 | 11 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42430 | 2025-05-28 | 2025-05-28 | Done | Nil | Done | 2025-05-29 | Nil | NA | NA
2 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 | Hari | 48069 | Activities - Admin - Relocate Split Billing to a Tab in Student Maintenance | Story Completed | 1 | 1 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42296 | 2025-05-20 | 2025-05-20 | Done | Nil | Done | 2025-05-20 | Nil | NA - Done in last sprint | NA - Done in last sprint
3 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 | Kaliammal | 48128 | Activities - Admin - Audit logging for New Split Billing | Story Completed | 2 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42296 | 2025-05-20 | 2025-05-20 | Done | Nil | Done | 2025-05-20 | Nil | NA - Done in last sprint | NA - Done in last sprint
4 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 | Hari | 48353 | Activities - Students - View/Read Only for Split Billing Tab | Story Completed | 3 | 3 | 13 | Done | Kaliammal | 1) Add space second row card 2) Long Contact name makes misalignment | Kaliammal | Remove unused component reference and components | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42416 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42448 | 2025-05-27 | 2025-05-27 | Done | Nil | Done | 2025-05-27 | Nil | 1. The percentage field name should be "Billing Percentage," as per the UI mockup. 2. If the toggle is set to off, the save button hover message shows "Contacts cannot be" blank—remove that message. 3. If the contact has no email ID, the validation message is not clear even if we selected the proper email contact. | Approved
5 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 | Kaliammal | 48377 | Activities - Accounting - Payments - Show MSB Invoice Details For Split Billing | Story Completed | 8 | 8 | 32 | Done | Hari | 1.Error in Purchase detail page when invoice is not uploaded 2.Collapsable panel is toggling between open and close when i click anywhere in the entire panel 3.Syntax error code being displayed in details page | Hari | 1.Create a separate component for Splitbilling voice instead on making UI Changes in the existing Component making Details page loosely coupled with new feature 2.create new variable by checking the length of msbInvoiceDetailModel instead of accessing 0th index -- detailspage and SplitBillingPage 3.rename InvoiceBy to IsInvoiceByEmail 4.Provide Onclick event to header alone to toggle expansion panel | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42487 | 2025-05-29 | 2025-05-29 | Done | Nil | Done | 2025-06-02 | Nil | Approved | Approved
6 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 | Hari | 45974 | Activities - Accounting - Retain Grid Records in Payments Page | Story Completed | 5 | 5 | 18 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42414 | 2025-05-27 | 2025-05-27 | Done | Nil | Done | 2025-05-27 | Nil | In the search bar, the searched value should display the table grid value based on the changing the date. | NA
7 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 | Allen | 48181 | Activities - SYSTEM - Include Additional Fields in Tenant Add Page | Story Completed | 1 | 2 | 10 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42342 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42548 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42415 | 2025-05-22 | 2025-05-22 | Done | Nil | Done | 2025-05-22 | Nil | NA - Done in last sprint | NA - Done in last sprint
8 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 | Kaliammal | 25123 | Activities - Admin - Total Record Count is showing wrongly in Roles Page | Defect Fixed | 1 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42284 | 2025-05-20 | 2025-05-21 | Done | Nil | Done | 2025-05-21 | Nil | NA | NA
9 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 Stretch | Allen | 25263 | Activities - Reports - Student Registration Report - Student Selector not searching past initial 50 - PROD | Defect Fixed | 2 | 2 | 8 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42332 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42357 | 2025-05-22 | 2025-05-27 | Done | Nil | Done | 2025-05-27 | Nil | NA | NA
10 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 Stretch | Hari | 25267 | Activities - Admin - Student Maintenance - Not redirecting after making an edit | Defect Fixed | 1 | 1 | 3 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42327 | 2025-05-21 | 2025-05-21 | Done | Nil | Done | 2025-05-21 | Nil | NA | NA
11 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 Stretch | Hari | 48485 | Activities - Admin - Deselect Optional Fields in Single Selection Drop-down Component | Story Completed | 2 | 1 | 5 | Done | Allen | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42480 | 2025-05-29 | 2025-04-29 | Done | Nil | Done | 2025-05-29 | Nil | Approved | Approved
12 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 Stretch | Hari | 48281 | Activities - Accounting - Retain Grid Records in Fees Page | Story Being Tested | 5 | 3.5 | 13.5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42530 | 2025-06-02 | 2025-06-02 | Done | Nil | Done | 2025-06-03 | Nil | If we select all the fees from the drop-down (All Selected) and click the search, the fee record is not displaying. | Approved
13 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 Stretch | Kaliammal | 25330 | Activities - Admin - Contacts - Getting "Model state invalid" error if we remove the E-mail Address | Defect Peer Review | 2 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42569 | 2025-06-03
14 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 Stretch | Kaliammal | 47956 | Activities - Admin - People - Update Icons and Tile Layout | Story Being Tested | 3 | 2.5 | 9 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42528 | 2025-06-02 | 2025-06-02 | Done | Nil | Done | 2025-06-03 | Nil | Approved | Approved
15 | MSB Activities | 2025-05-21 | 2025-06-03 | 3.9 Sprint S2 Stretch | Hari | 48400 | Activities - Students - Audit Log - Capture Updated Contact User ID for New Split Billing | Story Being Tested | 5 | 2.5 | 10.5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42531 | 2025-06-02 | 2025-06-02 | Done | Nil | Done | 2025-06-03 | Nil | Approved | Approved

## 3.9 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 3.9 Sprint S2 | 48069 - Activities - Admin - Relocate Split Billing to a Tab in Student Maintenance | 48069 | Hari | Bounceback/Sub-Defect | Delete contact and hit cancel, choose discard changes screen doesn't refresh | Significant | Manual | Internal | Defect Fixed | Development | Carried from previous sprint for testing | Jeff - Onshore QA
2 | 3.9 Sprint S2 | 48069 - Activities - Admin - Relocate Split Billing to a Tab in Student Maintenance | 48069 | Hari | Bounceback/Sub-Defect | While deleting the contact and discard changes, Cancel button is not enabled. | Significant | Manual | Internal | Defect Fixed | Development | Carried from previous sprint for testing | Manjunath - Onshore QA
3 | 3.9 Sprint S2 | 25213 Activities - Admin - Total Record Count is showing wrongly in Roles Page |  | Kaliammal | Defect | The total count of the record is showing wrongly in the Roles section. | Minor | Manual | External | Defect Fixed | Existing_Issues | "PROD Issue" [Internal Findings] Carried from previous sprint for testing | Kanchana - Offshore PO
4 | 3.9 Sprint S2 | 25219 Activities - Dynamic Report Generator - Duplicates on Report (Volusia) |  | Allen | Defect | It looks like the student selector search function is not searching for students past the initial 50 that it loads when the page loads the students into the selector. The students do appear when using the Select All functionality. | Significant | Manual | External | Defect Fixed | QA | PROD Issue | Reported by Stake holder
5 | 3.9 Sprint S2 | 48181 Activities - SYSTEM - Include Additional Fields in Tenant Add Page | 48181 | Allen | Bounceback/Sub-Defect | Required field validation for MSB provider ID not working, Need to change selection dropdown text. | Minor | Manual | Internal | Story Completed | Development | 48181 - Story Bounceback | Manjunath - Onshore QA
6 | 3.9 Sprint S2 | 48181 Activities - SYSTEM - Include Additional Fields in Tenant Add Page | 48181 | Allen | Bounceback/Sub-Defect | on the edit screen we are forcing the user to put in the password everytime they click save, we should only make them input the password when the username field changes | Minor | Manual | Internal | Story Completed | Development | 48181 - Story Bounceback | Jeff - Onshore QA
7 | 3.9 Sprint S2 Stretch | 25263 Activities - Reports - Student Registration Report - Student Selector not searching past initial 50 - PROD | 45905 | Allen | Defect | "When viewing the resulting report, there are duplicates of each student (typically 4 copies of each student) - have confirmed that these students are not enrolled 4 times in the program. I also tested it with using only 1 term and the result is the same, with 4 copies of each student." | Significant | Manual | External | Defect Fixed | Existing_Issues | PROD Issue | Reported by Stake holder
8 | 3.9 Sprint S2 Stretch | 25267 Activities - Admin - Student Maintenance - Not redirecting after making an edit | 48069 | Hari | Defect | When making an edit to a student, after clicking save, the screen does nothing. The save occurs, but we stay in the edit screen. (video attached) | Significant | Manual | Internal | Defect Fixed | Development |  | Jeff - Onshore QA
9 | 3.9 Sprint S2 Stretch | 25330 Activities - Admin - Contacts - Getting "Model state invalid" error if we remove the E-mail Address |  | Kaliammal | Defect | If we remove the email address field and save the contact, getting this error "Model state invalid" | Significant | Manual | External | Defect Peer Review | QA | PROD Issue [Carried to next sprint for testing] | Kaliammal - Offshore Dev

## 3.9 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story Meet Expectations?
1 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Allen | 48069 | Activities - Admin - Relocate Split Billing to a Tab in Student Maintenance | Story Being Tested | 3 | 5 | 19 | Done | Kaliammal | Suggestion: three box can be same height | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42229 | 2025-05-16 | 2025-05-19 | Done | Nil | Done | 2025-05-19 | Nil | 1. When I add a contact and click details tab it shows Edit student page. 2. When I disabled the split billing toggle, still cancel button enabled and shows message. 3. Save and Cancel button need to disable when the toggle off. | Approved | UI Layout to be responsive and UI Enhancements to handle discard change Confirmation increased dev effort by one more day and couple of bouncebacks during testing
2 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Kaliammal | 48171 | Activities - Split Billing - Capture Split Billing Invoice Details within Purchase Invoice Table | Story Completed | 5 | 4 | 14 | Done | Hari | Nil | Hari | need to update this only for splitbilling invoice | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42148?_a=files | 2025-05-13 | 2025-05-13 | Done | 1) Change word SplitBillingEnabled to isSplitBillingEnabled | Done | 2025-05-13 | Nil | NA | NA
3 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Hari | 48115 | Activities - Admin - Upgrade Existing Audit Log to a Table Grid for Student Maintenance | Story Completed | 8 | 8 | 32 | Done | Kaliammal | " 1) Splitbilling Removed status 2)Administrative Notes for Operating Day Alert and Status field - need to add" | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42160 | 2025-05-13 | 2025-05-14 | Done | Nil | Done | 2025-05-14 | Nil | 1.It should be "Added" - A should be caps 2.Instead of edited - change to "Updated" - U should be caps 3.Sorting does not work for case-sensitive sorting. 4.While deleting an Administrative notes, I got an server error in Audit log page. Suggestion given for transfer/withdrawal & schedule transfer/withdrawal display to the Dev team.
4 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Allen | 48189 | Activities - SYSTEM - Autofill District ID, State & TimeZone based on District Name | Story Completed | 3 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42141 | 2025-05-12 | 2025-05-12 | Done | Nil | Done | 2025-05-13 | 1.This comment doesn't match the upgrade 2.I may have missed it, but is this used? It looks as if the infinite scroll logic isn't happening only when this is set | Approved | Approved
5 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Allen | 48190 | Activities - SYSTEM - New component for Loading Fields within Dropdown [Dev Only] | Story Completed | 3 | 3 | 13 | Done | Hari | Nil | Hari | Nil | [8 empty] | 1.Without selecting a district name and clicking Save, the validation message is missing. 2.District name - clear search values once the district is selected. 3.District name search—loading (for characters/cursor point) | Approved
6 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Hari | 48193 | Activities - SYSTEM - Pagination showing page 0 when on page 2 and then a search returns less than 10 entries [3.9] | Story Completed | 1 | 1 | 4 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42029 | 2025-05-05 | 2025-05-07 | Done | Nil | Done | 2025-05-07 | Nil | NA | NA
7 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Kaliammal | 48194 | Activities - SYSTEM - Tech Debt - Move Job timing triggers into App Settings [3.9] | Story Completed | 1 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41894 | 2025-04-25 | 2025-05-05 | Done | Nil | Done | 2025-05-07 | Nil | NA | NA
8 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Kaliammal | 48076 | Activities - Registrations - Remove Scroll Bar in Header [3.9] | Story Completed | 1 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42037 | 2025-05-05 | 2025-05-06 | Done | Nil | Done | 2025-05-07 | Nil | NA | NA
9 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 | Kaliammal | 48077 | Activities - Admin - Registrations - Update Term Name breadcrumbs & header after hitting the Browser back button [3.9] | Story Completed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42036 | 2025-05-05 | 2025-05-06 | Done | Nil | Done | 2025-05-07 | Nil | NA | NA
10 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 Stretch | Kaliammal | 48128 | Activities - Admin - Audit logging for New Split Billing | Story Ready For Testing | 5 | 3.5 | 14 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42285 | 2025-05-20 | 2025-05-20 | Done | Nil | Done | 2025-05-21 | Nil | 1.First time enabling split billing Actions Columns should be - Added 2.Instead of Details should be Split Billing in Description column when split billing enabled | Approved
11 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 Stretch | Allen | 48181 | Activities - SYSTEM - Include Additional Fields in Tenant Add Page | Story Being Developed | 2 |  |  | Done | Hari | Nil | Hari | Nil | [8 empty] | 1.For add screen , Username, password and Provider are after time zone. I need three fields should match like edit screen. While adding these fields are must we can show top. 2.Then suggestion if possible include upload username, Provider field details in view screen
12 | MSB Activities | 2025-05-07 | 2025-05-20 | 3.9 Sprint S1 Stretch | Kaliammal | 25213 | Activities - Admin - Total Record Count is showing wrongly in Roles Page | Defect Being Tested | 2 | 1.5 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42284 | 2025-05-20 | 2025-05-20 | Done | Nil | Done | 2025-05-21 | Nil

## 3.9 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 3.9 Sprint S1 | 48189 - Activities - SYSTEM - Autofill District ID, State & TimeZone based on District Name | 48189 | Allen | Bounceback/Sub-Defect | District and Site settings getting render error after click edit and then either save or cancel. | Significant | Manual | Internal | Defect Fixed | Development |  | Kanchana - Offshore PO
2 | 3.9 Sprint S1 | 48189 - Activities - SYSTEM - Autofill District ID, State & TimeZone based on District Name | 48189 | Allen | Bounceback/Sub-Defect | It is auto populating existing districts that have no timezone | Significant | Manual | Internal | Defect Fixed | Development |  | Manjunath - Offshore QA
3 | 3.9 Sprint S1 | 48069 - Activities - Admin - Relocate Split Billing to a Tab in Student Maintenance | 48069 | Hari | Bounceback/Sub-Defect | Delete contact and hit cancel, choose discard changes screen doesn't refresh | Significant | Manual | Internal | Defect Being Fixed | Development | Carried to next sprint for testing | Jeff - Onshore QA
4 | 3.9 Sprint S1 | 48069 - Activities - Admin - Relocate Split Billing to a Tab in Student Maintenance | 48069 | Hari | Bounceback/Sub-Defect | While deleting the contact and discard changes, Cancel button is not enabled. | Significant | Manual | Internal | Defect Being Fixed | Development | Carried to next sprint for testing | Manjunath - Onshore QA
5 | 3.9 Sprint S1 Stretch | 25213 Activities - Admin - Total Record Count is showing wrongly in Roles Page |  | Kaliammal | Defect | The total count of the record is showing wrongly in the Roles section. | Minor | Manual | External | Defect Being Fixed | Existing_Issues | "PROD Issue" [Internal Findings] RCA: Because, we have default roles like Central Office, Site Coordinator, Full Control, Reporting Only, and Read Only, but currently the "Read Only" role works based on the config props enable (true/false). So, it takes the count of the default 5 roles and displays it. Carried to next sprint for testing | Kanchana - Offshore PO

## 3.8 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 | Hari | 47712 | Activities - SYSTEM - Pagination showing page 0 when on page 2 and then a search returns less than 10 entries [3.9] | Story Completed | 5 | 4.5 | 18 | Done | Kaliammal | 1) Searched word retained after action 2) Sort is undefined. | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42029 | 2025-05-05
2 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 | Allen | 47961 | Activities - RESEARCH - Split Billing Audit Logging Updates | Story Completed | 2 | 2 | 8
3 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 | Kaliammal | 47982 | Activities - SYSTEM - Tech Debt - Move Job timing triggers into App Settings [3.9] | Story Completed | 2 | 2 | 8 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41894 | 2025-04-25 | 2025-05-05 | Done | remove PreviousDaysLookup from appsettings.Development.json | Nil | 2025-05-06
4 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 Stretch | Kaliammal | 47819 | Activities - Admin - Registrations - Display Valid Message when Hitting the Browser Back Button | Story Completed | 1 | 1 | 4 | Done | Hari | Nil | Hari | 1.Use Enum Description instead of Switch Case 2.Use Bootstrap text-warning class instead of custom class | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41861 | 2025-04-23 | 2025-04-24 | Done | Nil | Nil | 2025-04-24
5 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 Stretch | Hari | 47857 | Activities - Admin - Include Search Criteria to Filter MSB Profile Fields Drop-Down List | Story Completed | 1 | 1.25 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41784 | 2025-04-17 | 2025-04-22 | Done | Nil | Done | 2025-04-22 | Can we use a different interface name, with these changes we have more than just a Name Value Pair, so this name could be confusing.
6 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 Stretch | Allen | 48034 | Activities - SYSTEM - Improve Handling for Adding Tenant [3.9] | Story Being Developed | 3 | 0
7 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 Stretch | Kaliammal | 48077 | Activities - Admin - Registrations - Update Term Name breadcrumbs & header after hitting the Browser back button [3.9] | Story Peer Review | 2 | 2.25 | 9 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42036 | 2025-05-05
8 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 Stretch | Kaliammal | 48076 | Activities - Registrations - Remove Scroll Bar in Header [3.9] | Story Peer Review | 1 | 1.25 | 5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42037 | 2025-05-05
9 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 Stretch | Hari | 48110 | Activities - RESEARCH - Display MSB Invoice Details For Split Billing in Activities | Story Completed | 5 | 4 | 16
10 | MSB Activities | 2025-04-23 | 2025-05-06 | 3.8 Sprint S3 Stretch | Kaliammal | 48150 | Activities - RESEARCH - Select Multiple EPs on Custom Registration Report | Story Completed | 3 | 2.75 | 11

## 3.8 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised

## 3.8 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 | Kaliammal | 45905 | Activities - Admin - Reports - Improve Student Filter Multi-Select dropdowns | Story Completed | 2 | 2 | 8 | Done | Hari | On hover, subtext label and value is not visible | Hari | remove isSubTextMode from IProps since it is not used | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41564 | 2025-04-09 | 2025-04-09 | Done | Nil | Andy |  | On this line we're modifying the value in props.student, props should be immutable in react. Can we create a new array that we'll populate from what we have received from the prop and update that instead? | 1. If no student is available based on the selection made we should display the same message "No Students Are Available" - Missed | Approved
2 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 | Allen | 46980 | Activities - Parent - Update Submit Page" Student" Labels | Story Completed | 1 | 1.25 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41722 | 2025-04-14 | 2025-04-14 | Done | Nil | Done | 2025-04-15 | Nil | Given Suggestions: To have Field name should start with Caps for contact, activity schedule, and forms | Pending
3 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 | Allen | 47331 | Activities - Central Office Role - Selected Actions Bulk Edit | Story Completed | 1 | 1.5 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41662 | 2025-04-09 | 2025-04-09 | Done | Nil | Done | 2025-04-09 | Nil | "Did the initial POV. Selected Actions—Edit not show in the drop-down list of the enrollment plan if the user was assigned to the central office role" - Fixed Approved | Approved
4 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 | Allen | 47750 | Activities - Enrollment Plans - Convert Custom Field toggles to tabs and display selected count | Story Completed | 2 | 2 | 8 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41635 | 2025-04-08 | 2025-04-08 | Done | Nil | Done | 2025-04-09 | Nil | 1.Bold missing for this AC point- if >1 custom fields are selected for that type, show as the number in parentheses bolded. ie: (#) - pov comment fixed. Approved | Approved
5 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 | Allen | 47685 | Activities - Admin - Split Billing Updates | Story Being Tested | 13 | 0 | 0 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41661 | 2025-04-09 | 2025-04-09 | Done | Nil | Done | 2025-04-09 | We're able to have more than one contact with the relationship type of parent, by doing FirstOrDefault on contacts that are contact type Primary or relationship type Parent, don't we open ourselves up to having multiple contacts that fit and picking one arbitrarily? Should we be looking only at primary contact? I may be misunderstanding the intent here. | 1.For existing split billing: once we enable config props -It automatically fetches the email address for the parent account (actually, it will fetch based on the MSB user account). 2. The first time, I enabled split billing for a student. For the parent, it first fetched the email address instead of the user account. 3.If not set selected in the drop-down—user account/email not clearing. 4. Search for any characters like TESTA,It is retained in the search box and not clearing the value, still able to update it and save. 5.If the retained user email/account in the search box matches with other contacts . After saving, it matches with the proper email address. 6. The previous selection notification is not showing. 7. Invoice part does not work as expected in MSB. 8. Contact page UI drop down - we can remove "Email" text because we are not matching with email. | 1. I think once an MSB user is selected for one of the split billing contacts for that student, we should not show that msb user as an option/disable that option for additional split billing contacts (can't have one msb user linked to 2 separate split billing contacts for the same student) Approved | Complexities of Split Billing, remaining testing efforts carried over 3.8 Sprint 3 Stretch (We are ahead of our release schedule)
6 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 | Kaliammal | 47631 | Activities - Registrations - Update Tile Layout and Icons | Story Completed | 5 | 3.5 | 14 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41702 | 2025-04-11 | 2025-04-11 | Done | Nil | Done | 2025-04-14 |  | Approved | POV feedback - everything looks great, but I'd like for the notification badge on the upper right corner of the tile to not overlap the title text for the District Overview Registration tiles. If we can reduce the radius of the notification badge (while keeping the number centered within the badge and easy to read for larger registration counts like 1,000+), and/or increase the padding above the title, and/or increase the length of the tile so that it does not appear crowded at the bottom of the tile when the notification badge is not present. Also, we should ensure that whatever changes we make to the district overview registration tiles we also apply to the site level registration tiles for consistency.
7 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 | Hari | 47839 | Activities - Split Billing - Prevent Deleting Split Billing Contacts & Error Messaging | Story Completed | 5 | 5.5 | 22 | Done | Kaliammal | 1. Parent Delete Button alignment issue and Showing error message for unlinked contact | Kaliammal | Remove unused imports | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41771 | 2025-04-16 | 2025-04-16 | Done | Nil |  |  |  | 1. Missing a red color for the X icon. 2. Contacts details screen field name needs to update as "Linked MSB Account" 3. Contact message need to confirm -- - "The linked MSB User Account for this contact cannot be changed at this time due to an association with another Split Billing configuration." 4. When I select Not set option in drop down - it throws server error. | Approved
8 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 Stretch | Kaliammal | 47016 | Activities - Parent - Update Submit Page "Forms" Labels | Story Completed | 3 | 3.25 | 13 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41772 | 2025-04-16 | 2025-04-16 | Done | Nil |  |  |  | Approved | Approved
9 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 Stretch | Hari | 47857 | Activities - Admin - Include Search Criteria to Filter G/L Account Drop-Down List | Story Peer Review | 8 | 0 |  | Done | Kaliammal | Nil | Nil | Nil | [8 empty] | 1. Getting server error. 2. Once searched values are selected, could not see other values in the dropdown list. | Approved | Carried to next sprint for PR & Testing
10 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 Stretch | Allen | 47849 | Activities - RESEARCH - Split Billing Audit Logging Updates | Story Completed | 5 | 5 | 20 | [13 empty] | NA | NA
11 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 Stretch | Kaliammal | 47819 | Activities - Admin - Registrations - Display Valid Message when Hitting the Browser Back Button | Story Being Developed | 3 | 0
12 | MSB Activities | 2025-04-09 | 2025-04-22 | 3.8 Sprint S2 Stretch | Allen | 47954 | Activities - People - Search by Student for Parents & Other Contacts | Story Completed | 3 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41777 | 2025-04-16 | 2025-04-16 | Done | Nil |  |  |  | NA | NA

## 3.8 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 3.8 Sprint S2 | Escalation:SRX26016 - Activities - Add User - Text hidden for Default Site dropdown | 47188 | Allen | Defect | Found that while adding a new admin user, the default site dropdown is expanding, however, the text for the Site Names is hidden. We are able to select a site from this dropdown, however, the text is blank/missing. Editing users does not appear to be affected. | Minor | Manual | External | Defect Fixed | QA | "PROD Issue" [Internal Findings] RCA: Issue is related with 3.7 last release. Issue happened due to update "Description" to Item Name in SQL Tables. | Kanchana - Offshore PO
2 | 3.8 Sprint S2 | Escalation:SRX25972- Activities - Admin Manual Registration for New Parent Account Issue |  | Andy | Defect | We are currently getting into an error state for admins manually registering a new parent account. - It appears this issue is caused by the contact relationship type field being required and us not saving the false value to that for these new parent accounts with admin manual registration. | Significant | Manual | External | Defect Fixed | Existing_Issues | "PROD Issue" [Existing Issue] | Reported by Stakeholder

## 3.8 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 | Allen | 47685 | Activities - Admin - Split Billing - Link MSB User ID/Login ID to Split Billing Contacts [Dev & PR] | Story Being Developed | 8 | 8 | 33 | Done | Hari | Nil | Hari | Nil | [8 empty] | 1.For existing split billing: once we enable config props -It automatically fetches the email address for the parent account (actually, it will fetch based on the MSB user account). 2. The first time, I enabled split billing for a student. For the parent, it first fetched the email address instead of the user account. 3.If not set selected in the drop-down—user account/email not clearing. 4. Search for any characters like TESTA,It is retained in the search box and not clearing the value, still able to update it and save. 5.If the retained user email/account in the search box matches with other contacts . After saving, it matches with the proper email address. 6. The previous selection notification is not showing. 7. Invoice part does not work as expected in MSB. 8. Contact page UI drop down - we can remove "Email" text because we are not matching with email | 1. I think once an MSB user is selected for one of the split billing contacts for that student, we should not show that msb user as an option/disable that option for additional split billing contacts (can't have one msb user linked to 2 separate split billing contacts for the same student)
2 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 | Allen | 47686 | Activities - Fees/Discounts/Forms - Update "Description" to Item Name in SQL Tables (System) [PR & QA - 3.8] | Story Completed | 5 | 8 | 30 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41304 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41247 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41382 | 2025-03-25 | 2025-03-25 | Done | Nil | Done | 2025-03-26 | Nil | NA | NA
3 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 | Allen | 47182 | Activities - Custom Fields/Dynamic Reports - Update "Description" to Item Name in SQL Tables (SYSTEM) *final [3.8] | Story Completed | 8 | 8 | 33 | [5 empty] | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41217 | 2025-03-31 | 2025-03-31 | Done | Nil | Done | 2025-04-01 | Nil | NA | NA
4 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 | Hari | 47250 | Activities - Admin - Enrollment Plan - Student, Parent, and Contacts Fields >Stock & Custom Fields > Multi-Selection | Story Completed | 8 | 8 | 30 | Done | Kaliammal | 1) Remove one field ,all fields are removed. 2) click Enrollment Plan-Custom fields, page got refreshed and details are cleared. 3)Remove saved fields and not enable in left side. | Kaliammal | Remove unused icon, | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41527 | 2025-04-01 | 2025-04-02 | Done | Nil | Done | 2025-04-03 | Nil | 1. Ok button disable. 2.Required field should be disable. 3.Add Field(s) button should display at the right corner. | Approved
5 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 | Kaliammal | 47418 | Activities - Reports - Update Tile Layout and Icons | Story Completed | 3 | 3 | 14 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41524?_a=updates | 2025-04-01 | 2025-04-03 | Done | Some Alignment of tile mismatch. | Nil | 2025-04-04 | Nil | Suggested increasing the size of the report name text within the tile (like we have for the Setup page) - . | Approved Kristy agreed the suggestions, provided by Kanchana. Kanchana suggested increasing the size of the report name text within the tile (like we have for the Setup page) - I agree. If we can, we should make it so that the icons and description text within the Reports tiles always are in line with each other (even if one report name takes up 2 lines while another only takes up 1 line).
6 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 | Kaliammal | 47393 | Activities - Admin - Update User Menu Options | Story Completed | 3 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41456 | 2025-03-28 | 2025-04-01 | Nil | Nil | Nil | 2025-04-01 | Nil | 1.Profile icon size is not fit the screen. 2. Show firstname,last name for user profile icon. | Approved
7 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 | Allen | 47462 | Activities - SYSTEM - Show 'Total Count' of Table Grid Entries with Pagination [PR & QA] | Story Completed | 1 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41383 Bounce PR: https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41451 | 2025-03-25 | 2025-03-26 | Done | Nil | Done | 2025-03-26 | Nil | 1. The Selected Actions table grid total count missing. 2. A few pages show 1 to 0 of 0 records (if there is no data in the table grid). | Approved
8 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 Stretch | Hari | 47750 | Activities - Enrollment Plans - Convert Custom Field toggles to tabs and display selected count | Story Peer Review | 3 | 3 | 12 | Done | Allen | Nil | Allen | Nil | [8 empty] | 1.Bold missing for this AC point- if >1 custom fields are selected for that type, show as the number in parentheses bolded. ie: (#) | Approved | Carried to Next sprint for PR and QA
9 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 Stretch | Kaliammal | 45905 | Activities - Admin - Reports - Improve Student Filter Multi-Select dropdowns | Product Owner - Verify | 5 | 5 | 20 | Done | Hari | On hover, subtext label and value is not visible | Hari | remove isSubTextMode from IProps since it is not used | [8 empty] | Pending | Pending | Carried to Next sprint for POV, PR and QA
10 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 Stretch | Allen | 47331 | Activities - Central Office Role - Selected Actions Bulk Edit | Product Owner - Verify | 2 | 1 | 2 | Done | Hari | Nil | Hari | Nil | [8 empty] | Did the initial POV. Selected Actions—Edit not show in the drop-down list of the enrollment plan if the user was assigned to the central office role | Pending | Carried to Next sprint for POV, PR and QA
11 | MSB Activities | 2025-03-26 | 2025-04-08 | 3.8 Sprint S1 Stretch | Allen | 46980 | Activities - Parent - Update Submit Page" Student" Labels | Product Owner - Verify | 3 | 1 | 2 | Done | Kaliammal | Nil | Kaliammal | Nil | [8 empty] | Pending | Pending | Carried to Next sprint for POV, PR and QA

## 3.8 Sprint 1- Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 3.8 Sprint 1 | 47462 - Activities - SYSTEM - Show 'Total Count' of Table Grid Entries with Pagination [PR & QA] | 47462 | Hari | Bounceback/Sub-Defect | Client Side sorting pages are not filtering record count by the total returned from the search, video attached | Significant | Manual | Internal | Defect Fixed | Development |  | Jeff - Onshore QA
2 | 3.8 Sprint 1 | 47462 - Activities - SYSTEM - Show 'Total Count' of Table Grid Entries with Pagination [PR & QA] | 47462 | Hari | Bounceback/Sub-Defect | Incorrect count number when the table or Grid is empty | Significant | Manual | Internal | Defect Fixed | Development |  | Manjunathan - Offshore QA
3 | 3.8 Sprint 1 Stretch | 24940 Activities - People - Contacts - Parent records are included in Other Contacts Table Grid | 47422 | Andy/Jeff | Defect | Parent Accounts records are showing in the Other Contact table grid. Once you click the record, it shows a server error: "Contact record not found". (Happening at Site level) | Significant | Manual | Internal | Defect Fixed | Development | RCA: Missed by development/testing scenario while doing performance improvements for Parent & Contacts Grids in the last sprint story. | Kanchana - PO
4 | 3.8 Sprint 1 Stretch | 24945 Activities - People - Parent & Contacts - Pagination is not navigating to the next page if record have more than 10 | 47422 | Andy/Jeff | Defect | For site level, parent and other contacts pagination is not navigating to the next page if the records are more than 10, the pagination still shows Page 1 of 1; could not navigate to the next page. | Significant | Manual | Internal | Defect Fixed | Development | RCA: Missed by development/testing scenario while doing performance improvements for Parent & Contacts Grids in the last sprint story. | Kanchana - PO

## 3.7 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-03-11 | 2025-03-25 | 3.7 Sprint S3 | Hari | 47083 | Activities - RESEARCH - Split Billing Improvements | Story Completed | 8 | 8 | 32 | [13 empty] | NA | NA
2 | MSB Activities | 2025-03-11 | 2025-03-25 | 3.7 Sprint S3 | Allen | 47422 | Activities - Admin - Performance Improvements, Search, Sorting ''Parent Account'' column in Parent/Other Contacts Grids [PR and QA] | Story Completed | 2 | 5 | 19 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41167 | 2025-03-11 | 2025-03-11 | Done | Nil | Andy | 2025-03-11 | The filter text needs to be parameterized to prevent against SQL injection | NA | NA | Discussed Multiple Approaches with Client and Decided suitable solution for this release took more effort than the initial estimate
3 | MSB Activities | 2025-03-11 | 2025-03-25 | 3.7 Sprint S3 | Allen | 46723 | Activities - Fees/Discounts/Forms - Update "Description" to Item Name in SQL Tables (System) [Dev Only - 3.8] | Story Completed | 5 | 6 | 26 | Done | Kaliammal | Nil | Kaliammal | Nil | [8 empty] | NA | NA
4 | MSB Activities | 2025-03-11 | 2025-03-25 | 3.7 Sprint S3 Stretch | Kaliammal | 47182 | Activities - Custom Fields/Dynamic Reports - Update "Description" to Item Name in SQL Tables (SYSTEM) *final [3.8] | Story Completed | 5 | 5 | 20 | Done | Hari | Nil | Hari | Nil | [8 empty] | NA | NA
5 | MSB Activities | 2025-03-11 | 2025-03-25 | 3.7 Sprint S3 Stretch | Kaliammal | 47540 | Activities - SYSTEM - Apply Background Color to Selected Actions Page [3.7] | Story Completed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41275 | 2025-03-18 | 2025-03-19 | Done | Nil | Done | 2025-03-19 | Nil | NA | NA
6 | MSB Activities | 2025-03-11 | 2025-03-25 | 3.7 Sprint S3 Stretch | Hari | 47462 | Activities - SYSTEM - Show 'Total Count' of Table Grid Entries with Pagination [3.8] | Story Peer Review | 5 |  |  | Done | Kaliammal | Nil | Kaliammal | NIl | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41383 | 2025-03-25 | [6 empty] | NA | NA

## 3.7 Sprint 3- Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 3.7 Sprint 3 | 24825 - Activities - Parent - Regression Defect - Missed renaming in group by for Tax Report | 24825 | Andy/Jeff | Defect | Parent tax report is throwing a 400 server error due to a missing rename in the group by portion of the querry. | Significant | Manual | Internal | Defect Fixed | Development | Client Development
2 | 3.7 Sprint 3 | 24832 - Activities - Admin - Regression Defect - Missed column information on new database approach in selected actions | 24832 | Andy/Jeff | Defect | Missed column information on new database approach in selected actions | Significant | Manual | Internal | Defect Fixed | Development | DB Changes [Internal Findings] Relevantz Development | Jeff - Onshore QA
3 | 3.7 Sprint 3 Stretch | 24854 - Activities - Admin - Dynamic Reports run button not working if all selected is present on the tree component selector | 24854 | Andy/Jeff | Defect | Dynamic Reports run button not working if all selected is present on the tree component selector (video shows it better) | Significant | Manual | External | Defect Fixed | Existing_Issues | PROD Issue [Internal Findings] Relevantz Development RCA: Impact areas covered to test | Jeff - Onshore QA
4 | 3.7 Sprint 3 Stretch | 24851 - Activities - Admin - EP creation gives an error on creation when select All activities is used | 24851 | Andy/Jeff | Defect | If you have only all activities are selected, when you are creating a new EP you get an error that you must select 1 activity. (looks like it displays "all Activities" selected but isnt picking up that there is one selected) | Significant | Manual | External | Defect Fixed | Existing_Issues | PROD Issue [Internal Findings] Relevantz Development RCA: Impact areas covered to test | Jeff - Onshore QA

## 3.7 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 | Allen | 46830 | Activities - Term/Site - Update "Description" to Item Name in SQL Tables (SYSTEM) | Story Completed | 5 | 6 | 24 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40853 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41083 | 2025-02-19 | 2025-03-06 | Done | Nil | Andy [Done] | 2025-03-06 | I think this should be IS NOT NULL? If the column was just added, we'll be missing the constraint that was added above when the table is originally added. I think we need to conditionally add the UK_SITE_Name constraint here if the column exists but the constraint does not Missing BEGIN after IF Suggestions: I think this comment is left from the old process, can we remove or update it to reflect the new approach The constraint name being added here doesn't match the name used below (UK_SITENAME) so it will be added a second time | NA | NA
2 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 | Allen | 47322 | Activities - Setup - Update icons, text position, and order for tiles | Story Completed | 3 | 3 | 10 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41007 | 2025-02-27 | 2025-02-27 | Done | Nil | Done | 2025-02-27 | Nil | Approved | Please increase the size of the icons, decrease padding between the icon and the header, Update Event Payment Profiles tile name to "Events"
3 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 Stretch | Allen | 47261 | Activities - Setup - Dynamically Assign Page Icons based on Page Section | Story Completed | 5 | 5 | 21 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41007 | 2025-02-27 | 2025-02-27 | Done | Nil | Done | 2025-02-27 | Nil | 1. Old icon is displayed for Pin Maintenance at header section | Approved
4 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 | Kaliammal | 47325 | Activities - Custom Registration Report - Include Student Number for Output Format (Albemarle) | Story Completed | 5 | 5 | 18 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41068 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41095 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41110 | 2025-03-04 | 2025-03-04 | Done | Nil | Done | 2025-03-04 | Nil | Approved 1.Tree selection count is displayed wrongly for student stock fields. 2.Once we clicked the select all, default Student Fields > Stock > First Name, Last Name and Student# fields are able to select. | POV Comment: Requirement:If we are able to, we should make: - The Student Fields > Stock > First Name and Last Name fields selected and disable them/prevent them from being deselected (since we are always showing those on the Report). - Consider adding "Student #" to the Student Fields > Stock Fields list (below Last Name) and have this selected, and prevent the field from being deselected (since it will always appear on the Report) - If the user tries to click the x on the First Name, Late Name, or Student # fields below the Student Fields dropdown, we should show the following text "Always included in Report Output" Please let Kristy and Kanchana know if a separate story is needed for this ^
5 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 | Kaliammal | 24727 | Activities -Custom Report - Delete/Add Contact-Hide Custom Field Answer for Updated status if their previous selection was removed [PR &QA] | Defect Fixed | 3 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40940 | 2025-02-25 | 2025-03-03 | Done | Optimize the code for data table changes | Done | 2025-03-03 | NIl | NA | NA
6 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 | Hari | 46969 | Activities - Other Contacts - Customizable Column Headers | Story Completed | 5 | 5 | 20 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41062 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41099 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41138 | 2025-03-04 | 2025-03-04 | Done | Nil | Done | 2025-03-04 | Nil | Approved | Approved
7 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 | Allen | 47348 | Activities - SYSTEM - Performance Improvements for Enrollment Plan Bulk Edit [PR &QA] | Story Completed | 2 | 2 | 7 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40959 | 2025-02-26 | 2025-02-26 | Done | Nil | Done | 2025-02-27 | Nil | NA | NA
8 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 Stretch | Allen | 24763 | Activities - Admin - Roles - 'Description' text missing for Stock Roles | Defect Fixed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41034 | 2025-02-28 | 2025-02-28 | Done | Nil | Done | 2025-02-28 | Nil | NA | NA
9 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 Stretch | Kaliammal | 24712 | Activities - Admin- Pending/Waitlist Registrations - Editing a Contact showing another contact's custom field information | Defect Fixed | 3 | 3 | 9 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41096 | 2025-03-05 | 2025-03-05 | Done | Nil | Done | 2025-03-05 | Nil | NA | NA
10 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 Stretch | Hari | 24718 | Activities - Admin - Student Enrollment - Edit Schedules [Daily/Weekly] Validation Message is not cleared | Defect Fixed | 2 | 2 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41113 | 2025-03-06 | 2025-03-07 | Done | Nil | Done | 2025-03-07 | Nil | NA | NA
11 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 Stretch | Allen | 47424 | Activites - Admin - Selected Actions - Data Table Insert for Bulk Copy | Story Completed | 1 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41092 | 2025-03-05 | 2025-03-05 | Done | Nil | Done | 2025-03-05 | Nil | NA | NA
12 | MSB Activities | 2025-02-26 | 2025-03-11 | 3.7 Sprint S2 Stretch | Allen | 47422 | Activities - Admin - Search ''Parent Account'' for Other Contacts Customizable Column | Story Peer Review | 5 |  |  | Done | Hari | Nil | Hari | Nil | [10 empty] | Carried to next sprint for Client PR and Testing.

## 3.7 Sprint 2- Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 3.7 Sprint 2 Stretch | 24763 Activities - Admin - Roles - 'Description' text missing for Stock Roles |  | Allen | Defect | Found that on the roles, the description text is missing for stock roles like Central Office, Reporting, Site Coordinator, and Read Only. | Minor | Manual | External | Defect Fixed | Existing_Issues | PROD Issue [Internal Findings] Relevantz Development | Kanchana - Offshore PO
2 | 3.7 Sprint 2 Stretch | 24712 Activities - Admin- Pending/Waitlist Registrations - Editing a Contact showing another contact's custom field information |  | Kaliammal | Defect | While editing a particular contact having a custom question in pending/waitlist registration, we can see another contact's custom question information that is not given by the first contact. | Significant | Manual | External | Defect Fixed | Existing_Issues | PROD Issue [Internal Findings] Relevantz Development | Kanchana - Offshore PO
3 | 3.7 Sprint 2 Stretch | 24718 Activities - Admin - Student Enrollment - Edit Schedules [Daily/Weekly] Validation Message is not cleared |  | Hari | Defect | When we edit a schedule in the student enrollment without selecting any single day or week, it will throw a message like" Please select at least one day to continue". & " Please select at least one week to continue" | Minor | Manual | External | Defect Fixed | Existing_Issues | PROD Issue [Internal Findings] Onshore Development | Kanchana - Offshore PO
4 | 3.7 Sprint 2 | 47325 - Activities - Custom Registration Report - Include Student Number for Output Format (Albemarle) | 47325 | Kaliammal | Bounceback | Facing index error while downloading custom registration report for excel format | Significant | Manual | Internal | Defect Fixed | Development | Bounceback of the story 47325 | Manjunathan - Offshore QA
5 | 3.7 Sprint 2 | 46969 - Activities - Other Contacts - Customizable Column Headers | 46969 | Hari | Bounceback | Relationship column is not sorting properly. | Significant | Manual | Internal | Defect Fixed | Development | Bounceback of the story 46969 | Jeff - Onshore QA

## 3.7 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 | Allen | 47187 | Activities - SYSTEM - Performance Improvements for Enrollment Plan Bulk Copy (PR & QA) | Story Completed | 3 | 4 | 15 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40738 | 2025-02-12 | 2025-02-12 | Done | Nil | Done | 2025-02-14 | Nil | NA | NA
2 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 | Kaliammal | 24618 | Activities - Admin - Custom Report - Hide Custom Field Answer for Updated status if their previous selection was removed | Defect Fixed | 5 | 5 | 19 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40796 | 2025-02-17 | 2025-02-17 | Done | Nil | Done | 2025-02-17 | Nil | NA | NA
3 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 | Hari | 46968 | Activities - Parent Accounts - Customizable Column Headers | Story Completed | 5 | 6 | 22.5 |  | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40827 | 2025-02-18 | 2025-02-19 | Done | Nil | Andy | 2025-02-20 | 1.Should these have changed? 2.Shouldn't this be GridID.ParentAccountsNoSiteSelected or GridID.ParentAccountsSiteSelected ? (Suggestions) | 1.Getting server error "Invalid Column Name" while viewing the district-level view of people. 2.When a site is selected, the student list should be based on the site level. Currently, it is displayed based on the district level of students. 3.User selection sessions are not maintained for students' and parents accounts for site-level and district-level 4.District level - Students are not listed based on their site level. | Approved
4 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 | Allen | 46831 | Activities - Enrollment Plan/Activity - Update "Description" to Item Name in SQL Tables (SYSTEM) | Story Completed | 5 | 5 | 20.5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40803 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40837 | 2025-02-18 | 2025-02-18 | Done | Nil | Done | 2025-02-18 | Nil | 1.In the Enrollment plan view section: The student, Parents, and Contacts fields are displayed blank. 2.Activity name is showing blank in Pin Maintenance. | NA
5 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 | Kaliammal | 47188 | Activities - Security Group/Kiosk/District Maintenance - Update "Description" to Item Name in SQL Tables (SYSTEM) | Story Completed | 5 | 5 | 22 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40800 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40797 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40874 | 2025-02-17 | 2025-02-17 | Done | Nil | Done | 2025-02-17 | NIL | POV Completed. 1. While logged in as HSS user, getting error Invalid Column name "District Name". 2. Modal message is missing for all Jobs tools. 3. System Volume report shows errors like Invalid Column 'District Name'. 4. Modal message is missing for all Jobs tools. 5. System Volume report shows errors like Invalid Column 'District Name'. | NA
6 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 Stretch | Allen | 47163 | Activities - SYSTEM - Performance Improvements for Enrollment Plan Bulk Edit [Dev only] | Story Completed | 8 | 8 | 34 | [13 empty] | NA | NA
7 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 Stretch | Hari | 24691 | Activities - Admin - Enrollment Plan - 'Selected Actions' dropdown is enabled if no Enrollment Plans are selected | Defect Fixed | 1 | 1 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40824 | 2025-02-18 | 2025-02-18 | Done | Nil | Done | 2025-02-19 | NIL | NA | NA
8 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 Stretch | Kaliammal | 23975 | Activities - Parent - Contacts - Accept First and Last Name Field without a Space | Defect Fixed | 2 | 2 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40820 | 2025-02-18 | 2025-02-18 | Done | Nil | Done | 2025-02-25 | NIL | NA | NA
9 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 Stretch | Kaliammal | 47246 | Activities - Admin - Enrollment Plan - Update Verbiage | Story Completed | 1 | 1 | 1 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40887 | 2025-02-21 | 2025-02-25 | Done | Nil | Done | 2025-02-25 | NIL | Approved | Approved
10 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 Stretch | Hari | 47182 | Activities - Custom Fields/Dynamic Reports - Update "Description" to Item Name in SQL Tables (SYSTEM) *final | Story Peer Review | 5 |  |  | Done | Hari | Nil | Hari | Nil | [8 empty] | Custom Fields POV completed. | NA | Moved to Regression sprint for PR .
11 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 Stretch | Allen | 46830 | Activities - Term/Site - Update "Description" to Item Name in SQL Tables (SYSTEM) | Story Peer Review | 5 |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40853 | 2025-02-19 | [6 empty] | 1.Term name showing 'Undefined' in operating days - Activity session. 2.In the users section, the Default site drop-down list shows blank. 3.Bulk enrollment - JSON file needs to change for Description to corresponding item name( activities, enrollment plan, and Term). POV Completed | NA
12 | MSB Activities | 2025-02-12 | 2025-02-25 | 3.7 Sprint S1 Stretch | Kaliammal | 24727 | Activities -Custom Report - Delete/Add Contact-Hide Custom Field Answer for Updated status if their previous selection was removed | Story Peer Review | 3 |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40940 | 2025-02-25 | [6 empty] | NA | NA

## 3.7 Sprint 1- Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect Raised
1 | 3.7 Sprint S1 | 24618 - Activities - Admin - Custom Report - Hide Custom Field Answer for Updated status if their previous selection was removed | 46343 | Kaliammal | Defect | Currently, in the custom registration report, if we run the updated registration report, we are still showing the field value without striking out /not highlighting in red color/ not showing in italics (because those values are removed). | Significant | Manual | Internal | Closed/Rejected | Requirements | Carried from previous sprint for dev fix. | Manjunathan - Offshore QA
2 | 3.7 Sprint S1 Stretch | 24691 Activities - Admin - Enrollment Plan - 'Selected Actions' dropdown is enabled if no Enrollment Plans are selected |  | Hari | Defect | If we select an enrollment plan and copy/edit using the selected actions, the enrollment plan is copied/edited, but the 'Selected Actions' dropdown list is still enabled. | Significant | Manual | External | Closed/Rejected | Existing_Issues | PROD Issue. Internal Findings | Kanchana - Offshore PO
3 | 3.7 Sprint S1 Stretch | 24727- Activities -Custom Report - Delete/Add Contact-Hide Custom Field Answer for Updated status if their previous selection was removed | 46343 | Kaliammal | Defect | While deleting a contact at the parent updated registration, that deleted contact is strike out in Admin updated registration but that contact is showing in the custom registration - updated status (actually we should not show it in the report) | Significant | Manual | Internal | Inprogress | Development | The scenario missed covering up in the defect id 24618 - So we have created a separate defect to address and informed to client. Dev work completed and carried to next sprint for QA for testing. | Kanchana - Offshore PO

## 3.6 Sprint S3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-01-29 | 2025-02-11 | 3.6 Sprint S3 | Hari | 24552 | Activities - Admin - Report - Contacts are missing in custom registration report for excel format | Defect Fixed | 3 | 3 | 6 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40549 | 2025-01-29 | 2025-01-29 | Done | Nil | Done | 2025-01-29 | Nil | NA | NA
2 | MSB Activities | 2025-01-29 | 2025-02-11 | 3.6 Sprint S3 | Kaliammal | 46343 | Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) [bounceback] | Story Completed | 5 | 5 | 11 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40529 | 2025-01-28 | 2025-01-28 | Done | Nil | Done | 2025-01-29 | Nil | NA | NA
3 | MSB Activities | 2025-01-29 | 2025-02-11 | 3.6 Sprint S3 | Hari | 24328 | Activities - Admin - Fix 'Register/Continue/Submit Registration' button in Manual Registration [3.6*] | Defect Fixed | 3 | 3 | 10 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40550 | 2025-01-29 | 2025-01-29 | Done | Nil | Done | 2025-01-31 | Nil | NA | NA
4 | MSB Activities | 2025-01-29 | 2025-02-11 | 3.6 Sprint S3 | Kaliammal | 47010 | Activities - Admin - Custom Registration Report - Show Italic font for Updated Status Data for Output Format | Story Completed | 1 | 4 | 16 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40553 | 2025-01-29 | 2025-01-30 | Done | Optimize two line string opertion to one line. | Done | 2025-01-31 | Nil | 1.Contact fields are not bold, italics for the updated registration section in PDF, Excel, and HTML 2.Could not see the same header text message in Excel format [*Updates Pending Admin Approval] | Approved | Took more effort to fix bounce back.
5 | MSB Activities | 2025-01-29 | 2025-02-11 | 3.6 Sprint S3 | Allen | 47045 | Activities - SYSTEM - Performance Improvements for Enrollment Plan Selected Actions [3.7] (dev only) | Story Completed | 8 | 8 | 35
6 | MSB Activities | 2025-01-29 | 2025-02-11 | 3.6 Sprint S3 Stretch | Kaliammal | 46724 | Activities - Security Group/Kiosk/District Maintenance - Update "Description" to Item Name in SQL Tables (SYSTEM) [3.7] | Story Completed | 5 | 9 | 36 | [15 empty] | Faced challenges while converting Table column from Description to DistrictName for Tenant Table due to its dependency in the Cache
7 | MSB Activities | 2025-01-29 | 2025-02-11 | 3.6 Sprint S3 Stretch | Allen | 46725 | Activities - Custom Fields/Dynamic Reports - Update "Description" to Item Name in SQL Tables (System) [3.7] | Story Completed | 5 | 5 | 20
8 | MSB Activities | 2025-01-29 | 2025-02-11 | 3.6 Sprint S3 Stretch | Allen | 24594 | Activities - Parent - Contacts - Hide "Primary" option from the Contact Type | Defect Fixed | 1 | 1 | 1 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40694 | 2025-02-07 | 2025-02-07 | Done | Nil | Done | 2025-02-07 | Nil | NA | NA

## 3.6 Sprint 3- Defects
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments | Defect/Bounceback raised
1 | 3.6 Sprint S3 | 46343 - Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) | 46343 | Kaliammal | Bounceback/Sub-Defect | When we select all student fields but still parent and contact fields are show in the pdf and excel. | Significant | Manual | Internal | Closed/Rejected | Development | Carried from previous sprint for QA, Dev is completed | Manjunathan - Offshore QA
2 | 3.6 Sprint S3 | 46343 - Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) | 46343 | Kaliammal | Bounceback/Sub-Defect | Select individual checkbox for stock, enrollment and district for contact fields - Contacts not working. | Significant | Manual | Internal | Closed/Rejected | Development | Carried from previous sprint for QA, Dev is completed | Manjunathan - Offshore QA
3 | 3.6 Sprint S3 | 46343 - Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) | 46343 | Kaliammal | Bounceback/Sub-Defect | Contact custom fields are updated with K1 and K0 for pdf and excel format. | Significant | Manual | Internal | Closed/Rejected | Development | Carried from previous sprint for QA, Dev is completed | Manjunathan - Offshore QA
4 | 3.6 Sprint S3 | 24552 - Activities - Admin - Report - Contacts are missing in custom registration report for excel format |  | Hari | Defect | Contacts are missing in custom registration report for excel format and working as expected for pdf format. | Significant | Manual | Internal | Closed/Rejected | Existing_Issues | "PROD Issue [Carried from previous sprint for dev fix]" | Manjunathan - Offshore QA
5 | 3.6 Sprint S3 | 47010 - Activities - Admin - Custom Registration Report - Show Italic font for Updated Status Data for Output Format | 47010 | Kaliammal | Bounceback/Sub-Defect | Pending, Waitlist and approved custom registration fields are also highlighted for excel and pdf format | Significant | Manual | Internal | Closed/Rejected | Development | Bounceback | Manjunathan - Offshore QA
6 | 3.6 Sprint S3 Stretch | 24594 Activities - Parent - Contacts - Hide "Primary" option from the Contact Type | 24594 | Allen | Defect | While navigating to the parent registration contact page. I saw that the Contact Type Field has an option " Primary." When I tried to choose that option, it was selected and tried to save it. That value is not saved but the old value was only retained. That option is not needed so we can hide it from UI, and it is a visual bug. | Significant | Manual | Internal | Closed/Rejected | Existing_Issues | PROD Issue | Kanchana - Offshore PO
7 | 3.6 Sprint S3 Stretch | 24618 - Activities - Admin - Custom Report - Hide Custom Field Answer for Updated status if their previous selection was removed | 46343 |  | Defect | Currently, in the custom registration report, if we run the updated registration report, we are still showing the field value without striking out /not highlighting in red color/ not showing in italics (because those values are removed). | Significant | Manual | Internal | Open | Requirements | Carried to next sprint for Dev fix - Its not going for Release | Manjunathan - Offshore QA
8 | 3.6 Sprint S3 Stretch | 24642 Activities - Parent - Tax Report - Student with Multi-Site payments displaying EIN incorrectly |  |  | Defect | The tax report in parent is displaying EINs incorrectly if the student has payments for more than one site in the date range (see attached, notice student Connor | Significant | Manual | External | Open | Existing_Issues | PROD Issue | Jeff - Onsite QA

## 3.6 Sprint S2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Kaliammal | 46343 | Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) | Story Being Tested | 13 | 14 |  | Done | Hari | 1.When Selecting Approved and Updated status, getting server error | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40461 | 2025-01-23 | 2025-01-23 | Done | Nil | Done | 2025-01-23 | Nil | 1. Registration status: Pending, and I have updated that pending registration stock fields for parents and contacts are not yet approved in the updated registration. While running the report, the pending registration fields were updated. 2. Need space after comma for each registration status. 3. All selected - It should be blank in excel filter info page. 4.We have one scenario for updated registration status if the parent updated only the schedule and forms section, and in that scenario, if we run the report for updated status, it won't show italic font for updated status because there won't be any changes for custom fields.Question: Do we still need to run the updated registration for the above scenario, or do we need to restrict it? Please confirm. 5.Sheet mismatch based on the registration status filter chosen. 6. If there is no data for any one of the registration statuses (Approved, Pending) we have chosen Excel info - We are showing the registration status as Approved, Pending but we are not showing the sheet for no data in Excel. | Approved | Development completed, Testing In progress. Will be Carried forward to next sprint for Testing.Data fetching and lot of testing scenarios , it took more efforts.
2 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Allen | 46828 | Activities - RESEARCH - Enrollment Plan - Selected Actions/Run Bulk Actions in the Background [V2] | Story Completed | 5 | 8
3 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Hari | 24494 | Activities - Admin - Calendar allowing headers through the calendar | Defect Fixed | 2 | 2 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40320 | 2025-01-16 | 2025-01-16 | Done | Nil | Done | 2025-01-16 | Q&A - Does this actually change the functionality at all? I may be missing something, but it is already set to Position.Bottom prior to the if (rect.bottom > 400) | NA | NA
4 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Hari | 46408 | Activities - Admin - District Level View of Open Operating Days | Story Completed | 5 | 5 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40394 | 2025-01-21 | 2025-01-21 | Done | Nil | Done | 2025-01-22 | Nil | 1.Number of sites count shown wrongly. 2. Reopen Day count is not considered for sites. Approved | Approved
5 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Allen | 45709 | Activities - Admin - Show Site with Term Name in Disable Enrollment Plan Validation | Story Completed | 1 | 2 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40356 | 2025-01-16 | 2025-01-16 | Done | Nil | Done | 2025-01-16 | Nil | Approved | Approved | Offshore and Onshore QA timelog collectively increased actual hours
6 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Hari | 38370 [Bounceback] | Activities - Split Billing - Add Audit Log [Bounceback] | Story Completed | 1 | 6 |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40347 | 2025-01-16 | 2025-01-21 | Done | Nil | Done | 2025-01-22 | UI Representation: Can we adjust this to match the following formatting: Field: Split Billing - Contact Removed Subrecord: [Contact Name] Old Value: N/A New Value N/A | NA | NA | Made changes in the code logic in the way of displaying Split billing in the Audit log which increased development effort
7 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Kaliammal | 45506 | Activities - Admin - Enrollment Plan - Update "Required Forms" page with Sorting and Pagination | Story Completed | 2 | 8 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40284 | 2025-01-10 | 2025-01-13 | Done | Nil | Done | 2025-01-15 | Nil | Pagination is not working when we search for anything on the second page and clear it. | Approved | I faced some challenges maintaining data because I converted the HTML table to a data table.so it took more story point.
8 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Kaliammal | 46819 | Activities - SYSTEM - Heartland Staff/Manage Users - Update to React (POV, PR & QA) | Story Completed | 2 | 4 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40364 | 2025-01-17 | 2025-01-17 | Done | Nil | Done | 2025-01-17 | Nil | NA | NA | Offshore and Onshore QA timelog collectively increased actual hours
9 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 | Hari | 46820 | Activities - SYSTEM - Heartland Staff/Districts - Update to React (POV, PR & QA) | Story Completed | 2 | 5 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40342 | 2025-01-16 | 2025-01-21 | Done | Nil | Done | 2025-01-21 | Nil | NA | NA | Offshore and Onshore QA timelog collectively increased actual hours
10 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 Stretch | Hari | 46967 | Activities - SYSTEM - Districts/Job Requests/Data - Update to React | Story Completed | 3 | 3 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40342 | 2025-01-16 | 2025-01-21 | Done | Nil | Done | 2025-01-21 | Nil | 1.While run the Schedule Withdraw/Transfer jon it redirect to registration notification job (wrong job request) | NA
11 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 Stretch | Hari | 46555 | Activities - MSB Invoice Profile - Remove filter by Provider for GL Codes | Story Completed | 3 | 3 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40470 | 2025-01-24 | 2025-01-24 | Done | Nil | Done | 2025-01-24 | Nil | Approved | Approved
12 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 Stretch | Allen | 24529 | Activities - Admin - Operating Day - Check Out Errors | Defect Fixed | 2 | 4 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40469 | 2025-01-24 | 2025-01-24 | Done | Nil | Done | 2025-01-24 | Nil | NA | NA
13 | MSB Activities | 2025-01-15 | 2025-01-28 | 3.6 Sprint S2 Stretch | Hari | 47010 | Activities - Admin - Custom Registration Report - Show Italic font for Updated Status Data for Output Format | Product Owner - Verify | 2 | 2 |  | Done | Kaliammal | Nil | Kaliammal | Nil | [9 empty] | 1. Facing the issue while running the updated registration - Index was outside the bounds of array. 2.Contact fields are not bold, italics for the updated registration section in PDF, Excel, and HTML 3.Could not see the same header text message in Excel format [*Updates Pending Admin Approval] | Development completed & Fixed POV Comments - Carried to next sprint for PR and Testing. | `

## 3.6 Sprint 2- Defects
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.6 Sprint S2 | 24494 Activities - Admin - Calendar allowing headers through the calendar | Hari | Defect | The changes made to the calendar component is causing the table headers to show through the calendar | Minor | External | Closed | Development | zIndex changes in common scss file missed while resolving conflicts | Jeff - Onshore
2 | 3.6 Sprint S2 | 46820 - Activities - SYSTEM - Heartland Staff/Districts - Update to React (POV, PR & QA) | Hari | Bounceback | Generate advance billing sites tree filter is not working as expected when we unselect sites and coudnt able click Ok button. | Significant | Internal | Closed | Development | Common Component change(Treeselect), changes did for other story impacted Generate advance billing page | Jeff - Onshore
3 | 3.6 Sprint S2 | 46820 - Activities - SYSTEM - Heartland Staff/Districts - Update to React (POV, PR & QA) | Hari | Bounceback | Job request for queue for download payments and upload invoices are not getting refreshed automatically, need to refresh Manually. | Minor | Internal | Closed | Development | We had two versions of JobRequest Queue page, React converted one and cshtml version. There were few differences in these two versions so we informed the client and worked on implementing the differences in the separate story (46967) | Jeff - Onshore
4 | 3.6 Sprint S2 | 38370 - Activities - Split Billing - Add Audit Log | Hari | Bounceback | Delete contacts is not tracked in the audit log. | Significant | Internal | Closed | Development |  | Jeff - Onshore
5 | 3.6 Sprint S2 | 46819 Activities - SYSTEM - Heartland Staff/Manage Users - Update to React (POV, PR & QA) | Kaliammal | Bounceback | Active/Inactive - Status displaying showing wrong in UI and functionality | Significant | Internal | Closed | Development |  | Kanchana - Offshore PO
6 | 3.6 Sprint S2 | 46343 - Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) | Kaliammal | Bounceback | When we select all student fields but still parent and contact fields are show in the pdf and excel. | Significant | Internal | Inprogress | Development | Carried to Next sprint for QA, Dev is completed | Manjunathan - Offshore QA
7 | 3.6 Sprint S2 | 46343 - Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) | Kaliammal | Bounceback | select individual checkbox for stock, enrollment and district for contact fields - Contacts not working. | Significant | Internal | Inprogress | Development | Carried to Next sprint for QA, Dev is completed | Manjunathan - Offshore QA
8 | 3.6 Sprint S2 | 46343 - Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) | Kaliammal | Bounceback | Contact custom fields are updated with K1 and K0 for pdf and excel format. | Significant | Internal | Inprogress | Development | Carried to Next sprint for QA, Dev is completed | Manjunathan - Offshore QA
9 | 3.6 Sprint S2 Stretch | 24529 - Activities - Admin - Operating Day - Check Out Errors | Allen | Defect | When performing an edit, because we update the records timestamp to the second, the system is triggering the fill in username logic for students that have not had an update. Underlined contact was the only one that I updated | Significant | External | Closed | Development | PROD Issue. Client Dev | Reported by Product team
10 | 3.6 Sprint S2 Stretch | 24552 - Activities - Admin - Report - Contacts are missing in custom registration report for excel format |  | Defect | Contacts are missing in custom registration report for excel format and working as expected for pdf format. | Significant | Internal | Open | Existing_Issues | PROD Issue. Relevantz Dev [Carried to Next sprint for dev fix] | Manjunathan - Offshore QA

## 3.6 Sprint S1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Hari | 46834 | Activities - SYSTEM - Expanded Admin Date Selector Calendar Overlay (POV, PR & QA) | Story Completed | 2 | 2 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40210 | 2025-01-07 | 2025-01-08 | Done | Nil | Done | 2025-01-08 | Nil | Approved | Approved
2 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Hari | 24409 | Activities - Admin - Prepaid Billing Used Instead of Drop In (Fuzzy Logic) (Fairbanks) | Defect Fixed | 5 | 8 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40257 | 2025-01-09 | 2025-01-14 | Done | Write common logic to handle DateWithdrawn | Done | 2025-01-14 | I think this change in logic may have unintended consequences, if we are comparing two inactive enrollments we would no longer favor prepaid over dropin. I think we may want to instead consider just bumping up the score associated with active vs withdrawn to make it the most important factor. Perhaps making enrolled plans worth 5000? | NA | NA
| MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Hari | 38370 | Activities - Split Billing - Add Audit Log | Story Ready For Testing | 2 | 4 |  | Done | Kaliammal | Nil | Kaliammal | Remove calender fix | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40238 | 2025-01-08 | 2025-01-14 | Done | Nil | Done | 2025-01-14 | Nil | Approved | Approved | Moved to next sprint - For Testing Reason : PR Held by Onsite QA
4 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Kaliammal | 44087 | Activities - Admin - Update Students page to Server Side sorting | Story Completed | 1 | 3 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40233 | 2025-01-08 | 2025-01-08 | Done | Nil | Done | 2025-01-09 | Nil | NA | NA
5 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Kaliammal | 44087 Bounceback | Activities - Admin - Update Students page to Server Side sorting | Story Completed |  |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40280 | 2025-01-10
6 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Hari | 46818 | Activities - SYSTEM - Admin Home - Update to React (POV, PR & QA) | Story Completed | 2 | 4 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40198 | 2025-01-06 | 2025-01-06 | Done | Nil | Done | 2025-01-08 | Nil | NA | NA
7 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Hari | 46818 Bounce Back | Activities - SYSTEM - Admin Home - Update to React (POV, PR & QA) | Story Completed |  |  |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40279 | 2025-01-10
8 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Hari | 46832 | Activities - Admin - Term - Capture Attendance Calendar modifications in Audit Log (PR & QA) | Story Completed | 1 | 1 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40084 | 2024-12-16 | 2024-12-30 | Done | Nil | Done | 2025-01-08 | Nil | When Weekly calendar enrollment plan is set to weekly but in activity we changed to daily calendar it will throw message and wont allow to save but in audit log it capture both logs Approved | Approved
9 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 | Hari | 24452 | Activities - Admin - Term filter tree selector for dynamic report generator works incorrectly for active and inactive Terms [3.5] | Defect Fixed | 1 | 4 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40197 | 2025-01-06 | 2025-01-07 | Done | Nil | Done | 2025-01-07 | Nil | NA | NA
10 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 Stretch | Allen | 46830 | Activities - Term/Site - Update "Description" to Item Name in SQL Tables (SYSTEM) [POV, PR & QA] | Story Peer Review | 3 | 3 |  | Done | Hari | Change Description to EnrollmentPlanName in the payload of bulk edit and bulk copy | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40267 | 2025-01-09 | [8 empty] | Client Dev Manager - Hold this story. Reason: Contains DataBase Column Name Changes - Slated for 3.7 release
11 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 Stretch | Allen | 46831 | Activities - Enrollment Plan/Activity - Update "Description" to Item Name in SQL Tables (SYSTEM) [POV, PR & QA] | Story Peer Review | 3 | 3 | [16 empty] | Client Dev Manager - Hold this story. Reason: Contains DataBase Column Name Changes - Slated for 3.7 release
12 | MSB Activities | 2025-01-03 | 2025-01-14 | 3.6 Sprint S1 Stretch | Kaliammal | 45506 | Activities - Admin - Enrollment Plan - Update "Required Forms" page with Sorting and Pagination | Story Ready For Testing | 3 |  |  | Done | Kaliammal | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40284 | 2025-01-10 | 2025-01-13 | Done | Nil | Done | 2025-01-14 | Nil | Mode - M should be caps. Per AC Validation for the required form modal up - Missing. | Approved | Moved to next sprint - For Testing

## 3.6 Sprint 1- Defects
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Comments* (Mandatory) | Defect raised
1 | 3.6 Sprint S1 | 24409 - Activities - Admin - Prepaid Billing Used Instead of Drop In (Fuzzy Logic) (Fairbanks) | Hari/Allen | Defect | Prepaid Billing Used Instead of Drop In (Fuzzy Logic) (Fairbanks) | Minor | External | Closed | Existing_Issues | PROD Issue,Found in the last sprint and carry forwarded to the current sprint | Onshore QA - Jeff
2 | 3.6 Sprint S1 | 24452 - Activities - Regression - Admin - Term filter tree selector for dynamic report generator works incorrectly for active and inactive Terms. | Hari | Defect | Term filter tree selector for dynamic report generator works incorrectly for active and inactive Terms. When we select any one term from active and inactive site, it is displayed as all active terms are selected. | Significant | Internal | Closed | Development | QA,Integration and Cert env broken,Found in the last sprint and carry forwarded to the current sprint | Offshore QA Manjunathan
3 | 3.6 Sprint S1 | 46818 - Activities - SYSTEM - Admin Home - Update to React (POV, PR & QA) | Hari | BounceBack | While clicking Pending and update registration for site level, It is redirected to pending and update registration overview pages. | Significant | Internal | Closed | Development |  | Offshore QA Manjunathan
4 | 3.6 Sprint S1 | 44087 - Activities - Admin - Update Students page to Server Side sorting. | Kaliammal | BounceBack | Pagination is not working properly for purchases. | Significant | Internal | Closed | Development |  | Onshore QA - Jeff

## 3.5 Sprint S4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 Stretch | Allen | 46160 | Activities - Admin - Term - Capture Attendance Calendar modifications in Audit Log (Timeboxed) [3.6] | Story Completed | 3 | 3 |  | Hari | Kaliammal | Full Calendar toggle value not tracked on initial add | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40084 | 2024-12-16 | [6 empty] | When Weekly calendar enrollment plan is set to weekly but in activity we changed to daily calendar it will throw message and wont allow to save but in audit log it capture both logs
2 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 | Hari | 39396 | Activities - SYSTEM - Admin Home - Update to React (Dev Only) [3.6] | Story Completed | 8 | 8 |  | Hari | Kaliammal | Nil | Kaliammal | Nil
3 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 | Kaliammal | 42050 | Activities - SYSTEM - Heartland Staff/Manage Users - Update to React (Dev Only) [3.6] | Story Completed | 5 | 8 |  | Done | Hari | 1.Inactive users are being listed without Show Inactive Users selected 2.Unable to change the username and role in editPage using Role Dropdown 3.Username field is disabled in dev environment, we should disable username 4.We are displaying the user name whom we are deleting in the delete confirmation popup, Refer Setup => Users => Delete 5.We don't have Tabs in existing Staff details page, discuss with kanchana regarding this | Hari | 1.Return as JsonResult instead of IActionResult for all API 2.Two methods calling same API, make use of one and remove the another one 3.We don't need multipart/form-data and getFormData payload if we are not going to upload any files 4.Remove unused imports AuditLog and AuditLogModel and console logs line number 46 5.Remove FileUploadRef in EditStaffUser component and console logs in saveStaffUser function 6.Are we using this newly defined property SystemRole? If not we can remove this
4 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 | Hari | 42051 | Activities - SYSTEM - Heartland Staff/Districts - Update to React (Dev Only) [3.6] | Story Completed | 8 | 8 |  |  | Kaliammal | Nil | Kaliammal | Nil
5 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 | Allen | 24354 | Activities - Admin - Term Maintenance - Handle Validation Message while adding Enrollment Plan | Defect Fixed | 3 | 3 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39952 | 2024-12-04 | 2024-12-04 | Done | Nil | Done | 2024-12-04 | Nil | NA | NA
6 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 Stretch | Allen | 46579 | Activities - Enrollment Plan/Activity - Update "Description" to Item Name in SQL Tables (SYSTEM) [3.6] dev only | Story Completed | 8 | 8 |  | Done | Hari | Nil | Hari | Nil
7 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 Stretch | Hari | 46726 | Activities - SYSTEM - Expanded Admin Date Selector Calendar Overlay [3.6] | Story Completed | 2 | 2 |  | Done | Kaliammal | Nil | Kaliammal | Nil
8 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 Stretch | Allen | 24373 | Activities - Admin - Modification to Fee Item is not reflected Immediately in Grid | Defect Fixed | 2 | 2 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40046 | 2024-12-11 | 2024-12-11 | Done | Nil | Done | 2024-12-11 | Nil | NA | NA
9 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 Stretch | Allen | 46722 | Activities - Term/Site - Update "Description" to Item Name in SQL Tables (SYSTEM) [3.6] dev only | Story Completed | 5 | 5 |  | Done | [14 empty] | Peer test, POV, PR and QA - Moved to next sprint
10 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 Stretch | Kaliammal | 44087 | Activities - Admin - Update Students page to Server Side sorting [3.6] dev only | Story Completed | 3 | 3 |  | Done | [14 empty] | Peer test, POV, PR and QA - Moved to next sprint
11 | MSB Activities | 2026-05-06 | 2026-05-19 | 3.5 Sprint S4 Stretch | Hari | 38370 | Activities - Split Billing - Add Audit Log [3.6] | Story Completed | 5 | 5 |  | Done | [14 empty] | Peer test, POV, PR and QA - Moved to next sprint

## 3.5 Sprint 4- Defects
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.5 Sprint S4 | 24355 Activities - Admin - Term Maintenance - Activity Required Message showing twice | Allen | Defect | While adding an enrollment plan via term maintenance without choosing an enrollment plan and clicking save, a server error validation message appeared: Enrollment Plan Record not Found. | Minor | Internal | Closed | Existing_Issues | PROD Issue | Offshore Kanchana PO
2 | 3.5 Sprint S4 | 24354 Activities - Admin - Term Maintenance - Handle Validation Message while adding Enrollment Plan | Jeff | Defect | While adding a new activity without choosing an activity and clicking Save, the Activity required message is showing twice [Activity requiredActivity required] | Minor | Internal | Closed | Existing_Issues | PROD Issue | Offshore Kanchana PO
3 | 3.5 Sprint S4 | 45967 - Activities - Pending Registrations and Enrollments - Hide the View button when Count is "0" | Jeff | BounceBack | We are able to still click the record and open the page even though if we have 0 count. | Significant | Internal | Closed | Development | Developed by Client | Offshore QA Manjunathan
4 | 3.5 Sprint S4 | 45968 - Activities - Waitlist Registrations - Hide the View button when Count is "0" | Jeff | BounceBack | We are able to still click the record and open the page even though if we have 0 count. | Significant | Internal | Closed | Development | Developed by Client | Offshore QA Manjunathan
5 | 3.5 Sprint S4 Stretch | 24388 Activities - Regression Defect - Admin - HSS - System Summary Report - Generating report showing "Internal Server Error" | Andrew | Defect | While generating the System Summary report for PDF, Excel, and Webpage, getting the Internal Server Error. | Significant | Internal | Closed | Existing_Issues | QA,Integration and Cert env broken | Offshore Kanchana PO
6 | 3.5 Sprint S4 Stretch | 24390 Activities - Regression Defect - Admin - Styling Changes | Jeff | Defect | The styling changes made through earlier stories in this sprint are conflicting on certain screens (Operating Day - when you only have 2 Activities it leaves a bad user experience and you have to scroll to get to the kiosk section, Discount & User - status direction arrow is under the term "Status") | Significant | Internal | Closed | Development | Developed by Client | Offshore Kanchana PO
7 | 3.5 Sprint S4 Stretch | 24373 - Activities - Admin - Fee Item - Modification to Fee Item is not reflected immediately in table, need to refresh the page. | Allen | Defect | Modification status or description to Fee Item is not reflected immediately in table, need to refresh the page to get reflected. | Significant | Internal | Closed | Existing_Issues | PROD Issue | Offshore QA Manjunathan
8 | 3.5 Sprint S4 Stretch | 24409 - Activities - Admin - Prepaid Billing Used Instead of Drop In (Fuzzy Logic) (Fairbanks) |  | Defect | Prepaid Billing Used Instead of Drop In (Fuzzy Logic) (Fairbanks) | Significant | External | Open | Existing_Issues | PROD Issue | Onshore QA - Jeff
9 | 3.5 Sprint S4 Stretch | 24415 - Acitivites - Admin - Invalid Purchase Period Kind (Orchard Farm) |  | Defect | Orchard Farm is getting an Invalid Purchase Period Kind error for one of their EPs. (this was found internally through nightly error emails). | Significant | External | Open | Existing_Issues | PROD Issue | Onshore QA - Jeff
10 | 3.5 Sprint S4 Stretch | 24452 - Activities - Regression - Admin - Term filter tree selector for dynamic report generator works incorrectly for active and inactive Terms. | Hari | Defect | Term filter tree selector for dynamic report generator works incorrectly for active and inactive Terms. When we select any one term from active and inactive site, it is displayed as all active terms are selected. | Significant | Internal | Open | Development | QA,Integration and Cert env broken | Offshore QA Manjunathan

## 3.5 Sprint S3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date2 | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 3.5 Sprint S3 | Hari | 46511 | Activities - Capacity Report - Total "All Enrollment Plans" count in Excel Output Format | Story Completed | 5 | 6 | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39882 | 2024-11-27 | 2024-12-02 | Done | Nil | Done | 2024-12-02 | typo in activities parameter name | POV Approved | POV Approved | Since we are making changes in common component, Extra effort has been taken to make sure it is not broken anywhere else in the system
2 | 3.5 Sprint S3 | Kaliammal | 46302 | Activities - Attendance Report - Group By Grade (Evergreen Community Charter) | Story Completed | 5 | 8 | Done | Hari | Page break not returning report while selecting multiple site | Hari | Remove unused line | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39880 | 2024-11-27 | 2024-12-02 | Done | Change filter code from component specific to common . | Done | 2024-12-02 | Nil | 1.Found the term filter is not loading at the district and site levels | POV Approved | Attendance Report already had Page break by student option,with this story we have to introduce page break by grade which leads to new filter criteria of Multiple page break options for a report and it took some extra effort to make sure the existing page break by student functionality is not broken
3 | 3.5 Sprint S3 | Allen | 46557 | Activities - Enrollment Plan Maintenance - Limit number for Selected Actions & Config Prop | Story Completed | 8 | 8 | Done | Kaliammal | 1) Apply Bulk Registartion End Date ,Validation not working properly | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39833 | 2024-11-21 | 2024-11-21 | Done | Nil | Done | 2024-11-21 | The messaging on this error is specific to Enrollment Plans, but this is in the shared DataTable component, can we pass in a string prop that contains the name, or take some other approach to make this reusable | 1. Need to disable the Select All button (when already selected all) 2.For new district, disable select all check box 3.Validation message missing capitalize. 4.When 10 count is set in config props, when I select the enrollment plan at last page - it is selecting first 10 EP. | Please update config prop name to capitalize the P in "Plan", Please update the error messaging at the bottom so that the text color is black and use an amber triangle-exclamation icon to the right of the text (https://fontawesome.com/icons/triangle-exclamation?f=classic&s=solid),
4 | 3.5 Sprint S3 | Allen | 46577 | Activities - Admin - Update "Description" to Item Name [UI Labels Only](PR & QA) | Story Completed | 3 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39718 | 2024-11-14 | 2024-11-19 | Done | Nil | Done | 2024-11-19 | Nil | NA | NA
5 | 3.5 Sprint S3 Stretch | Hari | 46523 | Activities - Reports - Term Status Count on Term instead of Site | Story Completed | 5 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39883 | 2024-11-27 | 2024-11-28 | Done | Nil | Done | 2024-12-02 | Nil | Approved | Approved
6 | 3.5 Sprint S3 Stretch | Allen | 46590 | Activities - SYSTEM - Optimize Student Maintenance Queries | Story Completed | 5 | 5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39892 | 2024-11-28 | 2024-12-02 | Done | Nil |  |  |  | 1.Profile photo missing in table grid. 2.The first time loading nearly to 30 seconds | NA
7 | 3.5 Sprint S3 Stretch | Kaliammal | 46160 | Activities - Admin - Term - Capture Attendance Calendar modifications in Audit Log [3.6?] | Story Being Developed (POV Comments) |  |  | Done | Hari | Nil | Hari | Nil | [8 empty] | Allow Weekly and Number of weeks to schedule should not be displayed (that belongs to the weekly calendar) Expected: Allow daily and days/weeks before the calendar should be displayed. |  | Developer working on POV Comment
8 | 3.5 Sprint S3 Stretch | Hari | 46549 | Activities - Admin - Reports - Invoice Summary Report - Separate Excel logic from PDF | Story Need more Info and moved to backlog | [17 empty] | Story Need more Info and moved to backlog
9 | 3.5 Sprint S3 Stretch | Kaliammal | 24351 | Activities - Admin - Reports - Capacity Report shows Incorrect data when same enrollment plan is included for multiple term for PDF | Defect Fixed | 2 | 2 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39893 | 2024-11-29 | 2024-12-02 | Done | Nil |  |  |  | NA | NA | Added in mid of the sprint
10 | 3.5 Sprint S3 Stretch | Kaliammal | 24179 | Activities - Admin - Term - Disable the "Remove" button for Term Activities after Editing[3.6?] | Defect Fixed | 1 | 2 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39900 | 2024-12-02 | 2024-12-02 | Done | Nil | Done | 2024-12-02 | Nil | NA | NA | Pushed from Backlog defects 5.5Hrs Logged, so 1.5hrs more than initial estimate leading to final estimate as 2sp
11 | 3.5 Sprint S3 | Hari | 46557 | Activities - Enrollment Plan Maintenance - Limit number for Selected Actions & Config Prop - [Bounce Backs Handled] | Story Completed |  |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39881 | 2024-11-27 | 2024-11-28 | Done | Nil | Done | 2024-12-02 | Nil | NA | NA
12 | 3.5 Sprint S3 Stretch | Hari | 24350 | Activities - Reports - Multi-Student Data is not showing in Invoice Payment Summary for Excel | Defect Rejected

## 3.5 Sprint 3- Defects
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.5 Sprint S3 Stretch | 24287 Activities - Admin - Fix 'Day Selector Header' for Attendance Calendar | Jeff | Defect | While scrolling through the student attendance calendar the day selector header is not fixed (constant) at the student enrollment and manual registration sections. | Minor | Internal | Closed | Existing_Issues | Existing Prod issue | Offshore PO - Kanchana
2 | 3.5 Sprint 3 | 46557 - Activities - Enrollment Plan Maintenance - Limit number for Selected Actions & Config Prop | Hari | Bounceback | Multiple edit and copy is not getting reflected immediately after save message, need to refresh the page to get reflected. | Significant | Internal | Closed | Development |  | Offshore QA - Manjunathan
3 | 3.5 Sprint 3 | 46557 - Activities - Enrollment Plan Maintenance - Limit number for Selected Actions & Config Prop | Hari | Bounceback | When we select all active and inactive enrollment, if we try copy and edit inactive enrollment plans are skipped, and we are able to edit and copy only active enrollment plans. | Significant | Internal | Closed | Development |  | Offshore QA - Manjunathan
4 | 3.5 Sprint 3 Stretch | 24350-Activities - Reports - Multi-Student Data is not showing in Invoice Payment Summary for Excel | Hari | Defect | Data missing in Excel, only the first student record is available in excel when multiple students or Multiple Enrollment plans selected | Significant | Internal | Closed | Existing_Issues | Existing Prod issue - Defect Rejected | Offshore Dev - Hari
5 | 3.5 Sprint 3 Stretch | 46523 - Activities - Reports - Term Status Count on Term instead of Site. | Hari | Bounceback | When we select all active or inactive terms and remove any of the terms still shows All active terms are full selected instead of partial select. | Significant | Internal | Closed | Development |  | Offshore QA - Manjunathan
6 | 3.5 Sprint 3 Stretch | 24351 - Activities - Admin - Reports - Capacity report shows incorrect data when same enrollment plan is included for multiple term for PDF. | Kalimmal | Defect | Capacity report shows incorrect data when same enrollment plan is included for multiple term for PDF format.(Working fine for Excel.) | Significant | Internal | Closed | Development |  | Offshore QA - Manjunathan
7 | 3.5 Sprint 3 | 46302 - Activities - Attendance Report - Group By Grade (Evergreen Community Charter) | Kalimmal | Bounceback | When we are having 2 terms and same activity, enrollments, when we set "group by" Grade and "page break" by grade we are seeing wrong data, it is grouping by grade irrespective of the Terms, but works fine if we set "group by" Grade and "page break" by none. | Significant | Internal | Closed | Development |  | Offshore QA - Manjunathan

## 3.5 Sprint S2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Status | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 3.5 Sprint S2 | Hari | 46334 | Activities - Enrollment Plans - Selected Actions Bulk Edit (Seminole) [Timeboxed] | 8 | 8 | Closed | Done | Kaliammal | 1) Alignment issue 2) Checkbox issue | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39743 | 2024-11-15 | 2024-11-18 | Done | Nil | Done | 2024-11-18 | Nil | 1. Color missing for Edit icon 2. Permission for Bulk edit is still deny access for Hss users. | Approved
2 | 3.5 Sprint S2 | Kaliammal | 46032 | Activities - Capacity Report - Dropdown Tree for Activity and EP Filters (Seminole) | 5 | 8 | Closed | Done | Hari | Empty sheet for terms | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39744 | 2024-11-15 | 2024-11-18 | Done | Nil | Done | 2024-11-18 | Nil | 1.Getting syntax error : Error Value cannot be null. Parameter name: s 2. If the Activity have multiple enrollment plan with same name the selection is not single but its selecting all activity. | Approved
3 | 3.5 Sprint S2 | Allen | 46426 | Activities - Admin - Show Login ID instead of "Staff" for Operating Days [Check-In/Out] & Attendance Report | 3 | 3 | Closed | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39694 | 2024-11-13 | 2024-11-13 | Done | Nil | Done | 2024-11-13 | Nil | Scenario: When we edit a student without checking in time and have not specified any contact, that scenario still shows the staff for check-in contact instead of the user ID. | Approved
4 | 3.5 Sprint S2 | Hari | 46478 | Activities - Enrollment Plans - Selected Actions Bulk Copy (Seminole) [Timebox] | 5 | 4 | Closed | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39640 | 2024-11-07 | 2024-11-08 | Done | Nil | Done | 2024-11-11 | Nil | 1.We can remove it - Please enter valid details because already we are displaying messages for the EP text field 2.Add color code for copy icon -#593CBC shall we change to "No Bulk Update to apply" 3.Duplicate enrollment plan name validation should be - Another Enrollment Plan already exists with this name 4.If no enrollment plan in the copy screen - disable the Continue button 5.We can remove it - Please enter valid details - for the scenario, EP name reached 100 characters Is it possible for a character limit display? | Approved
5 | 3.5 Sprint S2 | Hari | 24257 | Activities - Report filter counts not showing correctly when Search criteria entered to select | 3 | 4 | Closed | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39637 | 2024-11-07 | 2024-11-08 | Done | Nil | Done | 2024-11-11 | Nil | NA | NA | Carried from last sprint stretch to Current sprint main
6 | 3.5 Sprint S2 | Allen | 46323 | Activities - HSS - Custom Export via Dynamic Report Generator (Seminole, Volusia)[PR &QA] | 3 | 3 | Closed | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39468 | 2024-10-24 | 2024-10-24 | Done | Nil | Done | 2024-10-28 | 1.Do the newly inserted reports need to be added here and to the getReportOptionDescription? 2.Typo in Command | Approved | Approved | Reason:Carried from last sprint to commit for testing [Due to unavailability for QA (onshore and offshore)]
7 | 3.5 Sprint S2 | Allen | 46336 | Activities - Reports - Component for Tree select to Show selection Counts (PR & QA) | 2 | 2 | Closed | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39502 | 2024-10-28 | 2024-11-01 | Done | Nil | Done | 2024-11-04 | Nil | Selection of the check box is not working properly for Active terms | Approved | Reason:Carried from last sprint to commit for testing [Due to unavailability for QA (onshore and offshore)]
8 | 3.5 Sprint S2 Stretch | Allen | 24286 | Activities - Admin - Reports - Invoice Payment Summary report not showing total for multi-line invoice | 1 | 1 | Closed | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39676 | 2024-11-12 | 2024-11-12 | Done | Nil | Done | 2024-11-12 | Nil | NA | NA | PROD Defect added in the stretch & mid of the sprint.
9 | 3.5 Sprint S2 Stretch | Allen | 46499 | Activities - RESEARCH - Update Admin "Description" to Item Name | 3 | 3 | Research Completed | [15 empty] | Pulled story from backlog to stretch in the mid of the sprint
10 | 3.5 Sprint S2 Stretch | Allen | 24301 | Activities - RESEARCH - Invoice summary reports, we are able to see enrollment name, Site and Address twice | 1 | 1 | Research Completed | [15 empty] | Additionally added on stretch
11 | 3.5 Sprint S2 Stretch | Hari | 46511 | Activities - Capacity Report - Total "Enrollment Plan Count" in Excel Output Format | 5 | 1 | Not Started [Carried to next sprint] | [15 empty] | Pulled story from backlog to stretch in the mid of the sprint
12 | 3.5 Sprint S2 Stretch | Kaliammal | 46302 | Activities - Attendance Report - Group By Grade (Evergreen Community Charter) | 5 | 4 | Development in progress. [Carried to next sprint]
13 | 3.5 Sprint S2 Stretch | Allen | 46557 | Activities - Enrollment Plan Maintenance - Limit number for Selected Actions | 8 | 3 | Analysis [Carried to next sprint] | [15 empty] | Additionally added in stretch on last Friday by client

## 3.5 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.5 Sprint S2 Stretch | 24286 - Activities - Admin - Reports - Invoice Payment Summary report not showing total for multi-line invoice | Allen | Defect | While performing smoke testing on the deployment of 3.4 I noticed that the Invoice Payment Summary report is not properly displaying the total payment for that invoice, it looks to be only showing the payment for one line of the invoice. This multi-line invoice shows that 3 lines was paid and that the total payment was $30 | Significant | External | Closed | Existing_Issues |  | Found By Onshore QA - Jeff
2 | 3.5 Sprint S2 Stretch | 24301 - Activities - Admin - Reports - Invoice summary reports, we are able to see enrollment name, Site and Address twice. | Allen | Defect | Invoice summary reports, we are able to see enrollment name, Site and Address twice for Excel format.(This is an existing issue in production) | Minor | Internal | Closed | Existing_Issues | We have created as a separate story | Found By Offshore QA - Manjunathan
3 | 3.5 Sprint 2 | 24257 - Activities - Report filter counts not showing correctly when Search criteria entered to select | Hari | Defect | When search criteria is entered while selecting Terms for Report filters, the counts are not displaying correctly for the Active/Inactive Terms. | Significant | Internal | Closed | Development |  | Carry Forwarded from Previous SPrint

## 3.5 Sprint S1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.5 Sprint S1 | Allen | 46323 | Activities - HSS - Custom Export via Dynamic Report Generator (Seminole, Volusia)[PR &QA] | 3 | 2 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39468 | 2024-10-24 | 2024-10-24 | Done | Nil | Done | 2024-10-28 | 1.Do the newly inserted reports need to be added here and to the getReportOptionDescription? 2.Typo in Command | Approved | Approved | Inprogress | Testing is inprogress and carried to next sprint main commit (due to unavailability for QA (onshore and offshore)
2 | 3.5 Sprint S1 | Hari | 46329 | Activities - Enrollment Plan Maintenance - Selected Actions (Seminole) | 8 | 8 | Done | Kaliammal | Nil | Kaliammal | Nil | [10 empty] | Closed | This story used to create common component for Bulk copy so we are closing this story and this pr will be merge with main story
3 | 3.5 Sprint S1 | Allen | 46336 | Activities - Reports - Component for Tree select to Show selection Counts (PR & QA) | 2 | 2 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39502 | 2024-10-28 | 2024-11-01 | Done | Nil | Done | 2024-11-04 | Nil | Selection of the check box is not working properly for Active terms | Approved | Inprogress | Testing is inprogress and carried to next sprint main commit (due to unavailability for QA (onshore and offshore)
4 | 3.5 Sprint S1 | Allen | 46355 | Activities - Enrollment Plans - Selected Actions Bulk Copy (Seminole) [Timebox] | 8 | 6 | Done | Kaliammal | Nil | Kaliammal | Nil | [8 empty] | 1. Partial Selector: We need to change the CSS. 2. Registration Start Date and End Date: The format is different. 3. Apply Bulk update clicked; it showed a success message (if I didn't give find and replace). 4. Clear bulk update controls BUTTON: Color we need to check with Kristy 5. Cancel message—we need to check—the cancel message is not proper. 6. Confirm changes page; column sorting is missing. 7. Confirm page—date format missing 8. Confirm page; remove asterisk for column 9. The validation message is not proper for the mandatory field. [Description must be less than 100 characters] 10. Copy button—color code 11. SAME EP name given; need to continue; create; after we see the message 12. Remove the date text from the copy and confirm the page 13. We can set the default date for the find and replace page like in other pages. 14. Same EP given - the message is not proper. |  | Closed | Given Internal POV comments - Inprogress. Client PO have closed this story and duplicated as a new story in next sprint commit.
5 | 3.5 Sprint S1 | Allen | 46348 | Activities - Enrollments - Sort Dates Chronologically (Albemarle) | 3 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39460 | 2024-10-24 | 2024-10-24 | Done | Nil | Done | 2024-10-24 | Nil | Approved | Approved | Closed
6 | 3.5 Sprint S1 Stretch | Kaliammal | 46032 | Activities - Capacity Report - Dropdown Tree for Activity and EP Filters (Seminole) | 8 | [17 empty] | Development Inprogress
7 | 3.5 Sprint S1 Stretch | Hari | 24257 | Activities - Report filter counts not showing correctly when Search criteria entered to select | 3 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39600 | 2024-11-05 | [9 empty] | Peer review (Additionally included defect in the mid of the sprint) and carried to next sprint commit

## 3.5 Sprint 1 - Defects
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised

## 3.4 Sprint S3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.4 Sprint S3 | Kaliammal | 46110 | Activities - Custom Registration Report - Handle Transferred/Withdrawn Students (3.4) | 3 | 2 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39256 | 2024-10-08 | 2024-10-09 | Done | Nil | Nil | 2024-10-09 | Nil | 1.Student Transferred out of this Activity on 10/4/2024 - it should be Student Transferred out of this Enrollment Plan on 10/4/2024 2.Student Transferred into this Activity on 10/4/2024 - it should be Student Transferred into this Enrollment Plan on 10/4/2024 3.Please change in PDF, Excel and HTML formats | NA | Closed
2 | 3.4 Sprint S3 | Kaliammal | 24139 | Activities - Student with scheduled transfer billed for both EPs (Charter School Associates) (dev & pr) [3.5] | 3 | 6 | Done | Hari | 1.Billing for November for student scheduled to be withdrawn before November | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39366 | 2024-10-17 | 2024-10-17 | Done | Rename the PurchaseLastDate to PurchaseEndDate | Nil | 2024-10-17 | Nil | NA | NA | Closed
3 | 3.4 Sprint S3 | Hari | 45998 | Activities - RESEARCH - HSS Custom Export (Seminole) | 5 | 5 | Done | Hari | Nil | Hari | Nil | [8 empty] | 1. School Year Student Enrollment Counts report download report is disabled even we have selected all the report filters. 2. If I selected term filters and moved to select another still the other reports able to run based on the previous report selections. |  | Closed | Client POV and PR&QA are added to next sprint with new story
4 | 3.4 Sprint S3 Stretch | Allen | 46094 | Activities - Admin - Dynamic Report Generator - Add Date Range Validation [3.5] | 3 | 8 | Done | Hari | Nil | Hari | Nil | [8 empty] | 1. Date range validation should restrict for 1 year. |  | Closed | Client POV and PR&QA are added to next sprint with new story
5 | 3.4 Sprint S3 Stretch | Kaliammal | 46122 | Activities - Reports - Component for Tree select to Show selection Counts [3.5] | 3 | 6 | [15 empty] | Closed | Client POV and PR&QA are added to next sprint with new story
6 | 3.4 Sprint S3 Stretch | Hari | 46133 | Activities - RESEARCH - Expedite Program Setup & Bulk Edits (Seminole) | 5 | 4 | [15 empty] | Closed | Research completed

## 3.4 Sprint 3 - Defects
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
Regression Sprint

## 3.4 Sprint S2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.4 Sprint S2 | Allen | 23996 | Activities - Fast Check-In - Failure when checking in ~220+ students (Charter Schools) | 3 | 2 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39050 | 2024-09-24 | 2024-09-24 | Done | Nil | Done | 2024-09-24 | Nil | NA | NA | Closed
2 | 3.4 Sprint S2 | Kaliammal | 45623 | Activities - Reports - Dropdown Tree Multi-select for Term Filter | 3 | 4 | Done | Hari | Nil | Hari | 1.Remove unused function paraments 2.Initialise boolean variable directly from the condition | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39113 | 2024-09-30 | 2024-09-30 | Done | Nil | Done | 2024-10-02 | Nil | 1.Include 's' in the text - Select Term(s) 2.Please remove the term status from the chipset to avoid confusion regarding the site-selected district. (as discussed) - Actually, we can check with Allen too - It looks good to show. Approved | Approved | Closed
3 | 3.4 Sprint S2 | Hari | 46033 | Activities - Admin - Report - Multi-select Terms for Capacity Report | 5 | 7 | Done | Kaliammal | 1) Data Mismatch pdf and excel 2)Existing Selection maintained | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39138 | 2024-09-30 | 2024-09-30 | Done | Nil | Done | 2024-10-02 | Should this say Node instead of Mode? | Approved | Approved | Closed
4 | 3.4 Sprint S2 | Hari | 46099 | Activities - Parent - Update Retrieve PIN UI | 3 | 1 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39139 | 2024-09-30 | 2024-10-01 | Done | Nil | Done | 2024-10-02 | Nil | Approved | please increase the padding below Select a Site/before list of sites (consider matching the amount of padding above Select a Site). Consider aligning the hyperlink text with the Site list. Approved | Closed
5 | 3.4 Sprint S2 | Allen | 46040 | Activities - Admin - District ACL - Restrict Central Office Role from Add/Delete Full Control District ACLs | 3 | 3 | Done | Hari | Issue while reading data from datatable | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39190 | 2024-10-02 | 2024-10-02 | Done | Nil | Done | 2024-10-02 | Can we please parameterize the userRecId in the 3 places that we use it in the SQL query | 1. Able to add and delete via Security group if the user have central office access. Approved | Approved | Closed
6 | 3.4 Sprint S2 Stretch | Kaliammal | 46110 | Activities - Custom Registration Report - Combined student records and blank custom fields - HTML/PDF | 5 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39227 | 2024-10-04 | 2024-10-04 | Done | Nil | Done | 2024-10-04 | Nil | 1. Student Transferred out of this Activity on 10/4/2024 - it should be Student Transferred out of this Enrollment Plan on 10/4/2024 2. Student Transferred into this Activity on 10/4/2024 - it should be Student Transferred into this Enrollment Plan on 10/4/2024 3. Please make changes to PDF, HTML, and Excel | Approved | Bounceback reported, Testing will be carried forward | Bounceback reported, Testing will be carried forward
7 | 3.4 Sprint S2 Stretch | Hari | 23735 | Activities - Admin - Term - Disable "Remove" button for Term Enrollment Plan after Editing | 2 | 1 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39159 | 2024-10-01 | 2024-10-01 | Done | Nil | Done | 2024-10-02 | Nil | NA | NA | Closed
8 | 3.4 Sprint S2 Stretch | Hari | 24075 | Activities - Admin - Term, Site and Enrollment dropdown Values are not getting cleared while we cancel the transfer. | 2 | 1 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39160 | 2024-10-01 | 2024-10-01 | Done | Nil | Done | 2024-10-02 | Nil | NA | NA | Closed
9 | 3.4 Sprint S2 Stretch | Hari | 24095 | Activities - Admin - Enrollment - ReEnroll being displayed as a transfer |  |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39206 | 2024-10-03 | 2024-10-04 | Done | Nil | Done | 2024-10-04 | Nil | NA | NA | In progress [Testing will be carried forward] | Additional Defect introduced during mid of the sprint
10 | 3.4 Sprint S2 Stretch | Hari | 24096 | Activities - Admin - Enrollment - ReEnroll causing the audit log not to render |  |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39206 | 2024-10-03 | 2024-10-04 | Done | Nil | Done | 2024-10-04 | Nil | NA | NA | In progress [Testing will be carried forward] | Additional Defect introduced during mid of the sprint
11 | 3.4 Sprint S2 Stretch | Kaliammal | 24135 | Activities - Admin - Capacity Report - Able to download empty report when no enrollment plan are available by Select all option . |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39225 | 2024-10-04 | 2024-10-04 | Done | Nil | Done | 2024-10-04 | Nil | NA | NA | Closed | Additional Defect introduced during mid of the sprint

## 3.4 Sprint 2 - Defects
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.4 Sprint S2 Stretch | 24095 - Activities - Admin - Enrollment - ReEnroll being displayed as a transfer | Hari | Defect | If a student is re-enrolled after being withdrawn for 24 hours, the enrollment screen displays the student was transferred from the current enrollment plan to the current enrollment plan. | Significant | External | Closed | Existing_Issues | Production issue | Reported By client
2 | 3.4 Sprint S2 Stretch | 24096 - Activities - Admin - Enrollment - ReEnroll causing the audit log not to render | Hari | Defect | If a student is re-enrolled after being withdrawn for 24 hours a new entry is made for the student in the enrollment table. When clicking on the audit log for the new entry, the audit log fails to render. | Significant | External | Closed | Existing_Issues | Production issue | Reported By client
3 | 3.4 Sprint S2 Stretch | 24097 - Activities - Admin - Research - Billing Full Week instead of partial Week Non-Calendar (Orchard) |  | Defect | If a student is re-enrolled after being withdrawn for 24 hours a new entry is made for the student in the enrollment table. If the original schedule was for 2 days a week, it looks like the re-enroll might not be honoring the original schedule day count, and is billing the full week vs 2 day pricing. | Significant | External | Closed | Existing_Issues | Production issue | Reported By client
4 | 3.4 Sprint S2 Stretch | 23735 - Activities - Admin - Term - Disable "Remove" button for Term Enrollment Plan after Editing | Hari | Defect | While editing the term enrollment plan and saving, the "Remove" button is enabled. | Minor | Internal | Closed | Existing_Issues |  | Found by Offshore QA - Kanchana
5 | 3.4 Sprint S2 Stretch | 24075 - Activities - Admin - Term, Site and Enrollment dropdown Values are not getting cleared while we cancel the transfer. | Hari | Defect | Term, Site and Enrollment dropdown Values are not getting cleared while we cancel the transfer. | Minor | Internal | Closed | Existing_Issues |  | Found by Offshore QA - Manjunathan
6 | 3.4 Sprint S2 Stretch | 24135-Activities - Admin - Capacity Report - Able to download empty report when no enrollment plan are available by Select all option . | Kaliammal | Defect | Able to download empty report when no enrollment plan are available by Select all option (Issue exist in production) | Minor | Internal | Closed | Existing_Issues | Production issue | Found by Offshore QA - Manjunathan
7 | 3.4 Sprint S2 Stretch | 46110 - [Activities - Custom Registration Report - Handle Transferred/Withdrawn Students] | Kaliammal | Bounceback | Same contacts records are duplicated multiple times in custom report. | Significant | Internal | Closed | Development |  | Found by Offshore QA - Manjunathan

## 3.4 Sprint S1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Onsite Lead Code Review Comments, if any | Client Code Review | PR Approved Date | Client Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.4 Sprint S1 | Hari | 45892 | Activities - Admin - Allow Full Control and Central Office Roles to add District ACLs | 3 | 5 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38908 | 2024-09-16 | 2024-09-16 | Allen | Nil | Andy | 2024-09-17 | Nil | Approved | Approved | Closed
2 | 3.4 Sprint S1 | Hari | 45934 | Activities - Admin - Allow Tables to be Downloaded/Exported (Server Side) | 5 | 4 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38955 | 2024-09-18 | 2024-09-19 | Allen | Nil | Andy | 2024-09-20 | Nil | 1.The file name should be PendingRegistrations_DateFormat.csv and PendingRegistrations_DateFormat.xlsx applicable for Waitlist, Updated, and View All [The first character should be Caps] 2.Could you remove the date column from the report info sheet? 3.Rename the sheet1 name to 'PendingRegistrations' (applicable for Waitlist, Updated and View all) 4.The Student Count should be left aligned in the report. 5.When the student name is enabled, we need to increase the cell size of the row. 6.Add the below information in the Report info sheet for Pending, Waitlist. - Term - Enrollment Plan - Pending Registrations - Show Student Name(s) - Enabled/Disabled 7. Design of the download breaks the border. 8.In CSV format, Student name is not displayed. 9.For View all registrations, include Term, EP details in filter info | Can we think of a way to make the Student Name stand out when we have the toggle enabled for showing the Student Name(s)? It kind of gets lost in the same cell as the parent name. Maybe adding another column to the right of the parent name? Or doing a carriage return to indent/show the student names below? | Closed
3 | 3.4 Sprint S1 | Kaliammal | 45787 | Activities - Admin - Kiosk - Auto-assign PIN for Other Contacts added (Baldwin) | 3 | 5 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38949 | 2024-09-18 | 2024-09-19 | Allen | Nil | Andy | 2024-09-19 | Nil | Approved | Approved | Closed
4 | 3.4 Sprint S1 | Allen | 45329 | Activities - Tech Debt - Download Duplicate Student ID Report | 3 | 2 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38649 | 2024-08-27 | 2024-08-27 | Allen | Nil | Andy | 2024-09-12 | 1.Can we add permission checks for HSS users only on the functions in the controller 2.Consider moving all of these to a new DBDynamicReports class/file instead of adding them to DBTenants, I think that would follow our existing pattern of having a DB class to match the table in SQL. | NA | NA | Closed
5 | 3.4 Sprint S1 | Allen | 23994 | Activities - SYSTEM - Attendance Report - Run report deactivating | 1 | 2 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38729 | 2024-09-02 | 2024-09-02 | Allen | Nil | Andy | 2024-09-12 | I don't think this gives the correct list of students, this seems to give every student in students list that isn't in the list of studentIDs in the queryParams | NA | NA | Closed | Closed (carried from last sprint for testing)
6 | 3.4 Sprint S1 Stretch | Allen | 45996 | Activities - Invoices - Include the Late Pickup Fee Day in Description | 5 | 3 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38911 | 2024-09-16 | 2024-09-16 | Allen | Nil | Andy | 2024-09-17 | Nil | Change date format from dd/mm/yyyy to mm/dd/yyyy | Approved | Closed
7 | 3.4 Sprint S1 Stretch | Kaliammal | 45994 | Activities - Dev Express Dynamic Template [QA] | 2 | 3 Sp | Done | Hari | 1.Display Labels only when fields are available | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38891 | 2024-09-13 | 2024-09-13 | Allen | Nil | Andy | 2024-09-13 | Nil | NA | NA | Closed
9 | 3.4 Sprint S1 Stretch | Allen | 23996 | Activities - Fast Check-In - Failure when checking in ~220+ students (Charter Schools) | 5
10 | 3.4 Sprint S1 Stretch | Hari | 24039 | Activities - Admin - Relationship not reflecting for "Parent" selection in Updated Registration | 1 | 1 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38972 | 2024-09-19 | 2024-09-19 | Allen | Nil | Andy | 2024-09-19 | Nil | NA | NA | Closed | [Defect found during this sprint]
11 | 3.4 Sprint S1 Stretch | Kaliammal | 45623 | Activities - Reports - Dropdown Tree Multi-select for Term Filter | 5 | 5 | Done | Hari |  | Hari |  |  |  |  | Allen |  | Andy | [5 empty] | Additional story introduced during mid of the sprint
12 | 3.4 Sprint S1 Stretch | Hari | 46033 | Activities - Admin - Report - Multi-select Terms for Capacity Report | 8 |  |  | Kaliammal | 1) Data Mismatch pdf and excel 2)Existing Selection maintained | Kaliammal | Nil | [11 empty] | Additional story introduced during mid of the sprint

## 3.4 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.4 Sprint S1 | 24039 Activities - Admin - Relationship not reflecting for "Parent" selection in Updated Registration | Hari | Defect | When editing your info details in parent admin, you select the relationship as "Parent" and update the registration. Once you back and check in admin it does not update in the updated registration for that relationship field instead, it shows the previously changed relationship. | Significant | Internal | Closed | Existing_Issues |  | Found by PO - Kanchana
2 | 3.4 Sprint S1 | 24063 - Activities - Admin - Contacts - Relationship field shows Number for value instead of Name while updating registration |  | Defect | While a parent updates a registration by adding a new contact and selecting the relationship type as "Parent". In the updated registration, the Relationship shows the number as "0" instead of Parent. Same, if the parent updated a registration by adding a new contact and selecting the relationship type as "Other". In the updated registration, the Relationship shows blank instead of the name. | Minor | Internal | Closed | Existing_Issues | Found defect in the mid of the sprint | Found by Offshore QA - Manjunathan

## 3.3 Sprint S3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.3 Sprint S3 | Kaliammal | 45116 | Activities - Reports - Custom Registration Report(QA) | 2 | 3 Sp | [5 empty] | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38679 | [9 empty] | Closed
2 | 3.3 Sprint S3 | Allen | 23905 | Activities - Admin - Attendance Report - Run report deactivating [3.4] | 2 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38729 | 2024-09-02 | Allen | 2024-09-02 | Nil | Andy |  | I don't think this gives the correct list of students, this seems to give every student in students list that isn't in the list of studentIDs in the queryParams |  |  | Inprogress | Client informed to move to next release
3 | 3.3 Sprint S3 | Kaliammal | 23906 | Activities - Parent - Gender stock field value gets empty while updating the students information | 3 | 2 Sp | Done | Hari |  | Hari |  | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38678 | 28-08-2024 | Allen | 29-08-2024 | Nil | Andy | 29-08-2024 | Nil |  |  | Closed
4 | 3.3 Sprint S3 | Hari | 23866 | Activities - Admin - Prorated Pricing is being honored for both "Drop In" and "Prepaid" method | 2 | 4 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38680 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38727 | 28-08-2024 | Allen | 28-08-2024 | Nil | Andy | 28-08-2024 | Nil |  |  | Closed
5 | 3.3 Sprint S3 | Hari | 23867 | Activities - Admin - Getting server error while check-in and check-out when prorated date is before then enrollment start date. | 1 | 1 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38680 | 28-08-2024 | Allen | 28-08-2024 | Nil | Andy | 28-08-2024 | Nil |  |  | Closed
6 | 3.3 Sprint S3 | Allen | 44143 | Activities - Invoices - Include the Late Pickup Fee Day in Description [Timebox] [3.4] | 5 | [16 empty] | Inprogress | Client informed to move to next release
7 | 3.3 Sprint S3 | Hari | 23937 | Activities - Admin - Regression - Student Registration and Custom Report - Parent and contact field values joined with comma separated for same Parent | 2 | 2 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38726 | 2024-09-02 | Allen | 2024-09-02 | Nil | Andy | 2024-09-03 | Nil | Nil | Nil | Closed
8 | 3.3 Sprint S3 | Hari | 23942 | Activities - Admin - Regression - Reports - Term filter not getting cleared while modifying Site filter by selecting all option directly | 4 | 4 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38733 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38809 | 2024-09-09 | Allen | 2024-09-09 | Nil | Andy | 2024-09-09 | Nil |  |  | Closed
9 | 3.3 Sprint S3 Stretch | Allen | 45329 | Activities - Tech Debt - Download Duplicate Student ID Report [3.4] | 2 | [16 empty] | Inprogress | Stretch Story
10 | 3.3 Sprint S3 Stretch | Kaliammal | 45806 | Activities - RESEARCH - Dev Express Dynamic Template[3.4] | 5 | 6 | [15 empty] | Closed

## 3.3 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.3 Sprint S3 | 23937 - Activities - Admin - Regression - Student Registration and Custom Report - Parent and contact field values joined with comma separated for same Parent. | Kaliammal | Defect | Student Registration and Custom Report - Parent and contact field values joined with comma separated for same Parent. | Significant | Internal | Closed | Development |  | Found by Offshore QA - Manjunathan
2 | 3.3 Sprint S3 | 23942 - Activities - Admin - Regression - Reports - Term filter not getting cleared while modifying Site filter by selecting all option directly. | Hari | Defect | Term filter not getting cleared while modifying Site filter by selecting all option directly. This issue occurs for all the reports where we have site and term filters. | Significant | Internal | Closed | Existing_Issues |  | Found by Offshore QA - Manjunathan
3 | 3.3 Sprint S3 | 23906 - Activities - Parent - Gender stock field value gets empty while updating the students information | Kaliammal | Defect | Gender stock field value gets empty while updating the students information | Significant | Internal | Closed | Existing_Issues |  | Found by Offshore QA - Manjunathan
4 | 3.3 Sprint S3 | 23866 - Activities - Admin - Prorated Pricing is being honored for both the "Drop-In" and "Prepaid" method | Hari | Defect | Prorated Pricing is being honored for both the "Drop-In" and "Prepaid" method | Significant | Internal | Closed | Existing_Issues | Carried from 3.3 S2 to regression sprint
5 | 3.3 Sprint S3 | 23867 - Activities - Admin - Getting server error while check-in and check-out when the prorated date is before the enrollment start date. | Hari | Defect | Getting server error while check-in and check-out when the prorated date is before the enrollment start date. | Significant | Internal | Closed | Existing_Issues | Carried from 3.3 S2 to regression sprint
6 | 3.3 Sprint S3 | 23905 Activities - SYSTEM - Attendance Report - Run report deactivating [3.4] | Allen | Defect | If you choose all your filters, and then change the default date or toggles the run report button greys out again. (see attached video) | Significant | External | Closed | Existing_Issues | Moved to 3.4 | Found by client

## 3.3 Sprint S2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.3 Sprint S2 | Allen | 44163 | Activities - Enrollment Plans - Convert Activities to multi-select dropdown and Validation | 2 Sp | 2 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38450 | 2024-08-16 | Andy | 2024-08-19 | Nil | Andy | 2024-08-19 | Nil | 1. AC part not addressed: Prevent Enrollment Plan creation if no Activities are created/available for a District: 2. Add a red asterisk next to Activities to show the field is required 3.If I select one activity, it shows as All selected. 4.If no activity is created it should display as none or select an activity. 5. Sort alphabetically. | POV Approved | Closed | Carried from last sprint stretch for POV, PR and Testing.
2 | 3.3 Sprint S2 | Hari | 45363 | Activities - Reports - Add the Site Name with the Term Name for the Excel Output Filter Info tab | 3 Sp | 2 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38463 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38499 | 2024-08-19 | Allen | 2024-08-19 | Nil | Andy | 2024-08-19 | Nil | POV Approved | POV Approved | Closed
3 | 3.3 Sprint S2 | Kaliammal | 45116 | Activities - Reports - Custom Registration Report | 13 Sp | 13 | Done | Hari | 1.Decrypt encrypted columns | Hari |  | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38620 | 2024-08-23 | Allen | 2024-08-23 | Nil | Andy | 2024-08-23 |  | 1. The header should be Custom Fields Report. 2. If Select All is done, it's not selected and the chipset is hidden. 3. No student enrolled for an enrollment; currently we are showing the error message "Unable to pull reports." Please check the screenshot. 4. If we enable the Report headers 1, 2, and 3 via district settings, that is not added in custom reports for PDF and HTML. 5. Also, if we set the display as last name or first name, that also does not apply to custom reports. - I am not sure how to handle this for "student name" for PDF and HTML. 6.In Excel, add include's' for Student Field(s), Parent Field(s), and Contact Field(s). 7.In Excel, if all fields are selected for student, parent, and contacts—in filter info—it shows an empty—but currently, if all stock fields, parent fields, and contact fields alone are selected, we are displayed in the info page. 8. Extra spacing there in pdf at the top—please compare the student registration report for both cases (enable district settings and disable settings). 9. If more than 1 contact is there for an enrollment plan, Excel displays only 1 contact field alone. 10. For PDF and Excel, Enrollment plan custom and district custom field answers are not displayed in the reports. | 1. Contact Type value is showing as "3" instead of "Authorized Pickup" for all outputs. Can we have that show the name of the value instead of the number associated with the value? 2. Can we show the custom fields in order of how they appear on the registration for the Excel Output Filters? It threw me off seeing First Name listed last when that's the first field. | Inprogress | QA In progress
4 | 3.3 Sprint S2 [Stretch] | Hari | 23764 | Activities - Parent - Footer - Next Navigation Bar Hide's the Required Field Message | 3 Sp | 1 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38500 | 2024-08-20 | Allen | 2024-08-20 | Nil | Andy | 2024-08-20 | Nil | NA | NA | Closed
5 | 3.3 Sprint S2 [Stretch] | Hari | 23765 | Activities - Admin - Time Format - AM/PM showing twice in System | 3 Sp | 2 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38502 | 2024-08-20 | Allen | 2024-08-20 | Nil | Andy | 2024-08-20 | Nil | NA | NA | Closed
6 | 3.3 Sprint S2 | Allen | 45329 | Activities - Tech Debt - Download Duplicate Student ID Report | 3 Sp | 5 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38649 | 2024-08-26 | Allen | 2024-08-26 |  |  |  |  | 1. While downloading the report it throws server error -Exception Type: System.ArgumentException | NA | Closed | Moved to next sprint 3.3 S3 (regression sprint)
7 | 3.3 Sprint S2 [Stretch] | Allen | 44143 | Activities - Invoices - Include the Late Pickup Fee Day in Description[3.4] | 5 Sp | 1 Sp | [15 empty] | Closed | Moved to next sprint 3.3 S3 (regression sprint)

## 3.3 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.3 Sprint S2 [Stretch] | 23765 Activities - Admin - Time Format - AM/PM showing twice in System | Hari | Defect | If we include "ss" seconds in the time format in district settings like h:mm:ss tt it shows the AM/PM twice in the system. We include in the Date/Time Format also facing the same issue. | Minor | Internal | Closed | Existing_Issues |  | Found by Kanchana - PO
2 | 3.3 Sprint S2 [Stretch] | 23764 Activities - Parent - Footer - Next Navigation Bar Hide's the Required Field Message | Hari | Defect | In the Parent registration screen, for the tab Student Info, Your Info, and Contacts pages if any type of (stocks, district custom, and enrollment plan custom) fields are required, the validation message of the last field is hidden due to the footer next navigation bar is static. Specifically when there are multiple custom fields taking up the entire page. Note: The Fix should also be for Responsive design | Significant | Internal | Closed | Existing_Issues |  | Found by Kanchana - PO
3 | 3.3 Sprint S2 [Stretch] | 23845 Activities - Admin - Sites - Getting Server Error while viewing my Site | Andy | Defect | When I try to view my site (from Setup - Sites - View), I see a server error in QA and DEV. | Major | Internal | Closed | Existing_Issues |  | Found by Kanchana - PO
4 | 3.3 Sprint S2 [Stretch] | Activities - Admin - Enrollment Plan Fee ID and Fee Name Validation | Andy | Defect | Currently when saving an Enrollment Plan when a site is selected, we are showing a validation message forcing the user to input a Fee Name and Fee ID for the enrollment plan if the Fee ID and Fee Name aren't set at the Site level, even if the Fee ID and Fee Name are set at the district level. | Significant | Internal | Closed | Existing_Issues |  | Found by Kanchana - PO
5 | 3.3 Sprint S2 | 45363 - Activities - Reports - Add the Site Name with the Term Name for the Excel Output Filter Info tab. | Hari | BounceBack | Site Name is not appended with Term, If we are having single Term, But works if are having multiple Terms. | Significant | Internal | Closed | Development |  | Found by Manjunathan - QA
6 | 3.3 Sprint S2 | 45116 - Activities - Reports - Custom Registration Report. | Hari | BounceBack | When we modify the Site and Term filters, Select all checkbox for student, parent and contact field are not cleared. | Significant | Internal | Closed | Development |  | Found by Manjunathan - QA
7 | 3.3 Sprint S2 [Stretch] | 23866 - Activities - Admin - Prorated Pricing is being honored for both the "Drop-In" and "Prepaid" method | Hari | Defect | Prorated Pricing is being honored for both the "Drop-In" and "Prepaid" method | Significant | Internal | Open | Existing_Issues | Moved to 3.3 S3 regression sprint | Found by Manjunathan - QA
8 | 3.3 Sprint S2 [Stretch] | 23867 - Activities - Admin - Getting server error while check-in and check-out when the prorated date is before the enrollment start date. | Hari | Defect | Getting server error while check-in and check-out when the prorated date is before the enrollment start date. | Significant | Internal | Open | Existing_Issues | Moved to 3.3 S3 regression sprint | Found by Manjunathan - QA

## 3.3 Sprint S1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.3 Sprint S1 | Hari | 45509 | Activities - Reports - Dropdown Tree Multi-select (Dev) | 5 | 4.5 Sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38275 | 2024-08-08 | Allen | 2024-08-08 | Nil | Andy | 2024-08-12 | Nil | 1.In Search bar the text Search 's' should be caps. 2.Search text is not clear if the selection option is removed. 3.Sequential order selection clear is missing. 4.Need scroll bar if more selections made. 5. | 1. Have a clear separation of Active Sites vs. Inactive Sites in the Term dropdown, 2. Active Sites and Active Terms should be expanded by default when the user clicks the Terms filter, 3. If a Site is selected (site-level view of a report), we should not make the user expand the site in the Term dropdown, we should just show the Active and Inactive Terms sections and expand the active terms section by default. | Closed
2 | 3.3 Sprint S1 | Kaliammal | 45149 | Activities - Retainer Fees - Allow No Cost | 5 | 7.5 Sp | Done | Hari | 1.Audit log not tracking No cost changes 2.Unable to toggle No cost switch | Hari | 1.Write new script upgrade function for any new/upgrade script in UpgradeDatabase.cs | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38276 | 2024-08-08 | Allen | 2024-08-08 | Nil | Andy | 2024-08-08 | Nil | Approved | Approved | Closed
3 | 3.3 Sprint S1[Stretch] |  | 45116 [Stretch] | Activities - Reports - Custom Registration Report | 13 | [16 empty] | Inprogress
4 | 3.3 Sprint S1 | Hari | 45370 | Activities - Tech Debt - Update Dev Express (QA) | 1 Sp | 2 Sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37928 | 2024-07-18 | Allen | 2024-07-30 | Nil | Andy | 2024-07-30 | Nil | NA | NA | Closed | Testing Stories from last sprint. Waited upto regression completes
5 | 3.3 Sprint S1 | Allen | 45373 | Activities - SYSTEM - Student Data Migration to include Tenant/Client/District ID (QA) | 5 Sp | 3.5 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37948 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37947 | 2024-07-19 | Allen | 2024-07-31 | Nil | Andy | 2024-07-31 | Nil | NA | NA | Closed | Testing Stories from last sprint. Waited upto regression completes
5 | 3.3 Sprint S1 | Hari | 45374 | Activities - Admin - Reports - Add 'Grade' as Group By in Student Roster Report (QA) | 3 Sp | 5 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38072 | 2024-07-19 | Allen | 2024-07-31 | Use SelectEnum component instead of new SelectGroupBy Component | Andy | 2024-08-05 | Nil |  |  | Closed | Testing Stories from last sprint. Waited upto regression completes
6 | 3.3 Sprint S1[Stretch] | Hari | 45211 | Activities - Enrollment Plans - Status Dropdown in Table & Change Order of EP Fields [QA] | 3 Sp | 2 Sp | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38170 | 2024-08-02 | Allen | 2024-08-05 | Nil | Andy | 2024-08-05 | Nil | POV Approved | POV Approved | Closed | Testing Stories from last sprint. Waited upto regression completes
7 | 3.3 Sprint S1[Stretch] | Kaliammal | 45391 | Activities - Admin - Registrations - Term drop-down box filtering[QA] | 2 Sp | 2 Sp | Done | Hari | Nil | Hari | Refactor Props to make it common component | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38102 | 2024-07-30 | Allen | 2024-07-30 | Nil | Andy | 2024-08-02 | Nil |  |  | Closed | Testing Stories from last sprint. Waited upto regression completes

## 3.3 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.3 Sprint S1 | 23737 Activities - Admin - Fee Item - Proper Validation message for Registration Fee without Flat Rate | Jeff | Defect | When creating a Registration Fee without enabling the Flat Rate toggle it throws an error message as "Oops! Please choose Flat Rate or Hourly Rate for this fee" Note: For registration fee type we don't have an Hourly rate but it displays the error message "choose Flat Rate or Hourly Rate for this fee" | Minor | Internal | Closed | Existing_Issues |  | Found by Kanchana - PO
2 | 3.3 Sprint S1 | 23734 Activities - Admin - Fee Item - Validation for Amount for Late Payment Fee | Jeff | Defect | When creating a Late Payment Fee without entering the Late Payment Flat Rate it's getting saved and on the Details page, it displays as blank. There is no validation for "Late Payment Flat Rate". Try to fix the field name for Late Fee Amount on the details screen to "Late Payment Flat Rate". | Minor | Internal | Closed | Existing_Issues |  | Found by Kanchana - PO

## 3.2 Sprint S3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.2 Sprint S3 | Kaliammal | 23662 | Activities - Editing Single Special Date shows Date Range [3.2] | 1 Sp | 1 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37870 | 2024-07-16 | Allen | 2024-07-16 | Nil | Andrew | 2024-07-16 | Nil | NA | NA | Closed
2 | 3.2 Sprint S3 | Hari | 23536 | Activities - Admin - Week appearing when no days are available (another schedule visual bug) | 3 Sp | 3 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37895 | 2024-07-17 | Allen | 2024-07-17 | Nil | Andrew | 2024-07-17 | Nil |  |  | Closed
3 | 3.2 Sprint S3 | Allen | 45330 | Activities - SYSTEM - Student Data Migration to include District ID (Timeboxed) [3.3] | 3 Sp | 1.5 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37947 | 2024-07-19 | Allen | [7 empty] | Closed | Development completed. Hold the PR until regression completes.
4 | 3.2 Sprint S3 | Hari | 45231 | Activities - Tech Debt - Update Dev Express (Timeboxed) [3.3] | 3 Sp | 1 Sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37928 | 2024-07-18 | Allen | [5 empty] | NA | NA | Closed | Development completed. Hold the PR until regression completes.
5 | 3.2 Sprint S3 [Stretch] | Kaliammal | 44397 [Stretch] | Activities - SYSTEM - Large Scale Testing Improvements | 3 Sp | 6 Sp | Done | Hari | When no site selected, getting error | Hari | When no site selected, read siteId from Registration Model | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37982 | 2024-07-23 | Allen | [5 empty] | NA | NA | Closed
6 | 3.2 Sprint S3 [Stretch] | Allen | 45371 [Stretch] | Activities - SYSTEM - Include District ID while adding/changing Students (Timeboxed) [3.3] | 5 Sp | 2 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37948 | 2024-07-19 | Allen | [5 empty] | 1. Faced server error at district level while viewing the students in the Student Maintenance Section 2. Facing the severe error "Property set method not found" showing while checking in an activity in operating days. |  | Closed | Development completed. Hold the PR until regression completes.
7 | 3.2 Sprint S3 [Stretch] | Hari | 45299 | Activities - Admin - Reports - Add 'Grade' as Group By in Student Roster Report (Timeboxed) [3.3] | 8 Sp | 4 Sp | Done | Kaliammal | object must be of type string | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38072 | 2024-07-29 | Allen |  | Use SelectEnum component instead of SelectGroupBy |  |  |  | 1.In Excel filter info, for the Page Break column - It is showing as Disbled instead of "Disabled" 2.Roster report, for Group By =None option - Non-scheduled students are showing in the scheduled section instead of the "Non scheduled " sections. 3.Roster report, for Group By =Grade option- Non-scheduled students are showing in the scheduled section instead of the "Non scheduled " sections. 4.Issues 2 and 3 are happening for PDF, Excel, and HTML. 5. Scheduled and Non Scheduled section are not sorting for excel format for Group by None and Grade |  | Closed | Development,POV completed. Hold the PR until regression completes.
8 | 3.2 Sprint S3 | Hari | 23695 | Activities - Regression - Admin - Reports - Enrollment custom fields are not displayed in student registration report. | 3 Sp | 3 Sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38037 | 2024-07-24 | Allen | 2024-07-24 | Nil | Andrew | 2024-07-24 | Nil | NA | NA | Closed | Regression defect - Testing completed.
9 | 3.2 Sprint S3 [Stretch] | Hari | 45211 | Activities - Enrollment Plans - Status Dropdown in Table & Change Order of EP Fields [3.3] | 8 Sp | 4 Sp | Done | [15 empty] | Develpment Completed. POV, PR pending. Hold until regression completes.
10 | 3.2 Sprint S3 [Stretch] | Kaliammal | 45391 | Activities - Admin - Registrations - Term drop-down box filtering [3.3] | 3 Sp | 2 Sp | Done | Hari |  | Hari | Refactor Props to make it common component | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/38102 | 2024-07-30 | Allen | 2024-07-30 |  |  |  |  | POV Approved | POV Approved |  | Development,POV completed. Hold the PR until regression completes.

## 3.2 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.2 Sprint S3 | 23695 - Activities - Regression - Admin - Reports - Enrolment custom fields are not displayed in student registration report. | Hari | Defect | Enrolment Custom fields are not displayed in the student registration report for all the formats. | Significant | Internal | Closed | Development |  | Found by Manjunathan - Offshore QA
2 | 3.2 Sprint S3 | 23712 - Activities - Admin - Regression Defect - Object reference error when an EP does not contain the activity | Andrew | Defect | When running the Roster report, if you manually choose an EP that has the selected activity and an EP that does not, we get the below error. | Significant | External | Closed | Development |  | Found by Jeff - Onshore QA

## 3.2 Sprint S2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.2 Sprint S2 | Hari | 44766 [Testing] | Activities - Student Maintenance - Convert Administrative Notes to Table | 2 Sp | 2.5 sp | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Carried from Last sprint for Testing
2 | 3.2 Sprint S2 | Allen | 45114 [Bouncebacks] | Activities - Admin - Per Child Pricing Improvement : Bounceback on Advance Billing | 3 Sp | 7 sp | Done | Hari | No | Allen | No | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37675 | 2024-07-08 | Allen | 2024-07-08 | Nil | Andrew | 2024-07-08 | Nil | NA | NA | Closed | Carried from Last sprint for Testing
3 | 3.2 Sprint S2 | Allen | 45203 | Activities - Admin - Multi select for the Terms filter for the Student Registration Report | 5 Sp | 7 Sp | Done | Hari | No | Allen | No | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37813 | 2024-07-11 | Allen | 2024-07-11 | Nil | Andrew | 2024-07-11 | Nil | 1.For district level and site level: In the Term Filter dropdown - Include the Site name after the Term Name - Missing 2.PDF, HTML, and Excel - Sorting is not working for district and site-level 3.The report output name changed and should be StudentRegistration_Dateformat for PDF, Excel, and HTML. Currently, it's showing as ApprovedRegistration_Dateformat 4.For Excel output in the filter info sheet needs space after the comma for Site, Term filters ------------------------------------------------------------------------------- POV comments fixed - Approved. | Approved | Closed
4 | 3.2 Sprint S2 | Hari | 45117 | Activities - Student Maintenance - Operating Day Alerts | 8 Sp | 7 Sp | Done | Kaliammal | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37810 | 2024-07-11 | Allen | 2024-07-11 | Nil | Andrew | 2024-07-12 | Nil | 1. The scroll bar is missing for fast mode if more than two students have the administrative notes with more characters. 2. Due to scroll bar the design of the page breaks for family mode if more than two students have the administrative notes with more characters. 3. Non schedules students try to check in and out for family and fast mode - Modal pop up missing. ------------------------------------------------------------------------------- POV comments fixed - Approved. | Approved | Closed
5 | 3.2 Sprint S2 [Stretch] | Kaliammal | 44444 [Stretch] | Activities - Terms - Show Activity Date Range in Special Dates Modal and Validate | 8 Sp | 9 Sp | Done | Hari | 1.Getting error when selecting valid date and with no existing special dates | Hari | 1.Combine multiple setstates 2.Update the state values after validation | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37835 | 2024-07-12 | Allen | 2024-07-12 | Nil | Andrew | 2024-07-12 | Nil | 1. Date validation is showing (without entering date click ok ) and add any date before activity date - It is showing both validation message; 2.Start date is required message is missing if the date field is blank. 3.There is an overlapping of date validation message with special date. 4.Edit scenario for date validation is not working properly. 5. Accepting the future date of the activity in the end date column. 6.Special Dates end date being saved when toggled from Date Range to Single, causing the error message for outside activity to persist and stopping the OK button from working. 7.If you set the end date outside of the activity date range, then change the start date, the validation disappears and your able to save ------------------------------------------------------------------------------ POV comments fixed - Approved. | Approved | Closed

## 3.2 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.2 Sprint S2 | 23622 Activities - Admin - Reports - Deselection of Multi-Site filters is not working | Allen | Defect | We are unable to deselect Site Filter if we are selecting more than 3 sites. This issue occurs for all the reports. | Minor | Internal | Closed | Existing_Issues |  | Found by Manjunathan - Offshore QA
2 | 3.2 Sprint S2 | 45114 - Activities - Admin - Per Child Pricing Improvement. | Hari | Bounceback | 1.Multiple child index 1 purchases. 2.index count and its pricing every student the same discounted price | Significant | External | Closed | Development |  | Found by Jeff - Onshore QA
3 | 3.2 Sprint S2 | 44444 - Activities - Terms - Show Activity Date Range in Special Dates Modal and Validate. | Kalimmal | Bounceback | 1. Special Dates end date being saved when toggled from Date Range to Single, causing the error message for outside activity to persist and stopping the OK button from working. 2. If you set the end date outside of the activity date range, then change the start date, the validation disappears and your able to save | Significant | Internal | Closed | Development |  | Found by Kanchana - PO
4 | 3.2 Sprint S2 | 44444 - Activities - Terms - Show Activity Date Range in Special Dates Modal and Validate. | Kalimmal | Bounceback | Single date given and set Ok, while editing the record and opening we are able to see same date in start date and end date in the data range. | Significant | Internal | Open | Development |  | Found by Manjunathan - Offshore QA

## 3.2 Sprint S1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.2 Sprint 1 | Hari | 44764 | Attendance report - Total attending | 3 sp | 3 sp | done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37547 | 2024-06-21 | Allen | 2024-06-21 | None | Brian | 2024-06-24 | None | None | None | Closed
1.b |  | Hari | 44764 - Bounceback | Attendance Report BB |  |  | done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37569 | 2024-06-24 | Allen | 2024-06-24 | None | Andrew | 2024-06-24 | None
2 | 3.2 Sprint 1 | Hari | 44806 | Activities - Admin - Student Maintenance - Schedule Withdraw & Transfer [V2] | 8 Sp | 6 Sp | Done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37610 | 2024-06-26 | Allen | 2024-06-26 | None | Andrew | 2024-06-26 | None | 1. Geting server error at the time of scheduling withdraw and transfer | Approved | Closed
3 | 3.2 Sprint 1 | Kaliammal | 43773 | Activities - Admin - Record "Re-enrolled" status for withdrawal/Transfers in Student Enrollment/Maintenance Audit Log | 3 Sp | 8 Sp | done | Hari | None | Hari | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37612 | 2024-06-26 | Allen | 2024-06-26 | None | Andrew | 2024-06-26 | None | NA | Approved | Closed
3.b |  |  | 43773 | Re-Enrolled status bounce back fix |  |  | done | Hari | None | Hari | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37648 | 2024-07-01 | Allen | 2024-07-01 | None | Andrew | 2024-07-01
4 | 3.2 Sprint 1 | Allen | 45114 | Activities - Admin - Per Child Pricing Improvement | 8 Sp | 10 Sp | done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37609 | 2024-06-26 | Allen | 2024-06-26 | None | Andrew | 2024-06-26 | None | NA | Approved | Inprogress | BB found - PR raised. Moved to next sprint
5 | 3.2 Sprint 1 | Hari | 44766 | Activities - Student Maintenance - Convert Administrative Notes to Table | 8 Sp | 5 Sp | done | Allen | None | Allen |  | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37636 | 2024-06-28 | Allen | 2024-07-01 | None | Andrew | 2024-07-02 | Should this be Boolean instead of Byte? | 1.Required field Validation - Client-side server validation message at the time of Save 2.Edit an existing operating day note - The visibility column is showing as "Administrative Notes " instead of Operating Days. 3.After deleting the operating days and Administrative notes try to Add a note, and the value gets retained. 4.Delete Pop-up header should be " Delete Administrative Notes " 5.After deleting both notes and trying to add a new note with inactive status - visibility shows wrong in the notes screen 6.District level - Student Notes - saving a note with inactive status shows an error | Approved | Inprogress | Moved to nedxt sprint for testing

## 3.2 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.2 Sprint S1 | 44764 - Activities - Attendance Report - Total Attending. | Hari | Bounceback | No totals for PDF or HTML | Significant | External | Closed | Development |  | Found by Jeff - Onshore QA
2 | 3.2 Sprint S1 | 43773 - Activities - Admin - Record "Re-enrolled" status for withdrawal/Transfers in Student Enrollment/Maintenance Audit Log. | Kalimmal | Bounceback | 1. Audit log data getting overwritten. 2. when we transfer and re-enrol we are able to see audit log data properly. But when we are withdraw the same employee, we are not able to see and track in the audit log for student and enrolment and previous value getting lost in Student Maintenance. 3.when we re -enrol the student that is "withdraw" old value is showing ad "transferred" instead of withdraw in Student enrolment and in student Maintenance. | Minor | Internal | Closed | Development |  | Found by Manjunathan - Offshore QA
3 | 3.2 Sprint S1 | 45114 Activities - Admin - Per Child Pricing Improvement | Allen | Bounceback | Multiple child index 1 purchases | Significant | External | Inprogress | Development |  | Found by Jeff - Onshore QA

## 3.1 Sprint S3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.1 Sprint 3 | Hari | 23401 [Testing Story] | Activities - Admin Registration - Pages (Pending/Waitlist/Enrollments) not showing week - Weekly Calendar - Visual Bug (Yukon) | 2 sp | 2 sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37348 | 2024-06-06 | Allen | 2024-06-06 | Nil | Andy | 2024-06-06 | None |  |  | Closed
1.b |  |  | 23401 [DEFECT- Bounceback] | 23401-Admin & Parent Registration special days for whole week |  |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37385 | 2024-06-10 | Allen | 2024-06-10 | Nil | Andy | 2024-06-10 | None | NA | NA
2 | 3.1 Sprint 3 | Allen | 23427 [Testing Story] | Activities - Parent Registration - Pages (Pending/Waitlist/Enrollments) showing week - Weekly Calendar - Visual Bug | 5 sp | 5 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37355 | 2024-06-06 | Allen | 2024-06-06 | Nil | Andy | 2024-06-06 | None |  |  | Closed
2.b |  |  | 23401 [DEFECT- Bounceback] | 23427]-Parent Registration - visual bug for service available days |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37411 | 2024-06-11 | Allen | 2024-06-11 | Nil | Andy | 2024-06-11 | 1. missing semicolon | NA | NA
3 | 3.1 Sprint 3 | Allen | 44827 [Testing Story] | Activities - Admin - Student Enrollments - Scheduled Changes Audit Log [V1] | 3 sp | 3 sp | [15 empty] | Closed
4 | 3.1 Sprint 3 | Hari | 44765 [Testing Story] | Activities - Admin - Student Enrollments - Scheduled Changes Table [V1] | 3 sp | 3 sp | [15 empty] | Closed
4.b |  |  | 44765 [Bounceback] | 44765]-Scheduled Transfer and withdraw schedule date validation |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37353 | 2024-06-06 | Allen | 2024-06-06 | Nil | Andy | 2024-06-06 | None | NA | NA | Closed
5 | 3.1 Sprint 3 | Hari | 23500 | Activities - Scheduled Transfer/Withdraw Time Zone Issue [3.1] | 3 sp | 3 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37392 | 2024-06-10 | Allen | 2024-06-10 | Nil | Andy | 2024-06-10 | None | NA | NA | Closed
6 | 3.1 Sprint 3 [Stretch] | Hari | 44764 [Stretch] | Activities - Attendance Report - Total Attending [3.2] | 8 sp | 8 sp | [13 empty] | None | Please consider adding a line between the filters section and date range section for HTML and PDF. | Closed | Development and Internal/Client POV are completed. Due to regression sprint, PR moved to next sprint.
7 | 3.1 Sprint 3 [Stretch] | Allen | 44971 [Stretch] | Activities - RESEARCH - Per Child Pricing Improvement | 5 sp | 5 sp | [15 empty] | Closed | Research story completed

## 3.1 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.1Sprint S3 | 23401 - Activities - Admin Registration - Pages (Pending/Waitlist/Enrollments) not showing week - Weekly Calendar - Visual Bug (Yukon). | Hari | Defect | Schedule Change Date are not correctly displayed (Pending/waitinglist/Enrolments), While Admin Registration | High | Internal | Closed | Development |  | Found by Manjunathan- Offshore QA
2 | 3.1Sprint S3 | 23427 Activities - Parent Registration - Pages (Pending/Waitlist/Enrollments) showing week - Weekly Calendar - Visual Bug (Yukon) | Hari | Defect | Schedule Date changes shows incorrect date changes in Weeks attending schedule changes. While Parent Registration. | High | Internal | Closed | Development |  | Found by Manjunathan- Offshore QA

## 3.1 Sprint S2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.1 Sprint S2 | Hari | 44691 | Activities - Reports - District Level Attendance Report | 5 Sp | 7 Sp | Done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36993 | 2024-05-16 | Allen | 2024-05-17 | Nil | Brian | 2024-05-21 | Nil |  | Approved | Closed
1.a |  | Hari | 44691[Bouncebacks] | Attendance report filter bounceback fix |  |  | Done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37085 | 2024-05-22 | Allen | 2024-05-22 | Nil | Andy | 2024-06-03 | Nil
2 | 3.1 Sprint S2 | Hari | 44765 | Activities - Admin - Student Enrollments - Scheduled Changes Table [V1] | 8 sp | 13 Sp | Done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37212 | 2024-05-30 | Allen | 2024-05-30 | Nil | Andy | 2024-05-31 | 1.We check client side to see if the date matches todays date, to know if we should be scheduling the transfer or performing it immediately, should we do a similar check server side? If the date matches we could instead perform the standard transfer immediately? Or perhaps just validation to ensure the date selected is valid. | NA | Approved | Closed | Testing Phase [Carried to next sprint]
2.a |  |  | 44765 [Bouncebacks] | Scheduled Transfer Withdraw - Bounceback fix |  |  | Done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37252 | 2024-06-03 | Allen | 2024-06-03 | Nil | Andy | 2024-06-03 | Nil
3 | 3.1 Sprint S2 | Allen | 44827 | Activities - Admin - Student Enrollments - Scheduled Changes Audit Log [V1] | 5 Sp | 8 Sp | Done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37235 | 2024-05-31 | Allen | 2024-05-31 | Nil | Andy | 2024-05-31 | Nil | NA | Approved | Closed | Testing Phase [Carried to next sprint]
3.a |  |  | 44827 [Bouncebacks] | Scheduled transfer and withdraw - Audit log bounce back fix |  |  | Done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37278 | 2024-06-04 | Allen | 2024-06-04 | Nil | Andy | 2024-06-04 | Nil
4 | 3.1 Sprint S2 | Hari | 23401 | Activities - Admin Registration - Pages (Pending/Waitlist/Enrollments) not showing week - Weekly Calendar - Visual Bug (Yukon) | 5 Sp | 4 Sp | Done | Allen | None | Allen | None | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/37167 | 2024-06-04 | Allen | 2024-06-04 | Nil | Andy | 2024-06-04 | Nil | NA | NA | Closed | Testing Phase [Carried to next sprint]
5 | 3.1 Sprint S2 | Hari | 44764 [Stretch] | Activities - Attendance Report - Total Attending | 8 sp | [17 empty] | Stretch story carried to next sprint

## 3.1 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.1Sprint S2 | 44691 Activities - Reports - District Level Attendance Report | Hari | Bounceback | 1.Activity and Student filter is not getting clear when we are unselecting the term filter. 2.Facing Server error while have multiple Site, Term and enabled page break on student option when running as excel. | Minor | Internal | Closed | Development |  | Found by Manjunathan- Offshore QA
2 | 3.1Sprint S2 | 23401 Activities - Admin Registration - Pages (Pending/Waitlist/Enrollments) not showing week - Weekly Calendar - Visual Bug (Yukon) | Hari | Defect | Schedule Changes not displaying Week Days properly: | Significant | Internal | Open | Development |  | Found by Manjunathan- Offshore QA
3 | 3.1Sprint S2 | 44765 - Activities - Admin - Student Enrollments - Scheduled Changes Table [V1] | Hari | Bounceback | 1.Random 0 is displayed on the enrollment screen grid or table, if we are not have grid record. 2. manual execution button does not line up completely with the other buttons (down just a smidge) 3. While editing record, we are able to add past date, Need to restrict past date. 4. While job gets Failed, while edting record and updating the record status is not getting changed from failed to pending. | Significant | External | Closed | Development |  | Found by Jeff - Offshore QA
4 | 3.1Sprint S2 | 44827 - Activities - Admin - Student Enrollments - Scheduled Changes Audit Log [V1]. | Hari | Bounceback | if a student has been transferred/withdrawn, reenrolled, transferred/withdrawn (so more than 1 entry in the schedule table) the audit log in the enrollment errors on load (to be honest Im not sure how often we will see that, a kid withdrawing/transferring and then reenrolling, I mean it doesnt stop any functionality just the audit log gets mad and blows up for that enrollment), but everything else functions | Significant | External | Closed | Development |  | Found by Jeff - Offshore QA

## 3.1 Sprint S1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.1 Sprint S1 | Hari | 44651 | Activities - Admin - Student Enrollments - Schedule Withdraw & Transfer [V1] (Timeboxed) | 8 Sp | 6.5 Sp | [15 empty] | Closed | Note: This story has sub-stories to complete. Currently in this sprint, as per commit V1, development has been completed. Once other sub-storylines are completed, we will raise PR.
2 | 3.1 Sprint S1 | Allen | 44691 | Activities - Reports - District Level Attendance Report | 13 Sp | 8.5 Sp | Done | Hari | Nil | Nil | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36993 | 2024-05-16 | Allen | 2024-05-16 | Nil | Brian | 2024-05-21 | Nil | 1.Include the Site Name after the Term Name ie: Term Name - Site Name - Missing in term drop down filter 2.Filter sequential order missing and RUN Report is enabled if (Term filter is unselected) 3.Output format for pdf, excel and Html - Header portion showing as , , 4.Change the report output name like AttendanceReport_5_14_2024.pdf and AttendanceReport_5_14_2024.xlsx | It was taking a really long time to load minimal data for a 5 month date range (should be a single page of students for a single day within that range). I can't rule out user error or something unique to the dev environment where I was testing this, so I'm moving it forward and I'll continue to test on my side as well. | Inprogress | Testing carried to next sprint due to unavailability of onshore team to approve PR
3 | 3.1 Sprint S1 | Allen | 44501 | Activities - Admin - New Stock User Roles [QA - Testing ] | 8 Sp | 4 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36843 | 2024-05-13 | Allen | 2024-05-13 | Nil | Andy | 2024-05-13 | - I think I missed this in a past PR, but AccessLevel is mispelled on the Permission class - This will prevent the link from being added to the menu when we aren't in debug mode, but can we add similar checks to the feature itself to ensure this can't ever be used in a non-debug setting? Particularly the AddNewSystemRole POST in the SystemRolesController - This fails for me locally, it looks like the column that was added in UpgradeLevel84 was a bit called [SYSTEM_ROLE] not a string field for {TYPE] | Done in last sprint | Done in last sprint | Closed | Scope of this story is only for testing.

## 3.1 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.1 Sprint S1 | 44182 Activities - System - Rewrite/Refactor District Settings [3.1] | Andrew | Bounceback | Advance Billings Days for Prepaid Plans value is not retained when we redirect from other pages. | Minor | Internal | Closed | Development |  | Manjunath - Offshore
2 | 3.1 Sprint S1 | 44501 Activities - Admin - New Stock User Roles | Hari | Bounceback | Facing server side validation error while viewing the roles. | Minor | Internal | Closed | Development |  | Manjunath Offshore
3 | 3.1 Sprint S1 | 23401 - Activities - Admin Registration - Pages (Pending/Waitlist/Enrollments) not showing week - Weekly Calendar - Visual Bug (Yukon) |  | Defect |  | Significant | External | Open | Existing_Issues
4 | 3.1 Sprint S1 | 23427 Activities - Parent Registration - Pages (Pending/Waitlist/Enrollments) showing week - Weekly Calendar - Visual Bug (Yukon) |  | Defect |  | Significant | Internal | Open | Existing_Issues |  | Manjunath Offshore

## 3.0 Sprint S3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.0 Sprint S3 | Allen | 44190 [Testing Phase] | Activities - Admin - Allow Student Enrollment Schedule Changes for periods already billed (Ashburnham) | 5 Sp | 3 SP | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36578 | 2024-04-22 | Allen | 2024-04-22 | Nil | Andrew | 2024-04-23 | Nil | Approved | Approved | Closed
1.b | [6 empty] | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36658 | 2024-04-25 | Allen | 2024-04-25 | Nil | Andrew | 2024-04-25 | Nil | NA | NA
2 | 3.0 Sprint S3 | Hari | 23239 [Testing Phase] | Activities - Capacity report showing total number enrolled for no service special dates Bounceback : Activities - Capacity Report bounce back fix for Excel format | 1 Sp | 1 Sp | Done | Hari | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36571 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36589 | 2024-04-22 | Allen | 2024-04-22 | Nil | Andrew | 2024-04-22 | Nil | NA | NA | Closed
3 | 3.0 Sprint S3 | Deva | 44384 | Activities - System - Automation [Timeboxed] | 8 Sp | 6 Sp | [15 empty] | Closed | Automation story Completed [Automation done for Enrollment Plan custom fields for ADD scenario in Student, Parent and Contact Tab]
4 | 3.0 Sprint S3 | Allen | 44183 | Activities - SYSTEM - Hide Large Scale Testing Improvements [3.0] | 1 Sp | 1 Sp | Done | Hari | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36604 | 2024-04-23 | Allen | 2024-04-23 | Nil | Andrew | 2024-04-24 | Typo - should be Unauthorized | NA | NA | Closed
5 | 3.0 Sprint S3 [Stretch] | Allen | 44185 [Stretch] | Activities - Admin - New Stock User Roles [3.1] (dev only) | 3 Sp | 2 Sp | Done | Hari | Nil | Allen | Nil | [8 empty] | 1.The central office role has site coordinator access; 2.The site coordinator role has central office access. 3.I have assigned reporting, site coordinator, and central office roles to my user. And I logged in as that user, but I could not see any menus. 4.For site coordinator roles - It should have access permission but still we have permission to add and edit. | Client PO - Inprogress | Closed | Client POV Inprogress [ Due to regression sprint]
6 | 3.0 Sprint S3 [Stretch] | Hari | 44492 [Stretch] | Activities - Research - Schedule Withdraw & Transfer [3.1] (Timeboxed) | 8 Sp | 8 Sp | [15 empty] | Closed | Research story
7 | 3.0 Sprint S3 [Stretch] | Allen | 44502 [Stretch] | Activities - SYSTEM - Large Scale Testing Improvements (dev only) [3.1] | 5 Sp | 2 Sp | Done | Hari | Nil | Allen | Nil | [10 empty] | Closed

## 3.0 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.0 Sprint S3 | 44190 Activities - Admin/UI - Allow Student Enrollment Schedule Changes for periods already billed (Ashburnham) | Hari | Internal | Verbiage is incorrect for combo add and remove scenario | Minor | Internal | Closed | Developmnt

## 3.0 Sprint 2-CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.0 Sprint S2 | Deva | 22715 | Activities - Admin - Fee Items - Retainer Fee: The Flat Amount entry is missing on the details page | 1 Sp | 2 Sp | Done | Deva | Nil | Deva | Done | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36351 | 2024-04-09 | Allen | 2024-04-10 | Nil | Andrew | 2024-04-10 | Nil | NA | NA | Closed
1.b |  |  | 22715 - [Bounecback] |  |  |  | Done | Deva | Nil | Deva | Done | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36388 | 2024-04-11 | Allen | 2024-04-11 | Nil | Andrew | 2024-04-12 | Nil | NA | NA
2 | 3.0 Sprint S2 | Allen | 43604 | Activities - Admin Roles - Allow Student Enrollment Schedule Changes for periods already billed (Ashburnham) | 1 Sp | 3 sp | Done | Allen | Nil | Allen | Done | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36364 | 2024-04-09 | Allen | 2024-04-10 | Nil | Andrew | 2024-04-10 | Nil | Done | Done | Closed
3 | 3.0 Sprint S2 | Hari | 44019 [Bounceback] | Custom field bounce back fix [Activities - Admin - Reports - Combine the Student Registration Output Format] | 2 Sp | 5 Sp | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36321 | 2024-04-09 | Allen | 2024-04-10 | Nil | Andrew | 2024-04-10 | Nil | NA | NA | Closed
3.b |  |  |  | Student registration report bounce back fix [Activities - Admin - Reports - Combine the Student Registration Output Format] |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36435 | 2024-04-15 | Allen | 2024-04-15 | Nil | Andrew | 2024-04-16 | Nil | NA | NA
3.c |  |  |  | Student registration report bounce back fix [Activities - Admin - Reports - Combine the Student Registration Output Format]-Allergies and dietery encryption |  |  | Done | Hari | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36553 | 2024-04-22 | Allen | 2024-04-22 | Nil | Andrew | 2024-04-22 | Nil | NA | NA
4 | 3.0 Sprint S2 | Allen | 44015 | Activities - Users - Prevent duplicates and Logic Improvement [3.0] | 3 Sp | 6 Sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35854 | 2024-03-08 | Allen | 2024-03-08 | Nil | Brian | 2024-04-11 | Nil | Done | Done | Closed
|  |  | 44016 | Activities - District ACLs - Update to React [3.0]
4.b |  |  | 44015 [Bounceback] | Bounce Fix: Restrict Mapping Multiple Roles |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36441 | 2024-04-16 | Allen | 2024-04-16 | Nil | Andrew | 2024-04-16 | Nil | NA | NA
4.c |  |  |  | Bounce Fix: A user can still alter their own security group, and someone in the security group can still delete the group from the district ACL screen |  |  | Done | Hari | nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36552 | 2024-04-22 | Allen | 2024-04-22 | Nil | Andrew | 2024-04-22 | Rather than using the users username for checking the currently logged in user, can we use the users RecID instead? | NA | NA
5 | 3.0 Sprint S2 | Allen | 44184 | Activities - Admin - Roles Improvements | 2 Sp | 2 Sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36292 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36397 | 2024-04-09 | Allen | 2024-04-10 | Nil | Andrew | 2024-04-10 | Nil | Completed in last sprint | Completed in last sprint | Closed
6 | 3.0 Sprint S2 | Deva | 44140 | Activities - Admin - Pricing Method changes when a Discount is already applied to the Enrollment Plan | 3 Sp | 4 Sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36279 | 2024-04-11 | Allen | 2024-04-11 | Nil | Andrew | 2024-04-11 | Nil | Approved | Approved | Closed
7 | 3.0 Sprint S2 | Allen | 44190 | Activities - Admin - Allow Student Enrollment Schedule Changes for periods already billed (Ashburnham) | 8 Sp | 6 Sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36578 | 2024-04-22 | Allen | 2024-04-22 | Nil |  |  |  | Approved | Approved | Inprogress | Development completed on 17-Apr, Client POV happened only on 22-Apr (Which is uncontrol) PR created on 22-Apr, Review 2 pending from client and stroy moved to next sprint.
8 | 3.0 Sprint S2 [Stretch] | Allen | 44185 [ Stretch] | Activities - Admin - New Stock User Roles | 13 Sp | [16 empty] | Inprogress | Development inprogress
9 | 3.0 Sprint S2 [Stretch] | Deva | 44330 [ Stretch] | Activities - System - Automation | 5 Sp | 3 sp | [15 empty] | Inprogress
10 | 3.0 Sprint S2 [Stretch] | Hari | 23239 [ Stretch] | Activities - Capacity report showing total number enrolled for no service special dates | 2 Sp | 1 sp | Done | Hari | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36571 | 2024-04-22 | Allen | 2024-04-22 | Nil | Andrew | 2024-04-22 | Nil | NA | NA | Inprogress | Testing inprogress

## 3.0 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.0 Sprint S2 | Story: 44019 : Activities - Admin - Reports - Combine the Student Registration Output Format | Hari | Bounceback | If we have same label custom fields for students, parents and contacts, custom fields are not showing in the student registration report. | Significant | Internal | Closed | Development |  | Found by Manjunathan - Offshore QA
2 | 3.0 Sprint S2 | Story:44015 Activities - Users - Prevent duplicates and Logic Improvement | Allen | Bounceback | Still able to add a user/security grouple multiple times as long as its tied to a different role (image in comments) | Significant | External | Closed | Development |  | Found by Jeff - Onshore QA
3 | 3.0 Sprint S2 | Story: 44019 : Activities - Admin - Reports - Combine the Student Registration Output Format | Hari | Bounceback | Allergy field is encrypted in the excel version of the report Dietery Notes field is encrypted in the excel version of the report | Significant | External | Closed | Development |  | Found by Jeff - Onshore QA
4 | 3.0 Sprint S2 | Story:44015 Activities - Users - Prevent duplicates and Logic Improvement | Allen | Bounceback | A user can still alter their own security group, and someone in the security group can still delete the group from the district ACL screen | Significant | External | Closed | Development |  | Found by Jeff - Onshore QA
5 | 3.0 Sprint S2 | Story: 44016 Activities - District ACLs - Update to React [3.0] | Hari | Bounceback | Cancel button is still deleting the ACL. Click Delete on an ACL, then click Cancel on the modal. | Significant | External | Closed | Development |  | Found by Jeff - Onshore QA

## 3.0 Sprint S1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 3.0 Sprint S1 | Hari | 44010 | Activities - SYSTEM - Roles - Update to React [3.0] | 3 Sp | 3.5 Sp | Done | Done | Done | Done | Done | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36156 | 2024-03-26 | Allen | 2024-03-26 | Nil | Andrew | 2024-03-28 | 1.Can we bring the 0 up to the same line to make this a bit more clear 2.Should we also check that this isn't a system defined role? 3.I may have missed it, but are we leveraging this new field in the code anywhere? It seems we always use the role ID < 100 to determine if this is a system role or a custom role | Done in last sprint | Approved [Done in last sprint] | Closed
|  |  | 44151 | Activities - Roles - Use "N/A" for Audit Log Nulls
|  | Allen | 44010 [BounceBack] | Roles-React-Conversion Bounce Back |  |  | Done | Done | Nil | Done | Done | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36273 | 04/03/2024 | Allen | 04/03/2024 | Nil | Andrew | 04/03/2024 | Nil | Done | NA | Closed
2 | 3.0 Sprint S1 | Deva | 44140 | Activities - Admin - Pricing Method changes when a Discount is already applied to the Enrollment Plan | 5 Sp | 6.5 Sp | Done | Done | Nil | Done | Done | [8 empty] | Done | Pending | Inprogress | Development completed. Client POV pending = Moved to Next Sprint
3 | 3.0 Sprint S1 | Allen | 44184 | Activities - Admin - Roles Improvements | 5 Sp | 4 sp | Done | Hari | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36292 | 04/04/2024 | Andrew | 04/09/2024 | NA | Andrew | 04/09/2024 |  | 1.Description Column Header should not be sortable. 2.Role Name validation message is showing wrong in add /edit section. 3.Capture Role Name and Description value in Audit Log for Custom Role 4.While copying a role, still it is showing as copy security role in the header instead of that copy name. | Completed - Approved | Closed | Development completed, testing part moved to next sprint by client.
4 | 3.0 Sprint S1 | Allen | 44183 | Activities - SYSTEM - Large Scale Testing Improvements | 1 Sp | 1 Sp | Done | Hari | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36236 | 04/01/2024 | Brian |  |  | Brian |  |  | NA | NA | Closed
5 | 3.0 Sprint S1 [Stretch] | Allen | 43604 [Stretch] | Activities - Admin Roles - Allow Student Enrollment Schedule Changes for periods already billed (Ashburnham) | 5 Sp | 3 sp | Done | Allen | Nil | Allen | Nil | [8 empty] | Completed - Approved | Completed - Approved | Inprogress | PR approval pending from client.
6 | 3.0 Sprint S1 [Stretch] | Hari | 44019 [Stretch] | Activities - SYSTEM - Admin - Reports - Combine the Student Registration Output Format [3.0] | 3 Sp | 5 Sp | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36195 | 04/02/2024 | Allen | 04/02/2024 | Nil | Andrew | 04/02/2024 | Nil | Done in last sprint | Approved [Done in last sprint] | Inprogress | 1 bb added
7 | 3.0 Sprint S1 [Stretch] | Deva | 44019 [Stretch] [BounceBack] | Custom field bounce back fix | [7 empty] | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36321 | 04/09/2024 | Allen | [7 empty] | Inprogress | Peer review pending from client, so Moved to next sprint for testing
8 | 3.0 Sprint S1 [Stretch] | Allen | 44185 [Stretch] | Activities - Admin - New Stock User Roles | 13 Sp | 3 sp | [15 empty] | Inprogress | Developement Inprogress
Summary
|  | Main commit - | 44140 Moved to next sprint for Client POV, Peer review and testing
44184 - Moved for next sprint for Testing

## 3.0 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 3.0 Sprint S1 | 44018 Activities - Roles - Update to React [3.0] | Allen Xavier | Bounceback | Incorrect error message is being dsiplayed when the user does not have access to the roles page, see included images | Minor | External | Closed | Development | Issue Fixed | Found by Jeff - Onshore QA
2 | 3.0 Sprint S1 | 44019 Activities - Admin - Reports - Combine the Student Registration Output Format [3.0] | Allen Xavier | Bounceback | PM Custom field column header is showing wrongly for student, parent and contact for Student registration report of Excel format type. | Significant | Internal | Inprogress | Development | Column Header Miss Match in Report | Found by Manjunathan- Offshore QA

## 2.9.5 Sprint S3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 2.9.5 Sprint S3 | Hari | 41950 [Stretch] | Activities - SYSTEM - Roles - Update to React [3.0] | 3 sp | 5 Sp | Done | Deva | 1. Sorting is not working 2. Please move sort button little bit like "Security Group" 3. If i add same description client side error message need to be set as QA 4. Cancel Button is not working 5. Insert "Audit Log" Headers like other audit log pages 6. Please check client side error message in edit scenario 7. Change Caption 8. Pagination is not working here. it is existing but we can do in react conversion. | Deva | 1. If you want Place id and reference inside one common class and then inherit "AddOrEditRoleModelBase" or you can ignore 2. Re name it "Post add role " like this 3. Remove un used hooks 4. is this method needed in Security group controller ? (e | [8 empty] | 1.While editing a role, that role name should display in the header; instead, it is showing as “Edit Security Role." [It's an existing issue]. 2.Color for Access: Green should highlight "Allow,” not all the columns. 3.Color for Deny: Light red should highlight "Deny,” not all the columns. 4.Highlight the text color for Allow and Deny: Green is for allow, and red should highlight "deny.” 5.In current roles, they are showing Full Control and Read only at the top, followed by other role creation. I am thinking we can follow the same (I knew sorting we had given but still that static roles we can show at the top). |  | Closed | Need to Raise PR once the regression sprint over.
|  |  | 44005 [Stretch] | Activities - Roles - Use "N/A" for Audit Log Nulls | 2 sp | [15 empty] | No comments.
2 | 2.9.5 Sprint S3 | Deva | 22999 | Activities - Parent - Weekly Calendar " Saturday and Sunday" are not selectable at Edit Registration | 5 Sp |  |  | Hari | 1.Newly added days indication,when parent does not add any new day in daily calendar 2.Newly added week indication when parent does not added any new week | Hari | 1.Dont bind activities schedule which does not contain schedule changes made by parent | [11 empty] | Defect rejected,will be worked as a separate story
3 | 2.9.5 Sprint S3 | Hari | 23013 | Activities - Parent - Current Schedule Changes - Added date showing in Weeks Removed | 3 sp | 1 sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35997 | 2024-03-15 | Allen | 2024-03-15 | Nil | Andrew | 2024-03-15 | Nil | Nil | Nil | Closed
4 | 2.9.5 Sprint S3 | Deva | 43992 | Activities - Research [TIMEBOXED] - Roles Improvements | 8 sp | 6 Sp | [15 empty] | Closed | Research Story - document attached in user story.
5 | 2.9.5 Sprint S3 | Allen | 43986 [Stretch] | Activities - Research [TIMEBOXED] - New Stock User Roles | 8 sp | 6 Sp | [15 empty] | Closed | Research Story - document attached in user story.
6 | 2.9.5 Sprint S3 | Allen | 44004 [Stretch] | Activities - SYSTEM - Large Scale Testing Improvements | 3 sp | 3 sp | [16 empty] | Completed 1.Creates new activity with given name in the payload 2.Creates new enrolment plan with the given name and assigns created activities to this enrollment plan 3.Creates new term with the given name and assigns created enrollmentplan and activities to this term
7 | 2.9.5 Sprint S3 | Hari | 42875 [Stretch] | Activities - SYSTEM - Admin - Reports - Combine the Student Registration Output Format [3.0] | 5 Sp | 4.5 Sp |  | Deva | 1. Display enum value instead of number like male or female 2. In Existing Excel report, We have parent contacts upto 6 but in New Excel we have 4. (Please ensure in local) 3. Index was outside bounds of the array. | Deva | Nil | [8 empty] | 1. Please remove Enabled from the header for the PDF 2. Please remove Enabled from the header for HTML. 3. If the address is not given for contacts, it is showing as a comma (,) in the excel. | No comments. | Closed | Need to Raise PR once the regression sprint over.
8 | 2.9.5 Sprint S3 | Hari | 23095 [Regression Defect] | Activities - Regression - Admin - Reports - Invoice Payment Summary, Student Roster, Capacity Run button staying greyed out when using select all | 1 Sp | 1 Sp | Hari | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/36132 | 2024-03-25 | Allen | 2024-03-25 | Nil | Brian | 2024-03-26 | NIL | NA | NA | Closed

## 2.9.5 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 2.9.5 Sprint S3 | 23095 Activities - Regression - Admin - Reports - Invoice Payment Summary, Student Roster, Capacity Run button staying greyed out when using select all | Hari | Defect | When choosing the filters for the Invoice Payment Summary, Student Roster, Capacity report, if you use select all in the enrollment plan filter the run button doesnt enable, it does work if you choose an enrollment plan. | Significant | External | Inprogress | QA | We found an issue in regression due to the report optimization story. Regression Defect | Found by Jeff - Onshore QA

## 2.9.5 Sprint S2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 2.9.5 Sprint S2 | Hari | 43659 [ Last sprint ] | Activities - Parent - Call out Pending Schedule Changes in Schedule Overview | 5 sp | 8 sp | Done | Deva | Activity, Schedule and Attendance needs to be aligned like existing | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35567 | 2024-02-26 | Allen | 2024-02-29 | NIL | Andrew |  | NIL | 1.For the weekly and daily attendance calendars, in parent, it is showing an error: Note: I added an activity (daily or weekly) after registration was done, but an error showed at the time of editing a registration. 2.For a normal calendar with attendance calendar scenario, I have changed the normal calendar schedule but not touched the daily attendance calendar; it is showing the schedule changes; it needs to be hidden. 3.The download button is not working if the current approved schedule is not expandable. 4.Suggestion: Add a comma separator, like in the current schedule section, because the pages got scrolled due to more days added or removed. 5.For Days removed comma separator missing 6.Showin an error " Cannot read properties of undefined(reading 'special days') 7.Current day is showing in days added/days removed 8.Days added/removed - 2025 DAYS not showing 9.Schedule days of days added/removed is showing in current schedule section. | NIL | Closed
2 | 2.9.5 Sprint S2 | Deva | 43208 [ Last sprint ] | Activities - District Settings - Update Max Advance Billings | 2 sp | 2 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35697 | 2024-02-28 | Allen | 2024-02-29 | NIL | Brian | 2024-02-29 | NIL | NIL | NIL | Closed
3 | 2.9.5 Sprint S2 | Hari | 42874 [ Last sprint :Bounceback] | Activities - Admin - Reports - Combine the Student Roster Report Output Format [2.9.5] | 2 sp | 1 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35662 | 2024-02-27 | Allen | 2024-02-29 | NIL | Brian | 2024-02-29 | NIL | NA | NA | Closed
4 | 2.9.5 Sprint S2 | Hari | 22931 | Activities - Admin and Parent - Visual bug showing non-selected days when activity starts mid week | 8 sp | 6 sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35721 | 2024-02-29 | Allen | 2024-03-01 | NIL | Brian | 2024-03-01 | NIL | NIL | NA | Closed
5 | 2.9.5 Sprint S2 | Allen | 22909 | Activities - Admin - Operating Days - Non-Scheduled Modal Overlapped in the Check-In page | 3 Sp | 4 sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35722 | 2024-02-29 | Allen | 2024-03-04 | NIL | Andrew | 2024-03-04 | NIL | NA | NA | Closed
6 | 2.9.5 Sprint S2 | Hari | 22951 | Activities - Admin - Sundays not showing for Schedule | 3 Sp | 2 sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35723 | 2024-02-29 | Allen | 2024-03-01 | NIL | Brian | 2024-03-01 | NIL | Nil | NA | Closed
7 | 2.9.5 Sprint S2 | Deva | 22949 | Activities - Parent able to edit schedule when allow modifications to schedule is disabled on the Term | 8 Sp | 11 sp | Done | Hari | 1.Schedule tab missing when admin enables Allow modifications to schedule for any activity 2.I am able to navigate back to schedule page from submit page by clicking on back arrow button after admin approves the registration 3.During new registration,when the user is in submit page and if the user click back button, it is navigating back to contacts page instead of schedule page 4.For approved registration,when i enable allow modifications to schedule to any activity,i am unable to modify the schedule since i am not able to click schedule tab and also navigation from contacts page and from submit page is not navigating to schedule page. 5.Schedule tab is visible for approved registration when allow modifications to schedule is not enabled for any activity | Hari | 1.Changes made in SchedulesView.tsx is not required, revert those changes 2.Next button navigation is being handled in two methods handleContactsMoveNextAsync And in handleMoveNext. Handle it in handleContactsMoveNextAsync method alone | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35853 | 2024-03-08 | Allen | [5 empty] | 1.In the enrollment plan if “Prompt for Schedule” is set to OFF and in term maintenance if “Allow Modifications to Schedules” is set to OFF, still the “Schedule” section is showing for new registration. Actually, if the prompt for schedule is set off days and time for an ep, the schedule menu should not display in parent. 2.In the enrollment plan if “Prompt for Schedule” is set to OFF and in term maintenance if “Allow Modifications to Schedules” is set to ON, still the “Schedule” section is showing for new registration. Actually, if the prompt for schedule is set off days and time for an ep, the schedule menu should not display in parent. 3. Schedule header still shows in Parent. | NA | Inprogress | Given POV testing comments. Still PR pending
8 | 2.9.5 Sprint S2 | Hari | 22998 [Stretch] | Activities - Admin - Operating Days - Admin Menu Persists for Mode "Fast" in Check-In/Out page |  | 1 sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35865 | 2024-03-08 | Allen | 2024-03-08 | NIL | Andrew | 2024-03-11 | NIL | Nil | NA | Closed
9 | 2.9.5 Sprint S2 | Hari | 43383 [Stretch] | Activities - Admin - Discount Summary Reports - Show the Site name in the filters option | 3 Sp | 4 sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35867 | 2024-03-11 | Allen | 2024-03-11 | NIL | Andrew | 2024-03-11 | NIL | Nil | Nil | Closed
10 | 2.9.5 Sprint S2 | Allen | 43629 [Stretch] | Activities - Users - Prevent duplicates and Logic Improvement [3.0] | 5 Sp | 7 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35854 | 2024-03-08 | Allen | 2024-03-08 | NIL | Brian | 2024-03-12 | 1.This is used but it is not is not in the query. 2.Is anything here except TenantID ever used? 3.Why were the discounts removed? | 1. Add red asterisk to Principal field. 2. If Role field is not selected, it showing server error. 3. Acl removed successfully - Change to ACL Removed | Nil | Inprogress | PR review pending. Planned for Next Release by Brian
11 | 2.9.5 Sprint S2 | Allen | 41966 [Stretch] | Activities - District ACLs - Update to React [3.0] | 3 sp | 4 Sp | [15 empty] | Inprogress
12 | 2.9.5 Sprint S2 | Hari | 41950 [Stretch] | Activities - Roles - Update to React [3.0] | 8 sp | 3 sp | [15 empty] | Inprogress | Development inprogress
13 | 2.9.5 Sprint S2 | Deva | 22999 [Stretch] | Activities - Parent - Weekly Calendar " Saturday and Sunday" are not selectable at Edit Registration | [17 empty] | Inprogress | Development inprogress
|  |  | Notes | Carry Forward to Next Sprint [2.9.5 S3]
|  |  | 1 | 22949 - Due to internal POV findings, PR Pending
|  |  | 2 | Stretch : 41950, 22999 - Development in progress 43629, 41966 - Client PR pending

## 2.9.5 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 2.9.5 Sprint S2 | 22998 Activities - Admin - Operating Days - Admin Menu Persists for Mode "Fast" in Check-In/Out page | Hari | Bounceback | When the activity mode is FAST for drop off/pick up, if the admin tries to check in or out a student, notice that the admin left-side menu persists on those pages. | Major | Internal | Closed | Development |  | Found by Kanchana - PO
2 | 2.9.5 Sprint S2 | 22999 Activities - Parent - Weekly Calendar " Saturday and Sunday" are not selectable at Edit Registration | Deva | Defect | If Saturday and Sunday are added to an activity, at the time of editing a registration in the parent for the weekly calendar, I could not select Saturday and Sunday on the calendar. | Significant | Internal | Inprogress | Existing_Issues |  | Found by Kanchana - PO
3 | 2.9.5 Sprint S2 | 23013 Activities - Parent - Current Schedule Changes - Added date showing in Weeks Removed | Hari | Defect | At the time of editing a registration, while we add a new weeks, it includes a week in the "Weeks Removed" section. Expected: It should show only Weeks added alone. Dev Note: Related to the story 43659 | Significant | Internal | Inprogress | Development |  | Found by Kanchana - PO

## 2.9.5 Sprint S1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 2.9.5 Sprint S1 | Hari | 43335 | Activities - SYSTEM - Admin - Replace "Server communicating message" with Spinning Loader [2.9.5] | 1 sp | 2.5 sp | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35238 | 2024-02-08 | Allen | 2024-02-09 | NIL | Andrew | 2024-02-14 | Can we try to avoid using inline styling and move this css into a class in the site.scss file | Due to exclude the side navigation panel in admin - its affected operating days - Check in page design | Please center spinning loader within the page contents (exclude the side navigation panel) for Admin. This is not needed for Parent Registration pages since the side navigation panel is not present. Other than this comment, initial POV approved. | Closed
2 | 2.9.5 Sprint S1 | Hari | 43336 | Activities -SYSTEM - Parent - Replace "Server communicating message" with Spinning Loader [2.9.5] | 1 sp | 1 sp | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35239 | 2024-02-08 | Allen | 2024-02-09 | NIL | Andrew | 2024-02-14 | Can we try to avoid using inline styling and move this css into a class in the site.scss file | Completed | Completed | Closed
3 | 2.9.5 Sprint S1 | Hari | 22756 [Defect] | Activities - Admin - Student Purchases Period Filter not accounting for year [2.9.5] | 2 sp | 5 sp | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35415 | 2024-02-12 | Allen | 2024-02-12 | NIL | Andrew | 2024-02-13 | NIL | Completed | Completed | Closed
4 | 2.9.5 Sprint S1 | Hari | 22756 [Defect - Bounceback] | Activities - Admin - Student Purchases Period Filter not accounting for year [2.9.5] [Bounceback] | 2 sp | 1 sp | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35464 | 2024-02-15 | Allen | 2024-02-15 | NIL | Andrew | 2024-02-15 | NIL | Completed | Completed | Closed
5 | 2.9.5 Sprint S1 | Deva | 43486 | Activities - SYSTEM - Mass Assign/RemoveDiscounts [3.0] | 5 sp | 6 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35240 | 2024-02-14 | Allen | 2024-02-16 | 1.Give a reasonable name for methods 2.Do we need to select all the columns from student table as it lines up in group by. 3.Move all the style to css file instead of using inline css. 4.Use PUT method insead of Post. Mostly use appropriate method to nased on the operation that we perform 5.Remove unnecessary indent and space. 6.Keep all our new implementation at the bottom of the tag so that we know what we have induced. | Andrew | 2024-02-21 | 1.Can we rename and not use GetAll to avoid confusion? Maybe GetStudentListByIDsAsync or something similar 2.Typo on word Changes 3.Can the header and the description text below be moved inside the Assignment component and showed conditionally based on the ASSIGN or REMOVE mode, to keep all of this contained to the component? 4.Can we use something other than a string value to designate the mode? Perhaps an enum declared in the model.tsx file like: | Added my POV comments in google doc and shared with team 1.Clear selection X not working for Assign and Remove 2.We change to Students from Student(s) - Minor change 3.This point not done : AC point not done - Major For Discount mass assignment, validation is needed to ensure that we are only showing students actively enrolled in enrollment plans set up to offer that discount. 4.Loading of Data takes time - Please check the performance of the page to load the students quick when we change the tabs (Mass/Assign) 5.For the New discount created, already enrolled students are showing. 6.Success message for assign and remove - change “Selected” - S caps to small letters - minor change. 7.Site name missing under the student name for assign and remove discounts - need site name for three sections - Select all, Clear selection and Current discount assignment. For remove two sections - Select all, Clear selection. 8.For verbiage - assign/remove - need indent spacing for last point 9.Once edit the discount name and click save, it should redirect to the Details page but it's redirecting to the Main discount page. Check other menus in the application to confirm. 10.The search icon for the search bar looks similar to all the pages on the application. Follow the same search bar. 11.Need spacing between the students for assign/ remove sections 12.Do we need the x button for the current discount assignment ? 13.No Site Selected - Scenario - For new discount if the student already assigned - Check assign and remove 14.For Remove scenario : Site name missing. 15.Add link to student Name; 16.If the admin assigns discount only in the student maintenance section for a student that student should not list in the remove assign section. | Completed | Closed
6 | 2.9.5 Sprint S1 | Deva | 43633 | Activities - Admin - Audit Log Refresh to show changes [2.9.5] | 5 sp | 4 sp | Done | Hari | Nil | Hari | 1.Remove onInit for auditlog tab in ActivitySessionDetailPage.tsx | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35409 | 2024-02-12 | Allen | 2024-02-14 | NIL | Andrew | 2024-02-15 | NIL | Completed | NA | Closed
7 | 2.9.5 Sprint S1 | Allen | 43550 | Activities - Admin - Student Registration Reports Improvement [2.9.5] | 5 sp | 10 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35437 | 2024-02-13 | Allen | 2024-02-16 | NIL | Andrew | 2024-02-22 | 1.Can this method be combined with the GetReportCriteriaModel method, and the IsSequentialFilter flag be used to handle the branching logic all inside this one function? Splitting them out may make it difficult to maintain in the future if we add additional reporting lo gic. As an example for where the logic differs when collecting enrollment plan information, I believe something like this would satisfy both sequential and non sequential reports: 2.I believe this section had been removed from your updated method, does this need to be conditionally skipped if this is a sequential filter report? | Completed | Completed | Inprogress | Testing in progress
8 | 2.9.5 Sprint S1 | Hari | 43536 | Activities - Parent - Registration navigation buttons fixed position [2.9.5] | 2 sp | 2 sp | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35416 | 2024-02-12 | Allen | 2024-02-13 | NIL | Andrew | 2024-02-14 | NIL | 1. Button at the bottom showing half size in the parent page | Completed | Closed
9 | 2.9.5 Sprint S1 | Deva | 42874 | Activities - Admin - Reports - Combine the Student Roster Report Output Format [2.9.5] | 5 sp | 8 sp | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35595 | 2024-02-22 | Allen | 2024-02-22 | NIL | Andrew | 2024-02-23 | NIL | 1.In AC - Mock up after PDF, Excel should show in drop down of output format. 2.Result : Column header should be Bold - I hope we are following the same in all excel reports. 3.In excel, Scheduled details will show first and then Non scheduled will display. 4. (increase the width and height of each column like existing output format). 5.Check-in and out should of the header be "Check-In and Check-Out. | Completed | Inprogress | Testing in progress
10 | 2.9.5 Sprint S1 | Hari | 43531 | Activities - Parent - Show Pending Days in Calendar Selector | 5 sp | 4 sp | Done | Deva | If no special dates marked in terms. Error will be found | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35566 | 2024-02-21 | Allen | 2024-02-21 | NIL | Andrew | 2024-02-23 | 1.Looks like missing semi colons 2.Can this CSS be included in the main bscustom.scss file? 3.Are we able to avoid using !important in this and the other css changes? | 1. Change the color of the pencil icon for inital registration 2. Yellow color border exists in student enroll page. - Remove it | One suggestion: When a Parent Edits, submits their changes, then before the admin approves the updated registration, the parent goes in to make additional updates, we are showing "Pending Approval" for changes that were not submitted by the parent. I think we should show the "Edit in Progress - Please Submit Changes for Approval" text if any change is made that has not yet been submitted by the parent - Its not needed explained to Kristy about functionality | Inprogress | Onshore Testing in progress
11 | 2.9.5 Sprint S1 | Hari | 43659 | Activities - Parent - Call out Pending Schedule Changes in Schedule Overview | 8 sp | 8 sp | Done | Deva | Activity, Schedule and Attendance needs to be aligned like existing | Deva | Nil | [8 empty] | 1.For the weekly and daily attendance calendars, in parent, it is showing an error: Note: I added an activity (daily or weekly) after registration was done, but an error showed at the time of editing a registration. 2.For a normal calendar with attendance calendar scenario, I have changed the normal calendar schedule but not touched the daily attendance calendar; it is showing the schedule changes; it needs to be hidden. 3.The download button is not working if the current approved schedule is not expandable. 4.Suggestion: Add a comma separator, like in the current schedule section, because the pages got scrolled due to more days added or removed. 5.For Days removed comma separator missing 6.Showin an error " Cannot read properties of undefined(reading 'special days') 7.Current day is showing in days added/days removed 8.Days added/removed - 2025 DAYS not showing 9.Schedule days of days added/removed is showing in current schedule section. | 1. Days Attending text to be "Days Added" in Schedule Changes. | Inprogress | PR not rasied due to more testing scenarios. Informed to Brian
12 | 2.9.5 Sprint S1 | Deva | 43582 [Stretch] | Activities - Terms - Prevent Adding Duplicate Enrollment Plans & Activities | 3 sp | 3 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35556 | 2024-02-21 | Allen | 2024-02-21 | NIL | Andrew | 2024-02-23 | NIL | 1.Edit Activity : Once clicked Edit button it is showing Render error. (issue) 2.Edit Enrollment Plan : Enrollment Plan name missing in drop down of EP (issue) | Approved | Closed
13 | 2.9.5 Sprint S1 | Deva | 43208 [Stretch] | Activities - District Settings - Update Max Advance Billings | 2 sp |  | Done | Hari | Nil | Hari | Nil | [11 empty] | Internal POV pending part of stretch story
14 | 2.9.5 Sprint S1 | Hari | 42874 [Bounceback] | Activities - Admin - Reports - Combine the Student Roster Report Output Format [2.9.5] |  | 1 sp | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35662 | 2024-02-27 | Allen |  |  | Andrew |  |  | NA | NA |  | Moved to next sprint
|  |  | Notes | Carry Forward to Next Sprint [2.9.5 S2] - Main Commit items
|  |  | 1 | 43659 - Parent Schedule Calendar change: Development was completed and client POV was done on February 21st, but while doing internal POV testing, I found more issues due to various scenarios. Allen informed Brian about this. He accepted to give without issues.
|  |  | 2 | 42874 - Student Roster Report: Due to 1 BB from Onshore QA. For testing efforts, move to the next sprint.
|  |  | 3 | 42550 - Student Registration : Due to 1 BB from Onshore QA. For testing efforts, move to the next sprint.
|  |  | 4 | 43531 - Parent UI Calendar changes: Testing is pending from onshore QA. He was occupied with other story-testing work.
Carry Forward to Next Sprint [2.9.5 S2] - Stretch items
|  |  | 1 | 43208 - Development completed. Internal and client POVs are pending.

## 2.9.5 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 2.9.5 Sprint 1 | 22909 Activities - Admin - Operating Days - Non-Scheduled Modal Overlapped in the Check-In page |  | Defect | On non-scheduled days, the students tried to check in, and we are showing a modal pop-up "Non Scheduled - Students" that got overlapped. | Significant | Internal | Open | Development | Due to changes of Admin loader story | Found by Kanchana - PO
2 | 2.9.5 Sprint 1 | 22934 Activities - Admin - Reports Activity error popup is missing | Andrew | Defect | In a Student and details registration report when a user able to run a report when Activity is deselected then Activity error message is missing. | Minor | Internal | Inprogress | Existing_Issues |  | Found by Johnson - Offshore QA
3 | 2.9.5 Sprint 1 | 22931 Activities - Admin and Parent - Visual bug showing non-selected days when activity starts mid week |  | Defect | A customer has brought to our attention when they start their activity on a Friday that the entire week is shown as having been selected. This looks to be a visual bug, the student roster report shows that it's only that Friday that the student is supposed to attend, the enrollments page shows that its only that Friday was selected. It looks to be an issue in the Pending/Waitlisted/Updated Registration in Admin, and the Parent schedule view in Parent. | Significant | External | Open | Existing_Issues |  | Found by Jeff - Onshore QA
4 | 2.9.5 Sprint 1 | 22756 Activities - Admin - Student Purchases Period Filter not accounting for year | Hari | Defect | While reviewing purchases under a Student, filtering by Period for this table is not applying correctly based on the full date (including the year). | Significant | External | Closed | Existing_Issues |  | Found by Jeff - Onshore QA
5 | 2.9.5 Sprint 1 | 42874 Activities - Admin - Reports - Combine the Student Roster Report Output Format [2.9.5] | Hari | Bounceback | excel version lists the names backwards compared to the pdf/html | Significant | External | Inprogress | Development |  | Found by Jeff - Onshore QA
6 | 2.9.5 Sprint 1 | 43550 Activities - Admin - Student Registration Reports Improvement [2.9.5] | Andrew | Bounceback | Red asterick is not added to all reports for needed filters | Significant | External | Inprogress | Development |  | Found by Jeff - Onshore QA
7 | 2.9.5 Sprint 1 | 22949 Activities - Parent able to edit schedule when allow modifications to schedule is disabled on the Term |  | Defect | As an admin user, when I have the Allow Modifications to Schedule setting disabled, I expect that Parents will not be able to modify their schedule for that activity. | Significant | Internal | Open | Existing_Issues | Found by New QA - Manjunathan
8 | 2.9.5 Sprint 1 | 22951 Activities - Admin - Sundays not showing for Schedule |  | Defect | As an admin user, when I offer my activity on Sundays, and a parent registers for Sundays, the Parent can see the scheduled attendance for Sundays in their schedule preview, however, I am unable to see these days when I review the Schedule in Pending Registrations, Waitlist Registrations, Updated Registrations, and Enrollments. | Significant | Internal | Open | Existing_Issues | Found by New QA - Manjunathan

## 2.9 Sprint S3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 2.9 Sprint S3 | Hari | 43335 [Stretch] | Admin - Replace "Server communicating message" with Spinning Loader [2.9.5] | 2 sp | 1.5 | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35238 | 2024-02-08 | Allen | 2024-02-09 | NIL | Andrew |  | Can we try to avoid using inline styling and move this css into a class in the site.scss file | Due to exclude the side navigation panel in admin - its affected operating days - Check in page design | Please center spinning loader within the page contents (exclude the side navigation panel) for Admin. This is not needed for Parent Registration pages since the side navigation panel is not present. Other than this comment, initial POV approved. | Inprogress | Client Peer review - Pending
2 | 2.9 Sprint S3 | Hari | 43336 [Stretch] | Parent - Replace "Server communicating message" with Spinning Loader [2.9.5] | 2 sp | 1 | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35239 | 2024-02-08 | Allen | 2024-02-09 | NIL | Andrew |  | Can we try to avoid using inline styling and move this css into a class in the site.scss file | Completed | Completed | Inprogress | Client Peer review - Pending
3 | 2.9 Sprint S3 | Deva | 43334 | Activities - Admin - Changing (null) to "N/A" for all Audit Logs [2.9] | 2 sp | 1.5 | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35251 | 2024-01-31 | Allen | 2024-01-31 | NIL | Brian |  |  | POV Approved. I thought of conveying this point to Client regarding story 43334 Activities - Admin - Changing (null) to "N/A" for all Audit Logs [2.9] If we add a new EP or Activity record IN TERM (Adding record scenarios wherever applicable in the application ), previously it would show blank, and now it will show N/A. | Client Okay for the feedback raised. | Closed
4 | 2.9 Sprint S3 | Hari | 42924 | 42924 Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] [Bounceback PR] | 2 sp | 2 | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35263 | 2024-01-31 | Allen | 2024-01-31 | NIL | Brian | 2024-01-31 | NIL | NA | NA | Closed
5 | 2.9 Sprint S3 | Hari | 22756 [Stretch] | Activities - Admin - Student Purchases Period Filter not accounting for year [2.9.5] | 5 sp | 4 | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35415 | 2024-02-12 | Allen | 2024-02-12 |  |  |  |  | Completed | Completed | Inprogress | Moved to testing
6 | 2.9 Sprint S3 | Deva | 43486 [Stretch] | Activities - SYSTEM - Mass Assign/RemoveDiscounts [3.0] | 5 sp | 2.5 | Done | Hari | Nil | Hari | Nil | [8 empty] | Added my POV comments in google doc and shared with team 1.Clear selection X not working for Assign and Remove 2.We change to Students from Student(s) - Minor change 3.This point not done : AC point not done - Major For Discount mass assignment, validation is needed to ensure that we are only showing students actively enrolled in enrollment plans set up to offer that discount. 4.Loading of Data takes time - Please check the performance of the page to load the students quick when we change the tabs (Mass/Assign) 5.For the New discount created, already enrolled students are showing. 6.Success message for assign and remove - change “Selected” - S caps to small letters - minor change. 7.Site name missing under the student name for assign and remove discounts - need site name for three sections - Select all, Clear selection and Current discount assignment. For remove two sections - Select all, Clear selection. 8.For verbiage - assign/remove - need indent spacing for last point 9.Once edit the discount name and click save, it should redirect to the Details page but it's redirecting to the Main discount page. Check other menus in the application to confirm. 10.The search icon for the search bar looks similar to all the pages on the application. Follow the same search bar. 11.Need spacing between the students for assign/ remove sections 12.Do we need the x button for the current discount assignment ? | Completed | Inprogress | Onsite coordinator - Peer review - Pending
7 | 2.9 Sprint S3 | Deva | 43388 [Stretch] | Activities - Admin - Audit Log Refresh to show changes [Timeboxed] [2.9.5] | 8 sp | 5 | Done | Hari | Nil | Hari | 1.Remove onInit for auditlog tab in ActivitySessionDetailPage.tsx | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35409 | 2024-02-12 | Allen | [5 empty] | Completed | NA | Inprogress | Onsite coordinator - Peer review - Pending
8 | 2.9 Sprint S3 | Allen | 43550 [Stretch] | Activities - Admin - Student Registration Performance | 5 sp | 4 | Done | Hari | Nil | Hari | [9 empty] | Completed | Completed |  | Client Peer review - Pending
9 | 2.9 Sprint S3 | Hari | 43536 [Stretch] | Activities - Parent - Registration navigation buttons fixed position [2.9.5] |  | 1 | Done | Allen | Nil | Allen | No comments | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35416 | 2024-02-12 | Allen | [5 empty] | 1. Button at the bottom showing half size in the parent page | Completed | Inprogress | Client Peer review - Pending
10 | 2.9 Sprint S3 | Deva | 42874 [Stretch] | Activities - Admin - Reports - Combine the Student Roster Report Output Format [2.9.5] |  | 4 | [16 empty] | Development

## 2.9 Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 2.9 Sprint S3 | 22814 Activities - admin -Sanitization Issue - Forbidden error popup coming |  | Defect | While User tries to add a New Enrollment plan and while editing the activity in term maintenance forbidden error pop up coming. | Minor | Internal | Open | Environment_Related |  | Found by Johnson - Offshore QA

## 2.9 Sprint S2-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | Reviewer 1 | PR Approved Date | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 2.9 Sprint S2 | Deva | Defect: 22657 | Activities - Admin - Fee Items - Percent amount being shown on General fee details page | 3 sp | 6 hrs | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35022 | 2024-01-17 | Allen | 2024-01-17 | Nil | Brian | 2024-01-18 | What is the difference between state and props? State sounds like page state. Props sounds like something from the server. My follow up question would be, how does it work on a page refresh, and/or FeeType change? Deva replied : In this line, State will hold the API call value but Props having UI changed value so when user changes the dropdown value it will handle in Props so that we can check the condition of Fee Type | Nil | N/A | Closed | Completed
2 | 2.9 Sprint S2 | Deva | 43149 | Activities - Mass Assign/RemoveDiscounts (Timeboxed) | 8 sp |  |  | Hari | Nil | Hari | [11 empty] | Inprogress | Development going
3 | 2.9 Sprint S2 | Hari | Defect: 22682 | Activities - Admin - Term Maintenance Permissions Issue | 5 sp | 5 hrs | Done | Deva | NIl | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35025 | 2024-01-17 | Allen | 2024-01-17 | Nil | Brian | 2024-01-17 | Nil | Nil | N/A | Closed | Completed
4 | 2.9 Sprint S2 | Hari | Defect:22676 | Activities - Admin - Reporting Permissions Issue | 3 sp | 5 hrs | Done | Deva | NIl | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35024 | 2024-01-17 | Allen | 2024-01-17 | Nil | Brian | 2024-01-17 | Nil | 1. Found access issue for the reports at the time of generating the output. | N/A | Closed | Completed
5 | 2.9 Sprint S2 | Allen | 43155 | Activities - Admin - Update Time Zone Verbiage | 3 sp |  | Done | Deva | NIl | Deva | remove null check | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35153 | 2024-01-24 | Allen | 2024-01-25 | Nil | Brian | 2024-01-25 | Nil | 1. The time zone should match exactly the previous time zone. 2. Should show the time zone options in the order mentioned in AC. |  | Closed | Completed
6 | 2.9 Sprint S2 | Hari | 42917 | Activities - Admin - Record Transfer/Withdraw in Audit Log [For 2 new scenarios] |  | 4 hrs | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35053 | 2024-01-18 | Allen | 2024-01-19 | Nil | Brian | 2024-01-20 | Nil | Asked to add the transfer scenario in the Student Maintenance section, like in student enrollment. | Approved | Closed | Completed
7 | 2.9 Sprint S2 | Hari | Defect :22676 | Activities - Admin - Reporting Permissions Issue - [Bouncebacks PR] |  | 4 hrs | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35059 | 2024-01-18 | Allen | 2024-01-19 | Nil | Brian | 2024-01-20 | Nil | Nil | N/A | Closed | Completed
8 | 2.9 Sprint S2 | Hari | 43289 [Stretch] | Activities - Admin - Hide Events Permissions under Roles | 3 sp | 4 hrs | Done | Deva | NIl | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35085 | 2024-01-18 | Allen | 2024-01-20 | Nil | Brian | 2024-01-23 | Let's rename this to something a little more meaningful. Here is a suggestion, but there might be something more succinct. | Approved | Approved | Closed | Completed
9 | 2.9 Sprint S2 | Hari | 43313 [Stretch] | Activities - Admin - District settings - Audit log - Hide provider info for non HSS user | 2 sp |  | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35086 | 2024-01-19 | Allen | 2024-01-19 | Nil | Brian | 2024-01-19 | This will work for now, but if we ever page audit results then we will need to update the query to not pull the data from the database when we query it. | Approved | Approved | Closed | Completed
10 | 2.9 Sprint S2 | Hari | 43313 [Stretch] | [Stretch] Activities - Admin - District settings - Audit log - Hide provider info for non HSS user - [Bouncebacks PR] |  |  | Done | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35150 | 2024-01-24 | Allen | 2024-01-25 | Nil | Brian | 2024-01-25 | 1.Minor text change | NA | NA | Closed | Completed
11 | 2.9 Sprint S2 | Hari | 42924 | Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] - [Bouncebacks PR] |  |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35129 | 2024-01-24 | Allen | 2024-01-24 | Nil | Brian | 2024-01-25 | Nil | NA | NA | Closed | Completed
12 | 2.9 Sprint S2 | Hari | 42924 | Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] - [Bouncebacks PR] |  |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35191 | 2024-01-26 | Allen | 2024-01-26 | Nil | Brian | 2024-01-26 | Nil | NA | NA | Closed | Completed
13 | 2.9 Sprint S2 | Hari | 42924 | Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] - [Bouncebacks PR] |  |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35171 | 2024-01-26 | Allen | 2024-01-26 | Nil | Brian | 2024-01-26 | Nil | NA | NA | Closed | Completed
14 | 2.9 Sprint S2 | Hari | 42924 | Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] - [Bouncebacks PR] |  |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35188 | 2024-01-26 | Allen | 2024-01-26 | Nil | Brian | 2024-01-26 | Nil | NA | NA | Closed | Completed
15 | 2.9 Sprint S2 | Hari | 42924 | Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] - [Bouncebacks PR] |  |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35191 | 2024-01-26 | Allen | 2024-01-26 | Nil | Brian | 2024-01-26 | Nil | NA | NA | Closed | Completed
16 | 2.9 Sprint S2 | Hari | 42923 | Activities - Admin - Reports - Discount Summary Report - UI Section [2.9] [Bouncebacks PR] |  |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35228 | 2024-01-30 | Allen | 2024-01-30 | Nil | Brian |  | Nil | NA | NA | Closed | Completed
17 | 2.9 Sprint S2 | Hari | 43313 [Stretch] | Activities - District Settings - Hide Provider Info for non-HSS users [Bouncebacks PR] |  |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/35227 | 2024-01-30 | Allen | 2024-01-30 | Nil | Brian |  | Nil | NA | NA | Closed | Completed
18 | 2.9 Sprint S2 | Hari | 43335 [Stretch] | Admin - Replace "Server communicating message" with Spinning Loader | 2 sp |  | Done | Deva | Nil | [13 empty] | Development completed [moved to next sprint]
19 | 2.9 Sprint S2 | Hari | 43336 [Stretch] | Parent - Replace "Server communicating message" with Spinning Loader | 2 sp |  | Done | Deva | Nil | [13 empty] | Development completed [moved to next sprint]

## 2.9 Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 2.9 Sprint S2 | 22717 Activities - Admin - Fee Items - Registration: The Flat Rate entry is missing on the details page |  | Defect | For the Registration fee, the flat rate amount entry is missing on the details page while adding or editing. NOTE: Fix should do for Add and Edit | Minor | Internal | Open | Existing_Issues | Moved to next sprint | Found by Kanchana - PO
2 | 2.9 Sprint S2 | 22716 Activities - Admin - Fee Items - Late Pickup: The Flat/Hourly Rate entry is missing on the details page |  | Defect | For the late pickup fee, the flat and hourly amount entry is missing on the details page while adding or editing. | Minor | Internal | Open | Existing_Issues | Moved to next sprint | Found by Kanchana - PO
3 | 2.9 Sprint S2 | 22715 Activities - Admin - Fee Items - Retainer Fee: The Flat Amount entry is missing on the details page |  | Defect | For the retainer fee, the flat amount entry is missing on the details page while adding or editing. | Minor | Internal | Open | Existing_Issues | Moved to next sprint | Found by Kanchana - PO
4 | 2.9 Sprint S2 | 22713 Activities - Admin - Roles "Access" being changed to "Execute" on screen resize | Jeff | Defect | In admin if you resize the window while in the Roles edit section the word Access gets changed to Execute | Minor | External | Closed | Existing_Issues |  | Found by Jeff - Onshore QA
5 | 2.9 Sprint S2 | 42917 Activities - Admin - Record Transfer/Withdraw in Audit Log | Hari | Bounceback | When transferring out of an EP, in Enrollments audit log is only showing a withdraw not a transfer. (Image 2) | Minor | External | Closed | Requirements | Requirement missed | Found by Jeff - Onshore QA
6 | 2.9 Sprint S2 | 22676 Activities - Admin - Reporting Permissions Issue | Hari | Defect - Bounceback | When we use the URL below we should get a page similar to the below screenshot https://bnacare-qa.hssdev.com/T102/reports | Minor | External | Closed | Development | Develpoment team missed | Found by Jeff - Onshore QA
7 | 2.9 Sprint S2 | 22720 Activities - Admin - Audit - Report filtering not properly refreshing after selection |  | Defect | This defect will list the reports and the filters that are having an update issue after choosing a filter and then changing that filter to select all. Listed below are the reports, level, and filters facing this issue. | Minor | Internal | Open | Existing_Issues | Existing | Found by Johnson - Offshore QA
8 | 2.9 Sprint S2 | 42923 Activities - Admin - Reports - Discount Summary Report - UI Section | Hari | Bounceback | In Discount Summary page after adding invalid Sites, Enrollment plans and activities If User set filters that result in a "We are unable to pull information based on your reporting filters. Please try again." message for pdf and html, it should throw a "We are unable to pull information based on your reporting filters. Please try again." message when choosing excel with those same filters | Minor | Internal | Inprogress | Development | Develpoment team missed | Found by Johnson - Offshore QA
9 | 2.9 Sprint S2 | 42924 Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] | Hari | Bounceback | when the student has the discount removed/switched in student maint it is no longer counting them in the figures for the discount summary report | Minor | Internal | Inprogress | Development | Develpoment team missed | Found by Jeff - Onshore QA
10 | 2.9 Sprint S2 | 43313 Activities - District Settings - Hide Provider Info for non-HSS users | Hari | Bounceback | While logged in as a non-hss user I am still able to see provider info in the audit log | Minor | External | Closed | Development | Develpoment team missed | Found by Jeff - Onshore QA
11 | 2.9 Sprint S2 | 42924 Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] | Hari | Bounceback | but its now counting purchases instead of counting students. | Minor | External | Inprogress | Development | Develpoment team missed | Found by Jeff - Onshore QA
12 | 2.9 Sprint S2 | 42923 Activities - Admin - Reports - Discount Summary Report - UI Section [2.9] | Hari | Bounceback | Discount filter not worked as expected.This does not Discounts = choose the only discount shown and it converts to select all in the picker Discounts = choose a specific discounes to select multiple discount and it throws aan error. | Minor | Internal | Closed | Development | Develpoment team missed | Found by Johnson - Offshore QA
13 | 2.9 Sprint S2 | 42923 Activities - Admin - Reports - Discount Summary Report - UI Section [2.9] | Hari | Bounceback | Invalid Column name ="Discount Id" | Minor | External | Inprogress | Development | Develpoment team missed | Found by Jeff - Onshore QA
14 | 2.9 Sprint S2 | 42923 Activities - Admin - Reports - Discount Summary Report - UI Section [2.9] | Hari | Bounceback | found that the activities filter does nothing, it shows a list of activities but does not actually filter anything create an activity, but do not assign it to anything (EP/Term) click on the discount report choose that activity and run the report | Minor | External | Inprogress | Development | Develpoment team missed | Found by Jeff - Onshore QA
15 | 2.9 Sprint S2 | 43313 Activities - District Settings - Hide Provider Info for non-HSS users | Hari | Bounceback | found that the provider info was still showing on the details page if the user has the "Full Control" security role | Minor | External | Inprogress | Development | Develpoment team missed | Found by Jeff - Onshore QA

## 2.9 Sprint S1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | PR Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 2.9 Sprint S1 | Deva | 37677 | Activities - District Settings - Add audit log [2.9] | 5+2 =7 sp | 36 hrs | Completed | Hari | Nil | Hari | 1.Have a common method to toggle audit log mode | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34848 | 2024-01-04 | 2024-01-08 | Allen | Nil | Brian | 2024-01-10 | Nil | 1.Sub-records need spaces. 2.Old Value to New Value for (0 to 1) changed to True and False 3.Audit Log header is missing. 4.Passwords should be encrypted for Password field. | 1.maybe using the actual sub record name (that contains spaces and is easier to read) 2.make results easier to read that are showing up in json (ie: changes to the Fee ID and Fee Name) [ Added as follow up story] | Closed | Testing Completed
2 | 2.9 Sprint S1 | Hari | 22646 | Defect- Activities - Admin - generate advanced billing error |  | 4 hrs | Completed | Hari | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34797 | 2024-01-02 | 2024-01-03 | Allen | Nil | Brian | 2024-01-03 | Nil | NA | NA | Closed
3 | 2.9 Sprint S1 | Allen | 22653 | Activities - Admin - Fee Items - percentAmount variable does not error when negative value injected |  |  | Completed | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34868 | 2024-01-05 | 2024-01-08 | Allen | Nil | Brian | 2024-01-08 | Nil | NA | NA | Closed
4 | 2.9 Sprint S1 | Allen | 22655 | Activities - Admin - Fee Items - Visual bug for late payment details screen |  |  | Completed | Deva | Nil | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34857 | 2024-01-05 | 2024-01-05 | Allen | Nil | Brian | 2024-01-05 | Nil | NA | NA | Closed
5 | 2.9 Sprint S1 | Allen | 22655 and 22653 | Bounce back PR |  |  | Completed | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34868 | 2024-01-05 | 2024-01-05 | Allen | Nil | Brian | 2024-01-08 | Nil | NA | NA | Closed
6 | 2.9 Sprint S1 | Allen | 22642 | Activities - Admin - Accounting Page Visual Bug not Showing Single-Activity Name | 3 sp | 12 hrs | Completed | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34962 | 2024-01-11 | 2024-01-11 | Allen | Nil | Brian | 2024-01-12 | Nil | NA | NA | Inprogress | Testing Inprogress
7 | 2.9 Sprint S1 | Allen | 42923 | Activities - Admin - Reports - Discount Summary Report - UI Section [2.9] | 8+3 =11 sp | 35.5 hrs | Completed | Deva | 1. Getting Error after selecting Enrollment Plan 2. When selecting term level enrollment plan we should display only those EP instead of All Ep's. | Deva | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34981 | 2024-01-12 | 2024-01-16 | Allen | Nil | Brian | 2024-01-17 | 1.Do we not need the Criteria folder anymore? 2.Should this support select all like 3.Should this be singular or plural? 4.Is this needed? 5.Why was this changed? Seems like we aren't consistent here. 6.Is this needed anymore? | 1. Change the Date range name to Discount Date range. 2. Change the Output file name for Excel and PDF as per AC. 3. Discount date range validation message missing. Question to Kristy 4.For Excel, include a second tab or sheet in the Excel file for "Filter Info." Currently, we have done the report by allowing the report to be run without anything there and treating it as Select All, so in the report "Filter Info," we are showing blank for the filters (Sites, EP, Terms, Activity, Discounts) 5.Please check the labels (names) of the fields (like Site, Term, EP, Activity, and Discounts). 6.Subheader AC Point Questions: If all Sites, Terms, Enrollment Plans, Activities, or Discounts are listed in the subheader, skip that item (i.e., if all Sites, all Enrollment Plans, and all Activities are listed in the subheader: 3 Terms ¦ 4 Discounts),Do we need to skip the subheader if all selections are made in the report filter? | Kristy Feedback: 4.Blank works for the excel filter info if all are selected. 5.We can keep labels for reports as is for now - we can create a follow up story for a different release to update all report filters (the way they look in Hari’s pov is consistent with how the labels look for the registration report. 6.We can show the subheader like how Hari has it in his POV. We can strike through that point of AC to not show if all are selected. Client POV comments :I noticed one thing: It looks like there's a typo in the word Discounts (showing as Disounts) while displaying the total number of Discounts based on report filtering. I noticed that for both PDF and Excel. | Inprogress | PR need to review by Brian
8 | 2.9 Sprint S1 | Hari | 42924 | Activities - Admin - Reports - Discount Summary Report - Output Format section [2.9] | 8+5 =13 sp | 52 hrs | Completed | Deva | 1. If we give long descrition if will be overlaped. Please adjust | Deva | 1. Please give meaningfull name for code consistancy 2. Instead of Lengthy parameters make it QueryParams 3. Remove un used codes 4. No need to assign here | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34981 | 2024-01-12 | 2024-01-16 | Allen | Nil | Brian |  |  |  |  | Inprogress | PR need to review by Brian
9 | 2.9 Sprint S1 | Hari | 42917 | Activities - Admin - Record Transfer/Withdraw in Audit Log | 5 sp | 22 hrs | Completed | Deva | Nil | Deva | 1. Please make sure while push code to repository if the file only changed. 2. There is no changes in DBStudent file | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/34977 | 2024-01-12 | 2024-01-12 | Allen | Nil | Brian | 2024-01-13 | Nil | 1. Date and time format need to change in student enrollment page for date withdrawn 2.Sub record column is missed. | Nil | Inprogress | Testing Inprogress
10 | 2.9 Sprint S1 | Deva | 42989 | Activities - Mass Assign/Remove Discounts (Timeboxed) | 8 sp | 31 hrs | [15 empty] | Closed | Scope of this story is research and is completed

## 2.9 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments | Defect raised
1 | 2.9 Sprint S1 | 22642 Activities - Admin - Accounting Page Visual Bug not Showing Single-Activity Name | Allen Xavier | Defect | The Single-Activity is not being displayed in the Accounting-Payments section. The Single-Activity is being used in Enrollment plan. | Minor | Internal | Open | Existing_Issues |  | Found by Offshore PO - Kanchana
2 | 2.9 Sprint S1 | 22657 Activities - Admin - Fee Items - Percent amount being shown on General fee details page |  | Defect | Activities - Admin - Fee Items - Percent amount being shown on General fee details page | Minor | External | Open | Existing_Issues |  | Found by Onshore QA - Jeff.
3 | 2.9 Sprint S1 | 22653 Activities - Admin - Fee Items - percentAmount variable does not error when negative value injected | Allen Xavier | Defect | Return an error message anytime a negative value is injected into the percentAmount variable | Minor | External | Closed | Development |  | Found by Onshore QA - Jeff.
4 | 2.9 Sprint S1 | 22655 Activities - Admin - Fee Items - Visual bug for late payment details screen | Allen Xavier | Defect | There is a visual bug for fees set to late payment that is not showing values that have a decimal point on the details page for that fee. | Minor | External | Closed | Existing_Issues |  | Found by Onshore QA - Jeff.
5 | 2.9 Sprint S1 | 22646 Activities - Admin - generate advanced billing error | Hariharan | Defect | It looks like the batch details page was deleted while cleaning up the react conversion pages and needs added back in | Significant | External | Closed | Development |  | Found by Onshore QA - Jeff.
6 | 2.9 Sprint S1 | 22585 Activities - Admin - Invoice Payment Summary performance issue |  | Defect | When loading the Invoice Payment Summary in QA it is taking 1-1.5 minutes to load the page. | Significant | External | Open | Development | Rejected | Found by Onshore QA - Jeff.
7 | 2.9 Sprint S1 | 22676 Activities - Admin - Reporting Permissions Issue | Hariharan | Defect | There is an issue with the Reporting permissions in production. Despite the "Run Reports" permission being set to allow, the Reports section is not showing up on the left nav menu when set at the Site Level | Major | External | Open | Existing_Issues |  | Client Found this
8 | 2.9 Sprint S1 | 22682 Activities - Admin - Term Maintenance Permissions Issue | Hariharan | Defect | There is an issue with the Term Maintenance permissions in production. Despite the "Add, Edit, Delete" permission being set to allow, the Terms section is not showing the "Add, Edit Delete" at the Site Level. | Significant | External | Closed | Existing_Issues |  | Client Found this

## Checklist (hidden)
Code Review Comments received from Client for 2.5 Sprint |  | S No | Execution Steps | Status
1 | index.tsx /AugustWeb/Features/ContactMaintenance/Components/index.tsx Search doesn't work on the details page. Please remove the search component from the header. | 1 | Code conflict | FALSE
2 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs If the admin doesn't set up any of the new options, then the system rejects every registration. | 2 | Coding Standard | FALSE
3 | PickEnrollmentPlanView.tsx /ParentWeb/ClientApp/src/pages/Registration/PickEnrollmentPlanView.tsx This should be filtered before this ternary statement so the "No enrollment plans" message could be shown if all plans are at capacity and closed. | 3 | Existing Functionality | FALSE
4 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs Could we add a TermEnrollmentPlanId query parameter and query for it directly instead of pulling all the plans for the term? | 4 | Acceptance Criteria coverage | FALSE
|  | 5 | Code execute | FALSE
|  | 6 | Code Performance | FALSE
|  | 7 | Code cleanup | FALSE
|  | 8 | Understandable code comments | FALSE

## Details (hidden)
Root Cause category
Enhancements
Existing_Issues
Requirements
QA
Design
Documentation
Development
Project_Management
Environment_Related

## Temp
2.9 Sprint 2
Story # | Status | CRC # | Bouncebacks # | Comments
42917 | Completed | Nil | Nil
43289 | Completed | 1 | Nil
22682 | Completed | Nil | Nil
22676 | Completed | Nil | 1
22657 | Completed | 1 | Nil
22642 | Completed | Nil | Nil
43155 | Testing pending from onshore | Nil | Nil | Main commit
42924 | Pending BB PR Approval Brian | Nil | 2 | Main commit
42923 | Pending BB PR Approval Brian | Nil | 4 | Main commit
43313 | Pending BB PR Approval Brian | 2 | 3 | Stretch

## Settings
Story Completed
Story Being Tested
Story Ready For Testing
Story Peer Review
Product Owner - Verify
Story Being Developed
Story Approved
Defect Found
Defect Verified
Defect Being Fixed
Defect Peer Review
Product Owner - Verify
Defect Ready For Testing
Defect Being Tested
Defect Fixed
Defect Rejected
Defect Needs More Info
Defect Blocked

## ExportData
1 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 Stretch | Allen | 46160 | Activities - Admin - Term - Capture Attendance Calendar modifications in Audit Log (Timeboxed) [3.6] | Story Completed | 3 | 3 |  | Hari | Kaliammal | Full Calendar toggle value not tracked on initial add | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40084 | 45642 | [6 empty] | When Weekly calendar enrollment plan is set to weekly but in activity we changed to daily calendar it will throw message and wont allow to save but in audit log it capture both logs
2 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 | Hari | 39396 | Activities - SYSTEM - Admin Home - Update to React (Dev Only) [3.6] | Story Completed | 8 | 8 |  | Hari | Kaliammal | Nil | Kaliammal | Nil
3 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 | Kaliammal | 42050 | Activities - SYSTEM - Heartland Staff/Manage Users - Update to React (Dev Only) [3.6] | Story Completed | 5 | 8 |  | Done | Hari | 1.Inactive users are being listed without Show Inactive Users selected 2.Unable to change the username and role in editPage using Role Dropdown 3.Username field is disabled in dev environment, we should disable username 4.We are displaying the user name whom we are deleting in the delete confirmation popup, Refer Setup => Users => Delete 5.We don't have Tabs in existing Staff details page, discuss with kanchana regarding this | Hari | 1.Return as JsonResult instead of IActionResult for all API 2.Two methods calling same API, make use of one and remove the another one 3.We don't need multipart/form-data and getFormData payload if we are not going to upload any files 4.Remove unused imports AuditLog and AuditLogModel and console logs line number 46 5.Remove FileUploadRef in EditStaffUser component and console logs in saveStaffUser function 6.Are we using this newly defined property SystemRole? If not we can remove this
4 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 | Hari | 42051 | Activities - SYSTEM - Heartland Staff/Districts - Update to React (Dev Only) [3.6] | Story Completed | 8 | 8 |  |  | Kaliammal | Nil | Kaliammal | Nil
5 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 | Allen | 24354 | Activities - Admin - Term Maintenance - Handle Validation Message while adding Enrollment Plan | Defect Fixed | 3 | 3 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/39952 | 45630 | 45630 | Done | Nil | Done | 45630 | Nil | NA | NA
6 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 Stretch | Allen | 46579 | Activities - Enrollment Plan/Activity - Update "Description" to Item Name in SQL Tables (SYSTEM) [3.6] dev only | Story Completed | 8 | 8 |  | Done | Hari | Nil | Hari | Nil
7 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 Stretch | Hari | 46726 | Activities - SYSTEM - Expanded Admin Date Selector Calendar Overlay [3.6] | Story Completed | 2 | 2 |  | Done | Kaliammal | Nil | Kaliammal | Nil
8 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 Stretch | Allen | 24373 | Activities - Admin - Modification to Fee Item is not reflected Immediately in Grid | Defect Fixed | 2 | 2 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40046 | 45637 | 45637 | Done | Nil | Done | 45637 | Nil | NA | NA
9 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 Stretch | Allen | 46722 | Activities - Term/Site - Update "Description" to Item Name in SQL Tables (SYSTEM) [3.6] dev only | Story Completed | 5 | 5 |  | Done | [14 empty] | Peer test, POV, PR and QA - Moved to next sprint
10 | MSB Activities | 45952 | 45965 | 3.5 Sprint S4 Stretch | Kaliammal | 44087 | Activities - Admin - Update Students page to Server Side sorting [3.6] dev only | Story Completed | 3 | 3 |  | Done | [14 empty] | Peer test, POV, PR and QA - Moved to next sprint
1 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Hari | 46834 | Activities - SYSTEM - Expanded Admin Date Selector Calendar Overlay (POV, PR & QA) | Story Completed | 2 | 2 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40210 | 45664 | 45665 | Done | Nil | Done | 45665 | Nil | Approved | Approved
2 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Hari | 24409 | Activities - Admin - Prepaid Billing Used Instead of Drop In (Fuzzy Logic) (Fairbanks) | Defect Fixed | 5 | 8 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40257 | 45666 | 45671 | Done | Write common logic to handle DateWithdrawn | Done | 45671 | I think this change in logic may have unintended consequences, if we are comparing two inactive enrollments we would no longer favor prepaid over dropin. I think we may want to instead consider just bumping up the score associated with active vs withdrawn to make it the most important factor. Perhaps making enrolled plans worth 5000? | NA | NA
| MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Hari | 38370 | Activities - Split Billing - Add Audit Log | Story Ready For Testing | 2 | 4 |  | Done | Kaliammal | Nil | Kaliammal | Remove calender fix | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40238 | 45665 | 45671 | Done | Nil | Done | 45671 | Nil | Approved | Approved | Moved to next sprint - For Testing Reason : PR Held by Onsite QA
4 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Kaliammal | 44087 | Activities - Admin - Update Students page to Server Side sorting | Story Completed | 1 | 3 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40233 | 45665 | 45665 | Done | Nil | Done | 45666 | Nil | NA | NA
5 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Kaliammal | 44087 Bounceback | Activities - Admin - Update Students page to Server Side sorting | Story Completed |  |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40280 | 45667
6 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Hari | 46818 | Activities - SYSTEM - Admin Home - Update to React (POV, PR & QA) | Story Completed | 2 | 4 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40198 | 45663 | 45663 | Done | Nil | Done | 45665 | Nil | NA | NA
7 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Hari | 46818 Bounce Back | Activities - SYSTEM - Admin Home - Update to React (POV, PR & QA) | Story Completed |  |  |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40279 | 45667
8 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Hari | 46832 | Activities - Admin - Term - Capture Attendance Calendar modifications in Audit Log (PR & QA) | Story Completed | 1 | 1 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40084 | 45642 | 45656 | Done | Nil | Done | 45665 | Nil | When Weekly calendar enrollment plan is set to weekly but in activity we changed to daily calendar it will throw message and wont allow to save but in audit log it capture both logs Approved | Approved
9 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 | Hari | 24452 | Activities - Admin - Term filter tree selector for dynamic report generator works incorrectly for active and inactive Terms [3.5] | Defect Fixed | 1 | 4 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40197 | 45663 | 45664 | Done | Nil | Done | 45664 | Nil | NA | NA
10 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 Stretch | Allen | 46830 | Activities - Term/Site - Update "Description" to Item Name in SQL Tables (SYSTEM) [POV, PR & QA] | Story Peer Review | 3 | 3 |  | Done | Hari | Change Description to EnrollmentPlanName in the payload of bulk edit and bulk copy | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40267 | 45666 | [8 empty] | Client Dev Manager - Hold this story. Reason: Contains DataBase Column Name Changes - Slated for 3.7 release
11 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 Stretch | Allen | 46831 | Activities - Enrollment Plan/Activity - Update "Description" to Item Name in SQL Tables (SYSTEM) [POV, PR & QA] | Story Peer Review | 3 | 3 | [16 empty] | Client Dev Manager - Hold this story. Reason: Contains DataBase Column Name Changes - Slated for 3.7 release
12 | MSB Activities | 45660 | 45671 | 3.6 Sprint S1 Stretch | Kaliammal | 45506 | Activities - Admin - Enrollment Plan - Update "Required Forms" page with Sorting and Pagination | Story Ready For Testing | 3 |  |  | Done | Kaliammal | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40284 | 45667 | 45670 | Done | Nil | Done | 45671 | Nil | Mode - M should be caps. Per AC Validation for the required form modal up - Missing. | Approved | Moved to next sprint - For Testing
1 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Kaliammal | 46343 | Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) | Story Being Tested | 13 | 14 |  | Done | Hari | 1.When Selecting Approved and Updated status, getting server error | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40461 | 45680 | 45680 | Done | Nil | Done | 45680 | Nil | 1. Registration status: Pending, and I have updated that pending registration stock fields for parents and contacts are not yet approved in the updated registration. While running the report, the pending registration fields were updated. 2. Need space after comma for each registration status. 3. All selected - It should be blank in excel filter info page. 4.We have one scenario for updated registration status if the parent updated only the schedule and forms section, and in that scenario, if we run the report for updated status, it won't show italic font for updated status because there won't be any changes for custom fields.Question: Do we still need to run the updated registration for the above scenario, or do we need to restrict it? Please confirm. 5.Sheet mismatch based on the registration status filter chosen. 6. If there is no data for any one of the registration statuses (Approved, Pending) we have chosen Excel info - We are showing the registration status as Approved, Pending but we are not showing the sheet for no data in Excel. | Approved | Development completed, Testing In progress. Will be Carried forward to next sprint for Testing.Data fetching and lot of testing scenarios , it took more efforts.
2 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Allen | 46828 | Activities - RESEARCH - Enrollment Plan - Selected Actions/Run Bulk Actions in the Background [V2] | Story Completed | 5 | 8
3 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Hari | 24494 | Activities - Admin - Calendar allowing headers through the calendar | Defect Fixed | 2 | 2 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40320 | 45673 | 45673 | Done | Nil | Done | 45673 | Q&A - Does this actually change the functionality at all? I may be missing something, but it is already set to Position.Bottom prior to the if (rect.bottom > 400) | NA | NA
4 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Hari | 46408 | Activities - Admin - District Level View of Open Operating Days | Story Completed | 5 | 5 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40394 | 45678 | 45678 | Done | Nil | Done | 45679 | Nil | 1.Number of sites count shown wrongly. 2. Reopen Day count is not considered for sites. Approved | Approved
5 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Allen | 45709 | Activities - Admin - Show Site with Term Name in Disable Enrollment Plan Validation | Story Completed | 1 | 2 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40356 | 45673 | 45673 | Done | Nil | Done | 45673 | Nil | Approved | Approved | Offshore and Onshore QA timelog collectively increased actual hours
6 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Hari | 38370 [Bounceback] | Activities - Split Billing - Add Audit Log [Bounceback] | Story Completed | 1 | 6 |  | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40347 | 45673 | 45678 | Done | Nil | Done | 45679 | UI Representation: Can we adjust this to match the following formatting: Field: Split Billing - Contact Removed Subrecord: [Contact Name] Old Value: N/A New Value N/A | NA | NA | Made changes in the code logic in the way of displaying Split billing in the Audit log which increased development effort
7 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Kaliammal | 45506 | Activities - Admin - Enrollment Plan - Update "Required Forms" page with Sorting and Pagination | Story Completed | 2 | 8 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40284 | 45667 | 45670 | Done | Nil | Done | 45672 | Nil | Pagination is not working when we search for anything on the second page and clear it. | Approved | I faced some challenges maintaining data because I converted the HTML table to a data table.so it took more story point.
8 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Kaliammal | 46819 | Activities - SYSTEM - Heartland Staff/Manage Users - Update to React (POV, PR & QA) | Story Completed | 2 | 4 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40364 | 45674 | 45674 | Done | Nil | Done | 45674 | Nil | NA | NA | Offshore and Onshore QA timelog collectively increased actual hours
9 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 | Hari | 46820 | Activities - SYSTEM - Heartland Staff/Districts - Update to React (POV, PR & QA) | Story Completed | 2 | 5 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40342 | 45673 | 45678 | Done | Nil | Done | 45678 | Nil | NA | NA | Offshore and Onshore QA timelog collectively increased actual hours
10 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 Stretch | Hari | 46967 | Activities - SYSTEM - Districts/Job Requests/Data - Update to React | Story Completed | 3 | 3 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40342 | 45673 | 45678 | Done | Nil | Done | 45678 | Nil | 1.While run the Schedule Withdraw/Transfer jon it redirect to registration notification job (wrong job request) | NA
11 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 Stretch | Hari | 46555 | Activities - MSB Invoice Profile - Remove filter by Provider for GL Codes | Story Completed | 3 | 3 |  | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40470 | 45681 | 45681 | Done | Nil | Done | 45681 | Nil | Approved | Approved
12 | MSB Activities | 45672 | 45685 | 3.6 Sprint S2 Stretch | Allen | 24529 | Activities - Admin - Operating Day - Check Out Errors | Defect Fixed | 2 | 4 |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40469 | 45681 | 45681 | Done | Nil | Done | 45681 | Nil | NA | NA
1 | MSB Activities | 45686 | 45699 | 3.6 Sprint S3 | Hari | 24552 | Activities - Admin - Report - Contacts are missing in custom registration report for excel format | Defect Fixed | 3 | 3 | 6 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40549 | 45686 | 45686 | Done | Nil | Done | 45686 | Nil | NA | NA
2 | MSB Activities | 45686 | 45699 | 3.6 Sprint S3 | Kaliammal | 46343 | Activities - Custom Registration Report - Filter by Registration Status (Seminole & Albermarle) [bounceback] | Story Completed | 5 | 5 | 11 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40529 | 45685 | 45685 | Done | Nil | Done | 45686 | Nil | NA | NA
3 | MSB Activities | 45686 | 45699 | 3.6 Sprint S3 | Hari | 24328 | Activities - Admin - Fix 'Register/Continue/Submit Registration' button in Manual Registration [3.6*] | Defect Fixed | 3 | 3 | 10 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40550 | 45686 | 45686 | Done | Nil | Done | 45688 | Nil | NA | NA
4 | MSB Activities | 45686 | 45699 | 3.6 Sprint S3 | Kaliammal | 47010 | Activities - Admin - Custom Registration Report - Show Italic font for Updated Status Data for Output Format | Story Completed | 1 | 4 | 16 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40553 | 45686 | 45687 | Done | Optimize two line string opertion to one line. | Done | 45688 | Nil | 1.Contact fields are not bold, italics for the updated registration section in PDF, Excel, and HTML 2.Could not see the same header text message in Excel format [*Updates Pending Admin Approval] | Approved | Took more effort to fix bounce back.
5 | MSB Activities | 45686 | 45699 | 3.6 Sprint S3 | Allen | 47045 | Activities - SYSTEM - Performance Improvements for Enrollment Plan Selected Actions [3.7] (dev only) | Story Completed | 8 | 8 | 35
6 | MSB Activities | 45686 | 45699 | 3.6 Sprint S3 Stretch | Kaliammal | 46724 | Activities - Security Group/Kiosk/District Maintenance - Update "Description" to Item Name in SQL Tables (SYSTEM) [3.7] | Story Completed | 5 | 9 | 36 | [15 empty] | Faced challenges while converting Table column from Description to DistrictName for Tenant Table due to its dependency in the Cache
7 | MSB Activities | 45686 | 45699 | 3.6 Sprint S3 Stretch | Allen | 46725 | Activities - Custom Fields/Dynamic Reports - Update "Description" to Item Name in SQL Tables (System) [3.7] | Story Completed | 5 | 5 | 20
1 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 | Allen | 47187 | Activities - SYSTEM - Performance Improvements for Enrollment Plan Bulk Copy (PR & QA) | Story Completed | 3 | 4 | 15 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40738 | 45700 | 45700 | Done | Nil | Done | 45702 | Nil | NA | NA
2 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 | Kaliammal | 24618 | Activities - Admin - Custom Report - Hide Custom Field Answer for Updated status if their previous selection was removed | Defect Fixed | 5 | 5 | 19 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40796 | 45705 | 45705 | Done | Nil | Done | 45705 | Nil | NA | NA
3 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 | Hari | 46968 | Activities - Parent Accounts - Customizable Column Headers | Story Completed | 5 | 6 | 22.5 |  | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40827 | 45706 | 45707 | Done | Nil | Andy | 45708 | 1.Should these have changed? 2.Shouldn't this be GridID.ParentAccountsNoSiteSelected or GridID.ParentAccountsSiteSelected ? (Suggestions) | 1.Getting server error "Invalid Column Name" while viewing the district-level view of people. 2.When a site is selected, the student list should be based on the site level. Currently, it is displayed based on the district level of students. 3.User selection sessions are not maintained for students' and parents accounts for site-level and district-level 4.District level - Students are not listed based on their site level. | Approved
4 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 | Allen | 46831 | Activities - Enrollment Plan/Activity - Update "Description" to Item Name in SQL Tables (SYSTEM) | Story Completed | 5 | 5 | 20.5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40803 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40837 | 45706 | 45706 | Done | Nil | Done | 45706 | Nil | 1.In the Enrollment plan view section: The student, Parents, and Contacts fields are displayed blank. 2.Activity name is showing blank in Pin Maintenance. | NA
5 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 | Kaliammal | 47188 | Activities - Security Group/Kiosk/District Maintenance - Update "Description" to Item Name in SQL Tables (SYSTEM) | Story Completed | 5 | 5 | 22 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40800 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40797 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40874 | 45705 | 45705 | Done | Nil | Done | 45705 | NIL | POV Completed. 1. While logged in as HSS user, getting error Invalid Column name "District Name". 2. Modal message is missing for all Jobs tools. 3. System Volume report shows errors like Invalid Column 'District Name'. 4. Modal message is missing for all Jobs tools. 5. System Volume report shows errors like Invalid Column 'District Name'. | NA
6 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 Stretch | Allen | 47163 | Activities - SYSTEM - Performance Improvements for Enrollment Plan Bulk Edit [Dev only] | Story Completed | 8 | 8 | 34 | [13 empty] | NA | NA
7 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 Stretch | Hari | 24691 | Activities - Admin - Enrollment Plan - 'Selected Actions' dropdown is enabled if no Enrollment Plans are selected | Defect Fixed | 1 | 1 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40824 | 45706 | 45706 | Done | Nil | Done | 45707 | NIL | NA | NA
8 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 Stretch | Kaliammal | 23975 | Activities - Parent - Contacts - Accept First and Last Name Field without a Space | Defect Fixed | 2 | 2 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40820 | 45706 | 45706 | Done | Nil | Done | 45713 | NIL | NA | NA
9 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 Stretch | Kaliammal | 47246 | Activities - Admin - Enrollment Plan - Update Verbiage | Story Completed | 1 | 1 | 1 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40887 | 45709 | 45713 | Done | Nil | Done | 45713 | NIL | Approved | Approved
10 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 Stretch | Hari | 47182 | Activities - Custom Fields/Dynamic Reports - Update "Description" to Item Name in SQL Tables (SYSTEM) *final | Story Peer Review | 5 |  |  | Done | Hari | Nil | Hari | Nil | [8 empty] | Custom Fields POV completed. | NA | Moved to Regression sprint for PR .
11 | MSB Activities | 45700 | 45713 | 3.7 Sprint S1 Stretch | Allen | 46830 | Activities - Term/Site - Update "Description" to Item Name in SQL Tables (SYSTEM) | Story Peer Review | 5 |  |  | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40853 | 45707 | [6 empty] | 1.Term name showing 'Undefined' in operating days - Activity session. 2.In the users section, the Default site drop-down list shows blank. 3.Bulk enrollment - JSON file needs to change for Description to corresponding item name( activities, enrollment plan, and Term). POV Completed | NA
1 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 | Allen | 46830 | Activities - Term/Site - Update "Description" to Item Name in SQL Tables (SYSTEM) | Story Completed | 5 | 6 | 24 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40853 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41083 | 45707 | 45722 | Done | Nil | Andy [Done] | 45722 | I think this should be IS NOT NULL? If the column was just added, we'll be missing the constraint that was added above when the table is originally added. I think we need to conditionally add the UK_SITE_Name constraint here if the column exists but the constraint does not Missing BEGIN after IF Suggestions: I think this comment is left from the old process, can we remove or update it to reflect the new approach The constraint name being added here doesn't match the name used below (UK_SITENAME) so it will be added a second time | NA | NA
2 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 | Allen | 47322 | Activities - Setup - Update icons, text position, and order for tiles | Story Completed | 3 | 3 | 10 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41007 | 45715 | 45715 | Done | Nil | Done | 45715 | Nil | Approved | Please increase the size of the icons, decrease padding between the icon and the header, Update Event Payment Profiles tile name to "Events"
3 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 Stretch | Allen | 47261 | Activities - Setup - Dynamically Assign Page Icons based on Page Section | Story Completed | 5 | 5 | 21 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41007 | 45715 | 45715 | Done | Nil | Done | 45715 | Nil | 1. Old icon is displayed for Pin Maintenance at header section | Approved
4 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 | Kaliammal | 47325 | Activities - Custom Registration Report - Include Student Number for Output Format (Albemarle) | Story Completed | 5 | 5 | 18 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41068 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41095 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41110 | 45720 | 45720 | Done | Nil | Done | 45720 | Nil | Approved 1.Tree selection count is displayed wrongly for student stock fields. 2.Once we clicked the select all, default Student Fields > Stock > First Name, Last Name and Student# fields are able to select. | POV Comment: Requirement:If we are able to, we should make: - The Student Fields > Stock > First Name and Last Name fields selected and disable them/prevent them from being deselected (since we are always showing those on the Report). - Consider adding "Student #" to the Student Fields > Stock Fields list (below Last Name) and have this selected, and prevent the field from being deselected (since it will always appear on the Report) - If the user tries to click the x on the First Name, Late Name, or Student # fields below the Student Fields dropdown, we should show the following text "Always included in Report Output" Please let Kristy and Kanchana know if a separate story is needed for this ^
5 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 | Kaliammal | 24727 | Activities -Custom Report - Delete/Add Contact-Hide Custom Field Answer for Updated status if their previous selection was removed [PR &QA] | Defect Fixed | 3 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40940 | 45713 | 45719 | Done | Optimize the code for data table changes | Done | 45719 | NIl | NA | NA
6 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 | Hari | 46969 | Activities - Other Contacts - Customizable Column Headers | Story Completed | 5 | 5 | 20 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41062 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41099 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41138 | 45720 | 45720 | Done | Nil | Done | 45720 | Nil | Approved | Approved
7 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 | Allen | 47348 | Activities - SYSTEM - Performance Improvements for Enrollment Plan Bulk Edit [PR &QA] | Story Completed | 2 | 2 | 7 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/40959 | 45714 | 45714 | Done | Nil | Done | 45715 | Nil | NA | NA
8 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 Stretch | Allen | 24763 | Activities - Admin - Roles - 'Description' text missing for Stock Roles | Defect Fixed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41034 | 45716 | 45716 | Done | Nil | Done | 45716 | Nil | NA | NA
9 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 Stretch | Kaliammal | 24712 | Activities - Admin- Pending/Waitlist Registrations - Editing a Contact showing another contact's custom field information | Defect Fixed | 3 | 3 | 9 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41096 | 45721 | 45721 | Done | Nil | Done | 45721 | Nil | NA | NA
10 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 Stretch | Hari | 24718 | Activities - Admin - Student Enrollment - Edit Schedules [Daily/Weekly] Validation Message is not cleared | Defect Fixed | 2 | 2 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41113 | 45722 | 45723 | Done | Nil | Done | 45723 | Nil | NA | NA
11 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 Stretch | Allen | 47424 | Activites - Admin - Selected Actions - Data Table Insert for Bulk Copy | Story Completed | 1 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41092 | 45721 | 45721 | Done | Nil | Done | 45721 | Nil | NA | NA
12 | MSB Activities | 45714 | 45727 | 3.7 Sprint S2 Stretch | Allen | 47422 | Activities - Admin - Search ''Parent Account'' for Other Contacts Customizable Column | Story Peer Review | 5 |  |  | Done | Hari | Nil | Hari | Nil | [10 empty] | Carried to next sprint for Client PR and Testing.
1 | MSB Activities | 45727 | 45741 | 3.7 Sprint S3 | Hari | 47083 | Activities - RESEARCH - Split Billing Improvements | Story Completed | 8 | 8 | 32 | [13 empty] | NA | NA
2 | MSB Activities | 45727 | 45741 | 3.7 Sprint S3 | Allen | 47422 | Activities - Admin - Performance Improvements, Search, Sorting ''Parent Account'' column in Parent/Other Contacts Grids [PR and QA] | Story Completed | 2 | 5 | 19 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41167 | 45727 | 45727 | Done | Nil | Andy | 45727 | The filter text needs to be parameterized to prevent against SQL injection | NA | NA | Discussed Multiple Approaches with Client and Decided suitable solution for this release took more effort than the initial estimate
3 | MSB Activities | 45727 | 45741 | 3.7 Sprint S3 | Allen | 46723 | Activities - Fees/Discounts/Forms - Update "Description" to Item Name in SQL Tables (System) [Dev Only - 3.8] | Story Completed | 5 | 6 | 26 | Done | Kaliammal | Nil | Kaliammal | Nil | [8 empty] | NA | NA
4 | MSB Activities | 45727 | 45741 | 3.7 Sprint S3 Stretch | Kaliammal | 47182 | Activities - Custom Fields/Dynamic Reports - Update "Description" to Item Name in SQL Tables (SYSTEM) *final [3.8] | Story Completed | 5 | 5 | 20 | Done | Hari | Nil | Hari | Nil | [8 empty] | NA | NA
5 | MSB Activities | 45727 | 45741 | 3.7 Sprint S3 Stretch | Kaliammal | 47540 | Activities - SYSTEM - Apply Background Color to Selected Actions Page [3.7] | Story Completed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41275 | 45734 | 45735 | Done | Nil | Done | 45735 | Nil | NA | NA
6 | MSB Activities | 45727 | 45741 | 3.7 Sprint S3 Stretch | Hari | 47462 | Activities - SYSTEM - Show 'Total Count' of Table Grid Entries with Pagination [3.8] | Story Peer Review | 5 |  |  | Done | Kaliammal | Nil | Kaliammal | NIl | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41383 | 45741 | [6 empty] | NA | NA
1 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 | Allen | 47685 | Activities - Admin - Split Billing - Link MSB User ID/Login ID to Split Billing Contacts [Dev & PR] | Story Being Developed | 8 | 8 | 33 | Done | Hari | Nil | Hari | Nil | [8 empty] | 1.For existing split billing: once we enable config props -It automatically fetches the email address for the parent account (actually, it will fetch based on the MSB user account). 2. The first time, I enabled split billing for a student. For the parent, it first fetched the email address instead of the user account. 3.If not set selected in the drop-down—user account/email not clearing. 4. Search for any characters like TESTA,It is retained in the search box and not clearing the value, still able to update it and save. 5.If the retained user email/account in the search box matches with other contacts . After saving, it matches with the proper email address. 6. The previous selection notification is not showing. 7. Invoice part does not work as expected in MSB. 8. Contact page UI drop down - we can remove "Email" text because we are not matching with email | 1. I think once an MSB user is selected for one of the split billing contacts for that student, we should not show that msb user as an option/disable that option for additional split billing contacts (can't have one msb user linked to 2 separate split billing contacts for the same student)
2 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 | Allen | 47686 | Activities - Fees/Discounts/Forms - Update "Description" to Item Name in SQL Tables (System) [PR & QA - 3.8] | Story Completed | 5 | 8 | 30 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41304 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41247 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41382 | 45741 | 45741 | Done | Nil | Done | 45742 | Nil | NA | NA
3 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 | Allen | 47182 | Activities - Custom Fields/Dynamic Reports - Update "Description" to Item Name in SQL Tables (SYSTEM) *final [3.8] | Story Completed | 8 | 8 | 33 | [5 empty] | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41217 | 45747 | 45747 | Done | Nil | Done | 45748 | Nil | NA | NA
4 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 | Hari | 47250 | Activities - Admin - Enrollment Plan - Student, Parent, and Contacts Fields >Stock & Custom Fields > Multi-Selection | Story Completed | 8 | 8 | 30 | Done | Kaliammal | 1) Remove one field ,all fields are removed. 2) click Enrollment Plan-Custom fields, page got refreshed and details are cleared. 3)Remove saved fields and not enable in left side. | Kaliammal | Remove unused icon, | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41527 | 45748 | 45749 | Done | Nil | Done | 45750 | Nil | 1. Ok button disable. 2.Required field should be disable. 3.Add Field(s) button should display at the right corner. | Approved
5 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 | Kaliammal | 47418 | Activities - Reports - Update Tile Layout and Icons | Story Completed | 3 | 3 | 14 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41524?_a=updates | 45748 | 45750 | Done | Some Alignment of tile mismatch. | Nil | 45751 | Nil | Suggested increasing the size of the report name text within the tile (like we have for the Setup page) - . | Approved Kristy agreed the suggestions, provided by Kanchana. Kanchana suggested increasing the size of the report name text within the tile (like we have for the Setup page) - I agree. If we can, we should make it so that the icons and description text within the Reports tiles always are in line with each other (even if one report name takes up 2 lines while another only takes up 1 line).
6 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 | Kaliammal | 47393 | Activities - Admin - Update User Menu Options | Story Completed | 3 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41456 | 45744 | 45748 | Nil | Nil | Nil | 45748 | Nil | 1.Profile icon size is not fit the screen. 2. Show firstname,last name for user profile icon. | Approved
7 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 | Allen | 47462 | Activities - SYSTEM - Show 'Total Count' of Table Grid Entries with Pagination [PR & QA] | Story Completed | 1 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41383 Bounce PR: https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41451 | 45741 | 45742 | Done | Nil | Done | 45742 | Nil | 1. The Selected Actions table grid total count missing. 2. A few pages show 1 to 0 of 0 records (if there is no data in the table grid). | Approved
8 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 Stretch | Hari | 47750 | Activities - Enrollment Plans - Convert Custom Field toggles to tabs and display selected count | Story Peer Review | 3 | 3 | 12 | Done | Allen | Nil | Allen | Nil | [8 empty] | 1.Bold missing for this AC point- if >1 custom fields are selected for that type, show as the number in parentheses bolded. ie: (#) | Approved | Carried to Next sprint for PR and QA
9 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 Stretch | Kaliammal | 45905 | Activities - Admin - Reports - Improve Student Filter Multi-Select dropdowns | Product Owner - Verify | 5 | 5 | 20 | Done | Hari | On hover, subtext label and value is not visible | Hari | remove isSubTextMode from IProps since it is not used | [8 empty] | Pending | Pending | Carried to Next sprint for POV, PR and QA
10 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 Stretch | Allen | 47331 | Activities - Central Office Role - Selected Actions Bulk Edit | Product Owner - Verify | 2 | 1 | 2 | Done | Hari | Nil | Hari | Nil | [8 empty] | Did the initial POV. Selected Actions—Edit not show in the drop-down list of the enrollment plan if the user was assigned to the central office role | Pending | Carried to Next sprint for POV, PR and QA
11 | MSB Activities | 45742 | 45755 | 3.8 Sprint S1 Stretch | Allen | 46980 | Activities - Parent - Update Submit Page" Student" Labels | Product Owner - Verify | 3 | 1 | 2 | Done | Kaliammal | Nil | Kaliammal | Nil | [8 empty] | Pending | Pending | Carried to Next sprint for POV, PR and QA
1 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 | Kaliammal | 45905 | Activities - Admin - Reports - Improve Student Filter Multi-Select dropdowns | Story Completed | 2 | 2 | 8 | Done | Hari | On hover, subtext label and value is not visible | Hari | remove isSubTextMode from IProps since it is not used | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41564 | 45756 | 45756 | Done | Nil | Andy |  | On this line we're modifying the value in props.student, props should be immutable in react. Can we create a new array that we'll populate from what we have received from the prop and update that instead? | 1. If no student is available based on the selection made we should display the same message "No Students Are Available" - Missed | Approved
2 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 | Allen | 46980 | Activities - Parent - Update Submit Page" Student" Labels | Story Completed | 1 | 1.25 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41722 | 45761 | 45761 | Done | Nil | Done | 45762 | Nil | Given Suggestions: To have Field name should start with Caps for contact, activity schedule, and forms | Pending
3 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 | Allen | 47331 | Activities - Central Office Role - Selected Actions Bulk Edit | Story Completed | 1 | 1.5 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41662 | 45756 | 45756 | Done | Nil | Done | 45756 | Nil | "Did the initial POV. Selected Actions—Edit not show in the drop-down list of the enrollment plan if the user was assigned to the central office role" - Fixed Approved | Approved
4 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 | Allen | 47750 | Activities - Enrollment Plans - Convert Custom Field toggles to tabs and display selected count | Story Completed | 2 | 2 | 8 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41635 | 45755 | 45755 | Done | Nil | Done | 45756 | Nil | 1.Bold missing for this AC point- if >1 custom fields are selected for that type, show as the number in parentheses bolded. ie: (#) - pov comment fixed. Approved | Approved
5 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 | Allen | 47685 | Activities - Admin - Split Billing Updates | Story Being Tested | 13 | 0 | 0 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41661 | 45756 | 45756 | Done | Nil | Done | 45756 | We're able to have more than one contact with the relationship type of parent, by doing FirstOrDefault on contacts that are contact type Primary or relationship type Parent, don't we open ourselves up to having multiple contacts that fit and picking one arbitrarily? Should we be looking only at primary contact? I may be misunderstanding the intent here. | 1.For existing split billing: once we enable config props -It automatically fetches the email address for the parent account (actually, it will fetch based on the MSB user account). 2. The first time, I enabled split billing for a student. For the parent, it first fetched the email address instead of the user account. 3.If not set selected in the drop-down—user account/email not clearing. 4. Search for any characters like TESTA,It is retained in the search box and not clearing the value, still able to update it and save. 5.If the retained user email/account in the search box matches with other contacts . After saving, it matches with the proper email address. 6. The previous selection notification is not showing. 7. Invoice part does not work as expected in MSB. 8. Contact page UI drop down - we can remove "Email" text because we are not matching with email. | 1. I think once an MSB user is selected for one of the split billing contacts for that student, we should not show that msb user as an option/disable that option for additional split billing contacts (can't have one msb user linked to 2 separate split billing contacts for the same student) Approved | Complexities of Split Billing, remaining testing efforts carried over 3.8 Sprint 3 Stretch (We are ahead of our release schedule)
6 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 | Kaliammal | 47631 | Activities - Registrations - Update Tile Layout and Icons | Story Completed | 5 | 3.5 | 14 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41702 | 45758 | 45758 | Done | Nil | Done | 45761 |  | Approved | POV feedback - everything looks great, but I'd like for the notification badge on the upper right corner of the tile to not overlap the title text for the District Overview Registration tiles. If we can reduce the radius of the notification badge (while keeping the number centered within the badge and easy to read for larger registration counts like 1,000+), and/or increase the padding above the title, and/or increase the length of the tile so that it does not appear crowded at the bottom of the tile when the notification badge is not present. Also, we should ensure that whatever changes we make to the district overview registration tiles we also apply to the site level registration tiles for consistency.
7 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 | Hari | 47839 | Activities - Split Billing - Prevent Deleting Split Billing Contacts & Error Messaging | Story Completed | 5 | 5.5 | 22 | Done | Kaliammal | 1. Parent Delete Button alignment issue and Showing error message for unlinked contact | Kaliammal | Remove unused imports | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41771 | 45763 | 45763 | Done | Nil |  |  |  | 1. Missing a red color for the X icon. 2. Contacts details screen field name needs to update as "Linked MSB Account" 3. Contact message need to confirm -- - "The linked MSB User Account for this contact cannot be changed at this time due to an association with another Split Billing configuration." 4. When I select Not set option in drop down - it throws server error. | Approved
8 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 Stretch | Kaliammal | 47016 | Activities - Parent - Update Submit Page "Forms" Labels | Story Completed | 3 | 3.25 | 13 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41772 | 45763 | 45763 | Done | Nil |  |  |  | Approved | Approved
9 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 Stretch | Hari | 47857 | Activities - Admin - Include Search Criteria to Filter G/L Account Drop-Down List | Story Peer Review | 8 | 0 |  | Done | Kaliammal | Nil | Nil | Nil | [8 empty] | 1. Getting server error. 2. Once searched values are selected, could not see other values in the dropdown list. | Approved | Carried to next sprint for PR & Testing
10 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 Stretch | Allen | 47849 | Activities - RESEARCH - Split Billing Audit Logging Updates | Story Completed | 5 | 5 | 20 | [13 empty] | NA | NA
11 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 Stretch | Kaliammal | 47819 | Activities - Admin - Registrations - Display Valid Message when Hitting the Browser Back Button | Story Being Developed | 3 | 0
12 | MSB Activities | 45756 | 45769 | 3.8 Sprint S2 Stretch | Allen | 47954 | Activities - People - Search by Student for Parents & Other Contacts | Story Completed | 3 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41777 | 45763 | 45763 | Done | Nil |  |  |  | NA | NA
1 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 | Hari | 47712 | Activities - SYSTEM - Pagination showing page 0 when on page 2 and then a search returns less than 10 entries [3.9] | Story Completed | 5 | 4.5 | 18 | Done | Kaliammal | 1) Searched word retained after action 2) Sort is undefined. | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42029 | 45782
2 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 | Allen | 47961 | Activities - RESEARCH - Split Billing Audit Logging Updates | Story Completed | 2 | 2 | 8
3 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 | Kaliammal | 47982 | Activities - SYSTEM - Tech Debt - Move Job timing triggers into App Settings [3.9] | Story Completed | 2 | 2 | 8 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41894 | 45772 | 45782 | Done | remove PreviousDaysLookup from appsettings.Development.json | Nil | 45783
4 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 Stretch | Kaliammal | 47819 | Activities - Admin - Registrations - Display Valid Message when Hitting the Browser Back Button | Story Completed | 1 | 1 | 4 | Done | Hari | Nil | Hari | 1.Use Enum Description instead of Switch Case 2.Use Bootstrap text-warning class instead of custom class | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41861 | 45770 | 45771 | Done | Nil | Nil | 45771
5 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 Stretch | Hari | 47857 | Activities - Admin - Include Search Criteria to Filter MSB Profile Fields Drop-Down List | Story Completed | 1 | 1.25 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41784 | 45764 | 45769 | Done | Nil | Done | 45769 | Can we use a different interface name, with these changes we have more than just a Name Value Pair, so this name could be confusing.
6 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 Stretch | Allen | 48034 | Activities - SYSTEM - Improve Handling for Adding Tenant [3.9] | Story Being Developed | 3 | 0
7 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 Stretch | Kaliammal | 48077 | Activities - Admin - Registrations - Update Term Name breadcrumbs & header after hitting the Browser back button [3.9] | Story Peer Review | 2 | 2.25 | 9 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42036 | 45782
8 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 Stretch | Kaliammal | 48076 | Activities - Registrations - Remove Scroll Bar in Header [3.9] | Story Peer Review | 1 | 1.25 | 5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42037 | 45782
9 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 Stretch | Hari | 48110 | Activities - RESEARCH - Display MSB Invoice Details For Split Billing in Activities | Story Completed | 5 | 4 | 16
10 | MSB Activities | 45770 | 45783 | 3.8 Sprint S3 Stretch | Kaliammal | 48150 | Activities - RESEARCH - Select Multiple EPs on Custom Registration Report | Story Completed | 3 | 2.75 | 11
1 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Allen | 48069 | Activities - Admin - Relocate Split Billing to a Tab in Student Maintenance | Story Being Tested | 3 | 5 | 19 | Done | Kaliammal | Suggestion: three box can be same height | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42229 | 45793 | 45796 | Done | Nil | Done | 45796 | Nil | 1. When I add a contact and click details tab it shows Edit student page. 2. When I disabled the split billing toggle, still cancel button enabled and shows message. 3. Save and Cancel button need to disable when the toggle off. | Approved | UI Layout to be responsive and UI Enhancements to handle discard change Confirmation increased dev effort by one more day and couple of bouncebacks during testing
2 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Kaliammal | 48171 | Activities - Split Billing - Capture Split Billing Invoice Details within Purchase Invoice Table | Story Completed | 5 | 4 | 14 | Done | Hari | Nil | Hari | need to update this only for splitbilling invoice | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42148?_a=files | 45790 | 45790 | Done | 1) Change word SplitBillingEnabled to isSplitBillingEnabled | Done | 45790 | Nil | NA | NA
3 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Hari | 48115 | Activities - Admin - Upgrade Existing Audit Log to a Table Grid for Student Maintenance | Story Completed | 8 | 8 | 32 | Done | Kaliammal | " 1) Splitbilling Removed status 2)Administrative Notes for Operating Day Alert and Status field - need to add" | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42160 | 45790 | 45791 | Done | Nil | Done | 45791 | Nil | 1.It should be "Added" - A should be caps 2.Instead of edited - change to "Updated" - U should be caps 3.Sorting does not work for case-sensitive sorting. 4.While deleting an Administrative notes, I got an server error in Audit log page. Suggestion given for transfer/withdrawal & schedule transfer/withdrawal display to the Dev team.
4 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Allen | 48189 | Activities - SYSTEM - Autofill District ID, State & TimeZone based on District Name | Story Completed | 3 | 3 | 12 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42141 | 45789 | 45789 | Done | Nil | Done | 45790 | 1.This comment doesn't match the upgrade 2.I may have missed it, but is this used? It looks as if the infinite scroll logic isn't happening only when this is set | Approved | Approved
5 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Allen | 48190 | Activities - SYSTEM - New component for Loading Fields within Dropdown [Dev Only] | Story Completed | 3 | 3 | 13 | Done | Hari | Nil | Hari | Nil | [8 empty] | 1.Without selecting a district name and clicking Save, the validation message is missing. 2.District name - clear search values once the district is selected. 3.District name search—loading (for characters/cursor point) | Approved
6 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Hari | 48193 | Activities - SYSTEM - Pagination showing page 0 when on page 2 and then a search returns less than 10 entries [3.9] | Story Completed | 1 | 1 | 4 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42029 | 45782 | 45784 | Done | Nil | Done | 45784 | Nil | NA | NA
7 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Kaliammal | 48194 | Activities - SYSTEM - Tech Debt - Move Job timing triggers into App Settings [3.9] | Story Completed | 1 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/41894 | 45772 | 45782 | Done | Nil | Done | 45784 | Nil | NA | NA
8 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Kaliammal | 48076 | Activities - Registrations - Remove Scroll Bar in Header [3.9] | Story Completed | 1 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42037 | 45782 | 45783 | Done | Nil | Done | 45784 | Nil | NA | NA
9 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 | Kaliammal | 48077 | Activities - Admin - Registrations - Update Term Name breadcrumbs & header after hitting the Browser back button [3.9] | Story Completed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42036 | 45782 | 45783 | Done | Nil | Done | 45784 | Nil | NA | NA
10 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 Stretch | Kaliammal | 48128 | Activities - Admin - Audit logging for New Split Billing | Story Ready For Testing | 5 | 3.5 | 14 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42285 | 45797 | 45797 | Done | Nil | Done | 45798 | Nil | 1.First time enabling split billing Actions Columns should be - Added 2.Instead of Details should be Split Billing in Description column when split billing enabled | Approved
11 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 Stretch | Allen | 48181 | Activities - SYSTEM - Include Additional Fields in Tenant Add Page | Story Being Developed | 2 |  |  | Done | Hari | Nil | Hari | Nil | [8 empty] | 1.For add screen , Username, password and Provider are after time zone. I need three fields should match like edit screen. While adding these fields are must we can show top. 2.Then suggestion if possible include upload username, Provider field details in view screen
12 | MSB Activities | 45784 | 45797 | 3.9 Sprint S1 Stretch | Kaliammal | 25213 | Activities - Admin - Total Record Count is showing wrongly in Roles Page | Defect Being Tested | 2 | 1.5 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42284 | 45797 | 45797 | Done | Nil | Done | 45798 | Nil
1 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 | Allen | 25219 | Activities - Dynamic Report Generator - Duplicates on Report (Volusia) | Defect Fixed | 3 | 3 | 11 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42430 | 45805 | 45805 | Done | Nil | Done | 45806 | Nil | NA | NA
2 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 | Hari | 48069 | Activities - Admin - Relocate Split Billing to a Tab in Student Maintenance | Story Completed | 1 | 1 | 5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42296 | 45797 | 45797 | Done | Nil | Done | 45797 | Nil | NA - Done in last sprint | NA - Done in last sprint
3 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 | Kaliammal | 48128 | Activities - Admin - Audit logging for New Split Billing | Story Completed | 2 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42296 | 45797 | 45797 | Done | Nil | Done | 45797 | Nil | NA - Done in last sprint | NA - Done in last sprint
4 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 | Hari | 48353 | Activities - Students - View/Read Only for Split Billing Tab | Story Completed | 3 | 3 | 13 | Done | Kaliammal | 1) Add space second row card 2) Long Contact name makes misalignment | Kaliammal | Remove unused component reference and components | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42416 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42448 | 45804 | 45804 | Done | Nil | Done | 45804 | Nil | 1. The percentage field name should be "Billing Percentage," as per the UI mockup. 2. If the toggle is set to off, the save button hover message shows "Contacts cannot be" blank—remove that message. 3. If the contact has no email ID, the validation message is not clear even if we selected the proper email contact. | Approved
5 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 | Kaliammal | 48377 | Activities - Accounting - Payments - Show MSB Invoice Details For Split Billing | Story Completed | 8 | 8 | 32 | Done | Hari | 1.Error in Purchase detail page when invoice is not uploaded 2.Collapsable panel is toggling between open and close when i click anywhere in the entire panel 3.Syntax error code being displayed in details page | Hari | 1.Create a separate component for Splitbilling voice instead on making UI Changes in the existing Component making Details page loosely coupled with new feature 2.create new variable by checking the length of msbInvoiceDetailModel instead of accessing 0th index -- detailspage and SplitBillingPage 3.rename InvoiceBy to IsInvoiceByEmail 4.Provide Onclick event to header alone to toggle expansion panel | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42487 | 45806 | 45806 | Done | Nil | Done | 45810 | Nil | Approved | Approved
6 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 | Hari | 45974 | Activities - Accounting - Retain Grid Records in Payments Page | Story Completed | 5 | 5 | 18 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42414 | 45804 | 45804 | Done | Nil | Done | 45804 | Nil | In the search bar, the searched value should display the table grid value based on the changing the date. | NA
7 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 | Allen | 48181 | Activities - SYSTEM - Include Additional Fields in Tenant Add Page | Story Completed | 1 | 2 | 10 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42342 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42548 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42415 | 45799 | 45799 | Done | Nil | Done | 45799 | Nil | NA - Done in last sprint | NA - Done in last sprint
8 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 | Kaliammal | 25123 | Activities - Admin - Total Record Count is showing wrongly in Roles Page | Defect Fixed | 1 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42284 | 45797 | 45798 | Done | Nil | Done | 45798 | Nil | NA | NA
9 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 Stretch | Allen | 25263 | Activities - Reports - Student Registration Report - Student Selector not searching past initial 50 - PROD | Defect Fixed | 2 | 2 | 8 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42332 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42357 | 45799 | 45804 | Done | Nil | Done | 45804 | Nil | NA | NA
10 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 Stretch | Hari | 25267 | Activities - Admin - Student Maintenance - Not redirecting after making an edit | Defect Fixed | 1 | 1 | 3 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42327 | 45798 | 45798 | Done | Nil | Done | 45798 | Nil | NA | NA
11 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 Stretch | Hari | 48485 | Activities - Admin - Deselect Optional Fields in Single Selection Drop-down Component | Story Completed | 2 | 1 | 5 | Done | Allen | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42480 | 45806 | 45776 | Done | Nil | Done | 45806 | Nil | Approved | Approved
12 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 Stretch | Hari | 48281 | Activities - Accounting - Retain Grid Records in Fees Page | Story Being Tested | 5 | 3.5 | 13.5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42530 | 45810 | 45810 | Done | Nil | Done | 45811 | Nil | If we select all the fees from the drop-down (All Selected) and click the search, the fee record is not displaying. | Approved
13 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 Stretch | Kaliammal | 25330 | Activities - Admin - Contacts - Getting "Model state invalid" error if we remove the E-mail Address | Defect Peer Review | 2 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42569 | 45811
14 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 Stretch | Kaliammal | 47956 | Activities - Admin - People - Update Icons and Tile Layout | Story Being Tested | 3 | 2.5 | 9 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42528 | 45810 | 45810 | Done | Nil | Done | 45811 | Nil | Approved | Approved
15 | MSB Activities | 45798 | 45811 | 3.9 Sprint S2 Stretch | Hari | 48400 | Activities - Students - Audit Log - Capture Updated Contact User ID for New Split Billing | Story Being Tested | 5 | 2.5 | 10.5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42531 | 45810 | 45810 | Done | Nil | Done | 45811 | Nil | Approved | Approved
1 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Kaliammal | 25123 | Activities - Admin - Total Record Count is showing wrongly in Roles Page | Defect Fixed | 1 | 1 | 3 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42284 | 45797 | 45798 | Done | Nil | Done | 45798 | Nil | NA | NA
2 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Kaliammal | 25330 | Activities - Admin - Contacts - Getting "Model state invalid" error if we remove the E-mail Address[3.9] | Defect Fixed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42569 | 45811 | 45813 | Done | Nil | Done | 45813 | Nil | NA | NA | Carried from last sprint stretch for testing
3 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Kaliammal | 47956 | Activities - Admin - People - Update Icons and Tile Layout [3.9] | Story Completed | 1 | 1 | 4 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42528 | 45810 | 45810 | Done | Nil | Done | 45811 | Nil | Approved | Approved | Carried from last sprint stretch for testing
4 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Hari | 48281 | Activities - Accounting - Retain Grid Records in Fees Page[3.9] | Story Completed | 1 | 1 | 4 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42530 | 45810 | 45810 | Done | Nil | Done | 45811 | Nil | If we select all the fees from the drop-down (All Selected) and click the search, the fee record is not displaying. | NA | Carried from last sprint stretch for testing
5 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Hari | 48400 | Activities - Students - Audit Log - Capture Updated Contact User ID for New Split Billing [3.9] | Story Completed | 1 | 1 | 4 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42531 | 45810 | 45810 | Done | Nil | Done | 45811 | Nil | Approved | Approved | Carried from last sprint stretch for testing
6 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Hari | 48567 | Activities - Accounting - Payments - Formatting Split Billing Contacts UI [3.9] | Story Completed | 2 | 2 | 5 | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42576?_a=files | 45811 | 45811 | Done | Nil | Done | 45811 | Nil | Approved | Approved
7 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Allen | 25337 | Activities - Admin - Failed uploads due to "glAcctID" not matched for District or Login [3.9] | Defect Fixed | 2 | 2 | 7 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42566 | 45811 | 45811 | Done | Nil | Done | 45811 | Nil | NA | NA
8 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Ram | 48529 | Activities - SYSTEM - Update Admin Header to React & Start Vega UI Updates [Timebox] | Story Completed | 8 | 8 | 32 | [13 empty] | NA | NA
9 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Bala/Athi | 48528 | Activities - SYSTEM - Update Admin Left Nav to React & Start Vega UI Updates [Timebox] | Story Completed | 13 | 16 | 64 | [13 empty] | NA | NA
10 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 | Kaliammal | 25389 | Activities - Admin - Regression Defect - MSB Invoice Details tab is missing, When we enable Split billing toggle. | Defect Fixed | 3 | 5 | 20 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42750 | 45819 | 45819 | Done | Nil | Done | 45819 | Nil | NA | NA
11 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 Stretch | Allen | 25369 | Activities - Admin - Accounting Payments - Dynamically showing split billing yes/no instead of historically | Defect Fixed | 2 | 4 | 16 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42673 | 45814 | 45814 | Done | Nil | Done | 45817 | Nil | NA | NA
12 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 Stretch | Allen | 48576 | Activities - SYSTEM - Convert to Functional Components [Dev] | Story Completed | 5 | 5 | 18 | [13 empty] | NA | NA
13 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 Stretch | Allen | 45713 | Activities - Integrate with NotificationHub (Discovery) | Story Completed | 5 | 5 | 18 | [13 empty] | NA | NA
14 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 Stretch | Hari | 48672 | Activities - SYSTEM - Update Tile Layout Pages to React [DEV Only] | Story Completed | 5 | 4 | 16 | [13 empty] | NA | NA
15 | MSB Activities | 45812 | 45825 | 3.9 Sprint S3 Stretch | Hari | 48717 | Activities - Registration - Specific URLs Discovery | Story Completed | 3 | 2 | 8 | [13 empty] | NA | NA
1 | MSB Activities | 45826 | 45839 | 4.0 Sprint S1 | Kaliammal | 48126 | Activities - Reports - Add "Multi-Selection" for Enrollment Plan Filter on Custom Registration Report [SYSTEM] [DEV Only] | Story Completed | 5 | 7 | 27.5 | Done | Hari | 1) Select All not working | Hari | 1) Add column name instead of index 2) Add Break | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43068 | 45838 | [6 empty] | Approved | Approved
2 | MSB Activities | 45826 | 45839 | 4.0 Sprint S1 | Hari | 48725 | Activities - Split Billing - Partial Invoice Upload Failures | Story Completed | 5 | 8 | 31.5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43007 | 45834 | 45834 | Done | Nil | Done | 45834 | 1.isInvalidContact appears to be set to false when being initialized and isn't ever updated, so I believe this will never be true. Should this be using isValidContacts instead which is set by the ValidateSplitbillingContacts function? | NA | NA
3 | MSB Activities | 45826 | 45839 | 4.0 Sprint S1 | Hari | 48718 | Activities - SYSTEM - Update Tile Layout Pages to React [PR & QA] | Story Completed | 3 | 3 | 12 | Done | Allen | Nil | Allen | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/42890 | 45825 | 45826 | Done | NIL | Done | 45828 | Nil | 1.When I click the Heartland Staff bread crumb link, getting server error. 2.Bread crumb Setup link is missing for District settings page 3.Bread crumb Setup link is missing for Security Groups Name | NA
4 | MSB Activities | 45826 | 45839 | 4.0 Sprint S1 Stretch | Kaliammal | 48831 | Activities - Admin - Add a column for "State" to the Districts Page | Story Being Tested | 2 | 1.5 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43069 | 45838 | 45838 | Done | NIl | Done | 45838 | Nil | Approved | Approved | Testing was completed by offshore QA. Onsite QA is not available in this sprint waiting for his approval for completion.
5 | MSB Activities | 45826 | 45839 | 4.0 Sprint S1 Stretch | Kaliammal | 48970 | Activities - SYSTEM - URL Update for React Converted Pages | Story Being Developed | 3 | 1.5 | 6 | [15 empty] | Carried to Next Sprint for Dev & Testing
1 | MSB Activities | 45840 | 45853 | 4.0 Sprint S2 | Kaliammal | 48805 | Activities - Reports - Add "Multi-Selection" for Enrollment Plan Filter on Custom Registration Report [PR & QA] | Story Completed | 2 | 2 | 8.5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43068 | 45838 | 45842 | Done | Nil | Done | 45846 | Can we update this name to be more fitting, GetByQueryAsync or something along those lines? | Approved | Approved | Waiting for Onsite QA approval to mark it complete
2 | MSB Activities | 45840 | 45853 | 4.0 Sprint S2 | Kaliammal | 48831 | Activities - Admin - Add a column for "State" to the Districts Page | Story Completed | 1 | 2 | 7.5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43069 | 45838 | 45838 | Done | NIl | Done | 45838 | Nil | Approved | Approved | Carried from previous sprint to this sprint for onsite QA to test
3 | MSB Activities | 45840 | 45853 | 4.0 Sprint S2 | Allen | 48653 | Activities - Admin - Reorder Program Setup Tile Order | Story Completed | 2 | 2 | 6 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43106 | 45839 | 45839 | Done | NIl | Done | 45839 | Nil | Approved | Approved
4 | MSB Activities | 45840 | 45853 | 4.0 Sprint S2 | Kaliammal | 48970 | Activities - SYSTEM - URL Update for React Converted Pages | Story Completed | 5 | 6 | 24.5 | Done | Hari | Nil | Hari | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43236 | 45847 | 45847 | Done | NIl | Done | 45847 | Remove TenantId string in returnURL | NA | NA
5 | MSB Activities | 45840 | 45853 | 4.0 Sprint S2 | Hari | 49001 | Activities - Accounting - Retain Historical Split Billing Invoice By Value | Story Completed | 5 | 7 | 27.5 | Done | Kaliammal | Nil | Kaliammal | NIl | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43291 | 45848 | 45848 | Done | NIl |  | 45848 | Nil | NA | NA
6 | MSB Activities | 45840 | 45853 | 4.0 Sprint S2 Stretch | Sivaraja | 25529 | Activities - Admin - Operating days page UI overlay with "One or more students are not scheduled for attendance" notification message" | Defect Fixed | 2 | 2 | 6.5 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43318 | 45849 | 45849 | Done | Nil | Done | 45849 | Nil | NA | NA
7 | MSB Activities | 45840 | 45853 | 4.0 Sprint S2 Stretch | Kaliammal | 44086 | Activities - Admin - Update View All[Registrations] page to Server Side sorting [4.1] Dev only | Story Peer Review | 5 | 3.5 | 14 | Done | Sivaraja | 1. 'Update Search' button does not fetch the records based on the Registrations-Status selected 2.Status column is not sorted properly | Sivaraja | Nil | [10 empty] | This story is not part of the release (4.0) and will be part of the next release (4.1)
1 | MSB Activities | 45854 | 45867 | 4.0 Sprint S3 | Allen Xavier | 49188 | Activities - Admin - Add MSB District ID to Job Request Queue | Story Completed | 1 | 1 | 4 | 45854 | 45854 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43425 | 45854 | 45854 | Done | Nil | Done | 45854 | Nil | Approved
2 | MSB Activities | 45854 | 45867 | 4.0 Sprint S3 | Allen Xavier | 48830 | Activities - Integrating Notification Hub to MSB Activities [4.1] | Story Peer Review | 5 | 5 | 20 | 45855 | 45867 | Done | Sivaraja | Nil | Sivaraja | Nil | [8 empty] | NA
3 | MSB Activities | 45854 | 45867 | 4.0 Sprint S3 | Sivaraja | 49151 | Activities - SYSTEM - Update ' Record you requested was not found' page to React [4.1] dev only | Story Completed | 5 | 5 | 19 | 45854 | 45860 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Activities | 45854 | 45867 | 4.0 Sprint S3 | Kaliammal | 49152 | Activities - SYSTEM - Update 'Site & Tenant Mismatch' Page to React [4.1] - dev only | Story Completed | 5 | 5 | 20 | 45854 | 45860 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Activities | 45854 | 45867 | 4.0 Sprint S3 Stretch | Sivaraja | 49202 | Activities - SYSTEM - Remove CSHTML Pages For REACT Conversions | Story Peer Review | 1 | 1 | 4 | 45863 | 45866 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Activities | 45854 | 45867 | 4.0 Sprint S3 Stretch | Kaliammal | 25604 | Activities - Reports - All term, enrollment fields are selected automatically, when we modify site filter by adding new site. | Defect Rejected | 5 |  | 6 | 45862 | 45867
1 | MSB Activities | 45868 | 45881 | 4.1 Sprint S1 | Allen Xavier | 44086 | Activities - Admin - Update View All[Registrations] page to Server Side sorting [PR&QA] | Story Completed | 1 | 2 | 9 | NA | NA | Done | Sivaraja | 1. 'Update Search' button does not fetch the records based on the Registrations-Status selected 2.Status column is not sorted properly | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43488 BounceBack PR Link https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43774 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43841 | 45868 | 45868 | Done | Nil | Done | 45869 | Nil | Approved
3 | MSB Activities | 45868 | 45881 | 4.1 Sprint S1 | Sivaraja | 49199 | Activities - SYSTEM - Update ' Record you requested was not found' page to React [PR &QA] | Story Completed | 5 | 3.25 | 13 | NA | NA | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43500 Bounceback PR Link: https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43844 | 45868 | 45869 | Done | Nil | Done | 45869 | Nil | NA
3 | MSB Activities | 45868 | 45881 | 4.1 Sprint S1 | Kaliammal | 49201 | Activities - SYSTEM - Update 'Site & Tenant Mismatch' Page to React [PR &QA ] | Story Completed | 3 | 3 | 13.5 | NA | NA | Done | Sivaraja | 1.SiteMismatch need to handle in Kiosk | Sivaraja | 1.MisMatchExceptionController.cs (string MisMatchType) Change Variable to CamelCase 2.ControllerApp.tsx window.location.href : use this only one time by reusing TenantId and SiteId variable | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43579 Bounceback PR Link: https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43836 | 45868 | 45869 | Done | Nil | Done | 45873 | There are a number of places where Mismatch is spelled with both M's capitalized MisMatch, for consistencies sake can we make it Mismatch everywhere? | NA
4 | MSB Activities | 45868 | 45881 | 4.1 Sprint S1 | Sivaraja | 49202 | Activities - SYSTEM - Remove CSHTML Pages For REACT Conversions [PR & QA] | Story Completed | 1 | 1 | 4 | NA | NA | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43670 | 45868 | 45880 | Done | Nil | Done | 45880 | Nil | NA
5 | MSB Activities | 45868 | 45881 | 4.1 Sprint S1 | Sivaraja | 25685 | Activities - Admin - Modal popup 'Override Site Settings' Shown incorrectly when saving unrelated fields | Defect Fixed | 2 | 2 | 8 | 45868 | 45869 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/43710 | 45870 | 45876 | Done | Nil | Done | 45877 | Nil | Nil
6 | MSB Activities | 45868 | 45881 | 4.1 Sprint S1 | Allen Xavier | 48830 | Activities - Integrating Notification Hub to MSB Activities [4.1] | Story Peer Review | 3 | 5 | 19 | NA | NA | Done | Sivaraja | Nil | Sivaraja | Nil
7 | MSB Activities | 45868 | 45881 | 4.1 Sprint S1 | Kaliammal | 49397 | Activities - Registration - Site Registrations URL [Discovery ] | Story Completed | 5 | 3 | 12 | 45868 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Activities | 45868 | 45881 | 4.1 Sprint S1 Stretch | Sivaraja | 49280 | Activities - Admin - Implement Tree component for Job Request Queue | Story Being Developed | 8 | 3 | 12 | 45876
1 | MSB Activities | 45882 | 45895 | 4.1 Sprint S2 | Kaliammal | 25741 | Activities - Reports - Unselected Students are being selected from the Student dropdown list | Defect Fixed | 3 | 3 | 16.5 | 45882 | 45889 | Done | Sivaraja | 1. 'Unselected student appears when we search & unselect the user 2.Selected students not appears when we search & select the user | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44053 | 45889 | 45891 | Done | Nil | Done | 45891 | Nil | NA
2 | MSB Activities | 45882 | 45895 | 4.1 Sprint S2 | Kaliammal | 48830 | Activities - Parent - Integrating Notification Hub to MSB Activities | Story Completed | 2 | 2 | 16 | 45883 | 45890 | Done | Athi | Nil | Athi | Nil | NA | 45889 |  | Done | Nil | Done |  | Nil | NA
3 | MSB Activities | 45882 | 45895 | 4.1 Sprint S2 | Allen | 49407 | Activities - Registration - Site Registrations URL | Story Peer Review | 8 | 7 | 28.5 | 45883 | 45891 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44172 | 45895 | 45895 | Done | Nil | Done |  |  | Below points are not working as per AC: 1.URL redirection is navigating wrongly after selecting an students (again redirecting to a Site selection page to select a site). 2.If no Enrollment Plans are open for registration, we should show a message "No Enrollment Plans currently open for registration" 3.If no students in their household, we should route them to the current parent-facing page that gives a redirect to MSB option to add students to their household. 4.If the parent has students in their household, but no students in their household for the particular district associated with the site registration URL, we should show the following message "Your account does not currently have any students associated with this district, please select this district and add students to your account to continue" 5.Once the site is inactive in the admin, do we still give access to the site registration URL from the parents? Currently, in parents, we usually show only the active site to register. No, we don't need to give access to the Site registration URL if the Site is inactive. We can hide the URL at that time. We can do that in a separate story next release if needed. 6.If the parent knows the active site registration URL link and then the site is inactive, what message do we need to show to the parent admin if they access the URL again? We could keep it simple with "No results found" for now if that works. 6. New Registration is not working.
4 | MSB Activities | 45882 | 45895 | 4.1 Sprint S2 | Sivaraja | 49578 | Activities - Site Home Page - Fix the Vertical Scroll Bar | Story Completed | 5 | 5 | 21.5 | 45882 | 45888 | Done | Ram | Nil | Ram | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44062 | 45889 | 45890 | Done | Nil | Done | 45890 | typo: change 'secreen' to 'screen' | Given suggestion, to align the verbiage in the center. Approved
5 | MSB Activities | 45882 | 45895 | 4.1 Sprint S2 Stretch | Sivaraja | 49280 | Activities - Admin - Implement Tree component for Job Request Queue [4.2] | Story Being Developed | 8 | 3.75 | 15 | 45876 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Activities | 45882 | 45895 | 4.1 Sprint S2 Stretch | Allen | 49604 | Activities - Admin - Integrating Notification Hub to MSB Activities | Story Completed | 3 | 3 | 10 | 45883 | 45890 | Done | Athi | Nil | Athi | Nil | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Activities | 45882 | 45895 | 4.1 Sprint S2 Stretch | Kaliammal | 25686 | Activities - Admin - Accounting - Fees Icon mismatch in Page header of the Fees Page | Defect Fixed | 1 | 1 | 2 | 45890 | 45890 | Done | Sivaraja | Nil | Sivaraja | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44084 | 45891 | 45894 | Done | Nil | Done | 45894 | Nil | NA
8 | MSB Activities | 45882 | 45895 | 4.1 Sprint S2 Stretch | Kaliammal | 25807 | Activities - Admin - Reports - Multiselect component selection not working for the first time selection. | Defect Being Fixed | 3 | 2 | 8 | 45895 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Activities | 45896 | 45909 | 4.1 Sprint S3 | Kaliammal | 25807 | Activities - Admin - Reports - Multiselect component selection not working for the first time selection. | Defect Blocked | 3 | 3 | 19 | 45897 | 45898 | Done | SivaRaja Athi | Nil | SivaRaja Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44276 | 45898 | 45898 | Done | Nil | Done | 45902 | Nil | NA
2 | MSB Activities | 45896 | 45909 | 4.1 Sprint S3 | Sivaraja | 49280 | Activities - Admin - Implement Tree component for Job Request Queue [4.2] (timeboxed) | Story Completed | 5 | 6 | 24 | 45876 | 45909 | Done | Ram/Athi | Nil | Ram/Athi | 1. use Count instead of .Count() 2. Remove unused variables 3. Simplify the GetTenants() 4. Simplify the useEffect in MultiTreeSelect Component 5. Found some of spelling mistake 6.Instead of using any use Number 7. Consolidate useEffect method in single call | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Activities | 45896 | 45909 | 4.1 Sprint S3 | Allen | 49407 | Activities - Registration - Site Registrations URL [4.2] (timeboxed) | Story Completed | 3 | 3 | 3 | 45883 | 45891 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44172 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44208 | 45895 | 45895 | Done | Nil | Done | Hold for next release | Can we move the styling into a class in the site.scss file instead of using inline styling | Below points are not working as per AC: 1.URL redirection is navigating wrongly after selecting an students (again redirecting to a Site selection page to select a site). 2.If no Enrollment Plans are open for registration, we should show a message "No Enrollment Plans currently open for registration" 3.If no students in their household, we should route them to the current parent-facing page that gives a redirect to MSB option to add students to their household. 4.If the parent has students in their household, but no students in their household for the particular district associated with the site registration URL, we should show the following message "Your account does not currently have any students associated with this district, please select this district and add students to your account to continue" 5.Once the site is inactive in the admin, do we still give access to the site registration URL from the parents? Currently, in parents, we usually show only the active site to register. No, we don't need to give access to the Site registration URL if the Site is inactive. We can hide the URL at that time. We can do that in a separate story next release if needed. 6.If the parent knows the active site registration URL link and then the site is inactive, what message do we need to show to the parent admin if they access the URL again? We could keep it simple with "No results found" for now if that works. 6. New Registration is not working.
4 | MSB Activities | 45896 | 45909 | 4.1 Sprint S3 | Kaliammal | 25890 | Activities - Admin - Regression - Facing validation "The EnrollmentplanId field is required" even if we select enrollment plan | Defect Fixed | 3 | 3 | 3 | 45905 | 45905 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44400 | 45905 | 45905 | Done | Nil | Done | 45908 | Nil | NA
5 | MSB Activities | 45896 | 45909 | 4.1 Sprint S3 Stretch | NA | 49748 | Activities - Registration - Term Enrollment Plan specific URLS (Discovery) | Story Approved | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Activities | 45896 | 45909 | 4.1 Sprint S3 Stretch | Kaliammal | 25853 | Activities - Reports - Student Filter Tree Select Component issue in Search/Selection | Defect Blocked | NA | 2 | 10 | 45901 | 45902 | Done | Athi | Nil | Ram/Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44326 | 45903 | NA | NA | NA | NA | NA | NA | NA
7 | MSB Activities | 45896 | 45909 | 4.1 Sprint S3 Stretch | Kaliammal | 25859 | Activities - Reports - Student Filter Tree Select Component Search issue [4.2] | Defect Blocked | NA | 1 | 4 | 45903 | 45903 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Activities | 45910 | 45923 | 4.2 Sprint S1 | Sivaraja | 49796 | Activities - Registration - New Parent Account for Site Registration URL | Story Completed | 3 | 3 | 12 | 45910 | 45912 | Done | Ram | Nil | Ram/Athi | Minor change != to !== in loginreturn.tsx | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44575 | 45917 | 45917 | Done | Nil | Done | 45918 | Nil | Approved
2 | MSB Activities | 45910 | 45923 | 4.2 Sprint S1 | Sivaraja | 49848 | Activities - Admin - Implement Tree component for Job Request Queue (PR &QA) | Story Completed | 3 | 3 | 15 | 45876 | 45909 | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44529 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44675 | 45912 | 45915 | Done | Nil | Done | 45915 | Nil | Approved. Given one pov comment: 1. If the multi select dropdown (have more data it extended below the footer at the bottom and showing extra space) - Addressed with cllient - We plan to have a separate story.
3 | MSB Activities | 45910 | 45923 | 4.2 Sprint S1 | Allen | 49849 | Activities - Registration - Site Registrations URL (QA) | Story Completed | 3 | 3 | 15 | 45883 | 45891 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44172 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44208 https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/44610 | 45895 | 45895 | Done | Nil | Done | 45902 | Nil | Below points are not working as per AC: 1.URL redirection is navigating wrongly after selecting an students (again redirecting to a Site selection page to select a site). 2.If no Enrollment Plans are open for registration, we should show a message "No Enrollment Plans currently open for registration" 3.If no students in their household, we should route them to the current parent-facing page that gives a redirect to MSB option to add students to their household. 4.If the parent has students in their household, but no students in their household for the particular district associated with the site registration URL, we should show the following message "Your account does not currently have any students associated with this district, please select this district and add students to your account to continue" 5.Once the site is inactive in the admin, do we still give access to the site registration URL from the parents? Currently, in parents, we usually show only the active site to register. No, we don't need to give access to the Site registration URL if the Site is inactive. We can hide the URL at that time. We can do that in a separate story next release if needed. 6.If the parent knows the active site registration URL link and then the site is inactive, what message do we need to show to the parent admin if they access the URL again? We could keep it simple with "No results found" for now if that works. 6. New Registration is not working.
4 | MSB Activities | 45910 | 45923 | 4.2 Sprint S1 Stretch | Kaliamal | 49964 | Activities - Reports - Multi Tree Select Component (Search & Selection) | Story Being Developed | 8 | 6 | 24 | 45910
1 | MSB Activities | 45924 | 45937 | 4.2 Sprint S2 | Sivaraja | 50066 | Activities - Admin - Prevent 'Admin' from Deleting Activities in Enrollment Plan if used in Operating Days | Story Completed | 3 | 2.5 | 10 | 45924 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Activities | 45924 | 45937 | 4.2 Sprint S2 | Kaliamal | 49964 | Activities - Reports - Multi Tree Select Component (Search & Selection) | Story Being Developed | 5 | 5 | 20 | 45910 | 45937 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Activities | 45924 | 45937 | 4.2 Sprint S2 Stretch | Allen | 49748 | Activities - Registration - Term Enrollment Plan specific URLS (Discovery) | Story Completed | 3 | 3 | 12 | 45925 | 45937 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Activities | 45938 | 45951 | 4.2 Sprint S3 | Sivaraja | 50339 | Activities - Registration - Term Enrollment Plan specific URLS [4.3] (Discovery/ Dev only) | Story Completed | 5 | 7 | 29 | 45938 | 45951 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Activities | 45938 | 45951 | 4.2 Sprint S3 | Kaliammal | 49964 | Activities - Reports - Multi Tree Select Component (Search & Selection) (Dev & PR, POV only) [4.3] | Story Completed | 5 | 3 | 14 | 45910 | 45910 | Done | Athi | Nil | Athi | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45070 | 45940 | 45943 | Allen | Nil | NA | NA | NA | NA
3 | MSB Activities | 45938 | 45951 | 4.2 Sprint S3 | Allen | 26142 | Activities - Regression - Admin - Split Billing Input deleting after 3rd character | Defect Fixed | 1 | 1 | 4 | 45945 | 45946 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45170 | 45946 | 45946 | Allen | Nil | Done | 45946 | Nil | NA
4 | MSB Activities | 45938 | 45951 | 4.2 Sprint S3 Stretch | Allen | 50159 | Activities - View Districts - Hide Advanced Tools for HSS CustomerSupport [4.3] | Story Peer Review | 2 | 1 | 4 | 45938 | 45939 | Done | Kaliammal | Nil | Kaliammal | Nil | https://dev.azure.com/heartlandschools/Activities/_git/Activities/pullrequest/45049 | 45939 | 45939 | Allen | Nil | Done |  | Can we update this to instead check for a match against the allowed roles? something like AppContext.systemRole == SystemRoleID.Admin ¦¦ AppContext.systemRole == SystemRoleID.Support so that if systemRole is ever not set correctly or we add another role they aren't given access accidentally
5 | MSB Activities | 45938 | 45951 | 4.2 Sprint S3 Stretch | Kaliammal | 50160 | Activities - Parent - Site Registration URL for Inactive Site and Tenant | Story Being Developed | 3 | 2 | 8 | 45943 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Activities | 45938 | 45951 | 4.2 Sprint S3 Stretch | Kaliammal | 50161 | 50161 Activities - Parent - Site Registration URL for Site without EPs | Story Being Developed | 5 | 2 | 8 | 45944 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA