## Dashboard
Current Sprint | 26.7 M Sprint 1 | Current Sprint Sheet | 26.7 M Sprint 1-Status | Sprint Start Date | 2026-05-15 | Sprint End Date | 2026-05-28 | Application NAme | MSB Mobile | Users | sambath.selvam@relevantz.com;rupesh.kumar@relevantz.com;vaishnavi.shanmugavel@relevantz.com;ashwin.majella@relevantz.com;premkumar.rajendran@relevantz.com;bavithra.arasakumaran@relevantz.com;gursewak.jaspal@relevantz.com;amrit.harjit@relevantz.com;jagdeep.singh@relevantz.com | Teams Name(GP-MSB.Mobile) | 19:aa5856a8e6e3487ab79589431d926322@thread.v2
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story Points Story points introduced/removed | Sprint Summary | Accomplishments | Remarks | Retro Points (Internal & External) | Unplanned Leaves | Data sanity Audit Status | AuditDate | Completed Stretch | Backlog Health
NA | 13.5 Spirnt 2 | 2024-01-10 | 2024-01-23 | 26 | 26 |  |  |  | 7 Story point introduced in mid of the sprint NOTE: MAUI stories are also in progress, but paused due to high priority defects. | Internal: External: |  |  |  | 7
NA | 13.5 Sprint 3 | 2024-01-24 | 2024-02-06 | 15 | 17 |  |  |  | Strech Stories are holded by client because of regression defects NOTE: MAUI stories are also in progress, but paused due to high priority regression defects. | Internal: External: |  |  |  | 8
NA | 13.6 Sprint 1 | 2024-02-07 | 2024-02-20 | 17 | 12 |  |  |  | The development of the 43394 story is complete, but a new POV scope has been added. So this story is carried to the next sprint. NOTE: Comments added respective stories | Internal: External: |  |  |  | 3
NA | 13.6 Sprint 2 | 2024-02-21 | 2024-03-05 | 24 | 19 |  |  |  | MAUI Stories Update 42130 story is carried due to the bounce backs. 42138 story is completed and its under the testing. MAUI Stretch Stories Update 42131 story is compled but gokul have the build issue in Mac Mini so he is fixing the issue. 42142 story is completed, Testing is under progress. | Internal: External: |  |  |  | 4
NA | 13.6 Sprint 3 | 2024-03-06 | 2024-03-19 | 13 | 13 | 13 |  |  | All MAUI Stories are moved to Stretch, Working with POV comments and bounebacks. 42130 - Maui Story is completed and now it's ready for testing | Internal: External: |  |  |  | 2
NA | 13.7 Sprint 1 | 2024-03-20 | 2024-04-02 | 14 | 14 | 11 |  |  | 42129 - Login Maui story bounce back issue fixed, and it is needed some foundation level fix so sean is looking into that issue. 42131,42138 - Gokul is fixing the internal testing issues, once done, wrap up all the committed MAUI stories, and close it as soon as possible. NOTE: Detailed comments added in respective stories. | Internal: External:
NA | 13.7 Sprint 2 | 2024-04-03 | 2024-04-16 | 21 | 15 | 16 |  |  | 43928 is dev completed, New changes add at end of the sprint, and POV and Testing is Pending. Defect 19537 is fixed, but added peer review comments so this defect is carried to the next sprint MAUI Stories are still in External Testing. NOTE: Detailed comments added in respective stories. | Internal: External:
NA | 13.7 Sprint 3 | 2024-04-17 | 2024-04-30 | 12 | 12 | 17 |  |  | The story 43928 has been completed but it hasn't been tested yet, thus we need help testing it. so the brain will support the tests Completing high priority tasks by fixing regression defects, and after those are finished, moving on to stretch stories. Pulled the new MAUI stretch stories and Working on it. Note: Not pulled new committed stoies to work because this is a regression sprint. | Internal: External:
NA | 13.8 Sprint 1 | 2024-05-01 | 2024-05-14 | 10 | 10 |  |  |  | Regression Sprint. We are working on stretch stories for MAUI. and for this sprint, no newly committed stories were pulled. | Internal: External:
NA | 13.8 Sprint 2 | 2024-05-15 | 2024-05-28 | 22 | 17 |  |  |  | Some stories cannot be tested since the iOS device and simulator are not operating, therefore they are carried over to the next sprint. | Internal: External:
NA | 13.8 Sprint 3 | 2024-05-29 | 2024-06-11 | 25 | 21 |  |  |  | This sprint, we are worked on regression issues, therefore some of the committed stories only partially worked. | Internal: External:
NA | 14.0 Sprint 1 | 2024-06-12 | 2024-06-25 | 14 | 11 | 2 |  |  | Due to POV comments, the story 42133 is carried over to the next sprint. | Internal: External:
NA | 14.0 Sprint 2 | 2024-06-26 | 2024-07-11 | 11 | 15.5 | 6.5 |  |  | Completed 1 stretch story. | Internal: External:
NA | 14.0 Sprint 3 | 2024-07-12 | 2024-07-25 | 13 | 13 | 26 |  |  | Completed 1 stretch story, and currently working on MAUI stretch stories. | Internal: External:
NA | 14.1 Sprint 1 | 2024-07-26 | 2024-08-08 | 11 | 11 | 29 |  |  | Completed 2 strech stories and 1 committed story, and we are worked on MAUI Strech stories. | Internal: External:
NA | 14.1 Sprint 2 | 2024-08-09 | 2024-08-22 | 7 | 7 | 25 |  |  | we are cotinued to working on MAUI stretch stories | Internal: External:
NA | 14.1 Sprint 3 | 2024-08-23 | 2024-09-05 | 29 | 27.5 | 21 |  |  | Cotinued to working on MAUI stretch stories | Internal: External:
NA | 14.2 Sprint 1 | 2024-09-06 | 2024-09-19 | 8.5 | 13.5 | 16 |  |  | Cotinued to working on MAUI stretch stories. Regression defects are worked and the SP are burned down to the regression Stories | Internal: External:
NA | 14.2 M Sprint 2 | 2024-09-20 | 2024-10-03 | 4 | 4 | 14 |  |  | CRC Peer - 0, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 0.
NA | 14.2 M Sprint 3 | 2024-10-04 | 2024-10-17 | 13 | 16 | 21
NA | 14.3 M Sprint 1 | 2024-10-18 | 2024-10-31 | 19 | 14 | 15
NA | 14.3 M Sprint 2 | 2024-11-01 | 2024-11-14 | 17.5 | 6.5 | 8 |  | Maui Stories-Development and testing completed. | Testing was delayed due to a deployment issue in the build pipeline, GSOC scope change and DS dependency
NA | 14.3 M Sprint 3 | 2024-11-15 | 2024-12-02 | 18 | 5 | 10 |  | Development completed for most of the MAUI stories from stretch. | MSBP regression could not be completed due to external dependency for greenLight testing(functionality).The workflow in GLs end was changed which was not intimated until Letashia tested it and found it. GL cannot be tested offshore due to region specific restriction. Dotnet 9 update caused the bottom sheet issues(Internal Component) so MAUI stories could not be tested. | Most of the stories are blocked due the .Net 9 update
NA | 14.4 M Sprint 1 | 2024-12-03 | 2024-12-12 | 11 | 11.3 | 25 |  | Completed Regression testing before the release | Dotnet 9 and Telerik updated caused the bottom sheet issues(Internal Component) and input modal crash issue respectively. So MAUI stories could not be tested. The Blockers were addressed by Client Dev. | Most of the stories are blocked due to .Net 9 and Telerik updates. Client decided to go with MAUI controls instead of telerik for Datepicker and Input Modal entry control due to the long time blocker.
NA | 14.4 M Sprint 2 | 2024-12-13 | 2025-01-09 | 10 | 16 | 5 |  | Maui- commited stories completed within the sprint target date | Fixing Dotnet9 issues.
NA | 14.4 M Sprint 3 | 2025-01-10 | 2025-01-23 | 12 | 13 | 12 |  | Maui- commited stories completed. MSBP regression testing completed. Major defects found | Continue to working on MAUI Stretch Stories |  |  |  |  | 1
NA | 14.5 M Sprint 1 | 2025-01-24 | 2025-02-06 | 12 | 12 | 28 |  | Maui- Completed all committed stories and started working on stretch stories. Issues found were fixed and tested withing the sprint timeline |  | Moving the status and logging time sheet and adding comments to the story before sprint planning |  |  |  | 8
NA | 14.5 M Sprint 2 | 2025-02-07 | 2025-02-20 | 21 | 35 | 14 |  | Most of the committed stories completed, and one of the story is get delayed to due to tesing and bounce backs | we can't run the code in iOS simulator or iOS device. we have bloker on this. |  |  |  |  | 8
NA | 14.5 M Sprint 3 | 2025-02-21 | 2025-03-06 | 21 | 33.5 | 2.5 |  | Completed Regression testing. Team picked the defects from stretch and completed fixing those. Retesting completed for those defects. | [5 empty] | 14
NA | 14.6 M Sprint 1 | 2025-03-07 | 2025-03-24 | 26.5 | 52.88 | 0 |  | Completed the development and testing for the defects found and started finding issues in Maui as part of Maui regression(Post migration testing) | Client has approved to work in Defects, considering the Migration to MAUI is done for Major Stories. Telerik CollectionView control is having some issues some of which are still open issues tickets. Hence we are migrating to native collection view and it is missing some features of Telerik control. So working on it to manully replicate the features in native control. Please Note: All the Defects found were logged directly to Commit. These defects were found during Post migration Maui Regression testing. |  |  |  |  | 0
NA | 14.6 M Sprint 2 | 2025-03-25 | 2025-04-03 | 14.5 | 10.5 | 0 |  | Completed fixing and testing the Maui-Staging regression defects. Added camera support for Tickets Box office in MSBA | [5 empty] | 5
NA | 14.6 M Sprint 3 | 2025-04-04 | 2025-04-17 | 5 | 4.5 | 0 |  | Completed MSBP Xamarin regression testing. Worked on few MSB Anywhere stories and defects from the stretch | [5 empty] | 29.25
NA | 14.7 M Sprint 1 | 2025-04-18 | 2025-05-01 | 3 | 1 | 2 |  | Completed MSBP CA regression testing. Development completed for stories/defects from the stretch. updated the test cases for the stories under development. | Due to app crash in iOS and android, testing was delayed by 1 day. later we found an workaround to test that. Now that issue has been fixed. Build issues in main brach caused delay in development. |  |  |  |  | 7
NA | 14.7 M Sprint 2 | 2025-05-02 | 2025-05-15 | 18.5 | 18.5 | 0 |  | New requirement 'Family Pass' and 'Events' has been developed and tested successfully - Cross sell popup - Hooray screen - FP Payment method | NA CRC Peer - 0, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 0. |  |  |  |  | 2
NA | 14.7 M Sprint 3 | 2025-05-16 | 2025-05-29 | 12 | 7 | 0 |  | 1. Completed testing and development for MSBA Maui defects found during Xamarin to Maui conversion. | Due to an iOS app crash, testing and development activities were blocked. The issue was brought up during daily standup and Sean was working on it. CRC Peer - 0, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 0. |  |  |  |  | 0
NA | 15.0 M Sprint 1 | 2025-05-30 | 2025-06-12 | 42 | 23 | 0 |  | 1. Completed MSBA MAUI Regression defects 2.Regression testing completed for MSBP 14.7 Xamarin version 3.Smoke testing against prod environment completed for Xamarin - MSB Parent app - MSB Anywhere app - MSBP CA app | 1.Defects were tested and closed at the end of the sprint as we were unable to test in IOS devices due to build issues in iOS. 2.This was fixed by Client dev. Client is already aware of these issues. CRC Peer - 3, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 0. |  |  |  |  | 8
NA | 15.0 M Sprint 2 | 2025-06-13 | 2025-06-25 | 28.5 | 22 | 0 |  | Completed the below items 1. MSBA Maui defects. 2. MSBP Maui defects 3. MSBP CA regression 4. MSBA Xamarin Regression 5. Appium set up in iOS and Android | CRC Peer - 0, Onsite - 0, Client - 0. Internal Defect - 0, External Defect - 0. |  |  |  |  | 4
NA | 15.0 M Sprint 3 | 2025-06-26 | 2025-07-10 | 40 | 10 | 0 |  | Completed the below items 1. MSBP Maui Regression 2. Appium setup in iOS and android 3. Few automation stories development completed, waiting for client review. 4. MSBA Stretch stories completed. | CRC Peer - 0, Onsite - 0, Client - 0. Internal Defect - 1, External Defect - 0. 1. Due to Firewall update, all domain request failed, API and Logins were not working. 2. Bottom sheet issue and Acceptance criteria for automation stories modified at the end of the sprint timeline RCA: Due to issues with Owen's environment and there is no proper framework, automation fails in Owen's system. Some of the framework are not reusable due to that which is causing delay in automation work. Fix: Needs a discussion with Ashwin and Owen on this. | Internal 1. Environment setup for Automation 2. MAUI MSBP Regression 3. Started working on Automation stories 4. Completed MSBP Events story Needs Improvement - 1. Last minute AC update leads to delay in completiong automation stories. 2.Delays due to Peer review from Owen(Client) 3.Bottom sheet issues in iOS caused delay 4. Delay in setting up the environment in local |  |  |  | 14
NA | 15.1 M Sprint 1 | 2025-07-11 | 2025-07-24 | 38 | 14 | 0 |  | Completed below items 1. CA MSBP Smoke Testing against Prod version 2. Few automation stories completed. 3. MSBA Maui coversion stories completed 4. Development completed for automation stories, client review is pending | CRC Peer - 2, Onsite - 6, Client - 6. Internal Defect - 0, External Defect - 0. | Internal 1. Framework re-build for Automation 2. New functionalities included as part of automation 3. Needs Improvement - 1. Last minute AC update/modification on requirement. 2.Delays due to Peer review from Owen(Client) 3.Bottom sheet issues in iOS caused delay |  |  |  | 0
NA | 15.1 M Sprint 2 | 2025-07-25 | 2025-08-07 | 46 | 32 | 0 |  | "Completed below items 1. Completed the automation stories from main sprint | CRC Peer - , Onsite - , Client - . Internal Defect - 0, External Defect - 0. Commited Stories: 15 Completed - 12 Being Developed - 1 Being Peer review - 2 (AC update and reviewed delayed) |  |  |  |  | 0
NA | 15.1 M Sprint 3 | 2025-08-08 | 2025-08-21 | 25 | 14 | 0 | 1. In this sprint, we were focused on completing the pending automation stories. 2. No new automation stoires were picked as we were having many MSBA Maui Regression defects which needs to be fixed and tested. 3. Due to automation story 49019 which was not closed, we were unable to complete 2 automation stories which has the dependency with story 49019. 4. Development and testing completed for 10 MSBA MAUI defects. | Completed below items 1. Automation stories stuffs going well. Able to completed most of the automation stories. 2. MSBA MAUI Regression defects were fixed and tested. | CRC Peer - 2, Onsite - 1, Client - 1 Internal Defect - 0, External Defect - 3. Commited Stories/Defects: 10 Completed - 6 Being Developed - 1 Being Peer review - 3 (Due to dependency of story 49019, 2 automaiton stories were unable to complete) Completed Stretch Defects - 10 | External (Needs Improvement) - 1. After completing the commited stories from main sprint then only we can pick the stretch stories/defects. 2. Focus on main commit defects/stories |  |  |  | 21
NA | 15.2 M Sprint 1 | 2025-08-22 | 2025-09-04 | 23 | 20 | 0 | 1. In this sprint we focused on completing all the committed stories. Completed all the committed stories. 2. Pending automation stories were completed and approved by Client except 1 story which client review is pending 3. Completed all the MSBA/MSBP defect and stories 4. Worked on the defects and stories from the stretch | 1. Completed all completed MSBA/MSBP defects 2. Automation stories completed 3. Picked defects from backlog and completed | CRC Peer - , Onsite - 2, Client - 1 Internal Defect - 0, External Defect - . Total Commited Stories/Defects: 18 Completed - 17 Being Developed - 0 Being Peer review - 1 (Due to merging issue, Client is unable to run the automation script. Fixed the merging issue and sent for review) Completed Stretch Defects - 13 Completed Stretch Stories - 2 | (External) 1. Axosoft hours needs to be done on daily basis. |  |  |  | 18
NA | 15.2 M Sprint 2 | 2025-09-05 | 2025-09-18 | 18.5 | 18 | 0 | 1. In this sprint we focused on completing all the committed stories. Completed all the committed stories/defects 2. Completed all the MSBA/MSBP defect and stories 3. Worked on the defects and stories from the stretch | 1. Completed all completed MSBA/MSBP defects 2. Automation stories from main commit completed 3. Picked defects from stretch/backlog and completed | CRC Peer - , Onsite - , Client - Internal Defect - 0, External Defect - . Total Commited Stories/Defects: 16 Completed - 14 Rejected - 1 Being Tested - 1 (Defect was fixed by onsite developer and moved to testing at the end date of the sprint. Issue was not reproducible by Relevantz QA and Client QA. Only Jason from client was able to reproduce) Total Stretch Stories/Defects - 10 Completed Stretch Defects - 9 Blocked Stretch Defects - 1 | (External) 1. Got appreciation from client for completing the committed stories/defects from last 2 sprints. 2. If Test MSB is down, use Dev MSB |  |  |  | 21
NA | 15.2 M Sprint 3 | 2025-09-19 | 2025-10-02 | 50.5 | 50.5 | 0 | 1. In this sprint we focused on completing all the committed stories/regression defects. Completed all the committed stories/defects 2. Production defects were fixed by the offshore developers on time. | 1. Testing and Development Completed for all the committed stories 2. Regression Testing completed. 3. Developers fixed the Production defect | CRC Peer - , Onsite - 0, Client - 1 Internal Defect - 0, External Defect - 0, Regression Defects - 6 Total Commited Stories/Defects: 31 Completed - 28 Rejected - 1 Need more info - 1 Ready for testing - 1 Total Stretch Stories/Defects - 5 Under Development/Peer review - 5 | (External) 1. Got appreciation from PM for Offshore on amazing progress and Sprint forecast & goal was basically SPOT ON. |  |  |  | 0
NA | 15.3 M Sprint 1 | 2025-10-03 | 2025-10-16 | 22.5 | 18.5 | 0 | 1. In this sprint we focused on all the committed stories and defects. 2. Kickstarted the planning for MSBA Automation. created userstories for the automation. . 3. Stories/defects were developed and tested within the sprint 4. Team worked on the MSBP automation story from stretch | 1. Testing and Development Completed for most of the committed stories 2. Planning completed for MSBA automation. 3. Defects fixed and tested | CRC Peer - , Onsite - 2, Client - 2 Internal Defect - 2, External Defect - 0 Total Commited Stories/Defects: 13 Completed - 10 Need more info - 1 Peer Review - 2 Total Stretch Stories/Defects - 10 Under Development/Peer review - Completed - 5 Under Development - 4 Rejected - 1 . | External - Needs Improvement 1. Needs to double check the bouncebacks before approving PR & sending to testing 2. Ashwin appreciated Sambath for helping work with offshore team on getting unblocked |  |  |  | 6
NA | 15.3 M Sprint 2 | 2025-10-17 | 2025-10-30 | 23.5 | 20.5 | 0 | 1. In this sprint we focused on all the committed stories and defects. 2. Automation fixes for iOS completed. 3. Stories/defects were developed and tested within the sprint 4. Stretch defects/stories has been completed | 1. Testing and Development Completed for most of the committed stories 2. Automation fixes for most of the workflow completed in MSBP Maui. 3. Defects fixed and tested | CRC Peer - , Onsite -2 , Client - 2 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 16 Completed - 12 Rejected: 2 Ready For testing: 1 Under development - 1 . Total Stretch Stories/Defects - 14 Under Development/Peer review - 2 Completed - 7 Under Development - 3 Need more info - 1 Ready for testing: 1 | External 1. Jason appreciated Bavithra for co-ordinating the team on the automation story.. 2. Comments from Letashia"we have automation looking like its doing a good job covering with our recent fixes-" Internal: Automation failing randomly when run end to end in BS - Team is working on the fix for that issue. |  |  |  | 12
NA | 15.3 M Sprint 3 | 2025-10-31 | 0 | 28.5 | 28.5 | 0 | 1. In this sprint we focused on completing the regression testing and fixing/testing the regression defects. 2. MSBAautomation stories were completed and approved by Client. Also merged to Main branch. 3. All regression defects were tested and closed within the sprint. 4. Worked on the defects and stories from the stretch. 5.Completed all the commited stories in this sprint | 1. MSBAautomation stories were completed and approved by Client. Also merged to Main branch. 2. All regression defects were tested and closed within the sprint. 3.Completed all the commited stories in this sprint | CRC Peer - , Onsite - , Client - Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 26 Completed - 25 Rejected: 1 Total Stretch Stories/Defects - 12 Under Development/Peer review - 1 Completed - 3 Under Development - 4 Need more info - 1 Rejected: 3 | External Jason - So much work completed. Great team collab. Internal: Ashwin - Regression, Automation and MSBP App improvements |  |  |  | 11.5
NA | 26.1 M Sprint 1 | 2025-11-14 | 2025-11-26 | 16.5 | 5.5 | 0 | 1. In this sprint we focused on completing the committed stories/defects. 2. Worked on MSBA Automation stories. 3. MSBP CA Regression testing completed 4. Worked on the defects and stories from the stretch. | 1. Development completed for MSBAautomation stories 2. MSBP CA Regression testing completed 3. New enhancement stories were completed. 5. Defects from Main and stretch were completed. | CRC Peer -1 , Onsite - 0, Client - 0 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 11 Completed - 6 Under Development - 3 Under Peer reveiw - 1 Need more infor - 1 Total Stretch Stories/Defects - 11 Under Development/Peer review - 2 Completed - 5 Under Development - 4 | External: Team Goal - Pair coding / Swarm coding (maintain focus + help others = finish faster & better quality) |  |  |  | 5
NA | 26.1 M Sprint 2 | 2025-11-27 | 2025-12-11 | 24.5 | 21.5 | 0 | 1. In this sprint we focused on completing the committed stories/defects. 2. Worked on MSBA Automation story 3. New enhancembent stories were completed 4. Completed defects and stories from the stretch. | 1. Development completed for MSBAautomation story 2. New enhancement stories were completed. 3. Defects /stories from Main and stretch were completed. | CRC Peer -17 , Onsite - 1, Client - 37 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 10 Completed - 8 Under Development - 1(due to bb this story was carried) Rejected - 1 Total Stretch Stories/Defects - 6 Under Development/Peer review - 1 Completed - 4 Under Development - 1 | External: . 1.QA should not be going to dev management for clarification on testing criteria 2. Communication related to stories with client needs to be documented in the axosoft stories/defects 3.Team Goal: Pair coding / Swarm coding (maintain focus + help others = finish faster & better quality). 4.Double checking on bouncebacks before approving PR & sending to testing. |  |  |  | 5.5
NA | 26.1 M Sprint 3 | 2025-12-12 | 2026-01-08 | 41 | 38 | 0 | 1. This is a one month sprint.We focused on completing all the committed stories/defects. 2. Worked on MSBA Automation story 3. MSBP .net10 package upgrade stories were completed. 4. MSBP Maui regression testing completed. . 5. MSBP CA Smoke testing completed. 6. MSBA Smoke testing completed. 7. Completed the new enhancement Tickets stories. | 1. Completed MSBA Automation story 2. Completed MSBP .net10 package upgrade stories 3. Completed MSBP Maui regression testing . . 4. Completed MSBP CA Smoke testing . 5. Completed MSBA Smoke testing . 6. Completed the new enhancement Tickets stories. | CRC Peer - 4, Onsite - 4, Client - 5 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 16 Completed - 15 Under Development - 1 Total Stretch Stories/Defects: 1 Under Development - 1 (Defect picked for developement at the end day of the sprint, so it got carry forwarded) | . (External) 1. Jason: Thank you to Bavithra for reviewing over 200 enhancement requests and assigning personas.. 2. Jason: We are making great progress on our big goals. Congrats to the team for getting MSBP Tickets in the state that it is, ready for 26.1 release. |  |  |  | 0
NA | 26.3 M Sprint 1 | 2026-01-09 | 2026-01-22 | 23.5 | 21.5 | 0 | 1. MSBA .NET 10 package update completed successfully 2. Defects from main sprint has been fixed and tested 3. Started testing the the MSBP Kaleida stories 4. Defects and stories from stretch were completed 5. Smoke test of MSBA application after .net 10 package update completed | 1. Completed MSBA .NET 10 package update 2. Completed development and testing of MSBA/MSBP Defects/stories from main sprint and stretch 3. Completed Smoke test of MSBA application after .net 10 package update 4. Started to work on Kaleida stories for parent ap | CRC Peer - 1, Onsite -0 , Client - 1 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 13 Completed - 10 Under Development - 2 ( Bounceback created and onsite developer is working on the fix). Blocked - 1 (testing blocked due to an another issue for which new defect will be created) Total Stretch Stories/Defects: 22 Completed - 10 .Under Development - 5 Ready For Testing - 2 Peer review - 2 Verified - 1 Rejected - 1 . Blocked - 1 | (External) 1. Jason: Incredible amount of work completed. Improvement-Keep backlog refined & consistent storage location for all new things we’ll pull for Next Work and early notification of needed work to help keep in front of it and be able to refine if needed. |  |  |  | 14.5
NA | 26.3 M Sprint 2 | 2026-01-23 | 2026-02-05 | 21.5 | 19.5 | 0 | 1. MSBP Kaleida stories were completed. 2. .net10 Defects from main sprint has been fixed and tested 3. New enhancement stories were completed. 4. Defects and stories from stretch were completed 5. Started development for MSBA Kaleida stories | 1. Completed the Kaleida stories for MSBP. 2. Testing and development completed for .net10 Defects from main sprint 3. Completed the development and teting for the New enhancement stories 4. Completed Defects and stories from stretch | CRC Peer - 1, Onsite -1 , Client - 4 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 16 Completed - 15 Under Development - 1(51191 - This story was picked up on the end day of the sprint and moved to development phase due to an open bounceback. This is being worked by the Onsite developer) Total Stretch Stories/Defects: 17 Completed - 11 Under Development - 4 Peer review - 2 | External: . 1. Ashwin – Good progress on MSBA Kaleida and defect fixes |  |  |  | 19.5
NA | 26.3 M Sprint 3 | 2026-02-06 | 2026-02-19 | 38 | 22 | 0 | 1. MSBP - Full regression testing completed 2. MSBA - Smoke testing completed 3. MSBP CA - regression testing completed. 4. MSBA Kaleida enhancement stories completed. 5. Regression defects completed. 6. Team worked on the MSBA new enhancement Kaleida stories. | 1. Completed MSBP - Full regression testing 2. CompletedMSBA - Smoke testing completed 3. CompletedMSBP CA - regression testing completed. 4. CompletedMSBA Kaleida enhancement stories completed. 5. Completed Regression defects completed. | CRC Peer - 1, Onsite -1 , Client - 7 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 18 Completed - 13 Need more info - 1 Rejected - 1 Being Tested - 1 (Deployment to prod was not happned due to which testing blocked). Peer review - 2 Total Stretch Stories/Defects: 5 Under Development - 1 Ready for Testing: 4 ( Moved to testing at the EOD of the sprint end date) |  |  |  |  | 0
NA | 26.4 M Sprint 1 | 2026-02-20 | 2026-03-05 | 39.5 | 26.5 |  | 1. MSBA - Regression defects fixed and tested. 2. MSBA Kaleida enhancement stories completed. 3. Stretch stories completed 4. Team worked on MSBA new enhancement Kaleida stories.. 5. Team worked on MSBP new enhancements stories as well. | 1. Completed MSBA - Regression defects. 2. Completed MSBP defects. 3.MSBA Kaleida and MSBP enhancement stories completed. 4. Stretch stories completed | CRC Peer - 0, Onsite -2 , Client - 7 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 27 Completed - 23 Under Development - 4 Total Stretch Stories/Defects: 6 Completed - 3. Under Development - 1 Need more info: 2 | AM: MSBA Kaleida is making good progress. Transaction history story passed without a BB! Which proves the additional dev test on multiple devices is helping. Also lots of defects fixed. AM – Figma occasionally still getting followed by dev more than AC. Has reminded Relevantz offshore team to follow AC more than Figma. Improvements - Has asked Relevantz offshore team to get on call/discuss with BA,QA,Dev to fully understand the AC for each of our work items. |  |  |  | 10
NA | 26.4 M Sprint 2 | 2026-03-06 | 2026-03-19 | 32 | 24 |  | 1.Team worked on MSBA Kaleida enhancement stories 2.MSBP CA 26.3 release smoke test in prod completed 3. MSBP US 26.3 release smoke test in prod completed 4. Worked on MSBA/MSBP regression defect 5.Smoke test of MSBP Kaleida merge into Main completed. | 1.Completed MSBP CA 26.3 release smoke test in prod 2.Completed MSBP US 26.3 release smoke test in prod. 3.Completed the MSBA/MSBP regression defects 4.Smoke test of MSBP Kaleida merge into Main completed. 5.Team worked on the MSBA Kaleida enhancement stories. | CRC Peer - 4, Onsite -3 , Client - 7 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 19 Completed - 12 Under Development - 3 Peer review - 1 Rejected -3 Total Stretch Stories/Defects: 14 Completed - 6 Under Development - 1 Need more info -1 Approved - 3 (hours entered for test case update) Peer review - 3 . . | What went well:​ (External)​ SJ – Offshore / Ashwin on task and implementing components & getting it to look good​ JM: Ashwin/Bavithra - keeping the lights on at night, keeping the team moving.​ JM: Bavithra – completed analysis for multiple WCAG things, got started early on VPAT too. ​ ​ ​ What Didn't go well: ​ - Settings story blowing out of proportion due to the kaleida common control changes​ Now not blocked on moving forward with controls. |  |  |  | 8.5
NA | 26.04 M Sprint 3 | 2026-03-20 | 2026-04-02 | 32 | 29 |  | 1.Team worked on MSBA Kaleida enhancement stories 2.MSBP Kaleida components stories completed 3. MSBP and MSBA Regression defects completed. | 1.Team worked on MSBA Kaleida enhancement stories 2.Completed MSBP Kaleida components stories 3. Developmnet and testing completed for MSBP and MSBA Regression defects . 4. New enhancement MSBP Tickets season pass story completed. | CRC Peer - 9, Onsite -1 , Client - 18 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 33 Completed - 22 Under Development - 3 Peer review - 3 Rejected - 1 Being Tested - 1 Need more info - 2. Ready for testing - 1 Total Stretch Stories/Defects: 8 Completed - 3 Under Development - 3 Approved -1 Being Tested - 1 | Retro not conducted due to absence of Product Manager |  |  |  | 0
NA | 26.5 M Sprint 1 | 2026-04-03 | 2026-04-16 | 33.5 | 17.5 | 0 | 1.Team worked on MSBA Kaleida enhancement stories 2.MSBP CA 26.4 release smoke test completed 3. MSBP US 26.4 release smoke test in prod completed 4. MSBA - Smoke Test Against 26.4 Web RC 5.Completed the high priority regression defects for MSBA and MSBP | 1.Completed MSBP CA 26.4 release smoke test in prod 2.Completed MSBP US 26.4 release smoke test in prod. 3.Completed the MSBA/MSBP regression defects 4.Team worked on the MSBA Kaleida enhancement stories. | CRC Peer - 4, Onsite - 1, Client - 24 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 24 Completed - 15 Under Development - 5 Peer review - 1 Being Tested - 2 Need more info - 1 Total Stretch Stories/Defects: 1 Under Development - 1 | What went well:​ Ashwin - Good amount of regression defects fixed. Owen - QA channel for QA team to stay on top of things and Owen can answer when needed. Letashia - Got Beta out! What Didn't go well: ​ Letashia - we had a ton of carryover due to things not moving until the end of the sprint. This included stories that were estimated as “mostly testing” that had 0sp left by the time it reached testing.This adversely impacted the velocity tracking sheet. Additionally there were things marked for tomorrows release that seemed to be deprioritized behind Kaleida and Maui stories. Still struggling with missing AC things at times- there have been a lot of back and forth about what we are supposed to have in a story despite the increased details we have tried to put into each one Owen QA still has to log each of the things they find. Need to follow it and dive in for each (if it’s released to work). Improvements- - If we have development in flight which we have to put on hold in order to fix a high priority defect/story/escalation, we should move the Workflow Step to “Approved”, keep developer name assigned, and update the Status to “On Hold” with a comment in the story such as “I paused this in order to fix the high priority defect 1234”. - Try Live Pov video as a preference | 3
NA | 26.5 M Sprint 2 | 2026-04-17 | 2026-04-30 | 19 | 26 | 0 | 1.Team worked on MSBA Kaleida enhancement stories 2. Worked on MSBA and MSBP defects 3. Completed few stories/defects from stretch | 1.Completed the MSBA/MSBP defects 2.Development completed for MSBA Kaleida enhancement stories. . 3. | CRC Peer -4 , Onsite - 1, Client - 3 Internal Defect - 6 , External Defect - 3 Total Commited Stories/Defects: 13 Completed - 12 Under development - 1 (this story being worked by Sean Onsite developer) Total Stretch Stories/Defects: 13 Under Development - 5 Completed - 5 Peer review - 2 PO Verify - 1 | What went well:​ LJ- got through a lot of work (beta defects, release defects, Kaleida work) SJ – MSBA beta seems to be going well AM- Strong sprint. The coordination within the team was great. What Didn't go well: ​ NA Improvements- LJ- less release defects, either less changes after regression testing has been completed or more thorough view after so many extra changes are made to prevent catching it at the last minute LJ – Dev communicate with QA on if there are possibly other areas which might be affected on changes. Kudos - BS training went really well, great questions and participation Brags - JM: Bavithra learned Pendo – is currently tagging the MSBA App JM: MSBA Beta – going swell JM: VPAT is complete and we are further along now understanding Accessibility needs than before, and QA is trained on Browserstack as well.
NA | 26.5 M Sprint 3 | 2026-05-01 | 2026-05-14 | 13 | 22 | 0 | 1.Team worked on MSBA Kaleida enhancement stories 2. Worked on MSBA and MSBP defects 3. Completed high priority stories/defects from stretch. 4. Worked on MSBP Regression testing | 1.Completed the MSBA/MSBP defects 2.Team worked on the MSBA Kaleida enhancement stories. | CRC Peer -5 , Onsite - 0, Client - 5 Internal Defect - 0 , External Defect - 0 Total Commited Stories/Defects: 9 Completed - 7 Under development - 2 (One defect worked by Onsite developer) Total Stretch Stories/Defects: 14 Blocked - 1 Completed - 1 Peer review - 3 Ready for testing- 7. Being tested - 2 | What went well:​ JM: So much – appreciate the flexibility with the Beta/test flight. AM: Communication between offshore and Avery has been good to resolve the Kaleida control issues and updates What Didn't go well: ​ NA Improvements- LJ- Dev/QA balance (this sprint is looking much better) Kudos - CR – Letashia & QA team for hanging in there Brags - MSBA GA – let's not count our chickens yet but I mean...the plan seems solid! Customers are reporting that things are working well. No major issues or reasons to NOT GA. |  |  |  |  | 10
NA | 26.7 M Sprint 1 | 2026-05-15 | 2026-05-28

## Defect-template
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## Unplanned Leaves
Total Leaves | 12
Resource Name
Sprint | Amrit Pal Harjit Singh | Ashwin Majella | Bavithra Arasakumaran | Gursewak Singh Jaspal Singh | Jagdeep Singh | Premkumar Rajendran | Rupesh Kumar | Sambath Selvam | Vaishnavi Shanmugavel | Remarks
26.3 M Sprint 2 (23-Jan-2026 to 5-Feb-2026) | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 27-Jan-26 Vaishnavi - well its planned but updated at the last minute so it is unplanned leave in Leave tracker, 29-Jan-26 Amrit took sick leave
26.4 M Sprint 1 (20-Feb-2026 to 05-Mar-2026) | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 9-Feb-26 Gursewak took the leave for family emergency.
26.3 M Sprint 3 (06-Feb-2026 to 19-Feb-2026) | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14 Feb - Ashwin Sick leave
26.4 M Sprint 1 (20-Feb-2026 to 05-Mar-2026) | 0 | 1 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 27 Feb - Ashwin Sick Leave, 3 Mar - Bavithra emergency leave met with small accident, Prem Sick leave.
26.4 M Sprint 3 (20-Mar-2026 to 02-Apr-2026) | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 30 Mar - Bavithra Sick leave and Sambath network issue.
26.5 M Sprint 1 (03-Apr-2026 to 16-Apr-2026) | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 0 | 1 | 6th Apr - Vaishnavi sick leave, 10th Apr - Prem Sick Leave 9th Apr- Amrit Unplanned sick leave
Total | 2 | 2 | 2 | 1 | 0 | 2 | 0 | 1 | 2 | 0

## 26.7 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.7 M Sprint 1 | chandler/vaishnavi/ | 27320 | 27320 MSBP - Android - All text and sizes are inflated on pixel pro devices, sometimes pushing items off viewable area (26.5) | Defect Being Tested |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15-May - chandler working on the fix.
2 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Jagdeep/vaishnavi | 52343 | [WAVE] MSBA - Kaleida - Update Offset Language - Difference(Over/Short) | Story Being Tested |  |  |  | 2026-05-05 | 2026-05-06 | NA | Amrit/Vashnavi | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48842 | 2026-05-05 | 2026-05-07 | Ashwin | NA | Avery | 2026-05-07 | NA | POV done with Bavithra No Comment | POV done with Jason No Comment | 15-May- will work on the testing
3 | MSB Mobile | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Amrit/Gursewak | 27283 | MSBA - MAUI - iOS- meal payments screen changing formatting when cart preview is on with items in it | Defect Ready For Testing |  |  |  | 2026-05-08 | 2026-05-11 | NA | Gursewak | Yes | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48972 | 2026-05-11 | NA | NA | NA | NA | Na | NA | POV done with Bavithra No Comment | NA | 14 May - PR Pending from Ashwin and Client Side 15 May - Defect ready for testing
4 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Jagdeep | 27276 | MSBP - Android - Can double click and open multiple stacks of menus | Defect Ready For Testing |  |  |  | 2026-05-06 | 2026-05-08 | NA | Gursewak | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48903 | 2026-05-07 | 2026-05-13 | Ashwin | NA | Avery | 2026-05-13 | NA | POV done with Bavithra No Comment | NA | Will pick this after completing the MSBA, MSBP CA, MSBP smoke tests
5 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Gursewak/Prem | 27015 | MSBA - MAUI - iphone - invoice add to cart button not formatted correctly (regression) | Defect Fixed |  |  |  | 2026-05-08 | 2026-05-08 | NA | Yes | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48924 | 2026-05-08 | 2026-05-08 | NA | NA | NA | NA | NA | POV done with Bavithra No Comment | NA | Will pick this after completing the MSBA, MSBP CA, MSBP smoke tests 15 May - Testing completed
6 | MSB Mobile | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Amrit | 27006 | MSBA - MAUI - iOS - Cart has extra space underneath buttons (regression) | Defect Ready For Testing |  |  |  | 2026-05-08 | 2026-05-11 | NA | Gursewak | Yes | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48926 | 2026-05-11 | NA | NA | NA | NA | NA | NA | POV done with Ashwin No Comment | NA | 14 May - PR Pending from Ashwin and Client Side 15 May - Defect ready for testing
7 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Jagdeep | 27255 | MSBP - missing phone number page and profile phone pages do not match | Defect Peer Review |  |  |  | 2026-05-08 | 2026-05-11 | NA | Amrit | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/49015 | 2026-05-11 | NA | NA | NA | NA | NA | NA | POV done with Bavithra No Comment | NA | 15 May - Waiting for aproval from Ashwin and Client side.
8 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Gursewak | 26881 | MSBA - Cart icon/badge is larger than expected (regression) | Defect Ready For Testing |  |  |  | 2026-05-08 | 2026-05-11 | NA | Yes | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48932 | 2026-05-11 | 2026-05-11 | NA | NA | NA | NA | NA | POV done with Bavithra No Comment | NA | 15 May- Merged, ready for testing.
9 | MSB Mobile | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Vaishnavi/Prem | 53092 | REG - MSBP - Regression 26.5 | Story Being Tested |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Work on the invoice push notificaiton test cases
10 | MSB Mobile | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Rupesh/Vaishnavi | 27394 | MSBA - stock option formatting issues (regression) | Defect Being Tested |  |  |  | 2026-05-13 | [16 empty] | WIll start the testing.
12 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Prem | 53090 | MSBP CA - Regression/Smoke Test Against Staging 26.5 RC | Story Being Tested | 1 |  |  | NA | NA | NA | NA` | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15 May - Testing is in Progress
13 | MSB Mobile | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 Stretch | Amrit/Prem | 52344 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Hamburger Menu | Story Ready For Testing |  |  |  | 2026-04-20 | 2026-04-22 | NA | Jagdeep | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48532 | 2026-04-26 | 2026-04-28 | Sambath | NA | Avery | 2026-04-28 | NA | POV done with Bavithra No Comment | NA | After completing the main commit stories/defects will work on these stories
14 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 Stretch | Gursewak | 52346 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Header | Story Ready For Testing |  |  |  | 2026-04-21 | 2026-04-30 | NA | Yes | NA | Rupesh/Sambath | Total Comments: 3 Rupesh Kumar (1 Comment) Please use static resource color from Kaleida. Sambath Selvam (2 Comments) Remove default value properties. Remove RowSpacing="0". | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48736 | 2026-04-30 | 2026-04-30 | Ashwin | NA | Avery | 2026-05-06 | Total Comments: 5 Avery Wold (5 Comments) Remove this since Demo Mode is not used. Use "K" colors – KAppHeaderBackgroundColor. Fix KCircleButton property mismatch and incorrect styling. Use correct "K" color – KChipBackgroundColor. Remove unnecessary CornerRadius (handled by KCircleButton). Do not hardcode Black; use KPrimaryTextColor. | POV done with Bavithra No Comment | POV done with Jason No Comment | After completing the main commit stories/defects will work on these stories
15 | MSB Mobile | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 Stretch | Sambath | 52347 | 52347 [WAVE] MSBA - Update Components/Fonts to Kaleida - Transaction History | Story Ready For Testing |  |  |  | 2026-04-21 | 2026-05-04 | NA | Rupesh | NA | Rupesh | remove the default value properties | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48726 | 2026-05-04 | 2026-05-04 | NA | NA | Avery | 2026-05-11 | Count (10) Exiting Code:Shell.Current.DisplayAlertAsync changed to DialogService.ShowDialogAsync(), this is new change has added by avery (16). Exiting Code:Naming convension changed to ShowHideAdminLoginModalCommand instead of ShowHideBarcodeModalCommand (2) New change : Loading Inidicator changes, that is new changes (4) Kcolor missed in two places (2). Exiting Code:Font size removed from all Kcontrol, it take default font size from K library (21) KButton has been repalced with KIconButton (1) New change :Custom ItemTemplate was removed, instead used New KListTile control (1). Exiting Code:Image control has been replaced with Klable to show the icon only option (1) Exiting Code: For consistency with other buttons change this to HeightRequest="44" (2) Exiting Code:exiting EmailRefundPopup Code has been refacored based on avery suggesion (10). | POV Done |  | After completing the main commit stories/defects will work on these stories
16 | MSB Mobile | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 Stretch | Rupesh/Prem | 52348 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Forgot Login Workflow | Story Ready For Testing |  |  |  | 2026-04-22 | NA | NA | Jagdeep | NA | Jagdeep/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48656 | 2026-04-27 | 2026-05-04 | Ashwin | NA | Avery | 2026-05-06 | Comments - 14 This should be using the Kaleida component(For BG image). - 5 Get rid of this since we do not have Demo mode - 5 KHeader is already defaulted to use KPrimaryColor, no need to add this." - 1 KHeader is already Bold, no need to add this - 1 This should probably be a KHeader(KLabel was used):- 1 Get rid of this old style and consider using the KHeader (Old style was used as it was before)- 6 This should probably be a KCircleButton(This was a Klabel ) - 3 This is the default, adding this is redundant - 9 Consider using the KLabelFootnote style for consistency.(Label was used) - 1 This is overcomplicated, can be simplified - 4 if this needs to be a Header based on the old style still attached consider using a KHeader, otherwise this could be simplified : - 1 This is not a phonenumber field and the name here should be updated to reflect that(This was existing one)- 1 KPasswordField has a build in error message, simplify it- 4 | POV done with Ashwin No Comment | NA | After completing the main commit stories/defects will work on these stories
17 | MSB Mobile | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Rupesh | 27406 | MSBA - Shift Mode - Unable to Start Shift - Errors with Starting Shifts | Defect Found | 3 |  |  | 2026-05-15
18 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Gursewak | 53208 | MSBA - TECH DEBT - Unit Tests - Update to .NET10 | Story Being Developed | 3 |  |  | 2026-05-15 | [16 empty] | 15 May - start working on it.
19 | MSB Mobile Kaleida | 2026-05-15 | 2026-05-28 | 26.7 M Sprint 1 | Jagdeep | 53209 | MSBP - TECH DEBT - Unit Tests - Update to .NET10 | Story Being Developed | 3 |  |  | 2026-05-15 | NA | NA | NA` | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15 May - start working on it. |  |  | Main

## 26.5 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
2 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Amrit/Prem | 52344 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Hamburger Menu | Story Ready For Testing | 3 |  | 8.5 | 2026-04-20 | 2026-04-22 | NA | Jagdeep | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48532 | 2026-04-26 | 2026-04-28 | Sambath | NA | Avery | 2026-04-28 | NA | POV done with Bavithra No Comment | NA | 04,05-may- Amrit PTO 6 May - Space issue InProgress for small devices android, Transaction history crash is being fixed by sambath in different PR 7 May - Transaction History Sambath PR is in Review, Space Issue we are not doing as discussed with client. 8 May - Waiting for Sambath PR to be merged for transaction history PR. 11 May - Story Moved to Need more info its pending until 52347 is merged 12 May - Story ready for testing 52347 is merged | Exceeds Expectation | Due to regression testing and other high priority defects/stories, this story was not picked up by the tester | Stretch
4 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Gursewak | 52346 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Header | Story Ready For Testing | 2 |  | 4 | 2026-04-21 | 2026-04-30 | NA | Yes | NA | Rupesh/Sambath | Total Comments: 3 Rupesh Kumar (1 Comment) Please use static resource color from Kaleida. Sambath Selvam (2 Comments) Remove default value properties. Remove RowSpacing="0". | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48736 | 2026-04-30 | 2026-04-30 | Ashwin | NA | Avery | 2026-05-06 | Total Comments: 5 Avery Wold (5 Comments) Remove this since Demo Mode is not used. Use "K" colors – KAppHeaderBackgroundColor. Fix KCircleButton property mismatch and incorrect styling. Use correct "K" color – KChipBackgroundColor. Remove unnecessary CornerRadius (handled by KCircleButton). Do not hardcode Black; use KPrimaryTextColor. | POV done with Bavithra No Comment | POV done with Jason No Comment | 04 May - PR review pending from Sambath, Ashwin,client side. 05 May - Client review pending. 06 May - Avery added some comments, start working on it, will test and update the PR. 06 May - EOD - Ready for test.. 08-May- QA team working on the main commit defects/stories follwed by regression testing. | Exceeds Expectation | Due to regression testing and other high priority defects/stories, this story was not picked up by the tester | Stretch
5 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Sambath | 52347 | 52347 [WAVE] MSBA - Update Components/Fonts to Kaleida - Transaction History | Story Ready For Testing | 8 |  | 35 | 2026-04-21 | 2026-05-04 | NA | Rupesh | NA | Rupesh | remove the default value properties | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48726 | 2026-05-04 | 2026-05-04 | NA | NA | Avery | 2026-05-11 | Count (10) Exiting Code:Shell.Current.DisplayAlertAsync changed to DialogService.ShowDialogAsync(), this is new change has added by avery (16). Exiting Code:Naming convension changed to ShowHideAdminLoginModalCommand instead of ShowHideBarcodeModalCommand (2) New change : Loading Inidicator changes, that is new changes (4) Kcolor missed in two places (2). Exiting Code:Font size removed from all Kcontrol, it take default font size from K library (21) KButton has been repalced with KIconButton (1) New change :Custom ItemTemplate was removed, instead used New KListTile control (1). Exiting Code:Image control has been replaced with Klable to show the icon only option (1) Exiting Code: For consistency with other buttons change this to HeightRequest="44" (2) Exiting Code:exiting EmailRefundPopup Code has been refacored based on avery suggesion (10). | POV Done |  | i have to run the POV with client, 07-May - Resolving merge conflicts, testing the app 08-May - Found some issue in KPopup and checked with avery, he modifed in library and i need to work updating the new Kpopup feature into app. 11- May - Working with code review changes 12- it is moved to ready for testing | Meets Expectation | Due to regression testing and other high priority defects/stories, this story was not picked up by the tester 14-May -26 - This story only covers Kcontrol and font and kcolor changes, but I also worked on other code refactor changes based on Avery’s suggestions. We need to plan what changes are included in this story, because if we spend time on items outside the AC, it will take longer and lead to more review comments | Stretch
6 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Rupesh/Prem | 52348 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Forgot Login Workflow | Story Ready For Testing | 3 |  | 6 | 2026-04-22 | NA | NA | Jagdeep | NA | Jagdeep/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48656 | 2026-04-27 | 2026-05-04 | Ashwin | NA | Avery | 2026-05-06 | Comments - 14 This should be using the Kaleida component(For BG image). - 5 Get rid of this since we do not have Demo mode - 5 KHeader is already defaulted to use KPrimaryColor, no need to add this." - 1 KHeader is already Bold, no need to add this - 1 This should probably be a KHeader(KLabel was used):- 1 Get rid of this old style and consider using the KHeader (Old style was used as it was before)- 6 This should probably be a KCircleButton(This was a Klabel ) - 3 This is the default, adding this is redundant - 9 Consider using the KLabelFootnote style for consistency.(Label was used) - 1 This is overcomplicated, can be simplified - 4 if this needs to be a Header based on the old style still attached consider using a KHeader, otherwise this could be simplified : - 1 This is not a phonenumber field and the name here should be updated to reflect that(This was existing one)- 1 KPasswordField has a build in error message, simplify it- 4 | POV done with Ashwin No Comment | NA | 04 May : POV’d by Jason, I have published the PR for review. 05 May : Client approval is pending. Received pr comments , resolved and sent them back for review. 08 - QA team working on the main commit defects/stories follwed by regression testing. 08 May - Testing is in Progress 11 May - Tested and Raised a BB.And assigned back to dev to fix the same 12 May - Received some BB’s related to Primary button, I connected with Avery and he made some changes, need to pull Kaleida and test it and if everything looks okay, will raise the PR. | Exceeds Expectation | Due to regression testing and other high priority defects/stories, this story was not picked up by the tester | Stretch
9 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Amrit/Vaishnavi | 52633 | MSBP - Store Catalog - General header changed to Products | Story Completed | 1 |  | 4 | 2026-04-27 | 2026-04-27 | NA | Jagdeep | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48662 | 2026-04-27 | 2026-04-27 | Ashwin | NA | Avery | 2026-04-30 | NA | POV done with Bavithra No Comment | NA | 4-May-Will be starting the testing. | Exceeds Expectation |  | Main
12 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Amrit/Vaishnavi | 26882 | MSBA - Cart Icon does not have the correct MSBA blue background | Defect Fixed | 1 |  | 4 | 2026-04-29 | 2026-04-29 | NA | Rupesh | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48721 | 2026-04-30 | 2026-04-30 | Ashwin | NA | NA | 2026-04-30 | NA | POV done with Bavithra No Comment | NA | 4-May-Will be starting the testing. | Exceeds Expectation |  | Main
13 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Rupesh/Vaishnavi | 52964 | MSBA - Admin Settings - BETA build - Require Elevated Privileges | Story Completed | 3 |  | 18 | 2026-04-29 | 2026-05-11 | NA | Jagdeep | NA | Jagdeep/Sambath | Can we use StaticResource colors instead of hardcoded value. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48865 | 2026-05-06 | 2026-05-06 | Ashwin | NA | Avery | 2026-05-08 | Comments - 3 -This array is duplicated from ViewModelBase.cs Add a protected helper method to ViewModelBase for consistency -This is missing an await -The ApplyPendingChange() and RevertPendingChange() methods add ~200 lines - Instead consider simpler approach. | POV done with Bavithra No Comment | NA | 04 May : Other day, I had a plan to do the POV, however during UT, i found some issue, so will be working on that issue and then will run the POV. 05 May : Found some issue during peer testing, will be fixing those. 06 May : did the POV both internal and external and raised the PR.. 07-Vaishnavi- Will be updating the test cases for this story 08 - Received few comment from Avery, will resolve it today. 11 May - Receive one BB, will be working on that. | Exceeds Expectation |  | Main
15 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Jagdeep/Prem | 48498 | [WAVE] MSBA - Receipt Screen - Show Confirmation/Green Check once SMS/Email Sent | Story Completed | 1 |  | 11 | 2026-04-30 | 2026-05-04 | NA | Rupesh | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48815 | 2026-05-04 | 2026-05-05 | Ashwin | NA | Avery | 2026-05-05 | Count :- 2 1. WasSent should be reset to false in OnError handler, failed sends should show 'Send' not 'Resend' 2. Change OriginalButtonText from field to property. | POV done with Bavithra No Comment | POV done with Jason No Comment | 04 May - Will continue work on this defect and will do POV today. 05 May - Will work for to resolve PR comment.(Comment Resolved Story under peer a review) 06 May - Story ready for testing. 07 May - Test Case updation and testing completed | Exceeds Expectation |  | Main
16 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Gursewak/Sambath/Prem | 27318 | MSBA - Kaleida - I/A - Unable to navigate back from Admin Settings when shift is already active | Defect Fixed | 3 |  | 14 | 2026-05-04 | 2026-05-07 | NA | Yes | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48817?base=2&iteration=3 | 2026-05-07 | 2026-05-07 | Ashwin | NA | Avery | 2026-05-07 | NA | POV done with Bavithra No Comment | NA | 04 May - Will start working on this defect. 04 May-EOD-Worked on analyzing and reproducing the issue, then started working on a fix. After that, the issue was resolved and tested on iPhone and iPad. Reviewed the code with Ashwin, and he suggested finding an alternative approach to resolve the problem. I will work with Sambath on this. 05 May - As ashwin suggested need to work with Sambath on this defect. 06 May - Ashwin sent message on slack for more clarification from Jason, waiting for reply. 07 May - As Sambath discussed with Ashwin, need to check on Meal Money page and Transaction Page, if it is not effect on these pages we will inform to client., Sambath also support me on the same today. 07 May - EOD - Merged, ready for test. QA team working on the main commit defects/stories follwed by regression testing. 08 Apr - Testing Completed | Exceeds Expectation | NA | Stretch
17 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | chandler/vaishnavi/ | 27320 | 27320 MSBP - Android - All text and sizes are inflated on pixel pro devices, sometimes pushing items off viewable area (26.5) | Defect Being Tested | 2 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This is issue is not reproduced in emaulator, need to test with device, so once received new device, i will continue to work. Waiting for new device to fix this issue. 7- May - will relate the new user stories to solve the correct way with responsive design. will relate the new epic which we'll refine. Added by RJ may be it could move to rejected status.. . 08-Apr - Prem/Vaishnavi - As per disucssion with Letashia, we will work on the testing with different devices.. 11-May - testing in progress. . 12-May- chandler working on the fix. 14-May- testing in progress. still facing few issues with pixel devices. will be sending those to letashia's review. |  |  | Main
18 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Prem | 52989 | MSB - Web - Parent Portal - Re-attach orphaned Invoices to students that were deleted and returned - MOBILE TESTING STORY | Story Completed | 2 |  | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 05 May - will start working on test case updation and will continue once the test case updation gets done 06 May - Test case updation and testing is completed | Exceeds Expectation |  | Main
19 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Jagdeep/vaishnavi | 52343 | [WAVE] MSBA - Kaleida - Update Offset Language - Difference(Over/Short) | Story Being Tested | 2 |  | 5 | 2026-05-05 | 2026-05-06 | NA | Amrit/Vashnavi | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48842 | 2026-05-05 | 2026-05-07 | Ashwin | NA | Avery | 2026-05-07 | NA | POV done with Bavithra No Comment | POV done with Jason No Comment | 05 May - Starting work on this story. 06 May - Will create apk file and will share to Vashnavi for internal testing with printer.(POV done , Story under peer review , waiting Approval from Ashwin and client side). 08 May - Story ready for testing.QA team working on the main commit defects/stories follwed by regression testing.. 12-May - Due to regression testing, testing is on hold for this story. |  | Due to regression testing and other high priority defects/stories, this story was not worked by the tester | Stretch
20 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Rupesh | 27234 | MSBA - Cart consolidated after promocode addition causing issue when allow user to set qty = no (26.7) | Defect Blocked | 2 |  | 4 | 2026-05-05 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 06 May - Development is in progress. 07 May - looks like api issue, I will get all the api response and see where it is breaking. 08 May - Ashwin asked me to try one approach(Same product with different stock option) and then see how orders are getting created. 11 May - Created a doc with all the possible scenarios, Ashwin reviewed and asked to make some changes. | Exceeds Expectation | When allow user to set qty = no (26.7) the issue is that the API result when applying promocode is combining the products into a single order. The fix for this should be that for products with allow user to set qty set to no should create separate orders for each product and not combine it under one order. Request: curl --location --request PUT 'https://test.www.myschoolbucks.com/mobilepay/3.0/checkout/process/' \ --header 'apiKey: EX87L7NSH3WM5X5FB25LMM1PBY5ELW' \ --header 'token: 94VWV2BY31EJYP5' \ --header 'mfaSessionKey: KH4AYWBNTIIKQR6' \ --header 'Content-Type: application/json' \ --header 'Cookie: JSESSIONID=YpWUueQMj9D00UJCi41sOKYJF07oXEwEi_gXVTnU.schoolbucks-cluster-5965cd768c-ktlbx; TS01dc4fc6=010e7b7cc2cf32352e80dfb1c4ca91a26abc4b34a2d73c7d46c0a91c1342c1bb6dcbd91c913ca9c8f24714f13e25787edf3de8a672' \ --data '{ "fundingDetailsInvoices": {}, "fundingDetailsMeals": {}, "storeItems": [ { "productRef": "KytlcCcpfSR1I3krJXdy", "quantity": 1, "unitPrice": 100.00, "stockOptionID": "opt1607", "studentKey": null, "formFields": null, "ignoreAddOn": false, "ignoreInventory": false, "ignoreSalesTax": false }, { "productRef": "KytlcCcpfSR1I3krJXdy", "quantity": 1, "unitPrice": 100.00, "stockOptionID": "opt1607", "studentKey": null, "formFields": null, "ignoreAddOn": false, "ignoreInventory": false, "ignoreSalesTax": false } ], "paymentMethodDetails": { "paymentMethodType": "Cash", "signatureImageFormat": "JPG" }, "promoCodeId": "regressiontest1", "appVersion": "15", "deviceDesc": "417591003b5efa57" }' Response: { "result": 1, "message": "", "basketKey": "", "programFee": 0.00, "salesTax": 0.00, "subtotal": 190.00, "subTotalBeforePromoCodes": 200.00, "promoCodeTotal": -10.00, "appliedPromoCodes": [ { "amount": 10.00, "quantity": -1, "amountIsPercentage": false, "minimumOrderTotal": 10.00, "name": "regressiontest1", "id": "regressiontest1", "desc": "", "error": "" } ], "failedPromoCodes": [], "orders": [ { "clientKey": "ZZJ22K7JR50ZCV3", "fees": 0.00, "salesTax": 0.00, "orderSubtotal": 190.00, "cardEntryType": [], "storeItems": [ { "studentKey": "", "imageLink": "", "name": "TestRupesh2", "unitPrice": 90.00, "unitPriceBeforePromoCode": 100.00, "amount": 90.00, "amountBeforePromoCode": 100.00, "quantity": 1, "availableQuantity": 1, "clientKey": "ZZJ22K7JR50ZCV3", "productRef": "KytlcCcpfSR1I3krJXdy", "productID": "prod448", "storeID": "10OQG", "clientID": "", "stockOptionID": "opt1607", "propertyValues": [] }, { "studentKey": "", "imageLink": "", "name": "TestRupesh2", "unitPrice": 100.00, "unitPriceBeforePromoCode": 100.00, "amount": 100.00, "amountBeforePromoCode": 100.00, "quantity": 1, "availableQuantity": 1, "clientKey": "ZZJ22K7JR50ZCV3", "productRef": "KytlcCcpfSR1I3krJXdy", "productID": "prod448", "storeID": "10OQG", "clientID": "", "stockOptionID": "opt1607", "propertyValues": [] } ], "invoiceItems": [], "mealPayments": [], "gatewayDetails": [ { "paymentMethodType": "cash", "userName": null, "password": null, "siteID": null, "licenseID": null, "deviceID": null, "developerID": null, "versionNumber": null, "url": null, "message": "Order not for (Chip/Contactless) credit card txn" } ] } ], "redirectUrl": "", "returnToSiteUrl": "" } After this when we try to checkout since the qty is changed the below API is throwing an error. curl --location 'https://test.www.myschoolbucks.com/mobilepay/3.0/checkout/paymentMethods' \ --header 'apiKey: EX87L7NSH3WM5X5FB25LMM1PBY5ELW' \ --header 'token: 94VWV2BY31EJYP5' \ --header 'mfaSessionKey: KH4AYWBNTIIKQR6' \ --header 'Content-Type: application/json' \ --header 'Cookie: JSESSIONID=3bTmR4zbXdLD6PJOXcyyd4m0kEZWnDxzbbmatjWD.schoolbucks-cluster-7d6d5594b-7nrrl; TS01dc4fc6=010e7b7cc2d0b63ca816bf6e93c45505976c7223911e6c4b234f37a1bd14afa6ff3a6e811f963dde0197c017fec585426131190645' \ --data '{ "storeItems": [ { "productRef": "KytlcCcpfSR1I3krJXdy", "quantity": 2, "unitPrice": 100.00, "stockOptionID": "opt1607", "studentKey": null } ] } Response: { "result": 2, "message": "Unable to create basket items from checkout request. Ex: KytlcCcpfSR1I3krJXdy:You are not allowed to set the quantity." } | Stretch
21 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Vaishnavi | 52988 | MSB - Web - Parent Portal - Allow Payment on Invoices for Deleted Students - MOBILE TESTING STORY | Story Completed | 3 |  | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 05 May - will start working on test case updation and will continue once the test case updation gets done. 06-May- will work on the testing. Had the doubts clarified from letashia yesterday. 07-As per Jason and troy discussion, this story can be closed as it needs a future enhancement. Will be confirming with Letashia and closing this story today. . 08-Apr - Prem/Vaishnavi - As per disucssion with Letashia, we will work on the testing with different devices. |  |  | Main
22 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Amrit/Gursewak | 27283 | MSBA - MAUI - iOS- meal payments screen changing formatting when cart preview is on with items in it | Defect Peer Review | 1 |  | 6 | 2026-05-08 | 2026-05-11 | NA | Gursewak | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48972 | 2026-05-11 | NA | NA | NA | NA | Na | NA | POV done with Bavithra No Comment | NA | 6 May - Reproducing and analyzing defect 7 May - Issue is in particular iPad 9 26.3.1 real device we will have to test internally in this device 8 May - TODO PEER Testing today 08 May -Gursewak - Support to Amrit for Peer testing. 11 May - Defect PR Created POV Pending 12 May - PR Approved by Rupesh pending from Samath 13 May - PR Approved by Rupesh pending from Samath 14 May - PR Pending from Client Side | Exceeds Expectation | Peer review | Stretch
23 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Jagdeep | 27276 | MSBP - Android - Can double click and open multiple stacks of menus | Defect Ready For Testing | 3 |  | 9 | 2026-05-06 | 2026-05-08 | NA | Gursewak | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48903 | 2026-05-07 | 2026-05-13 | Ashwin | NA | Avery | 2026-05-13 | NA | POV done with Bavithra No Comment | NA | 6 May- Starting work on this defect. 7 May - will continue work on this defect. 8 May - Defect under Peer review . 14 May - Defect ready for testing. |  | Due to regression testing and other high priority defects/stories, this story was not worked by the tester | Stretch
25 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Gursewak | 27015 | MSBA - MAUI - iphone - invoice add to cart button not formatted correctly (regression) | Defect Ready For Testing | 1 |  | 2.5 | 2026-05-08 | 2026-05-08 | NA | Yes | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48924 | 2026-05-08 | 2026-05-08 | NA | NA | NA | NA | NA | POV done with Bavithra No Comment | NA | 08 May, Start working on it, issue fixed, POV done, ready for review. 09 May - Ashwin marked the pull request as a draft 14 May - New release branch 26.5 is created, now change the branch, and ready for review. internal team review the PR. Ashwin and client side pending. 14 May - EOD - Merged, ready for test now. | Exceeds Expectation | NA | Stretch
26 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Amrit | 27006 | MSBA - MAUI - iOS - Cart has extra space underneath buttons (regression) | Defect Peer Review | 1 |  | 6 | 2026-05-08 | 2026-05-11 | NA | Gursewak | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48926 | 2026-05-11 | NA | NA | NA | NA | NA | NA | POV done with Ashwin No Comment | NA | 8 May - Analyzing and reproducing defect 11 May - Defect ready for PEER Review 12 May - PR In Review 13 May - PR Pending Internal review 14 May - PR Pending from Ashwin and Client Side | Exceeds Expectation | Peer review | Stretch
27 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Jagdeep | 27255 | MSBP - missing phone number page and profile phone pages do not match | Defect Peer Review | 1 |  | 3 | 2026-05-08 | 2026-05-11 | NA | Amrit | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/49015 | 2026-05-11 | NA | NA | NA | NA | NA | NA | POV done with Bavithra No Comment | NA | 11 May - requirement cleared today will work and complete it. 12 May - Defect under peer review.(Sambath , ashwin, and client side pending). 14 May - Waiting for aproval from Ashwin and Client side. |  | Defect fixed still PR in Review, Ashwin and client side review pending | Stretch
28 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Gursewak | 26881 | MSBA - Cart icon/badge is larger than expected (regression) | Defect Ready For Testing | 1 |  | 4.5 | 2026-05-08 | 2026-05-11 | NA | Yes | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48932 | 2026-05-11 | 2026-05-11 | NA | NA | NA | NA | NA | POV done with Bavithra No Comment | NA | 08 May- Working on it. 11 May - Will fix this issue, do the POV, and create the PR. 12 May - Ashwin and client side review pending. 14 May - New release branch 26.5 is created, now change the branch, and ready for review. internal team review the PR. Ashwin and client side pending. 14 May - EOD - Merged, ready for test now. | Exceeds Expectation | NA | Stretch
29 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 Stretch | Vaishnavi/Prem | 53092 | REG - MSBP - Regression 26.5 | Story Being Tested | 8 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 12-May - Will work on the testing today. 14-May - Testing in progress. Vaishnavi - As per letashia, defect 27320 needs to be completed first, will be working on that. later will work on the pending regression test cases. |  |  | Stretch
30 | MSB Mobile Kaleida | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Jagdeep | 27389 | MSBP - MAUI - Android - Cart icon showing the badge count when no items available in the shopping cart (regression) | Defect Fixed | 0 |  | 4 | 2026-05-13 | 2026-05-13 | NA | Gursewak | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/49020 | 2026-05-13 | 2026-05-13 | Ashwin | NA | Avery | 2026-05-13 | NA | POV done with Ashwin No Comment | NA | 13 May - Start work on this defect. 14 May - Defect ready for testing. |  |  | Main
31 | MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Rupesh | 27394 | MSBA - stock option formatting issues (regression) | Defect Peer Review | 0 |  | 8 | 2026-05-13 | [16 empty] | 13 May - will analyse and then start the development. 14 May - will try to fix it and run the POV today. |  | Picked up on 13th May as this regression defect was created at the last moment. | Main
| MSB Mobile | 2026-05-01 | 2026-05-14 | 26.5 M Sprint 3 | Dev Team | 87660 | MSB Mobile - Exploratory Testing | Story Completed | 8 |  | 62

## 26.5 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.5 M Sprint 3 | 26882 MSBA - Cart Icon does not have the correct MSBA blue background | 26882 MSBA - Cart Icon does not have the correct MSBA blue background | Amrit/ | Defect |  | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 3 Stretch | 27318 MSBA - Kaleida - I/A - Unable to navigate back from Admin Settings when shift is already active | 27318 MSBA - Kaleida - I/A - Unable to navigate back from Admin Settings when shift is already active | Gursewak/Sambath | Defect |  | Minor | Manual | Internal | Closed | Development | Relevantz QA | Maui to Kaleida conversion defects
| 26.5 M Sprint 3 | 27320 MSBP - Android - All text and sizes are inflated on pixel pro devices, sometimes pushing items off viewable area (26.5)" | 27320 MSBP - Android - All text and sizes are inflated on pixel pro devices, sometimes pushing items off viewable area (26.5)" | chandler | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 3 Stretch | 27234 MSBA - Cart consolidated after promocode addition causing issue when allow user to set qty = no (26.7) | 27234 MSBA - Cart consolidated after promocode addition causing issue when allow user to set qty = no (26.7) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Enhancement
| 26.5 M Sprint 3 Stretch | 27283 MSBA - MAUI - iOS- meal payments screen changing formatting when cart preview is on with items in it | 27283 MSBA - MAUI - iOS- meal payments screen changing formatting when cart preview is on with items in it | Amrit/Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 3 Stretch | 27276 MSBP - Android - Can double click and open multiple stacks of menus | 27276 MSBP - Android - Can double click and open multiple stacks of menus | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 3 Stretch | 27015 MSBA - MAUI - iphone - invoice add to cart button not formatted correctly (regression) | 27015 MSBA - MAUI - iphone - invoice add to cart button not formatted correctly (regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Regression defects
| 26.5 M Sprint 3 Stretch | 27006 MSBA - MAUI - iOS - Cart has extra space underneath buttons (regression) | 27006 MSBA - MAUI - iOS - Cart has extra space underneath buttons (regression) | Amrit | Defect |  | Minor | Manual | Internal | Inprogress | Development | Relevantz QA | Regression defects
| 26.5 M Sprint 3 Stretch | 27255 MSBP - missing phone number page and profile phone pages do not match | 27255 MSBP - missing phone number page and profile phone pages do not match | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 3 Stretch | 26881 MSBA - Cart icon/badge is larger than expected (regression) | 26881 MSBA - Cart icon/badge is larger than expected (regression) | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Regression defects
| 26.5 M Sprint 3 | 27389 MSBP - MAUI - Android - Cart icon showing the badge count when no items available in the shopping cart (regression) | 27389 MSBP - MAUI - Android - Cart icon showing the badge count when no items available in the shopping cart (regression) | Jagdeep | Defect |  | Minor | Manual | Internal | Closed | Development | Relevantz QA | Regression defects
| 26.5 M Sprint 3 | 27394 MSBA - stock option formatting issues (regression) | 27394 MSBA - stock option formatting issues (regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Regression defects

## 26.5 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Sean/ Vaishnavi | 51966 | [WAVE] MSBA - Kaleida - Settings - Apps & Stores | Story Being Developed | 5 |  |  | 2026-02-18 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47478 | 25/2/2026 | 2026-03-13 | Ashwin | NA | Avery | 2026-03-20 | NA | POV done with Bavithra |  | 20- Apr - Rupesh - Ashwin assigned this defect to Rupesh, will be continuing on that. This story will be on hold until defect 27072 is completed. 24 Apr - BB testing is in progress. 27 - Apr - will do a round of testing except the BB which was work by Sean. 28 -Apr - Still the BB fix by the onsite developer is in progress. Waiting for the fix. |  |  | Main
2 | MSB Mobile | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Rupesh/Prem | 52056 | MSBA - Close Out - Offer Portrait and Landscape Orientation | Story Completed | 3 |  | 20 | 2026-03-16 | 2026-04-23 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48454 | 2026-04-16 | 2026-04-23 | Ashwin | Use common color | Avery | 2026-04-23 | NA | POV done with Bavithra | NA | 17 Apr - Few BB’s are fixed, will be working on remaking ones Today. Raised the PR, pending from Ashwin. 21: Resolved Ashwin PR comments and implemented copilot PR suggestions. Ashwin approved it , pending from client side. 23 Apr - testing completed | Exceeds Expectation |  | Main
3 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Jagdeep/Vaishnavi | 51972 | [WAVE] MSBA - Kaleida - Settings - Admin Settings | Story Completed | 2 |  | 12 | 2026-03-24 | 2026-04-13 | NA | NA | NA | Rupesh/Sambath | Count - 2 * don't hard code the sales tag method DiscardIncompleteFields instead of pass from cancelButtonAction paramsdon't hard code the sales tag method DiscardIncompleteFields instead of pass from cancelButtonAction params * move to AdminSettings validation rule | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48410 | 2026-04-07 | 2026-04-15 | Ashwin | NA | Avery | 2026-04-13 | NA | Count - 3 POV done with Bavithra with solved comments:- 1. “School Number and Custom Label value should show if we already selected and come back on the screen. 2. Text not matching in Record sales tag section. 3. Search bar width and custom label entry width looking different | POV Done with JASON No Comments | 17 April - Will fix and done POV and will create PR. 20Apr- will work on this story after completing testing defect 27078.. 21-Apr - Completed testing in all devices. will close it shortly. | Exceeds Expectation |  | Main
4 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Amrit/Vaishnavi | 51967 | [WAVE] MSBA - Kaleida - Settings - Item Visibility | Story Completed | 2 |  | 2 | 2026-03-24 | 2026-04-06 | Na | NA | NA | Rupesh/Sambath | Ashwin - The assignment is redundant since DisplayFeaturedItems already has that value. (3) | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48175 | 2026-01-04 | 15/4/2026 | Ashwin | NA | Avery | 2026-04-14 | NA | POV Done with JASON No Comments | Na | 17-Apr- Testing in progress. EOD - Testing completed. | Exceeds Expectation |  | Main
5 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Gursewak/Vaishnavi | 51968 | [WAVE] MSBA - Kaleida - Settings - Cart and Transactions | Story Completed | 3 |  | 17.5 | 2026-03-24 | 2026-04-14 | NA | Yes | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48183 https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48183 | 2026-04-14 | 2026-04-14 | Ashwin | NA | Avery | 2026-04-15 | Avery Comments (2) Save/Load key mismatch (missing CurrentUserId suffix) • Count: 3 Missing blank line before next property definition • Count: 3 | POV done with Bavithra No Comment | NA | 17-April- Working on the same BB. 17 Apil - BB fixed, POV done, created PR, PR merged & ready for test.. 21-Apr-Will work on the testing today 27 April - Gursewak - As discussed with Ashwin, start working on BB on this story - Required signature field value is not clearing after enabling/disabling the toggle when user has entered some amount and save previously. 27-Apr - Testing in progress. 27-Apr-EOD- Below two BB has been fixed. - Required signature field value is not clearing after enabling/disabling the toggle when user has entered some amount and save previously - Discard and Stay & complete button loaded after showing some incorrect button name at first Both are merged, and ready for test.. 28-Apr - BB testing in progress. | Exceeds Expectation | This story took more time than estimated because additional bugs were identified during testing, requiring further fixes, POV validation, PR creation/merge, and multiple testing cycles. Extra effort was also needed to resolve newly reported issues related to toggle behavior, field value clearing, and incorrect button labels before final validation. | Main
6 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Jagdeep/vaishnavi | 27078 | 27078 MSBA - MAUI - android phone - app crash when trying to apply filters (regression) | Defect Fixed | 2 |  | 2 | 2026-04-01 | 2026-04-15 | NA | NA | NA | Rupesh/Sambath | Count: 1 why ExecuteGroupsStores was removed, Group filter is required after changing the stores | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48418 | 2026-04-15 | 2026-04-17 | Ashwin | NA | Avery | 2026-04-17 | NA | "POV done with Ashwin No Comment" | POV Done with Bavithra No Comments | 17 April - Will fix and done POV and will create PR. 20Apr- will work on this story after completing testing defect 27078. 06 - April - not yet started to work 14 - April - Today will investigate and try to find root cause and then will work for fix it. 15 - April - First will work for BB coming on story 51972 then will start continue work on it. 15 - April - Work with Jagdeep on the defect. 16- April - As Ashwin suggestion , reverted all performance based changes only kept bug fixes related changes.(defect now Peer a review ) 20 April - Defect ready for testing. | Exceeds Expectation |  | Main
8 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Prem/Gursewak | 52194 | [WAVE] MSBA - Kaleida - Update Shift Mode Status Icons on Top Header Bar | Story Completed | 2 |  | 23.5 | 2026-03-16 | 2026-04-24 | NA | Yes | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48615 | 2026-04-24 | 2026-04-24 | Ashwin | NA | Avery | 2026-04-24 | NA | POV done with Ashwin No Comment | NA | 17 Apr - tested and raised a BB. and assigned top dev fix the same 22 Apr - Tested and still the BB exists. Reassigning back to dev to fix the same 23 Apr - Fixed BB - Android - Mobile - Buttons (Shift On/Off), Cart, Search) shows bigger which is overlapping with the header text. Added screenshot for reference, Created PR, and it is merged. 24 Apr - Start work on BB - Clock icon being cut off in shift mode status icon on Top header bar in Android tablet 24 Apr - BB testing is in progress 24 Apr-EOD-Clock icon being cut off in shift mode status icon on Top header bar in Android tablet issue has been already fixed. tested On BS today i checked on all Samsung tabs like:- Galaxy Tab S7 11, Galaxy Tab S8 12, Galaxy Tab S9 13, Galaxy Tab S9+ 14, Galaxy Tab S10+ 15, Galaxy Tab S11 16 27 Apr - Testing Completed | Exceeds Expectation | Story #52194 took more time than estimated because multiple UI issues were identified during testing, requiring additional fixes, re-testing, and validation across different Android devices and Samsung tablets to ensure the top header status icons worked correctly on all supported devices. | Main
9 | MSB Mobile | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Amrit | 27019 | MSBA - MAUI - phones - cannot drag to sort products | Defect Fixed | 3 |  | 14 | 2026-04-15 | 2026-04-16 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48491 | 2026-04-17 | 2026-04-20 | Ashwin | NA | Avery | 2026-04-20 | Avery 1 targetItem should be verified as ProductSummary type before passing to ReorderProductAsync. Should be reverted to: if (_draggedItem is ProductSummary sourceProduct && targetItem is ProductSummary targetProduct) | NA | POV Done with Bavithra No Comments | 17 Apr - Testing done, POV Done , PR Created 20 Apr - Working on PR Comments, PR Merged | Exceeds Expectation |  | Main
11 | MSB Mobile | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Amrit/Prem | 52344 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Hamburger Menu | Story Being Developed | 3 |  | 8.5 | 2026-04-20 | 2026-04-22 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48532 | 2026-04-26 | NA | Sambath | NA | Avery | NA | Avery Comments (17) Remove unnecessary Grid wrappers • Count: 7 Redundant Command / CommandParameter on CustomMenuItem • Count: 6 Use proper Kaleida styles (KLabelFootnote / KLabelSectionHeader) • Count: 2 Use proper component (KCircleButton for close button) • Count: 1 Component consistency / standard Kaleida pattern • Count: 1 | POV done with Bavithra No Comment | NA | 20 Apr - Will start after compleing 27019 21 Apr - Working on Component Changes 22 Apr - Status is Product Owner Verifying . Amrit is fixing few spaces issue for android and update PR 23 Apr - Need to do PEER testing by Jagdeep and Peer Review, POV with Bavithra 24 Apr - PR Level 1 Approved , Pending from Level 2 and 3 25 Apr - PR Pending from Level 3 28 Apr - Working on PR Comments 29 Apr - Tested and raised a BB. And assigned the same to dev 30 Apr - Will Test and fix scrolling issue in Pixel device | Exceeds Expectation | Space Issue in only android small devices, which can take some time to fix, 90% done | Stretch
12 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Jagdeep | 27204 | MSBA - MAUI- iOS - Transparency issue in iOS on clicking shift mode icon. (26.5) | Defect Fixed | 2 |  | 6 | 2026-04-20 | 2026-04-20 | NA | Yes | Rupesh | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48519 | 2026-04-20 | 2026-04-20 | Ashwin | NA | Avery | 2026-04-20 | NA | "POV done with Ashwin No Comment" | NA | 20 April - Will reproduce the issue and start work to fix this defect. 21 April - Defect ready for testing. | Exceeds Expectation |  | Main
13 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Gursewak | 26762 | MSBP - allows identical Routing # and Account # for eCheck Autopay, causing silent payment failure and missing notifications. | Defect Fixed | 2 |  | 5.5 | 2026-04-20 | 2026-04-20 | NA | Yes | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48514 | 2026-04-20 | 2026-04-20 | Ashwin | NA | Avery | 2026-04-20 | NA | POV done with Bavithra No Comment | NA | 20 April - I will analyze the issue, reproduce it, and start working to fix this defect. 20 april - EOD - Development completed, did POV, Created PR, PR merged, Ready for test. | Exceeds Expectation |  | Stretch
14 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Gursewak | 52346 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Header | Story Being Developed | 2 |  |  | 2026-04-21 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48736 | 2026-04-29 | NA | NA | NA | NA | NA | NA | NA | NA | 21 April - Start working on it. 21 April - EOD - Worked on this story, development is completed, did the POV with Vaishnavi. During the POV we found issue on tablet, large District name is cut off. working on it. 22 April - District name cut off in tablet, need to fix the issue in KStatusChip, working on it. after that will do the POV and will create PR. 24 Apr - Not work on this story today, becuase 52194 story BB need to fix on first prority. 27 Apr - Not working on this story due to BB on the story 51968, working on BB on story 51968 28 Apr - Start working on the pending work on this story, will merge the Kaleida branch, and try to complete and did the POV. 29 Apr - Will start work on BB on this story 30-Apr-Doing testing, did the POV, after that create PR. 30 Apr-EOD- Development is complete, including fixes for the Android header white space issue, while another reported issue could not be reproduced and was verified with QA. Testing has been completed across all devices (Android/iOS, phone and tablet), along with peer testing and POV | Exceeds Expectation | NA | Stretch
16 | MSB Mobile | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Sambath | 52347 | 52347 [WAVE] MSBA - Update Components/Fonts to Kaleida - Transaction History | Story Being Developed | 8 |  |  | 2026-04-21 | [16 empty] | 21 - Apr - Startred to working on this story 22 - Apr - Working with tablet UI changes 23- Apr - Working with tablet design changes, 24- Apr - Tested desing for tablet, and started wokring on phone design 27 - Apr - Contiue to working with Phone design changes 28 - Apr - Worked Phone design and testing is in-progress 29 - Apr - Dev Testing is in-progress. 30 - Apr - Fixing the POV changes, testing issues
17 | MSB Mobile | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Rupesh | 52348 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Forgot Login Workflow | Product Owner - Verify | 3 |  | 14 | 2026-04-22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | POV done with Ashwin No Comment | NA | 22 Apr - Will start development today. 27 Apr - Will try to finish remaining steps as first 2 steps has been done. 28 Apr - Will request for peer testing and then will have POV. 29 Apr - Will share the POV with client today and then raise the PR today, shared the screen recording with Ashwin and he confirmed it looks okay. 29 Apr : POV pending from Jason side. | Exceeds Expectation |  | Stretch
15 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Jagdeep | 27257 | MSBP - Android - App navigation hidden under phone navigation (release defect) | Defect Fixed | 0 |  | 6 | 2026-04-21 | 2026-04-21 | NA | Yes | Rupesh | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48539 | 2026-04-21 | 2026-04-22 | Ashwin | NA | Avery | 2026-04-22 | NA | "POV done with Vashnavi No Comment" | NA | 21 April - First will try to reproduce and will start work on it. 22-Apr- Letashia will be testing this. need to check this with Ashwin | Exceeds Expectation |  | Main
18 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Jagdeep | 27088 | MSBP - A - Button does not turn blue even after meeting the entry requirements (regression) | Defect Fixed | 0 |  | 6 | 2026-04-23 | 2026-04-24 | NA | Yes | Rupesh | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48632 | 2026-04-24 | 2026-04-24 | Ashwin | NA | Avery | 2026-04-24 | NA | POV done with Bavithra No Comment | NA | 23 April - First will reproduce then will start work on it.(Tested but not reproduced issue informed to QA so hold it and working with Gursawek on stroy 52346. 24 April- Now able to reproduce with different repro steps after discussion with Latisha and Ashwin , today will work on it and will fix it.. 27 - Assigned to Letashia | Exceeds Expectation |  | Main
19 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 | Gursewak | 27275 | MSBP - Android - Add to cart button in invoices under nav bar after adding invoice (release defect) | Defect Fixed | 0 |  | 3.5 | 2026-04-23 | 2026-04-23 | NA | Yes | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48619 | 2026-04-23 | 2026-04-23 | Ashwin | NA | Avery | 2026-04-23 | NA | POV done with Ashwin No Comment | NA | 23 April - Start working on it. 23 April - EOD - Development completed, PR merged, ready for test. | Exceeds Expectation | NA | Main
20 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Amrit/Vaishnavi | 52516 | MSBP - Wrap Product Name Text on Store Page to the 3rd line | Story Completed | 1 |  | 3.5 | 2026-04-24 | 2026-04-24 | NA | Yes | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48629 | 2026-04-24 | 2026-04-24 | Ashwin | NA | Avery | 2026-04-25 | NA | POV done with Bavithra No Comment | NA | 23 April - Start working on it. After 52334 24 Apr - Will be testing in all devices then will do POV and Create PR. 28 - Apr - Testing in progress. | Exceeds Expectation |  | Stretch
21 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Amrit/Vaishnavi | 52726 | MSBA - Settings - Update Optimal Settings Message | Story Completed | 1 |  | 1.5 | 2026-04-27 | 2026-04-27 | NA | Yes | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48655 | 2026-04-27 | 2026-04-27 | Ashwin | NA | Avery | 2026-04-28 | NA | POV done with Bavithra No Comment | NA | 27 Apr - Working on story, PEER Testing DONE by Rupesh. 29-Apr- Will be starting the testing. | Exceeds Expectation |  | Stretch
22 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Amrit | 52633 | MSBP - Store Catalog - General header changed to Products | Story Peer Review | 1 |  | 1.5 | 2026-04-27 | 2026-04-27 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48662 | 2026-04-27 | 2026-04-27 | Ashwin | NA | NA | NA | NA | POV done with Bavithra No Comment | NA | 27 Apr - Working on story - PEER Testing Pending 28 Apr - PEER Testing will be done with Jagdeep 29 Apr - Working on changes told by Ashwin for check value 30 Apr - PR Pending from Ashwin and Client | Exceeds Expectation |  | Stretch
23 | MSB Mobile | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Avery/Prem | 52345 | [WAVE] MSBA - Update Components/Fonts to Kaleida - Bottom Nav | Story Completed | 1 |  | 19.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 28 Apr - Testcase updation is in progress. And will start testing once test case updation gets done. Raised a BB and assigned back to dev 30 Apr - Testing is in progress | Exceeds Expectation
24 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Jagdeep/Vaishnavi | 27033 | MSBA - MAUI - error presented after logo | Defect Fixed | 2 |  | 6 | 2026-04-28 | 2026-04-29 | NA | Yes | Rupesh | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48698 | 2026-04-28 | 2026-04-29 | Ashwin | NA | Avery | 2026-04-29 | NA | POV done with Bavithra(By Shared Video) No Comment | NA | 28 April - Will reroduce first then will start work on it. 29 April - will do peer a testing with Rupesh ,if found any issue then will work.. 30-Apr-WIll work on the testing. |  |  | Stretch
25 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Amrit | 26882 | MSBA - Cart Icon does not have the correct MSBA blue background | Defect Peer Review | 1 |  | 0 | 2026-04-29 | NA | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48721 | Na | NA | NA | NA | NA | NA | NA | NA | NA | 29 Apr- Defect Fixed, Sent for peer testing 30 Apr - PR Ready for Review for internal |  |  | Stretch
26 | MSB Mobile | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Rupesh | 52964 | MSBA - Admin Settings - BETA build - Require Elevated Privileges | Story Being Developed | 5 |  | 12 | 2026-04-29 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 29 Apr - started analysing and then willd o the development. 30 Apr - Will continue the development and try to run the internal POV by EOD today. | Exceeds Expectation |  | Stretch
27 | MSB Mobile Kaleida | 2026-04-17 | 2026-04-30 | 26.5 M Sprint 2 Stretch | Jagdeep | 48498 | [WAVE] MSBA - Receipt Screen - Show Confirmation/Green Check once SMS/Email Sent | Story Being Developed | 1 |  | 2 | 2026-04-30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 30 April - Started work on it in sprint last day, Still working on it. |  | This Story took last day of sprint, so still continue working on it . Testing , POV , peer testing pending so it will goes into next sprint. | Stretch

## 26.5 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.5 M Sprint 2 | 27078 MSBA - MAUI - android phone - app crash when trying to apply filters (regression) | 27019 MSBA - MAUI - phones - cannot drag to sort products | Jagdeep/vaishnavi | Defect |  | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 2 | 27019 MSBA - MAUI - phones - cannot drag to sort products | 27204 MSBA - MAUI- iOS - Transparency issue in iOS on clicking shift mode icon. (26.5) | Amrit | Defect |  | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 2 Stretch | 27204 MSBA - MAUI- iOS - Transparency issue in iOS on clicking shift mode icon. (26.5) | 26762 MSBP - allows identical Routing # and Account # for eCheck Autopay, causing silent payment failure and missing notifications. | Jagdeep | Defect |  | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 2 | 26762 MSBP - allows identical Routing # and Account # for eCheck Autopay, causing silent payment failure and missing notifications. | 27257 MSBP - Android - App navigation hidden under phone navigation (release defect) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Enhancement
| 26.5 M Sprint 2 | 27257 MSBP - Android - App navigation hidden under phone navigation (release defect) | 27088 MSBP - A - Button does not turn blue even after meeting the entry requirements (regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Production defects
| 26.5 M Sprint 2 | 27088 MSBP - A - Button does not turn blue even after meeting the entry requirements (regression) | 27275 MSBP - Android - Add to cart button in invoices under nav bar after adding invoice (release defect) | Jagdeep | Defect |  | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 2 | 27275 MSBP - Android - Add to cart button in invoices under nav bar after adding invoice (release defect) | 27033 MSBA - MAUI - error presented after logo | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Production defects
| 26.5 M Sprint 2 Stretch | 27033 MSBA - MAUI - error presented after logo | 26882 MSBA - Cart Icon does not have the correct MSBA blue background | Jagdeep/Vaishnavi | Defect |  | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 2 Stretch | 26882 MSBA - Cart Icon does not have the correct MSBA blue background | 26882 MSBA - Cart Icon does not have the correct MSBA blue background | Amrit | Defect |  | Minor | Manual | Internal | Inprogress | Development | Client QA | Xamarin to Maui conversion defects

## 26.5 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Sambath/ Vaishnavi/Rupesh | 51966 | [WAVE] MSBA - Kaleida - Settings - Apps & Stores | Story Being Developed | 2 |  | 25.5 | 2026-02-18 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47478 | 25/2/2026 | 2026-03-13 | Ashwin | NA | Avery | 2026-03-20 | NA | POV done with Bavithra |  | 3-Apr - Testing in progress. . 7-Apr - BB testing in progress. 7 Apr - (Amrit)- Worked as supportive for Redirection issue 08 - April - Gursewak - Will work on BB Android/iphone - when scrolling through the settings screen, able to see some white spaces at top and bottom 08-April-EOD-Gursewak-Development completed, tested, did POV with Bavithra, Created PR. (Ashwin marked PR draft -09 April) 09-Apr Sambath - Working with bounce backs, 10 - one BB fixed, that has been approved. . 13 - Apr - Will be testing the 1 bb which was fixed. 15 - Apr - Sambath - Working with New BB 16- Apr - Sambath - Continue to working with BB This story will be on hold until defect 27072 is completed. |  | Wait for the Kaleida merge from the develop branch before starting the test. and This story will be on hold until defect 27072 is completed. New Bounce back has been added by letaisa. The testing and fixing the bounce backs took longer than originally estimated | Main
2 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Rupesh/Amrit/Prem | 52056 | MSBA - Close Out - Offer Portrait and Landscape Orientation | Story Being Developed | 3 |  | 32.75 | 2026-03-16 | NA | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47877 | 2026-03-18 | 2026-04-13 | Ashwin | NA | Avery | 2026-04-14 | NA | POV done with Bavithra | NA | Yet to check with Ashwin to check the priority. 08 Apr : I will be starting once done with the POV of 27120. 09 Apr : I will be working on the UI issues, found during unit testing. 10 Apr : Will run a POV with Bavithra. 13 Apr : Got some suggestion on my PR from Ashwin, looks like PR has been reviewed on complete file not for my changes only. I will fix the applicable ones. 15 Apr - Tested and raised a BB. And informed to dev to fix the same 16 Apr - Testing and raised a new BB's and assigned back to dev to fix the same | Exceeds Expectation | Bounce backs received, will be carriying forward to next sprint because of BB's. | Main
3 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Jagdeep/Vaishnavi | 51972 | [WAVE] MSBA - Kaleida - Settings - Admin Settings | Story Being Developed | 3 |  | 13 | 2026-03-24 | 2026-04-13 | NA | NA | NA | Rupesh/Sambath | Count - 2 * don't hard code the sales tag method DiscardIncompleteFields instead of pass from cancelButtonAction paramsdon't hard code the sales tag method DiscardIncompleteFields instead of pass from cancelButtonAction params * move to AdminSettings validation rule | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48410 | 2026-04-07 | 2026-04-15 | Ashwin | NA | Avery | 2026-04-13 | Count - 6 1. This PR implements a custom popup using Telerik RadBorder instead of the Kaleida Components KModal * This is only cleared in OnAppearing() but is never used anywhere in the codebase. Remove it and it's usage on line 1031 * Under what scenario would AppSession.UserSettings be null anywhere in SettingsViewModel? If it's never null, remove all the defensive checks. If it can be null, add a guard at OnAppearing instead of scattered checks. * One line - Please format this line properly * This is handled above, no need for the duplicate, could cause race conditions. Delete these lines. * This command is overcomplicated for toggling a radio button. The validation, school lookups, and error handling should live in the property setters and existing validation commands, not in a 70+ line selection handler. Can this be simplified? * These three admin toggle commands (ShiftModeToggledCommand, AllowOversellToggledCommand, CloseDayBlindCountToggledCommand) are architecturally redundant: | Count - 3 POV done with Bavithra with solved comments:- 1. “School Number and Custom Label value should show if we already selected and come back on the screen. 2. Text not matching in Record sales tag section. 3. Search bar width and custom label entry width looking different | POV Done with JASON No Comments | 08 April - Starting work on this defect. 09 April - development completed , Internal PR approved , waiting for client approval. 03 April- First will close my opened regression defect. 06 April - This story still on hold today first will completed the defect 27087 then will start work on it. 07 April - Will continue work on this story and will do internal and external POV today. 08 April - Story under Peer a Review. 09 April - Will work for resolve PR comments regarding Required field popup and remove background image for phone device . 10 April - Story PR approved by Rupesh and Sambath , pending from Ashwin and client side. 14 April - Story ready for testing. will work on the testing. 15 Apr - Testing in progress. 15 April - Will work on BB If found during testing. 16-Apr - Will test this after completing the defects testing. 16 April - Will work on BB issues. |  | Major functionality is complete, but QA testing revealed bounce-backs related to sales tag format. These fixes, along with the required POV validation, will extend beyond the current sprint and will go next sprint. | Main
4 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Amrit/Vaishnavi | 51967 | [WAVE] MSBA - Kaleida - Settings - Item Visibility | Story Being Tested | 2 |  | 20 | 2026-03-24 | 2026-04-06 | Na | NA | NA | Rupesh/Sambath | Ashwin - The assignment is redundant since DisplayFeaturedItems already has that value. (3) | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48175 | 2026-01-04 | 15/4/2026 | Ashwin | NA | Avery | NA | Avery Comments(7) Use CurrentUserId instead of AppSession.UserSettings.UserId • Count: 3 Missing AutomationId in toggle switches • Count: 3 Load/Save mismatch for ShowAllStudentsInInvoice • Count: 1 (Critical) XAML structure not following standard pattern • Count: 1 | POV Done with JASON No Comments | Na | 3 Apr - Continue working on Story 6 Apr- Continue working on story 7 Apr - Story Peer Review (Doing some testings with multiple users) 8 Apr - Working on PR comment given by Ashwin 9 Apr- PR Pending from Ashwin and Client 10 Apr - Will solve merge conflicts 13 Apr - Working on save command changes as suggested by Avery 14 Apr - Working on PR Comments and testing 15 Apr - PR Merged story ready for testing 15 Apr - Will work once the 52056 gets done. 16-Apr - Testing in progress. Completed testing in Android and iOS tablet. Execution pending in Mobile devices and iOS18 devices | Exceeds Expectation | Testing in progress. Completed testing in Android and iOS tablet. Execution pending in Mobile devices and iOS18 devices. Will not be able to close it today as I need the obsevation clarified from letashia inbetween. | Main
5 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Gursewak | 51968 | [WAVE] MSBA - Kaleida - Settings - Cart and Transactions | Story Being Developed | 3 |  | 25 | 2026-03-24 | 2026-04-14 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48183 | 2026-04-14 | 2026-04-14 | Ashwin | NA | Avery | 2026-04-15 | Avery Comments (6) Save/Load key mismatch (missing CurrentUserId suffix) • Count: 3 Missing blank line before next property definition • Count: 3 | POV done with Bavithra No Comment | NA | 06 April - Start working on it today, will try to completed and do the POV. 07 April - Some functionality is pending while entering amount on the same page, will work on it, and complete and do the POV and create PR. 08 April - POV done with Bavithra, Also sent the POV video in slack group for client review, but not recieve any feedback yet. Will do code cleaning and create the PR. after that will work on BB scrolling issue on the settings screen 09-April-Jason added comment under POV video for update the new design (POV - Update the Portrait/landscape phone view to be borderless, working on it. https://www.figma.com/design/r24M7rgybpJJgMyntCNhwJ/MSB-Anywhere?node-id=1926-14689&t=QUAXe1OLdPmd88kg-0) 10-April - Ashwin sent comment on slack (Avery has checked in into the MSBA Kaleida branch which is causing conflicts in your PRs. So merge the latest and update the PR.) work on it. also complete the validation process on popup. 13 April - Waiting for merge "51972" story. 14 April - This story "51972" has been merged. Today, I will pull the latest code, merge it into my branch, resolve any merge conflicts, make the necessary code changes, test them, and then create the POV and publish the PR for review. 15 April - Client review pending. 15 April-EOD-Merged, ready for testing.. 16-Apr- Testers will pick this after competing the pending defects and stories. 16 April - Working on BB - App crash when user Deleting the value from required signature field after entering the amount | Exceeds Expectation | The story took additional time due to design changes after POV, delayed client feedback, merge conflicts, and dependency on story 51972 (Admin Settings). Final implementation and testing could only be completed after that story was merged. | Main
6 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Gursewak/Amrit/Prem | 27052 | MSBA - MAUI - Android - unable to read entire product description (regression) | Defect Fixed | 0 |  | 11.5 | 2026-03-27 | 2026-04-02 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48200 | 2026-04-03 | 2026-04-03 | Ashwin | NA | Avery | 2026-04-03 | NA | POV done with Bavithra No Comment | NA | 27 March - Will work, test, do the POV and create the PR 27 March-EOD - Completed defect 27063, start workin on the it, issue has been fixed, facing scrolling issue in iOS trying to resolve it. 30 March - Today will try on fix the scroll issue in iOS, test the defect, do the POV and will create the PR. after that will start work on 51968 31 March - This issue been fixed, Testing and POV pending, will complete today. 01 april - internal and external review pending. 02 April - As discussed with Ashwin on call, Amrit will work on today on same task. Defect Fixed POV DONE, PR Created 06 Apr - Testing Completed | Exceeds Expectation | NA | Main
7 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Sambath/Avery | 27072 | MSBA - MAUI - Android - Bottom navigation icons are showing the icons which were not enabled from the Settings menu(regression) | Defect Being Fixed | 0 |  | 20 | 2026-03-30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 6 April- Started working with this defect as discussed with ashiwn 7 - April - found the root cause of the defect, and started fixing. 8- Apr - Fixed the issue and testing is pending 13 - Apr - Fixed the issue, waitng for PR resoution 13 Apr - Amrit - First will finish 51967 changes for save commands then will try to check this defect 14-Apr - Sambath - going to work with Avery comments |  | This defect has been fixed, but avery took this defect for further investication so it will not be included in the current release. It is planned for the next release due to major changes in the login flow, so for now it is looking by avery | Main
8 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Gursewak/vaishnavi | 27001 | MSBA - MAUI - phones - now only displaying 3 products in landscape (regresssion) | Defect Fixed | 0 |  | 6 | 2026-04-01 | 2026-04-01 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48166 | 2026-04-01 | 2026-04-01 | Ashwin | Avery Comments (3) Event handler not unsubscribed in OnDisappearing() • Count: 1 Duplicate property (already exists in ViewModelBase) • Count: 1 XAML margin formatting should be Margin="5, 10" • Count: 1 | Avery | 2026-04-02 | This needs to be unsubscribed. Add in OnDisappearing(): This property is identical to CurrentDeviceOrientation already defined in ViewModelBase (which this class inherits from). Remove these lines and use the inherited property instead. | POV done with Bavithra No Comments. | NA | 3-Apr - Testing in progress. | Exceeds Expectation | NA | Main
9 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Jagdeep/Prem | 27087 | MSBP - Total value shows incorrect once removing the promotion code(regression) | Defect Fixed | 1 |  | 4 | 2026-04-01 | 2026-04-06 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48237 | 2026-04-06 | 2026-04-06 | Ashwin | NA | Avery | 2026-04-06 | NA | "POV done with Ashwin No Comment" | NA | 03 April - Will start work on it after discussion with sambath and vashnavi. 06 April - Today will start work on it and will complete it, as discussion with Ashwin. 07 April - Defect ready for testing. 07 Apr - Testing is in progress | Exceeds Expectation |  | Main
10 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Amrit/Prem | 27098 | MSBP - I/A - Search text is not clearing even after adding a product to the cart or switching to a different school (regression) | Defect Fixed | 0.5 |  | 6 | 2026-04-01 | 2026-04-01 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48172 | 2026-04-01 | 2026-03-04 | Ashwin | NA | Avery | 2026-03-04 | NA | POV done with Bavithra No Comment | NA | 3 Apr - PR Pending from Client Side (Approved by Ashwin,rupesh,sambath) 06 Apr - Testing Completed | Exceeds Expectation |  | Main
11 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Jagdeep/Gursewak | 27078 | 27078 MSBA - MAUI - android phone - app crash when trying to apply filters (regression) | Defect Peer Review | 0 |  | 9.5 | 2026-04-01 | 2026-04-15 | NA | NA | NA | Rupesh/Sambath | Count: 1 why ExecuteGroupsStores was removed, Group filter is required after changing the stores | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48418 | 2026-04-15 | NA | NA | NA | NA | NA | NA | "POV done with Ashwin No Comment" | NA | 06 - April - not yet started to work 14 - April - Today will investigate and try to find root cause and then will work for fix it. 15 - April - First will work for BB coming on story 51972 then will start continue work on it. 15 - April - Work with Jagdeep on the defect. | Exceeds Expectation | This defect assigned to Jadeep on (14 April) by Ashwin. On 15 April defect fixed and done POV and Created the PR , review pending from Ashwin and client side. Because review and testing pending so it will go in next sprint. | Main
12 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Jagdeep/Prem | 27104 | MSBP - I/A - Missing Profile Information screen, Answer Field appears disabled and only becomes enabled on switching to navigation icons(regression) | Defect Fixed | 1 |  | 4 | 2026-04-02 | 2026-04-03 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48222 | 2026-04-03 | 2026-04-04 | Ashwin | NA | Avery | 2026-04-04 | NA | "POV done with Bavithra No Comment" | NA | 03 April - will continue work on these defect. 03 April - defect fixed done POV and created the PR. 06 April - defect ready for testing. 06 Apr - Testing Completed | Exceeds Expectation |  | Main
13 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Rupesh/Prem | 27105 | MSBP - A - Missing Profile Information screen, Text (We need to update your profile) is shows in cut off mode(regression) | Defect Fixed | 0.5 |  | 1 | 2026-04-02 | 2026-04-06 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48201 | 2026-04-02 | 2026-04-03 | Ashwin | NA | Avery | 2026-04-03 | NA | POV done with Bavithra. | NA | 02 April - Will reproduce it first and then fix. PR is pending from internal team. 06 Apr - Testing Completed | Exceeds Expectation |  | Main
14 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Rupesh/Prem | 27106 | MSBP - I/A - Bottom navigation icons should not present in Missing Profile Information screen(regression) | Defect Fixed | 0.5 |  | 1 | 2026-04-02 | 2026-04-06 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48201 | 2026-04-02 | 2026-04-03 | Ashwin | NA | Avery | 2026-04-03 | NA | POV done with Bavithra. | NA | 02 April - Will reproduce it first and then fix. PR is pending from internal team. 06 Apr - Testing Completed | Exceeds Expectation |  | Main
15 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Prem | 52440 | MSBP CA - Regression/Smoke Test Against Staging 26.4 RC | Story Completed | 1 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 03 April - Testing is in Progress 06 Apr - will contiue once the regression defects testing gets done 07 Apr - Testing Completed | Exceeds Expectation |  | Main
16 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Rupesh | 27120 | MSBP - Upon return of sign up from Greenlight, home page is not refreshing to show assign card tray (regression) | Defect Needs More Info | 3 |  | 12 | 2026-04-03 | NA | NA | NA | NA | NA | NA | [6 empty] | NA | NA |  |  | 03 April - Will reproduce the issue and then will be fixing it. 06 April - looks like it’s not happening in test environment and happening in staging. Will continue to fix this issue. 07 April : Fixed with another approach(Max attempts). 08 April : Will run the POV with Bavithra and then will be moving on 52056. After POV, raised the PR. 09 April : Comment is resolved given by Sambath, Pending from Ashwin Side. 10 April : Need to implement another approach as the current one may have performance issue. 13 April : Looks like API Issue, Ashwin will discuss with backend team . 14 Apr : As Ashwin suggested, will implement cache approach and see if it fixes the issue. 15 Apr : This has dependency on backend team, so moved to defect needs more info state. |  | This has dependency on backend team, so moved to defect needs more info state. | Main
17 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Vaishnavi | 52439 | MSBA - Smoke Test Against 26.4 Web RC | Story Completed | 2 |  | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 08 - Apr - Testing in progress 09 Apr - Will continue working on testing | Exceeds Expectation |  | Main
18 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Prem | 52442 | MSBP - Prod Smoke Test Against RC | Story Completed | 1 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 08 - Apr - Testing in progress 09 Apr - Testing Completed | Exceeds Expectation |  | Main
19 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Jagdeep/Prem | 27142 | MSBP CA - iOS - Value is not showing after the decimal point for Sub Total in the Checkout Page(regression) | Defect Fixed | 0 |  | 5 | 2026-04-08 | 2026-04-08 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48288 | 2026-04-08 | 2026-04-09 | Ashwin | NA | Avery | 2026-04-09 | NA | "POV done with Bavithra No Comment" | NA | 08 April - Starting work on this defect. 09 April - development completed , Internal PR approved , waiting for client approval. 10 April - defect ready for testing. Testing was blocked due to login issues in Test environment. 13 April - Testing completed | Exceeds Expectation |  | Main
20 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Sambath/vaishnavi | 27162 | MSBP - Home Screen is blank when logged in with the user credential created in Web MSB (26.4) | Defect Fixed | 0 |  | 17.5 | 2026-04-10 | 2026-04-14 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48409 | 2026-04-14 | 2026-04-14 | Ashwin | NA | Avery | 2026-04-14 | NA | "POV done with Bavithra No Comment" | NA | 10-Apr - Merged . ready for testing. 16-Aprl- testing in progress. | Exceeds Expectation |  | Main
21 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Rupesh/vaishnavi | 27119 | MSBP - Showing Portal Cards from Other Districts In Household | Defect Fixed | 5 |  | 14 | 2026-04-13 |  | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48422 | 2026-04-15 | 04/152026 | Ashwin | NA | Avery | 2026-04-15 | Code has been reverted due to UI change but that is not part of this defect, so avery added comments to revert it back Please revert the StudentProfileSheet.xaml changes and keep only the HomeViewModel.cs changes. The layout changes here require additional QA effort and are out of scope for this defect. | POV done with Ashwin | NA | 113 Apr : Will anyalyze first and the will start the development. 14 Apr : After 27120, I will move on this. 15 Apr : Will try to do the POV and raise the PR.. 16-Apr - Testing completed. checking with Letashia for confirmation on the scenarios which needs to covered as this is a prod issue. Testing completed. got confirmation from letashia | Exceeds Expectation |  | Main
22 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Jagdeep/Prem | 52193 | [WAVE] MSBA - Kaleida - Side Menu - Update Shift Mode Start/End and Open Cash Drawer Buttons | Story Completed | 2 |  | 7 | 2026-03-16 | 2026-04-10 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47973 | 3.24/2026 | 3.24/2026 | Ashwin | NA | Avery | 2026-03-25 | Comment count:- 2 1. This should be using PrimaryGhost buttonType. Can be simplified to: 2. Replace these with: Padding="24,8" | "POV done with Bavithra No Comment" | POV done with Jason, No Comment. | 10-Apr - Merged . ready for testing. 14-Aprl- testing in progress. | Exceeds Expectation |  | Main
23 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 Stretch | Amrit | 27019 | MSBA - MAUI - phones - cannot drag to sort products | Defect Being Fixed | 3 |  | 5 | 2026-04-15 | NA | NA | NA | NA | NA | NA | Na | NA | NA | NA | NA | NA | NA | NA | NA | NA | 15 Apr - Analyzing and trying to reproduce 15 Apr - Defect reproduced now fixing. 16 Apr - if no BB on main task then will complete testing and POV |  | Currently on hold supporting team members for their main stories | Stretch
24 | MSB Mobile Kaleida | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Prem | 52194 | [WAVE] MSBA - Kaleida - Update Shift Mode Status Icons on Top Header Bar | Story Being Tested | 2 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 16 Apr - Will start once the testing for 52056 gets completed.Started testing. Yet to do the executions | Exceeds Expectation |  | Main
25 | MSB Mobile | 2026-04-03 | 2026-04-16 | 26.5 M Sprint 1 | Letashia/Offshore team | 52655 | MSBA - End to End Testing of Maui [Time Box] Pt 4 | Story Completed | 3 |  | 29 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testers and developers will be logging the worklogs for the regression defects. | Exceeds Expectation |  | Main

## 26.5 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.5 M Sprint 1 | 27052 MSBA - MAUI - Android - unable to read entire product description (regression) | 27052 MSBA - MAUI - Android - unable to read entire product description (regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27001 MSBA - MAUI - phones - now only displaying 3 products in landscape (regresssion) | 27001 MSBA - MAUI - phones - now only displaying 3 products in landscape (regresssion) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27087 MSBP - Total value shows incorrect once removing the promotion code(regression) | 27087 MSBP - Total value shows incorrect once removing the promotion code(regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27098 MSBP - I/A - Search text is not clearing even after adding a product to the cart or switching to a different school (regression) | 27098 MSBP - I/A - Search text is not clearing even after adding a product to the cart or switching to a different school (regression) | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27078 MSBA - MAUI - android phone - app crash when trying to apply filters (regression)" | 27078 MSBA - MAUI - android phone - app crash when trying to apply filters (regression)" | Sambath | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27104 MSBP - I/A - Missing Profile Information screen, Answer Field appears disabled and only becomes enabled on switching to navigation icons(regression) | 27104 MSBP - I/A - Missing Profile Information screen, Answer Field appears disabled and only becomes enabled on switching to navigation icons(regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27105 MSBP - A - Missing Profile Information screen, Text (We need to update your profile) is shows in cut off mode(regression) | 27105 MSBP - A - Missing Profile Information screen, Text (We need to update your profile) is shows in cut off mode(regression) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27106 MSBP - I/A - Bottom navigation icons should not present in Missing Profile Information screen(regression) | 27106 MSBP - I/A - Bottom navigation icons should not present in Missing Profile Information screen(regression) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27120 MSBP - Upon return of sign up from Greenlight, home page is not refreshing to show assign card tray (regression) | 27120 MSBP - Upon return of sign up from Greenlight, home page is not refreshing to show assign card tray (regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27142 MSBP CA - iOS - Value is not showing after the decimal point for Sub Total in the Checkout Page(regression) | 27142 MSBP CA - iOS - Value is not showing after the decimal point for Sub Total in the Checkout Page(regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27162-MSBP - Home Screen is blank when logged in with the user credential created in Web MSB (26.4) | 27162-MSBP - Home Screen is blank when logged in with the user credential created in Web MSB (26.4) | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.5 M Sprint 1 | 27119-MSBP - Showing Portal Cards from Other Districts In Household | 27119-MSBP - Showing Portal Cards from Other Districts In Household | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects

## 26.4 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Sambath/ Vaishnavi/Rupesh | 51966 | [WAVE] MSBA - Kaleida - Settings - Apps & Stores | Story Being Tested | 3 |  | 35 | 2026-02-18 | NA | NA | NA | NA | Sambath | Used KDivider unnecessary places, model clsass refference not propery used. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47478 | 25/2/2026 | 2026-03-13 | Ashwin | NA | Avery | 2026-03-20 | Move to color resource file(4) , Changed all maui native controls into Kaleida controls, code refactoring changes. | POV done with Bavithra |  | 20-Mar - Deployment failed. sambath will be checking that and resolve the issue. 23 - Vaishnavi - will be starting the testing today. 24 - Testing in progress. created BB for the issue identified. 25- Rupesh- will be working on BB issue. 25- Sambath i working with BB issues 26-Sambath working with app crash bb issue. 31-mar - Regression defects are priority. will be working on the MSBA regression defects later will work on this. . 2-Apr - Will test the bb once completing the greenlight regression. This story includes testing in 4 different device and 4 different orientations. Will not be able to complete the testing by today. | Needs Improvement | This story has been delayed due to new Kaleida control changes. At the same time, the client is working with Kaleida control libraries, which has caused multiple issues while integrating the control into the MSBA project. In addition, Some new AC has been updated, which has further delayed the move to testing.. 2 - Apr - This story will be challenging to complete it today as we have to run the test cases in 4 different physical devices(mobile/tablet), each device with portrait and landscape mode and also with ios26 OS versions. This story was taken to testing on 1st April EOD only. | Main
2 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Amrit/Vaishnavi/Prem | 46158 | MSBP - Tickets - Season Passes | Story Completed | 2 |  | 54.75 | 2026-02-27 | 2026-05-03 | NA | NA | NA | Rupesh/Sambath | Selvam Sambath Count: 14 • Remove StrokeThickness • Remove Margin • Move logic from code-behind to XAML • Use DataTriggers for expand/collapse icons • Use Core.FontAwesome instead of hardcoded glyphs • Move strings to resources • Replace hardcoded values • Remove unnecessary code Majella Ashwin Count: 6 • Remove unnecessary curly braces • Simplify if/else statements • Improve alignment and readability • Remove unnecessary layouts • Use localization Kumar Rupesh Count: 6 • Move else to new line • Simplify conditions into single line • Remove unnecessary brackets • Use static colors • Improve layout structure | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47624 | 2026-06-03 | 2026-09-03 | Rupesh,Ashwin | NA | Avery | 2026-10-03 | Wold Avery Count: 8 Replace hardcoded colors with static resources Remove unused methods Replace AsyncCommand with Command Remove redundant API calls Merge duplicate methods Cache computed lists Remove duplicate UI elements Delete unused templates | Internal POV done with Vaishnavi, Bavithra - 1 comment regarding bottomsheet size and fixed | POV done with Jason, No Comment. | 20 Mar - PR is in internal Review (Approved by rupesh and ashwin) 23 Mar - PR Review pending from Sambath 24 - story ready for testing 24 Mar - Tested and Blocked due to transactions getting failed 25 Mar - Testing Completed | Exceeds Expectation |  | Main
3 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Sambath/ Gursewak/Prem | 26897 | MSBA - MAUI -Android - recent students search cut off (regression) | Defect Fixed | 3 |  | 5.5 | 2026-03-18 | 2026-03-19 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47844?_a=files | 2026-03-17 | 2026-03-20 | Ashwin | remobed the RecentHeaderRowHeight property from viewmodel | Avery | 20/3/2026 | NA | Done the POV with Bavithra | NA | 20 Mar - Testing Completed | Exceeds Expectation |  | Main
4 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Gursewak/Prem | 52194 | [WAVE] MSBA - Kaleida - Update Shift Mode Status Icons on Top Header Bar | Story Needs More Info | 3 |  | 12.25 | 2026-03-16 | 2026-03-19 | NA | NA | NA | Rupesh | 1. Can we give some other name fo Text. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47852?_a=files | 2026-03-18 | 2026-03-19 | Ashwin | NA | Avery | 2026-03-20 | Double command execution: parent HorizontalStackLayout has a TapGestureRecognizer and KStatusChip has its own Command binding. Since KStatusChip internally wraps a TapGestureRecognizer that executes Command, tapping fires GoToAsync("CloseDaySession") twice. Remove the outer TapGestureRecognizer from the HorizontalStackLayout for the shift chip, or remove the Command binding from KStatusChip. Rather than adding a new StopWatchOn = "\uf2f2" constant, just update the existing Stopwatch = "\u23f1" to "\uf2f2". \u23f1 is the correct FA glyph. Stopwatch has no usages anywhere in the codebase so there's no risk of breakage, and it keeps the file clean with a single stopwatch constant. | POV done with Bavithra No Comments. | POV done with Jason, No Comment. | 20 March - Client review pending. 20 Mar - Will work on udpating test cases 20 March - Merged, ready for test. 23 mar - Completed test case review comments From RJ - in order to be able to test, we have added 51972 and 51968 as a related items which will need to be completed before QA is able to test this user story. |  | Story still on hold , 51972 will have to be completed first in order to be able to test. | Main
5 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Jagdeep/Prem | 52193 | WAVE] MSBA - Kaleida - Side Menu - Update Shift Mode Start/End and Open Cash Drawer Buttons | Story Needs More Info | 2 |  | 0 | 2026-03-16 | 2026-03-17 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47973 | 2026-03-16 | NA | Ashwin | NA | Avery | NA | Comment count:- 2 1. This should be using PrimaryGhost buttonType. Can be simplified to: 2. Replace these with: Padding="24,8" | POV done with Bavithra No Comments. | POV done with Jason, No Comment. | 23 Mar- 52193 depends on 51972, will have to have 51968 completed first.(So 51972 will have to be completed first in order to be able to test.) |  | Story still on hold , 51972 will have to be completed first in order to be able to test. | Main
6 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Ashwin/vaishnavi | 26886 | MSBA - MAUI - Close day is missing EMV transactions from Expected payment summary and Sales summary and credit total (regression) | Defect Fixed | 0 | 0 | 2 | NA | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47979 | 2026-03-24 | 2026-03-24 | NA | NA | Avery | 2026-03-24 | NA | NA | NA | will work on the testing part after completing the pending testing stories/defects/ . 26-Mar - will work on this after updating the test cases for regression suite. | Exceeds Expectation |  | Main
7 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Jagdeep/Prem | 26977 | MSBA - MAUI - iOS - Error message behind other popup in shift mode (regression) | Defect Fixed | 0 |  | 4 | 2026-03-18 | 2026-03-18 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47882 | 2026-03-18 | 2026-03-18 | Ashwin | NA | Avery | 2026-03-20 | Comment count:- 1 1. Please restore these TODOs and the corresponding commented out ShowCustomDialogAsync because we have not yet implemented the Kaleida custom dialog. Removing them here is inconsistent and may cause these to be missed when the Kaleida migration is completed. | POV done with Bavithra No Comments. | NA | 20 March- PR approved internally and Ashwin side , waiting for client approval. 23 March - PR approved internally and client side , and Merged now it’s ready for testing. Will start the testing today. 24 Mar - Testing Completed | Exceeds Expectation |  | Main
8 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Gursewak/vaishnavi | 52433 | MSBP - Kaleida - Use Kaleida Components: Bottom Nav | Story Completed | 2 |  | 8 | 2026-03-20 | 2026-03-24 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47936 | 2026-03-24 | 2026-03-24 | Ashwin | NA | Avery | 2026-03-24 | NA | POV done with Bavithra No Comments. | POV done with Jason, No Comment. | 20 March - Start analyzing, reviewing, and working on this story 20 Mar - Vaishnavi- Test case updated 23 March - Working on it, implement K control or colors etc and test. 24 March - Development completed, will test more and will do the POV. Draft PR is already created. after that will start work on "51968" 24-March- merged, ready for test. 25 Mar - Will pick this once testing of 46158 &52435 gets done 26 March - Gursewak - Start work on BB, after fix it Will start work pending changes on 51968. 27 March - As Ashwin sent message on slack "No need to work on the BBs on the MSBP kaleida stories as it will be created as defects as per my discussion. So work on the assigned defects." start working on 27052 and 27063 | Exceeds Expectation |  | Main
9 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Amrit/Prem | 27024 | MSBA - MAUI - shift mode error message incorrect (regression) | Defect Fixed | 0 | 0 | 2 | 2026-03-20 | 2026-03-21 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47928 | 2026-03-21 | 2026-03-20 | Ashwin | NA | Avery | 2026-03-20 | NA | POV Done with Bavithra No Comments. | NA | 20 Mar - Analyzing ,Reproducing and fixing 23 Mar - Testing completed | Exceeds Expectation |  | Main
10 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Sambath/Vaishnavi | 27009 | 27009 MSBA - MAUI - iphone - buzzing on barcode scan/not closing camera in background after scan (regression) | Defect Fixed | 0 | 0 | 5 | 2026-03-20 | 2026-03-20 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47941?_a=files https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48074 | 2026-03-27 | 2026-03-27 | NA | NA | Avery | 2026-03-27 | NA | NA | NA | Fixed the defect, moved to testing 24 Mar - Tested and reopened because app crash. 25 -Mar - Sambath - Working with App crash issue 27-Mar - Sambath fixed the app crash issue for bar code scan. 31-mar - Will start the testing. | Exceeds Expectation |  | Main
11 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Rupesh/Prem | 52434 | MSBP - Kaleida - Use Kaleida Components: Header Bar | Story Completed | 2 |  | 12.75 | 2026-03-20 | 2026-03-26 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47998 | 2026-03-25 | 2026-03-25 | Ashwin | NA | Sean | 2026-03-25 | NA | POV done with Bavithra. | NA | 20 March -Rupesh - Start analyzing, reviewing, and working on this story. 20 Mar - Vaishnavi- Test case updated 23 March - Rupesh - Will try to finis it today and will run the POV. 24 March - Rupesh - 52434 and 52435 have some common code changes, PR has been raised for 52435 and once it it merged to main, I will merge main to my 52434 and then will be raising the PR. PR has been raised.Internal review is pending from Internal Team/Sambath. 26 Mar - Tested and Raised BB and assigned back to Rupesh to fix the same 27 Mar - Testing is in Completed. Since the new build did not fix the BB. As per discussion in scrum, Informed to Raise this as Defect and close this story if there is no other BB. | Exceeds Expectation |  | Main
12 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Jagdeep/Prem | 52435 | MSBP - Kaleida - Use Kaleida Components: Hamburger Menu | Story Completed | 2 |  | 11.25 | 2026-03-20 | 2026-03-23 | NA | NA | NA | Rupesh/Sambath | Comment count:- 1 1. please remove unused reference | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47930 | 2026-03-23 | 2026-03-24 | Ashwin | NA | Avery | 2026-03-24 | Comment count:- 3 1. This should be using a KCircleButton. It will also provide the correct pressed state. 2. There's a style for these Section Navigation Items consistent with the figma design: 3.You can remove HorizontalOptions="Start" since it's already provided by the KLink implicit style. | POV done with Bavithra No Comments. | POV done with Jason, No Comment. | 20 March - Start work on this story. 23 March - Development completed , POV has been done and created the PR 24 March - Story in a peer a review. 25 Mar - Tested and Raised a BB and assigned back to Jagdeep to fix the same 26 Mar - BB fix is not available in the latest build. Assigning back to Jagdeep to confirm the same 26 March - BB fixed in development side, need to merge Kalieda.Maui control branch into main branch and then need to create latest build.(Found changes not merged into latest build yet. ) 27 Mar - testing completed | Exceeds Expectation |  | Main
13 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Amrit/Prem | 27036 | MSBA - MAUI - iOS - when in shift mode adding/deleting shift user, can swipe to get to a different box (regression) | Defect Fixed | 0 | 0 | 4 | 2026-03-23 | 2026-03-23 | NA | Na | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47961 | 24/3/2026 | 24/3/2026 | Ashwin | NA | Avery | 2026-03-24 | NA | POV done with Bavithra No Comments. | NA | 23 - Reproducing and analyzing 24 mar - Testing Completed | Exceeds Expectation |  | Main
14 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Sambath/vaishnavi | 27032 | MSBA - MAUI - phone - app crash on session ending (regression) | Defect Fixed | 0 | 0 | 3 | 2026-03-23 | 2026-03-24 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47984 | 24/3/2026 | 24/3/2026 | Ashwin | NA | Avery | 2026-03-25 | NA | POV done with Bavithra | NA | will work on the testing part after completing the pending testing stories/defects/ 24-Mar - Sambath - fixing the app crash issue. 25 -Mar - After completing the priority task, will work on this. . 27 - Mar - Testing in progress. . | Exceeds Expectation |  | Main
15 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Amrit/Vaishnavi | 27058 | MSBP - Unable to scroll in the payment method drawer under meal money autopay and invoice autopay(regression) | Defect Fixed | 0 | 0 | 5 | 2026-03-26 | 2026-03-26 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48048 | 26/3/2026 | 27/3/2026 | Ashwin | NA | Avery | 27/3/2026 | NA | POV done with Bavithra No Comments. | NA | 26 Mar - Defect Being Fixed (PR Created Sent for Review) 27 Mar - Defect Ready For Testing. 31-mar - Will start the testing. | Exceeds Expectation |  | Main
16 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Prem | 52438 | MSBP - Full Regression 26.4 | Story Completed | 8 |  | 35.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 26 -Mar - Will be updating the regression suite as per discussion with Letashia. After completing will work on defect 26886 30 Mar - Testing is in Progress 31 Mar - Will continue the testing 01 Apr - Will continue the regression testing 02 Apr - Testing is in Progress. Greenlight test cases validation pending. Waiting response from Letashia. |  |  | Main
17 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 Stretch | Rupesh/Amrit | 52056 | MSBA - Close Out - Offer Portrait and Landscape Orientation | Story Being Developed |  |  | 13 | 2026-03-16 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | RJ - Due to main commit stories , it is kept on Hold. |  | First working for regression defects, After complete regression defects will start work on it . untill it is on Hold. | Main
18 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 Stretch | Jagdeep | 51972 | [WAVE] MSBA - Kaleida - Settings - Admin Settings | Story Being Developed | 5 |  | 6 | 2026-03-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | POV done with Bavithra with solved comments:- 1. “School Number and Custom Label value should show if we already selected and come back on the screen. 2Text not matching in Record sales tag section. 3Search bar width and custom label entry width looking different | NA | 24 March - Started work on this story. 25 March - Continue work on this story , will complete Blind count settings and Enable Shift mode settings functionality. 26 March - Continue work on this story Blind count and Enabled Shift Mode has been done , will complete OverSell and Sales tag functionality. 27 March - Continue work on this story , will complete it and will POV for this story 30 March - First will work on 27072(regression), After complete it will start work on it . 31 March - first will clean up code and will create PR . 01 April - Hold it due to regression defects need to fix fiest . |  | Will be moved to next sprint because priority is regression defect and this is in stretch | Stretch
19 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 Stretch | Amrit | 51967 | [WAVE] MSBA - Kaleida - Settings - Item Visibility | Story Being Developed | 3 |  | 3 | 2026-03-24 | NA | Na | NA | NA | NA | NA | NA | NA | NA | NA | NA | Na | NA | NA | NA | Na | 24 Mar - Amrit - Continuing Development 24 Mar - Tablet UI and functionality DONE 25 Mar - Phone UI and functionality in Progress (Facing issue in phone for navigation) 26 Mar - Provided branch to Ashwin for testing Product search cases & Ashwin will cherry pick gursewak fix for featured item then POV will be possible 31 Mar - Will try to connect with vaishnavi for testing and accounts information otherwise blocked 1 Apr - Giving one round of testing then it will ready for POV but keeping it on hold because of regression defects are high priority |  | Working on regression defect (main commit) that is on prority. This story is from stretch that's the reason stop work on it right now. when we complete all defect will start work on. | Stretch
20 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 Stretch | Gursewak | 51968 | [WAVE] MSBA - Kaleida - Settings - Cart and Transactions | Story Approved | 5 |  | 15 | 2026-03-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 24 Mar - will start work on it. first will do the POV for story 52433 24 March-EOD-completed tablet view design. 25 March- Start working on phone design view and data binding after that will do the testing. 26 March - First will start work on 52433 BB, after that will work on the same story for fix the phone changes as discussed with Ashwin on standup call. 27 March - if i will get time then i will work on this, because already assigned two regression defect and story is need to fix the BB. 30 March - will complete the defect 27052, after that will start work on this story. 31 March, Will complete assigned regression defects due to on high prority. | Exceeds Expectation |  | Stretch
21 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Rupesh/vaishnavi | 27034 | MSBA - MAUI - iphone - edges of the printers and readers menus cut off (regression) | Defect Fixed | 0 |  | 9 | 2026-03-26 | 2026-03-27 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48075 | 2026-03-27 | 2026-03-27 | Ashwin | NA | Avery | 2026-03-27 | 5 times The text alignment should remain HorizontalTextAlignment="Start" | POV done with Bavithra | NA | Will reproduce and then fix the defect. As per the discussion with Ashwin will add some margin/padding then will take it from there.. 31-mar - Will start the testing. | Exceeds Expectation | Internal and external review pending. | Main
22 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Gursewak/Amrit | 27052 | MSBA - MAUI - Android - unable to read entire product description (regression) | Defect Ready For Testing | 0 |  | 11.5 | 2026-03-27 | 2026-04-02 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48200 | 2026-04-03 | 2026-04-03 | Ashwin | NA | Avery | 2026-04-03 | NA | POV done with Bavithra No Comment | NA | 27 March - Will work, test, do the POV and create the PR 27 March-EOD - Completed defect 27063, start workin on the it, issue has been fixed, facing scrolling issue in iOS trying to resolve it. 30 March - Today will try on fix the scroll issue in iOS, test the defect, do the POV and will create the PR. after that will start work on 51968 31 March - This issue been fixed, Testing and POV pending, will complete today. 01 april - internal and external review pending. 02 April - As discussed with Ashwin on call, Amrit will work on today on same task. Defect Fixed POV DONE, PR Created | Exceeds Expectation | Moved to ready for testing at the end day of the sprint. | Main
23 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Gursewak/Prem | 27063 | MSBA - MAUI - Save & Close button not centered (regression) | Defect Fixed | 0 |  | 3 | 2026-03-27 | 2026-03-27 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48135 | 2026-03-27 | 2026-03-27 | Ashwin | NA | Avery | 2026-03-27 | NA | POV Done with Bavithra No Comment. | NA | 27 March - Will work, test, do the POV and create the PR 27 March - EOD - completed this defect, did the POV, tested, PR created, PR merged, now ready for test. 31 - Testing in progress. 31 March - reopen for button bottom space fixes, development and POV done, ready for code review. 01 April - client review pending 01 April - EOD - merged, ready for test. 02 Apr - Testing Completed | Exceeds Expectation | We spent some time exploring possible workarounds for the RadSlideView issue, but none of them worked, so we are currently blocked on this because it is offical maui issue as already informed to CLIENT | Main
24 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Amrit/Prem | 27065 | MSBA - MAUI -Android phone - on returning to step 1 from a later step, cannot scroll to pick a shift in close out (regression) | Defect Fixed | 0 |  | 0 | 2026-04-03 | 2026-01-04 | NA | NA | NA | Chandler | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48191 | 2026-01-04 | 2026-01-04 | Avery | NA | Avery | 2026-01-04 | NA | POV Done client side by chandler | NA | 27 Mar - Reproducing 31 Mar - This is official issue of MAUI no workaround is working till now so totally blocked for now 1 Apr - Will give workaround to radslideview as suggested by Ashwin for 1 hour max 1 Apr - As discussed with client defect is blocked and put down in backlog ( Defect fixed by Chandler and merged) 02 Apr - Testing Completed | Exceeds Expectation |  | Main
25 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Rupesh/Prem | 27047 | MSBA - MAUI - Android tablet - Nav icons small (regression) | Defect Fixed | 0 |  | 9 | 2026-03-27 | 2026-04-01 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48163 | 2026-04-01 | 2026-04-01 | Ashwin | NA | Avery | 2026-04-01 | NA | POV done with Bavithra | NA | 30 Mar - development is in progress. 31 Mar - Yesterday tried custom handler and other approaches like made the changes in MainActivity and tried fixing setting Shell style. Looks like Android has limitation with BottomNavigationView. Today I will try tabbar approach and see how it goes. 1 Apr - Issue has been fixed, will run the POV today. 02 Apr - Testing Completed | Exceeds Expectation |  | Main
27 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 Stretch | Jagdeep/Prem | 26986 | MSBA - MAUI - iphone - when rotated in landscape mode there are white bars on edges of screen (regression) | Defect Fixed | 0 |  | 4 | 2026-03-30 | NA | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48104 | 2026-03-30 | 2026-04-01 | Ashwin | NA | Sean | 2026-04-01 | Comment count:- 1 1. Change this to the following. You don't need the Android switch anymore | POV done with Bavithra and Ashwin No Comments. | NA | 31 March - will do POV and will create PR. 01- April - defect in peer a review , (Internal review done by Rupesh and Ashwin) 02 Apr - Testing Completed | Exceeds Expectation |  | Stretch
28 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 Stretch | Gursewak/vaishnavi | 27000 | MSBA - MAUI - tablet - Barcode on store page now transparent (regression) | Defect Fixed | 0 |  | 2.5 | 2026-03-30 | 2026-03-30 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48105 | 2026-03-30 | 2026-03-30 | Ashwin | NA | Avery | 2026-03-30 | NA | POV done with Ashwin No Comment | NA | 30 March - Start working on it. 30 March-EOD-This issue has been fixed, did the POV with Ashwin, create PR, PR merged, now ready for test.. 31-mar - After completing the main | Exceeds Expectation |  | Main
29 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 Stretch | Gursewak/vaishnavi | 27001 | MSBA - MAUI - phones - now only displaying 3 products in landscape (regresssion) | Defect Being Tested | 0 |  | 6 | 2026-04-01 | 2026-04-01 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48166 | 2026-04-01 | 2026-04-01 | Ashwin | Change to Margin="5, 10" Change to Margin="3, 5" | Avery | NA | This needs to be unsubscribed. Add in OnDisappearing(): This property is identical to CurrentDeviceOrientation already defined in ViewModelBase (which this class inherits from). Remove these lines and use the inherited property instead. | POV done with Bavithra No Comments. | NA | 01 April, start working on it. 01 April, development completed, POV done, created PR, resolved PR comments added by Ashwin. 02 April - Resolved two comments added by Avery, again client review pending. | Exceeds Expectation |  | Main
30 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Jagdeep/Prem | 27086 | MSBP - Value is not showing after the decimal point for Total in the Checkout Page(regression) | Defect Fixed | 0 |  | 4 | 2026-03-31 | 2026-03-31 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48141 | 2026-03-31 | 2026-04-01 | Ashwin | NA | Avery | 2026-04-01 | NA | POV done with Bavithra No Comments. | NA | 31 -March - Started work on it. 01 -April - Defect ready for peer a review. 02 Apr - Testing Completed | Exceeds Expectation |  | Main
31 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 Stretch | Jagdeep/vaishnavi | 27002 | MSBA - MAUI - product name when no image no longer wrapping in portrait (regression) | Defect Fixed | 0 |  | 0 | 2026-03-31 | 2026-03-31 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/48110 | 2026-03-30 | 2026-03-30 | Ashwin | NA | Avery | 2026-03-30 | NA | POV done with Ashwin No Comments. | NA | 30- March - started work and fixed. 01-April - defect ready for testing. Will work on the priority defects from main commit and later work on the stretch items. | Exceeds Expectation |  | Stretch
32 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Jagdeep | 27087 | MSBP - Total value shows incorrect once removing the promotion code(regression) | Defect Being Fixed | 0 |  | 2 | 2026-04-01 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 01- April - Will reproduce then will start work on it.(,defect reason found but Need to dissus with Ashwin ) 02 April - As discussion with Ashiwn today will check it vashnavi by create new account and student and will try to reproduce it again. |  | The same behavior is also observed in the Xamarin app. Need to disscussion. | Main
33 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Vaishnavi | 27077 | MSBA - MAUI - if select print on close day more than once before button goes in disabled state, it doubles the deposit slip only (regression) | Defect Fixed | 0 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation | 02 April- Created the new account with help of Vashnavi and checked it’s happened first time with new account in current year, and same behavior in Xamarin App. (Will inform to client , this is existing behavior.) | Main
34 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Vaishnavi | 27076 | MSBA - MAUI - Android phone - Close Day print button does not go back into ready (regression) | Defect Fixed | 0 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main
35 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Amrit | 27098 | MSBP - I/A - Search text is not clearing even after adding a product to the cart or switching to a different school (regression) | Defect Peer Review | 0 |  | 5 | 2026-04-01 | 2026-04-01 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48172 | 2026-04-01 | NA | NA | NA | NA | NA | NA | POV done with Bavithra No Comment | NA | 1 Apr - Reporoducing Defect - Working on Fix - POV DONE(PR Created) 2 Apr - PR Approved by Sambath and Rupesh | Exceeds Expectation | Client review pending. | Main
36 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Jagdeep/Prem | 27099 | MSBP - I/A - Save button remains enabled even after clearing the value in 'Other Amount', and field value still updates when clicking Save(regression) | Defect Fixed | 0 |  | 4 | 2026-04-01 | 2026-04-01 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48164 | 2026-04-01 | 2026-04-01 | Ashwin | NA | Avery | 2026-04-01 | NA | POV done with Bavithra No Comments. | NA | 1 April - start working on it. 02 Apr - Testing Completed | Exceeds Expectation |  | Main
37 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Rupesh | 27088 | MSBP - A - Button does not turn blue even after meeting the entry requirements (regression) | Defect Rejected | 0 |  | 3 | 2026-04-01 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Jason rejected it as it is happening on old devices like, Pixel 4a. |  |  | Main
38 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Sambath | 27078 | 27078 MSBA - MAUI - android phone - app crash when trying to apply filters (regression) | Defect Being Fixed | 0 |  |  | 2026-04-01 | [16 empty] | 1 Apr - Started anysing this defect 2 Apr - Still finding the root cause of crash and freeze issue |  | it seems to be telerick control issue so still finding the root cause of crash and freeze issue
39 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Letashia and offshore team | 52225 | MSBA - End to End Testing of Maui [Time Box] Pt 3 | Story Completed | 5 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testers and Developers will be adding the worklogs in this story as part of MSBA regression defects
40 | MSB Mobile Kaleida | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Jagdeep | 27104 | MSBP - I/A - Missing Profile Information screen, Answer Field appears disabled and only becomes enabled on switching to navigation icons(regression) | Defect Being Fixed | 0 |  | 0 | 2026-04-02 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 02 April - starting work on this defect. |  | picked up this defect midway through the day, so I still need more time to work on it. As a result, it will carry over into the next sprint. | Main
41 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Rupesh | 27105 | MSBP - A - Missing Profile Information screen, Text (We need to update your profile) is shows in cut off mode(regression) | Defect Peer Review | 0 |  | 0 | 2026-04-02 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48201 | 2026-04-02 | NA | NA | NA | NA | NA | NA | POV done with Bavithra. | NA | 02 April - Will reproduce it first and then fix. PR is pending from internal team. | Exceeds Expectation | Client review pending. | Main
42 | MSB Mobile | 2026-03-20 | 2026-04-02 | 26.4 M Sprint 3 | Rupesh | 27106 | MSBP - I/A - Bottom navigation icons should not present in Missing Profile Information screen(regression) | Defect Peer Review | 0 |  | 0 | 2026-04-02 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/48201 | 2026-04-02 | NA | NA | NA | NA | NA | NA | POV done with Bavithra. | NA | 02 April - Will reproduce it first and then fix. PR is pending from internal team. | Exceeds Expectation | Client review pending. | Main

## 26.4 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.4 M Sprint 3 | 26897 MSBA - MAUI -Android - recent students search cut off (regression) | 26897 MSBA - MAUI -Android - recent students search cut off (regression) | Sambath/ Gursewak/Prem | Defect |  | Minor | Manual | External | Closed | Development | Others | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 26886 MSBA - MAUI - Close day is missing EMV transactions from Expected payment summary and Sales summary and credit total (regression) | 26886 MSBA - MAUI - Close day is missing EMV transactions from Expected payment summary and Sales summary and credit total (regression) | Ashwin | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 26977 MSBA - MAUI - iOS - Error message behind other popup in shift mode (regression) | 26977 MSBA - MAUI - iOS - Error message behind other popup in shift mode (regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27024 MSBA - MAUI - shift mode error message incorrect (regression) | 27024 MSBA - MAUI - shift mode error message incorrect (regression) | Amrit/ | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27009 MSBA - MAUI - iphone - buzzing on barcode scan/not closing camera in background after scan (regression)" | 27009 MSBA - MAUI - iphone - buzzing on barcode scan/not closing camera in background after scan (regression)" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27036 MSBA - MAUI - iOS - when in shift mode adding/deleting shift user, can swipe to get to a different box (regression) | 27036 MSBA - MAUI - iOS - when in shift mode adding/deleting shift user, can swipe to get to a different box (regression) | Amrit/ | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27032 MSBA - MAUI - phone - app crash on session ending (regression) | 27032 MSBA - MAUI - phone - app crash on session ending (regression) | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27058 MSBP - Unable to scroll in the payment method drawer under meal money autopay and invoice autopay(regression) | 27058 MSBP - Unable to scroll in the payment method drawer under meal money autopay and invoice autopay(regression) | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27034 MSBA - MAUI - iphone - edges of the printers and readers menus cut off (regression) | 27034 MSBA - MAUI - iphone - edges of the printers and readers menus cut off (regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27052 MSBA - MAUI - Android - unable to read entire product description (regression) | 27052 MSBA - MAUI - Android - unable to read entire product description (regression) | Gursewak/Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27063 MSBA - MAUI - Save & Close button not centered (regression) | 27063 MSBA - MAUI - Save & Close button not centered (regression) | Gursewak/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27065 MSBA - MAUI -Android phone - on returning to step 1 from a later step, cannot scroll to pick a shift in close out (regression) | 27065 MSBA - MAUI -Android phone - on returning to step 1 from a later step, cannot scroll to pick a shift in close out (regression) | Amrit/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27047 MSBA - MAUI - Android tablet - Nav icons small (regression) | 27047 MSBA - MAUI - Android tablet - Nav icons small (regression) | Rupesh/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27072 MSBA - MAUI - Android - Bottom navigation icons are showing the icons which were not enabled from the Settings menu(regression) | 27072 MSBA - MAUI - Android - Bottom navigation icons are showing the icons which were not enabled from the Settings menu(regression) | Jagdeep/Prem | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27086 MSBP - Value is not showing after the decimal point for Total in the Checkout Page(regression) | 27086 MSBP - Value is not showing after the decimal point for Total in the Checkout Page(regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27087 MSBP - Total value shows incorrect once removing the promotion code(regression) | 27087 MSBP - Total value shows incorrect once removing the promotion code(regression) | Onsite developer | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27077 MSBA - MAUI - if select print on close day more than once before button goes in disabled state, it doubles the deposit slip only (regression) | 27077 MSBA - MAUI - if select print on close day more than once before button goes in disabled state, it doubles the deposit slip only (regression) | Onsite developer | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27076 MSBA - MAUI - Android phone - Close Day print button does not go back into ready (regression) | 27076 MSBA - MAUI - Android phone - Close Day print button does not go back into ready (regression) | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27098 MSBP - I/A - Search text is not clearing even after adding a product to the cart or switching to a different school (regression) | 27098 MSBP - I/A - Search text is not clearing even after adding a product to the cart or switching to a different school (regression) | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27099 MSBP - I/A - Save button remains enabled even after clearing the value in 'Other Amount', and field value still updates when clicking Save(regression) | 27099 MSBP - I/A - Save button remains enabled even after clearing the value in 'Other Amount', and field value still updates when clicking Save(regression) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27088 MSBP - A - Button does not turn blue even after meeting the entry requirements (regression) | 27088 MSBP - A - Button does not turn blue even after meeting the entry requirements (regression) | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27078 MSBA - MAUI - android phone - app crash when trying to apply filters (regression)" | 27078 MSBA - MAUI - android phone - app crash when trying to apply filters (regression)" | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27104 MSBP - I/A - Missing Profile Information screen, Answer Field appears disabled and only becomes enabled on switching to navigation icons(regression) | 27104 MSBP - I/A - Missing Profile Information screen, Answer Field appears disabled and only becomes enabled on switching to navigation icons(regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27105 MSBP - A - Missing Profile Information screen, Text (We need to update your profile) is shows in cut off mode(regression) | 27105 MSBP - A - Missing Profile Information screen, Text (We need to update your profile) is shows in cut off mode(regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 3 | 27106 MSBP - I/A - Bottom navigation icons should not present in Missing Profile Information screen(regression) | 27106 MSBP - I/A - Bottom navigation icons should not present in Missing Profile Information screen(regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects

## 26.4 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Sambath/Prem | 51966 | [WAVE] MSBA - Kaleida - Settings - Apps & Stores | Story Being Developed | 5 |  |  | 2026-02-18 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47478 | 25/2/2026 | NA | Na | NA | NA | NA | Move to color resource file(4) |  |  | Dev completed, testing this story, new ac has been updated at end of sprint so i am working with that. 8 Mar - Sambath - Working on testing fixes. 09 Mar - Test Case Comments Updations is Completed 9 Mar -Amrit - Working on PR Comments and Code Cleanup and fixed dropdown issue 9 March - Jagdeep - will test app accordingly AC point (Found some crash issues and fixed and for dropdown refresh issue informed to Sambath) 10 - Mar - Sambath working on the Merge the latest code from maui and fixed build issue, and testing the story. 11- Mar - Sambath - Woking on POV Changes and Testing in Android device. 12-March-Gursewak - Will work on color code fixes need to move in common place. 13-Mar - Sambath worked the testing fixes and review comments. 17 Mar - Rupesh - worked on POV findings. 18 Mar - Rupesh - will run the POV again. Fixed the crash that we found out during crash and added missing code form existing SettingsViewModel. 19 Mar - Will have to run POV again. | Needs Improvement | 21 Feb - AC Changed by Client, Few changes was discussed along with development with client. (27 Feb) Requirement changed by client discussion in progress 27-Feb - Sambath - going to work with new AC changes in settings screen. This story is carried from previous sprint, so for this sprint initally added 5 SP then alter added 8 SP for New AC Update. Time logged for this sprint 59.5 Hrs, and Previouse sprint logged 23.5 Hrs 9-Mar - Sambath - Work with review comments and testing with iOS 13-Mar - Sambath - i am working with Avery changes for Kcontrol and fixng the iOS issue. | Main
2 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Gursewak/Prem | 26879 | MSBA - when using the "display featured items" toggle, other products don't display (regression) | Defect Fixed | 0 |  | 18.5 | 2026-03-02 | 2026-03-10 | NA | NA | NA | Rupesh | Remove the curly braces and make it in one line as this block is having one statement to execute. Please do it for all the places wherever it's aplicable. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47712 | 2026-03-10 | 2026-03-10 | Ashwin | Use common color Add this Automation ID back | Avery | 2026-03-16 | NA | POV done with Bavithra No Comments. | NA | 06-March - The original issue has been fixed. During testing, a spacing issue was identified in both Featured and Products, which has now been resolved. Currently, when clicking collapse and expand, the data is not displaying under Featured and Products. I am working on fixing this issue. Once it is resolved, I will complete the POV and create the PR. 09-March- Trying to implement telerik:RadCollectionView as discussed in Friday standup call. 09-March-EOD-Implemented and completed the functionality with RadCollectionView, also did the POV with "Bavithra", during the code review with Rupesh we found one crash issue on his system, The RadCollectionView working fine in debug mode but app crash in release mode. same thing discussed in standup also with ashwin. 10-March-Gursewak-Will work on RadCollectionView crash issue in release mode will try to fix the issue. 10 -March - Jagdeep will work with Gurusewak and support on this story. 10 March - EOD - Telerik RadCollectionView is not working as expected according to the reported defect. Additionally, if we add a simple Telerik RadCollectionView to a blank XAML page and test it in Release mode, the application crashes. Today, we tried implementing a bindable VerticalStackLayout and FlexLayout instead. This approach fixed the issue according to our requirements. We tested it on iOS and Android (both phone and tablet). We also completed a POV with Bavithra and Ashwin, and it is working fine. 11-March-Gursewak- As ashwin send message on slack for all dev team, Will work on copilot prompt to review my code that created a PR, and test it again and update the PR. after that will start work on "52142" 11-March-EOD-Rupesh approved the PR. 12-March- PR review pending from Sambath,Ashwin and client side. 13 March - As Ashwin comment on slack, "The app is crashing when I run it in release mode in simulator and both in debug and release mode on a physical device from your branch when landing on the stores page. If I keep the default as meals or invoice it lands on it but when I switch to store it crashes. Check and fix this", working on it today. 13 March - EOD - The issue has been fixed. I have done the POV testing on both the simulator and a real device, and the app is no longer crashing when landing on the Stores page. 16-March-Client side PR review pending. 16-March-EOD- Merged, ready for test. 17 Mar - Testing Completed | Exceeds Expectation | The delay was due to unexpected issues with Telerik RadCollectionView, where the app was crashing in release mode despite working in debug. This required investigation and a shift to an alternative approach using VerticalStackLayout and FlexLayout, along with additional testing and POV validations. There were also a few review comments and crash fixes during PR validation, which added to the timeline. After resolving all issues, the changes were merged and tested successfully. | Stretch
3 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Jagdeep/Prem | 26887 | MSBA - MAUI - Android - Close day check does not show entire "Reconcile" button (regression) | Defect Fixed | 0 |  | 6 | 2026-03-05 | 2026-03-06 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47640 | 2026-03-06 | 2026-03-09 | Ashwin | NA | Avery | 2026-03-09 | Remove Margin="0" , Padding="0" and StrokeThickness="0" | POV done with Bavithra. | NA | March 6 - Pov with Bavithra after approval then will create PR. March 9- POV done PR created , Resolved the PR comments, Waiting for internal PR approval. March 10 - PR approved internal and external and merged , Defect ready for testing. Mar 10 - Testing Completed |  |  | Main
4 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Amrit/Vaishnavi | 46158 | MSBP - Tickets - Season Passes | Story Being Developed | 3 |  | 44 | 2026-02-27 | 2026-05-03 | NA | NA | NA | Avery | “Please use static color here.” — fixed in EventDetailsSheet.xaml by replacing hardcoded black with a static resource. “Remove the brackets and make it to single line.” — fixed in BarcodePopup.xaml.cs (if (showQrCode) return;). “Please use static color from Colors class for both inner and outer color.” — fixed in MyPassesSheet.xaml and MyTicketsSheet.xaml, with new color keys added in Colors.xaml. “Please remove brackets and make it in one line, wherever it’s applicable.” — fixed in MyPassesSheet.xaml.cs for applicable single-line if/else. “Please this else part in new line.” — fixed in UpcomingTicketEventsViewModel.cs. “Make it in single line, if possible.” — fixed in UpcomingTicketEventsViewModel.cs where applicable. “Is this VerticalStackLayout necessary?” (Pass details image area) — fixed in PassDetailsSheet.xaml by removing redundant wrapper. “Align the properties from line 65 to 67 for better readability.” — fixed in EventDetailsPage.xaml. “Remove unwanted curly braces if the if/else statement has only one line. Do this in all the places in this file.” — fixed in | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47624 | 2026-06-03 | 2026-09-03 | Rupesh,Ashwin | NA | Avery | 2026-10-03 | SeasonPassItemTemplate is declared as a resource but never used — nothing references {StaticResource SeasonPassItemTemplate} anywhere in the file. The Season Passes CollectionView has its own inline template instead. This whole block can be deleted.,This second CollectionView duplicates ~100 lines of the template above it. The only difference is no date/time row — but the first CollectionView already hides that row when IsSeasonPass = true (see the InvertedBoolConverter binding on the date grid). The My Tickets tab already uses this same single-template approach with a merged list. The Season Passes tab could do the same, removing the need for this second CollectionView and CurrentSeasonPassItems entirely.,CurrentItems getter re-sorts and re-allocates a new list on every access. This fires on every scroll/property change. Cache this result and only recompute when Tickets or UpdatedSeasonPassData change.SharePassesAsync is identical to ShareEventAsync except for the title string. Merge into one method with a title parameter. | Internal POV done with Vaishnavi, Bavithra - 1 comment regarding bottomsheet size and fixed | POV done with Jason, No Comment. | Solving PR Comments, 7 Mar PR approved by Ashwin and Rupesh 9 Mar Amrit Worked on PR Comments and done testing. 10-Mar- Wil be starting the testing after completing the story 52221 11 Mar - AC Changed need to update Season pricing text to season pass number 12 Mar - PR Merged for ac changes. 13 - Mar -BB Testing in progress. EOD - BB testing completed. Letashia told to test one scenario. She is creating a season pass with long text. will check that functionality and close this story if no issues found 16 Mar- Amrit - Working on BB Changes points 17 Mar - PR Pending from client side. 18- Will be testing the bouncebacks 19 Mar - working on Minor description BB | Exceeds Expectation | AC Changed by client and discussed in slask regarding barcodes and other functionalities, Exact figma not available working as per mentioned AC points, 11 Mar - Ac Changed working on that | Main
5 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Rupesh/Prem | 26901 | MSBA - MAUI - upon returning to store page after item to cart, the search does not clear products (regression) | Defect Fixed | 0 |  | 8 | 2026-03-05 | 2026-03-12 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47649 | 2026-03-06 | 2026-03-12 | Ashwin | NA | Avery,Sean | 2026-03-12 | 4 Comments: The indentation inside this block is broken, everything is at the same column as the outer if, making the scope unreadable. Please fix formatting when restructuring. Don't need to carry around a boolean, just check the if there are items in the ticket list Remove this : Related to 2nd one. You don't need this. If there are items in the TicketList that is items in the cart : Related to 2nd one. | done with Ashwin | NA | Mar 6- will test it from end and then run the POV. Its under internal review. Mar 10 : Internal review is done, pending from client end. Mar 11 : got some PR comments, will be working on that. Mar 12 - Testing Completed | Exceeds Expectation |  | Main
6 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Vaishnavi | 52221 | MSBP CA 26.3 Release | Story Completed | 2 |  | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 9- Mar - Build is available for Android internal testing for prod apps. Will be testing in Android now. Will be checking with Letashia for the iOS build as well. . .10-Mar - Android testing completed. Will be checking the iOS builds. Testing completed | Exceeds Expectation |  | Main
7 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Vaishnavi | 52220 | MSBP US 26.3 Release | Story Completed | 2 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 9- Mar - Build is available for Android internal testing for prod apps. Will be testing in Android now. Will be checking with Letashia for the iOS build as well. Testing completed. | Exceeds Expectation |  | Main
8 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Jagdeep/Jason | 26878 | MSBA - slowness opening 3rd party SSO on relogin (regression) | Defect Rejected | 0 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | March 6 - will start work after creating PR for defect 26879. March 9 - Debug and found reason for slow performance for SSO login. And added the reason for it in Axosoft. (Waiting for next step) March 10 - As discussion with client will create new story for work on it. In this story found reason and added with defect as Defect AC point. March 11- As discussion with Ashwin, Added comment what I finding was and what needs to be done to improve the performance. And assign it back to Jason |  | Since this story was for analysis only that part I have done and add the reason of slowness with this story, it's now reassigned to Sean for client decision. A new implementation story has been created, and this one is marked as rejected. | Main
19 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Jagdeep | 26964 | MSBA - MAUI - iOS - When Featured items toggle is on, there is no heading (regression) | Defect Rejected | 0 |  | 0 | 2026-03-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 13 March - fixed in another defect 26879. |  | This defect has been resolved under defect ID 26879, which is currently (not merged) pending peer review. | Main
20 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Rupesh/Prem | 26965 | MSBA - Kaleida - Hamburger menu hitbox small, opening Transaction History | Defect Fixed | 0 |  | 6 | 2026-03-12 | 2026-03-13 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47778 | 2026-03-12 | 2026-03-13 | Ashwin | NA | Avery | 2026-03-13 | NA | done with Ashwin | NA | 12 Mar - Will analyze and start the development later. This needs to be verified through physical device , I have asked Ashwin to run this chnage on his device. 13 Mar - I will ask Sambath to test it on physical device. 16 Mar - Testing is in Progress | Exceeds Expectation |  | Main
| MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Vaishnavi/Avery | 26949 | MSBA - split order receipts not printing both (regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 17-Mar - Testing in progress | Exceeds Expectation |  | Main
| MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Vaishnavi/Avery | 26945 | MSBA - MAUI - receipt shows total incorrectly when promo code is applied(regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 17-Mar - will be testing after testing 26949 | Exceeds Expectation |  | Main
| MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Vaishnavi | 26898 | MSBA - unable to use forgot password phone workflow due to opt in restrictions | Defect Fixed | 2 |  | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed. Letashia asked to verify the flow in kaleida build as well. Will be checking that. | Exceeds Expectation |  | Main
16 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Vaishnavi/Chandler | 26885 | MSBA - Maui - Card reader not showings as 'connected' when saving and coming back to user settings (Regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 11 Mar- Testing in progress. Testing completed | Exceeds Expectation |  | Main
9 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Prem | 51968 | MSBA - Kaleida - Settings - Cart and Transactions | Story Approved | 5 |  |  |  |  | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA | NA | NA |  |  | 06 Mar - Test case updation completed | Exceeds Expectation | AC Changed by client and discussed in slask regarding barcodes and other functionalities, Exact figma not available working as per mentioned AC points | Main
10 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Vaishnavi | 51967 | [WAVE] MSBA - Kaleida - Settings - Item Visibility | Story Approved | 3 |  | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Test case update in progress.. 9-Mar - Will be modifying the test cases based on reveiw comments. | Exceeds Expectation |  | Main
12 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Amrit/Prem | 26869 | MSBP - iOS - 2nd Add A student screen has a white bar at top and bottom of screen | Defect Fixed | 1 | 3 | 8 | 2026-10-03 | 2026-10-03 | NA | NA | Na | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47715 | 2026-10-03 | NA | Rupesh | NA | NA | NA | NA | POV done with Bavithra No Comments. | NA | 10 Mar- Analyzing and reproducing will start fix after that. (12:30 PM) 10 Mar - Defect Fixed POV DONE, PR Created (6:00 PM) 11 Mar - PR Sent for Internal Review 17 Mar - Testing Completed | Exceeds Expectation |  | Stretch
13 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Rupesh/Vaishnavi/Sean | 26928 | MSBA - Tickets Box Office - No Order Created | Defect Fixed | 3 |  | 1 | 2026-03-10 | [16 empty] | 10 Mar - will analyze and reproduce first then will do the fixing. Assigned to Sean as he can work with Ethan. 12Mar - Will be doing the testing. . 13-Mar - Testing completed. | Exceeds Expectation | Assigned to Sean as he can work with Ethan | Stretch
14 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Jagdeep | 48650 | MSBP - Shake for Logs Enabled | Story Needs More Info | 5 |  | 12 | 2026-03-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 11 March started work on it . 12 March UI part has been done export zip and new screen has been created , facing issue with new support log API , Need specific format for support log as request. Waiting for that.(Current in block status) 13 march - will check with sambath for api issue. 16 March - Story marked as blocked due to backend team working for fix api issue. |  | Story blocked due to still in progress from api side. api not ready. | Stretch
15 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Prem | 51969 | MSBA - Kaleida - Settings - Receipts & Hardware | Story Approved | 8 |  |  |  |  | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA | NA | NA |  |  | 11 Mar - Test case updation completed and shared for review 12 Mar - Feedback Comments updation in Progress | Exceeds Expectation | AC Changed by client and discussed in slask regarding barcodes and other functionalities, Exact figma not available working as per mentioned AC points | Main
17 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Gursewak/Prem | 52142 | MSBA - [Kaleida] Transaction history change authorization code to Receipt ID | Story Completed | 1 |  | 8 | 2026-03-11 | 2026-03-11 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47741 | 2026-03-11 | 2026-03-11 | Ashwin | NA | Avery | NA | NA | POV done with Bavithra No Comments. | POV done with Jason, No Comment. | 11-March - Start workin on it. 11-March - EOD, merged ready for test. 12 Mar - Tested and raised a application is not responding 16 Mar - Testing Completed | Exceeds Expectation |  | Stretch
18 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Chandler/Prem | 26896 | MSBA - Camera Orientation - iOS - Camera Opening Sideway | Defect Fixed | 3 |  | 7 | 2026-03-05 | 2026-03-06 | NA | NA | NA |  | NA |  |  | NA | NA | NA | NA | NA | NA | NA | NA | 12 Mar- Testing Completed |  |  | Stretch
19 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Sambath/ Gursewak | 26897 | MSBA - MAUI -Android - recent students search cut off (regression) | Defect Peer Review | 0 |  | 5.5 | 2026-03-18 | 2026-03-19 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47844?_a=files | 2026-03-17 |  | Ashwin | remobed the RecentHeaderRowHeight property from viewmodel |  |  |  | Done the POV with Bavithra | NA | 13 Mar - Reproducing and analyzing Defect not reproduced in BS and Emulator, defect is coming in Tablet physical device its blocker for developer right now 16-Mar- Sambath - Going to work with this defect due to the lack of device. Bavithra 17- Mar PR created by sambath so changed the status under rupesh review. | Exceeds Expectation |  | Stretch
20 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Amrit/Vaishnavi | 26904 | MSBA - MAUI - Android - information bar for prior purchase requirement cut off (regression) | Defect Fixed | 0 |  | 3 | 2026-03-13 | 2026-03-13 | NA | NA | NA | Rupesh/Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47804 | 13/3/2026 | 16/3/2026 | Ashwin | Why are you using StackLayout? | Avery | NA | NA | POV done with Bavithra No Comments. | NA | 13 Mar - Reproduced and fixed , POV Pending 16 Mar - Working on PR Comments, PR Merged 17 Mar - Ready for testing. Testing completed | Exceeds Expectation |  | Stretch
21 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Rupesh/Amrit | 52056 | MSBA - Close Out - Offer Portrait and Landscape Orientation | Story Being Developed | 5 |  | 13 | 2026-03-16 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 16 Mar - Will do the analysis and later on will start the development. 17 Mar - Supported Rupesh for UI fixes and changes 18 Mar - Will Testing on Android and Code Refinement 19 Mar - Ashwin will be checking if possible in android physical device for Rotation and UI Rendering Issue | Exceeds Expectation |  | Stretch
22 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Letashia and offshore team | 52107 | MSBA - End to End Testing of Maui [Time Box] Pt 2 | Story Completed | 16 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Developers and testers will enter worklogs in this story for the regression defects which they work
23 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Gursewak | 26987 | MSBA - MAUI - iphone - no device status bar present in landscape (regression) | Defect Rejected | 0 |  | 0 | 2026-03-16 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 16 March - Start working on it. 16 March - 2.30 PM - This behavior is expected on iOS devices. In landscape mode, the system hides the status bar by default on iPhones, which causes the application header/navigation bar to appear directly at the top of the screen. This is controlled by the iOS operating system and not by the application or .NET MAUI. I verified this behavior in several native iOS applications, including Apple Maps, Apple Photos, and Apple Contacts, where the status bar is also hidden in landscape orientation. Therefore, the current behavior is consistent with the standard iOS UI behavior, while Android keeps the status bar visible in landscape, which explains the platform difference. 16 March - Jason Added comment - Talked with Bavithra, approved to reject this as this is standard IOS behavior | Exceeds Expectation | NA
24 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Gursewak | 52194 | [WAVE] MSBA - Kaleida - Update Shift Mode Status Icons on Top Header Bar | Story Peer Review | 3 |  | 10 | 2026-03-16 | 2026-03-19 | NA | NA | NA | Rupesh | 1. Can we give some other name fo Text. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47852?_a=files | 2026-03-18 | NA | NA | NA | NA | NA | NA | POV done with Bavithra No Comments. | POV done with Jason, No Comment. | 16 March - Start working on it. 17 March - AC has been changed for design only for phone/Tablet. As per 16 March refinement meeting they have changed it. Start working as per new design changes. 18 March - As discussed with Ashwin one AC point is pending "In landscape on phone, design like the view for tablet." will work in it after that will do the POV and create the PR. 19 March - Will work on PR comments - one small comments has been fixed. again sent PR for review. | Exceeds Expectation | NA | Stretch
25 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Jagdeep/Prem | 52193 | WAVE] MSBA - Kaleida - Side Menu - Update Shift Mode Start/End and Open Cash Drawer Buttons | Story Peer Review | 3 |  | 10.25 | 2026-03-16 | 2026-03-17 | NA | NA | NA | Rupesh | can we remove this spacing as it is 0. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47850 | 2026-03-16 | NA | NA | NA | NA | NA | NA | POV done with Bavithra No Comments. | POV done with Jason, No Comment. | 16 March - Start work on it. 17 March - Today will complete it and will do POV and create PR.(18 March Created the PR) 18 Mar - Test Case Updation completed and shared for review 19 March - Story ready for PR review |  |  | Stretch
26 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Sambath | 26886 | MSBA - MAUI - Close day is missing EMV transactions from Expected payment summary and Sales summary and credit total (regression) | Defect Being Fixed | 0 | 0 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Card reader is not connected in android and also facing connectivity issue in iOS, so i can't able to reproduce the defect | Main
27 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 Stretch | Avery/Prem | 26999 | MSBA - Kaleida - Application crashes when trying to access the Transaction History | Defect Fixed | 0.5 |  | 1.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 18 Mar - testing completed |  | NA | Stretch
28 | MSB Mobile Kaleida | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Jagdeep | 26977 | MSBA - MAUI - iOS - Error message behind other popup in shift mode (regression) | Defect Peer Review | 0 |  | 4 | 2026-03-18 | 2026-03-18 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47882 | 2026-03-18 | NA | NA | NA | NA | NA | NA | NA | NA | 18 March - Today started work on it. 19 March - Defect fixed POV done ready for PR review.(Rupesh Approved , Waiting for Sambath and client approval) | Exceeds Expectation | 19 March - This defect picked on the last day of this sprint , Defect has been done POV done but PR review pending(internal and external both PR review). So this defect going to in next sprint. | Main
29 | MSB Mobile | 2026-03-06 | 2026-03-19 | 26.4 M Sprint 2 | Vaishnavi | 52171 | MSBP - Kaleida - Merge Screens into Main Build | Story Completed | 2 |  | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 19 March - Will be starting the testing. . BB created for the issues | Exceeds Expectation |  | Stretch

## 26.4 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.4 M Sprint 2 | 26879 MSBA - when using the "display featured items" toggle, other products don't display (regression) | 26879 MSBA - when using the "display featured items" toggle, other products don't display (regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Others | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26887 MSBA - MAUI - Android - Close day check does not show entire "Reconcile" button (regression) | 26887 MSBA - MAUI - Android - Close day check does not show entire "Reconcile" button (regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26901 MSBA - MAUI - upon returning to store page after item to cart, the search does not clear products (regression) | 26901 MSBA - MAUI - upon returning to store page after item to cart, the search does not clear products (regression) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26878 MSBA - slowness opening 3rd party SSO on relogin (regression) | 26878 MSBA - slowness opening 3rd party SSO on relogin (regression) | Jagdeep/Jason | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26964 MSBA - MAUI - iOS - When Featured items toggle is on, there is no heading (regression) | 26964 MSBA - MAUI - iOS - When Featured items toggle is on, there is no heading (regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26965 MSBA - Kaleida - Hamburger menu hitbox small, opening Transaction History | 26965 MSBA - Kaleida - Hamburger menu hitbox small, opening Transaction History | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26949 MSBA - split order receipts not printing both (regression) | 26949 MSBA - split order receipts not printing both (regression) | Avery | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26945 MSBA - MAUI - receipt shows total incorrectly when promo code is applied(regression) | 26945 MSBA - MAUI - receipt shows total incorrectly when promo code is applied(regression) | Avery | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26898 MSBA - unable to use forgot password phone workflow due to opt in restrictions | 26898 MSBA - unable to use forgot password phone workflow due to opt in restrictions | Avery | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26885 "MSBA - Maui - Card reader not showings as 'connected' when saving and coming back to user settings (Regression) | 26885 "MSBA - Maui - Card reader not showings as 'connected' when saving and coming back to user settings (Regression) | Avery | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26869 MSBP - iOS - 2nd Add A student screen has a white bar at top and bottom of screen | 26869 MSBP - iOS - 2nd Add A student screen has a white bar at top and bottom of screen | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26928 MSBA - Tickets Box Office - No Order Created | 26928 MSBA - Tickets Box Office - No Order Created | Rupesh/Sean | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 48650 MSBP - Shake for Logs Enabled | 48650 MSBP - Shake for Logs Enabled | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26896 MSBA - Camera Orientation - iOS - Camera Opening Sideway | 26896 MSBA - Camera Orientation - iOS - Camera Opening Sideway | Chandler | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26897 MSBA - MAUI -Android - recent students search cut off (regression) | 26897 MSBA - MAUI -Android - recent students search cut off (regression) | Sambath/ Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26904 MSBA - MAUI - Android - information bar for prior purchase requirement cut off (regression) | 26904 MSBA - MAUI - Android - information bar for prior purchase requirement cut off (regression) | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26987 "MSBA - MAUI - iphone - no device status bar present in landscape (regression)" | 26987 "MSBA - MAUI - iphone - no device status bar present in landscape (regression)" | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26999 MSBA - Kaleida - Application crashes when trying to access the Transaction History | 26999 MSBA - Kaleida - Application crashes when trying to access the Transaction History | Avery | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 2 | 26977 MSBA - MAUI - iOS - Error message behind other popup in shift mode (regression) | 26977 MSBA - MAUI - iOS - Error message behind other popup in shift mode (regression) | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects

## 26.4 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Sambath/Amrit/Rupesh/Prem | 51795 | MSBA - Kaleida - Transaction History UI Update (V2) | Story Completed | 3 |  | 12.5 | 2026-02-09 | 2026-02-18 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47331 | 2026-02-18 | 2026-02-20 | Ashwin | Use/Add a common color | Avery | 2026-02-20 | 2 Comments: Please reformat so the { is on it's own line for consistency - 2 times Please use either VerticalStackLayout or HorizontalStackLayout - 5 times | NA | NA | 19 Feb -Vaishnavi Test case update in progress. 20 Feb - got some PR comments from Avery , will resolve that. 23 Feb - Will continue work on test case updation 24 Feb - Completed test case updation 25 Feb - Testing is in Progress 26 Feb - Testing Completed | Needs Improvement |  | Main
2 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Jagdeep/Prem | 48598 | [WAVE] MSBA - Kaleida - Update Bottom Navigation Icons | Story Completed | 2 |  | 9 | 2026-02-06 | 2026-02-11 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47142 | 2026-02-09 | 2026-02-11 | Ashwin | NA | Avery | 2026-02-11 |  | NA | NA | 20 Feb - Updated the PrimaryBlue color instead of KaleidaBlue color PR updated . Still PR in Peer Review. 24 Feb - Tested and raised a BB and assigned back to Dev to fix the same 25 Feb - Tested and raised a BB and assigned back to Dev to fix the same 26 Feb - Testing Completed | Exceeds Expectation |  | Main
3 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Gursewak/Prem | 51834 | MSBP - Center Page Headings | Story Completed | 0.5 |  | 3 | 2026-02-10 | 2026-02-10 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47166 | 2026-02-10 | 2026-02-10 | Ashwin | NA | Avery | 2026-02-19 | NA | NA | NA | 20 Feb - Test Case Updation and Testing is in Completed | Exceeds Expectation |  | Main
4 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Sambath/Rupesh/Vaishnavi | 26748 | MSBP (IOS/Android) - Bottom Sheets - Pull Bar Hard to Interact with | Defect Fixed | 1 |  | 14 | 2026-02-10 | 2026-02-12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47249 | 2026-02-13 | 2026-02-19 | Ashwin | NA | Avery | 2026-02-19 | NA | NA | NA | 20-Feb-Testing in progress. BB created and assgned back to development. Will be fixing on the missing pages.. 24 - Feb - Will pick this one after completing the story 51680 23- Feb Sambath - I tested and fixed the one sheet issue. and reviewed code and moved to testing. 24 - Feb - Testing in progress. . 25 - Testing in progress. | Exceeds Expectation |  | Main
5 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Gursewak/Vaishnavi | 51680 | MSBA - Close Out - Print Button - Provide Warning to User when No Printer is Selected in Settings | Story Completed | 1 |  | 5 | 2026-02-16 | 2026-02-18 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47317 | 2026-02-19 | 2026-02-19 | Ashwin | NA | Avery | 2026-02-19 | NA | NA | NA | 20 - Feb - Will pick this story after completing the already assigned 2 stories/defect. EOD - Test cases updated and shared for reveiw. 23 - test cases update based on review comments in progress. . 24 - Testing in progress. Seperate defect created for the issues identified. will be continuing with the testing. | Exceeds Expectation |  | Main
6 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Vaishnavi/Chandler | 51842 | MSBA - Search Updates - WAF Block (Tech Debt) | Story Completed | 1 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20-Feb-Test case update in progress. EOD - Testing completed. | Exceeds Expectation |  | Main
7 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Prem/Avery | 26808 | MSBP - Installment plan and Autopay subscription drawers not closing when tapped in the background(regression) | Defect Fixed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20 Feb - Tested and raised to create a autopay subscription invoice to Nithish. 23 Feb - Testing Completed | Exceeds Expectation |  | Main
8 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Prem/Avery | 26807 | MSBP - iOS - Students name in Suggested student drawer not displayed in list mode( regression) | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20 Feb - Testing completed | Exceeds Expectation |  | Main
9 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Amrit/Gursewak/Jagdeep/Prem/Sambath | 51966 | [WAVE] MSBA - Kaleida - Settings - Apps & Stores | Story Being Developed | 13 |  | 59.5 | 2026-02-18 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47478 | 25/2/2026 | NA | Na | NA | NA | NA | Move to color resource file(4) |  |  | 20-Feb-Gursewak-Tablet design done, start work in phone design. 23-Feb-Gursewak- Continue work on the same story, will do the POV today. 23 Feb - Amrit Working on Tablet UI and funcitionality and make it ready for POV 24-Feb-Gursewak-Start working on Default Stores page design. 24 Feb - Amrit - Working on Default Store Functionality part 24 Feb - Jagdeep - Working for Toggle button issue and will support to Gursewak and Amrit 25 Feb - will work on some changes suggesed by Ashwin, Test, Code optimize, after that will do the POV. 25 Feb Amrit - Will work on Popup Alert, 2 columns for Stores Data, Code Optimisation and Gursewak will support to Amrit complete these fixs. 26 Feb - Amrit Move Custom controls to separate kaleida branch and create PR. 26-Feb - Sambath New AC has been added so i am taking remaing part of devlepment 02 -Mar - Sambath Continue to working with settings validation logics 03-Mar - Sambath working on save logics for menus and defults stores. 03 Mar Amrit - Worked on Store Toggel default scenario as suggested by sambath 04 Mar - Test Case updation completed and shared to review | Needs Improvement | 21 Feb - AC Changed by Client, Few changes was discussed along with development with client. (27 Feb) Requirement changed by client discussion in progress 27-Feb - Sambath - going to work with new AC changes in settings screen. This story is carried from previous sprint, so for this sprint initally added 5 SP then alter added 8 SP for New AC Update. Time logged for this sprint 59.5 Hrs, and Previouse sprint logged 23.5 Hrs | Main
10 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Sambath/Vaishnavi | 25805 | 25805 MSBA - MAUI - iOS - FOLLOW UP - filter sidebar in store does not change for groups or filters (26.4) | Defect Fixed | 1 |  | 6.5 | 2026-02-20 | 2026-02-20 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47413?_a=files | 2026-02-20 | 2026-02-21 | Ashwin | NA | Sean | 2026-02-21 | NA | NA | NA | 24 Feb - Will pick this defect for testing after completing story 516580-. | Exceeds Expectation |  | Main
11 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Rupesh/vaishnavi | 26842 | MSBA - MAUI - settings store search is broken (regression) | Defect Fixed | 0 |  | 0 | 2026-02-24 | 2026-02-25 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47461 | 2026-02-24 | 2026-02-25 | Ashwin | NA | Avery | 2026-02-25 | NA | NA | NA | 24 Feb - Will start fixing this defect today.. 25 - Feb - yet to start Testing | Exceeds Expectation |  | Main
12 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Sambath | 26840 | 26840 MSBA - MAUI - Selecting a store in settings is not applying on store page (regression) | Defect Fixed | 0 |  | 0 | 2026-02-25 | 2026-02-26 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47510?_a=files | 26/2/2026 | 26/2/2026 | Ashwin | NA | Avery | 26/2/2026 | NA | NA | NA | 25-Feb - Anaylsed, and started working on this defect. Clarified with client, and this is new implementation for filter selection restoration 26-Feb Woking on the store setting selection and Manual selection restoration | Exceeds Expectation |  | Main
13 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Rupesh/vaishnavi | 26844 | 26844 MSBA - MAUI - Payment receipt window is showing product total, not actual total with tax (regression) | Defect Fixed | 0 |  | 0 | 2026-02-25 | 2026-02-26 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47487 | 2026-02-25 | 2026-02-26 | Ashwin | NA | Avery | 2026-02-26 | NA | NA | NA | 25 Feb- Will be starting the development/fixing today.. 26 Feb - Yet to start the testing. | Exceeds Expectation |  | Main
14 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Vaishnavi/Avery | 26839 | MSBA - iOS - Printer Configuration showing as 'System Printer' when BT is turned OFF and Star printer option is selected (Regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 26- Feb- Testing in progress. 27 Feb - Still waiting confirmation from letashia for an observation. | Exceeds Expectation |  | Main
15 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Rupesh/Prem | 26853 | MSBA - MAUI - recent student list showing student not applicable, when selecting the error message doesn't make sense (regression) | Defect Fixed | 0 |  | 0 | 2026-02-26 | 2026-02-27 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47524 | 2026-02-26 | 2026-02-27 | Ashwin | NA | Avery | 2026-02-27 | NA | NA | NA | 26 Feb - will analyse and then will start the development. 02 Mar - Testing Completed | Exceeds Expectation |  | Main
16 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Vaishnavi/Avery | 26855 | MSBA - MAUI - iOS - Difficulty Searching for Students with Apostrophe (') in name (regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | BB test in progress. | Exceeds Expectation |  | Main
17 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Vaishnavi/Chandler | 26856 | MSBA - MAUI - Meal Balance missing when 0.00 (regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main
18 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Vaishnavi/Avery | 26861 | MSBA - MAUI - Settings screen does not show reader serial number on connection right away(regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main
19 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Vaishnavi/Avery | 26859 | MSBA - MAUI - crash when Open Cash Drawer is selected multiple times(regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main
20 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Gursewak/Jagdeep | 26879 | MSBA - when using the "display featured items" toggle, other products don't display (regression) | Defect Being Fixed | 0 |  | 0 | 2026-03-02 | [16 empty] | 02 March, First I will complete my task 50837, after that will start work on Jagdeep PR comments "52043" after that i will start work on this defect. 03 March - First complete the AC changes on "50837" after that will start work on this defect. 04 March - Will start work on this task as Ashwin comment on Slack (I went back to 15.2.0.168 which the oldest in MAUI in BS from Oct 2025 and it has the same issue reported in 26879. So this could be broken for long. Check in xamarin and see what's the difference and fix it accordingly.) 05-March- Orignal issue has been fixed , during the testing found some space issue in Featured & Products. trying to fix this issue. working on it. after fix this will do the POV and create the PR., Jagdeep also support some time if need to requried on the same. 05-March-EOD - Spacing issue has been fixed for the both Featured & Products, but when we clicked on collapse and expand then data not show under the Featured & Products. working on it. | Exceeds Expectation | The original issue has been fixed. During testing, a spacing issue was identified in both Featured and Products, which has now been resolved. Currently, when clicking collapse and expand, the data is not displaying under Featured and Products. I am working on fixing this issue. Once it is resolved, I will complete the POV and create the PR. | Stretch
21 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Jagdeep/Prem | 26884 | MSBA - MAUI - can multi-tap shift clock and stack screen (regression) | Defect Fixed | 0 |  | 0 | 2026-03-04 | 2026-03-04 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47602 | 2026-03-04 | 2026-03-04 | Ashwin | NA | Avery | 2026-03-04 | NA | NA | NA | 04 March - Will start work on this task. 05 March - Defect ready for testing. 05 Mar - Testing Completed | Exceeds Expectation |  | Main
22 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Vaishnavi/Chandler | 26871 | MSBAnywhere Card Fails if Payment Method does not accecpt Cash | Defect Fixed | 3 |  | 1.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 04 - March - Testing completed.. | Exceeds Expectation |  | Main
23 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Jagdeep | 26887 | MSBA - MAUI - Android - Close day check does not show entire "Reconcile" button (regression) | Defect Being Fixed | 0 |  | 0 | 2026-03-05 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 05 March - Will start work on this task. |  | development is done, testing in different scenario and POV is pending. This was taken on the last day of sprint so carry forwarded to the next sprint. | Main
24 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Vaishnavi/Chandler | 26868 | MSBP - Let's Add Your Phone Number screen is showing the nav bar at the bottom | Defect Fixed | 0 |  | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 05-mar - Testing completed | Exceeds Expectation |  | Main
25 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 Stretch | Gursewak | 51968 | [WAVE] MSBA - Kaleida - Settings - Cart and Transactions | Story Need More Info | 5 |  | 6 | 2026-02-26 | NA | NA | NA | Na | Na | NA | NA | NA | NA | NA | NA | Na | Na | NA | NA | NA | 26 Feb - Start working on this story today. 26 Feb - EOD - Ashwin change this story status (Story Need More Info) and assign me new story 50837. 02 Mar - Test Case Updation Completed and shared to review | Exceeds Expectation |  | Stretch
26 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 Stretch | Jagdeep/Prem | 52043 | MSBA - WAVE - Kaleida - Forgot Login Workflow Updated | Story Completed | 5 |  | 26 | 2026-02-25 | 2026-03-02 | NA | NA | NA | Sambath | NA | Pull Request 47527: jagdeep.singh/52043-MSBA-WAVE-Kaleida-Forgot Login Workflow Updated | 2026-02-26 | 2026-03-02 | Ashwin | Replace stacklayout with VerticalStackLayout. Remove the parenthesis | Avery | 2026-03-02 | 1.Use VerticalOptions="Fill" insead of VerticalOptions="FillAndExpand" is deprecated in .NET MAUI. 2.OnIdiom is used with identical values for Tablet and Phone (e.g., Margin="{OnIdiom Tablet=20, Phone=20}"). When values are the same across idioms, please simplify to just Margin="20" for better readability. 3.The Grid with ColumnDefinitions="," only uses Grid.Column="0" - the second column is unused. This appears to be copy-pasted from the other steps that include a close button in the second column. 4.The Grid with ColumnDefinitions="," only uses Grid.Column="0" - the second column is unused. This appears to be copy-pasted from the other steps that include a close button in the second column. Since Step 3 doesn't have a close button, please remove the Grid wrapper and place the Label directly in the VerticalStackLayout. Since Step 3 doesn't have a close button, please remove the Grid wrapper and place the Label directly in the VerticalStackLayout. | NA | NA | 25- Feb- Started work on it. 26- Feb - Working on setp 3 screen still in progress. 27- Feb - Resolved the PR comments. Story ready for Peer Review. 02 March - Gursewak will work on PR comments and after that will start work on "26879" 02 Mar - Test Case Updation Completed and shared to review 02 March - Gursewak - PR comments resolved. 03 Mar - Will continue work on updating test case comments 04 Mar - Tested and raised BB and assigned back to Dev 05 Mar - Testing Completed |  |  | Stretch
27 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 Stretch | Amrit | 51967 | [WAVE] MSBA - Kaleida - Settings - Item Visibility | Story Need More Info | 3 |  | 3 | 2026-02-26 | [16 empty] | 26 Feb - Tablet UI Completed 27 Feb -Story Blocked as per requirement changed by Client |  | Story Blocked as per requirement changed by client | Stretch
28 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 Stretch | Gursewak/Vaishnavi | 50837 | 50837 MSBP - Cannot Checkout with 0.00 | Story Completed | 2 |  | 10.5 | 2026-02-27 | 2026-03-03 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47540?_a=files | 2026-03-03 | 2026-03-03 | Ashwin | NA | Avery | 2026-03-03 | NA | Internal POV done with Vaishnavi, Sambath - No Comment | POV done with Jason, No Comment. | 27 Feb - (Gursewak) Start working on on it today. 02 March - Gursewak, I have completed this task by 27th, but during the testing I found one test case that I have discussed with client call, so need to work on that case, When 100%promo coupon is applied that and amount is zero then need to disable the Pay Now buttom, working on it and will test, and will do the POV and create the PR. and after will start work on PR comments "52043" 03 March - Gursewak - As Ashwin discussed with Jason "hide the program fee when making a 0 dollar payment instead of displaying 0.00. The AC also has been updated. Check and make the change." Today start working on AC changes, will test, and do the POV after that start work on "26879".. 3 Mar- Vaishnavi - modifying the test cases. 03 March - EOD - Merged, ready for test... 04 - Mar - Will start the testing once completing the defect 26871 from main sprint | Exceeds Expectation | Implement the Program Fees = 0.00 when applying a 100% promo code. Disable the Pay Now button when the total amount is 0.00. Additionally, the AC has been updated to support the new logic for setting the Program Fees to 0.00. This is the reason for the additional effort added from my side. Thanks. | Stretch
29 | MSB Mobile Kaleida | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 Stretch | Jagdeep/Amrit | 46158 | MSBP - Tickets - Season Passes | Story Being Developed | 8 |  | 22.5 | 2026-02-27 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Internal POV done with Vaishnavi, Bavithra - 1 comment regarding bottomsheet size and fixed | POV done with Jason, No Comment. | 27- Feb- Jagdeep Worked on UI and Busienss Logic Today started work on this story. 27 Feb Amrit - Worked on API Call Methods and API Integration 2 Mar - Amrit - Working on Ac changes tasks for story.. 3 Mar - vaishnavi - will start updating the test cases 3 Mar Amrit - Working on one functionality change view My ticket to View my passes make it ready for Internal POV 4 Mar Amrit - Working on Ac Changes suggested by Jason 5 Mar - Amrit, Few changes was done sharing and view ticket one is inprogress Working on Code refinement and create PR | Exceeds Expectation | AC Changed by client and discussed in slask regarding barcodes and other functionalities, Exact figma not available working as per mentioned AC points | Stretch
30 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 Stretch | Rupesh/Vaishnavi | 52021 | MSBP - Restrict E-Check Payments | Story Completed | 3 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Will be starting development today.. 5-Mar - Testing completed. | Exceeds Expectation |  | Stretch
31 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Rupesh | 26901 | MSBA - MAUI - upon returning to store page after item to cart, the search does not clear products (regression) | Defect Being Fixed | 0 |  |  | 2026-03-05 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 5 Mar - Will do the fixing/development today. will test it from my end and then run the POV. | Exceeds Expectation | development is done, testing in different scenario and POV is pending. This was taken on the last day of sprint so carry forwarded to the next sprint. | Main
32 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Letashia and Offshore Team | 51329 | MSBA - End to End Testing of Maui [Time Box] | Story Completed | 8 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Team has entered the worklogs for the regression defects in this story. | Exceeds Expectation |  | Main
33 | MSB Mobile | 2026-02-20 | 2026-03-05 | 26.4 M Sprint 1 | Letashia and Offshore Team | 52108 | MSBA - End to End Testing of Maui [Time Box] Pt 1.1 | Story Completed | 5 |  | 13.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This story is being tested by Letashia. Developers and testers were logging hours for the regression defects they worked as part of this story.

## 26.4 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.4 M Sprint 1 | 26748 MSBP (IOS/Android) - Bottom Sheets - Pull Bar Hard to Interact with | 26748 MSBP (IOS/Android) - Bottom Sheets - Pull Bar Hard to Interact with | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Others | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26808 MSBP - Installment plan and Autopay subscription drawers not closing when tapped in the background(regression) | 26808 MSBP - Installment plan and Autopay subscription drawers not closing when tapped in the background(regression) | Avery | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26807 MSBP - iOS - Students name in Suggested student drawer not displayed in list mode( regression) | 26807 MSBP - iOS - Students name in Suggested student drawer not displayed in list mode( regression) | Avery | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 25805 MSBA - MAUI - iOS - FOLLOW UP - filter sidebar in store does not change for groups or filters (26.4)" | 25805 MSBA - MAUI - iOS - FOLLOW UP - filter sidebar in store does not change for groups or filters (26.4)" | Sambath | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26842 MSBA - MAUI - settings store search is broken (regression) | 26842 MSBA - MAUI - settings store search is broken (regression) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26840 MSBA - MAUI - Selecting a store in settings is not applying on store page (regression)" | 26840 MSBA - MAUI - Selecting a store in settings is not applying on store page (regression)" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26844 MSBA - MAUI - Payment receipt window is showing product total, not actual total with tax (regression)" | 26844 MSBA - MAUI - Payment receipt window is showing product total, not actual total with tax (regression)" | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26839 MSBA - iOS - Printer Configuration showing as 'System Printer' when BT is turned OFF and Star printer option is selected (Regression) | 26839 MSBA - iOS - Printer Configuration showing as 'System Printer' when BT is turned OFF and Star printer option is selected (Regression) | Avery | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26853 MSBA - MAUI - recent student list showing student not applicable, when selecting the error message doesn't make sense (regression) | 26853 MSBA - MAUI - recent student list showing student not applicable, when selecting the error message doesn't make sense (regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26855 MSBA - MAUI - iOS - Difficulty Searching for Students with Apostrophe (') in name (regression) | 26855 MSBA - MAUI - iOS - Difficulty Searching for Students with Apostrophe (') in name (regression) | Avery | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26856 MSBA - MAUI - Meal Balance missing when 0.00 (regression) | 26856 MSBA - MAUI - Meal Balance missing when 0.00 (regression) | Chandler | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26861 MSBA - MAUI - Settings screen does not show reader serial number on connection right away(regression) | 26861 MSBA - MAUI - Settings screen does not show reader serial number on connection right away(regression) | Avery | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26859 MSBA - MAUI - crash when Open Cash Drawer is selected multiple times(regression) | 26859 MSBA - MAUI - crash when Open Cash Drawer is selected multiple times(regression) | Avery | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26879 MSBA - when using the "display featured items" toggle, other products don't display (regression) | 26879 MSBA - when using the "display featured items" toggle, other products don't display (regression) | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26884 MSBA - MAUI - can multi-tap shift clock and stack screen (regression) | 26884 MSBA - MAUI - can multi-tap shift clock and stack screen (regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26871 MSBAnywhere Card Fails if Payment Method does not accecpt Cash | 26871 MSBAnywhere Card Fails if Payment Method does not accecpt Cash | Chandler | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26887 MSBA - MAUI - Android - Close day check does not show entire "Reconcile" button (regression) | 26887 MSBA - MAUI - Android - Close day check does not show entire "Reconcile" button (regression) | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26868 MSBP - Let's Add Your Phone Number screen is showing the nav bar at the bottom | 26868 MSBP - Let's Add Your Phone Number screen is showing the nav bar at the bottom | Chandler | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.4 M Sprint 1 | 26901 MSBA - MAUI - upon returning to store page after item to cart, the search does not clear products (regression) | 26901 MSBA - MAUI - upon returning to store page after item to cart, the search does not clear products (regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion defects

## 26.3 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Vaishnavi/Avery | 51191 | MSBA - Readers - Handle Busy State (MAUI Build) | Story Completed | 2 |  | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 6-Feb- BB testing in progress. .Build was deployed only in iOS. Android buld got failed and redeployed at the evening. 9-Feb- Testing in progress.. | Exceeds Expectation |  | Main
2 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Jagdeep/Prem | 48597 | [WAVE] MSBA - Kaleida - Hamburger Menu Enhancements | Story Completed | 2 |  | 5 | 2026-01-30 | 2026-02-04 | NA | NA | NA | Sambath | 1. Use FontAwesomeHelper.cs for all awesome fonts, 2. move the all color code to resource 3. Use Fill, don't use FillAndExpand | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47037 | 2026-02-05 | 2026-02-09 | Ashwin | NA | Avery | 2025-02-09 | 1.Update the key to KaleidaBlueColor as this is currently a typo. 2.Use a static resource for the color here. | NA | NA | Feb 11 - Testing Completed | Exceeds Expectation |  | Main
3 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Rupesh/Prem | 48599 | [WAVE] MSBA - Kaleida - New Header Bar (Cart + Help Icon) | Story Completed | 1 |  | 4 | 2026-02-02 | 2026-02-07 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47105 | 2026-02-05 | 2025-02-06 | Ashwin | NA | Avery | 2025-02-06 | What does this change do? Can we use a static resource for the color here please | NA | NA | PR approved, ready for testing. Build has not been deployed yet. MSBP Regression testing in progress. Will pick this once regression testing is completed. Feb 11 - Will start once the testing of 48697 completed Feb 12 - Testing Completed | Exceeds Expectation |  | Main
4 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Sambath/Amrit | 51795 | MSBA - Kaleida - Transaction History UI Update (V2) | Story Peer Review | 13 |  | 112 | 2026-02-09 | 2026-02-18 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47331 | 2026-02-18 | NA | Ashwin | Use/Add a common color | Avery | NA | NA | NA | NA | 10-Feb - Sambath - Continue to working trasaction UI design for Tablet 10 Feb - Amrit - Continue work on Transaction History UI Mobile 11 Feb - Amrit Working on Transaction Detail Mobile View 11-Feb Sambath i continue to working with trasaction detail design 12-Feb Sambath, working with filters and new AC changes 12 Feb - Continue work on refund functionality and Email (Code merge with sabbath) 13 Feb - Amrit - Doing code modification for tablet and phone for filters 13-Feb - Sambath done UI for Email and fixed some UI alignment issues. 16 - Feb Sambath- Today i am going to test this story, if anything found, then i will fix it. Shared the POV with client , waiting for response. will run the internal POV with Bavithra Today. 17-Feb Sambath -Fixed the UI issues as per POV observations and done the code cleanup and reviewed the code.. 19 Feb -Vaishnavi Test case update in progress. | Needs Improvement | A new AC has been added, filter changes and refund flows have been implemented, and UI issues across different devices have been fixed. Due to these updates, the completion of this story has been delayed We are facing many challenges with filters. When filtering different types of payments, if a filter is deselected or changed, the transaction details section should close and the transaction list should expand to full screen The refund process was initially missed in AC, but we have now added it. Once a refund is successfully processed from the transaction details page, it navigates back from the details page. In tablet landscape mode, the transaction details section is closed, and the transaction list is expanded and reloaded. The admin popup flow was missed in the design, but it has now been implemented. Since there is no Kaleida design available for the admin popup, we reused the Kaleida button, and for the entry text, we applied the old design. Unit Price and Quantity was added later after discussion with client and it was not in UI figma design. | Main
5 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Jagdeep/Prem | 26717 | MSBA MAUI - Student name field gets hidden behind keyboard in landscape mode on Product detail screen | Defect Fixed | 1 |  | 9.5 | 2026-02-05 | 2026-02-12 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47227 | 2026-02-05 | 2026-02-12 | Ashwin | NA | Avery | 2025-02-12 | NA | NA | NA | Internal PR approved , Client side waiting. 10 Feb - After discussion with client need changes so today start work to update changes. 11 feb- need discussion Feb 12 - Tested. Still issue exist, Reassigned back to Developer to fix the same Feb 13 - Testing Completed | Exceeds Expectation |  | Main
6 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Jagdeep/Prem | 48598 | [WAVE] MSBA - Kaleida - Update Bottom Navigation Icons | Story Ready For Testing | 2 |  | 23.5 | 2026-02-06 |  | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47142 | 2026-02-09 |  | Ashwin | NA | NA | NA | The comment mentions "iOS 26+" but the code checks for iOS 15+. Should this be CheckSystemVersion(26, 0) to match the comment, or should the comment be updated to reflect that this configuration applies to iOS 15+? | NA | NA | Feb 6 - Test Case Updation Completed Feb 6 - Today started development on it. Feb 9 - Today continue work on it clean up code and will create PR Feb 10 - Story 48597 merged so need to merge latest code into it and update PR. Feb 11 - Waiting for Client PR approval Feb 13 - Kaleida Builds is not listed on firebase app. Raised the same to client side. Will start testing once the Builds availble Feb 16 - Tested and Raised a BB and assigned back to developer to fix the same. Feb 17 - Working for BB comment. Feb18- Fixed the BB comment , today will do the POV. feb | Exceeds Expectation | This task take additional effort due to a known .NET MAUI issue with the Liquid Water Glass feature on iOS. After another PR enabled the feature, it impacted the completed story. Merging into main caused an unexpected bounce-back, which required rework and a new PR. | Main
7 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Amrit/Vaishnavi | 26716 | MSBA - Shift Mode - Problem Getting Shift | Defect Fixed | 1 |  | 7 | 2026-02-05 | 2026-02-05 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47137 | 2026-02-06 | 2026-02-07 | Ashwin | NA | Sean | 2026-02-06 | Please put this else on a new line for better readability | NA | NA | Feb 6 - Adding Delay as per discussed with Ashwin. Feb 9 - After testing story 51191. Will be testing this defect Feb 10 - Testing in progress. | Exceeds Expectation |  | Main
9 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Gursewak/Vaishnavi | 26718 | MSBA MAUI - Search bar input box not visible in store screen is not grey active (IOS26) | Defect Fixed | 1 |  | 6 | 2026-02-05 | 2026-02-06 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47094 | 2026-02-06 | 2026-02-06 | Ashwin | NA | Avery | 2026-02-07 | NA | NA | NA | 05 Feb - Analyzing the task and reproducing the issue on iOS and Android. Development will start once the issue is confirmed and understood. 06-Feb- The issue has been fixed on the Store page and is working correctly across all iOS versions. However, these changes impact other pages where the SearchBar control is used. As Ashwin suggested fix the issue on all other pages also same as Store Page. Today I will complete, test on ios/android, will do the POV, and create the PR. 06-Feb-EOD-The fix has been applied to Store, Invoice, and Meals pages. Tested on iOS (iPhone & iPad) and Android (phone & tablet). POV done and PR created. 07-Feb-Merged, ready for test.. 09 - Feb- Will pick this one after completing testing for story 51191 | Exceeds Expectation |  | Main
8 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Rupesh | 48604 | [WAVE] MSBA - Kaleida - Background Color Update | Story Needs More Info | 1 |  | 6 | 2026-02-05 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | story moved to needs more info, as ac were not clear | NA | NA | story need more info as some of the ac point are not clear. I applied the BG Image then shared this with Ashwin since other controls were not looking good this BG image, After discussion with Jason, he moved this story to need more info status. | Needs Improvement | story need more info as some of the ac point are not clear. I applied the BG Image then shared this with Ashwin since other controls were not looking good this BG image, After discussion with Jason, he moved this story to need more info status. | Main
10 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Rupesh/Prem | 43491 | MSBA - Close Out Report - Mobile to send endCash for Reconciled Shifts | Story Completed | 2 |  | 16 | 2026-02-09 | 2026-02-12 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47197 | 2026-02-11 | 2026-02-11 | Ashwin | NA | Avery | 2026-02-12 | NA | NA | NA | PR created, Internal review done, pending from client side. Feb13 - After completing all the MSBP regression defects testing, will work on the MSBA defects/stories. Feb 16 - Will start once the 48598 & 26766 gets done Feb 17 - Test Case Updation Completed and Shared to Letashia Feedback and Testing is in Progress Feb 18 - Test Case Feedback comments done and completed the testing | Exceeds Expectation | Dev-10hrs Test -7 hrs | Main
11 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Vaishnavi/Prem | 51813 | MSBP - Full Regression 26.3 | Story Completed | 8 |  | 33 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Feb 10 - Vaishnavi - Will be testing this story after completing testing the defect 26716. Feb 12 - Testing in progress. After completing the test suite, will start executing the test from automation sheet. . Feb 13 - Testing in progress for Android devices from the automation sheet. Will be able to close it by today. . Feb 16 - Staging updated to 26.3 but still waiting confirmation from Doug to start the testing . Feb 17 - 2 test cases were in progress in staging. Will be able to close it shortly Feb 18 - 1 test case related to invoice notification needs to be run in Android device. It was not initally added in the suite. As per Letashia, will be executing that in Onsite timing. All other test cases were completed. | Exceeds Expectation |  | Main
12 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Rupesh/Prem | 26759 | MSBP - I/A - Not accepting the date selection in the webform's products(regression) | Defect Fixed | 0 |  | 0 | 2026-02-11 | 2026-02-12 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47199 | 2026-02-11 | 2026-02-11 | Ashwin | NA | Avery | 2026-02-12 | NA | NA | NA | PR created, Internal review done, pending from client side. Feb 13 - Testing Completed | Exceeds Expectation |  | Main
13 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Gursewak/Prem | 26766 | MSBP - iOS - Payment history not showing the transaction data (regression) | Defect Fixed | 0 |  | 6 | 2026-02-12 | 2026-02-12 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47234 | 2026-02-12 | 2026-02-12 | Ashwin | NA | Avery | 2026-02-13 | 1. If we aren't using booleanNegationConverter on this page anymore remove it from the ResourceDictionary. 2. The Grid in EmptyView is unnecessary and inconsistent with ItemTemplate which uses VerticalStackLayout. Since there's only a single child Label, either remove the container entirely and apply BackgroundColor to the Label, or change Grid to VerticalStackLayout for consistency with ItemTemplate. | NA | NA | 12 Feb - Start working on it, Issue has been fixed, POV done, Created PR, Internal team approved the PR. 13 Feb - Will work on PR comment. 13 Feb - EOD - Merged, ready for test. Feb 16 - Testing Completed | Exceeds Expectation |  | Main
14 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Jagdeep | 26778 | MSBP - Greenlight - Selecting the assigned GL card from homecreen, the GL screen opens multiple times(regression) | Defect Fixed | 0 |  | 4 | 2026-02-12 | 2026-02-12 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47220 | 2026-02-12 | 2026-02-12 | Ashwin | NA | Avery | 2026-02-12 | NA | NA | NA | Feb-12 - Development done . Feb - 13 - Ready for Testing. | Exceeds Expectation |  | Main
15 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Jagdeep | 26779 | MSBP - Greenlight - Upon selecting 'Share & Continue to Greenlight' is not navigating to the Greenlight webpage(regression) | Defect Rejected | 0 |  | 1 | 2026-02-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Feb-13 - Development in Progress.(Issue not reproducible. I tried multiple times by creating new accounts, and it’s working fine on both Android and iOS.) | Exceeds Expectation |  | Main
16 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Amrit/Avery | 26771 | MSBA - Application Crashes on iOS versions below 18 | Defect Being Fixed | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Feb 13 - Crash Report shared and analysis DONE. (Need to discuss with Ashwin and Client) - Avery assigned to himself Feb 18 - This is handled by the Onsite Developer Avery. | Exceeds Expectation | Avery assigned to himself Feb 18 - This is handled by the Onsite Developer Avery. | Main
17 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Vaishnavi/Letashia | 26654 | MSBA - MAUI - iOS/Android - tap is not working on readers | Defect Being Tested | 1 |  | 4 | [17 empty] | Testing in progress. Completed testing in 3 devices. Still pending in Android tab. Feb 18 -Due to not having active credit card visa and master cards, the remaining testing will be handled by the Onsite QA Letashia. | Exceeds Expectation | This defect is tested by the Onsite QA | Main
18 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Vaishnavi | 51816 | MSBP CA - Release 26.1 to Stores | Story Being Tested | 1 |  | 0 | [17 empty] | Unable to get the 26.1 to prod apps. Had discussed with Letashia. As per her, Sean needs to pull this manually to stores. Awaiting reply from letashia on the further steps. Feb 18 - This story was on hold as Sean (onsite developer) was on PTO for past 2 days. He will be availabel today. He only be able to push the build to production apps. Already communicated to client aswell. Testing was not started and it is blocked. | Exceeds Expectation | Onsite Developer Sean has to push the deployment to store for MSBA CA production apps. Already communicated to client aswell. Testing was not started and it is blocked. | Main
19 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Prem | 51815 | MSBP CA - Regression/Smoke Test Against Staging 26.3 RC | Story Completed | 1 |  | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 18 Feb - Testing completed. | Exceeds Expectation |  | Main
20 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 | Vaishnavi | 51814 | 51814 MSBA - Smoke Test Against 26.3 Web RC | Story Completed | 2 |  | 3.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 18 Feb - Testing completed. | Exceeds Expectation |  | Main
21 | MSB Mobile | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 Stretch | Gursewak | 51834 | MSBP - Center Page Headings | Story Ready For Testing | 2 |  | 6 | 2026-02-10 | 2026-02-10 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47166 | 2026-02-10 | 2026-02-10 | Ashwin | NA | Avery | 2026-02-19 | NA | NA | NA | 10 Feb - Start working on it. 11 Feb - Ashwin mark as a draft PR now, because need to create new branch for merge this PR 12-Feb - Waiting for create a new branch to merge this code. 18 Feb - Internal team and Ashwin approved the PR. 19 Feb - Client review pending. 19 Feb- EOD - Merged, ready for test | Exceeds Expectation |  | Stretch
22 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 Stretch | Jagdeep/Gursewak | 26748 | MSBP (IOS/Android) - Bottom Sheets - Pull Bar Hard to Interact with | Defect Ready For Testing | 5 |  | 20 | 2026-02-10 | 2026-02-12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/47249 | 2026-02-13 | 2026-02-19 | Ashwin | NA | Avery | 2026-02-19 | NA | NA | NA | 11 Feb -Will start work on it today (Jagdeep will work for Android and Gursewak work for iOS). 12 Feb - Continue working on it.(Development in Progress).(Hold it move for regression defect) 12 Feb - Gursewak - try to complete today asap.(Hold it move for regression defect) 13 Feb - Resolve the PR comment on 26766, after that work on it. 16- Feb - Defect ready for PeerReview. 19 - Feb - Merged, ready for test. | Exceeds Expectation |  | Stretch
23 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 Stretch | Jagdeep/Gursewak | 51680 | MSBA - Close Out - Print Button - Provide Warning to User when No Printer is Selected in Settings | Story Ready For Testing | 2 |  | 14 | 2026-02-16 | 2026-02-18 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47317 | 2026-02-19 | 2026-02-19 | Ashwin | NA | Avery | 2026-02-19 | NA | NA | NA | Feb-16 - Will work on it.(Development in progress) Feb-17 - Development has been done, will test and done POV then will create PR. Feb -18 - Testing has been done POV pending.( Gursewak will create the PR After POV ). 19 - Feb - Internal POV done, for external POV sent the video and screen shots, draft PR created. 19-Feb-EOD-Merged, Ready for test. |  |  | Stretch
24 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 Stretch | Gursewak/Jason | 51853 | MSBA (IOS/Android) - Pendo SDK (3.11.0) | Story Ready For Testing | 2 |  | 5 | 2026-02-16 | 2026-02-16 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47274?_a=files | 2026-02-16 | 2026-02-18 | Ashwin | NA | Avery | 2026-02-18 | NA | NA | NA | 16 - Feb - Reviewed story requirements for upgrading Pendo SDK (MSBA iOS/Android) to v3.11.0. Verified current SDK version and checked the official SDK updates page to confirm latest available version. 16 Feb - As discussed with ashwin in the call PR created. 17 Feb - Ashwin Approved the PR, Client review pending. 18 Feb - It's merged now. | Exceeds Expectation |  | Stretch
25 | MSB Mobile Kaleida | 2026-02-06 | 2026-02-19 | 26.3 M Sprint 3 Stretch | Amrit/Gursewak/Jagdeep/Prem | 51966 | [WAVE] MSBA - Kaleida - Settings - Apps & Stores | Story Being Developed | 8 |  | 13.5 | 2026-02-18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | Na | NA | NA | NA |  |  |  | 17 Feb - AmritAnalysis Done, Starting Implementation of UI from Kaleida Branch 18 Feb - Amrit Continuing on implementing UI for this story 19 Feb - Prem Test Case Updation is in Progress 19 Feb - Amrit - Working on UI Dropdown for default value and functionality 20-Feb-Gursewak-Tablet design done, start work in phone design. | Exceeds Expectation |  | Stretch

## 26.3 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.3 M Sprint 3 | 26717 MSBA MAUI - Student name field gets hidden behind keyboard in landscape mode on Product detail screen | 26717 MSBA MAUI - Student name field gets hidden behind keyboard in landscape mode on Product detail screen | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Others | Xamarin to Maui conversion defects
| 26.3 M Sprint 3 | 26716 MSBA - Shift Mode - Problem Getting Shift | 26716 MSBA - Shift Mode - Problem Getting Shift | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion defects
| 26.3 M Sprint 3 | 26718 MSBA MAUI - Search bar input box not visible in store screen is not grey active (IOS26) | 26718 MSBA MAUI - Search bar input box not visible in store screen is not grey active (IOS26) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Others | Xamarin to Maui conversion defects
| 26.3 M Sprint 3 Stretch | 26748 MSBP (IOS/Android) - Bottom Sheets - Pull Bar Hard to Interact with | 26748 MSBP (IOS/Android) - Bottom Sheets - Pull Bar Hard to Interact with | Jagdeep/Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client Dev | .net10 upgraded defects
| 26.3 M Sprint 3 | 26759 MSBP - I/A - Not accepting the date selection in the webform's products(regression) | 26759 MSBP - I/A - Not accepting the date selection in the webform's products(regression) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 3 | 26766 MSBP - iOS - Payment history not showing the transaction data (regression) | 26766 MSBP - iOS - Payment history not showing the transaction data (regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 3 | 26778 MSBP - Greenlight - Selecting the assigned GL card from homecreen, the GL screen opens multiple times(regression) | 26778 MSBP - Greenlight - Selecting the assigned GL card from homecreen, the GL screen opens multiple times(regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.3 M Sprint 3 | 26779 MSBP - Greenlight - Upon selecting 'Share & Continue to Greenlight' is not navigating to the Greenlight webpage(regression) | 26779 MSBP - Greenlight - Upon selecting 'Share & Continue to Greenlight' is not navigating to the Greenlight webpage(regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 3 | 26771 "MSBA - Application Crashes on iOS versions below 18 | 26771 "MSBA - Application Crashes on iOS versions below 18 | Amrit | Defect |  | Minor | Manual | External | Inprogress | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 3 | 26654 MSBA - MAUI - iOS/Android - tap is not working on readers | 26654 MSBA - MAUI - iOS/Android - tap is not working on readers | Onsite | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | .net10 upgraded defects

## 26.3 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Jagdeep/Vaishnavi | 26556 | MSBA - MAUI- Android -Meals and Ticket tabs are not displaying when selecting Store,Invoice,Meals and Tickets under Enabled Menu item in User Settings | Defect Fixed | 1 |  | 2 | 2026-01-13 | 2026-01-16 | NA | NA | NA | Gursewak | NA | Pull Request 46694: jagdeep.singh/26556-MSBA-MAUI-Android-Meals and Ticket tabs are not displayin... | 2026-01-16 | 2026-01-22 | Ashwin | NA | Avery | 2026-01-22 | These routes are already defined in AppShell.xaml as ShellContent elements with Route attributes (Store, Invoices, Meals, InPerson). When routes are declared in XAML, you don't need to register them again in code. Routing.RegisterRoute() is only needed for pages that are NOT declared in the Shell XAML. | NA | NA |  | Exceeds Expectation |  | Main Sprint
2 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Sambath/Vaishnavi | 26505 | 26505 MSBA - MAUI - iphone + iPhone/Android- Card Reader Configure UI hard to interact with | Defect Fixed | 1 |  | 6 | 2026-01-19 | 2026-01-23 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46819 | 2026-01-23 | 2026-01-24 | Ashwin | NA | Avery | NA | NA | NA | NA | defect fixed, it's ready for testing.. 28 - Testing in progress. | Exceeds Expectation |  | Main Sprint
3 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Amrit | 26534 | MSBP - Tickets - Event Details Drawer - Event Name not Wrapping | Defect Fixed | 3 | NA | 9 | 2026-01-19 | 23/1/2026 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46853?_a=files | 23/1/2026 | 23/1/2026 | Ashwin | NA | Avery | 23/1/2026 | NA | NA | NA | 23 Jan - Will Be working on 3rd solution Html Text Formatting and will share output 27 Jan - Ready For Testing.. 28 - Jan-Tested by Onsite QA | Exceeds Expectation | AC changed by client | Main Sprint
4 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Rupesh/Vaishnavi | 51561 | MSBP - AutoPay - Land on Home Screen After Successful Top Off | Story Completed | 1 | NA | 3 | 2026-01-20 | NA | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46743 | 2026-01-20 | 2026-01-22 | Ashwin | NA | Sean | 2026-01-22 | NA | NA | NA | 28 - Jan- Test cases creation in progrss. . 29 - Jan- Testing in progress | Exceeds Expectation |  | Main Sprint
5 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Gursewak/Vaishnavi/Prem | 51564 | MSBP - Forgot Password - Update Text on Forgot Login Info Page | Story Completed | 1 | NA | 6 | 2026-01-20 | 2026-01-21 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46760 | 2026-01-21 | 2026-01-22 | Ashwin | NA | Sean | 2026-01-22 | NA | NA | NA | Testing in progress and raised a BB 27 Jan - Prem - Testing is in progress. Raised a Clarification to Jason/Letashia 28 Jan - Testing Completed | Exceeds Expectation |  | Main Sprint
6 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Jagdeep/Vaishnavi | 26507 | MSBA - MAUI - iphone - UI hamburger menu version is difficult to read | Defect Fixed | 0.5 | NA | 2 | 2026-01-21 | 2026-01-21 | NA | NA | NA | NA | NA | Pull Request 46768: jagdeep.singh/26507-MSBA-MAUI-iphone-UI hamburger menu version is difficult t... | 2026-01-21 | 2026-01-22 | Ashwin | NA | Sean | 2026-01-22 | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
7 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Prem/Chandler | 49399 | MSBP - Kaleida - Header Bar update | Story Completed | 0.5 | NA | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Tested and Raised BB and assigned back to Chandler to fix the same 27 Jan - Mentioned build for testing is not available in the list. Raised the same to Chandler 28 Jan - Tested and BB needs to get fix as per discussion and assigning back to Chandler to fix the same 29 Jan - Story is in Peer Review 30 Jan - Testing Completed | Exceeds Expectation |  | Main Sprint
8 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Vaishnavi/Chandler/Prem | 49363 | MSBP - Kaleida - Hamburger Menu Enhancements | Story Completed | 2 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Tested and Raised BB and assigned back to Chandler to fix the same 27 Jan - Mentioned build for testing is not available in the list. Raised the same to Chandler 28 Jan - Done a testing and Raised a BB and assigned back to Chandler to fix the same 29 Jan - Story is in Peer Review 30 Jan - Testing Completed | Exceeds Expectation |  | Main Sprint
9 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Gursewak/Letashia | 26590 | MSBP - iOS/Android - Meal Money AutoPay Payment methods has an extra space above header | Defect Fixed | 0.5 |  | 4 | 2026-01-22 | 2026-01-22 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46796 | 2026-01-22 | 2026-01-22 | Ashwin | NA | Sean | 2026-01-23 | Remove the StackLayout and replace it with HorizontalStackLayout | NA | NA | 23 Jan - Client review pending. | Exceeds Expectation |  | Main Sprint
10 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Rupesh/Prem | 26608 | MSBA - Checkout Pay button gets disabled after entering a custom amount and then deleting it | Defect Fixed | 1 | NA | 7.5 | 2026-01-22 | 2026-01-23 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46823 | 2026-01-23 | 2026-01-23 | Ashwin | NA | Avery | 2026-01-23 | please restore the blank line between properties | NA | NA | 23 Jan - Started working on it. Out of 2 test scenario one is fixed , another one is in progress. will try to wrap up the development, POV today and will raise the PR. 27 Jan - Testing Completed | Exceeds Expectation |  | Main Sprint
11 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Jagdeep/Prem | 26588 | MSBA - .NET10 - A - Values are getting retained in step 3, on choosing different shift/turning off and on the closeout entire day | Defect Fixed | 2 |  | 6 | 2026-01-22 | 2026-01-23 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46828 | 2026-01-23 | 2026-01-23 | Ashwin | NA | Sean | 2026-01-23 | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
12 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Gursewak/Prem | 26598 | MSBP - iOS26 - Store Search Bar Formatting differences | Defect Fixed | 2 |  | 6.5 | 2026-01-23 | 2026-01-23 | NA | Na | NA | Sambath | Remove this handler and move to SearchBarHandler.Mapper.AppendToMapping("CancelButtonColor") | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46838 | 2026-01-23 | 2026-01-23 | Ashwin | Change FillAndExpand to Fill as its not supported | Avery | 2026-01-29 | NA | NA | NA | 23 Jan - Start working on it. 23 Jan - EOD - This issue has been fixed and tested on iOS and Android. The POV was completed with Bavithra, and a draft PR has been created. 28 Jan - Will work on PR comment after that start work on 51675 28 Jan - EOD - Worked on PR comments and update the PR, internal team approved the PR. 29 Jan - Under PR review. 1 comment added by Ashwin will work on it also. 30 Jan - Testing Completed 30 Jan - merged, ready for testing. | Exceeds Expectation |  | Main Sprint
13 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Rupesh | 26520 | MSBP - .NET 10 - Nav bar Doesn't Appear | Defect Fixed | 2 |  | 2 | 2026-01-23 | 2026-01-23 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46851 | 2026-01-23 | 2026-01-23 | Ashwin | NA | Avery | NA | NA | NA | NA | Defect fixed, tested by Letashia. | Exceeds Expectation |  | Main Sprint
14 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Jagdeep/Vaishnavi | 26506 | MSBA - MAUI - phones - UI issue card reader status and card mode overlap | Defect Fixed | 1 |  | 9 | 2026-01-16 | 2026-01-29 | NA | NA |  | Rupesh |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47004 | 2026-01-19 | 2026-01-21 | Ashwin | NA | Avery | 2026-01-30 | I checked this change on android tablet and it looks weird. Please fix the reconnect button to be centered and ensure it looks good on all platforms. | NA | NA | Defect blockage resolved and now it's ready for testing.. 28-Jan- Testing in progress. 29- Jan - BB comment resolved POV done and PR Udated. 30 Jan - Internal PR Approved waiting for client Approval. 30 Jan Defect approved and merged now defect ready for testing. 3-FEB - BB testing in progress. Testing completd. | Exceeds Expectation |  | Main Sprint
15 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Vaishnavi/Chandler | 48982 | MSBP - Remove Opt In and Update Text (26.3) | Story Completed | 1 |  | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 3-Feb - Testing in progress. Created BB . Chandler willbe fixing that. . 4-Feb- BB Testing completed. | Exceeds Expectation |  | Main Sprint
16 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 | Vaishnavi/Avery | 51191 | MSBA - Readers - Handle Busy State (MAUI Build) | Story Being Developed | 2 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 5FEB- Bounceback created and assigned to the Onsite developer
17 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Jagdeep/Prem | 26631 | MSBA - .NET10 - Android - Blue color Header bar is too tall | Defect Fixed | 2 |  | 10.5 | 2026-01-27 | 2026-01-27 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46881 | 2026-01-27 | 2026-01-28 | Ashwin | NA | Sean | 2026-01-28 | NA | NA | NA | 27- Jan - Today will identify and start work on it. (After updating to MAUI 10.0.30, the header tall issue was resolved. However, this not covered up bottom bar and status bar color issues, which I identified and fixed.) 28- Jan- Today will do POV for fixed issues with this defect. 29 Jan - Testing Completed | Exceeds Expectation |  | Stretch
18 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Amrit/Vaishnavi | 26624 | MSBA - iOS26 - Meals/invoice - Placing cursor on the search field , camera icon and cancel icon overlaps when keyboard displays | Defect Fixed | 2 |  | 13 | 2026-01-27 | 2026-01-28 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46938 | 2026-01-28 | 2026-01-29 | Ashwin | NA | Sean | 2026-01-29 | NA | NA | NA | 27 Jan - Starting work on defect. 28 Jan - Fix done Testing on all versions and devices tablets & Phones (12 Devices). 30 - Testing in progress. | Exceeds Expectation |  | Stretch
19 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Rupesh/Prem | 26625 | MSBA - iOS26 - Searching in Invoice search text box, the search results student data is partially cut off | Defect Fixed | 2 |  | 11 | 2026-01-27 | 2026-01-28 | NA | NA | NA | Jagdeeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46909 | 2026-01-28 | 2026-01-28 | Ashwin | NA | Avery | 2026-01-28 | NA | NA | NA | 28 Jan- Will be working to accept any length of student name. 29 -Jan-Testing Completed | Exceeds Expectation |  | Stretch
20 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Sambath/Prem | 26609 | 26609 MSBA - iOS - Promo-code field is getting displayed for meals/invoice when cart preview is enabled | Defect Fixed | 2 |  | 22 | 2026-01-27 | 2026-01-30 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46983 | 1//30/2026 | 2026-01-31 | Ashwin | NA | Avery | 2026-01-31 | NA | NA | NA | 28-Jan - issue has been fixed, testing now 29-Jan - Discussed in standup today regarding the empty space being shown when a non store item is added to cart preview and decided to spend additional effort on fixing this with collection view instead of HorizontalLayout as HorizontalLayout has been problematic in MAUI 30-Jan Fixed the issue, and Created th PR. 2 Feb - Testing Completed | Exceeds Expectation | I fixed the reported issues, but afterward the promo code and checkout section broke randomly when adding a product to the cart using Single Action mode. I resolved that issue, but then the auto-adjustment stopped working, which caused the checkout section to move out of the screen. I fixed it without using auto-adjustment and it worked fine, but now I am trying to fix the auto-adjustment to avoid empty space between the list items and the checkout section. Discussed in standup today regarding the empty space being shown when a non store item is added to cart preview and decided to spend additional effort on fixing this with collection view instead of HorizontalLayout as HorizontalLayout has been problematic in MAUI | Stretch
21 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Jagdeep/Prem | 26601 | MSBA - Android - Bottom of screen cut off by system navigation and app navigation bar if enabled .net10 | Defect Fixed | 1 |  | 5.5 | 2026-01-27 | 2026-01-28 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46881 | 2026-01-28 | 2026-01-28 | Ashwin | NA | Sean | 2026-01-28 | NA | NA | NA | 28 Jan - Today will test it with both platforms with Latest Maui version and Fix if still an issue in this defect. 29 Jan - Testing Completed | Exceeds Expectation |  | Stretch
22 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Gursewak/Prem | 51675 | MSBP - Privacy Notice Label Update | Story Completed | 2 |  | 11.5 | 2026-01-28 | 2026-01-29 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46946 | 2026-01-29 | 2026-01-29 | Ashwin | NA | Avery | 2026-01-29 | NA | NA | NA | 28 Jan - Today First will work on 26598 PR comment, after that will start work on this story. 28 Jan - EOD - I’ve started working on this task. I’m analyzing it and updating the “Privacy Policy” label text across the entire project. 29 Jan (Prem) - Will start working on writing test cases 29 Jan - Privacy Policy label changes are pending in some places. I’ll complete and test them on iOS and Android, then do the POV and create the PR. 29 Jan - EOD - Completed the 51675 MSBP - Privacy Notice Label Update, did the POV with "Bavithra" send the POV video in slack group, created the draft PR. 30 Jan - Test Case Updation Completed and shared to Letashia 30 Jan - PR merged, ready for test. 2 Feb - Testing Completed | Exceeds Expectation |  | Stretch
23 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Rupesh/Vaishnavi | 51676 | MSBA - Privacy Notice - Label Update | Story Completed | 2 |  | 8 | 2026-01-29 | 2026-01-29 | NA | NA | NA | Jagdeeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46952 | 2026-01-29 | 2026-01-29 | Ashwin | NA | Avery | 2026-01-29 | NA | NA | NA | 29 Jan- Will be starting the development today.. 30 - Will be drafting the test cases. | Exceeds Expectation |  | Stretch
24 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Jagdeep/Prem | 48597 | [WAVE] MSBA - Kaleida - Hamburger Menu Enhancements | Story Peer Review | 8 |  | 27 | 2026-01-30 | 2026-02-04 | NA | NA | NA | Sambath | 1. Use FontAwesomeHelper.cs for all awesome fonts, 2. move the all color code to resource 3. Use Fill, don't use FillAndExpand | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47037 | 2026-02-05 | NA | NA | NA | NA | NA | NA | NA | NA | Jan- 30 - Today will start work on it. Feb -02 - Continue work on it . Feb-03- UI design and navigation binding completed and tested with Android Today will work for iOS. 4 Feb - Today will work for handle top status bar color issue with humbuger menu on iOS (Development and POV done created the PR)(Internal PR approved , Ashwin and Client side waiting) |  |  | Stretch
25 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Amrit/Prem | 26668 | MSBP - Android - Event description in my tickets is not showing line breaks properly | Defect Fixed | 2 |  | 13.5 | 2026-01-30 | 2026-02-02 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46999 | 2026-02-02 | 2026-03-02 | Ashwin | NA | Sean | 2026-03-02 | NA | NA | NA | 30 Jan - Analyzing and fixing defect 2 Feb - Defect Fixed will test in all devices and version then will create PR 3 Feb - Tested and Assigned back to Amrit. Since the fix is not clear 3 Feb - Working on BB because changes are not reflecting on real device and Browserstack. Will fix it Feb 4- Testing Completed | Exceeds Expectation |  | Stretch
26 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Gursewak/Prem | 26673 | MSBP - I/A - Forgot Login Info - Next button shows enable even if no mobile number is entered. | Defect Fixed | 2 |  | 8.25 | 2026-01-30 | 2026-01-30 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46984 | 2026-01-30 | 2026-01-30 | Ashwin | NA | Avery | 2026-02-02 | NA | NA | NA | 30 Jan - Analyze the defect, reproduce the issue, coordinate with QA if required, and then start working on it. 30 Jan - EOD - Completed the task, tested on iOS and Android, conducted the POV with Bavithra, created the PR, and received internal team approval. 02 Feb - Client review pending. 03 - Feb - Testing Completed | Exceeds Expectation |  | Stretch
27 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Vaishnavi | 26623 | MSBA - iOS26 - Navigation bars and icon style changed with iOS26(Test Only) | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Stretch
28 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Rupesh/Prem | 26663 | MSBP - iOS/Android - Nav bar persists in store and product screens (.net10) | Defect Fixed | 2 |  | 7.5 | 2026-01-30 | 2026-01-30 | NA | NA | NA | Jagdeeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46982 | 2026-01-30 | 2026-01-30 | Ashwin | NA | Sean | 2026-01-30 | NA | NA | NA | will reproduce it and then will try to fix it. 2 Feb - Testing Completed | Exceeds Expectation |  | Stretch
29 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Rupesh/Prem | 48599 | [WAVE] MSBA - Kaleida - New Header Bar (Cart + Help Icon) | Story Being Developed | 8 |  |  | 2026-02-02 |  | NA | NA | NA | [12 empty] | Analyzed, and clarified with client, and started woking on it 03 Feb - Gursewak - Working with Sambath on this task, "Transactions" page For Android and iOS phone designs, the work is almost complete. A few tweaks and code refinements are pending, and I’m working on it. 04-Feb-Gursewak - Working on the same page design changes and will design the "Transaction details" bottom sheet 04-Feb - Sambath - Continue to working with sorting functinality and UI part 04-Feb - Amrit - Working on Transaction History Filtration & Detail Modal Page 05 Feb - Test Case Updation Completed |  |  | Stretch
30 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Sambath/Gursewak/Amrit | 51700 | 51700 MSBA - Transaction History UI Update (Conversion without updated API Endpoints) | Story Being Developed | 13 |  | 32 | 2026-02-02 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Analyzed, and clarified with client, and started woking on it 03 Feb - Gursewak - Working with Sambath on this task, "Transactions" page For Android and iOS phone designs, the work is almost complete. A few tweaks and code refinements are pending, and I’m working on it. 04-Feb-Gursewak - Working on the same page design changes and will design the "Transaction details" bottom sheet 04-Feb - Sambath - Continue to working with sorting functinality and UI part 04-Feb - Amrit - Working on Transaction History Filtration & Detail Modal Page | Needs Improvement | This story is holded due to the mix up in figma design | Stretch
31 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Jagdeep | 26717 | MSBA MAUI - Student name field gets hidden behind keyboard in landscape mode on Product detail screen | Defect Peer Review | 2 |  | 6 | 2026-02-05 | 2026-02-05 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47097 | 2026-02-05 | NA | NA | NA | NA | NA | NA | NA | NA | 05-Feb - Today starting work on it, (Internal PR approved client side pending ) |  |  | Stretch
32 | MSB Mobile Kaleida | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Gursewak/Amrit | 26718 | MSBA MAUI - Search bar input box not visible in store screen is not grey active (IOS26) | Defect Peer Review | 1 |  | 9 | 2026-02-05 | 2026-02-06 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47094 | 2026-02-06 | 2026-02-06 | [7 empty] | 05 Feb - Analyzing the task and reproducing the issue on iOS and Android. Development will start once the issue is confirmed and understood. 06-Feb- The issue has been fixed on the Store page and is working correctly across all iOS versions. However, these changes impact other pages where the SearchBar control is used. As Ashwin suggested fix the issue on all other pages also same as Store Page. Today I will complete, test on ios/android, will do the POV, and create the PR. 06-Feb-EOD-The fix has been applied to Store, Invoice, and Meals pages. Tested on iOS (iPhone & iPad) and Android (phone & tablet). POV done and PR created.
30 | MSB Mobile | 2026-01-23 | 2026-02-05 | 26.3 M Sprint 2 Stretch | Sambath/Amrit | 26716 | MSBA - Shift Mode - Problem Getting Shift | Defect Being Fixed | [20 empty] | 5 Feb - Analyzing and reproducing defect 5 Feb - Defect did not reproduce

## 26.3 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.3 M Sprint 1 | 26556 MSBA - MAUI- Android -Meals and Ticket tabs are not displaying when selecting Store,Invoice,Meals and Tickets under Enabled Menu item in User Settings | 26556 MSBA - MAUI- Android -Meals and Ticket tabs are not displaying when selecting Store,Invoice,Meals and Tickets under Enabled Menu item in User Settings | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.3 M Sprint 1 | 26505 MSBA - MAUI - iphone + iPhone/Android- Card Reader Configure UI hard to interact with" | 26505 MSBA - MAUI - iphone + iPhone/Android- Card Reader Configure UI hard to interact with" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.3 M Sprint 1 | 26534 MSBP - Tickets - Event Details Drawer - Event Name not Wrapping | 26534 MSBP - Tickets - Event Details Drawer - Event Name not Wrapping | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client Dev
| 26.3 M Sprint 1 | 26507 MSBA - MAUI - iphone - UI hamburger menu version is difficult to read | 26507 MSBA - MAUI - iphone - UI hamburger menu version is difficult to read | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.3 M Sprint 1 | 26590 MSBP - iOS/Android - Meal Money AutoPay Payment methods has an extra space above header | 26590 MSBP - iOS/Android - Meal Money AutoPay Payment methods has an extra space above header | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion defects
| 26.3 M Sprint 1 | 26608 MSBA - Checkout Pay button gets disabled after entering a custom amount and then deleting it | 26608 MSBA - Checkout Pay button gets disabled after entering a custom amount and then deleting it | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.3 M Sprint 1 | 26588 MSBA - .NET10 - A - Values are getting retained in step 3, on choosing different shift/turning off and on the closeout entire day | 26588 MSBA - .NET10 - A - Values are getting retained in step 3, on choosing different shift/turning off and on the closeout entire day | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.3 M Sprint 1 | 26598 MSBP - iOS26 - Store Search Bar Formatting differences | 26598 MSBP - iOS26 - Store Search Bar Formatting differences | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | .net10 upgraded defects
| 26.3 M Sprint 1 | 26520 MSBP - .NET 10 - Nav bar Doesn't Appear | 26520 MSBP - .NET 10 - Nav bar Doesn't Appear | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client Dev | .net10 upgraded defects
| 26.3 M Sprint 1 | 26506 MSBA - MAUI - phones - UI issue card reader status and card mode overlap | 26506 MSBA - MAUI - phones - UI issue card reader status and card mode overlap | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26631 MSBA - .NET10 - Android - Blue color Header bar is too tall | 26631 MSBA - .NET10 - Android - Blue color Header bar is too tall | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26624 MSBA - iOS26 - Meals/invoice - Placing cursor on the search field , camera icon and cancel icon overlaps when keyboard displays | 26624 MSBA - iOS26 - Meals/invoice - Placing cursor on the search field , camera icon and cancel icon overlaps when keyboard displays | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26625 MSBA - iOS26 - Searching in Invoice search text box, the search results student data is partially cut off | 26625 MSBA - iOS26 - Searching in Invoice search text box, the search results student data is partially cut off | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26609 MSBA - iOS - Promo-code field is getting displayed for meals/invoice when cart preview is enabled" | 26609 MSBA - iOS - Promo-code field is getting displayed for meals/invoice when cart preview is enabled" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26601 MSBA - Android - Bottom of screen cut off by system navigation and app navigation bar if enabled .net10 | 26601 MSBA - Android - Bottom of screen cut off by system navigation and app navigation bar if enabled .net10 | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26668 MSBP - Android - Event description in my tickets is not showing line breaks properly | 26668 MSBP - Android - Event description in my tickets is not showing line breaks properly | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26673 MSBP - I/A - Forgot Login Info - Next button shows enable even if no mobile number is entered. | 26673 MSBP - I/A - Forgot Login Info - Next button shows enable even if no mobile number is entered. | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.3 M Sprint 1 Stretch | 26623 MSBA - iOS26 - Navigation bars and icon style changed with iOS26(Test Only) | 26623 MSBA - iOS26 - Navigation bars and icon style changed with iOS26(Test Only) | Vaishnavi | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26663 MSBP - iOS/Android - Nav bar persists in store and product screens (.net10) | 26663 MSBP - iOS/Android - Nav bar persists in store and product screens (.net10) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | .net10 upgraded defects
| 26.3 M Sprint 1 Stretch | 26717 MSBA MAUI - Student name field gets hidden behind keyboard in landscape mode on Product detail screen | 26717 MSBA MAUI - Student name field gets hidden behind keyboard in landscape mode on Product detail screen | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Others | regression defects
| 26.3 M Sprint 1 Stretch | 26718 MSBA MAUI - Search bar input box not visible in store screen is not grey active (IOS26) | 26718 MSBA MAUI - Search bar input box not visible in store screen is not grey active (IOS26) | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Others | regression defects

## 26.3 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Sambath/Rupesh/Jagdeep/Prem | 50984 | 50984 MSBA - .NET10 & Package Updates | Story Completed | 3 |  | 21 | 2025-12-11 | 2026-01-09 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46379 | 2025-12-31 | 2026-01-12 | Ashwin | NA | NA | NA | NA | NA | NA | 13 Jan - Will start the testing once the defects testing gets completed . . 14 January- Will continue with the smoke testing of MSBA apps. 19 January - Smoke test in progress in mobile devices. . Testing completed. | Exceeds Expectation |  | Main Sprint
2 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Gursewak/Amrit/Prem | 26482 | MSBA - MAUI - Meal Payment Page other box is blank/white when typing | Defect Fixed | 2 |  | 8.5 | 2026-01-08 | 2026-01-12 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46575 | 2026-01-12 | 2026-01-12 | Sambath | NA | Sean | 2026-01-12 | NA | NA | NA | 9 Jan - Working on it, Text color issue has been fixed, telerikControls:RadEntry background issue is still there trying to fix the issue. 11 Jan - Isssue has been fixed, tested in iOS, working fine, need to test in android, need help any other developer for test the android because in android some project build issue in my side. Issue has been tested in android and iOS, POV done, created PR. Merged, ready for test. 13 Jan - Testing Completed | Exceeds Expectation | Due to some issue ion RadEntry control find the solution take some time. | Main Sprint
3 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Amrit/Vaishnavi | 26552 | MSBP - MAUI - iOS - .net10 - My Tickets -Tickets showing in vertical box instead of showing the ticket details | Defect Fixed | 2 |  | 8 | 2026-01-09 | 2026-01-09 | NA | NA | NA | Sambarth | Na | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46543 | 2026-01-09 | 2026-01-09 | Sambath | NA | NA | 2026-01-09 | NA | NA | NA | 9 - Jan - InProgress 12 - Jan - PR Merged Ready for testing. Testing in progress. Testing completed | Exceeds Expectation |  | Main Sprint
4 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Prem/Chandler | 26514 | MSBP - My tickets - Multiple Buttons greyed out when selecting a single button (regression) | Defect Fixed | 0.5 |  | 5.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 9 Jan - Testing completed | Exceeds Expectation |  | Main Sprint
5 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Rupesh/Prem | 26555 | MSBP - MAUI - iOS - .net10 - Promocode text box is not showing any validation error when invalid code is entered | Defect Fixed | 2 |  | 7 | 2026-01-09 | 2026-01-09 | NA | NA | NA | Sambath | FillAndExpand is depreciated, Please use "Fill" | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46544 | 2026-01-09 | 2026-01-09 | Ashwin | NA | Sean | 2026-01-09 | NA | NA | NA | 12 Jan - Testing completed | Exceeds Expectation |  | Main Sprint
6 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Jagdeep | 26553 | MSBP - MAUI - iOS - .net10 - Hamburger menu Header disappears when navigating back to Homescreen from Tickets screen | Defect Blocked | 3 |  | 11 | 2026-01-09 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Defect Blocked ( Worked and fixed with workround fixes but client side they Waiting for Microsoft Maui new Update) |  |  | Main Sprint
7 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Sambath | 20562 | 20562 MSBP - Unable to Pay Installment Plan after Due Date Passes(verify | Defect Fixed | 1 |  | 19.5 | 2026-01-12 | 2026-01-14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | I am preparing the documents as ashwin discussion, most of them coverd and now getting the api response doing the final verification with api stack. I have shared the document with Ashwin, and one API response needs to be update in the document. so I will check and update it today. | Meets Expectation | The analysis took longer than estimated because there are many processes involved in the invoice workflow. All the processes have been documented and shared with Ashwin. Additionally, we need to wait at least one day to check past invoice dues, so it requires more time than initially estimated. | Main Sprint
8 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Sambath/Prem | 26549 | MSBP - MAUI - Android - .net10 - No spacing between the text and the save button in Partial Payment and Meal money Other amount field | Defect Fixed | 2 |  | 12 | 2026-01-12 | 2026-01-14 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46618 | 2026-01-13 | 2026-01-15 | Ashwin | NA | Ashwin | 2026-01-13 | NA | NA | NA | it can reproduce it in Pixel 4a, so i am fixing it Jan 19 - Testing Completed | Exceeds Expectation |  | Main Sprint
9 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Gursewak/Prem | 26548 | MSBP - MAUI - iOS - .net10 - Program Fees shows in cut off mode after credit card selection | Defect Fixed | 1 |  | 10 | 2026-01-12 | 2026-01-12 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46578 | 2026-01-12 | 2026-01-12 | Sambath | NA | Sean | 2026-01-12 | NA | NA | NA | 12 Jan - Start working on. Issue has been fixed, POV Done, Created PR. Merged, Ready for test. 13 Jan - Testing Completed | Exceeds Expectation |  | Stretch
10 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Gursewak/vaishnavi | 26551 | MSBP - MAUI - iOS/Android - .net10 - When photo is captured, cropping/saving screen is displaying in blue/white background [Timebox] | Defect Fixed | 2 |  | 13 | 2026-01-13 | 2026-01-16 | NA | NA | NA | Na | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46673 | 2026-01-15 | 2026-01-16 | Ashwin | NA | Avery | 2026-01-16 | NA | NA | NA | 13 Jan - Analyze the task, reproduce the issue on Android and iOS, and discuss it with the team if required. Check online to see if this is a .NET 10 issue. After that, I will start development. 13 Jan - EOD - Worked on this task and issue has been fixed with change the Shell.PresentationMode="Animated" to Shell.PresentationMode="ModalAnimated", it's working fine in ios and android but in android showing the status bar after use the Shell.PresentationMode="ModalAnimated". Discussed with Ashwin, Need to will work with Jagdeep on android side with find the solution to fix. 14 Jan - As discussed with ashwin in the call need to work with jagdeep and find the solution for status bar in android. We will check in android and find the solutaion for this. I am facing some project build issue in android, I will try to fix that issue after that I will start working on implement the safe area issue inn android. 14 Jan - EOD - Worked on fix the issue in android status bar color. Tried to implement the safe bar area in android but it's not working, also i have checked it's common issue after android 16 it's working fine but below 16 status bar color not work. trying to find out the solution. 16 Jan - I have done the changes, and discuss the all solution with Ashwin on Slack. He is updated the code that i have suggested to him. now he is created the PR. 16 Jan - EOD - Merged and ready for test... 19 - Ready for testing. Testing completed. | Exceeds Expectation |  | Stretch
11 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Rupesh | 26557 | MSBA - MAUI - iOS - Closeout screen not auto-rotated to Landscape mode | Defect Rejected | 2 |  | 6 | 2026-01-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 13 January : Tried multiple approached to fix this issue. Like tried geometry (UIWindowSceneGeometryPreferencesIOS), made it inside MainThread but that also didn’t work.Tried another approach for connected scene, but no success. Closing the defect as 51539 will be the enhancement story to support/test portrait(Ashwin's comment) | Exceeds Expectation |  | Stretch
12 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Amrit/Prem | 26550 | MSBP - MAUI - Android - .net10 - Cart icon and notification bell icon are not aligned in a straight line | Defect Fixed | 2 |  | 11 | 2026-01-13 | 14/1/2026 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46641 | 2026-01-14 | 2026-01-16 | Sambath | NA | Sean | 2026-01-14 | NA | NA | NA | 13 Jan - Reproducing the defect then will continue for solution of this defect 14 Jan - 60% Complete Will fix for iOS and then will do POV and Review Request 19 Jan - Testing Completed | Exceeds Expectation |  | Stretch
13 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Jagdeep | 26556 | MSBA - MAUI- Android -Meals and Ticket tabs are not displaying when selecting Store,Invoice,Meals and Tickets under Enabled Menu item in User Settings | Defect Ready For Testing | 3 |  | 14 | 2026-01-13 | 2026-01-16 | NA | NA | NA | Gursewak | NA | Pull Request 46694: jagdeep.singh/26556-MSBA-MAUI-Android-Meals and Ticket tabs are not displayin... | 2026-01-16 | NA | Ashwin | NA | Avery | 2026-01-22 | These routes are already defined in AppShell.xaml as ShellContent elements with Route attributes (Store, Invoices, Meals, InPerson). When routes are declared in XAML, you don't need to register them again in code. Routing.RegisterRoute() is only needed for pages that are NOT declared in the Shell XAML. | NA | NA | (13-Jan) Today First will resolve Emulator sdk jdk issue and for simulator with Sambath (Then will start work on it). (14-Jan) Found this is .NET MAUI know issue for Android , found workaround solution and confirmed from Sambath and Ashiwn and continue work on it to Implement it. 16 -Jan will created PR after testing 19 Jan -PR review is pending from Ashwin and Client side. 20 Jan - Internal PR review done Client side pending. 22 jan - Avery commented on PR .(Resolved) Ready for Testing. |  |  | Stretch
14 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Rupesh/Vaishnavi | 26591 | MSBP- iOS/Android - All Webforms Product causes a crash (.net10/datepicker?) | Defect Fixed | 2 |  | 8 | 2026-01-14 | 2026-01-14 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46654 | 2026-01-14 | 2026-01-16 | Ashwin | NA | Sean | 2026-01-15 | NA | NA | NA | 14 Jan- will try to find the exception and then will be working on to fix it. | Exceeds Expectation |  | Main Sprint
15 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Amrit/Vaishnavi | 26593 | MSBP - Android - Add Another Student is causing resource not found on several sections | Defect Fixed | 2 |  | 10 | 2026-01-16 | 2026-01-19 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46719 | 2026-01-19 | 2026-01-21 | Ashwin | NA | Sean | 2026-01-21 | NA | NA | NA | 19 Jan - InProgress 20 Jan - PR Review Approved by Ashwin 21 Jan - Due to this fix, found issues with different screen in parent app. Created BB and assigned this story back to the development. 21 Jan - BB Fixed PR Created 22 Jan - Testing completed | Exceeds Expectation |  | Main Sprint
16 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Gursewak/Vaishnavi | 26547 | MSBP - MAUI - Android - .net10 - Shopping cart, checkout, Refund request , Meal money transfer Headers are not center aligned | Defect Fixed | 3 |  | 15 | 2026-01-16 | 2026-01-20 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46721?_a=files | 2026-01-20 | 2026-01-20 | Ashwin | NA | Sean | 2026-01-20 | NA | NA | NA | 16 Jan - I’ll start working on it, analyze the task, reproduce the issue, and discuss it with the team if required. After that, I’ll begin development. 16 Jan- EOD -Changes completed on Shopping Cart, Checkout, and Refund Request pages. 19 Jan – Started working on pending changes across pages. As suggested by Ashwin, need to check the header title issue throughout the application. After that, will complete the POV and create the PR. 19 Jan EOD - I have completed the functionality as per the AC description and tested it on both iOS and Android. The implementation is working as expected, and I also completed the POV with @bavithra.arasakumaran. After that, I reviewed the code with @sambath.selvam. and based on his review, he suggested some code improvements. He also recommended discussing all these points with you for further clarification. Additionally, header text alignment needs to be fixed across almost the entire application. In some places it’s a minor issue (left/right alignment), but it is present in multiple screens. 20 Jan - Test the app one round of testing, if found any issue i will fix it after that will start work on another task."51564" 20 Jan-Testing completed | Exceeds Expectation |  | Stretch
17 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Jagdeep | 26506 | MSBA - MAUI - phones - UI issue card reader status and card mode overlap | Defect Blocked | 2 |  | 10 | 2026-01-16 | 2026-01-19 | NA | NA | NA | Rupesh | NA | jagdeep.singh/26506-MSBA-MAUI-phones-UI-issue-card-reader-status-and-card-mode-overlap | 2026-01-19 | 2026-01-21 | Ashwin | NA | Avery | 2026-01-21 | NA | NA | NA | 16 Jan - Picked defect after disscuss with Sambath and starting work on it. 19 Jan - Working on it today will do POV and will create PR 20 Jan - PR created , Defect ready for client PR review. 22 Jan - Ready for Testing |  |  | Backlog
18 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Prem | 26596 | MSBP - iOS26 - System message and information boxes style change | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 19 Jan - Testing Completed | Exceeds Expectation |  | Stretch
19 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Prem | 26597 | MSBP - iOS26 - Keyboard and selector Done indicator changed to checkmark and formatting differences | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 19 Jan - Testing Completed | Exceeds Expectation |  | Stretch
20 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Sambath | 26505 | 26505 MSBA - MAUI - iphone + iPhone/Android- Card Reader Configure UI hard to interact with | Defect Being Fixed | 2 |  | 18 | 2026-01-19 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | three issues reported in this defect, One issue has been fixed, and the other two are still in progress.
21 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Prem | 26598 | MSBP - iOS26 - Store Search Bar Formatting differences | Defect Verified | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20 Jan - Assigned to jason to check the fix is not match as expected 21 Jan - Discussion Happened, and its ready for developer | Exceeds Expectation |  | Stretch
22 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Prem | 26599 | MSBP - iOS26 - toggle shape and size has changed | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20 Jan - Testing completed | Exceeds Expectation |  | Stretch
23 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Amrit | 26534 | MSBP - Tickets - Event Details Drawer - Event Name not Wrapping | Defect Being Fixed | 0 |  | 18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 20 Jan - Defect Being Fixed 21 Jan - Client Asked for 1 more change after discussion not included in AC - Working on that 22 Jan - As Discussed with Ashwin will check once with WebView |  | AC changed by client | Stretch
24 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Vaishnavi | 26595 | MSBP - iOS26 - Student card sheet is semi opaque | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Stretch
25 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Jagdeep/Prem | 51560 | MSBP - Android - Payment Receipt - Block Back Button in OS | Story Completed | 0 |  | 8.5 | 2026-01-20 | 2026-01-20 | NA | NA | NA | Ashwin | NA | Pull Request 46730: jagdeep.singh/51560-MSBP-Android-Payment Receipt-Block Back Button in OS | 2026-01-20 | 2026-01-21 | Ashwin | NA | Sean | 2026-01-21 | NA | NA | NA | Testing completed | Exceeds Expectation |  | Stretch
26 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Rupesh | 51561 | MSBP - AutoPay - Land on Home Screen After Successful Top Off | Story Being Developed | 0 |  | 12 | NA | NA | NA | NA | [13 empty] | 20 January - will do the analysis and later will start the development. 21st Jan - Ashwin asked to do some research,so will do that.Research done and informd Ashwin how the payment is getting triggered. |  |  | Stretch
27 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Gursewak | 51564 | MSBP - Forgot Password - Update Text on Forgot Login Info Page | Story Peer Review | 0 |  | 12 | 2026-01-20 | 2026-01-21 | NA | NA | NA |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46760 | 2026-01-21 | [8 empty] | 20 Jan - Will start work on today. 20 Jan - EOD - Started working on this task by analyzing the requirements. Converted the text for all supported languages as part of the multilingual implementation. Discussed the changes with Ashwin during the call. Also started implementing the Terms of Service ¦ Privacy Notice tag and continuing work on it. 21 Jan - As Ashwin discussed with Json, need to implement Terms of Service ¦ Privacy Notice tag and continuing work on it. after that will do Testing, POV and create the PR. 21 Jan - EOD - This task has been completed as per the new changes Jason mentioned. The TOS and PP have been implemented as links to the existing TOS and PP. I did the POV with Bavithra and shared the POV video in the Mobile Team Slack channel. afte that Jason provide some new changes that's also done on the same day and sent the screen shots on slack. |  |  | Stretch
29 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Jagdeep | 26507 | MSBA - MAUI - iphone - UI hamburger menu version is difficult to read | Defect Ready For Testing | 1 |  | NA | 2026-01-21 | 2026-01-21 | NA | NA | NA | NA | NA | Pull Request 46768: jagdeep.singh/26507-MSBA-MAUI-iphone-UI hamburger menu version is difficult t... | 2026-01-21 | NA | Ashwin | NA | Sean | 2026-01-22 | NA | NA | NA | 21 Jan- Will start working on it. 22 Jan - Internal review done , Client side waiting. 22 Jan PR Approved and merged. Defect Ready for Testing |  |  | Stretch
28 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Prem/Chandler | 49399 | MSBP - Kaleida - Header Bar update | Story Being Developed | 1 |  | 25.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Bounceback created and assigned to Onsite developer. Due to open Bounceback, this story is being carry forwarded to the next sprint | Exceeds Expectation | Bounceback created and assigned to Onsite developer. Due to open Bounceback, this story is being carry forwarded to the next sprint | Main Sprint
30 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Prem/Avery | 49398 | MSBP - Kaleida - Bottom Navigations Icons update | Story Completed | 5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 21 Jan - Will start the testing once the build gets done 22 Jan - Testing Completed | Exceeds Expectation | Bounceback created and assigned to Onsite developer. Due to open Bounceback, this story is being carry forwarded to the next sprint | Main Sprint
31 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 | Vaishnavi/Chandler | 49363 | MSBP - Kaleida - Hamburger Menu Enhancements | Story Being Developed | 1 | [19 empty] | Bounceback created and assigned to Onsite developer. Due to open Bounceback, this story is being carry forwarded to the next sprint | Exceeds Expectation | Bounceback created and assigned to Onsite developer. Due to open Bounceback, this story is being carry forwarded to the next sprint | Main Sprint
32 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Gursewak | 26590 | MSBP - iOS/Android - Meal Money AutoPay Payment methods has an extra space above header | Defect Peer Review | 1 |  | 4 | 2026-01-22 | 2026-01-22 | NA | NA | NA | NA |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46796 | 2026-01-22 | [8 empty] | 22 Jan - Start working on it. 22 Jan - EOD - The issue has been fixed and thoroughly tested on both iOS and Android. Conducted a POV with Bavithra and created the PR. |  |  | Stretch
33 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Rupesh | 26608 | MSBA - Checkout Pay button gets disabled after entering a custom amount and then deleting it | Defect Being Fixed | 2 |  |  | 2026-01-22 | [16 empty] | 22 Jan - Started working on it. |  |  | Stretch
34 | MSB Mobile Kaleida | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Jagdeep | 26588 | MSBA - .NET10 - A - Values are getting retained in step 3, on choosing different shift/turning off and on the closeout entire day | Defect Being Fixed | 3 |  | 4 | 2026-01-22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 22 Jan - Start working on it. |  |  | Stretch
35 | MSB Mobile | 2026-01-09 | 2026-01-22 | 26.3 M Sprint 1 Stretch | Vaishnavi | 26579 | MSBP - iOS - Navigation bars and icons changed with iOS26 | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Stretch

## 26.1 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Rupesh/Gursewak/Prem/Vaishnavi | 50972 | MSBP - Tickets - My Tickets Drawer | Story Completed | 3 |  | 86 | 2025-11-21 | 2025-12-10 | NA | Amrit | NA | Sambath | move to resource "Virtual" rename it as GetTicketEventOrdersResponse remove this set remove this comment | Pull Request 46114: 50972-MSBP - Tickets - My Tickets Drawer | 2025-12-09 | 2025-12-10 | Sambath | Total: 4 1: remove this comment 2: move to resource "Virtual" 3: rename it as GetTicketEventOrdersResponse 4: remove this set | Avery | 2025-12-10 | Total: 3 1: SelectUpcomingEventsTabCommand should use Command instead of AsyncCommand since it only contains synchronous property assignments (no await operations). Change back to: new Command(() => { ... }); and remove async keyword. As an aside, for SelectMyTicketsTabCommand - good catch fixing the pre-existing bug since it contains await Refresh(). 2: Creating new HttpClient() for each image causes socket exhaustion. Replace with IoC.Current.Resolve<ParentHttpClient>().Client or use a static readonly HttpClient field to reuse connections. 3: This could cause a race condition - Multiple carousel swipes can trigger OnImageLoadedAsync() simultaneously for the same TicketEvent, causing the image to be downloaded and processed multiple times. Wrap the IsImageProcessed check and processing logic in a SemaphoreSlim to ensure only one thread processes each image. Also fix spacing: "if(" should be "if (". | NA | NA | 17 Dec - I was worked on BB, All BB design issue has been fixed and created the PR. and spend 4hr only. | Needs Improvement | • New AC point added, 2 days before the sprint ennding. • AC Points vs Sigma: Acceptance criteria and sigma values didn’t align, causing confusion and leading to rework. • Changing Requirements: Scope shifted after development began (e.g., QR/Barcode design later added to another story), leading to rework. • Post-POV Changes: Even after proof of value was delivered, new requests were raised, creating scope creep. Overall: Misalignment, shifting requirements, and late changes delayed progress and reduced efficiency. | Main Sprint
2 | MSB Mobile | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Sambath/Rupesh/Jagdeep | 50984 | 50984 MSBA - .NET10 & Package Updates | Story Being Developed | 3 |  | 206 | 2025-11-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | working on it, fixing the biding issues | NA |  | Dec-24 will work to fix the issue’s for CloseDayUserPopup and ClosedaySession screen, completed Student invoice page where binding were broken. Endofdayreconcilation is in progress. EndofdayReconcilation is completed, looks like all the functionality has been verified and fixed, will do one more round of verfication,if we don't find any major issue crashes/binding broken then will close it. For CheckoutPage, We have applied another approach and Informed Sambath to verify it. We have done changes and clean up code also. Need to Disscus with Sambath(Then it will go in Story Peer Review) . We have fixed the back button binding in EndofDayReconcilation Page , it was not throwing any exception but it was not givigng the desired result. We also fixed minor iOS UI Issue. 7 Jan - Gursewak - Start working on iOS And Android EndofReconcilationPage Not holding to landscape mode Reason for dealy | Needs Improvement | This story was initially estimated only for a .NET 10 and package update, but due to the update, many pages has UI issues and page navigation stopped working. As discussed in the standup, we are finding and fixing these issues within the existing story so we couldn’t close this story within this sprint. | Main Sprint
3 | MSB Mobile | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Vaishnavi/Prem | 51219 | MSBP - Full Regression 26.1 | Story Completed | 8 |  | 75.5 | 2025-12-12 | 2025-12-30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Justification for story 51219 - MSBP -Full Regression . Estimated 8sp. Actual - 75.5 The Actual worklogs is beyond the estimation, as all the developers who worked on the regression defects were also filing the worklogs in this regression story. This was the process told by the client and it is followed as a scrum process. | Exceeds Expectation | Justification for story 51219 - MSBP -Full Regression . Estimated 8sp. Actual - 75.5 The Actual worklogs is beyond the estimation, as all the developers who worked on the regression defects were also filing the worklogs in this regression story. This was the process told by the client and it is followed as a scrum process. | Main Sprint
4 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Amrit/Gursewak/Prem | 50197 | MSBP - Make Links Clickable in Notifications | Story Completed | 3 |  | 38 | 2025-10-12 | 2025-12-12 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46172 | 2025-01-12 | 17/12/2025 | Sambath | NA | NA | 17/12/2025 | NA | NA | NA | Gursewak - (11 Dec) - After the implement Webview, there is showing some design different, will work on it after the will give the POV and create the PR. Checked the design that we are added the notification from web showing same as in mobile. Spend some time on notification not showing on UI that added in the portal. Work on android, url is not opening in android but in ios working fine and fix the issue. Doing the testing and will create the POV video for android and iOS. Set the design format for both iOS and Android Friday Sambath told to replace navigation event of android as per MSBA. Working on that. Prem - (Dec 15) - Test Case Updation is completed PR Review Pending from Client Side PR Merged Prem - Dec 18 - Testing completed and closed | Exceeds Expectation | The task was delayed due to design discrepancies identified after the WebView implementation, which required additional alignment for both Android and iOS. Time was also spent fixing an Android-specific issue where notification URLs were not opening, while they worked correctly on iOS. Additional efforts included testing, UI verification, POV preparation, and updating Android navigation as per MSBA guidelines. The delay was further impacted by a pending PR review from the client side. | Main Sprint
5 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Gursewak/Amrit/Prem | 26105 | MSBA - MAUI - Enabling 'Allow oversell' toggle in settings and doing checkout for a product throws error | Defect Fixed | 2 |  | 33 | 2025-10-12 | 16/12/2025 | NA | Sambath | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46247 | 15/12/2025 | 18/12/2025 | Sambath | NA | Sean | 18/12/2025 | NA | NA | NA | 15 Dec - Working on it, today i will try to complete asap. 15 Dec (EOD) - Fixed the issue in "Checkout payment methods(POST)" and it's working fine, As per AC need to implement on two more methods "Checkout preview store item (PUT)" & "Checkout process payment store item(POST)" working on it. 16 Dec - Working on checkout/process/ API facing application stuck issue after the fix this issue will implement same functionality on Checkout preview store item (PUT) 16 Dec (EOD) - worked on same task and completed the all functionality as per the AC and tested on iOS and android. POV is completed with "Bavithra" Not able to build MSBA develop branch due to this issue I am not able to create the PR. changes check with Sambath after that will work with Jagdeep 17 Dec - MSBA build issue has been fixed, will merge the develop branch and test and will create the PR. after that will work on rupesh BB 18 Dec - Fixed the changes as Ashwin suggested, updated the PR, 18 Dec (EOD) - This PR is merged. Prem (19 Dec) - Defect Tested and Closed | Exceeds Expectation | The task involved fixing issues in checkout payment APIs and extending the same functionality to additional endpoints as per AC requirements. During implementation, an application stuck issue was encountered, which required further investigation and resolution before proceeding. Although the functionality was completed and tested on both iOS and Android with POV recorded, a build issue in the MSBA develop branch prevented PR creation. After the build issue was resolved, further updates were made based on review feedback, the PR was updated and merged, and the defect was finally tested and closed. These dependencies and technical issues contributed to the delay. | Main Sprint
6 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Jagdeep/Vaishnavi | 26440 | MSBA - MAUI - Recent student list showing the same student multiple times | Defect Fixed | 2 |  | 6 | 2025-12-15 | 2025-12-15 | NA | NA | NA | Sambath | NA | Pull Request 46221: jagdeep.singh/26440-MSBA-MAUI-Recent student list showing the same student mu... | 2025-12-15 | 2025-12-16 | NA | NA | Sean | 2025-12-16 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
7 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Vaishnavi/Gurusewak/Amrit | 51005 | MSBP - Tickets - Redeemed Ticket UI Update (26.2) | Story Completed | 3 |  | 14 | 2025-12-24 | 2025-12-26 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46370 | 2025-12-26 | 2025-12-26 | NA | NA | Sean | 2025-12-28 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
8 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Jagdeep | 51029 | MSBA - Automation - Store Page | Story Completed | 5 |  | 18 | 2025-12-16 | 2025-12-18 | NA | NA | NA | Sambath | NA | Pull Request 46295: jagdeep.singh/51029-MSBA-Automation-Store Page | 2025-12-18 | NA | Sambath | NA | Owen | 2026-01-06 | I changed this to show how these methods should be addressed. We should be able to run all these methods by themselves. I had to change one from private to public. Please check the rest and make sure they follow this approach. | Completed | NA |  | Exceeds Expectation |  | Main Sprint
9 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Amrit/Prem | 49011 | MSBP - Tickets - Share Ticket Info (26.2) | Story Completed | 3 |  | 31.5 | 2025-12-17 | 22/12/2025 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46335 | 2025-12-22 | 23/12/2025 | Jagdeep | PR Internal Comments - 3 -We have already resource value for Event Details Please remove new one and use existing "EventDetails". -Please remove Padding="0". -Please use TextColor="{StaticResource TitleBlackColor}"> Instead of color code. | Sean | 23/12/2025 | NA |  | NA | Dec 16 - Test Case Updation Completed Dec 17 - Test Case Review Comments Updation - inProgress Dec 18 - Development for Android and Message for sharing text - DONE Prem (Dec 18) - Test Case Comments Updation - Completed Jason ask for UI changes - DONE Share Icon added on MyTickets - DONE iOS POV Pending from Sambath. - Done Android From Rupesh - Done PR Merged Ready for testing 24 Dec - As of now Regression is the high priority. After completing regression testing, will work on these 26.2 items. 30 Dec - Testing is in Progress. Raised a BB and assigned back to Dev 31 Dec -BB is blocked because Physical Device required. Sambath Will check it. 2 Jan - Per conversation during Standup there is an issue where the current Facebook share option is not sending URL and text.Since we can only share either URL or text for now it would make sense to share the URL and allow the user to add their own text. If needed for future can add a story to utilize the SDK and split the share options or find alternative dev solution for this. Jan 5 - Raised a BB and assigned back to developer Jan 6 – Further testing is required on Prem’s device to determine the reason for the Twitter (X) post failure, since the same flow is working on Rupesh’s Android physical device. Jan 7 - Testing completed and closed the BB's | Exceeds Expectation | Physical Device Dependency developer did not have physical device to work and test Share Issue in FB Application Restriction | Main Sprint
10 | MSB Mobile | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Vaishnavi | 51220 | MSBA - Smoke Test | Story Completed | 2 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
10 | MSB Mobile | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Vaishnavi | 51221 | MSBP CA - Regression/Smoke Test Against Staging 26.1 RC | Story Completed | 1 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
11 | MSB Mobile | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Amrit | 50973 | MSBP - Tickets - My Tickets - QR Code/Barcode Ticket (26.1) | Story Completed | 3 |  | 10.5 | 23/12/2025 | 23/12/2025 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46348 | 23/12/2025 | 23/12/2025 | Jagdeep | NA | Sean | 23/12/2025 | NA | NA | NA | 23 - Dec - Testing completed by Letashia. | Exceeds Expectation |  | Main Sprint
12 | MSB Mobile | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Amrit/Rupesh/Prem | 26498 | MSBP - Android - Tickets - Sheets stack when multiple taps occur (regression) | Defect Fixed | 0 |  | 0 | 26/12/2025 | 2026-01-01 | Na | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46389 | 31/12/2025 | 2026-05-01 | Ashwin | NA | Sean | 2026-05-01 | NA | NA | Is this necessary even with the allowsMultipleExecutions set to false? | Current Fix is 60-70% accurate Rupesh Amrit trying to find 100% accurate fix for this Defect PR in Review Prem - 05 Jan - Testing Completed | Exceeds Expectation |  | Main Sprint
13 | MSB Mobile | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Sambath/Gursewak/Amrit/Vaishnavi | 50983 | 50983 MSBP - .NET10 & Package Updates (26.2) | Story Completed | 3 |  | 63.5 | 26/12/2025 | 2026-06-01 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46398 | 31/1/2026 | 2026-06-01 | Ashwin | NA | Sean | 2026-06-01 | NA | NA | NA | fixed the build issue, found some UI issues and i will accomadate others to fixt that Gursewak - 31 dec - Start work on meal money drawer blank issue and notification and cart count UI issue. 02 Jan - Select payment method bottom sheet slow to open, working on it. 5 Jan - Android issues was found and fixed committed in PR. 6 Jan - Created a separate defect to handle(Hamburger iOS Issue)the .NET MAUI version update once the issue is resolved. This story will proceed with smoke testing, peer review, and PR creation, and then be moved to Testing. 8th jan - Testing in progress. | Meets Expectation | This story was initially estimated only for a .NET 10 and package update, but due to the update, many pages has UI issues and page navigation stopped working. As discussed in the standup, we are finding and fixing these issues within the existing story so we couldn’t close this story within this sprint. | Main Sprint
14 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Gursewak/Rupesh/Vaishnavi | 26502 | 26502 MSBP - MAUI - Single tickets are allowing to scroll horizontally and multiple tickets not showing the scroll (regression) | Defect Fixed | 0 |  | 6 | 29/12/2025 | 29/12/2025 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46409 | 29/12/2025 | 29/12/2025 | Amrit | NA | Sean | 2026-01-02 | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
15 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 | Gursewak/Vaishnavi | 26504 | 26504 MSBP - iOS- Pay for More students - Add to cart button color is not displaying in a disabled state in iOS (regression) | Defect Fixed | 0 |  | 6 | 30/12/2025 | 30/12/2025 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46408 | 30/12/2025 | 30/12/2025 | Sambath | NA | Sean | 2026-01-03 | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
16 | MSB Mobile Kaleida | 2025-12-12 | 2026-01-08 | 26.1 M Sprint 3 Stretch | Gursewak | 26482 | MSBA - MAUI - Meal Payment Page other box is blank/white when typing | Defect Being Fixed | 2 |  | 0 | 2026-01-08 | [16 empty] | 8 Jan - Start working on this task. I picked up this task at the end of the sprint, which is why it moved to the next sprint. On the same day, I worked on R&D and analysis and attempted to fix the text and background color issue.

## 26.1 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.1 M Sprint 3 | 26105 MSBA - MAUI - Enabling 'Allow oversell' toggle in settings and doing checkout for a product throws error | 26105 MSBA - MAUI - Enabling 'Allow oversell' toggle in settings and doing checkout for a product throws error | Gursewak/Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.1 M Sprint 3 | 26440 MSBA - MAUI - Recent student list showing the same student multiple times | 26440 MSBA - MAUI - Recent student list showing the same student multiple times | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion defects
| 26.1 M Sprint 3 | 26498 "MSBP - Android - Tickets - Sheets stack when multiple taps occur (regression) | 26498 "MSBP - Android - Tickets - Sheets stack when multiple taps occur (regression) | Amrit/Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | regression defects
| 26.1 M Sprint 3 | 26502 26502 MSBP - MAUI - Single tickets are allowing to scroll horizontally and multiple tickets not showing the scroll (regression) | 26502 26502 MSBP - MAUI - Single tickets are allowing to scroll horizontally and multiple tickets not showing the scroll (regression) | Gursewak/Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | regression defects
| 26.1 M Sprint 3 | 26504 26504 MSBP - iOS- Pay for More students - Add to cart button color is not displaying in a disabled state in iOS (regression) | 26504 26504 MSBP - iOS- Pay for More students - Add to cart button color is not displaying in a disabled state in iOS (regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | regression defects

## 26.1 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Jagdeep | 50462 | MSBA - Automation - Meals Page | Story Completed | 3 |  | 19 | 2025-11-11 | 2025-11-25 | NA | NA | NA | Sambath | Total PR Comments: 5 1. EnableCartPreviewBeforeCheckout().SettingsPageSaveButtonAction() method is there in SettingsPage, please use that method 2. remove this method, Use settings page 3. removed this loop, use FindByText() 4. remove the try catch block, and use FindUntilElementFound() 5. User Assert.Fail("") instead of Exception | Pull Request 45696: jagdeep.singh/50462-MSBA-Automation-Meals Page | 2025-11-13 | NA | Ashwin | NA | Owen | 2025-12-10 | NA | NA | NA |  | Exceeds Expectation | This story was developed from the initial state, including setting up a new project flow and common methods. Additional effort during PR review and incorporating client feedback helped refine and simplify the solution, making it more effective and widely usable. Which has resulted in logging more hours than originally estimated. Total estimated time | Main Sprint
2 | MSB Mobile | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Sambath/Gursewak/Jagdeep/Prem | 49777 | MSBP - Retain Meal Money Selection | Story Completed | 5 |  | 97.5 | 2025-11-13 | 2025-12-05 | NA | NA | NA | Sambath | Total PR Comments: 5 1. Why this amount.Parent = this ? 2. Why this prop? 3. No need to get from each, you can delete all cart items from the MealBasketItems 4. use GetExistingMealMoneyFromCart() method for basket Meal item 5. Move the logic for deleting basket items to a common place in the BaseViewModel, as this code is duplicated multiple times. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45785 | 2025-11-13 | 2025-12-05 | Ahwin | NA | Avery | 2025-12-05 | Total PR Comments: 24 1. The nested loop through FundingAmountList is unnecessary. You already have the amount from the cart, just check if it matches a preset button, and if not, set the 'Other' field. The current implementation processes the IsOtherAmount block multiple times per student when it should only run once. 2. This PR adds cart retention to AddFundsViewModel, but StudentDetailViewModel also has meal money functionality and lacks similar cart restoration logic. Should that be addressed in this PR or tracked separately for consistency? 3. Can you clarify? I don't see cart restoration logic in StudentDetailViewModel. When a user adds meal money from StudentDetailViewModel, navigates to the cart, then clicks 'Continue Shopping', does the selected amount get restored on StudentDetailViewModel like it now does on AddFundsViewModel? If yes, where is that code? If no, we need to add it for consistency. 4. Remove this null check - it's redundant since selectedStudents is already filtered by a LINQ .Where() clause that ensures non-null results. 5. This triple-nested loop has a fundamental logic issue. The innermost filter fundingAmounts.Where(x=> x.StudentKey == item.StudentKey) doesn't work as intended because all items in selectedStudent.FundingAmountList share the same StudentKey. This makes the filter redundant and causes all fundingAmounts for that student to be processed repeatedly for each preset amount button. The logic needs to be refactored to properly match cart items with their corresponding UI elements. 6. Why are you setting IsBusy = false here? This seems unrelated to the meal money retention requirement. Is this fixing a separate bug or could this cause issues if something is actually busy? 7. Is this early return behavior intentional for this feature, or should the deletion continue attempting remaining items even if one fails? 8. The outer parentheses wrapping the entire expression ((FundStudent?.FundAmount > 0) ¦¦ IsEditMealMoneyFromCart) are unnecessary and should be removed for cleaner code. 9. Change FundStudent?.FundingAmountList - to FundStudent.FundingAmountList 10. This checks if (FundStudent?.StudentKey == cartItem.StudentKey) but you already verified FundStudent != null at line 349 inside the outer if condition. Remove the null-conditional. 11. basketItemKeys can be null when GetExistingMealMoneyFromCart() returns null. Add null-conditional: if (basketItemKeys?.Any() ?? false) or check if (basketItemKeys != null && basketItemKeys.Any()) 12. studentsToDelete.Select(s => s.Student.StudentSID) is executed on every iteration of the Where() clause. Move it outside: var studentSIDs = studentsToDelete.Select(s => s.Student.StudentSID).ToList(); then use studentSIDs.Contains(x.StudentKey). 13. The else block is unnecessary - when FundAmount == 0, the code returns at line 245, so the else is redundant. Remove it to reduce nesting. 14. The BackgroundColor value was changed from {x:StaticResource SecondaryDisabledButtonBackgroundColor} to the hardcoded hex value #EAEBEE. This breaks the theming pattern used throughout the app and makes the color unmaintainable. Please restore the StaticResource or explain why it needed to change 15. This property unconditionally returns true. However, AddFundsViewModel and StudentDetailViewModel both check FundAmount > 0 OR if in edit mode. The current implementation allows users to submit with $0. The OnAmountChangedCommand at line 703 calls RaisePropertyChanged(() => IsFundAmountSelect) expecting the property to react to amount changes, but it's hardcoded to true. Compare with the pattern used in the other ViewModels. 16. Returning null instead of an empty list is inconsistent with standard C# patterns and forces all callers to perform null checks. Either change to return new List<MealBasketItem>(); or update the method signature to List<MealBasketItem>? to make the nullable intent explicit. 17. GetExistingMealMoneyFromCart() can return null, but you're calling .FirstOrDefault() directly on it without a null check. Add a null-conditional operator 18. You moved the validation check after creating two lists and iterating through FundStudentList. If validation fails (no amounts selected and not in edit mode), the list creation and loop execution were completely wasted. The original placement was correct - it followed the "fail fast" principle. 19. The ternary operator ? true : false is redundant. The equality comparison already returns a boolean. 20. Remove unnecessary outer parentheses around GetExistingMealMoneyFromCart()?.Any() == true - they serve no purpose. 21. Setting BackgroundColor directly may not trigger UI update. If this doesn't work in testing, you may need RaisePropertyChanged() or a bindable property. Also, cache the resource lookup outside the loop: var whiteColor = (Color)Application.Current.Resources["PrimaryWhiteColor"]; to avoid repeated dictionary lookups. 22. Variable name "item" is too generic. Rename to matchingPresetAmount or presetAmount to clarify what it represents in this context. 23. Excessive nesting (3 levels deep). Use early returns to flatten. This significantly improves readability. 24. Inconsistent brace placement. Fix this formatting. | NA | NA |  | Exceeds Expectation | Sambath: The AC is unclear. They referred only to the Meal page for retail selection, but later the new AC was added multiple times, which extended its scope of work. Amrith: Changes was done but as per AC things was not planned carefully with other scenarios in mind. Which is why AC was updated and took more efforts with discussion with client | Main Sprint
3 | MSB Mobile | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Sambath | 26316 | 26316 MSBAnywhere Android Version 14.7.1.147377 Missing Expected Cash on MSBA Close Out Report | Defect Fixed | 5 |  | 30 | 2025-11-14 | 2025-12-04 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46030?_a=files | 2025-12-03 | 2025-12-04 | Ahwin | NA | Avery | 2025-12-04 | NA | NA | NA | Tested by Onsite QA. | Exceeds Expectation |  | Main Sprint
4 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Sambath/Prem | 26327 | MSBP - MAUI - iOS -Contact info drawer not showing in Greenlight when selecting Contact Greenlight Support | Defect Fixed | 1 |  | 73 | 2025-11-19 | 2025-12-08 | NA | Gursewak | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46082 | 21/11/2025 | NA | Ahwin | NA | Avery | 2025-12-10 | Total PR Comments: 4 Use null-conditional operator for consistency with codebase patterns, Extract magic number 600 to named constant, Remove cast by adding GreenlightCards property to ISession interface. GreenlightSupport recreated on every tap. Initialize once in InitializeGreenlightComponents() instead. | Na | NA | dev has been completed, and working with code refactoring Gursewak (8 Dec) - Work with Sambath today. Prem (Dec-10) Testing is completed | Exceeds Expectation | Sambath : I tried with different ways to fix the issue in RadSlideView, but nothing worked. After discussing with Sean, he suggested splitting it into different bottom sheets instead of using a single RadSlideView page. As a result, the estimated time has been extended Amrith : Fix was not working it was discussed with team and client. Issue was only in IOS Issue was in Bottomsheet source code third party Plugin | Main Sprint
5 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Gursewak/Rupesh/Vaishnavi | 50970 | MSBP - Tickets - MyTickets update in Hamburger and Events Card | Story Completed | 1 |  | 17.5 | 2025-11-20 | 2025-11-26 | NA | NA | NA | Sambath | Total 2 1. move to resource file 2. remove this code, no need here | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45944 | 26/11/2025 | 26/11/2025 | Ahwin | NA | Avery | 2025-12-02 | NA | NA | NA | 21 Nov - Working on the same task, implement the Tab bar and bind the data as per requirement. 24 Nov - This task has been completed, POV is pending. 26 Nov - Discussed with team, Completed the new AC changes, POV is done after the changes, created the PR. 27 Nov - Worked on implement the navigation flow as discussed with Sambath, created the PR, resolved the PR comments. shared the video. | Exceeds Expectation | The task involved implementing the tab bar and binding data as per the requirements. Although the development was completed, the POV was pending initially. Additional time was required to discuss and incorporate new AC changes with the team, after which the POV was recorded and the PR was created. Further work included implementing the updated navigation flow as discussed with Sambath, addressing PR review comments, and sharing the final POV video, which contributed to the delay. | Main Sprint
6 | MSB Mobile | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Rupesh/Prem | 50972 | MSBP - Tickets - My Tickets Drawer | Story Being Developed | 3 |  | 86 | 2025-11-21 | 2025-12-10 | NA | Amrit | NA | Sambath | Total PR Comments: 5 • remove this comment • where is this logic? • move to resource "Virtual" • rename it as GetTicketEventOrdersResponse • remove this set | Pull Request 46114: 50972-MSBP - Tickets - My Tickets Drawer | 2025-12-09 | 2025-12-10 | Sambath | NA | Avery | 2025-12-10 | Total PR Comments: 3 • This could cause a race condition - Multiple carousel swipes can trigger OnImageLoadedAsync() simultaneously for the same TicketEvent, causing the image to be downloaded and processed multiple times. Wrap the IsImageProcessed check and processing logic in a SemaphoreSlim to ensure only one thread processes each image. Also fix spacing: "if(" should be "if (". • Creating new HttpClient() for each image causes socket exhaustion. Replace with IoC.Current.Resolve<ParentHttpClient>().Client or use a static readonly HttpClient field to reuse connections. • SelectUpcomingEventsTabCommand should use Command instead of AsyncCommand since it only contains synchronous property assignments (no await operations). Change back to: new Command(() => { ... }); and remove async keyword. As an aside, for SelectMyTicketsTabCommand - good catch fixing the pre-existing bug since it contains await Refresh(). | NA | NA | BB created and assigned back to developer | Needs Improvement | Due to some new changes in the AC, and implement the new changes in new ticket, first we have implement the all functionality in one ticket only. because some tickets in dependent on each other. | Main Sprint
7 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Jagdeep/Prem | 50971 | MSBP - Tickets - Update Events Screen with My Tickets | Story Completed | 2 |  | 15 | 2025-11-21 | 2025-11-28 | NA | NA | NA | Sambath | Total PR Comments: 5 1. You don’t need DataMember at all. If the property name is different, then use [JsonPropertyName("result")] 2. DataContract no need for MAUI 3. MaxPrice is not getting from api, then why you use it here? 4. My Tickets is already available with latest code, please re use it, and remove this resource 5. Do we need min and Max to be assigned a value her | Pull Request 45966: jagdeep.singh/50971-MSBP-Tickets-Update Events Screen with My Tickets | 2025-11-27 | NA | Ashwin | Do we need min and Max to be assigned a value here? | Avery | 2025-12-05 | Total PR Comments: 6 1. Add a null check for UpdatedTicketsData in the condition: if (eventName != null && UpdatedTicketsData != null). Currently, if UpdatedTicketsData is null when the user taps the ticket indicator, they'll be switched to an empty My Tickets tab which is confusing. 2. Nearly identical CollectionView markup is duplicated here from lines 117-259. The structures differ only in ItemsSource binding (Events vs Tickets), IsVisible binding, AutomationId values, and the My Tickets version is missing the TapGestureRecognizer. This creates maintenance overhead - any UI changes must be applied twice. Consider consolidating with a single CollectionView or extracting the common template. 3. Null-handling with x.Name ?? string.Empty in TryGetValue may not behave as expected when x.Name is null (empty string won't match existing dictionary keys). Consider: !string.IsNullOrEmpty(x.Name) && purchasedTicketCounts.TryGetValue(x.Name, out var count) ? count : 0. 4. EventLocation mapping is incomplete - the Coordinates property is not being populated. This will cause the directions feature to fail since EventDetailsSheet.xaml.cs checks for latitude and longitude values. Compare with the complete mapping in TicketService.cs 5. Can you fix this typo in TicketEvents.cs please, it's "ShoolNumber" but should be "SchoolNumber" 6. This is declared but never used anywhere in the codebase. Consider removing to reduce code clutter. | NA | NA |  | Exceeds Expectation | For this Story they give total (7 sp) in pervious sprint it was (5 sp) After fixing they have added some new AC point with story and new requirment and extend 2 sp with this sprint. So full compelted inclueded testing and PR review also it take 36 hours estimated time was 28 hours. | Main Sprint
8 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Amrit/Prem | 26335 | MSBA - MAUI - District name overlapping when it is greater than 43 characters | Defect Fixed | 0.5 |  | 35 | 2025-11-21 | 2025-11-24 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46010 | 2025-12-02 | 2025-03-12 | Rupesh | NA | Avery | 2025-05-12 | Total PR Comments - 3 1 - change to VerticalOptions="Fill". 2 - Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" /> change to VerticalOptions="Fill". Unnecessary nested StackLayout The outer StackLayout with x:Name="TitleGrid" only contains a single HorizontalStackLayout child and provides no layout value. Remove this StackLayout and move its properties (Grid.Column, x:Name, Margin) to the HorizontalStackLayout directly. Also update HorizontalOptions="CenterAndExpand" to HorizontalOptions="Center" on the updated HorizontalStackLayout. 3- Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" /> | NA | TOTAL PR Comments - 3 1 - change to VerticalOptions="Fill". 2 - Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" /> change to VerticalOptions="Fill". Unnecessary nested StackLayout The outer StackLayout with x:Name="TitleGrid" only contains a single HorizontalStackLayout child and provides no layout value. Remove this StackLayout and move its properties (Grid.Column, x:Name, Margin) to the HorizontalStackLayout directly. Also update HorizontalOptions="CenterAndExpand" to HorizontalOptions="Center" on the updated HorizontalStackLayout. 3- Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" /> | Requirement Changed multiple time during standup during discussion with client for Android and iOS Tablet. | Exceeds Expectation | -AC requirement was not defined for more than 43 characters for UI (Multiline,SingleLine) -Special account was created for this testing and development -Continue Review and Discussion happened with client for Approval -Pair coding was implicitly followed though not planned which was not required, which limited parallel work and increased effort. | Main Sprint
9 | MSB Mobile | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Amrit /Gursewak/Prem | 26147 | MSBP - MAUI - Stock options in Donation is not showing when it is added. Going back and front it is showing | Defect Fixed | 1 |  | 21.75 | 2025-11-25 | 2025-11-26 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45930 | 2025-04-12 | 2025-06-12 | Ashwin | NA | Avery | 2025-06-12 | NA | NA | Na | Defect was fixed in 4 hours. But discussion make it late from client side and internal side for changes also stock options data was not coming so it was difficult to test and verify. | Exceeds Expectation | Defect was fixed in 4 hours. But discussion make it late from client side and internal side for changes also stock options data was not coming so it was difficult to test and verify. -Pair coding was implicitly followed though not planned which was not required, which limited parallel work and increased effort. | Main Sprint
10 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 | Gursewak/Sambath | 25751 | MSBP - When selecting a list box there is a delay which does not always select option (regression) | Defect Rejected | 3 |  | 4 | 2025-11-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rejecting this as per discussion in standup as its an existing edge case scenario too and has not been reported yet. Tried to fix this issue but since this issue is low level and is in the RadListPicker control it could not be fixed. To repro this issue we have to be really fast in clicking the OK button after scroll before the value gets set in the SelectItem property. | Meets Expectation | NA | Main Sprint
11 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 Stretch | Chandler/Prem | 51025 | MSBP – Update MSB Activities Icon to Avoid Duplication with Tickets Icon | Story Completed | 0.5 |  | 1.75 | 2025-11-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Stretch
12 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 Stretch | Jagdeep/Vaishnavi | 45174 | MSBA - Searching for students with Scanner does not add them to recent student list (hardware) | Story Completed | 2 |  | 6 | 2025-12-01 | 2025-12-01 | NA | NA | NA | Gursewak | NA | Pull Request 45977: jagdeep.singh/45174-MSBA-Searching for students with Scanner does not add the... | 2025-12-01 | NA | Ashwin | NA | Avery | 2025-12-10 | NA | NA | NA |  | Exceeds Expectation |  | Stretch
13 | MSB Mobile | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 Stretch | Vaishnavi | 51132 | MSBA - Enabling Allow Oversell toggle in settings and doing checkout for product throws error (Xamarin) | Story Completed | 1 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Stretch
14 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 Stretch | Amrit/Gursewak | 50197 | MSBP - Make Links Clickable in Notifications | Story Peer Review | 3 |  | 12 | 2025-10-12 | 2025-12-12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46172 | 2025-01-12 | NA | NA | NA | NA | NA | NA | NA | NA | Gursewak - (11 Dec) - After the implement Webview, there is showing some design different, will work on it after the will give the POV and create the PR. Checked the design that we are added the notification from web showing same as in mobile. Spend some time on notification not showing on UI that added in the portal. Work on android, url is not opening in android but in ios working fine and fix the issue. Doing the testing and will create the POV video for android and iOS. Set the design format for both iOS and Android | Exceeds Expectation | -The task took extra time due to unplanned WebView UI differences, notification visibility issues from the portal, and an Android-specific URL handling problem that did not occur on iOS. -Additional testing and design alignment were required to ensure consistent behavior across both platforms before creating the POV and PR. -Pair coding was implicitly followed though not planned which was not required, which limited parallel work and increased effort. | Stretch
15 | MSB Mobile Kaleida | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 Stretch | Jagdeep/Rupesh | 51114 | Mobile - SHA2 Update | Story Completed | 2 |  | 4 | 2025-12-11 | 2025-12-11 | NA | NA | NA | NA | NA | Pull Request 46164: jagdeep.singh/51114-Mobile-SHA2 Update | 2025-12-11 | 2025-12-11 | Sambath | NA | Sean | 2025-12-11 | NA | NA | NA |  | Exceeds Expectation |  | Stretch
16 | MSB Mobile | 2025-11-27 | 2025-12-11 | 26.1 M Sprint 2 Stretch | Sambath | 50984 | 50984 MSBA - .NET10 & Package Updates | Story Being Developed | 3 |  | 5 | 2025-12-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Exceeds Expectation

## 26.1 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.1 M Sprint 2 | 26316 MSBAnywhere Android Version 14.7.1.147377 Missing Expected Cash on MSBA Close Out Report" | 26316 MSBAnywhere Android Version 14.7.1.147377 Missing Expected Cash on MSBA Close Out Report" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Others | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 2 | 26327 MSBP - MAUI - iOS -Contact info drawer not showing in Greenlight when selecting Contact Greenlight Support | 26327 MSBP - MAUI - iOS -Contact info drawer not showing in Greenlight when selecting Contact Greenlight Support | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz Dev | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 2 | 26335 MSBA - MAUI - District name overlapping when it is greater than 43 characters | 26335 MSBA - MAUI - District name overlapping when it is greater than 43 characters | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 2 | 26147 MSBP - MAUI - Stock options in Donation is not showing when it is added. Going back and front it is showing | 26147 MSBP - MAUI - Stock options in Donation is not showing when it is added. Going back and front it is showing | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 2 | 25751 MSBP - When selecting a list box there is a delay which does not always select option (regression) | 25751 MSBP - When selecting a list box there is a delay which does not always select option (regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects

## 26.1 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Jagdeep | 50462 | MSBA - Automation - Meals Page | Story Peer Review | 2 |  | 14 | 2025-11-11 | 2025-11-25 | NA | NA | NA | Sambath | NA | Pull Request 45696: jagdeep.singh/50462-MSBA-Automation-Meals Page | 2025-11-13 | NA | Ashwin | NA | NA | NA | NA | NA | NA | Owen review is pending. |  | This story was developed from the initial state, including setting up a new project flow and common methods. Additional effort during PR review and incorporating client feedback helped refine and simplify the solution, making it more effective and widely usable. Which has resulted in logging more hours than originally estimated. Total estimated time | Main Sprint
2 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Rupesh | 50460 | MSBA - Automation - User Settings – Edit and Verify | Story Completed | 1 |  | 37 | 2025-10-31 | 2025-11-19 | NA | NA | NA | Sambath | estContext.TestException params is missing like below code, please add it, IsSave = false, make as default params, why this identifier are passing as args? | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/45673 | 2025-11-14 | 2025-11-19 | Ashwin | NA | Owen | 2025-11-19 | NA | Completed | NA |  | Exceeds Expectation | It was carried from last sprint where estimation was 5 SP. There was a relation with Mealmoney page where another dev was working, initially it was implemented with extension method approach , however client wanted simpler approach, so we had to do some rework for that. | Main Sprint
3 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Gursewak/vaishnvi | 50876 | MSBP - Store - Dual Enrollment - Not Displaying Expected Stores | Story Completed | 2 |  | 33 | 2025-11-14 | 2025-11-19 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45733 | 2025-11-18 | 2025-11-18 | Ashwin | NA | Avery | 2025-11-20 | Add a check for enrollment status at the beginning of the Where condition to filter out inactive enrollments before checking school matches. Reuse the district variable to avoid unnecessary repeated lookups Extract the logo query to a variable so it's only executed once per enrollment. | NA | NA | 13 Nov - Start working on it. 14 Nov - This issue has been fixed, tested in iOS/Android also with "Vaishnavi". POV is pending. 17 Nov - Testing, did the POV with "Bavithra" and in client meeting. 18 Nov - Worked on check if there is any caching enabled in the app when making the API call. 19 Nov - Worked on PR comments, tested, Update the PR and tested the app with Web app as well as postman | Exceeds Expectation | The task involved fixing the reported issue and validating it on both iOS and Android with the team. While the fix was completed, the POV was initially pending. Additional time was spent on testing, recording the POV during the client meeting, and verifying whether caching was enabled during API calls. Further effort was required to address PR review comments, update the PR, and re-test the application with the web app and Postman, which contributed to the delay. | Main Sprint
4 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Rupesh/Vaishnavi | 23091 | MSBP - Announcements/Notifications - Showing as Received on Mon Jan 1 | Defect Fixed | 0.5 |  | 18.25 | 2025-11-13 | 2025-11-14 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45701 | 2025-11-14 | 2025-11-17 | Ashwin | NA | Awery | 2025-11-17 | NA | Completed | NA |  | Exceeds Expectation | There was development challenges, Initially thought backend support will be needed but later on we manage to it at our side only, that is why it took some extra time. | Main Sprint
5 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Sambath | 49777 | MSBP - Retain Meal Money Selection | Story Being Developed | 1 |  | 12 | 2025-11-13 | NA | NA | NA | NA | Gurwewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45785 | 18/11/2025 | NA | NA | NA | NA | NA | NA | NA | NA | AC Updated and assigned back to development. Partially completed but need to holding due AC challanges, and story is not yet refined | Needs Improvement | AC has been updated at the end of the sprint | Main Sprint
6 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Vaishnavi/Prem | 50880 | MSBP CA - Regression/Smoke Test Against Staging 15.3 RC | Story Completed | 1 |  | 4 | 2025-11-14 | 2025-11-14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
7 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Jagdeep | 50869 | MSBP - Get Existing Automation to Run in IOS: AssignGreenlight | Story Completed | 2 |  | 8 | 2025-11-14 | 2025-11-17 | NA | NA | NA | Sambath | NA | Pull Request 45726: jagdeep.singh/50869-MSBP-Get Existing Automation to Run in IOS AssignGreenlight | 2025-11-14 | 2025-11-18 | Ashwin | NA | Owen | 2025-11-18 | NA | Completed(With Ashwin) | NA |  | Exceeds Expectation |  | Main Sprint
8 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Sambath | 26316 | 26316 MSBAnywhere Android Version 14.7.1.147377 Missing Expected Cash on MSBA Close Out Report | Defect Being Fixed | 3 |  | 12 | 2025-11-14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Reverify with Dev service team for Time zone issue | Needs Improvement | there is not clear input is there find the root cause, we have only production data to find the root | Main Sprint
9 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Prem/Chandler/Vaishnavi | 50418 | MSBP - Deep linking - Finish Remaining App Intent Links (15.4) | Story Completed | 1 |  | 31.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Justification for higher actual worklogs : this was worked by the Onsite developer. We had around 10+ bouncebacks for this story. Initially it was estimated as 1 by due to re-testing of the bouncebacks we found few more issues for which we spend around which was addressed and closed by the developer. | Exceeds Expectation | Justification for higher actual worklogs : this was worked by the Onsite developer. We had around 10+ bouncebacks for this story. Initially it was estimated as 1 by due to re-testing of the bouncebacks we found few more issues for which we spend around which was addressed and closed by the developer. | Main Sprint
10 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Amrit | 26327 | MSBP - MAUI - iOS -Contact info drawer not showing in Greenlight when selecting Contact Greenlight Support | Defect Being Fixed | 2 |  | 13 | 19/11/2025 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45865 | 21/11/2025 | NA | NA | NA | NA | NA | NA | Na | NA | In Absence of Ashwin it was tested late and reviewed late so moved to next sprint with PR Comments | Exceeds Expectation | In Absence of Ashwin it was tested late and reviewed late so moved to next sprint with PR Comments | Main Sprint
11 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 | Sambath/Prem | 50841 | MSBP - AgentForce - Web View | Defect Needs More Info | 3 |  | 6 | 2025-11-20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | I’m blocked due to a CORS issue in Salesforce. We are unable to access the Salesforce endpoint because of an API error (401) and the message ‘Calls from this domain are not allow-listed.’ | Needs Improvement | Can't have conversations with them until at minimum next week. moving tobacklog until we're able to pull forward | Main Sprint
12 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Jagdeep | 26324 | MSBP - MAUI - Homescreen not loading the data when assigning/un-assigning GL and relogging in again. | Defect Fixed | 1 |  | 6 | 2025-11-20 | 2025-11-20 | NA | NA | NA | Rupesh | NA | Pull Request 45835: jagdeep.singh/26324-MSBP-MAUI-Homescreen not loading the data when assigning... | 2025-11-20 | 2025-11-22 | Ashwin | NA | Sean | 2025-11-22 | NA | Completed | NA | Tested by Letashia. | Exceeds Expectation |  | Stretch
13 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Gursewak | 50970 | MSBP - Tickets - MyTickets update in Hamburger and Events Card | Story Peer Review | 2 |  | 23 | 2025-11-20 | 2025-11-26 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45944 | 2025-11-26 | 2025-12-02 | Sambath | NA | Avery | 2025-12-02 | NA | NA | NA | 21 Nov - Working on the same task, implement the Tab bar and bind the data as per requirement. 24 Nov - This task has been completed, POV is pending. 26 Nov - Discussed with team, Completed the new AC changes, POV is done after the changes, created the PR. 27 Nov - Worked on implement the navigation flow as discussed with Sambath, created the PR, resolved the PR comments. shared the video. |  | The task included implementing the tab bar and binding data as per requirements. While development was completed, the POV was initially pending. Additional time was spent discussing and implementing new AC changes with the team, after which the POV was recorded and the PR was created. Further work involved implementing the updated navigation flow as discussed with Sambath, resolving PR review comments, and sharing the final video, which contributed to the delay. | Main Sprint
14 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Rupesh | 50972 | MSBP - Tickets - My Tickets Drawer | Story Being Developed | 8 |  | 20 | 2025-11-21 |  | NA | NA | NA | [12 empty] | QRCode/BArCode generation done. AC got chnaged, need to clarify those points. I had made the chnages as per the Ac, but now it looks like they are not part of it, so will have to revert those chnages from loacal and today will be working on UI as per the new chnages.
15 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 20.1 M Sprint 1 Stretch | Jagdeep | 50971 | MSBP - Tickets - Update Events Screen with My Tickets | Story Being Developed | 5 | 0 | NA | 2025-11-21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  |  |  |  | UI update on Upcoming Events screen completed. Today will work for integrate API and binding. |  |  | Stretch
16 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Rupesh /vaishnavi | 26132 | MSBP - MAUI - Checkout districts not in the same order as the cart districts | Defect Fixed | 1 |  | 9 | 2025-11-19 | 2025-11-21 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45847 | 2025-11-21 | 2025-11-21 | Ashwin | NA | Sean | 2025-11-21 | NA | Completed | NA |  | Exceeds Expectation |  | Stretch
17 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Gursewak | 23901 | MSBA - Sales Tag - Close Out - Not showing on reports when Shift Mode is not used | Defect Fixed | 1 |  | 6 | 2025-11-20 | 2025-11-20 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45846 | 2025-11-20 | 2025-11-20 | Ashwin | NA | Avery | 2025-11-21 | NA | NA | NA | Tested by Letashia | Exceeds Expectation |  | Stretch
18 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Rupesh/Prem | 26264 | MSBA MAUI - Iphone - Cancel button alignment is not proper in Close Out - Step 1 Screen | Defect Fixed | 1 |  | 7 | 2025-11-14 | 2025-11-17 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45730 | 2025-11-14 | 2025-11-17 | Ashwin | NA | Awery | 2025-11-17 | NA | Completed | NA |  | Exceeds Expectation |  | Stretch
19 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Rupesh/Prem | 26323 | MSBP MAUI - I/A - Info Message shows in cut off mode, when there are no students in Add Meal Money Page | Defect Fixed | 1 |  | 13 | 2025-11-17 | 2025-11-20 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45816 | 2025-11-19 | 2025-11-20 | Ashwin | NA | Awery | 2025-11-20 | NA | NA | NA |  | Exceeds Expectation |  | Stretch
20 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Amrit | 26335 | MSBA - MAUI - District name overlapping when it is greater than 43 characters | Defect Peer Review | 0.5 |  | 8 | 2025-11-21 | 2025-11-24 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45917 | NA | NA | NA | NA | NA | NA | NA | NA | 1 - change to VerticalOptions="Fill". 2 - Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" /> change to VerticalOptions="Fill". Unnecessary nested StackLayout The outer StackLayout with x:Name="TitleGrid" only contains a single HorizontalStackLayout child and provides no layout value. Remove this StackLayout and move its properties (Grid.Column, x:Name, Margin) to the HorizontalStackLayout directly. Also update HorizontalOptions="CenterAndExpand" to HorizontalOptions="Center" on the updated HorizontalStackLayout. 3- Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" /> | Working on comment during POV. Will do Again POV today Separate account was created for long district name and tested late Discussion went on with client during development so many changes happened after that Requirement was not defined exactly by client so discussed during call and in chat | Exceeds Expectation | Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" />
21 | MSB Mobile | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Amrit | 26147 | MSBP - MAUI - Stock options in Donation is not showing when it is added. Going back and front it is showing | Defect Being Fixed | 0 |  | 7 | 2025-11-25 | 2025-11-26 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45930 | NA | NA | NA | NA | NA | NA | NA | NA | Na | POV InProgress. Need to check API API Checked Issue was fixed in 4 hours But discussion internal went on to check and verify changes with Xamarin app which is why PR was approved late. | Exceeds Expectation | POV InProgress. Need to check API API Checked Issue was fixed in 4 hours But discussion internal went on to check and verify changes with Xamarin app which is why PR was approved late. | Stretch
22 | MSB Mobile Kaleida | 2025-11-14 | 2025-11-26 | 26.1 M Sprint 1 Stretch | Gursewak | 25751 | MSBP - When selecting a list box there is a delay which does not always select option (regression) | Defect Rejected | 0 |  | 4 | 2025-11-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Checking control if change anything perivousely in this control. |  |  | Stretch

## 26.1 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 26.1 M Sprint 1 | 23091 MSBP - Announcements/Notifications - Showing as Received on Mon Jan 1 | 23091 MSBP - Announcements/Notifications - Showing as Received on Mon Jan 1 | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Others | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 26316 MSBAnywhere Android Version 14.7.1.147377 Missing Expected Cash on MSBA Close Out Report" | 26316 MSBAnywhere Android Version 14.7.1.147377 Missing Expected Cash on MSBA Close Out Report" | Sambath | Defect |  | Minor | Manual | External | Inprogress | Development | Others | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 26327 MSBP - MAUI - iOS -Contact info drawer not showing in Greenlight when selecting Contact Greenlight Support | 26327 MSBP - MAUI - iOS -Contact info drawer not showing in Greenlight when selecting Contact Greenlight Support | Amrit | Defect |  | Minor | Manual | External | Inprogress | Development | Relevantz Dev | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 26324 MSBP - MAUI - Homescreen not loading the data when assigning/un-assigning GL and relogging in again. | 26324 MSBP - MAUI - Homescreen not loading the data when assigning/un-assigning GL and relogging in again. | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz Dev | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 26132 MSBP - MAUI - Checkout districts not in the same order as the cart districts | 26132 MSBP - MAUI - Checkout districts not in the same order as the cart districts | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 23901 MSBA - Sales Tag - Close Out - Not showing on reports when Shift Mode is not used | 23901 MSBA - Sales Tag - Close Out - Not showing on reports when Shift Mode is not used | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Others | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 26264 MSBA MAUI - Iphone - Cancel button alignment is not proper in Close Out - Step 1 Screen | 26264 MSBA MAUI - Iphone - Cancel button alignment is not proper in Close Out - Step 1 Screen | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 26323 MSBP MAUI - I/A - Info Message shows in cut off mode, when there are no students in Add Meal Money Page | 26323 MSBP MAUI - I/A - Info Message shows in cut off mode, when there are no students in Add Meal Money Page | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 26335 MSBA - MAUI - District name overlapping when it is greater than 43 characters | 26335 MSBA - MAUI - District name overlapping when it is greater than 43 characters | Amrit | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 26147 MSBP - MAUI - Stock options in Donation is not showing when it is added. Going back and front it is showing | 26147 MSBP - MAUI - Stock options in Donation is not showing when it is added. Going back and front it is showing | Amrit | Defect |  | Minor | Manual | External | Inprogress | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 26.1 M Sprint 1 Stretch | 25751 MSBP - When selecting a list box there is a delay which does not always select option (regression) | 25751 MSBP - When selecting a list box there is a delay which does not always select option (regression) | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects

## 15.3 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Vaishnavi/Chandler/Prem | 50414 | MSBP – Meal Money – Navigation from Home Picture Box to Meal Money Screen and Add Photo Functionality | Story Completed | 3 |  | 11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
2 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Rupesh/Prem | 26082 | MSBA-MAUI- A - Button Text is not shown as Reconciled, once the reconciled done. Displays only on clicking back and forth. | Defect Fixed | 0.5 |  | 24.5 | 2025-10-21 | 2025-10-24 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45229 | 2025-10-22 | 2015-10-24 | Jagdeep | NA | Avery | 2025-10-24 | Use data triggers, instaed implementing in view model. | Completed | NA |  | Exceeds Expectation |  | Main Sprint
3 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Rupesh/Prem | 26128 | MSBA - MAUI - iOS - rotating from portrait to landscape back to portrait removes information at bottom | Defect Fixed | 0.5 |  | 20 | 2025-10-22 | 2025-10-27 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45310 | 2025-10-27 | 2025-10-27 | Ashwin | NA | Avery | 2025-10-30 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
4 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Gursewak/Prem | 26057 | MSBP - MAUI - iOS - AutoPay information sheet not sized to text | Defect Fixed | 0.5 |  | 10 | 2025-10-27 | 2025-10-28 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45337?_a=files | 2025-10-28 | 2025-10-28 | Ashwin | NA | Avery | 2025-10-31 | NA | Completed | Yes |  | Exceeds Expectation |  | Main Sprint
5 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Rupesh/Vaishnavi | 26056 | MSBP- MAUI - iOS - Autopay subscription terms sheet not sized to text | Defect Fixed | 0.5 |  | 12 | 2025-10-27 | 2025-10-31 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45343 | 2025-10-31 | 2025-10-31 | Ashwin | NA | Avery | 2025-10-31 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
6 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Jagdeep/Prem | 26213 | MSBP - White Header - Android - Cannot See Icons or Top Bar | Defect Fixed | 1 |  | 8 | 2025-10-28 | 2025-10-31 | NA | NA | NA | Gursewak | NA | Pull Request 45403: jagdeep.singh/26213-MSBP-White Header Android Cannot See Icons or Top Bar (15.3) | 2025-10-31 | NA | Ashwin | NA | Avery | NA | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
7 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Jagdeep/Vaishnavi | 26107 | MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered (15.3) | Defect Fixed | 0.5 |  | 4 | 2025-10-31 | 2025-10-28 | NA | NA | NA | Gursewak | NA | Pull Request 45332: jagdeep.singh/MSBP-MAUI-Meal Money Settings in Add student workflow heading n... | 2025-10-28 | 2025-10-28 | Ashwin | NA | Avery | 2025-10-30 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
8 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Amrit | 26173 | MSBP - MAUI - Student name is not getting displayed in the Autopay Subscription in Scheduled Payments | Defect Rejected | 1 |  | 6 | 31/10/2025 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA |  |  |  | Main Sprint
9 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Jagdeep | 50648 | MSBP - Automation - Account Create | Story Completed | 5 |  | 16 | 2025-11-03 | 2025-11-04 | NA | NA | NA | Rupesh | NA | jagdeep.singh/50648-MSBP-Automation-Account-Create | 2025-11-03 | 2025-11-12 | Ashwin | NA | Owen | 2025-11-12 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
10 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Gursewak/Jagdeep | 50461 | MSBA - Automation - Login, Logout & Navigation Across Pages | Story Completed | 3 |  | 46 | 2025-10-31 | 2025-11-10 | NA | NA | NA | Rupesh | NA | Pull Request 45471: 50461 MSBA - Automation - Login, Logout & Navigation Across Pages | 2025-11-05 | 2025-11-12 | Ashwin | NA | Owen | 2025-11-12 | NA | Completed | NA |  | Exceeds Expectation | The task involved implementing login automation for MSBA, including login, logout, navigation, and settings automation on Android. While Android automation was completed and validated using BrowserStack, additional time was required to set up the automation framework from scratch, as this was the first MSBA automation story. Work was also carried out on iOS with the team to fix issues identified during testing and implementation. Extra effort was needed to resolve a device-related Bluetooth blockage issue along with AC requirements in the same story, which contributed to the delay but helped establish a stable automation foundation for future tasks. | Main Sprint
11 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Sambath/Amrit | 50642 | 50642 MSBP - Get Existing Automation to Run in IOS | Story Completed | 3 |  | 71 | 2025-11-03 | 2025-11-12 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/45165 | 2025-10-17 | 2025-11-12 | Ashwin | NA | Owen | 2025-11-12 | NA | NA | NA | Development and review completed. Merged to the main. status needs to be changed in Axosoft by Owen. For the failure test cases,new story will be created. | Exceeds Expectation | The following points were discussed and aligned with Owen: Story points were not required to be considered for this task. Multiple changes were directly made by Owen after the story was marked as DONE, which required additional refactoring by the development team. Multiple test accounts were created to cover all scenarios and properly handle concurrency-related test cases. | Main Sprint
12 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Prem/Kenneth | 26224 | MSBP - In checkout screen, the total amount field is displaying as '$0' (15.3) | Defect Fixed | 1 |  | 2.25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
13 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Avery/Prem | 26250 | MSBP - MAUI - Android - student sheet filter does not scroll the sheet (regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
14 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Vaishnavi//Prem | 50641 | MSBP Maui - Full Regression 15.3 | Story Completed | 8 |  | 106.25 | 2025-11-04 | 2025-11-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | The Actual worklogs is beyond the estimation, as all the developers who worked on the regression defects were also filing the worklogs in this regression story. This was the process told by the client and it is followed as a scrum process. | Exceeds Expectation | The Actual worklogs is beyond the estimation, as all the developers who worked on the regression defects were also filing the worklogs in this regression story. This was the process told by the client and it is followed as a scrum process. | Main Sprint
15 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Gursewak/Prem | 26277 | MSBP - MAUI - radio buttons and * symbol are not aligned properly in the webform(regression) | Defect Fixed | 0 |  | 0 | 2025-11-07 | 2025-11-07 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45566 | 2025-07-11 | 2025-11-07 | Ashwin | NA | Avery | 2025-11-07 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
16 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Amrit/Prem | 26281 | MSBP - MAUI - Drawer is not closing when selecting 'Dismiss' button in Student Info screen (regression) | Defect Fixed | 0 |  | 0 | 2025-11-07 | 2025-11-07 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45577 | 2025-07-11 | 2025-10-11 | Gursewak | NA | Sean | 2025-10-11 | NA | Na | NA | NA | Exceeds Expectation |  | Main Sprint
17 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Gursewak/Vaishnavi | 26282 | MSBP - MAUI - FamilyPass - Program fee is not showing in checkout screen and payment method drawer when cancelling the FP registration(regression) | Defect Fixed | 0 |  | 0 | 2025-11-10 | 2025-11-10 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45606 | 2025-11-10 | 2025-11-10 | Ashwin | NA | Avery | 2025-11-11 | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main Sprint
18 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Rupesh/Prem | 26284 | MSBP - MAUI - Selecting and adding more than 3 suggested students,success screen is not scrollable and bottom data is cut off (regression) | Defect Fixed | 0 |  | 0 | 2025-11-10 | 2025-11-11 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45598 | 2025-11-10 | 2025-11-10 | Ashwin | NA | Avery | 2025-11-11 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
19 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Sambath/Prem | 26288 | 26288 MSBP - MAUI - FP Registration - On selecting newly added payment method(cc), Not redirecting to checkout screen(regression) | Defect Fixed | 0 |  | 0 | 2025-11-10 | 2025-11-11 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45651 | 2025-11-11 | 2025-11-12 | Ashwin | NA | Avery | 2025-11-12 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
20 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Sambath/Vaishnavi | 26291 | MSBP - MAUI - Unable to register to FP after making 1st meal payment transaction (regression) | Defect Fixed | 0 |  | 0 | 2025-11-11 | 2025-11-11 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45651 | 2025-11-11 | 2025-11-12 | Ashwin | NA | Avery | 2025-11-12 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
21 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Gursewak/Vaishnavi | 26295 | MSBP - MAUI - Unselecting CC payment method from checkout screen, still shows the 'save on fees' for FP (regression) | Defect Fixed | 0 |  | 0 | 2025-11-11 | 2025-11-11 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45633 | 2025-11-11 | 2025-11-11 | Ashwin | NA | Avery | 2025-11-11 | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main Sprint
22 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Rupesh/Prem | 26289 | MSBP - MAUI - FP - Pay Now to Renew button is in disable mode even newly added cc is selected(regression) | Defect Fixed | 0 |  | 0 | 2025-11-10 | 2025-11-11 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45632 | 2025-11-11 | 2025-11-11 | Ashwin | NA | Avery | 2025-11-11 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
23 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Sambath/Vaishnavi | 26290 | 26290 MSBP - MAUI - FP renewal - Security code drawer having extra space and selecting ? icon information drawer is not opening(regression) | Defect Fixed | 0 |  | 0 | 2025-11-10 | 2025-11-11 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45651 | 2025-11-11 | 2025-11-12 | Ashwin | NA | Avery | 2025-11-12 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
24 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Vaishnavi | 26244 | MSBP - MAUI - iOS - Upon Clicking Donation from Student info quicklinks is not navigating to store products (regression) | Defect Fixed | 0 |  | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main Sprint
25 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Amrit | 49417 | MSBA - Stores Filtering - New Alphabetical Filtering | Story Need More Info | 5 |  | NA | 2025-11-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Client Assigned back to JASON, Need more infor for this story. |  | NA | Stretch
26 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Jagdeep | 50462 | MSBA - Automation - Meals Page | Story Being Developed | 5 |  | 12 | 2025-11-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Development done for Android and tested in local. Will work on the iOS development. |  |  | Stretch
27 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Chandler/Prem | 26296 | MSBP - MAUI - Family Pass Banner is not displaying in Maximized Mode(regression) | Defect Fixed | 0 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
28 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Rupesh | 50460 | MSBA - Automation - User Settings – Edit and Verify | Story Peer Review | 2 |  | 37 | 2025-10-31 |  | NA | NA |  |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/45673 | [9 empty] | Ashwin's review pending. | Exceeds Expectation |  | Stretch
29 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Avery/Prem | 26226 | MSBA - MAUI - unable to scroll check details when more than 4 present and check all not working | Defect Fixed | 0 |  | 2.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Estimated SP not updated. Will be checking with client today. | Exceeds Expectation |  | Stretch
30 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Amrit/Prem | 50649 | MSBA - Invoice Search - Update Status Message when Searching | Story Completed | 0.5 |  | 6 | 2025-07-11 | 2025-07-11 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45564 | 2025-07-11 | 2025-10-11 | Ashwin | NA | Avery | 2025-10-11 | NA | NA | NA | Testing Case Updation and Testing completed | Exceeds Expectation |  | Stretch
31 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Vaishnavi | 24923 | MSBP - MAUI - If long name wraps to a second line, cuts off student id in Add Student (15.4) | Defect Fixed | 1 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Stretch
32 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 | Chandler/Prem | 26223 | MSBP - MAUI - In Android phone, the district field is not showing the district name when adding student manually (15.4) | Defect Fixed | 1 |  | 3.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
33 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Gursewak | 26062 | MSBP - Store - Dual Enrollment - Not Displaying Expected Stores | Defect Being Fixed | 1 |  |  | 2025-11-12 | [16 empty] | Will be doing the analysis
34 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Gursewak | 26055 | MSBP - MAUI - iOS - bottom sheet issue, installment plan info sheet has button below edge | Defect Rejected | 1 |  | 1 | 2025-11-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 26055 is rejected by Jason since its working as expected.
35 | MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Gursewak | 25894 | MSBP - Add Student - State List is Blank | Defect Rejected | 2 |  | 1 | 2025-11-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rejected by Jason.
36 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Rupesh | 26298 | MSBP - Cannot Checkout with 0.00 with required Webforms (CAN) | Defect Rejected | 2 |  | 2 | 2025-11-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rejected by Jason.
37 | MSB Mobile | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Rupesh | 23091 | MSBP - Announcements/Notifications - Showing as Received on Mon Jan 1 | Defect Being Fixed | 2 |  |  | 2025-11-13 |  | NA | NA | NA | NA | NA | [10 empty] | Development in progress.
| MSB Mobile Kaleida | 2025-10-31 | 2025-11-13 | 15.3 M Sprint 3 Stretch | Amrit | 25032 | MSBA - tax on MSBA does not match web report | Defect Rejected | 3 |  |  | 2025-11-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Verified the issue in iOS xamarin version 14.7.1.147368. Made a meal transaction and verified the reports in Web. In web the tax is showing as '$0' and in MSBA also tax is showing as '$0. Unable to reproduce this issue. Attached screenshot for reference.

## 15.3 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.3 M Sprint 3 | 26082 MSBA-MAUI- A - Button Text is not shown as Reconciled, once the reconciled done. Displays only on clicking back and forth. | 26082 MSBA-MAUI- A - Button Text is not shown as Reconciled, once the reconciled done. Displays only on clicking back and forth. | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26128 MSBA - MAUI - iOS - rotating from portrait to landscape back to portrait removes information at bottom | 26128 MSBA - MAUI - iOS - rotating from portrait to landscape back to portrait removes information at bottom | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26057 MSBP - MAUI - iOS - AutoPay information sheet not sized to text | 26057 MSBP - MAUI - iOS - AutoPay information sheet not sized to text | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26056 MSBP- MAUI - iOS - Autopay subscription terms sheet not sized to text | 26056 MSBP- MAUI - iOS - Autopay subscription terms sheet not sized to text | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26213 MSBP - White Header - Android - Cannot See Icons or Top Bar | 26213 MSBP - White Header - Android - Cannot See Icons or Top Bar | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26107 MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered (15.3) | 26107 MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered (15.3) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26173 MSBP - MAUI - Student name is not getting displayed in the Autopay Subscription in Scheduled Payments | 26173 MSBP - MAUI - Student name is not getting displayed in the Autopay Subscription in Scheduled Payments | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26224 MSBP - In checkout screen, the total amount field is displaying as '$0' (15.3) | 26224 MSBP - In checkout screen, the total amount field is displaying as '$0' (15.3) | Kenneth | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26250 MSBP - MAUI - Android - student sheet filter does not scroll the sheet (regression) | 26250 MSBP - MAUI - Android - student sheet filter does not scroll the sheet (regression) | Avery | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26277 MSBP - MAUI - radio buttons and * symbol are not aligned properly in the webform(regression) | 26277 MSBP - MAUI - radio buttons and * symbol are not aligned properly in the webform(regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26281 MSBP - MAUI - Drawer is not closing when selecting 'Dismiss' button in Student Info screen (regression) | 26281 MSBP - MAUI - Drawer is not closing when selecting 'Dismiss' button in Student Info screen (regression) | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26282 MSBP - MAUI - FamilyPass - Program fee is not showing in checkout screen and payment method drawer when cancelling the FP registration(regression) | 26282 MSBP - MAUI - FamilyPass - Program fee is not showing in checkout screen and payment method drawer when cancelling the FP registration(regression) | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26284 MSBP - MAUI - Selecting and adding more than 3 suggested students,success screen is not scrollable and bottom data is cut off (regression) | 26284 MSBP - MAUI - Selecting and adding more than 3 suggested students,success screen is not scrollable and bottom data is cut off (regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 Stretch | 26226 MSBA - MAUI - unable to scroll check details when more than 4 present and check all not working | 26226 MSBA - MAUI - unable to scroll check details when more than 4 present and check all not working | Avery | Defect |  | Minor | Manual | External | Inprogress | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26288 "26288 | 26288 "26288 | Sambath | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26277 MSBP - MAUI - In Android phone, the district field is not showing the district name when adding student manually (15.4) | 26277 MSBP - MAUI - In Android phone, the district field is not showing the district name when adding student manually (15.4) | Sambath | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26291 MSBP - MAUI - Unable to register to FP after making 1st meal payment transaction (regression) | 26291 MSBP - MAUI - Unable to register to FP after making 1st meal payment transaction (regression) | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26281 MSBP - MAUI - Drawer is not closing when selecting 'Dismiss' button in Student Info screen (regression) | 26281 MSBP - MAUI - Drawer is not closing when selecting 'Dismiss' button in Student Info screen (regression) | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 | 26295 MSBP - MAUI - Unselecting CC payment method from checkout screen, still shows the 'save on fees' for FP (regression) | 26295 MSBP - MAUI - Unselecting CC payment method from checkout screen, still shows the 'save on fees' for FP (regression) | Sambath | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 3 Stretch | 26289 MSBP - MAUI - FP - Pay Now to Renew button is in disable mode even newly added cc is selected(regression) | 26289 MSBP - MAUI - FP - Pay Now to Renew button is in disable mode even newly added cc is selected(regression) | Chandler | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects

## 15.3 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Sambath/Prem/Vaishnavi | 26073 | MSBA - MAUI - unable to drag to sort | Defect Fixed | 2 |  | 55 | 2025-10-06 | 2025-10-08 | NA | Na | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45020?_a=files | 2025-10-08 | 2025-10-08 | Ashwin | NA | Sean | NA | NA | Completed | NA | NA | Exceeds Expectation | NA | Main Sprint
2 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Rupesh | 48146 | MSBA - MAUI - Gate Mode Settings In Prod | Story Completed | 2 |  | 15 | 2025-10-07 | 2025-10-17 | NA | NA | Na | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45050 | 2025-10-09 | 2025-10-10 | Ashwin | Renaming few fields | Sean | 2025-10-14 | Keep the Firebase props at right place. | Completed | NA |  | Exceeds Expectation | Initially I kept the firebase props in RemoteConfigurationService, however It should have been the part of RemoteConfig. | Main Sprint
3 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Sambath/Prem | 26097 | MSBA - MAUI - App crash while editing amount in Starting cash text box in closeout | Defect Fixed | 1 |  | 17 | 2025-10-14 | 2025-10-14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | this defect is exiting issue with older version, app is crasing with Android version 12 alone, so client decided to ignore this defect | Exceeds Expectation |  | Main Sprint
4 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Rupesh/Prem | 26092 | MSBA - MAUI - App crash after opening/closing Webform product | Defect Fixed | 0.5 |  | 18 | 2025-10-15 | 2025-10-17 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45152 | 2025-10-16 | 2025-10-17 | Ashwin | NA | Sean | 2025-10-17 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
5 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Amrit/Jagdeep/Gursewak/Sambath | 50285 | MSBP - Get Existing Automation to Run in IOS | Story Completed | 3 |  |  | 2025-10-06 | 2025-10-17 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/45165 | 2025-10-16 | NA | Jagdeep | NA | Ashwin | NA | Regarding Code usage of Thread.Sleep & Some conditions. Which are explained in comments and resolved | NA | NA | Completed around 26 testcases out of 33. Will be working on the remaining failed test cases. |  | 2 Test cases are blocked which are discussed, rest of 33 are done. | Main Sprint
6 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Vaishnavi | 26126 | MSBA - MAUI - Unable to do any action once entering in the Other Amount Field for the Meal Payment and later on app is getting crashed | Defect Fixed | 0.5 |  | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
7 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Jagdeep/Prem | 26138 | MSBA - MAUI - App crash when deleting amount from partial payment amount field in Invoice | Defect Fixed | 2 |  | 10.5 | 2025-10-17 | 2025-10-17 | NA | NA | NA | Sambath | NA | Pull Request 45186: jagdeep.singh/26138-MSBA-MAUI-App crash when deleting amount from partial pay... | 2025-10-17 | 2025-10-17 | Ashwin | NA | Avery | 2025-10-17 | NA | Completed(Ashwin) | NA |  | Exceeds Expectation |  | Main Sprint
8 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Gursewak/Prem | 24829 | MSBP - MAUI - long entry information on webform does not wrap to a second line | Defect Fixed | 3 |  | 23 | 2025-10-17 | 2025-10-23 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45235?_a=files | 2025-10-23 | 2025-10-23 | Ashwin | NA | Avery | 2025-10-24 | NA | Done | NA |  | Exceeds Expectation |  | Main Sprint
9 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Prem/Avery | 26061 | MSBA - MAUI - filters resetting on refresh page | Defect Fixed | 0.5 |  | 5 | 2025-10-14 | 2025-10-15 | NA | Na | NA | Jagdeep | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
10 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Prem/Avery | 26085 | MSBA-MAUI-A- Clicking on the dropdown icon in 'Select a shift text box' is not opening the shifts | Defect Fixed | 2 |  | 7 | 2025-10-15 | 2025-10-16 | NA | Na | NA | Jagdeep | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
11 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Vaishnavi/Chandler/Prem | 50414 | MSBP – Meal Money – Navigation from Home Picture Box to Meal Money Screen and Add Photo Functionality | Story Being Developed | 2 | [19 empty] | Bounceback created and moved back to development. Onsite developer is working on the issue |  |  | Main Sprint
12 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Amrit | 26087 | MSBA-MAUI- A - Select i icon from shift details from closeout, Dismiss is not showing in Blue displays as Black. | Defect Rejected | 0.5 |  | NA | 21/10/2025 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Discussed in standup today and rejecting based on the decision made as the link button colors on Alerts are not controllable from the code. |  |  | Main Sprint
13 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Jagdeep | 26090 | MSBA - MAUI - Close day step 2 not populate information for non-shift users | Defect Rejected | 2 | N | 4 | 21/10/2025 | 21/10/2025 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | There was a fix for a defect from the same original build which this was discovered in that was not populating information in step 3 (26083) that may have possibly fixed this issue with it. Defect can be rejected for now, we will reopen if we run into this issue again in the future |  |  | Main Sprint
14 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Rupesh/Vaishnavi | *5 | MSBA-MAUI- A - Button Text is not shown as Reconciled, once the reconciled done. Displays only on clicking back and forth. | Defect Ready For Testing | 1 |  | 13 | 2025-10-21 | 2025-10-24 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45229 | 2025-10-22 | 2015-10-24 | Jagdeep | NA | Avery | 2025-10-24 | Use data triggers, instaed implementing in view model. | Completed | NA | Issue fixed and updated the PR. Got comment from Avery to follow a different approach. As per Ashwin that cannot be followed. Awaiting reply from Avery | Exceeds Expectation |  | Main Sprint
15 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Amrit/Prem | 26086 | MSBA - MAUI -iOS- In iphone 'i' icon is not showing in the shift details in closeout | Defect Fixed | 0.5 |  | 6.5 | 21/10/2025 | 21/10/2025 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45212 | 21/10/2025 | 22/10/2025 | Ashwin | NA | NA | 22/10/2025 | NA | NA |  |  | Exceeds Expectation |  | Main Sprint
16 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 | Jagdeep/Prem | 26091 | MSBA - MAUI - Close Day step 4 offset/short box missing () when negative | Defect Fixed | 1 |  | 8.5 | 2025-10-21 | 2025-10-22 | NA | NA | NA | Rupesh | NA | Pull Request 45225: jagdeep.singh/26091-MSBA-MAUI-Close Day step 4 offset short box missing () wh... | 2025-10-22 | 2025-10-22 | Ashwin | NA | Avery | 2025-10-24 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
17 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Amrit | 26168 | Mobile - MSBP - AddFundsMainViewModel Null Pointer | Defect Fixed | 1 |  | 1 | 22/10/2025 | 23/10/2025 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45227 | NA | NA | Ashwin | NA | NA | 24/10/2025 | NA | Completed | NA | Tested by Onsite QA | Exceeds Expectation |  | Stretch
18 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Jagdeep | 23799 | MSBP - Cart Clears After Updating Expired Payment Method | Defect Needs More Info | 3 |  | 1 | 2025-10-22 | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Issue not reproducible. Ashwin will be doing the further investigation. |  |  | Stretch
19 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Amrit/Prem | 25179 | MSBA - MAUI -Store screen - filters not showing all headers | Defect Fixed | 2 |  | 13 | 22/10/2025 | 23/10/2025 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45256 | 23/10/2025 | NA | Ashwin | NA | NA | 27/10/2025 | NA | NA | NA |  | Exceeds Expectation |  | Stretch
20 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Jagdeep/Prem | 26146 | MSBA - MAUI - After entering and deleting the custom amount, predefined values are not getting enabled in Cash Payment | Defect Fixed | 2 |  | 9 | 2025-10-22 | 23/10/2025 | NA | NA | NA | Gurusewak | NA | Pull Request 45257: jagdeep.singh/26146-MSBA-MAUI-After entering and deleting the custom amount,... | 2025-10-23 | NA | Ashwin | NA | Avery | 2025-10-25 | NA | Completed | NA |  | Exceeds Expectation |  | Stretch
21 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Rupesh | 26128 | MSBA - MAUI - iOS - rotating from portrait to landscape back to portrait removes information at bottom | Defect Ready For Testing | 2 |  | 18 | 2025-10-22 | 2025-10-27 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45310 | 2025-10-27 | 2025-10-27 | Ashwin | NA |  |  | NA | Completed | NA | Client review pending from past 2 days | Exceeds Expectation |  | Stretch
22 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Gursewak/Vaishnavi | 49298 | MSBA - Display No Invoices on Students without Invoices - Post GA | Story Completed | 1 |  | 4 | 2025-10-27 | 2025-10-27 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45309?_a=files | 2025-10-27 | 2025-10-27 | Ashwin | NA | Avery | 2025-10-27 | NA | Completed | NA |  | Exceeds Expectation
23 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Gursewak | 26057 | MSBP - MAUI - iOS - AutoPay information sheet not sized to text | Defect Peer Review | 0 |  |  | 2025-10-27 | 2025-10-28 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45337?_a=files | 2025-10-28 | 2025-10-28 | Ashwin | NA |  |  |  |  | Yes | Fixed Avery commented on PR, pending review from client side.
24 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Jagdeep | 26107 | MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered | Defect Peer Review | 0.5 |  | 4 | 2025-10-28 | 2025-10-28 | NA | NA | NA | Gursewak | NA | Pull Request 45332: jagdeep.singh/MSBP-MAUI-Meal Money Settings in Add student workflow heading n... | 2025-10-28 | NA | Ashwin | NA | NA | NA |  | Completed | NA | Client review pending from past 2 days |  |  | Stretch
25 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Rupesh | 26056 | MSBP- MAUI - iOS - Autopay subscription terms sheet not sized to text | Defect Being Fixed | 0.5 |  |  | 2025-10-27 | [16 empty] | As per Ashwin's comments, will be doing some modification after completing the priority defect from the Main sprint
26 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Jagdeep | 26213 | MSBP - White Header - Android - Cannot See Icons or Top Bar | Defect Being Fixed | 2 |  | 2 | 2025-10-28 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | Assigning this defect to Amrit as I am working on the Automation story from main sprint which is the high priority. |  |  | Stretch
27 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Avery/Prem | 25645 | MSBA - MAUI - Android - In close day while opening the keyboard, see splash screen [Timebox] | Defect Fixed | 0.5 |  | 3.5 | 2025-10-28 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Stretch
28 | MSB Mobile Kaleida | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Prem | 26075 | MSBA - Students returning in the invoices tab when not have active invoices | Defect Fixed | 2 |  | 8.5 | 2025-10-28 | [16 empty] | Testing in progress | Exceeds Expectation |  | Stretch
29 | MSB Mobile | 2025-10-17 | 2025-10-30 | 15.3 M Sprint 2 Stretch | Vaishnavi | 49292 | MSBA - Maui - Remove Required * from Close Out Starting Cash | Story Completed | 0.5
30 | MSB Mobile |  |  | 15.3 M Sprint 2 Stretch | Amrit | 26107 | MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered (15.3) | Defect Being Fixed | 0.5 |  |  | 31/10/2025 | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 15.3 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.3 M Sprint 2 | 26073 MSBA - MAUI - unable to drag to sort | 26073 MSBA - MAUI - unable to drag to sort | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26097 MSBA - MAUI - App crash while editing amount in Starting cash text box in closeout | 26097 MSBA - MAUI - App crash while editing amount in Starting cash text box in closeout | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26092 MSBA - MAUI - App crash after opening/closing Webform product | 26092 MSBA - MAUI - App crash after opening/closing Webform product | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26126 MSBA - MAUI - Unable to do any action once entering in the Other Amount Field for the Meal Payment and later on app is getting crashed | 26126 MSBA - MAUI - Unable to do any action once entering in the Other Amount Field for the Meal Payment and later on app is getting crashed | Vaishnavi | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26138 MSBA - MAUI - App crash when deleting amount from partial payment amount field in Invoice | 26138 MSBA - MAUI - App crash when deleting amount from partial payment amount field in Invoice | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 24829 MSBP - MAUI - long entry information on webform does not wrap to a second line | 24829 MSBP - MAUI - long entry information on webform does not wrap to a second line | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26061 MSBA - MAUI - filters resetting on refresh page | 26061 MSBA - MAUI - filters resetting on refresh page | Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26085 MSBA-MAUI-A- Clicking on the dropdown icon in 'Select a shift text box' is not opening the shifts | 26085 MSBA-MAUI-A- Clicking on the dropdown icon in 'Select a shift text box' is not opening the shifts | Prem | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26087 MSBA-MAUI- A - Select i icon from shift details from closeout, Dismiss is not showing in Blue displays as Black. | 26087 MSBA-MAUI- A - Select i icon from shift details from closeout, Dismiss is not showing in Blue displays as Black. | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26090 MSBA - MAUI - Close day step 2 not populate information for non-shift users | 26090 MSBA - MAUI - Close day step 2 not populate information for non-shift users | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26082 MSBA-MAUI- A - Button Text is not shown as Reconciled, once the reconciled done. Displays only on clicking back and forth. | 26082 MSBA-MAUI- A - Button Text is not shown as Reconciled, once the reconciled done. Displays only on clicking back and forth. | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26086 MSBA - MAUI -iOS- In iphone 'i' icon is not showing in the shift details in closeout | 26086 MSBA - MAUI -iOS- In iphone 'i' icon is not showing in the shift details in closeout | Amrit | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 | 26091 MSBA - MAUI - Close Day step 4 offset/short box missing () when negative | 26091 MSBA - MAUI - Close Day step 4 offset/short box missing () when negative | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 26138 Mobile - MSBP - AddFundsMainViewModel Null Pointer | 26138 Mobile - MSBP - AddFundsMainViewModel Null Pointer | Amrit | Defect |  | Minor | Manual | External | Inprogress | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 23799 MSBP - Cart Clears After Updating Expired Payment Method | 23799 MSBP - Cart Clears After Updating Expired Payment Method | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 25179 MSBA - MAUI -Store screen - filters not showing all headers | 25179 MSBA - MAUI -Store screen - filters not showing all headers | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 26146 MSBA - MAUI - After entering and deleting the custom amount, predefined values are not getting enabled in Cash Payment | 26146 MSBA - MAUI - After entering and deleting the custom amount, predefined values are not getting enabled in Cash Payment | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 26128 MSBA - MAUI - iOS - rotating from portrait to landscape back to portrait removes information at bottom | 26128 MSBA - MAUI - iOS - rotating from portrait to landscape back to portrait removes information at bottom | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 26057 MSBP - MAUI - iOS - AutoPay information sheet not sized to text | 26057 MSBP - MAUI - iOS - AutoPay information sheet not sized to text | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 26107 MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered | 26107 MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 26056 MSBP- MAUI - iOS - Autopay subscription terms sheet not sized to text | 26056 MSBP- MAUI - iOS - Autopay subscription terms sheet not sized to text | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 26213 MSBP - White Header - Android - Cannot See Icons or Top Bar | 26213 MSBP - White Header - Android - Cannot See Icons or Top Bar | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 25645 MSBA - MAUI - Android - In close day while opening the keyboard, see splash screen [Timebox] | 25645 MSBA - MAUI - Android - In close day while opening the keyboard, see splash screen [Timebox] | Avery | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 2 Stretch | 26075 MSBA - Students returning in the invoices tab when not have active invoices | 26075 MSBA - Students returning in the invoices tab when not have active invoices | Prem | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects

## 15.3 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Amrit/Prem/Vaishnavi | 46089 | MSBA - Maui - Checkout - Cash - Predefined dollar fields do not make sense against the total and cannot be used | Story Completed | 1 |  | 12 | 2025-09-29 | NA | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44951?_a=files | 2025-03-10 | 2025-11-10 | Jagdeep | Changes in Code | Sean | 2025-11-10 | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
2 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Sambath | 50129 | 50129 MSBA - Automation - Implement MSBA automation similar to MSBP [Timebox] | Story Completed | 2 |  | 7 | 2025-09-24 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/45034 | 2025-10-08 | 2025-10-14 | Ashwin | NA | Owen | 2025-10-14 | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
3 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Jagdeep | 50045 | MSBP - After Adding Student - Show Loading Symbol Until Student is Added to Homescreen | Story Completed | 0.5 |  | 8 | 2025-09-30 | 2025-10-03 | NA | NA | NA | Rupesh | NA | Pull Request 44884: jagdeep.singh/50045-MSBP-After Adding Student show loading Symbol Until Stude... | 2025-09-30 | NA | Ashwin | NA | Sean | 2025-10-07 | Why is the state being set to Loading here? | Completed | NA |  | Exceeds Expectation |  | Main Sprint
4 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Jagdeep/Vaishnavi | 26042 | MSBP-MAUI - Negative amount showing with minus sign not in brackets( ) in Payment history(regression) | Defect Fixed | 0.5 |  | 3 | 2025-09-29 | 2025-09-29 | NA | NA | NA | Gursewak | NA | Pull Request 44845: jagdeep.singh/26042-MSBP-MAUI-Negative amount showing with minus sign not in... | 2025-09-29 | NA | Ashwin | NA | Sean | 2025-10-02 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
5 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Rupesh/Vaishnavi | 49816 | MSBA - MAUI - Update Login Screen Username Fields | Story Completed | 0.5 |  | 4 | 2025-09-30 | 2025-10-02 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44882 | 2025-09-30 | 2025-10-01 | Ashwin | NA | Sean | 2025-10-02 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
6 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Jagdeep | 24706 | MSBP - Maui - Cart reorder when donation is added on multidistrict (pre-existing) | Defect Fixed | 2 |  | 6 | 2025-10-03 | 2025-10-03 | NA | NA | NA | Amrit | NA | Pull Request 44949: jagdeep.singh/24706-MSBP-Maui-Cart reorder when donation is added on multidis... | 2025-03-10 | 2025-10-07 | Ashwin | NA | Sean | 2025-10-07 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
7 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Gursewak | 25569 | MSBP - Messages - Icon Opening In Stack | Defect Fixed | 2 |  | 6 | 2025-10-03 | 2025-10-03 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44948?path=/MSB.Parent/ViewModels/BaseViewModel.cs&discussionId=291404&_a=files | 2025-10-03 | 2025-10-07 | Ashwin | NA | Sean | 2025-10-07 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
8 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Jagdeep/Vaishnavi | 50227 | MSBP - Donation Products - Show Only District Donation Products | Story Completed | 3 | N | 14 | 2025-10-06 | 2025-10-07 | NA | NA | NA | Gursewak | No need to required else condition,Add null check if BasketItems is null. | Pull Request 45008: jagdeep.singh/50227-MSBP-Donation Products-Show Only District Donation Products | 2025-10-08 | 2025-10-09 | Ashwin | NA | Sean | 2025-10-09 | NA | Completed | NA |  |  |  | Main Sprint
9 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Rupesh | 26075 | MSBA - Students returning in the invoices tab when not have active invoices | Defect Needs More Info | 2 |  | 6 | 2025-10-06 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Its on hold for now, Investigating it for resolution.
10 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Vaihnavi/Prem | 45828 | MSBA - Maui - Close Out Workflow (Logic - Test Only) | Story Completed | 2 |  | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
11 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Vaihnavi/Prem | 48381 | MSBA - Maui - Settings Areas that have not been tested yet | Story Completed | 3 |  | 28 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Main Sprint
12 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Gursewak | 26073 | MSBA - MAUI - unable to drag to sort | Defect Peer Review | 2 |  | 18 | 2025-10-06 | 2025-10-08 | NA | Na | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45020?_a=files | 2025-10-08 | [8 empty] | Development completed. PR created. Internal comments also resolved. will be doing the POV
13 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 | Rupesh | 48146 | MSBA - MAUI - Gate Mode Settings In Prod | Story Peer Review | 2 |  | 15 | 2025-10-07 |  | NA | NA | Na | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45050 | 2025-10-09 | 2025-10-10 | Ashwin | Renaming few fields | Sean | 2025-10-14 | Keep the Firebase props at right place. | Completed | NA | Working on the bounceback. Issue related to Firebase. Sambath will be working with Rupesh to fix it. | Exceeds Expectation |  | Main Sprint
14 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Gursewak | 24714 | MSBP - MAUI- Error message missing when cannot verify account | Defect Rejected | 0 |  | 3 | 2025-10-09 | 2025-10-09 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Na | RJ added commented on the task - "team's discussed - we're able to reject after discussion today." |  |  | Stretch
15 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Gursewak/Ashwin | 26105 | MSBA - MAUI - Enabling 'Allow oversell' toggle in settings and doing checkout for a product throws error | Defect Being Fixed | 2 |  | 6 | 2025-10-10 | 2025-10-10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Na | NA | NA | NA | Assigned to ashwin, For Pi investigation not done yet so moved to 15.3 SP2
16 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Rupesh | 26104 | MSBA - MAUI - App crash on switching between the Close out entire day toggle or select a specific shift | Defect Fixed | 2 |  | 12 | 2025-10-10 | 2025-10-13 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45086 | 2024-10-13 | 2025-10-13 | Ashwin | NA | Avery | 2025-10-14 | NA | Completed | NA |  | Exceeds Expectation |  | Stretch
17 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Sambath | 26117 | 26117 MSBP - PictureStorageService - Null Pointer | Defect Fixed | 0.5 |  | 3 | 2025-10-13 | 2025-10-13 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45089 | 2025-10-13 | 2025-10-13 | Ashwin | NA | Sean | NA | NA | NA | NA |  | Exceeds Expectation |  | Stretch
18 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Sambath | 26097 | MSBA - MAUI - App crash while editing amount in Starting cash text box in closeout | Defect Being Fixed | 2 |  | 5 | 2025-10-14 |  | NA | NA | NA | NA | NA | [10 empty] | Investigation and analysis in progress for the issue. |  | i can able reproduce this defect, even dollar symbol is there, so i am trying to fixing it | Stretch
19 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Rupesh | 26092 | MSBA - MAUI - App crash after opening/closing Webform product | Defect Being Fixed | 2 | [19 empty] | Will be reviewing the PR with sambath
20 | MSB Mobile Kaleida | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Amrit/Jagdeep/Sambath | 50285 | MSBP - Get Existing Automation to Run in IOS | Defect Being Fixed | 5 |  |  | 2025-10-06 | [16 empty] | Development in progress. |  |  | Main Sprint
21 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Vaishnavi/Prem | 26084 | MSBA - MAUI-A -Check to reconcile is cut off, going back and forth it is not showing the cut off text in 'Count' screen | Defect Fixed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Stretch
22 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Vaishnavi/Prem | 26112 | MSBA - MAUI - Enabling product search from settings screen is not showing the product for all the student. | Defect Fixed | 2 |  | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Stretch
23 | MSB Mobile | 2025-10-03 | 2025-10-16 | 15.3 M Sprint 1 Stretch | Vaishnavi/Prem | 26083 | MSBA - MAUI - I/A - Cash & Check total is not sum up the check total. Displays only the Cash Value in the Cash & Check Totals field | Defect Fixed | 1 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation |  | Stretch

## 15.3 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.3 M Sprint 1 | 46089-MSBA - Maui - Checkout - Cash - Predefined dollar fields do not make sense against the total and cannot be used | 46089-MSBA - Maui - Checkout - Cash - Predefined dollar fields do not make sense against the total and cannot be used | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 1 | 26042MSBP-MAUI - Negative amount showing with minus sign not in brackets( ) in Payment history(regression) | 26042MSBP-MAUI - Negative amount showing with minus sign not in brackets( ) in Payment history(regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 1 | 24706MSBP - Maui - Cart reorder when donation is added on multidistrict (pre-existing) | 24706MSBP - Maui - Cart reorder when donation is added on multidistrict (pre-existing) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 1 | 25569 - MSBP - Messages - Icon Opening In Stack | 25569 - MSBP - Messages - Icon Opening In Stack | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 1 | 50227-MSBP - Donation Products - Show Only District Donation Products | 50227-MSBP - Donation Products - Show Only District Donation Products | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.3 M Sprint 1 | 26073-MSBA - MAUI - unable to drag to sort | 26073-MSBA - MAUI - unable to drag to sort | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects

## 15.2 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Amrit/Prem | 25905 | MSBA - MAUI - District tax rate not applied | Defect Fixed | 2 |  | 24 | 2025-09-16 | 2025-09-21 | NA | Jagdeep | NA | Ashwin | Check API before making changes | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44657 | 20/9/2025 | 22/9/2025 | Jagdeep | NA | Sean | 22/9/2025 | NA | NA | NA | Testing completed. | Meets Expectation | Faced issue in finding some tax values in user settings in MAUI. | Backlog
2 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Vaishnavi/Prem | 25936 | MSBA - MAUI - iOS - after a timeout force log out, cannot manually log out | Defect Fixed | 1 | 6 | 15 | 2025-09-17 | 2025-09-17 | NA | NA | NA | Gursewak | NA | jagdeep.singh/25846-MSBA-MAUI-upon-logout-no-message-and-cannot-log-back-in | 2025-09-17 | 2025-09-17 | Ashwin | NA | Sean | 2025-09-17 | NA | Completed | NA |  | Exceeds Expectation |  | Backlog
3 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Vaishnavi/Prem | 25846 | MSBA - MAUI - upon logout, no message and cannot log back in | Defect Fixed | 1 |  | 15.5 | 2025-09-17 | 2025-09-17 | NA | NA | NA | NA | NA | Pull Request 44612: jagdeep.singh/25846-MSBA-MAUI-upon logout, no message and cannot log back in(... | 2025-09-17 | 2025-09-17 | Ashwin | NA | Sean | 2025-09-17 | NA | Completed | NA |  | Exceeds Expectation |  | Backlog
4 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Sambath/Vaishnavi | 25964 | MSBA - MAUI - iOS - cart preview cut off if tablet rotated | Defect Fixed | 2 |  | 18 | 2025-09-16 | 2025-09-23 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44716 | 2025-09-23 | 2025-09-24 | Ashwin | NA | Sean | 2025-09-24 | NA | Completed | NA |  | Meets Expectation | Initially we are unable to repro this issue as repro steps were not clear. After checking with Sambath, we came to know one point was missed to update in AC as well as the Repro. If it would have been mentioned, we should have reproduced this earlier. | Stretch
5 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep/Prem | 25934 | MSBA - MAUI - iOS - double loading icon on the MFA pages | Defect Fixed | 1 |  | 12.5 | 2025-09-18 | 2025-09-19 | NA | NA | NA | Amrit | NA | Pull Request 44653: jagdeep.singh/25934-MSBA-MAUI-iOS-double loading icon on the MFA pages | 2025-09-19 | 2025-09-23 | Ashwin | NA | Sean | 2025-09-24 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
6 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Gursewak/Prem | 25927 | MSBA - MAUI - iOS - hamburger menu not all centered | Defect Fixed | 2 |  | 15.5 | 2025-09-18 | 2025-09-23 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44677?_a=files | 2025-09-23 | 2025-09-23 | Ashwin | NA | Sean | 2025-09-23 | NA | Completed | NA |  | Exceeds Expectation |  | Backlog
7 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Rupesh | 25844 | MSBA - MAUI - able to open/stack transaction history/settings/close out from hamburger menu | Defect Fixed | 2 |  | 20 | 2025-09-18 |  | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44649 | 2025-09-18 | 2025-09-24 | Ashwin | NA | Sean | 09/25/205 | Instead of doing all this just use the the CanExecute function on the AsyncCommand. You won't need to mess with any of the UI | Completed | NA | Client review is pending. (Delayed by 2 days) | Exceeds Expectation |  | Main Sprint
8 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Vaishnavi/Prem | 50147 | MSBP Maui - Full Regression 15.2 | Story Completed | 13 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Completed regression testing except the Greenlight. Ashwin/Letashia will be connecting with Greenlight team. | Exceeds Expectation |  | Main Sprint
9 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep | 50127 | MSB - Automation - Develop a strategy to handle iOS bottom sheet automation | Story Completed | 5 |  | 8 | 2025-09-19 | 2025-09-22 | NA | NA | NA | Gursewak | NA | Pull Request 44678: jagdeep.singh/50127-MSB-Automation-Develop a strategy to handle iOS bottom sh... | 2025-09-22 | 2025-09-23 | Ashwin | NA | Sean | 2025-09-24 | NA | Completed | NA | Story tested by Owen (Onsite QA) and closed. | Exceeds Expectation |  | Main Sprint
10 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Amrit | 50126 | MSB - Automation - Investigate and fix 7 broken automation tests | Story Completed | 5 |  | 30 | 22/9/2025 | 28/9/2025 | NA | NA | NA | Jagdeep | NA | MSBP MAUI , PR 1 . | 2025-09-26 | 30/9/2025 | Ashwin | NA | Owen | 30/9/2025 | NA | NA | NA | Story completed by Owen | Exceeds Expectation |  | Main Sprint
11 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep | 49122 | MSBP - Automation - Mappings for Automation - Checkout/Receipt | Story Completed | 5 |  | 20 | 2025-09-22 | 2025-09-26 | NA | NA | NA | Amrit | NA | Pull Request 44814: jagdeep.singh/49122-MSBP-Automation-Mappings for Automation-Checkout/Receipt | 2025-09-26 | 2025-10-01 | Ashwin | NA | Owen | 2025-10-01 | NA | Completed | NA | Story completed by Owen | Exceeds Expectation |  | Main Sprint
12 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep | 25986 | MSBP - GA - MSB.Parent.ViewModels.MealMoneyAutoPaySettingsViewModel | Defect Fixed | 0.5 |  | 2.75 | 2025-09-23 | 2025-09-23 | NA | NA | NA | Sambath | NA | Pull Request 44699: jagdeep.singh/25986-MSBP-GA-MSB.Parent.ViewModels.MealMoneyAutoPaySettingsVie... | 2025-09-23 | 2025-09-23 | Ashwin | NA | Sean | 2025-09-24 | NA | NA | NA | Defects tested by Onsite QA and closed | Exceeds Expectation |  | Main Sprint
13 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep | 25989 | MSBP - GA - MSB.Parent.ViewModels.StudentDetailViewModel | Defect Fixed | 0.5 |  | 2 | 2025-09-23 | 2025-09-23 | NA | NA | NA | Sambath | NA | jagdeep.singh/MSBP-GA-MSB.Parent.ViewModels.StudentDetailViewModel | 2025-09-23 | 2025-09-23 | Ashwin | NA | Sean | 2025-09-24 | NA | NA | NA | Defects tested by Onsite QA and closed | Exceeds Expectation |  | Main Sprint
14 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep | 25997 | MSBP - GA - MSB.Parent.Helpers.LoginHelper.RestoreSavedSession | Defect Fixed | 0.5 |  | 1 | 2025-09-23 | 2025-09-23 | NA | NA | NA | Sambath | NA | jagdeep.singh/25997-MSBP-GA-MSBP.Parent.Helpers.LoginHelper.RestoreSavedSession | 2025-09-23 | 2025-09-23 | Ashwin | NA | Sean | 2025-09-24 | NA | NA | NA | Defects tested by Onsite QA and closed | Exceeds Expectation |  | Main Sprint
15 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Amrit | 25998 | MSBP - GA - MSB.Parent.Core.NavigationService.OnNavigated | Defect Fixed | 1 |  | 3 | 2025-09-23 | 2025-09-23 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44704 | 2025-09-23 | 2025-09-23 | NA | NA | Sean | 2025-09-23 | NA | NA | NA | Defects tested by Onsite QA and closed | Exceeds Expectation |  | Main Sprint
16 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Rupesh | 25994 | MSBP - GA - MSB.Parent.ViewModels.ReceiptViewModel | Defect Fixed | 1 |  | 6 | 2025-09-23 | 2025-09-23 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44710 | 2025-09-23 | 2025-09-23 | NA | NA | Sean | 2025-09-23 | NA | NA | NA | Defects tested by Onsite QA and closed | Exceeds Expectation |  | Main Sprint
17 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Gursewak | 25993 | MSBP - GA - MSB.Parent.ViewModels.StoreViewModel | Defect Fixed | 0.5 |  | 2 | 2025-09-23 | 2025-09-23 | Na | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44708 | 2025-09-23 | 2025-09-23 | NA | NA | Sean | 2025-09-23 | NA | NA | NA | Defects tested by Onsite QA and closed | Exceeds Expectation |  | Main Sprint
18 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep | 25995 | MSBP - GA - MSB.Parent.ViewModels.ProductDetailViewModel | Defect Fixed | 0.5 |  | 2 | 2025-09-23 | 2025-09-23 | NA | NA | NA | Ashwin | NA | Pull Request 44705: jagdeep.singh/25995-MSBP-GA-MSB.Parent.ViewModels.ProductDetailViewModel | 2025-09-23 | 2025-09-23 | NA | NA | Sean | 2025-09-24 | NA | NA | NA | Defects tested by Onsite QA and closed | Exceeds Expectation |  | Main Sprint
19 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep | 26004 | MSBP - MAUI - Android- Keyboard switches away from numerical after first digit entry (regression) | Defect Rejected | 0 |  | 1 | 2025-09-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Issue seems to be fixed in the latest Maui version. So Onsite QA rejected this defect. |  |  | Main Sprint
20 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Gursewak | 26003 | MSBP - MAUI - Entering partial amount more than the remaining balance amount, screen freezes and unable to move forward (regression) | Defect Fixed | 0 |  | 6 | 2025-09-24 | 2025-09-25 | Na | NA | Na | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44798 | 2025-09-25 | 2025-09-26 | NA | NA | Brian | 2025-09-26 | NA | NA | NA | Tested by Onsite QA | Exceeds Expectation |  | Main Sprint
21 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Sambath | 25988 | 25988 MSBP - GA - Plugin.Fingerprint.FingerprintImplementation | Defect Fixed | 2 |  | 8 | 2025-09-23 | 2025-09-24 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44744 | 2025-09-24 | 2025-09-24 | Ashwin | NA | Sean | 2025-09-24 | NA | NA | NA | Testing completed by Onsite QA. | Exceeds Expectation |  | Main Sprint
22 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Vaishnavi/Prem | 25924 | MSBP - AutoPay - Reverting to Disabled | Defect Fixed | 2 |  | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main Sprint
24 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Rupesh | 26022 | MSBP - MAUI - Redirecting to from empty cart freezes app (regression) | Defect Fixed | 0 |  | 4 | 2025-09-25 | 2025-09-26 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44781 | 2025-09-25 | 2025-09-25 | Ashwin | NA | Brian | 2025-09-26 | NA | Completed | NA | Tested by Onsite QA | Exceeds Expectation |  | Main Sprint
25 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Gursewak | 26028 | MSBP -MAUI - Adding new payment method from Meal money autopay not prompting for cvv when autopay is saved(regression) | Defect Needs More Info | 0 |  | NA | 2025-09-26 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Ashwin Added comment on slack, "@Gursewak Singh The defect you are working on is not a app defect but a gateway data setup issue in test as its working as expected in Staging" |  |  | Main Sprint
26 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Sambath | 26030 | 26030 MSBP - MAUI - iOS26 - student meal payment is showing blank | Defect Fixed | 3 |  | 12 | 2025-09-26 | 2025-09-29 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44850 | 2025-09-29 | 2025-09-29 | Ashwin | NA | Sean | 2025-09-29 | NA | Completed | NA | Tested by Onsite QA | Exceeds Expectation |  | Main Sprint
27 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep/Prem | 25975 | MSBP - MAUI - Family Pass discount line showing when no program fee | Defect Fixed | 0 |  | 3 | 2025-09-29 | 2025-09-29 | NA | NA | NA | Sambath | NA | Pull Request 44842: jagdeep.singh/25975-MSBP-MAUI-Family Pass discount line showing when no progr... | 2025-09-29 | 2025-09-30 | Ashwin | NA | Sean | 2025-09-30 | NA | Completed | NA | Testing completed and defect closed. | Exceeds Expectation |  | Main Sprint
29 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Gursewak | 26034 | MSBP-MAUI-I-Bottom sheet not showing all information, Student info(regression) | Defect Fixed | 0 |  | 3 | 2025-09-29 | 2025-09-29 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44847 | 2025-09-29 | 2025-09-30 | Ashwin | NA | Sean | 2025-09-30 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
30 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Rupesh | 26033 | MSBP-MAUI- iOS-Selecting expired payment method for an invoice transaction,screen does not redirect to Edit Payment Method screen(regression) | Defect Fixed | 0 |  | 6 | 2025-09-29 | 2025-09-29 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44846 | 2025-09-29 | 2025-09-30 | Ashwin | NA | Sean | 2025-09-29 | NA | Completed | NA | Client review is pending. (Delayed by 1 day) | Exceeds Expectation |  | Main Sprint
33 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Jagdeep | 26042 | MSBP-MAUI - Negative amount showing with minus sign not in brackets( ) in Payment history(regression) | Defect Ready For Testing | 0 |  | 3 | 2025-09-29 | 2025-09-29 | NA | NA | NA | Gursewak | NA | Pull Request 44845: jagdeep.singh/26042-MSBP-MAUI-Negative amount showing with minus sign not in... | 2025-09-29 | NA | Ashwin | NA | Sean | 2025-10-02 | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
34 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Gursewak/Vaishnavi. | 26045 | MSBP-MAUI - Amount field is not right aligned in Add Meal money screen(regression) | Defect Fixed | 0 |  | 3 | 2025-09-29 | 2025-09-29 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44847?_a=files | 2025-09-29 | 2025-09-30 | Ashwin | NA | Sean | NA | NA | Completed | NA |  | Exceeds Expectation |  | Main Sprint
35 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 Stretch | Rupesh | 49816 | MSBA - MAUI - Update Login Screen Username Fields | Story Peer Review | 1 |  | 4 | 2025-09-30 |  | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44882 | 2025-09-30 | [6 empty] | Completed | NA | Under Internal review. | Exceeds Expectation |  | Backlog
36 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 | Gursewak | 26049 | MSBP-MAUI- Payment Installment schedule is not cleared after selecting 'Pay in Full' from Payment options(regression) | Defect Fixed | 0 |  | 6 | 2025-09-30 | 2025-09-30 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44890?_a=files | 2025-09-30 | 2025-10-01 | Ashwin | NA | Sean | 2025-10-01 | Na | Completed | NA | Merged, ready to test | Exceeds Expectation |  | Main Sprint
37 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 Stretch | Rupesh | 48146 | MSBA - MAUI - Hide Mode Settings In Prod | Story Peer Review | 1 |  | 2 | 2025-09-30 |  | NA | NA | NA |  | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44901 | 2025-09-30 |  |  | NA |  |  |  | NA | NA | Under Internal review. | Exceeds Expectation |  | Backlog
28 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 Stretch | Amrit | 46089 | MSBA - Maui - Checkout - Cash - Predefined dollar fields do not make sense against the total and cannot be used | Defect Being Fixed | 3 |  | 12 | 2025-09-29 | NA | NA | NA | NA | [12 empty] | Development in progress
31 | MSB Mobile | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 Stretch | Sambath | 50129 | 50129 MSBA - Automation - Implement MSBA automation similar to MSBP [Timebox] | Story Being Developed | 5 |  | 7 | 2025-09-24 | [16 empty] | Will continue with the investigation on the automation stuffs |  |  | Stretch
32 | MSB Mobile Kaleida | 2025-09-19 | 2025-10-02 | 15.2 M Sprint 3 Stretch | Jagdeep | 50045 | MSBP - After Adding Student - Show Loading Symbol Until Student is Added to Homescreen | Story Peer Review | 1 |  | 4 | 2025-09-30 | 2025-09-30 | NA | NA | NA | Rupesh | NA | Pull Request 44884: jagdeep.singh/50045-MSBP-After Adding Student show loading Symbol Until Stude... | 2025-09-30 | NA | NA | NA | NA |  | NA | Completed |  | Client review is pending. | Exceeds Expectation |  | Stretch

## 15.2 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.2 M Sprint 3 | 25905 MSBA - MAUI - District tax rate not applied | 25905 MSBA - MAUI - District tax rate not applied | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25936 MSBA - MAUI - iOS - after a timeout force log out, cannot manually log out | 25936 MSBA - MAUI - iOS - after a timeout force log out, cannot manually log out | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25964 MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox]" | 25964 MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox]" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25934 MSBA - MAUI - iOS - double loading icon on the MFA pages | 25934 MSBA - MAUI - iOS - double loading icon on the MFA pages | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | "25927MSBA - MAUI - iOS - hamburger menu not all centered | "25927MSBA - MAUI - iOS - hamburger menu not all centered | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25844 MSBA - MAUI - able to open/stack transaction history/settings/close out from hamburger menu | 25844 MSBA - MAUI - able to open/stack transaction history/settings/close out from hamburger menu | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25986 MSBP - GA - MSB.Parent.ViewModels.MealMoneyAutoPaySettingsViewModel | 25986 MSBP - GA - MSB.Parent.ViewModels.MealMoneyAutoPaySettingsViewModel | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25989 MSBP - GA - MSB.Parent.ViewModels.StudentDetailViewModel | 25989 MSBP - GA - MSB.Parent.ViewModels.StudentDetailViewModel | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25997 MSBP - GA - MSB.Parent.Helpers.LoginHelper.RestoreSavedSession | 25997 MSBP - GA - MSB.Parent.Helpers.LoginHelper.RestoreSavedSession | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25998 MSBP - GA - MSB.Parent.Core.NavigationService.OnNavigated | 25998 MSBP - GA - MSB.Parent.Core.NavigationService.OnNavigated | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25994 MSBP - GA - MSB.Parent.ViewModels.ReceiptViewModel | 25994 MSBP - GA - MSB.Parent.ViewModels.ReceiptViewModel | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25993 MSBP - GA - MSB.Parent.ViewModels.StoreViewModel | 25993 MSBP - GA - MSB.Parent.ViewModels.StoreViewModel | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25995 MSBP - GA - MSB.Parent.ViewModels.ProductDetailViewModel | 25995 MSBP - GA - MSB.Parent.ViewModels.ProductDetailViewModel | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26004 MSBP - MAUI - Android- Keyboard switches away from numerical after first digit entry (regression) | 26004 MSBP - MAUI - Android- Keyboard switches away from numerical after first digit entry (regression) | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26003 MSBP - MAUI - Entering partial amount more than the remaining balance amount, screen freezes and unable to move forward (regression) | 26003 MSBP - MAUI - Entering partial amount more than the remaining balance amount, screen freezes and unable to move forward (regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25988 MSBP - GA - Plugin.Fingerprint.FingerprintImplementation" | 25988 MSBP - GA - Plugin.Fingerprint.FingerprintImplementation" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25924 MSBP - AutoPay - Reverting to Disabled | 25924 MSBP - AutoPay - Reverting to Disabled | Vaishnavi/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26022 MSBP - MAUI - Redirecting to from empty cart freezes app (regression) | 26022 MSBP - MAUI - Redirecting to from empty cart freezes app (regression) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26028 MSBP -MAUI - Adding new payment method from Meal money autopay not prompting for cvv when autopay is saved(regression) | 26028 MSBP -MAUI - Adding new payment method from Meal money autopay not prompting for cvv when autopay is saved(regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26030 MSBP - MAUI - iOS26 - student meal payment is showing blank | 26030 MSBP - MAUI - iOS26 - student meal payment is showing blank | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 25975 MSBP - MAUI - Family Pass discount line showing when no program fee | 25975 MSBP - MAUI - Family Pass discount line showing when no program fee | Jagdeep/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26034 MSBP-MAUI-I-Bottom sheet not showing all information, Student info(regression) | 26034 MSBP-MAUI-I-Bottom sheet not showing all information, Student info(regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26033 MSBP-MAUI- iOS-Selecting expired payment method for an invoice transaction,screen does not redirect to Edit Payment Method screen(regression) | 26033 MSBP-MAUI- iOS-Selecting expired payment method for an invoice transaction,screen does not redirect to Edit Payment Method screen(regression) | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26042 MSBP-MAUI - Negative amount showing with minus sign not in brackets( ) in Payment history(regression) | 26042 MSBP-MAUI - Negative amount showing with minus sign not in brackets( ) in Payment history(regression) | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26045 MSBP-MAUI - Amount field is not right aligned in Add Meal money screen(regression) | 26045 MSBP-MAUI - Amount field is not right aligned in Add Meal money screen(regression) | Gursewak/Vaishnavi. | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 3 | 26049 MSBP-MAUI- Payment Installment schedule is not cleared after selecting 'Pay in Full' from Payment options(regression) | 26049 MSBP-MAUI- Payment Installment schedule is not cleared after selecting 'Pay in Full' from Payment options(regression) | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
[5 empty] | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects

## 15.2 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments | Sprint Tag
1 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Jagdeep | 49129 | MSBP - Automation - Mappings for Automation - Suggested Students workflow | Story Completed | 1 |  | 18 | 2025-07-30 | 2025-08-29 | NA | NA | NA | Gursewak | NA | Pull Request 44354: 49129- Automation - Mappings for Automation - Suggested Students workflow | 2025-08-29 | 2025-09-05 | Ashwin | NA | Owen | 2025-09-05 | NA | Completed | NA | Story completed | Exceeds Expectation |  | Main Sprint | Meets Expectation: Developer has a few doubts in AC, checked with PO, and development completed without any AC change
2 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Rupesh/Prem | 25565 | MSBA - MAUI - Transaction history missing () indicating refund | Defect Fixed | 0.5 |  | 30 | 2025-09-01 | 2025-09-12 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44335 | 2025-03-09 | 2025-03-09 | Ashwin | Rename one of the method | Sean | 2025-09-12 | TODO's are formatted like this //TODO: {message} | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
3 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Sambath/Prem | 25665 | MSBA - MAUI - shift mode search bar cut off in landscape mode | Defect Fixed | 0.5 |  | 9 | 2025-09-01 | 2025-09-12 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44532?_a=files | 2025-09-12 | 2025-09-12 | Ashwin | NA | Sean | 2025-09-12 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
4 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Jagdeep/Prem | 25625 | MSBA - MAUI - close day payment summary text is greyed out | Defect Fixed | 1 |  | 4 | 2025-09-02 | 2025-09-02 | NA | NA | NA | Rupesh | NA | Pull Request 44302: jagdeep.singh/25625 MSBA-MAUI-close day payment summary text is greyed out | 2025-09-02 | 2025-09-02 | Ashwin | NA | Sean | 2025-09-05 | These fields are not editable. You need to use a style or something when IsEnabled=false change the txt color | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
5 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Jagdeep/Prem | 25493 | MSBP - MAUI - On adding second student/district with tickets available, banner not showing | Defect Fixed | 2 |  | 13 | 2025-09-03 | 2025-09-05 | NA | NA | NA | Amrit | NA | Pull Request 44376: jagdeep.singh/25493 MSBP-MAUI-On adding second student district with tickets... | 2025-09-05 | 2025-09-09 | Ashwin | NA | Sean | 2025-09-10 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
6 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Gursewak/Vaishnavi | 25598 | MSBA - MAUI - Android - Login page formatting issues | Defect Fixed | 1 |  | 25 | 2025-09-04 | 2025-09-16 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44416?_a=files | 2025-09-15 | 2025-09-16 | Ashwin | NA | Sean | 2025-09-16 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
7 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Amrit/Vaishnavi | 25614 | MSBA - MAUI - Shift mode UI issues | Defect Fixed | 1 |  | 24 | 2025-09-05 | 2025-10-09 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44424 | 2025-08-09 | 2025-09-11 | Ashwin | NA | Avery | 2025-09-11 | NA | Completed | Regarding Font size changes | Testing completed | Exceeds Expectation |  | Main Sprint
8 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Rupesh/Prem | 25575 | MSBA - MAUI - meal payments screen changing formats | Defect Fixed | 1 |  | 14 | 2025-09-04 | 2025-10-09 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44417 | 2025-09-08 | 2025-09-09 | Ashwin | NA | Sean | 2025-09-10 | Wasn't this just added? | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
9 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Sambath/Prem | 25619 | MSBA - MAUI - Close day navigation buttons cut off | Defect Fixed | 0.5 |  | 13 | 2025-09-04 | 2025-09-10 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44475 | 2025-09-10 | 2025-09-10 | Ashwin | NA | Sean | 2025-09-10 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
10 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Sambath/Prem | 25617 | MSBA - MAUI - Android - close day progress indicators cut off | Defect Fixed | 0.5 |  | 14 | 2025-09-04 | 2025-09-10 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44475 | 2025-09-10 | 2025-09-10 | Ashwin | NA | Sean | 2025-09-10 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
11 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Jagdeep/Vaishnavi | 25838 | MSBA-MAUI - Unable to Scroll the product/invoice/meals from Cart screen | Defect Fixed | 1 |  | 5 | 2025-09-05 | 2025-09-05 | NA | NA | NA | Amrit | NA | Pull Request 44384: jagdeep.singh/25838-MSBA-MAUI-Unable to Scroll the product and invoice and me... | 2025-09-04 | 2025-09-05 | Ashwin | NA | Sean | 2025-09-10 | Collection view already contains a scrollview. Have two scroll controls embedded is not advisable | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
12 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Jagdeep/Prem | 25735 | MSBP - iOS - Tickets banner missing arrow icon when no events | Defect Fixed | 2 |  | 9 | 2025-09-09 | 2025-09-09 | NA | NA | NA | Rupesh | NA | Pull Request 44446: jagdeep.singh/25735-MSBP-iOS-Tickets banner missing arrow icon when no events | 2025-09-09 | 2025-09-09 | Ashwin | NA | Sean | 2025-09-10 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
13 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Amrit/Vaishnavi | 25478 | MSBP - MAUI - iOS - Error Messaging Validation and Formatting | Defect Fixed | 1 |  | 23 | 2025-09-08 | 2025-09-10 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44425 | 2025-09-09 | 2025-09-10 | Ashwin | NA | Avery | 2025-09-10 | NA | Completed | NA | Testing completed | Meets Expectation | Valid card details are shared with client if anything need update then we will get revert back from client. | Main Sprint
14 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Jagdeep/Vaishnavi | 25734 | MSBP - MAUI - "Password too common" error when adding an account that already exists | Defect Fixed | 2 |  | 9 | 2025-09-08 | 2025-09-08 | NA | NA | NA | Amrit | NA | Pull Request 44418: jagdeep.singh/25734-MSBP-MAUI-Password too common error when adding an accoun... | 2025-09-08 | 2025-09-09 | Ashwin | NA | Sean | 2025-09-10 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Main Sprint
15 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Sambath | 25885 | MSBP - MAUI - Auto login does not work after closing the browser and selecting tickets from application for the second time | Defect Fixed | 2 |  | 6 | 2025-09-09 | 2025-09-09 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44464?_a=files | 2025-09-09 | 2025-09-09 | Ashwin | NA | Sean | 2025-09-10 | NA | NA | NA | Testing completed | Exceeds Expectation |  | Main Sprint
16 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Sambath | 25811 | 25811 MSBP Android - Fingerprint Plugin causing crash [Timebox] | Defect Rejected | 1 |  | 11 | 2025-09-10 | 2025-09-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Analysed and shared the information to Ashwin. Waiting for the comments from him. | Needs Improvement | No proper repro step available in the Defect to reproduce this issue. | Main Sprint
| MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 | Vaishnavi/Prem | 25924 | MSBP - AutoPay - Reverting to Disabled | Defect Being Tested | 0.5 |  |  | 2025-09-18 | [16 empty] | This defect has only testing scope from offshore and it was taken at the end of the sprint. The original issue reported in PROD is not reproducible in PROD and TEST. Shared the video recordings and steps which we used to Onsite QA. Waiting for their reply on this. |  |  | Main Sprint
17 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Gursewak/Vaishnavi | 25562 | 25562 MSBA - MAUI - extra space on cart preview under cart items | Defect Fixed | 1 |  | 11 | 2025-09-08 | 2025-09-09 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44453 | 2025-09-09 | 2025-09-10 | Ashwin | NA | NA | 2025-09-10 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Backlog
18 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Vaishnavi/Prem | 49122 | MSBP - Automation - Mappings for Automation - Checkout/Receipt | Story Being Developed | 5 |  |  | 2025-09-05 | [16 empty] | As of now Automation is on hold, due to the main sprint defects testing. Once we have completed the commited defects testing, will continue with automation |  |  | Backlog
19 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25830 | MSBA - MAUI - Android - Product Detail formatting issues (quantity) | Defect Fixed | 1 |  | 4 | 2025-09-10 | 2025-09-10 | NA | NA | NA | Rupesh | Margin for phone can be removed as it is 0. | Pull Request 44466: jagdeep.singh/25830 MSBA-MAUI-Android-Product Detail formatting issues quantity | 2025-09-10 | 2025-09-10 | Ashwin | NA | Sean | 2025-09-10 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Backlog
20 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Rupesh/Vaishnavi | 25566 | MSBA - MAUI - phones - transaction history information cut off | Defect Fixed | 2 |  | 22.5 | 2025-09-09 | 2025-09-16 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44535 | 2025-09-12 | 2025-09-16 | Ashwin | ScollBar Visibility is not needed. | Scroll View under Scroll is not advisable. | 2025-09-16 | NA | Completed | NA |  | Exceeds Expectation |  | Backlog
21 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25846 | MSBA - MAUI - upon logout, no message and cannot log back in | Defect Being Tested | 3 |  | 13 | 2025-09-11 | 2025-09-11 | NA | NA | NA | C | NA | jagdeep.singh/25846-MSBA-MAUI-upon-logout-no-message-and-cannot-log-back-in | 2025-09-11 | 2025-09-16 | Ashwin | NA | Sean | 2025-09-16 | NA | Completed | NA | Timeout is not happening in all the devices. This is blocking us to test and close the defects |  |  | Backlog
22 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Jagdeep/Vaishnavi | 25848 | MSBA - MAUI - product name not showing on thumbnail when no image on store page | Defect Fixed | 2 |  | 8 | 2025-09-12 | 2025-09-12 | NA | NA | NA | Rupesh | NA | Pull Request 44530: jagdeep.singh/25848-MSBA-MAUI-product name not showing on thumbnail when no i... | 2025-09-12 | 2025-09-16 | Ashwin | NA | Sean | 2025-09-16 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Backlog
23 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Amrit | 25849 | MSBA - Group filters not showing the products when particular category is selected | Defect Blocked | 1 |  | 13 | 2025-09-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Defect is blocked due to an API issue | Exceeds Expectation | Issue is in backend api will be solved by backend team | Backlog
24 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Sambath/Vaishnavi | 25847 | 25847 MSBA - MAUI - products not available to be added to cart are not disabled when required field not filled | Defect Fixed | 2 |  | 8 | 2025-09-11 | 2025-09-15 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44577 | 2025-09-16 | 2025-09-16 | Ashwin | NA | Sean | NA | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Backlog
25 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25550 | MSBA - MAUI - Android phone - unable to interact with heading | Defect Fixed | 5 |  | 14 | 2025-09-15 | 2025-09-15 | NA | NA | NA | Rupesh | NA | Pull Request 44551: jagdeep.singh/25550-MSBA-MAUI-Android phone unable to interact with heading | 2025-09-15 | 2025-09-16 | Ashwin | NA | Sean | 2025-09-16 | NA | Completed | NA | Testing completed | Meets Expectation | Areas was not mentioned clearly to provide the fix in the defect | Backlog
26 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Rupesh/Vaishnavi | 25926 | MSBP - MAUI - Event banner is not clickable for a new user with no students | Defect Fixed | 3 |  |  | 2025-09-12 | 2025-09-16 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44622 | 2025-09-17 | 2025-09-17 | Ashwin | NA | Sean | 2025-09-17 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Backlog
27 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25845 | MSBA - MAUI - Store filters not showing the results based on the search criteria | Defect Fixed | 2 |  | 8 | 2025-09-16 | 2025-09-16 | NA | NA | NA | Gursewak | NA | Pull Request 44579: jagdeep.singh/25845-MSBA-MAUI-Store filters not showing the results based on... | 2025-09-16 | 2025-09-16 | Ashwin | NA | Sean | 2025-09-16 | NA | Completed | NA | Testing completed | Exceeds Expectation |  | Backlog
28 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Amrit | 25905 | MSBA - MAUI - District tax rate not applied | Defect Being Fixed | 3 |  |  | 2025-09-16 | [16 empty] | Development in progress. |  |  | Backlog
29 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Gursewak | 25892 | MSBA - MAUI - Android - Back button exists on first page of Close out | Defect Being Fixed | 1 |  |  | 2025-09-16 | [16 empty] | Jason added comment, = After Standup on 9/17, we can drop this in priority as it's problematic to solve. It's not a major issue to the user experience |  |  | Backlog
30 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25936 | MSBA - MAUI - iOS - after a timeout force log out, cannot manually log out | Defect Being Tested | 2 | 6 | 3 | 2025-09-17 | 2025-09-17 | NA | NA | NA | Gursewak | NA | jagdeep.singh/25846-MSBA-MAUI-upon-logout-no-message-and-cannot-log-back-in | 2025-09-17 | 2025-09-17 | Ashwin | NA | Sean | 2025-09-17 | NA | Completed | NA | Timeout is not happening in all the devices. This is blocking us to test and close the defects |  |  | Backlog
31 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Sambath | 25622 | 25622 MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox] | Defect Fixed | 2 |  | 8 | 2025-09-16 | 2025-09-16 | [15 empty] | Testing completed |  |  | Stretch
32 | MSB Mobile Kaleida | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Jagdeep | 25934 | MSBA - MAUI - iOS - double loading icon on the MFA pages | Defect Being Fixed | 2 |  | 6 | 2025-09-18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | [6 empty] | Development in progress. |  |  | Backlog
33 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Gursewak | 25927 | MSBA - MAUI - iOS - hamburger menu not all centered | Defect Peer Review | 2 |  | 18 | 2025-09-18 | 2025-09-22 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44677?_a=files | 2025-09-22 | [8 empty] | Development in progress. |  |  | Backlog
34 | MSB Mobile | 2025-09-05 | 2025-09-18 | 15.2 M Sprint 2 Stretch | Rupesh | 25844 | MSBA - MAUI - able to open/stack transaction history/settings/close out from hamburger menu | Defect Being Fixed |  |  |  | 2025-09-18 |  | NA | NA | NA | [15 empty] | Backlog

## 15.2 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.2 M Sprint 2 | 25565 MSBA - MAUI - Transaction history missing () indicating refund | 25565 MSBA - MAUI - Transaction history missing () indicating refund | Rupesh | Defect | When refunding a transaction, the amount is showing as -2.17 instead of (2.17) xamarin: | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25665 MSBA - MAUI - shift mode search bar cut off in landscape mode | 25665 MSBA - MAUI - shift mode search bar cut off in landscape mode | Gursewak | Defect | It appears when the device is in landscape more, the top value after searching is smaller and can cut off part of the information. In android the no results found is partially cut off but in both iOS and Android an actual searched value is smaller box- can appear to cut off in some screen sizes | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25625 MSBA - MAUI - close day payment summary text is greyed out | 25625 MSBA - MAUI - close day payment summary text is greyed out | Jagdeep | Defect | When close day blind count is off and you go to the sales summary portion of the close day process, the values within the summaries are grey instead of black like xamarin | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25493 MSBP - MAUI - On adding second student/district with tickets available, banner not showing | 25493 MSBP - MAUI - On adding second student/district with tickets available, banner not showing | Jagdeep | Defect | When a parent has an account with no tickets, and adds a student from a district which does, the Events banner on the home screen does not populate with the student. A pull to refresh or close/reopen is required before banner populates Additionally adding another student/district with more events is not updating the banner until a pull to refresh | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25598 MSBA - MAUI - Android - Login page formatting issues | 25598 MSBA - MAUI - Android - Login page formatting issues | Gursewak | Defect | Upon looking at the login page, it appears that there is a difference in color and font weight when compared to Xamarin Check color & font weight (font weight more bold?). we use the same Roboto font in Maui that we had in Xamarin yet now appears a bit more bold. --if this differs in other areas of the app, we'll need to consider addressing & note where to solve. | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25598 MSBA - MAUI - Android - Login page formatting issues | 25598 MSBA - MAUI - Android - Login page formatting issues | Gursewak | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25614 MSBA - MAUI - Shift mode UI issues | 25614 MSBA - MAUI - Shift mode UI issues | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25575 MSBA - MAUI - meal payments screen changing formats | 25575 MSBA - MAUI - meal payments screen changing formats | Rupesh/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25619 MSBA - MAUI - Close day navigation buttons cut off | 25619 MSBA - MAUI - Close day navigation buttons cut off | Sambath/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25617 MSBA - MAUI - Android - close day progress indicators cut off | 25617 MSBA - MAUI - Android - close day progress indicators cut off | Sambath/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25838 MSBA-MAUI - Unable to Scroll the product/invoice/meals from Cart screen | 25838 MSBA-MAUI - Unable to Scroll the product/invoice/meals from Cart screen | Jagdeep/Vaishnavi | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25735 MSBP - iOS - Tickets banner missing arrow icon when no events | 25735 MSBP - iOS - Tickets banner missing arrow icon when no events | Jagdeep/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25478 MSBP - MAUI - iOS - Error Messaging Validation and Formatting | 25478 MSBP - MAUI - iOS - Error Messaging Validation and Formatting | Amrit/Vaishnavi | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25734 MSBP - MAUI - "Password too common" error when adding an account that already exists | 25734 MSBP - MAUI - "Password too common" error when adding an account that already exists | Jagdeep/Vaishnavi | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25885 MSBP - MAUI - Auto login does not work after closing the browser and selecting tickets from application for the second time | 25885 MSBP - MAUI - Auto login does not work after closing the browser and selecting tickets from application for the second time | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25811 MSBP Android - Fingerprint Plugin causing crash [Timebox]" | 25811 MSBP Android - Fingerprint Plugin causing crash [Timebox]" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25562 MSBA - MAUI - extra space on cart preview under cart items | 25562 25562 MSBA - MAUI - extra space on cart preview under cart items | Gursewak/Vaishnavi | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25830 MSBA - MAUI - Android - Product Detail formatting issues (quantity) | 25830 MSBA - MAUI - Android - Product Detail formatting issues (quantity) | Jagdeep/Prem | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25566 MSBA - MAUI - phones - transaction history information cut off | 25566 MSBA - MAUI - phones - transaction history information cut off | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25846 MSBA - MAUI - upon logout, no message and cannot log back in | 25846 MSBA - MAUI - upon logout, no message and cannot log back in | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25848 MSBA - MAUI - product name not showing on thumbnail when no image on store page | 25848 MSBA - MAUI - product name not showing on thumbnail when no image on store page | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25849 MSBA - Group filters not showing the products when particular category is selected | 25849 MSBA - Group filters not showing the products when particular category is selected | Amrit | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25847 MSBA - MAUI - products not available to be added to cart are not disabled when required field not filled" | 25847 MSBA - MAUI - products not available to be added to cart are not disabled when required field not filled" | Sambath | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25550 MSBA - MAUI - Android phone - unable to interact with heading | 25550 MSBA - MAUI - Android phone - unable to interact with heading | Jagdeep | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25926 MSBP - MAUI - Event banner is not clickable for a new user with no students | 25926 MSBP - MAUI - Event banner is not clickable for a new user with no students | Rupesh | Defect |  | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 | 25924 MSBP - AutoPay - Reverting to Disabled | 25924 MSBP - AutoPay - Reverting to Disabled | Vaishnavi/Prem | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25905 MSBA - MAUI - District tax rate not applied | 25905 MSBA - MAUI - District tax rate not applied | Amrit | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25892 "MSBA - MAUI - Android - Back button exists on first page of Close out | 25892 "MSBA - MAUI - Android - Back button exists on first page of Close out | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25936 MSBA - MAUI - iOS - after a timeout force log out, cannot manually log out | 25936 MSBA - MAUI - iOS - after a timeout force log out, cannot manually log out | Jagdeep/Prem | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25622 MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox]" | 25622 MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox]" | Sambath | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25934 MSBA - MAUI - iOS - double loading icon on the MFA pages | 25934 MSBA - MAUI - iOS - double loading icon on the MFA pages | Jagdeep | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | "25927MSBA - MAUI - iOS - hamburger menu not all centered | "25927MSBA - MAUI - iOS - hamburger menu not all centered | Gursewak | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 2 stretch | 25844 MSBA - MAUI - able to open/stack transaction history/settings/close out from hamburger menu | 25844 MSBA - MAUI - able to open/stack transaction history/settings/close out from hamburger menu | Rupesh | Defect |  | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects

## 15.2 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments
1 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Amrit | 49019 | 49019 - MSBP - Automation - Mappings for Automation - Add Student | Story Completed | 1 |  | 56 | 2025-07-25 | 2025-01-07 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43802 | 2025-07-28 | 2025-03-09 | Sambath | Merge date picker code into appium actions | OWEN | 2025-03-09 | NA | Cover Negative case also | NA | Due to Owen was on leave for whole week. Later faced Server issue. Thats why this was delayed. | Meets Expectation |  | Exceeds Expectation: Story - AC is clear, no doubts in the AC, no AC changes. The developer completed the story without depending on the PO
2 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Jagdeep | 49129 | MSBP - Automation - Mappings for Automation - Suggested Students workflow | Story Peer Review | 3 |  | 18 | 2025-07-30 | 2025-08-29 | NA | NA | NA |  | NA | Pull Request 44354: 49129- Automation - Mappings for Automation - Suggested Students workflow | 2025-08-29 |  | NA | NA | NA | NA | NA | NA | NA | Due to merge issue, facing issues while running the automation script by Owen. Updated the changes and tested in local and Browser Stack. Test is passing. PR updated and sent to the client for review |  |  | Meets Expectation: Developer has a few doubts in AC, checked with PO, and development completed without any AC change
3 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Vaishnavi | 49130 | MSBP - Automation - Mappings for Automation - Greenlight card | Story Completed | 0.5 |  | 40 | 2025-08-04 | 2025-08-13 | NA | NA | NA | Sambath | Use TestCategory("OWEN"), remove other TestCategory | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43890 | 2025-08-11 | 2025-08-19 | Ashwin | NA | OWEN | 2024-09-03 | NA | Completed | NA |  | Meets Expectation | Due to Unavailablity of the client, story got delayed to get the approval | Needs Improvement: AC Changes after development starts. If the PO missed any points
4 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Gursewak/Vaishnavi | 25624 | MSBA - MAUI - close day has no data populated | Defect Fixed | 1 |  | 39 | 2025-08-11 | 2025-08-19 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44019?_a=files | 2025-08-19 | 2025-08-21 | Ashwin | NA | Avery | 2025-08-21 | NA | Completed | NA |  | Exceeds Expectation
5 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Rupesh/Vaishnavi | 25644 | MSBA - MAUI - Close day checks do not show for check reconciliation | Defect Fixed | 1 |  | 13 | 2025-08-13 | 2025-08-20 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44019?_a=files | 2025-08-19 | 2025-08-21 | Ashwin | NA | Avery | 2025-08-21 | NA | Completed | NA | This defect was fixed by defect : 25644. | Exceeds Expectation
6 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Gursewak/Vaishnavi | 25618 | MSBA - MAUI - Android - Close day count screen issues | Defect Fixed | 0.5 |  | 10 | 2025-08-19 | 2025-08-20 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44059 | 2025-08-20 | 2025-08-21 | Ashwin | NA | Avery | 2025-08-21 | NA | Completed | NA |  | Exceeds Expectation
7 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Jagdeep/Prem | 25626 | MSBA - MAUI - close day summary offset/short box is white | Defect Fixed | 0.5 |  | 4 | 2025-08-20 | 2025-08-20 | NA | NA | NA | Rupesh | NA | Pull Request 44060: jagdeep.singh/25626-MSBA-MAUI-close day summary offsetshort box is white | 2025-08-20 | 2025-08-20 | Ashwin | NA | Avery/Sean | 2025-08-21 | NA | Completed | NA |  | Exceeds Expectation
8 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Sambath/Prem/Vaishnavi | 25623 | 25623 MSBA - MAUI - if shift mode activated, badge appears behind clock for products added | Defect Fixed | 1 |  | 9 | 2025-08-20 | 2025-08-20 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44050 | 2025-08-20 | 2025-08-20 | Ashwin | NA | Sean |  | NA | Completed | NA |  | Exceeds Expectation
9 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Jagdeep/Prem | 25570 | MSBA - MAUI - Android - Product page formatting issues | Defect Fixed | 1 |  | 12 | 2025-08-21 | 2025-08-21 | NA | NA | NA | Amrit | NA | Pull Request 44088: jagdeep.singh/25570-MSBA-MAUI-Android-Product page formatting | 2025-08-21 | 2025-08-23 | Ashwin | NA | Avery | 2025-08-23 | Add a fallback to the default font size (e.g., 14) in case FontSize isn’t set or is invalid. | Completed | NA |  | Exceeds Expectation
10 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Rupesh/Prem | 25564 | MSBA - Android - transaction history page goes under device heading and navigation | Defect Fixed | 2 |  | 18 | 2025-08-21 | 2025-08-25 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44116 | 2025-08-22 | 2025-08-25 | Ashwin | NA | Sean |  | NA | Completed | NA |  | Meets Expectation
11 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Amrit/Vaishnavi | 25491 | MSBA - MAUI - Icon Missing on Ters & Condition | Defect Fixed | 0.5 |  | 2 | 2025-08-21 | 2025-08-22 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44076 | 2025-08-21 | 2025-08-22 | ashwin | NA | Avery | 2025-01-09 | NA | Completed | NA |  | Exceeds Expectation
12 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Gursewak/Vaishnavi | 25583 | MSBA - MAUI - on opening edit meal payment and saving, it clears amount | Defect Fixed | 1 |  | 15.3 | 2025-08-21 | 2025-08-22 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44105?_a=files | 2025-08-22 | 2025-08-25 | ashwin | NA | Sean | 2025-08-25 | NA | Completed | NA |  | Exceeds Expectation
13 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Amrit/Prem | 25544 | MSBA - MAUI - iOS - filter sidebar in store does not change for groups or filters | Defect Fixed | 1 |  | 3.5 | 2025-08-08 | 2025-08-19 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43963 | 2025-08-18 | 2025-08-20 | ashwin | NA | Avery | 29/8/2025 | NA | Cover Negative case also | NA |  | Exceeds Expectation
14 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Gursewak | 25479 | MSBP - MAUI - image missing on add payment method screen | Defect Fixed | 1 |  | 6.5 | 2025-08-22 | 2025-08-25 | Na | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44138?_a=files | 2025-08-25 | 2025-08-26 | ashwin | NA | Avery | 2025-08-26 | NA | Completed | NA |  | Exceeds Expectation
15 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Jagdeep/Prem | 25576 | MSBA - MAUI - Add to cart button cut off when cart preview active | Defect Fixed | 2 |  | 3 | 2025-08-22 | 2025-08-22 | Na | NA | NA | Rupesh | NA | Pull Request 44108: jagdeep.singh/25576-MSBA-MAUI-Add to cart button cut off when cart preview ac... | 2025-08-22 | 2025-08-23 | Ashwin | NA | Avery | 2025-08-23 | NA | Completed | NA |  | Exceeds Expectation
16 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Rupesh/Vaishnavi | 25586 | MSBA - MAUI - Android - cart difficult to enter edit screens | Defect Fixed | 1 |  | 13 | 2025-08-25 | 2025-08-29 | Na | NA | NA |  | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44142 | 2025-08-25 | 2025-08-28 | Ashwin | NA | Avery | 2025-08-29 | NA | Completed | NA |  | Exceeds Expectation
17 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Jagdeep/Vaishnavi | 25640 | MSBP-MAUI - iOS - Shows white screen on accessing links more than two times in Quick Links Section | Defect Fixed | 2 |  | 6.5 | 2025-08-25 | 2025-08-25 | NA | NA | NA | NA | Please remove margin if set as 0 | Pull Request 44130: jagdeep.singh/25640 MSBP-MAUI-iOS-Shows white screen on accessing links more... | 2025-08-25 | 2025-08-28 | Ashwin | Store was also having issue. fixed | Sean | 2025-08-28 | NA | Completed | NA |  | Exceeds Expectation
18 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 | Sambath/Vaishnavi | 49322 | 49322 MSBP - Tickets - App Token Call Update | Story Completed | 3 |  | 36.5 | 2025-08-22 | 2025-08-26 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44167 | 2025-08-26 | 2025-08-26 | Ashwin | NA | Sean | 2025-08-26 | NA | Completed | NA |  | Exceeds Expectation
19 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Sambath/Prem | 25577 | 25577 MSBA - MAUI - promocode error message cut off | Defect Fixed | 1 |  | 5 | 2025-08-22 | 2025-08-26 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44109 | 2025-08-26 | 2025-09-02 | Ashwin | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation
20 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Jagdeep/Vaishnavi | 25629 | MSBA - MAUI - iOS - error message for clerk behind entry box | Defect Fixed | 2 |  | 4 | 2025-08-25 | 2025-08-25 | Na | NA | NA | Rupesh | NA | Pull Request 44132: jagdeep.singh/25629 MSBA-MAUI-iOS-error message for clerk behind entry box | 2025-08-25 | 2025-08-25 | Ashwin | NA | Sean | 2025-08-25 | NA |  |  |  | Exceeds Expectation
21 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Gursewak/Prem | 25616 | MSBA - MAUI - Close day Icons missing/incorrect | Defect Fixed | 1 |  | 4 | 2025-08-28 | 2025-08-28 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44234 | 2025-08-28 | 2025-08-27 | Avery | NA | Avery | 2025-09-02 | NA | Completed | NA |  | Exceeds Expectation
22 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Amrit/Prem | 25615 | MSBA - MAUI - Android -shift mode typing phone number issue | Defect Fixed | 1 |  | 6 | 2025-08-25 | 2025-08-25 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44133 | 2025-08-25 | 2025-08-26 | Rupesh | NA | Avery | 26/8/2025 | NA |  | NA |  | Exceeds Expectation
23 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Gursewak/Vaishnavi | 25572 | MSBA - MAUI - invoice add to cart/remove button does not work | Defect Fixed | 2 |  | 6 | 2025-08-26 | 2025-08-26 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44168 | 2025-08-26 | 2025-08-27 | Ashwin | NA | NA | NA | NA | Completed | NA |  | Exceeds Expectation
24 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Amrit/Prem | 25549 | MSBA - MAUI - phone - acknowledgements half page in landscape | Defect Fixed | 1 |  | 6 | 2025-08-26 | 2025-08-26 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44183 | 2025-09-01 | 2025-09-02 | Rupesh | NA | Avery | 2025-03-09 | NA |  | NA |  | Meets Expectation
25 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Rupesh/Vaishnavi | 25559 | MSBA - MAUI - Android - Back arrow in product details cut off | Defect Fixed | 1 |  | 6 | 2025-08-26 | 2025-08-28 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44236 | 2025-08-28 | 2025-08-29 | Ashwin | NA | Awery | 2025-08-29 | NA | Completed |  |  | Meets Expectation
26 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Amrit/Vaishnavi | 25558 | MSBA - when signing in, if decline TOS and relog in, not presented with MFA | Defect Fixed | 2 |  | 10 | 2025-08-28 | 2025-08-29 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44281 | 2025-09-01 | 2025-09-02 | Ashwin | NA | Avery | 2025-02-09 | NA |  | NA |  | Meets Expectation
27 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Vaishnavi/Prem | 25829 | MSBA - MAUI - no error message on bad login, can't log in after | Defect Fixed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation
28 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Gursewak/Vaishnavi | 25666 | MSBA - MAUI - Android Phone - Cannot scroll to see entire Close day start page | Defect Fixed | 1 |  | 12 | 2025-08-29 | 2025-09-01 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44286?_a=files | 2025-09-01 | 2025-09-03 | Ashwin | NA | Sean | 2025-09-03 | NA | Completed | NA |  | Exceeds Expectation
29 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Rupesh | 25565 | MSBA - MAUI - Transaction history missing () indicating refund | Defect Being Fixed | 1 |  | 22 | 2025-09-01 |  | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44335 | 2025-03-09 | 2025-03-09 | [7 empty] | Yet to get approved by Ashwin and Client
30 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Jagdeep | 25840 | MSBA - MAUI - 'Successfully added invoice' message appears and disappears quickly in iOS after adding invoice to cart | Defect Peer Review | 1 |  | 4 | 2025-09-01 | 2025-09-01 |  |  |  | Amrit |  | Pull Request 44284: jagdeep.singh/25840 MSBA-MAUI-'Successfully added invoice' message appears an... | [7 empty] | Completed |  | Not yet merged. Needs a discussion with Ashwin
31 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Sambath | 25665 | MSBA - MAUI - shift mode search bar cut off in landscape mode | Defect Being Fixed | 1 |  | 3 | 2025-09-01 | [6 empty] | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44333
32 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Sambath/Vaishnavi | 25814 | 25814 MSBP - MAUI - Events banner not showing the Event count in Homescreen | Defect Fixed | 2 | 7 | 7 | 2025-09-01 | 2025-09-02 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44307 | 2025-09-02 | 2025-09-02 | Ashwin | NA | Avery | NA | NA |  | NA |  | Exceeds Expectation
33 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Jagdeep | 25622 | MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox] | Defect Needs More Info | 2 |  | 1 | 2025-09-02 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Issue not reproducible in test environment. Status changesd to need more information. Added comments in the axosoft aswell.
34 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Jagdeep/Vaishnavi | 25620 | MSBA - MAUI - Android - warning messages on close day missing margins | Defect Fixed | 0.5 |  | 2 | 2025-09-02 | 2025-09-02 | NA | NA | NA | Amrit | NA | Pull Request 44303: jagdeep.singh/25620 MSBA-MAUI-Android-warning messages on close day missing margins | 2025-09-02 | 2025-09-02 | Ashwin | NA | Avery | 2025-09-02 | NA | Completed | NA |  | Exceeds Expectation
35 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Jagdeep | 25625 | MSBA - MAUI - close day payment summary text is greyed out | Defect Peer Review | 1 |  | 4 | 2025-09-02 | 2025-09-02 | NA | NA | NA | Rupesh |  | Pull Request 44302: jagdeep.singh/25625 MSBA-MAUI-close day payment summary text is greyed out | 2025-09-02 | 2025-09-02 | Ashwin | NA |  |  |  | Completed |  | Yet to be get approved by Ashwin and Client
36 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Jagdeep/Prem | 25543 | MSBA - MAUI - Android - Camera icon cut off in store and invoice search bars | Defect Fixed | 2 |  | 6 | 2025-09-03 | 2025-09-03 | NA | NA | NA | Gursewak | NA | Pull Request 44323: jagdeep.singh/25543-MSBA-MAUI-Android-Camera icon cut off in store and invoic... | 2025-09-03 | 2025-09-04 | Ashwin | NA | Sean | 2025-09-04 | NA | Completed | NA |  | Exceeds Expectation
37 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Vaishnavi | 49775 | MSBP - Replace MSB Lab environment with MSB Dev environment | Story Completed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation
38 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Gursewak | 25571 | MSBA - MAUI - Android - adding product to cart does not redirect | Defect Needs More Info | 2 |  |  | 2025-09-03 | [16 empty] | Issue not reproducible. Added comments in the axosoft aswell.
39 | MSB Mobile Kaleida | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Jagdeep | 25493 | MSBP - MAUI - On adding second student/district with tickets available, banner not showing | Defect Peer Review | 2 |  | 3 | 2025-09-03 | 2025-09-05 | NA |  |  |  |  | Pull Request 44376: jagdeep.singh/25493 MSBP-MAUI-On adding second student district with tickets... | 2025-09-04 | NA | [5 empty] | Completed |  | Development in progress.
40 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Vaishnavi | 49776 | MSBA - Replace MSB Lab environment with MSB Dev environment | Story Completed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation
41 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Gursewak | 25598 | MSBA - MAUI - Android - Login page formatting issues | Defect Being Fixed | 2 |  | 3 | 2025-09-04 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Development in progress.
42 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Amrit | 25614 | MSBA - MAUI - Shift mode UI issues | Defect Being Fixed | 1 |  | 12 | 2025-09-04 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
43 | MSB Mobile | 2025-08-22 | 2025-09-04 | 15.2 M Sprint 1 Stretch | Rupesh | 25575 | MSBA - MAUI - meal payments screen changing formats | Defect Being Fixed | 1 |  | 3 | 2025-09-04 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 15.2 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.2 M Sprint 1 | 25544-MSBA - MAUI - iOS - filter sidebar in store does not change for groups or filters | 25544-MSBA - MAUI - iOS - filter sidebar in store does not change for groups or filters | Amrit | Defect | Store: when the sidebar is open, selecting groups or filters does not present any new information within | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25624-MSBA - MAUI - close day has no data populated | 25624-MSBA - MAUI - close day has no data populated | Gursewak | Defect | Upon completing transactions (shift mode or externally) and going to close day with blind mode off, there are no values populated within the sales | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25644-MSBA - MAUI - Close day checks do not show for check reconciliation | 25644-MSBA - MAUI - Close day checks do not show for check reconciliation | Rupesh | Defect | Upon selecting a specific shift, if you then toggle the close out entire day, then untoggle it, you cannot continue forward. The continue button is disabled as if there is not a shift selected when there is. opening the dropdown and reselecting does not enable button. | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25618-MSBA - MAUI - Android - Close day count screen issues | 25618-MSBA - MAUI - Android - Close day count screen issues | Gursewak | Defect | On entering counts the following issues are found: Bills: if go over $100 anything past the decimal is cut off Coins: anything after 3 digits is cut off (similar as above, however this can have cents so it can hit this with amounts above 10) Check total: the number of checks to reconcile is cut off *note: upon moving forward or backward in the process and re-entering this screen, the amounts get fixed and show in ful | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25626-MSBA - MAUI - close day summary offset/short box is white | 25626-MSBA - MAUI - close day summary offset/short box is white | Jagdeep | Defect | Upon going through the close day workflow with the blind count off, the last page has the offset/short box white unlike all other boxes on page | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25623 MSBA - MAUI - if shift mode activated, badge appears behind clock for products added | 25623 MSBA - MAUI - if shift mode activated, badge appears behind clock for products added | Sambath | Defect | When you have the cart preview enabled for a tablet and you also have shift mode activated, upon adding an item to your cart, a badge appears behind the shift icon where the cart would be if the preview was not on 7/23 update: added screenshot from phone as even though the cart is enabled, the badge is still showing behind the clock | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25570-MSBA - MAUI - Android - Product page formatting issues | 25570-MSBA - MAUI - Android - Product page formatting issues | Jagdeep | Defect | Product detail formatting in Android has a few formatting issues: Stock option font small instead of matching font size of rest of page (ex price line) Web form title line not wrapping | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25564-MSBA - Android - transaction history page goes under device heading and navigation | 25564-MSBA - Android - transaction history page goes under device heading and navigation | Rupesh | Defect | When you have the transaction history menu open, the top bar goes under the notification/time etc, blocking some from being viewable The bottom navigation bar the icons are over the buttons in the app causing it to not be able to navigate Update: this may have to do with app switching | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25491-MSBA - MAUI - Icon Missing on Ters & Condition | 25491-MSBA - MAUI - Icon Missing on Ters & Condition | Amrit | Defect | When getting to terms and conditions page, the icon in the upper left corner is a ? instead of the image which was previously there. | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25583 -MSBA - MAUI - on opening edit meal payment and saving, it clears amount | 25583 -MSBA - MAUI - on opening edit meal payment and saving, it clears amount | Gursewak | Defect | If you have an amount in the other box, open the edit page from the cart preview, it opens the edit meal payment page. This shows the other amount properly. Upon hitting save, the cart preview shows that there is a 0.00 amount in the cart. Additionally if you have a preset amount selected and open and save, the cart is being cleared out as well. This is happening from cart or cart preview | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25479-MSBP - MAUI - image missing on add payment method screen | 25479-MSBP - MAUI - image missing on add payment method screen | Gursewak | Defect | Upon putting a valid CC number in (ex 4242 4242 4242 4242 which is Visa) the image changes from the basic credit card to an x in android and a ? in iOS | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25576-MSBA - MAUI - Add to cart button cut off when cart preview active | 25576-MSBA - MAUI - Add to cart button cut off when cart preview active | Jagdeep | Defect | In both portrait and landscape mode, the add to cart button for products is partially cut off when cart preview is active *note, the length of the item does not have any bearing as page scrolls behind button | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25586-MSBA - MAUI - Android - cart difficult to enter edit screens | 25586-MSBA - MAUI - Android - cart difficult to enter edit screens | Rupesh | Defect | When you are in the cart, the hitbox for items to be able to enter the edit screen is very small. It doesnt even appear to be the entire length of the product/invoice/student name | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 | 25640-MSBP-MAUI - iOS - Shows white screen on accessing links more than two times in Quick Links Section | 25640-MSBP-MAUI - iOS - Shows white screen on accessing links more than two times in Quick Links Section | Jagdeep | Defect | In Quick Links Section, On accessing links more than two times, displays white screen unable to proceed further | Major | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25577 MSBA - MAUI - promocode error message cut off | 25577 MSBP - MAUI - Events banner not showing the Event count in Homescreen" | Sambath | Defect | If promocode is not able to be applied, it is missing part of the messaging | Major | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25629 MSBA - MAUI - iOS - error message for clerk behind entry box | 25629 MSBA - MAUI - iOS - error message for clerk behind entry box | Jagdeep | Defect | When you are entering a new user as a clerk account, it requires additional approval from admin. Putting in an incorrect credential here, populates and error message however, this is populated behind the entry box. Upon completing correct credentials after that, you will get a success box and the original error box persists under it | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25616 MSBA - MAUI - Close day Icons missing/incorrect | 25616 MSBA - MAUI - Close day Icons missing/incorrect | Gursewak | Defect | Within the close day menu, the top bar which has indicators of the page you are on have what appear to be Chinese characters in Android and a ? within iOS | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25615 MSBA - MAUI - Android -shift mode typing phone number issue | 25615 MSBA - MAUI - Android -shift mode typing phone number issue | Amrit/Prem | Defect | When typing in the phone number box, upon next space, the line will take one input and return to the beginning of the section. 585-944-6156 turns into 859-615-6445 | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25572 MSBA - MAUI - invoice add to cart/remove button does not work | 25572 MSBA - MAUI - invoice add to cart/remove button does not work | Gursewak | Defect | On the main invoice page, selecting the add to cart to add entire invoice to cart does nothing. After adding invoices to the cart, the remove button which replaces the add is not selectable | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25549 MSBA - MAUI - phone - acknowledgements half page in landscape | 25549 MSBA - MAUI - phone - acknowledgements half page in landscape | Amrit | Defect | When in landscape the iphone is showing only half screen. Unable to test Android due to display defect | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25559 MSBA - MAUI - Android - Back arrow in product details cut off | 25559 MSBA - MAUI - Android - Back arrow in product details cut off | Rupesh | Defect | In product details only seeing partial arrow for tablet and phone in landscape and portrait. Shows as expected in invoices though looks to be a different icon weight. Seeing in Meals also. | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25558 MSBA - when signing in, if decline TOS and relog in, not presented with MFA | 25558 MSBA - when signing in, if decline TOS and relog in, not presented with MFA | Amrit | Defect | When I am signing in on a new install if I MFA in, decline TOS and get returned to the login screen, I am not re-prompted for MFA on next sign in. | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25829 MSBA - MAUI - no error message on bad login, can't log in after | 25829 MSBA - MAUI - no error message on bad login, can't log in after | Vaishnavi/Prem | Defect | Upon entering an incorrect password and selecting the Login button, nothing happens and no error is presenting, acting like nothing was input. Only later by showing the password was I able to determine that is why the page did not log in. Upon fixing the password, it cannot log in afterwards | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25666 MSBA - MAUI - Android Phone - Cannot scroll to see entire Close day start page | 25666 MSBA - MAUI - Android Phone - Cannot scroll to see entire Close day start page | Gursewak | Defect | When in Android phone, the Close Day process does not show the bottom of the screen where it states blind counts are on | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25565 MSBA - MAUI - Transaction history missing () indicating refund | 25565 MSBA - MAUI - Transaction history missing () indicating refund | Rupesh | Defect | When refunding a transaction, the amount is showing as -2.17 instead of (2.17) xamarin: | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25840 MSBA - MAUI - 'Successfully added invoice' message appears and disappears quickly in iOS after adding invoice to cart | 25840 MSBA - MAUI - 'Successfully added invoice' message appears and disappears quickly in iOS after adding invoice to cart | Jagdeep | Defect | In iOS, From Invoice screen, after adding invoice using 'Add to cart' button or selecting 'Add all to cart' button, 'Successfully added invoice' message appears and disappears quickly. | Minor | Manual | External | Inprogress | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25665 MSBA - MAUI - shift mode search bar cut off in landscape mode | 25665 MSBA - MAUI - shift mode search bar cut off in landscape mode | Gursewak | Defect | It appears when the device is in landscape more, the top value after searching is smaller and can cut off part of the information. In android the no results found is partially cut off but in both iOS and Android an actual searched value is smaller box- can appear to cut off in some screen sizes | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25814 MSBP - MAUI - Events banner not showing the Event count in Homescreen" | 25814 MSBP - MAUI - Events banner not showing the Event count in Homescreen" | Sambath | Defect | In MSBP Maui application, After logging in, the Events banner in home screen is showing as 'No upcoming events. Check back later!". But there are already 4 active events available. After refreshing twice , the Events banner is updated with the event count. | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25622 MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox] | 25622 MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox] | Jagdeep | Defect | If you have the tablet in landscape mode and add a product, then rotate to portrait, the cart preview is off the screen and cannot see the checkout button area | Minor | Manual | External | Open | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25620 MSBA - MAUI - Android - warning messages on close day missing margins | 25620 MSBA - MAUI - Android - warning messages on close day missing margins | Jagdeep | Defect | Within close day process when going to complete, both warning and confirmation messages are missing right margins | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25625 MSBA - MAUI - close day payment summary text is greyed out | 25625 MSBA - MAUI - close day payment summary text is greyed out | Jagdeep | Defect | When close day blind count is off and you go to the sales summary portion of the close day process, the values within the summaries are grey instead of black like xamarin | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25543 MSBA - MAUI - Android - Camera icon cut off in store and invoice search bars | 25543 MSBA - MAUI - Android - Camera icon cut off in store and invoice search bars | Jagdeep | Defect | When in the main store or invoice menus, the camera icon is cut off in both invoice and store screen. they are also formatted differently than the meals screen Note: Meals screen is darker but appears to have correct alignment. None of the 3 screens matches search bar style | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25571 MSBA - MAUI - Android - adding product to cart does not redirect | 25571 MSBA - MAUI - Android - adding product to cart does not redirect | Gursewak | Defect | Upon adding a product to the cart, there is no redirect to the main store page. Android is opening the cart preview pane (on first item added) but is not closing product detail. iOS shows the item added to cart preview before exiting and it does hang in this state for longer than expected, but does resolve. | Major | Manual | External | Open | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25493 MSBP - MAUI - On adding second student/district with tickets available, banner not showing | 25493 MSBP - MAUI - On adding second student/district with tickets available, banner not showing | Jagdeep | Defect | When a parent has an account with no tickets, and adds a student from a district which does, the Events banner on the home screen does not populate with the student. A pull to refresh or close/reopen is required before banner populates Additionally adding another student/district with more events is not updating the banner until a pull to refresh | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.2 M Sprint 1 Stretch | 25598 MSBA - MAUI - Android - Login page formatting issues | 25598 MSBA - MAUI - Android - Login page formatting issues | Gursewak | Defect | Upon looking at the login page, it appears that there is a difference in color and font weight when compared to Xamarin Check color & font weight (font weight more bold?). we use the same Roboto font in Maui that we had in Xamarin yet now appears a bit more bold. --if this differs in other areas of the app, we'll need to consider addressing & note where to solve. | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects

## 15.1 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet the expectations? | Comments
1 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Amrit | 49019 | 49019 - MSBP - Automation - Mappings for Automation - Add Student | Story Peer Review | 3 |  | 56 | 2025-07-25 | 2025-01-07 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43802 | 2025-07-28 | NA | Sambath | Merge date picker code into appium actions | NA | NA | NA | Cover Negative case also | NA | Pending review from Owen |  |  | Exceeds Expectation: Story - AC is clear, no doubts in the AC, no AC changes. The developer completed the story without depending on the PO
2 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Rupesh | 49021 | MSBP - Automation - Mappings for Automation - Cart | Story Completed | 1 |  | 4 | 2025-07-15 | 2025-08-08 | NA | NA | NA | Amrit | use wait appium not thread, use assert for test case success and fail | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43509 | 2025-07-22 | 2025-07-22 | Ashwin | NA | OWEN | NA | None of the tests will execute for me. They login and fail on the main page. Please make sure they run for you. | Completed | NA |  | Needs Improvement | Ac's were about cart items only, to reach to the cart page manual intervention was required, however client expectation was no manual intervention, so to meet the expectation, I had to automate additional steps as well to reach out to to the cart. | Meets Expectation: Developer has a few doubts in AC, checked with PO, and development completed without any AC change
3 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Vaishnavi | 49125 | MSBP - Automation - Mappings for Automation - Greenlight | Story Completed | 2 |  | 8 | 2025-07-23 | 2025-08-07 | NA | NA | NA | Jagdeep | 1. fix the formatting here. (alignment of lines)2. These lines should be uncommented. | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43728 | 2025-08-01 | 2025-08-14 | Ashwin | 1. Rename this method to something like DontShareAndRegister and move the collapse functionality as a separate method. Also the edit could be a separate method or check it only in one of the follows. No need to check the edit in both share and dont share flow. | OWEN | 2025-08-18 | NA | Completed | NA |  | Needs Improvement | Client has changed the AC after completing the development | Needs Improvement: AC Changes after development starts. If the PO missed any points
4 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Jagdeep | 49129 | MSBP - Automation - Mappings for Automation - Suggested Students workflow | Story Being Developed | 3 |  | 0 | 2025-07-30 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Development completed. Waiting for story 49019 to be merged which is currently under review pending from Client. Due to that this story is on hold.
5 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Sambath | 49041 | 49041 MSBP - Automation - Mappings for Automation - Scheduled Payments | Story Completed | 3 |  | 0 | NA | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43754?_a=files | 2025-08-06 | 2025-08-07 | Ashwin | NA | OWEN | NA | NA | NA | NA | NA | Exceeds Expectation
6 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Premkumar | 49384 | MSBP - Automation - Mappings for Automation - Special Links | Story Completed | 3 |  | 20 | 2025-08-04 | 2025-08-11 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43887?_a=files | 2025-08-11 | 2025-08-18 | Ashwin | NA | OWEN | 2025-08-18 | NA | NA | NA |  | Meets Expectation
7 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Vaishnavi | 49130 | MSBP - Automation - Mappings for Automation - Greenlight card | Story Peer Review | 3 |  | 23 | 2025-08-04 | 2025-08-13 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43890 | 2025-08-11 | NA | Ashwin | NA | OWEN | NA | NA | Completed | NA | Received few comments from owen. Script not working in Client's system due to some changes in landing page for this story | Meets Expectation
8 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Sambath/Premkumar | 25545 | 25545 MSBA - MAUI - store tiles overlap when cart preview is on | Defect Fixed | 3 |  | 14 | 2025-08-08 | 2025-08-11 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43913 | 2025-08-12 | 2025-08-13 | Ashwin | NA | Sean | NA | NA | NA | NA | NA | Exceeds Expectation
9 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Vaishnavi/Premkumar | 25541 | MSBA - MAUI - student search in product doing a double search | Defect Fixed | 2 |  | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation
10 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 | Amrit | 25544 | MSBA - MAUI - iOS - filter sidebar in store does not change for groups or filters | Defect Being Fixed | 2 |  | 19 | 2025-08-08 | 2025-08-19 | NA | NA | NA | NA |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43963 | 2025-08-18 | 2025-08-20 | ashwin | NA | NA | NA | NA | Cover Negative case also | NA | Its blocker from telerik third party control check online https://feedback.telerik.com/maui/1681880-unable-to-switch-by-tab-click-when-tabview-contains-a-collectionview-that-has-been-scrolled
11 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Jagdeep/Vaishnavi | 25664 | MSBA - MAUI - Close day unable to move forward with shift user selected after toggling entire day | Defect Fixed | 3 |  | 9 | 2025-08-08 | 2025-08-08 | NA | NA | NA | NA | NA | Pull Request 43861: jagdeep.singh/25664 MSBA-MAUI-Close day unable to move forward with shift use... | 2025-08-08 | 2025-08-09 | NA | NA | NA | NA | NA | Completed | NA |  | Exceeds Expectation
12 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Jagdeep/Prem | 25667 | MSBA - MAUI - Android - Close day keyboard deleting values crashes | Defect Fixed | 3 |  | 15 | 2025-08-11 | 2025-08-13 | NA | NA | NA | NA | NA | Pull Request 43943: jagdeep.singh/25667 MSBA-MAUI- Android Close day keyboard deleting values cra... | 2025-08-13 | NA | NA | NA | NA | NA | NA | Completed | NA |  | Exceeds Expectation
13 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Gursewak | 25624 | MSBA - MAUI - close day has no data populated | Defect Being Tested | 2 |  | 39 | 2025-08-11 | 2025-08-19 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44019?_a=files | 2025-08-19 | NA | NA | NA | NA | 2025-08-20 | NA | Completed | NA
14 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Rupesh/Prem | 25560 | MSBA - MAUI - Android - unable to load student in meals menu | Defect Fixed | 2 |  | 19 | 2025-08-12 | 2025-08-19 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43970 | 2025-08-19 | 2025-08-19 | Ashwin | NA | Avery | 2025-08-20 | NA | Completed | NA |  | Meets Expectation
15 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Sambath | 25596 | 25596 MSBA - MAUI - remember me not logging back in | Defect Fixed | 2 |  | 5 | 2025-08-13 | 2025-08-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Unable to reproduce this issue since its working as expected. May be will move to rejected. Moved back to backlog
16 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Jagdeep/Prem | 25557 | MSBA-MAUI - Android - Student name displays in cut off view for both Product Detail and Edit Product Detail Page | Defect Fixed | 1 |  | 4 | 2025-08-14 | 2025-08-14 | NA | NA | NA | NA | NA | Pull Request 43961: jagdeep.singh/MSBA-MAUI-Android-Student name displays in cut off view for bot... | 2025-08-14 | 2025-08-19 | Ashwin | NA | Avery | 2025-08-19 | Since the issue was for Android only, would the tablet padding negatively affect an iPad? | Completed | NA |  | Exceeds Expectation
17 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Sambath/Prem | 25539 | 25539 MSBA - MAUI - promocode field missing in cart | Defect Fixed | 2 |  | 9 | 2025-08-14 | 2025-08-18 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44002 | 2025-08-18 | 2025-08-18 | Ashwin | NA | Sean | 2025-08-18 | NA | Completed | NA |  | Exceeds Expectation
18 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Rupesh | 25644 | MSBA - MAUI - Close day checks do not show for check reconciliation | Story Being Tested | 2 |  | 5 | 2025-08-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Sambath/Vaishnavi | 25540 | 25540 MSBA - MAUI - cart total section formated incorrectly | Defect Fixed | 2 |  | 8 | 2025-08-14 | 2025-08-18 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44002 | 2025-08-18 | 2025-08-18 | Ashwin | NA | Sean | NA | NA | Completed | NA |  | Exceeds Expectation
20 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Premkumar | 25643 | MSBA - MAUI - shift start unresponsive | Defect Fixed | 3 |  | 2 | 2025-08-18 | 2025-08-18 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44002 | 2025-08-18 | 2025-08-18 | Ashwin | NA | NA | NA | NA | NA | NA |  | Exceeds Expectation
21 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Jagdeep/Prem | 25563 | MSBA - MAUI - cart preview/cart missing tax | Defect Fixed | 2 |  | 12 | 2025-08-14 | 2025-08-19 | NA | NA | NA | Sambath | NA | Pull Request 44032: jagdeep.singh/25563 MSBA-MAUI- cart preview/cart missing tax | 2025-08-19 | 2025-08-20 | Ashwin | NA | NA | NA | NA | Completed | NA
22 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Gursewak | 25618 | MSBA - MAUI - Android - Close day count screen issues | Defect Being Tested | 2 |  | 8 | 2025-08-19 | 2025-08-20 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44059 | 2025-08-20 | NA | NA | NA | NA | 2025-08-20 | NA | Completed | NA | Completed, ready for testing
23 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Jagdeep | 25626 | MSBA - MAUI - close day summary offset/short box is white | Defect Peer Review | 1 |  | 2 | 2025-08-20 | 2025-08-20 | NA | NA | NA | Rupesh | NA | Pull Request 44060: jagdeep.singh/25626-MSBA-MAUI-close day summary offsetshort box is white | 2025-08-20 | NA | NA | NA | NA | NA | NA | Completed | NA | Under Peer review.
24 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Sambath/Prem | 25623 | 25623 MSBA - MAUI - if shift mode activated, badge appears behind clock for products added | Defect Being Tested | 2 |  | 9 | 2025-08-20 | 2025-08-20 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44050 | 2025-08-20 | 2025-08-20 | Ashwin | NA | Sean | NA | NA | Completed | NA | NA | Exceeds Expectation
25 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Jagdeep/Prem | 25627 | MSBA - MAUI - Android - text cut off on Close day screen | Defect Fixed | 1 |  | 7 | 2025-08-20 | 2025-08-20 | NA | NA | NA | NA | NA | Pull Request 44051: jagdeep.singh/25627 MSBA-MAUI-Android-text cut off on Close day screen | 2025-08-20 | NA | NA | NA | NA | NA | NA | Completed | NA |  | Exceeds Expectation
26 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Jagdeep | 25570 | MSBA - MAUI - Android - Product page formatting issues | Defect Being Fixed | 2 |  | 7 | 2025-08-21 | 2025-08-21 | NA | NA | NA | NA | NA | Pull Request 44086: jagdeep.singh/25570 MSBA-MAUI-Android-Product page formatting issues | 2025-08-20 | NA | NA | NA | NA | NA | NA | Completed | NA | Under Peer review.
27 | MSB Mobile | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Rupesh | 25564 | MSBA - Android - transaction history page goes under device heading and navigation | Story Being Developed | 3 |  | 10 | 2025-08-21 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
28 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Amrit | 25491 | MSBA - MAUI - Icon Missing on Ters & Condition | Defect Peer Review | 1 |  | 0 | 2025-08-21 | 2025-08-22 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44076 | 2025-08-21 | 2025-08-22 | ashwin | NA | NA | NA | NA | NA | NA | POV done waiting to be merged
29 | MSB Mobile Kaleida | 2025-08-08 | 2025-08-21 | 15.1 M Sprint 3 Stretch | Gursewak | 25583 | MSBA - MAUI - on opening edit meal payment and saving, it clears amount | Story Peer Review | 1 |  | 6 | 2025-08-21 | 2025-08-22 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44105?_a=files | 2025-08-22 | NA | ashwin | NA | NA | NA | NA | NA | NA

## 15.1 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.1 M Sprint 3 | 25545 MSBA - MAUI - store tiles overlap when cart preview is on | 25545 MSBA - MAUI - store tiles overlap when cart preview is on | Sambath | Defect | When the cart preview is on, the products tiles overlap each other update: Android does this as well if the keyboard is opened in landscape and the device is rotated while leaving the keyboard open | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 | 25541-MSBA - MAUI - student search in product doing a double search | 25541-MSBA - MAUI - student search in product doing a double search | Onsite | Defect | Upon searching for the student, and selecting them from the dropdown- MSBA is searching for them a second time causing a no student found error. This is error was seen in xamarin only if someone selected the student, then selected enter to "search again" in error. | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 | 25544-MSBA - MAUI - iOS - filter sidebar in store does not change for groups or filters | 25544-MSBA - MAUI - iOS - filter sidebar in store does not change for groups or filters | Amrit | Defect | Store: when the sidebar is open, selecting groups or filters does not present any new information within | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25664-MSBA - MAUI - Close day unable to move forward with shift user selected after toggling entire day | 25664-MSBA - MAUI - Close day unable to move forward with shift user selected after toggling entire day | Jagdeep | Defect | Upon selecting a specific shift, if you then toggle the close out entire day, then untoggle it, you cannot continue forward. The continue button is disabled as if there is not a shift selected when there is. opening the dropdown and reselecting does not enable button | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25624-MSBA - MAUI - close day has no data populated | 25624-MSBA - MAUI - close day has no data populated | Gursewak | Defect | Upon completing transactions (shift mode or externally) and going to close day with blind mode off, there are no values populated within the sales | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25667- MSBA - MAUI - Android - Close day keyboard deleting values crashes | 25667- MSBA - MAUI - Android - Close day keyboard deleting values crashes | Jagdeep | Defect | If you are in close day in android and try to edit the values by selecting in the box, once the keyboard opens if you delete the values, the app crashes | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25560-MSBA - MAUI - Android - unable to load student in meals menu | 25560-MSBA - MAUI - Android - unable to load student in meals menu | Rupesh | Defect | Upon searching for a student we are able to see them, upon selecting student card, the screen does not load and present meal payments screen | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25557-MSBA-MAUI - Android - Student name displays in cut off view for both Product Detail and Edit Product Detail Page | 25557-MSBA-MAUI - Android - Student name displays in cut off view for both Product Detail and Edit Product Detail Page | Jagdeep | Defect | Android -> In Product Detail & Edit Product Detail Screen, Student name displays in cut off mode for Android. Attached a screenshot for reference. Phone & tablet both. Watermark below also affected ("Search by Name or ID") | Minor | Manual | External | Closed | Development | Relevantz QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25539- MSBA - MAUI - promocode field missing in cart | 25539- MSBA - MAUI - promocode field missing in cart | Sambath | Defect | When in the cart view of the app, the promocode box is missing. Check formatting of error messages also. | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25644-MSBA - MAUI - Close day checks do not show for check reconciliation | 25644-MSBA - MAUI - Close day checks do not show for check reconciliation | Rupesh | Defect | Upon selecting a specific shift, if you then toggle the close out entire day, then untoggle it, you cannot continue forward. The continue button is disabled as if there is not a shift selected when there is. opening the dropdown and reselecting does not enable button. | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25540- MSBA - MAUI - cart total section formated incorrectly | 25540- MSBA - MAUI - cart total section formated incorrectly | Sambath | Defect | n both Landscape and portrait the cart totals section is showing different information/format missing promocode (already called out in 25539) tax calculation (in other defect already) extra cart total heading total savings line though no promocode present subtotal, tax and total not right justified for numbers | Significant | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25643-MSBA - MAUI - shift start unresponsive | 25643-MSBA - MAUI - shift start unresponsive | Onsite | Defect | f you have shift mode enabled and try to checkout with no shift started, you trigger the would you like to start shift box. If you say start shift, but then back out of it, if you attempt to start a shift by going to the clock, the page opens but is stuck in a loading loop of some sort requiring a force close | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25563-MSBA - MAUI - cart preview/cart missing tax | 25563-MSBA - MAUI - cart preview/cart missing tax | Jagdeep | Defect | upon comparing cart from xamarin to maui, the same product is showing tax within xamarin and not Maui in both cart and cart preview views (does exist on checkout totals though) | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25618-MSBA - MAUI - Android - Close day count screen issues | 25618-MSBA - MAUI - Android - Close day count screen issues | Gursewak | Defect | On entering counts the following issues are found: Bills: if go over $100 anything past the decimal is cut off Coins: anything after 3 digits is cut off (similar as above, however this can have cents so it can hit this with amounts above 10) Check total: the number of checks to reconcile is cut off *note: upon moving forward or backward in the process and re-entering this screen, the amounts get fixed and show in ful | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25626-MSBA - MAUI - close day summary offset/short box is white | 25626-MSBA - MAUI - close day summary offset/short box is white | Jagdeep | Defect | Upon going through the close day workflow with the blind count off, the last page has the offset/short box white unlike all other boxes on page | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25623 MSBA - MAUI - if shift mode activated, badge appears behind clock for products added | 25623 MSBA - MAUI - if shift mode activated, badge appears behind clock for products added | Sambath | Defect | When you have the cart preview enabled for a tablet and you also have shift mode activated, upon adding an item to your cart, a badge appears behind the shift icon where the cart would be if the preview was not on 7/23 update: added screenshot from phone as even though the cart is enabled, the badge is still showing behind the clock | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25627-MSBA - MAUI - Android - text cut off on Close day screen | MSBA - MAUI - Android - text cut off on Close day screen | Jagdeep | Defect | Upon selecting the toggle for close out entire day, the entire text of "Deselect close out entire day to select a specific shift" is not shown | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25576MSBA - MAUI - Add to cart button cut off when cart preview active | MSBA - MAUI - Add to cart button cut off when cart preview active | Jagdeep | Defect | In both portrait and landscape mode, the add to cart button for products is partially cut off when cart preview is active *note, the length of the item does not have any bearing as page scrolls behind button | Major | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25570-MSBA - MAUI - Android - Product page formatting issues | 25570-MSBA - MAUI - Android - Product page formatting issues | Jagdeep | Defect | Product detail formatting in Android has a few formatting issues: Stock option font small instead of matching font size of rest of page (ex price line) Web form title line not wrapping | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25564-MSBA - Android - transaction history page goes under device heading and navigation | 25564-MSBA - Android - transaction history page goes under device heading and navigation | Rupesh | Defect | When you have the transaction history menu open, the top bar goes under the notification/time etc, blocking some from being viewable The bottom navigation bar the icons are over the buttons in the app causing it to not be able to navigate Update: this may have to do with app switching | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25491-MSBA - MAUI - Icon Missing on Ters & Condition | 25491-MSBA - MAUI - Icon Missing on Ters & Condition | Amrit | Defect | When getting to terms and conditions page, the icon in the upper left corner is a ? instead of the image which was previously there. | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects
| 15.1 M Sprint 3 Stretch | 25583 -MSBA - MAUI - on opening edit meal payment and saving, it clears amount | 25583 -MSBA - MAUI - on opening edit meal payment and saving, it clears amount | Gursewak | Defect | If you have an amount in the other box, open the edit page from the cart preview, it opens the edit meal payment page. This shows the other amount properly. Upon hitting save, the cart preview shows that there is a 0.00 amount in the cart. Additionally if you have a preset amount selected and open and save, the cart is being cleared out as well. This is happening from cart or cart preview | Major | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion regression defects

## 15.1 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Amrit | 48945 | MSBP - Automation - Mappings for Automation - Payment Methods | Story Completed | 3 |  |  | 2025-07-07 | 2025-08-07 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43305 | 2025-07-10 | 2025-07-18 | Ashwin | NA | OWEN | First Approval (19-07-2025). Second Approval (25-07-2025) | Replace it with WaitForElement on all Thread.sleeps in the PR - We should not be checking in this. Leave the appPath empty. | NA | NA | Merged by Owen
2 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Amrit | 49043 | 49043 MSBP - Automation - Mappings for Automation - Events | Story Completed | 2 |  |  | 2025-07-18 | 2025-08-07 | NA | NA | NA | Rupesh |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43536 | 23/7/2025 | 31/7/2025 | NA | Use Verify Text Method,Remove Comented Code | NA | 31/07/2025 | NA | NA | Change method name, make event name dynamic to choose for testing | Approved and merged.
3 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Amrit | 49019 | 49019 - MSBP - Automation - Mappings for Automation - Add Student | Story Peer Review | 8 |  |  | 2025-07-25 | 2025-01-07 | NA | NA | NA | Ashwin |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43802 | 2025-07-28 | NA | NA | Merge date picker code into appium actions | NA | NA | NA | Cover Negative case also | NA | Waiting for PR Review
4 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Gursewak | 48959 | MSBP - Automation - Mappings for Automation - Meal Money Page - Add Funds Functionality | Story Completed | 2 |  |  | 2025-07-15 | 2025-08-07 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43273 | 2025-07-15 |  | Ashwin | Can you use automation ID instead of Xpath and remove this if condition | OWEN |  | 1.This method you pass in the amount you want to add. Looking through this, it appears the tests is just pressing on everything. If we want to add $10. It should find the student, add just $10 and save. Then verify it was done. | NA
5 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Gursewak | 49059 | 49059 MSBP - Automation - Mappings for Automation - Meal Money Page - AutoPay Functionality | Story Completed | 3 |  |  | 2025-07-15 | 2025-08-07 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43513?_a=files https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43514?_a=files | 2025-07-22 | NA | Ashwin |  | NA | NA | NA | Completed | NA
6 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Jagdeep | 49101 | MSBP - Automation - Mappings for Automation - Request a Refund | Story Completed | 2 |  | 3 | 2025-07-14 | 2025-07-28 | NA | NA | NA | Amrit | NA | Pull Request 43438: 49101-MSBP-Automation-Mappings for Automation-Request a Refund | 2025-07-17 | 2025-07-22 | Ashwin | 1. Why are we checking ResourceNotFound here? 2. To Uncomment lines. | OWEN | 2025-07-30 | IF this is always going to be the current date, then this can be moved into the class method as a hardcoded date. If this is going to be adjustable, then we can put in the class method a check for this existence of this key and if it is there, use this value and if not, use current date. | Completed | NA
7 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Jagdeep | 49042 | MSBP - Automation - Mappings for Automation - Store | Story Completed | 5 |  | 21 | 2025-07-25 | 2025-08-05 | NA | NA | NA | Amrit | add wait for appium on place of thread sleep | Pull Request 43615: 49042 MSBP-Automation-Mappings for Automation-Store | 2025-07-28 | NA | Ashwin | NA | OWEN | 2025-08-06 | NA | NA | NA | Completed
8 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Premkumar | 49123 | MSBP - Automation - Mappings for Automation - Quick Links | Story Completed | 2 |  | 32 | 2025-07-18 | 2025-07-25 | NA | NA | NA | NA |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43574 | 2025-07-25 | 2025-07-25 | NA | NA | NA | NA | NA | NA | NA | POV with bavithra pending. Created PR.
9 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Premkumar | 49131 | MSBP - Automation - Mappings for Automation - Student information (4 dots) | Story Completed | 3 |  | 26 | 2025-07-28 | 2025-08-05 | NA | NA | NA |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43702 | 2025-07-31 | 2025-08-06 | Ashwin | NA | OWEN | 2025-08-05 | NA | NA | NA | Approved and merged by Owen
10 | MSB Mobile | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Rupesh | 48946 | MSBP - Automation - Mappings for Automation - Add Meal Money | Story Completed | 1 |  |  | 2025-07-02 |  | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43391 | 2025-07-16 | 2025-07-16 | Ashwin | NA | OWEN | NA | com.hss.enterprise.msb:id/NavigateBack is the id for the back button. | NA | NA | Pending review from Owen.
11 | MSB Mobile | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Rupesh | 49021 | MSBP - Automation - Mappings for Automation - Cart | Story Peer Review | 3 |  | 35 | 2025-07-15 |  | NA | NA | NA | Amrit | use wait appium not thread, use assert for test case success and fail | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43509 | 2025-07-22 | 2025-07-22 | Ashwin | NA | OWEN | NA | None of the tests will execute for me. They login and fail on the main page. Please make sure they run for you. | Completed | NA | Review pending from owen.
12 | MSB Mobile | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Sambath | 48182 | MSBP - Tickets - Maintaining the session from the mobile app to tickets | Story Completed | 1 |  | 12 | 2025-07-25 | 2025-07-24 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43562 | 2025-07-23 |  | Amrit | use assert for test case success and fail |  | NA | NA | NA | NA | Testing on hold due to some API issues. Waiting for the new API. Follow-up sessions after 1st to be added/related after (separate work item). there is additional PI work to complete for this piece.
13 | MSB Mobile | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Sambath | 49060 | 49060 MSBP - Automation - Mappings for Automation - Meal Money Page - Transfer Funds Functionality | Story Completed | 3 |  | 18 | 2025-07-14 | 2025-07-31 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43503 | 2025-07-22 | 2025-07-23 | Ashwin | NA | OWEN | NA | The methods should be written where you pass in the students to transfer money to and from. That info is what is used to perform the actions. This appears to be all hard coded in the methods. This should be so consolidated into one class method | NA | NA | Working on PR comments from Owen.
14 | MSB Mobile | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Vaishnavi | 49125 | MSBP - Automation - Mappings for Automation - Greenlight | Story Peer Review | 3 |  | 30 | 2025-07-23 |  | NA | NA | NA | Jagdeep | 1. fix the formatting here. (alignment of lines)2. These lines should be uncommented. | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43728 | 2025-08-01 |  | Ashwin |  | NA | NA | NA | Completed | NA | Due to AC changes, script needs to be modified.
15 | MSB Mobile | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 | Rupesh | 49039 | MSBP - Automation - Mappings for Automation - Pay Invoices | Story Completed | 5 |  | 26 | 2025-07-29 | 2025-08-05 | NA | NA | NA | Gursewak | 1: Remove extra spaces 2: Use "!" for remove warning messages after ToString() | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43776 | 2025-08-05 | 2025-08-05 | Ashwin | NA | OWEN | 2025-08-06 | NA | Completed | NA | Merged by Owen
16 | MSB Mobile Kaleida | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 Stretch | Jagdeep | 49129 | MSBP - Automation - Mappings for Automation - Suggested Students workflow | Story Being Developed | 8 |  | 29 | 2025-07-30 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Development in progress. Dependent on another automation story 49019 which needs to be completed first.
17 | MSB Mobile | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 Stretch | Sambath | 49041 | 49041 MSBP - Automation - Mappings for Automation - Scheduled Payments | Story Peer Review | 3 |  | 32 | 2025-07-29 | 2025-08-06 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43754?_a=files | 2025-08-06 | 2025-08-07 | Ashwin | NA | OWEN | NA | NA | NA | NA | Review pending from owen.
18 | MSB Mobile | 2025-07-25 | 2025-08-07 | 15.1 M Sprint 2 Stretch | Premkumar | 49384 | MSBP - Automation - Mappings for Automation - Special Links | Story Being Developed | 3 |  |  |  |  | NA | NA | NA | [12 empty] | Development in progress. Android completed. iOS is in progress.

## 15.0 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Vaishnavi | 48938 | MSBP Maui - Full Regression | Story Completed | 5 |  | 17 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Vaishnavi/Chandler(onsite dev) | 45983 | MSBP - Store - No Students on Account - Show District Wide Products | Story Completed | 2 |  | 2.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Jagdeep/Premkumar | 25190 | MSBA - MAUI - Forgot login | Defect Fixed | 1 |  | 6 | NA | NA | NA | NA | NA | Pull Request 43051: Fixed keyboard overlap issue on Login ad forgot login screen. | 27-06-25 | 2025-08-07 | Ashwin | If this is used only for iOS can you add #if IOS condition here | Avery | 2025-08-07 | Since there's no corresponding Android handler this can go in the platforms/iOS to keep things neater and the iOS directives can be removed. Just be mindful of the namespace with for the USING in the basecontentpage | NA | NA
4 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Gursewak/Premkumar | 25380 | MSBA - MAUI - Unable to login after logout | Defect Fixed | 2 |  | 7.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42766 | 2025-06-11 | 2025-06-26 | 1
5 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Premkumar | 48944 | MSBP - Automation - Mappings for Automation - Messages | Story Being Developed | 5 |  | 5 | [15 empty] | Completed on adding the automation ID. And started writing the automation test cases for the same
6 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Gursewak | 48959 | MSBP - Automation - Mappings for Automation - Meal Money Page - Add Funds Functionality | Story Being Developed | 5 |  | 62 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43273?path=/Mobile%20Automation/src/Mobile%20Parent/MealMoney.cs https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43274?_a=files&path=/MSB.Parent/Pages/AddFundsPage.xaml | 2025-07-09 |  | 3 | Amrit, Jagdeep, Ashwin | [5 empty] | Need to change code according to aswin suggest to all developers
7 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Amrit | 48945 | MSBP - Automation - Mappings for Automation - Payment Methods | Story Peer Review | 5 |  | 37 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43305 | 2025-07-10 |  |  |  | OWEN | NA |  |  |  | Development completed. 2 days was blocked because of firewall, PR is create
8 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Jagdeep | 48943 | MSBP - Automation - Mappings for Automation - Payment History | Story Peer Review | 5 |  | 20 | NA | NA | NA | NA | NA | Pull Request 43125: Created test case for PaymentHistory. | 2025-07-02 | 2025-07-05 | Ashiwn | NA | Owen | NA | what are all these long sleeps for? Couldn't we use wait for appium element instead. | NA | NA | Start work on it again after client comments on PR.
9 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Rupesh | 48946 | MSBP - Automation - Mappings for Automation - Add Meal Money | Story Being Developed | 5 | 5 | 22 | NA | NA | NA | NA | NA |  | NA | NA |  | NA |  | NA |  | NA |  | Completed the Settings flow with both notifications and purchase control. Bottom sheet issue with iOS, working fine in Android.
10 | MSB Mobile | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Vaishnavi | 25509 | MSBP - Maui - Unable to enter value '0' after decimal point in Mealmoney and Invoice partial amount 15.0 (Regression) | Defect Fixed | 0 |  | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 | Jagdeep | 48942 | MSBP - Automation - Mappings for Automation - Contact Us | Story Peer Review | 5 |  | 17 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43170 | 2025-06-04 | 2025-06-09 | Ashwin | NA | Owen | NA | NA | NA | NA | Peer review in progress by client.
12 | MSB Mobile | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Sambath/Premkumar | 25191 | MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Defect Fixed | 2 |  | 16.5 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43230 | 2025-07-08 | 2025-07-08 | Ashwin | NA | NA | NA | NA | NA | NA | Testing in progress.
13 | MSB Mobile | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Sambath | 46156 | 46156 MSBP - Tickets - Event Details | Story Completed | 3 | 3 | 13 | NA | NA | NA | Amirt | move to resource file | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43070 | 2025-07-02 | 2025-07-02 | Avery | NA | NA | NA | NA | NA
14 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Rupesh/Premkumar | 48807 | MSBA - Maui - Cart - Edit Product Cart Items | Story Peer Review | 2 | 3 | 15 | NA | NA | NA | Sambath | Device.StartTimer is depreciated, please use alternate suggestion | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43099 | 2025-07-02 | 2025-07-03 | Avery | Since you're using a contentview that contains these resources this isn't needed here, Comment out this HeaderTemplate, demo mode is not implemented | NA | NA |  |  |  | Bouncebacks fixed by the developer. Yet to be deployed to QA.
15 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Jagdeep/Premkumar | 25178 | MSBA - MAUI -Store screen -filters not filling the whole screen | Defect Fixed | 1 |  | 1 | NA | NA | NA | Prem | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42996 | 24/06/2025 | 2025-02-07 | Avery | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Sambath | 46155 | 46155 MSBP - Tickets - Upcoming Events Screen | Story Completed | 2 | 2 | 19 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43161 | 2025-07-04 | 2025-07-07 | Avery | NA | NA | NA | NA | NA | NA | Testing in progress by Onsite QA.
17 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Avery/Premkumar | 48871 | MSBA - MAUI - Edit Meals in Cart | Story Completed | 2 |  | 11.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed.
18 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Amrit | 48956 | MSBP - Automation - Mappings for Automation - Profile - Additional IDs | Story Completed | 1 |  | 5 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43056?_a=files | 2025-06-27 | NA | Owen | NA | Avery | NA | NA | NA | NA | Peer review in progress by client.
19 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Jagdeep | 49063 | MSBP - Automation - Profile - Update Automation Framework to use IDs instead of XPath | Story Completed | 2 |  | 4 | NA | NA | NA | NA | NA | Pull Request 43224: Used AutomationId instead of Xpath. | 2025-07-08 | 2025-07-09 | Ashwin | NA | Owen | NA | NA | NA | NA | Tested and approved by client.
20 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Jagdeep | 49062 | MSBP - Automation - Login - Update Automation Framework to use IDs instead of XPath | Story Peer Review | 4 |  | 15 | NA | NA | NA | Sambath | NA | Pull Request 43249: 49062-Automation-Login-Update Automation Framework to use IDs instead of XPath | 2025-07-08 | 2025-07-09 | [7 empty] | Peer review in progress by client.
21 | MSB Mobile Kaleida wave | 2025-06-26 | 2025-07-10 | 15.0 M Sprint 3 Stretch | Amrit | 48965 | 48965 MSBP - Automation - Mappings for Automation - Login - Additional IDs | Story Completed | 1 |  | 7 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43056?_a=files | 2025-06-27 | NA | Owen | NA | Avery | NA | NA | NA | NA | Tested and approved by client.

## 15.1 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Premkumar | 48944 | MSBP - Automation - Mappings for Automation - Messages | Story Completed | 3 |  | 20 | 2025-07-08 | 2025-07-15 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43344 | 2025-07-14
2 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Gursewak | 48959 | MSBP - Automation - Mappings for Automation - Meal Money Page - Add Funds Functionality | Story Peer Review | 2 |  | 40 | 2025-07-15 | 2025-07-24 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43273 | 2025-07-15 |  | Ashwin | Can you use automation ID instead of Xpath and remove this if condition | OWEN |  | 1.This method you pass in the amount you want to add. Looking through this, it appears the tests is just pressing on everything. If we want to add $10. It should find the student, add just $10 and save. Then verify it was done. |  |  | Received comments from Owen. Will be working on that.
3 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Amrit | 48945 | MSBP - Automation - Mappings for Automation - Payment Methods | Story Peer Review | 3 |  | 29 | 2025-07-07 | 2025-07-15 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43305 | 2025-07-10 | 2025-07-18 | Ashwin | NA | OWEN | First Approval (19-07-2025) | Replace it with WaitForElement on all Thread.sleeps in the PR - We should not be checking in this. Leave the appPath empty. | NA | NA | Sent for review(Owen)
4 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Jagdeep | 48943 | MSBP - Automation - Mappings for Automation - Payment History | Story Completed | 3 |  | 10 | 2025-06-30 | 2025-07-21 | NA | NA | NA | NA | NA | Pull Request 43125: Created test case for PaymentHistory. | 2025-07-02 | 2025-07-16 | Ashwin | Resolved The dictionary should be formed by getting the text from the UI and not hardcoded like Jane0001 | OWEN | 2025-07-22 | This does not look correct com.hss.enterprise.msb:id/NavigateBack is the id for the back button. | Completed |  | Completed
5 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Rupesh | 48946 | MSBP - Automation - Mappings for Automation - Add Meal Money | Story Peer Review | 3 |  | 21 | 2025-07-02 | 2025-07-15 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43391 | 2025-07-16 | 2025-07-16 | Ashwin | NA | OWEN | NA | com.hss.enterprise.msb:id/NavigateBack is the id for the back button. | NA | NA | Got comments from owen. As login part is not working, unable to push the changes for this story.
6 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Jagdeep | 48942 | MSBP - Automation - Mappings for Automation - Contact Us | Story Completed | 1 |  | 9 | 2025-07-04 | 2025-07-18 | NA | NA | NA | NA | NA | Pull Request 43170: Mappings for Automation - Contact Us | 2025-07-04 | 2025-07-15 | Ashwin | NA | OWEN | 2025-07-19 |  | Completed | NA | Completed
7 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Rupesh/Premkumar | 48807 | MSBA - Maui - Cart - Edit Product Cart Items | Story Completed | 0.5 |  | 8 | NA | NA | NA | NA | NA | Ashwin | format it so that there is space above the declaration and also indent it properly for readability. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43297 | 2025-02-07 | 2025-03-07 | Avery | NA | NA | 2025-07-15 |  | NA | NA | Completed
8 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Jagdeep | 49062 | MSBP - Automation - Login - Update Automation Framework to use IDs instead of XPath | Story Completed | 0.5 |  | 4 | 2025-07-08 | 2025-07-21 | NA | NA | NA | NA | NA | Pull Request 43249: 49062-Automation-Login-Update Automation Framework to use IDs instead of XPath | 2025-07-09 | 2025-07-16 | Ashwin | Are these commented lines of code needed? | OWEN | 2025-07-16 |  | Completed | NA | Completed
9 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Vaishnavi | 48870 | MSBA - MAUI - Edit Invoices From Cart | Story Completed | 2 |  | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA
10 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Vaishnavi | 42140 | MSBA - Maui - Scanner Wizard - Latest Socket .NET MAUI Package Integration | Story Completed | 1 |  | 19 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Sambath | 48182 | MSBP - Tickets - Maintaining the session from the mobile app to tickets | Story Peer Review | 3 |  | 15 | 2025-07-03 | 2025-07-23 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43562 | 2025-07-23 |  | Amrit | use assert for test case success and fail |  | NA | NA | NA | NA | Delayed to work on this sotry due to the AC not proper. - Dev was completed and now it was in internal peer review
12 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Rupesh | 49021 | MSBP - Automation - Mappings for Automation - Cart | Story Being Developed | 5 |  | 23 | 2025-07-15 | 2025-07-21 | NA | NA | NA | Amrit | use wait appium not thread, use assert for test case success and fail | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43509 | 2025-07-22 | 2025-07-22 | Ashwin | NA | OWEN | NA | None of the tests will execute for me. They login and fail on the main page. Please make sure they run for you. | Completed | NA | Owen had mentioned that there should be no manual intervention for Add to Cart, and that this flow should be covered as part of automation. However, the Add to Cart flow is actually part of a separate story and is not covered under this one. To achieve the complete end-to-end automation as expected, it would require coverage across 3 separate stories, and currently, this particular acceptance criteria does not include it. Need further discussion on this. Note - From now on Team chooses indicators based on independent stories without waiting for dependencies. They also build on already completed stories to continue the app flow efficiently.
13 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Vaishnavi | 49160 | REG - MSBP CA - Prod Smoke Test Against Staging RC | Story Completed | 1 |  | 3.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Sambath | 49060 | 49060 MSBP - Automation - Mappings for Automation - Meal Money Page - Transfer Funds Functionality | Story Peer Review | 3 |  | 45 | 2025-07-14 | 2025-07-23 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43503 | 2025-07-22 | 2025-07-23 | Ashwin | NA | OWEN | NA | The methods should be written where you pass in the students to transfer money to and from. That info is what is used to perform the actions. This appears to be all hard coded in the methods. | NA | NA | Development completed. Created PR and waiting for review from client(Owen)
15 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Vaishnavi | 25524 | MSBP - MAUI - account creation confirm password not validating on return (regression) | Story Completed | 2 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 | Gursewak | 49059 | 49059 MSBP - Automation - Mappings for Automation - Meal Money Page - AutoPay Functionality | Story Peer Review | 5 |  | 49 | 2025-07-15 | 2025-07-22 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43513?_a=files https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43514?_a=files | 2025-07-22 | NA | Ashwin |  | NA | NA | NA | Completed | NA
17 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 Stretch | Amrit | 49043 | 49043 MSBP - Automation - Mappings for Automation - Events | Story Peer Review | 3 |  | 13 | 2025-07-18 |  | NA | NA | NA | Rupesh |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43536 | 23/7/2025 | NA | NA | Use Verify Text Method,Remove Comented Code | NA | NA | NA | NA | NA
18 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 Stretch | Jagdeep | 49101 | MSBP - Automation - Mappings for Automation - Request a Refund | Story Peer Review | 5 |  | 32.5 | 2025-07-14 | 2025-07-23 | NA | NA | NA | Amrit | NA | Pull Request 43438: 49101-MSBP-Automation-Mappings for Automation-Request a Refund | 2025-07-17 | 2025-07-22 | Ashwin | Why are we checking ResourceNotFound here? | OWEN | NA | NA | Completed | NA | PR created and sent for review(Owen)
19 | MSB Mobile Kaleida | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 Stretch | Premkumar | 49123 | MSBP - Automation - Mappings for Automation - Quick Links | Story Being Developed | 3 |  | 21 | 2025-07-18 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Working on Android setup test cases. iOS completed.
20 | MSB Mobile | 2025-07-11 | 2025-07-24 | 15.1 M Sprint 1 Stretch | Vaishnavi | 49125 | MSBP - Automation - Mappings for Automation - Greenlight | Story Being Developed | 3 |  | 18 | 2025-07-23 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Facing issues with build. Will be checking with Team and start working on this.

## 15.0 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 48364 | REG - MSBA - Regression | Story Completed | 5 | 1.125 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Rupesh/Premkumar | 25195 | MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Defect Fixed | 0.5 | 0.25 | 1 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42789 | 2025-06-12 | 2025-06-12 | Sean | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Jagdeep/Premkumar | 25183 | MSBA - MAUI - App not force logging out on time out | Defect Fixed | 1 | 0.5 | 2 | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Rupesh/Premkumar | 25198 | MSBA - MAUI - Invoice Details - Payment options pop up | Defect Fixed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42696 | 2025-06-09 | 2025-06-12 | Sean | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Sambath/Vaishnavi | 25359 | 25359 MSBP - MAUI - checkout not respecting promocode flag (15.0) | Story Completed | 1 | 0.125 | 0.5 | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Jagdeep | 25190 | MSBA - MAUI - Forgot login | Defect Peer Review | 0.5 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
7 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Gursewak | 25380 | MSBA - MAUI - Unable to login after logout | Defect Peer Review | 1 | 3.5 | 14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
8 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Sambath/Vaishnavi | 25414 | MSBP - MAUI - Resource not found in store filters (15.0) | Defect Fixed | 1 | 1.25 | 5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42842 | 2025-06-13 | 2025-06-13 | Sean | NA | N A | NA | NA | NA | NA
9 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Premkumar | 25202 | MSBA - MAUI - TXN History | Defect Fixed | 0.5 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Sambath/Premkumar | 25199 | 25199 MSBA - MAUI - Invoice Details - Payment options pop up - Alignment | Defect Fixed | 2 | 1.87 | 7.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42868 | 2025-06-16 | 2025-06-17 | Ashwin | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 48632 | MSBP CA - MAUI Regression | Story Completed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Sambath | 25427 | 25427 MSBA - Xamarin - Payment summary not showing the balance amount in receipt screen when printer is not connected (Regression) (14.7) | Defect Fixed | 2 | 5 | 20 | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Sambath/Vaishnavi | 25456 | 25456 MSBP - MAUI - Filter option not working in store 15.0 | Defect Fixed | 0 | 0.6 | 2.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42911 | 2025-06-18 | 2025-06-18 |  | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 25445 | MSBP- MAUI - Android_Total, Paid and Remaining balance field amounts are not aligned properly in Invoice payment option screen (regression) (15.0) | Defect Fixed | 0 | 0.125 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 25418 | MSBP - MAUI - iOS - sheet issue on invoice auto pay subscription(regression) (14.7) | Defect Fixed | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 25416 | MSBP - MAUI - no +Add Student on homepage of suggested student type account (15.0) | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
17 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 25414 | MSBP - MAUI - Resource not found in store filters (15.0) | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
18 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 25378 | MSBP - MAUI - Android - promotion code field not aligned (15.0) | Defect Fixed | 0.5 | .12`5 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 25367 | MSBP - MAUI - suggested student workflow does not reach final page if middle page navigates to inputs (15.0) | Defect Fixed | 0.5 | 0.125 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
20 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Gurserwak/Premkumar | 25197 | MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | Defect Fixed | 1 | 2 | 8 | NA | NA | NA | NA | NA |  |  |  | NA | NA | NA | NA | NA | NA | NA
21 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 45983 | MSBP - Store - No Students on Account - Show District Wide Products | Story Being Tested | 5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
24 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 25440 | MSBP CA - MAUI - Unable to enter CA Postal code while adding payment methods (Regression) | Defect Fixed | 0 | 1.125 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
23 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 | Vaishnavi | 25406 | MSBP - MAUI - Allows user to enter more values in the amount field. Maximum value limit is not been set (15.0) | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
32 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 Stretch | Jagdeep | 25178 | MSBA - MAUI -Store screen -filters not filling the whole screen | Story Peer Review | 2 | 3 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
25 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 Stretch | Vaishnavi | 25420 | MSBP - MAUI - iOS - invoice information sheet the header/back button not at top of page (15.0) | Defect Fixed | 1 | 0.125 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
26 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 Stretch | Vaishnavi | 25431 | MSBP - MAUI - iOS - invoice screen continues to scroll for an entire page past last information (15.0) | Defect Fixed | 0 | 0.125 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
27 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 Stretch | Amrit/Premkumar | 25191 | MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Defect Being Fixed | 2 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
28 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 Stretch | Premkumar | 25201 | MSBA - MAUI - Add to Cart - Android - expand/collapse only works when you drag a list item first | Defect Fixed | 2 | 1.75 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
29 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 Stretch | Sambath | 46156 | 46156 MSBP - Tickets - Event Details | Story Being Developed | 5 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
30 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 Stretch | Vaishnavi | 42146 | MSBA - Maui - Tickets | Story Completed | 1 | 0.375 | 1.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
31 | MSB Mobile | 2025-06-13 | 2025-06-25 | 15.0 M Sprint 2 Stretch | Rupesh | 48807 | MSBA - Maui - Cart - Edit Product Cart Items | Story Peer Review | 3 | 1.25 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint

## 15.1 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments

## 15.1 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.1 M Sprint 1 | 48870 MSBA - MAUI - Edit Invoices From Cart | 48870 MSBA - MAUI - Edit Invoices From Cart | Onsite | Bounceback/Sub-Defect | 1.IOS - While editing invoice from cart, selected partial amount field and tried editing the amount. When select X from that field, the keypad freezes and unable to do any actions 2.Android - upon selecting X icon, it does not clears the amount in the partial amount field. Just closes the keypad. | Major | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to MAUI conversion
| 15.1 M Sprint 1 | 48807 MSBA - Maui - Cart - Edit Product Cart Items | 48807 MSBA - Maui - Cart - Edit Product Cart Items | Onsite | Bounceback/Sub-Defect | 1. Checkout button is in enable mode on setting quantity more than 15 2. Edit Product Detail Page -> Validation should show instantly on increasing the quantity. Refer the attached video | Major | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to MAUI conversion
| 15.1 M Sprint 1 | 42140 MSBA - Maui - Scanner Wizard - Latest Socket .NET MAUI Package Integration | 42140 MSBA - Maui - Scanner Wizard - Latest Socket .NET MAUI Package Integration | Onsite | Bounceback/Sub-Defect | 1. I/A - After enabling ‘barcode scanner’ in setting screen, the scanner configuration is not showing configuration information. PFA for reference. 2. I/A - Scanner configuration UI is not matching the Xamarin. < > button are given at the screen 1 3. I - app crashes when < or > button is selected. 4. A - Selecting X form scanner configuration, the Barcode scanner button is still enabled. If trying to toggle it off, it reopens the scanner configuration menu. 5. I/A - icon is missing between X and Scanner configuration text. PFA for reference. 6. I/A - Student information is not populating when scanning the student barcode in Store/Invoice/meals 7. A- Products information not showing when barcode is scanned | Major | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to MAUI conversion

## 15.0 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.0 M Sprint 3 | 25190 MSBA - MAUI - Forgot login | 25190 MSBA - MAUI - Forgot login | Jagdeep | Defect | phone/tablet - In IOS Xamarin, on some screens, when keyboard was in use the Next button would move above keyboard. In both IOS and Android Maui, the keyboard now blocks the Next button. check to see if this is a limitation of Maui as this was working in IOS Xamarin. consistent through the app notes from Refinement: review Login here only new defects if this issue is located other places | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to MAUI conversion
| 15.0 M Sprint 3 stretch | 25191 MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | 25191 MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Sambath | Defect | phone/tablet - different package is needed for barcode scanning consider all four platforms Update Package and Verify Testing note: this will include product images and barcodes open within products for students as well | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to MAUI conversion
| 15.0 M Sprint 3 stretch | 25178 MSBA - MAUI -Store screen -filters not filling the whole screen | 25178 MSBA - MAUI -Store screen -filters not filling the whole screen | Jagdeep | Defect | Store screen -filters not filling the whole screen | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to MAUI conversion
| 15.0 M Sprint 3 | 25380 MSBA - MAUI - Unable to login after logout | 25380 MSBA - MAUI - Unable to login after logout | Gurusewak | Defect | Unable to login after logging out of the app testing note scenarios that log out: using logout button, immediately logging back in using logout button, closing app completely and then logging back in closing app which ends session and logging back in | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to MAUI conversion
| 15.0 M Sprint 3 | 25509-MSBP - Maui - Unable to enter value '0' after decimal point in Mealmoney and Invoice partial amount 15.0 (Regression) | 25509-MSBP - Maui - Unable to enter value '0' after decimal point in Mealmoney and Invoice partial amount 15.0 (Regression) | Onsite | Defect | Unable to enter value '0' after decimal point in Mealmoney and Invoice partial amount 15.0 (Regression) | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to MAUI conversion
| 15.0 M Sprint 3 stretch | 48807 MSBA - Maui - Cart - Edit Product Cart Items | 48807 MSBA - Maui - Cart - Edit Product Cart Items | Rupesh | Bounceback/Sub-Defect | Checkout button is in enable mode on setting quantity more than 15 | Minor | Manual | Internal | Inprogress | Development | Relevantz QA | Xamarin to MAUI conversion

## 15.0 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.0 M Sprint 2 | 25183 MSBA - MAUI - App not force logging out on time out | 25183 MSBA - MAUI - App not force logging out on time out | Jagdeep Singh | Defect | phone/tablet -Where: endpoint calls, Like MSBP, when user is timed out, need to force user out to Login | Significant | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25190 MSBA - MAUI - Forgot login | 25190 MSBA - MAUI - Forgot login | Jagdeep Singh | Defect | Phone/tablet - In IOS Xamarin, on some screens, when keyboard was in use the Next button would move above keyboard. In both IOS and Android Maui, the keyboard now blocks the Next button. check to see if this is a limitation of Maui as this was working in IOS Xamarin.consistent through the app | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25380 MSBA - MAUI - Unable to login after logout | 25380 MSBA - MAUI - Unable to login after logout | Jagdeep Singh | Defect | Unable to login after logging out of the app | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25197 MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | 25197 MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | Gursewak Singh | Defect | iOS - phone - More space between Partial Amount checkbox label and the amount entry field | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25195 - MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | 25195 - MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Rupesh | Defect | phone/tablet - Payment options pop up - | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25198 MSBA - MAUI - Invoice Details - Payment options pop up | 25198 MSBA - MAUI - Invoice Details - Payment options pop up | Rupesh | Defect | iPad - Able to enter alphabets and special characters in the amount entry field (unlike the Xamarin app, per Dev this is a common issue found in iPad across the Maui application for the amount entry fields Ex: product details page ‘Price’ entry field ) This likely affects anywhere with an entry field including meal payments (dev to document and list & communicate with QA the affected areas). Likely solved by numeric only keyboard behavior (deletes anything that's not a number). https://learn.microsoft.com/en-us/dotnet/communitytoolkit/maui/behaviors/numeric-validation-behavior | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25359 MSBP - MAUI - checkout not respecting promocode flag (15.0) | 25359 MSBP - MAUI - checkout not respecting promocode flag (15.0) | Sambath | Defect | When the system flag for promocodes is disabled, still able to see the promocodes box in Maui where we are not seeing it in xamarin | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25201 - MSBA - MAUI - Add to Cart - Android - expand/collapse only works when you drag a list item first | 25201 - MSBA - MAUI - Add to Cart - Android - expand/collapse only works when you drag a list item first | Onsite | Defect | phone/tablet - For the MAUI add to cart story that is working on the expand and collapse is not working as expected in android device, it working only when you drag the list item after expand or collapse as shown in the below recording. But its working as expected in iOS device without dragging. The issue seems to be that the Telerik listview control with grouping is not behaving as expected in Android. Also the swipe to delete in this control is not functioning as expected. We tried few work arounds but its not working as expected and we are blocked on this. Should we table it now as a known issues that needs to be fixed later in the list we maintain? | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25414 MSBP - MAUI - Resource not found in store filters (15.0) | 25414 MSBP - MAUI - Resource not found in store filters (15.0) | Sambath | Defect | Upon looking at store filters this morning, ran into the intermittent issue where it states that the resource is not found within the store filters. Items which stated this were the header (filters) the clear filters, and the show items button | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25202 MSBA - MAUI - TXN History | 25202 MSBA - MAUI - TXN History | Onsite | Defect | phone/tablet - The "Options" buttons is available in Xamarin forms app, but not available in MAUI's Grid control. | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25199 MSBA - MAUI - Invoice Details - Payment options pop up - Alignment | 25199 MSBA - MAUI - Invoice Details - Payment options pop up - Alignment | Sambath | Defect | OS (phone/tablet) - Watermark text ‘Amount’ in the Partial Amount entry field is not aligned along with the cursor Common control - other areas will need to be checked. Dev: add these other areas below and communicate with team/QA in order to determine the scope of test effort. | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25427 MSBA - Xamarin - Payment summary not showing the balance amount in receipt screen when printer is not connected (Regression) (14.7) | 25427 MSBA - Xamarin - Payment summary not showing the balance amount in receipt screen when printer is not connected (Regression) (14.7) | Sambath | Defect | In MSBA Staging 14.7 Xamarin version, the After completing transaction using payment type as 'Cash requiring change, the payment summary receipt screen is not showing balance amount more than bill amount is paid through cash Attached video for reference. | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25456 MSBP - MAUI - Filter option not working in store 15.0 | 25456 MSBP - MAUI - Filter option not working in store 15.0 | Sambath | Defect | In MSBP MAUI, under Store, select the filter and make any product selection. Then click on 'show items' items not listed. select clear filters, selection not cleared. | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25445 MSBP- MAUI - Android_Total, Paid and Remaining balance field amounts are not aligned properly in Invoice payment option screen (regression) (15.0) | 25445 MSBP- MAUI - Android_Total, Paid and Remaining balance field amounts are not aligned properly in Invoice payment option screen (regression) (15.0) | Onsite | Defect | MSBP CA - Maui - Android. - In Invoice payment option screen, the Totao, Paid and Remaining balance field amount are misaligned. Refer screenshot for reference. | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25418_MSBP - MAUI - iOS - sheet issue on invoice auto pay subscription(regression) (14.7) | 25418_MSBP - MAUI - iOS - sheet issue on invoice auto pay subscription(regression) (14.7) | Onsite | Defect | If you go into invoices where there is an invoice autopay subscription and turn it on, then before leaving the details page select the toggle to turn the auto pay off, it has the turn off auto pay warning- however the no, leave on button is under the screen fold | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25416 MSBP - MAUI - no +Add Student on homepage of suggested student type account (15.0) | 25416 MSBP - MAUI - no +Add Student on homepage of suggested student type account (15.0) | Onsite | Defect | Upon opening an account with suggested students and selecting later, there is no button to add students on home page If students are added on this account and then deleted, there is not add students button on the removal of the last student (this does work on other accounts which have students added but not through suggested workflow) | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25378 MSBP - MAUI - Android - promotion code field not aligned (15.0) | 25378 MSBP - MAUI - Android - promotion code field not aligned (15.0) | Onsite | Defect | When applying a promocode, the amount is not right justified like iOS and all other money amounts on the screen | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25367 MSBP - MAUI - suggested student workflow does not reach final page if middle page navigates to inputs (15.0) | 25367 MSBP - MAUI - suggested student workflow does not reach final page if middle page navigates to inputs (15.0) | Onsite | Defect | When accessing the suggested student workflow it should be list of students>notification/meal settings> done/add more student sheet If on the settings screen, you select the amount to change and navigate to the numerical input screen, upon navigating back and selecting next it loads the home page and never shows the final step of the process | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25440 MSBP CA - MAUI - Unable to enter CA Postal code while adding payment methods (Regression) | 25440 MSBP CA - MAUI - Unable to enter CA Postal code while adding payment methods (Regression) | Sambath | Defect | MSBP CA - In Maui application, while adding a payment method I selected state as 'Alberta, Canada' and CA postal code as 'T4A 0N2' but only 5 digits are allowed to enter in Postal code field. Checked in Xamarin, it is allowing to enter 6 digit postal code for the state Alberta, Canada. | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25406 MSBP - MAUI - Allows user to enter more values in the amount field. Maximum value limit is not been set (15.0) | 25406 MSBP - MAUI - Allows user to enter more values in the amount field. Maximum value limit is not been set (15.0) | Onsite | Defect | In MSBP Maui - When user tries to enter amount on Partial amount field in Invoice, It allows user to enter more digits than the maximum invoice amount. Same behaviour happening in below areas as well Meal Money - Add meal money in 'Other' field. Refund Request - Adding amount in refund amount. Store - Add product 'user set price' and try entering amount. It allows user to enter many digits | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25420 MSBP - MAUI - iOS - invoice information sheet the header/back button not at top of page (15.0) | 25420 MSBP - MAUI - iOS - invoice information sheet the header/back button not at top of page (15.0) | Onsite | Defect | in Android when selecting payment options the invoice title and back button are at the top of the page, in iOS they appear to be several lines down | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 2 | 25431 MSBP - MAUI - iOS - invoice screen continues to scroll for an entire page past last information (15.0) | 25431 MSBP - MAUI - iOS - invoice screen continues to scroll for an entire page past last information (15.0) | Onsite | Defect | When in the invoices screen, can continue to scroll past the final invoice. The scroll bar will get smaller and smaller indicating it is still "scrolling" but it snaps back to a blank page, which upon scrolling up appears to be about one screen length | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion

## 15.0 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Vaishnavi | 48363 | REG - MSBP - Regression | Story Completed | 5 | 3 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Vaishnavi | 42146 | MSBA - Maui - Tickets | Story Being Tested | 2 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Currently this story is on hold. As we faced iOS build issues due to that unable to test in iOS. MSBP and MSBA regression testing were prioritized so this defect was on hold
3 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Vaishnavi | 48364 | REG - MSBA - Regression | Story Being Tested | 5 | 3.25 | 13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Due to pending test cases, carried to next sprint.
4 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Mohamed/Premkumar | 48217 | MSBA - MAUI - Shake for Logs added to MSBA | Story Completed | 3 | 1.75 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Premkumar | 25192 | MSBA - MAUI -Forgot login - store tabs showing at bottom of screen | Defect Fixed | 1 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Rupesh/Premkumar | 25195 | MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Defect Peer Review | 2 | 1.5 | 6 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42789 | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
7 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Sambath/Vaishnavi | 25314 | MSBP - Maui - Store products not showing the price in checkout screen. | Defect Fixed | 1 | 2 | 8 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42506 | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Premkumar | 25196 | MSBA - MAUI - Invoice Details - buttons enabled behind payment options | Defect Fixed | 1 | 2.25 | 9 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Gursewak/Premkumar | 25181 | MSBA - MAUI - Header not Formatted Correctly | Defect Fixed | 2 | 2.25 | 9 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42498 | 2025-04-06 | 2025-04-06 | Ashwin Majjela | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Jagdeep | 25183 | MSBA - MAUI - App not force logging out on time out | Defect Fixed | 2 | 3 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
11 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Gursewak/Premkumar | 25194 | MSBA - MAUI -product details - camera not rotating | Defect Fixed | 2 | 1.25 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Rupesh | 25198 | MSBA - MAUI - Invoice Details - Payment options pop up | Story Peer Review | 2 | 2.5 | 10 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42696 | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Amrit/Premkumar | 25191 | MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Defect Being Fixed | 3 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
14 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Rupesh/Premkumar | 25193 | MSBA - MAUI -settings - after first login when re-entering settings screen loading symbol stuck | Defect Fixed | 3 | 3 | 10 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42572 | 2025-03-06 | 2025-04-06 | Ashwin Majjela | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Sambath | 25329 | 25329 MSBP- Maui -Unable to add payment method from checkout payment method drawer in iOS (Beta) | Defect Fixed | 1 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42589 | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Sambath | 25351 | 25351 MSBP - MAUI - Android - keyboard does not automatically open for district selection on account creation (14.7/15.0) | Defect Fixed | 1 | 2.25 | 9 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42698 |  | NA | NA | NA | NA | NA | NA | NA | NA
17 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Sambath | 25359 | 25359 MSBP - MAUI - checkout not respecting promocode flag (15.0) | Defect Ready For Testing | 1 | 0.5 | 2 | [5 empty] | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42736?_a=files | [7 empty] | NA | NA | Carried to next sprint
18 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Amrit Pal | 48217 | MSBA - Shake for device logs | Defect Fixed | 1 | 1 | 21 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42657 | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Jagdeep | 25190 | MSBA - MAUI - Forgot login | Defect Fixed | 2 | 5.25 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
20 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Premkumar | 25188 | MSBA - MAUI - Android - product details - ability to select today's date | Defect Fixed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | [7 empty] | NA | NA
21 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 | Vaishnavi | 25332 | MSBP - Maui - District drop down not showing the district while searching (Beta) | Defect Fixed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
22 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Mohamed | 46155 | MSBP - Tickets - Upcoming Events Screen | Story Ready For Testing | 3 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
23 | MSB Mobile | 2025-05-02 | 2025-05-15 | 15.0 M Sprint 1 Stretch | Amrit Pal | 25201 | MSBA - MAUI - Add to Cart - Android - expand/collapse only works when you drag a list item first | Defect Being Fixed | 2 | 2 | 16 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Defecct solved on Android and Ios phone, but crash happening in IPAD. working on that dnt have ipad device
24 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Premkumar | 25200 | MSBA - MAUI - Close Out Carousel - Close Out - Not Scrollable in Android | Defect Fixed | 2 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
25 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Premkumar | 25373 | MSBA - MAUI - Android/iOS - Start shift is unresponsive in Android and crashing in iOS | Defect Fixed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
26 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Vaishnavi | 48626 | REG - MSBA - Prod Smoke Test Against Staging RC | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
27 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Vaishnavi | 48627 | REG - MSBP CA - Prod Smoke Test Against Staging RC | Story Completed | 1 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
28 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Gursewak | 25380 | MSBA - MAUI - Unable to login after logout | Defect Being Fixed | 1 | 7.5 | 30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
29 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Premkumar | 25189 | 25189 MSBA - MAUI - IOS - forgot login - image background not scaling/tiling properly | Defect Fixed | 1 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42589 | NA | NA | NA | NA | NA | NA | NA | NA | NA
30 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Sambath | 46156 | 46156 MSBP - Tickets - Event Details | Story Being Developed | 8 | 3.75 | 15 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
31 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Jagdeep Singh | 25183 | 25183 MSBA - MAUI - App not force logging out on time out | Defect Fixed | 1 | 1.5 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42733 | 2025-10-06 | 2025-12-06 | Jacquelin, Sean | 1q | NA | NA | NA | NA | NA
32 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Jagdeep Singh | 25190 | 25190 MSBA - MAUI - Forgot login | Defect Peer Review | 1 | 1.5 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42765 | 2025-11-06 |  | Ashwin Majjela | NA | NA | NA | NA | NA | NA | Carried to next sprint
33 | MSB Mobile | 2025-05-30 | 2025-06-12 | 15.0 M Sprint 1 Stretch | Jagdeep Singh | 25196 | 25196 MSBA - MAUI - Invoice Details - buttons enabled behind payment options | Defect Fixed | 1 | 0.75 | 6 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42478 | 29/05/2025 | 29/05/2025 | Jacquelin, Sean | NA | NA | NA | NA | NA | NA

## 15.0 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 15.0 M Sprint 1 | 25183 MSBA - MAUI - App not force logging out on time out | 25183 MSBA - MAUI - App not force logging out on time out | Jagdeep Singh | Defect | phone/tablet -Where: endpoint calls, Like MSBP, when user is timed out, need to force user out to Login | Significant | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25190 MSBA - MAUI - Forgot login | 25190 MSBA - MAUI - Forgot login | Jagdeep Singh | Defect | Phone/tablet - In IOS Xamarin, on some screens, when keyboard was in use the Next button would move above keyboard. In both IOS and Android Maui, the keyboard now blocks the Next button. check to see if this is a limitation of Maui as this was working in IOS Xamarin.consistent through the app | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25196 MSBA - MAUI - Invoice Details - buttons enabled behind payment options | 25196 MSBA - MAUI - Invoice Details - buttons enabled behind payment options | Jagdeep Singh | Defect | phone/tablet - Able to tap the (Add All To Cart, Payment Options and Add/Remove all to cart) buttons when partial / full payment options pop up is open - (Android) | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25380 MSBA - MAUI - Unable to login after logout | 25380 MSBA - MAUI - Unable to login after logout | Jagdeep Singh | Defect | Unable to login after logging out of the app | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25181 MSBA - MAUI - Header not Formatted Correctly | 25181 MSBA - MAUI - Header not Formatted Correctly | Gursewak Singh | Defect | phone/tablet - header exists (6/18) but is not formatted correctly MSBA - MAUI - Camera Icon in search bar is not the same as Xamarin Header missing on store screen as well Doublecheck other two search areas on Invoices and Meals too Notes from Refinement: Copy Font Awesome from Parent app to MSBA and select the same icon and POV to Jason | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25189 MSBA - MAUI - IOS - forgot login - image background not scaling/tiling properly | 25189 MSBA - MAUI - IOS - forgot login - image background not scaling/tiling properly | Gursewak Singh | Defect | hone/tablet See below, it's tiled, rather than stretched. New Background image: Aspect Ratio 4:3image (1).png ​ need new image - not HQ but in aspect ratio X - use iPad Max as a reference - try to limit max image size from 1000KB | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25194 MSBA - MAUI -product details - camera not rotating | 25194 MSBA - MAUI -product details - camera not rotating | Gursewak Singh | Defect | phone/tablet adding product picture within product details when rotating device, camera doesn't change the rotation (question on if barcode affected also?) | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25197 MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | 25197 MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | Gursewak Singh | Defect | iOS - phone - More space between Partial Amount checkbox label and the amount entry field | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25380 MSBA - MAUI - Unable to login after logout | 25380 MSBA - MAUI - Unable to login after logout | Gursewak Singh | Defect | phone/tablet Unable to login after logging out of the app | Significant | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25192 - MSBA - MAUI -Forgot login - store tabs showing at bottom of screen | 25192 - MSBA - MAUI -Forgot login - store tabs showing at bottom of screen | Amrit | Defect | phone/tablet - if app is logged in, tabs added, log out, go to forgot password workflow and note that the tabs show. Close out and re-enter and it is gone fixed already for login page & subsequent pages previously | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25195 - MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | 25195 - MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Rupesh | Defect | phone/tablet - Payment options pop up - | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25314 - MSBP - Maui - Store products not showing the price in checkout screen. | 25314 - MSBP - Maui - Store products not showing the price in checkout screen. | Sambath | Defect | In checkout screen, the store products are not showing the price. Also, the district total field is also not showing the total amount. Attached screenshot for reference. | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25198 MSBA - MAUI - Invoice Details - Payment options pop up | 25198 MSBA - MAUI - Invoice Details - Payment options pop up | Rupesh | Defect | iPad - Able to enter alphabets and special characters in the amount entry field (unlike the Xamarin app, per Dev this is a common issue found in iPad across the Maui application for the amount entry fields Ex: product details page ‘Price’ entry field ) This likely affects anywhere with an entry field including meal payments (dev to document and list & communicate with QA the affected areas). Likely solved by numeric only keyboard behavior (deletes anything that's not a number). https://learn.microsoft.com/en-us/dotnet/communitytoolkit/maui/behaviors/numeric-validation-behavior | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25191 - MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | 25191 - MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Amrit | Defect | 25191 MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Minor | Manual | External | Inprogress | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25193 - MSBA - MAUI -settings - after first login when re-entering settings screen loading symbol stuck | 25193 - MSBA - MAUI -settings - after first login when re-entering settings screen loading symbol stuck | Rupesh | Defect | phone/tablet intermittent behavior seen / possibly bandwidth related? | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25329 MSBP- Maui -Unable to add payment method from checkout payment method drawer in iOS (Beta) | 25329 MSBP- Maui -Unable to add payment method from checkout payment method drawer in iOS (Beta) | Sambath | Defect | IOS Beta Version - In checkout screen, after selecting 'Add payment method' from the payment method drawer, user is not navigated to the add payment method screen. Nothing happens. Upon closing the payment method drawer and selecting back arrow does not navigate the user back. App stuck and has to close and re-open the application to work. This issue exists in below areas as well. Family pass sign up page Meal Money autopay | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25351 MSBP - MAUI - Android - keyboard does not automatically open for district selection on account creation (14.7/15.0) | 25351 MSBP - MAUI - Android - keyboard does not automatically open for district selection on account creation (14.7/15.0) | Sambath | Defect | When creating account and selecting the district box, the keyboard does not automatically open upon landing on the page | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25359 MSBP - MAUI - checkout not respecting promocode flag (15.0) | 25359 MSBP - MAUI - checkout not respecting promocode flag (15.0) | Sambath | Defect | When the system flag for promocodes is disabled, still able to see the promocodes box in Maui where we are not seeing it in xamarin | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25188 - MSBA - MAUI - Android - product details - ability to select today's date | 25188 - MSBA - MAUI - Android - product details - ability to select today's date | Onsite | Defect | phone/tablet In date selector, cannot select today's date on the product details page. This matters for webforms, pickup dates for example. has potential to be fixed by the Telerik Updates This was fixed in MSBP previously | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25314 - MSBP - Maui - Store products not showing the price in checkout screen. | 25314 - MSBP - Maui - Store products not showing the price in checkout screen. | Sambath | Defect | In checkout screen, the store products are not showing the price. Also, the district total field is also not showing the total amount. Attached screenshot for reference. | Minor | Manual | External | Closed | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25332 - MSBP - Maui - District drop down not showing the district while searching (Beta) | 25332 - MSBP - Maui - District drop down not showing the district while searching (Beta) | Onsite | Defect | Create account workflow - After selecting the state/province as Yucon, Canada and searching district as 'OneDistrict' is not showing any suggestion to select the district. Add student workflow - school drop down does not show any suggested schools. | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25201 - MSBA - MAUI - Add to Cart - Android - expand/collapse only works when you drag a list item first | 25201 - MSBA - MAUI - Add to Cart - Android - expand/collapse only works when you drag a list item first | Onsite | Defect | phone/tablet - For the MAUI add to cart story that is working on the expand and collapse is not working as expected in android device, it working only when you drag the list item after expand or collapse as shown in the below recording. But its working as expected in iOS device without dragging. The issue seems to be that the Telerik listview control with grouping is not behaving as expected in Android. Also the swipe to delete in this control is not functioning as expected. We tried few work arounds but its not working as expected and we are blocked on this. Should we table it now as a known issues that needs to be fixed later in the list we maintain? | Minor | Manual | External | Inprogress | Development | Client QA | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25200 - MSBA - MAUI - Close Out Carousel - Close Out - Not Scrollable in Android | 25200 - MSBA - MAUI - Close Out Carousel - Close Out - Not Scrollable in Android | Gursewak Singh | Defect | Hamburger Menu > Shifts & Closeout ¦ Closeout > Close out entire day or Select shift Page 3 or 4 information scrollable or the carousel itself | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 15.0 M Sprint 1 | 25273 - MSBA - MAUI - Android/iOS - Start shift is unresponsive in Android and crashing in iOS | 25273 - MSBA - MAUI - Android/iOS - Start shift is unresponsive in Android and crashing in iOS | gursewak Singh | Defect | Tapping on Start shift from Hamburger menu or the clock icon is crashing in iOS and unresponsive in Android. See attached recording for repro. | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion

## 14.7 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 | Vaishnavi | 48363 | REG - MSBP - Regression | Story Approved | 5 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not started due to beta release. Beta release was blocked due to a defect found while doing smoke test
2 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 | Vaishnavi | 48313 | MSB Mobile - Invalidate Session after Password Change 14.7 | Story Completed | 2 | 1.75 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 | Sambath/Vaishnavi | 25214 | MSBA - Tickets BoxOffice - IOS/Android - Payment Options are not presented to the user 14.7 | Defect Fixed | 3 | 6.75 | 27 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 | Ashwin | 48218 | MSBA - MAUI - Screens Not Yet Developed (timebox) | Story Completed | 2 | 2 | 2 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 | Vaishnavi | 25294 | MSBP - MAUI - iOS - Payment methods never resolves (Beta) | Defect Fixed | 0 | 0.5 | 2 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 | Vaishnavi | 25293 | MSBP - MAUI - Other field in meal money and auto pay not formatted correctly every time (regression) | Defect Fixed | 0 | 0.25 | 1 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 | Vaishnavi | 25284 | MSBP - MAUI - iOS - greenlight signup is too large for the screen (14.7) | Defect Fixed | 0 | 0.25 | 1 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 | Vaishnavi | 25292 | MSBP - MAUI - Android - Upon completing transaction and closing receipt, payment methods sheet is still open (regression) | Defect Fixed | 0 | 0.25 | 1 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 Stretch | Ashwin | 42146 | MSBA - Maui - Tickets | Story Ready For Testing | 2 | 2 | 12 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42386 | 2025-05-23 |  | Ashwin | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 Stretch | Mohamed | 46155 | MSBP - Tickets - Upcoming Events Screen | Story Ready For Testing | 8 | 7 | 28 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42330 | 2025-05-21 | 2025-05-23 | Sambath | NA | Ashwin | 2025-05-23 | NA | NA | NA
11 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 Stretch | Sambath | 25203 | 25203 MSBA - MAUI - Add to Cart - Delay updating cart items | Defect Blocked | 2 | 2 | 18 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Analysis showed the control was not performant. Going to write story to replace with Rad Collection View or MAUI Collection View instead of the Rad List control.
12 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 Stretch | Amrit/Premkumar | 25192 | MSBA - MAUI -Forgot login - store tabs showing at bottom of screen | Defect Being Tested | 1 | 0.5 | 2 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing in iOS blocked as the Maui builds are not opening in iOS devices.
13 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 Stretch | Rupesh/Premkumar | 25195 | MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Defect Being Tested | 2 | 0.75 | 3 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing in iOS blocked as the Maui builds are not opening in iOS devices.
14 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 Stretch | Gursewak | 25197 | MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | Defect Blocked | 1 | 0 | 0 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Blocked due to iOS crash issue in the latest build and Mac unavailability.
15 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 Stretch | Jagdeep | 25199 | MSBA - MAUI - Invoice Details - Payment options pop up - Alignment | Defect Being Fixed | 2 | 0 | 0 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Tested on Android devices it is working fine. Need to test it on iOS devices but due to MAUI iOS build issue not able to test. Waiting for MAUI iOS build fix.
16 | MSB Mobile | 2025-05-16 | 2025-05-29 | 14.7 M Sprint 3 Stretch | Vaishnavi | 25246 | MSBP - MAUI - some headers do not match | Defect Fixed | 0 |  | 0.5 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 14.7 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 | Vaishnavi | 46199 | [FAMILYPASS] MSBP - Payment Options - Cross-Sell Pop Up | Story Completed | 3 | 5.75 | 23 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42064?_a=files | 2025-05-07 | 2025-05-07 | Ashwin | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 | Ashwin/Vaishnavi | 24775 | MSBP - Maui/Xamarin - Supplement fee not applied for new user while adding 1st Meal/Store product | Defect Fixed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 | Mohammed | 46154 | MSBP - Tickets - Add Events Card to Home Screen | Story Completed | 8 | 8 | 32 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42086 | 2025-05-08 | 2025-05-09 | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 | Vaishnavi | 47517 | MSBP - AutoPay Screen - Show indication that AutoPay will not be processed due to Declined | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 | Sambath/Vaishnavi | 47753 | [FAMILYPASS] MSBP - Payment Options - Hooray Screen- Cross-Sell Pop up | Story Completed | 3 | 4.5 | 18 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42095 | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 | Sambath/Vaishnavi | 48247 | MSBP - FamilyPass - Auto select payment method | Story Completed | 3 | 4.25 | 17 | NA | NA | NA | Mohamad | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42107 | 2025-05-09 | 2025-05-09 | Ashwin | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 Stretch | Vaishnavi | 25036 | MSBP - Beta - 14.5 - Name bunched up in Add Meal Money | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 Stretch | Ashwin | 42146 | MSBA - Maui - Tickets | Story Being Developed | 8 | 9 | 36 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint. Development still in progress.
9 | MSB Mobile | 2025-05-02 | 2025-05-15 | 14.7 M Sprint 2 Stretch | Mohamed | 46155 | MSBP - Tickets - Upcoming Events Screen | Story Being Developed | 8 | 1 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint. Development still in progress.

## 14.7 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 14.7 M Sprint 2 | 24775 MSBP - Maui/Xamarin - Supplement fee not applied for new user while adding 1st Meal/Store product | 24775 MSBP - Maui/Xamarin - Supplement fee not applied for new user while adding 1st Meal/Store product | Ashwin | Defect | Supplement fee not applied when a new user adds 1st meal payment or 1st store product. In checkout screen after adding/selecting a new payment method, the supplement fee is not getting applied. Issue exists in both Maui and Xamarin | Minor | Manual | Internal | Closed | Development | Relevantz QA | Exisiting Xamarin behaviour,
| 14.7 M Sprint 2 | 46199 [FAMILYPASS] MSBP - Payment Options - Cross-Sell Pop Up | 46199 [FAMILYPASS] MSBP - Payment Options - Cross-Sell Pop Up | Sambath | Bounceback/Sub-Defect | 1.MSBP -Maui - I- when user selects 'X' from the FP sign up screen, it is not closing. 2.MSBP - Maui- I/A - If payment method is not selected from the drawer, able to view the cross sell pop up. Upon clicking that, it is allowing user to select payment method and when join now button is selected, there is no response. 3.MSBP - Maui-I/A - Family pass discount field is getting displayed in checkout screen after selecting payment method for a Non FP user while making invoice/store transaction/meal transaction before enabling the FP offer. FP user also showing that field while doing invoice/store transaction 4.MSBP - Maui -I/A - Payment summary screen is not showing MSB blue flag and ? in the Family Pass Discount field. Amount is also not showing in Green color 5.MSBP - Maui-I/A - echeck +meal payment showing FP cross sell offer | Significant | Manual | Internal | Closed | Development | Relevantz QA | Missed during development
| 14.7 M Sprint 2 | 48247 [FAMILYPASS] MSBP - Auto select payment method | 48247 [FAMILYPASS] MSBP - Auto select payment method | Sambath | Bounceback/Sub-Defect | MSBP - I/A - Newly added payment method is not pre-selected in FP sign up screen payment method drawer. Instead it is pre-selected the CC payment selected in checkout screen | Significant | Manual | Internal | Closed | Development | Relevantz QA | Missed during development
| 14.7 M Sprint 2 Stretch | 25036MSBP - Beta - 14.5 - Name bunched up in Add Meal Money | 25036 MSBP - Beta - 14.5 - Name bunched up in Add Meal Money | Onsite | Defect | Name bunched up in Add Meal Money | Significant | Manual | External | Closed | Development | Others | Xamarin to Maui conversion

## 14.7 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-04-18 | 2025-05-01 | 14.7 M Sprint 1 | Vaishnavi | 47809 | MSBP CA - Regression/Smoke Test 14.4 (Xam) against MSB RC in Staging | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 2025-04-18 | 2025-05-01 | 14.7 M Sprint 1 | Mohammed | 25040 | MSBP - MAUI - Android - When selecting area in Payment Methods sheet, drawer closes | Defect Blocked | 2 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This defect only occurred on Android. Have to change existing workflow to fix this issue in Android. So Jason needs to confirm, and then start work on this defect in future sprint.
3 | MSB Mobile | 2025-04-18 | 2025-05-01 | 14.7 M Sprint 1 Stretch | Sambath / Mohammed/Vaishnavi | 46199 | [FAMILYPASS] MSBP - Payment Options - Cross-Sell Pop Up | Story Being Tested | 13 | 13.75 | 55 | NA | NA | NA | Mohamad | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41966 | 2025-04-30 | 2025-04-30 | Ashwin | NA | NA | NA | NA | NA | NA | Development has been completed. Story is under peer review. will be carried to the next stprint.
4 | MSB Mobile | 2025-04-18 | 2025-05-01 | 14.7 M Sprint 1 Stretch | Mohammed/Vaishnavi | 47675 | MSBP - Password History - Prevent using last 4 passwords | Story Completed | 2 | 4 | 18.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41915 | 2025-04-28 | 2025-04-28 | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2025-04-18 | 2025-05-01 | 14.7 M Sprint 1 Stretch | Ashwin | 25051 | MSBP - MAUI - Android - when approving camera permissions not directed forward | Defect Fixed | 3 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41870 | 2025-04-23 | 2025-04-24 | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-04-18 | 2025-05-01 | 14.7 M Sprint 1 Stretch | Ashwin | 47517 | MSBP - AutoPay Screen - Show indication that AutoPay will not be processed due to Declined | Story Being Tested | 3 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41936 | 2025-04-28 | 2025-04-30 | NA | NA | NA | NA | NA | NA | NA | Development has been completed. Story moved to ready for testing. will be carried to the next stprint.
7 | MSB Mobile | 2025-04-18 | 2025-05-01 | 14.7 M Sprint 1 Stretch | Ashwin | 24775 | MSBP - Maui/Xamarin - Supplement fee not applied for new user while adding 1st Meal/Store product | Defect Ready For Testing | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41870 | 2025-04-23 | 2025-04-24 | NA | NA | NA | NA | NA | NA | NA | Development has been completed. Story moved to ready for testing. will be carried to the next stprint.
8 | MSB Mobile | 2025-04-18 | 2025-05-01 | 14.7 M Sprint 1 Stretch | Mohammed | 46964 | MSBP - Phone Edit - Only Allow Save and Verify if Changed | Story Ready For Testing | 2 | 2.5 | 10 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41972 | 2025-04-30 | 2025-05-01 | NA | NA | NA | NA | NA | NA | NA | Development has been completed. Story moved to ready for testing. will be carried to the next stprint.

## 14.7 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 14.7 M Sprint 3 | 25214 MSBA - Tickets BoxOffice - IOS/Android - Payment Options are not presented to the user 14.7 | 25214 MSBA - Tickets BoxOffice - IOS/Android - Payment Options are not presented to the user 14.7 | Sambath | Defect | There is bug in the new version of MSBA (iOS/Android) with the Tickets integration that mobile will need to investigate before it can release MSBA. Tickets has a defect 25212. Note: Android had an error as well. When attempting to checkout got through the same screens as iOS but instead of being stuck at the "processing" it is redirecting and saing "webpage not available" the error is net::ERR_UNKNOWN_URL_SCHEME | Major | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 14.7 M Sprint 3 Stretch | 25203 MSBA - MAUI - Add to Cart - Delay updating cart items | 25203 MSBA - MAUI - Add to Cart - Delay updating cart items | Sambath | Defect | Android Tablet - RadList Refresh delay issue not fixed in Android, - Delays the binding to UI due to RadList control. Android Tablet: Delay happens while trying to swipe and delete the products from the cart Comparing with iOS timing -- should be similar Re-estimate & add further AC if we need new control. | Minor | Manual | External | Closed | Development | Client Dev | Xamarin to Maui conversion
| 14.7 M Sprint 3 | 25294 MSBP - MAUI - iOS - Payment methods never resolves (Beta) | 25294 MSBP - MAUI - iOS - Payment methods never resolves (Beta) | Onsite | Defect | Upon selecting a payment method and [pay now] iOS is not moving to the receipt screen at all. I can "click out" of the sheet but I cant leave the checkout page. I can reopen payment methods and select another one but the pay button never turns blue. In looking at reports in the background, the transaction did actually complete though there is nothing indicating it on the screen. | Minor | Manual | Internal | Inprogress | Development | Client QA | Xamarin to Maui conversion
| 14.7 M Sprint 3 | 25293 -MSBP - MAUI - Other field in meal money and auto pay not formatted correctly every time (regression) | 25293 -MSBP - MAUI - Other field in meal money and auto pay not formatted correctly every time (regression) | Onsite | Defect | When typing in the other field on meal money and the auto pay pages, it does not always format correctly. If you put the other in the student specific other and then choose to pay for more students, it then loads the other amount as expected | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.7 M Sprint 3 Stretch | 25192 - MSBA - MAUI -Forgot login - store tabs showing at bottom of screen | 25192 - MSBA - MAUI -Forgot login - store tabs showing at bottom of screen | Amrit | Defect | phone/tablet - if app is logged in, tabs added, log out, go to forgot password workflow and note that the tabs show. Close out and re-enter and it is gone fixed already for login page & subsequent pages previously | Minor | Manual | External | Inprogress | Development | Others | Xamarin to Maui conversion
| 14.7 M Sprint 3 Stretch | 25195 - MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | 25195 - MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Rupesh | Defect | phone/tablet - Payment options pop up - | Minor | Manual | External | Inprogress | Development | Others | Xamarin to Maui conversion
| 14.7 M Sprint 3 Stretch | 25197 MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | 25197 MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | Gursewak | Defect | iOS - phone - More space between Partial Amount checkbox label and the amount entry field | Minor | Manual | External | Inprogress | Development | Others | Xamarin to Maui conversion
| 14.7 M Sprint 3 Stretch | 25199 - MSBA - MAUI - Invoice Details - Payment options pop up - Alignment | 25199 - MSBA - MAUI - Invoice Details - Payment options pop up - Alignment | Jagdeep | Defect | iOS (phone/tablet) - Watermark text ‘Amount’ in the Partial Amount entry field is not aligned along with the cursor Common control - other areas will need to be checked. Dev: add these other areas below and communicate with team/QA in order to determine the scope of test effort. | Minor | Manual | External | Inprogress | Development | Others | Xamarin to Maui conversion
| 14.7 M Sprint 3 | 25284 - MSBP - MAUI - iOS - greenlight signup is too large for the screen (14.7) | 25284 - MSBP - MAUI - iOS - greenlight signup is too large for the screen (14.7) | Onsite | Defect | When opening the marketing to sign up for greenlight the image is too big and goes off the screen. While scrolling the carousel you can see the image, but it overlaps the text with the following page which is also showing the same way | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.7 M Sprint 3 | 25292 - MSBP - MAUI - Android - Upon completing transaction and closing receipt, payment methods sheet is still open (regression) | 25292 - MSBP - MAUI - Android - Upon completing transaction and closing receipt, payment methods sheet is still open (regression) | Onsite | Defect | If you complete a transaction, you are directed to the payment complete page/receipt. Upon closing it prompted with FP as expected if available, then upon closing that the payment methods sheet is still open on the screen. You can click away from the sheet and dismiss it though | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
14.7 M Sprint 3

## 14.6 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 | Vaishnavi | 47806 | REG - MSBP - 14.4 (Xam) Regression | Story Completed | 5 | 4.5 | 18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing completed.
2 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Ashwin/vaishnavi | 47705 | MSBA - XAM - Show Product Name on Receipt - Synergy | Story Completed | 3 | 5.25 | 21 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/41708 | 2025-04-14 | 2025-04-14 | Client | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Ashwin/Vaishnavi | 24984 | MSBP - MAUI - Android - Student Add Meal Money - Other Amount -Sheet Closes | Defect Fixed | 2 | 2 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Ashwin/vaishnavi | 24983 | MSBP - MAUI - Android - when selecting payment method for the first time, drawer closes | Defect Fixed | 2 | 3.25 | 13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Mohammed / Vaishnavi | 38007 | 38007 MSBP - Maui - Store Landing Page - Hook up to API for School Logos | Story Completed | 2 | 4.75 | 19 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41674 | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24795 | MSBA - XAM - Close Out - Check Reconciliation Stacking | Defect Fixed | 2 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24917 | MSBP - MAUI - iOS - information cut off in ? sheet for scheduled payments (regression) | Defect Fixed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24931 | MSBP - MAUI - when opening student card and closing sheet, empty warning appears (regression) | Defect Fixed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24937 | MSBP - MAUI - Notification bell icon and cart icon are not aligned properly in iOS(regression) | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24946 | MSBP - MAUI - app crash on using saved biometrics (regression) | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24972 | MSBP - MAUI - Clicking off of admin pin sheet without typing anything shows an Incorrect Pin error | Defect Fixed | 0.5 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24973 | MSBP - MAUI - Auto Pay text not centered on student meal money card | Defect Fixed | 1 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi/Ashwin | 24974 | MSBP - MAUI - Android -TOS at bottom of Meal Money AutoPay page is close to button | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Mohammed / Vaishnavi | 24976 | MSBP - MAUI - Android - Disclaimer in the payment methods does not have any margin at the edge of the screen | Defect Fixed | 1 | 1.75 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41696 | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24978 | MSBP - MAUI - when editing phone number from profile, presented with 'lets add' screen momentarily | Defect Fixed | 1 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Mohammed / Vaishnavi | 25010 | MSBP - MAUI - Total = Resource Not Found in Payment Summary | Defect Fixed | 2 | 2 | 8 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41706 | NA | NA | NA | NA | NA | NA | NA | NA | NA
17 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24975 | MSBP - MAUI - Checkout payment methods adds a white space after selecting payment method | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
18 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Mohammed | 47675 | MSBP - Password History - Prevent using last 4 passwords | Story Being Developed | 2 | 2 | 10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Story Blocked as we are waiting for PI to complete the story
19 | MSB Mobile | 2025-04-04 | 2025-04-17 | 14.6 M Sprint 3 Stretch | Sambath | 24969 | 24969 MSBA - XAM - IOS - Tickets Box Office - Camera defect introduced with 47763 in 14.6 | Defect Fixed | 3 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/41748 | 2025-04-15 | 2025-04-15 | Ashwin | NA | NA | NA | NA | NA | NA

## 14.7 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 14.7 M Sprint 1 Stretch | 25051 MSBP - MAUI - Android - when approving camera permissions not directed forward | 25051 MSBP - MAUI - Android - when approving camera permissions not directed forward | Ashwin | Defect | When approving permissions after selecting student icon for picture, receiving the message usually seen at denial and camera options never open. Able to open the picture menu as expected afterwards | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion

## 14.6 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 14.6 M Sprint 3 Stretch | 24984 MSBP - MAUI - Android - Student Add Meal Money - Other Amount -Sheet Closes | 24984 MSBP - MAUI - Android - Student Add Meal Money - Other Amount -Sheet Closes | Ashwin | Defect | when using other amount, the sheet is closing after navigating to page to add money | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24983-MSBP - MAUI - Android - when selecting payment method for the first time, drawer closes | 24983-MSBP - MAUI - Android - when selecting payment method for the first time, drawer closes | Ashwin | Defect | When I am selecting a payment method (usually 3rd or 4th down on the sheet) the tray closes. Upon opening the sheet once more it appears nothing has been selected. On selecting again it remains selected even when navigating away from that page. | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24795 MSBA - XAM - Close Out - Check Reconciliation Stacking | 24795 MSBA - XAM - Close Out - Check Reconciliation Stacking | Onsite | Defect | Check reconciliation stacking | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24917 MSBP - MAUI - iOS - information cut off in ? sheet for scheduled payments (regression) | 24917 MSBP - MAUI - iOS - information cut off in ? sheet for scheduled payments (regression) | Mohammed | Defect | When looking at the ? section on scheduled payments, the Meal Money AutoPay ends in ... however, there does not appear to be a way to retrieve the rest of this information. I found this while looking at iphone 12 (not pixel 6) but it may be a screen size issue and not just iOS | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24931 MSBP - MAUI - when opening student card and closing sheet, empty warning appears (regression) | 24931 MSBP - MAUI - when opening student card and closing sheet, empty warning appears (regression) | Onsite | Defect | When in an account, if select the student card (4 dots) the student sheet opens. Upon swiping down to close it a warning box appears with no additional text in it | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24937 MSBP - MAUI - Notification bell icon and cart icon are not aligned properly in iOS(regression) | 24937 MSBP - MAUI - Notification bell icon and cart icon are not aligned properly in iOS(regression) | Onsite | Defect | Maui-iOS- Notification bell icon and cart icon are not aligned. It is aligned up and down, not in a straight order. Screenshot for reference. | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24946 MSBP - MAUI - app crash on using saved biometrics (regression) | 24946 MSBP - MAUI - app crash on using saved biometrics (regression) | Onsite | Defect | If you have biometrics enabled, then log out and press the fingerprint icon in the login, the app is crashing. Upin reopening the app, it will direct you in and request the biometrics to log in appropriately | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24972 MSBP - MAUI - Clicking off of admin pin sheet without typing anything shows an Incorrect Pin error | 24972 MSBP - MAUI - Clicking off of admin pin sheet without typing anything shows an Incorrect Pin error | Onsite | Defect | On the login page click the version number at the bottom Click off the sheet without typing anything The app throws an "Incorrect Pin" error | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24973 MSBP - MAUI - Auto Pay text not centered on student meal money card | 24973 MSBP - MAUI - Auto Pay text not centered on student meal money card | Onsite | Defect | When selecting single student meal money the auto pay section is not centered in box | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24974 MSBP - MAUI - Android -TOS at bottom of Meal Money AutoPay page is close to button | 24974 MSBP - MAUI - Android -TOS at bottom of Meal Money AutoPay page is close to button | Onsite | Defect | At the bottom of the Meal Money AutoPay page, the TOS line is very close to the save changes button, should have additional space | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24976 MSBP - MAUI - Android - Disclaimer in the payment methods does not have any margin at the edge of the screen | 24976 MSBP - MAUI - Android - Disclaimer in the payment methods does not have any margin at the edge of the screen | Mohammed | Defect | When payment methods is open the disclaimer above the pay now appears to go edge to edge on the screen without any side margins | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24978 MSBP - MAUI - when editing phone number from profile, presented with 'lets add' screen momentarily | 24978 MSBP - MAUI - when editing phone number from profile, presented with 'lets add' screen momentarily | Onsite | Defect | When opening a phone number to edit from the profile screen, instead of being directed straight to the edit mobile number screen, seeing the "lets add your phone number" screen which appears when there is no phone number before directing to the correct page | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 25010 MSBP - MAUI - Total = Resource Not Found in Payment Summary | 25010 MSBP - MAUI - Total = Resource Not Found in Payment Summary | Mohammed | Defect | MSBP 14.5 Make a payment On Payment Summary screen, observe FP Post sale offer Close Offer | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to Maui conversion
| 14.6 M Sprint 3 Stretch | 24795 MSBP - MAUI - Checkout payment methods adds a white space after selecting payment method | 24795 MSBP - MAUI - Checkout payment methods adds a white space after selecting payment method | Onsite | Defect | I believe this was previously fixed during the Maui dev, but when opening payment methods you will see full screen of payment methods. Selecting a payment method which does not have CVV required adds a large white blank area above the total charges box that cuts off part of the screen. It is more prominent in Android than iOS as it only shows 2.75 payment methods to iOS' 3.5 | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion

## 14.6 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-03-25 | 2025-04-03 | 14.6 M Sprint 2 | Vaishnavi | 47622 | REG - MSBP - 14.5 MAUI Regression (Formal Regression) | Story Completed | 13 | 9 | 36.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | The actual story point is 9sp as this estimated SP includes the worklog of client QA and Dev also
2 | MSB Mobile | 2025-03-25 | 2025-04-03 | 14.6 M Sprint 2 | Vaishnavi | 47679 | MSBP - MAUI - Hide Chat button | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 2025-03-25 | 2025-04-03 | 14.6 M Sprint 2 | Ashwin | 47222 | MSBA - XAM - Tickets Box Office - Android - Support for Camera In Web Browser 14.6 | Story Completed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Reserach Story. TimeBoxed
4 | MSB Mobile | 2025-03-25 | 2025-04-03 | 14.6 M Sprint 2 | Mohamed | 24917 | MSBP - MAUI - iOS - information cut off in ? sheet for scheduled payments (regression) | Defect Ready For Testing | 0 | 0 | 0 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41567 | 2025-04-03 | 2025-04-03 | Client | NA | NA | 2025-04-03 | NA | NA | NA | Development completed and PR created at the last date of sprint. Carried to the Sprint 3. Testing will be done in spirnt 3
5 | MSB Mobile | 2025-03-25 | 2025-04-03 | 14.6 M Sprint 2 | Ashwin/Vaishnavi | 24920 | MSBP - MAUI - Request balance transfer opens a Blank drawer when 'To Account' is selected | Defect Fixed | 0 | 0 | 0 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41547 | 2025-04-02 | 2025-04-02 | Client | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-03-25 | 2025-04-03 | 14.6 M Sprint 2 Stretch | Ashwin/Vaishnavi | 47763 | MSBA - Tickets Box Office - Android - Support for Camera in Web Browser | Story Completed | 5 | 5 | 20 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/41521 | 2025-03-31 | 2025-03-31 | Client | NA | NA | NA | NA | NA | NA | Story closed as it works as expected in Android

## 14.6 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 14.6 M Sprint 2 | 24892 MSBP - MAUI Beta - profile update password missing save button(regression) | 24892 MSBP - MAUI Beta - profile update password missing save button(regression) | Onsite | Defect | When going through profile to update password there is no save button present on screen | Minor | Manual | Internal | Closed | Development | Client QA | xamarin to MAUi conversion
| 14.6 M Sprint 2 | 24900 MSBP - MAUI Beta - Android - background missing on sheet invoices payment option (regression) | 24900 MSBP - MAUI Beta - Android - background missing on sheet invoices payment option (regression) | Onsite | Defect | Within invoices when selecting the payment option, the background is not there. (Installment plans sheet on this page works as expected) | Minor | Manual | Internal | Closed | Development | Client QA | xamarin to MAUi conversion
| 14.6 M Sprint 2 | 24908 MSBP - MAUI Beta - iOS - School drop down carrot too close to cart | 24908 MSBP - MAUI Beta - iOS - School drop down carrot too close to cart | Onsite | Defect | The drop down carrot is very close to the cart icon | Minor | Manual | Internal | Closed | Development | Client QA | xamarin to MAUi conversion
| 14.6 M Sprint 2 | 24918 MSBP -MAUI - Selected Meal money from student card is unselected in when navigated from 'Pay for more students' option(regression) | 24918 MSBP -MAUI - Selected Meal money from student card is unselected in when navigated from 'Pay for more students' option(regression) | Onsite | Defect | Maui - I have selected a Meal money from student card and selected 'Pay for more students' button. It navigated to Add Meal money screen. There, the already selected Meal money is not highlighted and "Add to cart" button is also disabled. In Xamarin, the selected Meal money is still highlighted. | Minor | Manual | Internal | Closed | Development | Relevantz QA | xamarin to MAUi conversion
| 14.6 M Sprint 2 | 24839 MSBP - MAUI Beta - Android status bar text turns white when a sheet is open (regression) | 24839 MSBP - MAUI Beta - Android status bar text turns white when a sheet is open (regression) | Onsite | Defect | When a bottom sheet opens in Android the text in the status bar at the top of the screen turns white. This causes it to be unreadable on the white status bar. | Minor | Manual | Internal | Closed | Development | Client Dev | xamarin to MAUi conversion
| 14.6 M Sprint 2 | 24922 MSBP - MAUI - After deleting student if click before success message appears, app crashes (regression) | 24922 MSBP - MAUI - After deleting student if click before success message appears, app crashes (regression) | Onsite | Defect | When deleting a student a loader appears. There are times when the loader clears but the student deleted success message is slow to populate. If you interact with the app in this time frame (ie hamburger menu) the app will crash. Usually there is not much transition between the two for time, but occasionally the time frame is longer and allows for this interaction. | Minor | Manual | Internal | Closed | Development | Client QA | xamarin to MAUi conversion
| 14.6 M Sprint 2 | 24919 MSBP - MAUI - Payment history filter is not showing the filter results as expected (regression) | 24919 MSBP - MAUI - Payment history filter is not showing the filter results as expected (regression) | Onsite | Defect | Payment history - Selected a filter to view payment history for the student 'Roger'. 2 records got displayed. selected the first record and viewed the payment details. Came back to the main payment history screen, the data is refreshed and showing the payment history for all the students. But still, the filter is tagged as 'Roger' | Minor | Manual | Internal | Closed | Development | Relevantz QA | xamarin to MAUi conversion
| 14.6 M Sprint 2 | 24920 MSBP - MAUI - Request balance transfer opens a Blank drawer when 'To Account' is selected | 24920 MSBP - MAUI - Request balance transfer opens a Blank drawer when 'To Account' is selected | Ashwin | Defect | Request balance transfer - Tap 'From account' and Selected student 'Mobile-1 Test RJ District' from the drawer. Received a warning. Select 'ok' to close the warning. Try tapping on 'To account' A blank drawer opened. | Minor | Manual | Internal | Closed | Development | Relevantz QA | xamarin to MAUi conversion
| 14.6 M Sprint 2 Stretch | 47763 MSBA - XAM - Tickets Box Office - Android - Support for Camera in Web Browser | 47763 MSBA - XAM - Tickets Box Office - Android - Support for Camera in Web Browser | Ashwin | Bounceback/Sub-Defect | MSBA-iOS - Tickets Box Office homescreen not loading in IPAD. | Significant | Manual | Internal | Closed | Development | Relevantz QA | Story closed, as this bounceback is not related to this story. It will be fixed later
| 14.6 M Sprint 2 | 24907 MSBP - MAUI - Android - when entering 3rd party sso login, not redirecting on click off (regression) | 24907 MSBP - MAUI - Android - when entering 3rd party sso login, not redirecting on click off (regression) | Onsite | Defect | when entering the 3rd party login information, app is no longer automatically redirecting to the 3rd party login page. Must use login button to proceed | Minor | Manual | Internal | Closed | Development | Client QA | xamarin to MAUi conversion

## 14.6 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Vaishnavi | 24797 | MSBP - MAUI - Edit payment method not working as expected | Defect Fixed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Vaishnavi | 24792 | MSBP - MAUI - Value Add Student appearing when after all students are deleted from household | Defect Fixed | 1 | 0.38 | 1.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Gokul/Vaishnavi | 24799 | MSBP - MAUI - Android - cursor does not default to end on boxes with amounts in them by default | Defect Fixed | 1 | 3.75 | 15 | Done | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41166?path=/MSB.Parent/Resources/StyleControls/Entry.xaml.cs | 2025-03-10 | 2025-03-10 | Ashwin | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24796 | MSBP - MAUI - iOS - meal money autopay other box is cut off on right side of screen | Defect Fixed | 2 | 1 | 3 | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41134 | 2025-03-07 | 2025-03-07 | Ashwin | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24798 | 24798 MSBP - MAUI - Adding payment method at checkout closes tray | Defect Fixed | 3 | 3 | 11 | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41168 | 2025-03-11 | 2025-03-11 | Ashwin | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Gokul | 24810 | MSBP - MAUI - Android - Login not load all icons in navigation (regression) | Defect Needs More Info |  |  |  | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA | NA | NA | Attempted to reproduce the defect several times in the local environment(both device and simulator), but it occurred very rarely. Even though the icons were partially loaded first, it then took few more seconds for the remaining icons to get loaded. Unfortunately, couldn’t capture it in the local development environment, so the issue couldn’t be fixed.
7 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Gokul | 24816 | MSBP - MAUI - Greenlight carousel shows "payment method" when no echeck available (regression) | Defect Fixed |  |  |  | NA | NA | NA | Sambath | NA |  |  |  |  | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Vaishnavi | 24644 | MSBP - Maui - Drawer issues | Defect Fixed | 3 | 1.5 | 6
9 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24815 | 24815 MSBP - MAUI - GL share info drawer closing after edit information (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41222 | 2025-03-13 | 2025-03-13 | Ashwin | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Ashwin/Vaishnavi | 47477 | MSBP - MAUI Only - Show Declined Payment Methods on Payment Method Screen 14.5 | Story Completed | 3 | 0.25 | 1 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41214 | 2025-03-12 | 2025-03-13 | Client |  | NA | NA | NA | NA | NA
11 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Team | 47488 | REG - MSBP - 14.5 MAUI Regression | Story Completed | 13 | 42.5 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All Defects Time were logged here. Client conveyed the Team to log all the work log in this story.
12 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Gokul | 24821 | MSBP - MAUI - quicklink to product very slow to load(regression) | Defect Fixed |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24824 | 24824 MSBP - MAUI - Bottom sheet closes on editing information Family Pass profile change payment method (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41226 | 2025-03-14 | 2025-03-14 | Ashwin | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24823 | 24823 MSBP - MAUI - Bottom sheet closes on editing information AutoPay screen (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41225 | 2025-03-13 | 2025-03-13 | Ashwin | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24826 | 24826 MSBP - MAUI - Bottom sheet closes on editing information Family Pass sign up change payment method (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41232 | 2025-03-14 | 2025-03-14 | Ashwin | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Gokul | 24822 | MSBP - MAUI - iOS - when minimizing product groups there are item names stacking (regression) | Defect Blocked |  |  |  | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Defect is blocked because of the Collection view issue in iOS related to expand / collapse grouping. Adding links to few of the open issues: https://github.com/dotnet/maui/issues/21271 https://github.com/dotnet/maui/issues/23033 https://github.com/dotnet/maui/issues/19186
17 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24836 | 24836 MSBP - MAUI -Family Pass User_Newly added payment method is not auto-checked in payment method drawers | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41257 | 2025-03-17 | 2025-03-17 | NA | NA | NA | NA | NA | NA | NA
18 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Gokul | 24835 | MSBP - MAUI - When product sections are minimized, refreshing opens them again (regression) | Defect Being Fixed |  |  |  | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA |  | Changing from Telerik collectionview control to MAUI native collectionview control to fix the issue related to controls. Since native MAUI control is lacking features of Telerik collectionview control, need to implement them manually. Hence the development is carried to next sprint.
19 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24862 | 24862 MSBP - MAUI - Basket page Swipe Delete icon is not aligned in center (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41305 | 2025-03-19 | 2025-03-19 | NA | NA | NA | NA | NA | NA | NA
20 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Sambath | 24877 | MSBP - MAUI - Android - if tap filters in store 2x in succession, filters and up arrow no longer responsive (regression) | Defect Being Fixed | [18 empty] | Still in Progress. All the Defects found were logged directly to Commit
21 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Ashwin | 24891 | 24891 MSBP - MAUI - Prior purchase is removed when the student is changed in product details (regression) | Defect Fixed |  |  |  | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41352 | 2025-03-17 | 2025-03-18 | NA | NA | NA | NA | NA | NA | NA
22 | MSB Mobile | 2025-03-07 | 2025-03-24 | 14.6 M Sprint 1 | Ashwin | 24827 | 24827 - MSBP - MAUI - Prior purchase required items messaging cut off | Defect Fixed |  |  |  | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41230 | 2025-03-21 | 2025-03-21 | NA | NA | NA | NA | NA | NA | NA

## 14.6 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 14.6 M Sprint 1 | 24824 MSBP - MAUI - Bottom sheet closes on editing information Family Pass profile change payment method (regression) | 24824 MSBP - MAUI - Bottom sheet closes on editing information Family Pass profile change payment method (regression) | Sambath | Defect | In profile when adding a new card or editing an expired/declined card under family pass information, upon completing changes, the tray is closed (similar to 24798 and 24815 and 24823) | Significant | Manual | Internal | Closed | Development | Client QA | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24823 MSBP - MAUI - Bottom sheet closes on editing information AutoPay screen (regression) | 24823 MSBP - MAUI - Bottom sheet closes on editing information AutoPay screen (regression) | Sambath | Defect | In autopay when adding a new card or editing an expired/declined card, upon completing changes, the tray is closed (similar to 24798 and 24815) | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24799 MSBP - MAUI - Android - cursor does not default to end on boxes with amounts in them by default | 24799 MSBP - MAUI - Android - cursor does not default to end on boxes with amounts in them by default | Gokul | Defect | In boxes, like the Quantity box in products, that are defaulted to an amount in them, first selection of box is before the input value instead of the end like Xamarin and iOS | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24798 MSBP - MAUI - Adding payment method at checkout closes tray | 24798 MSBP - MAUI - Adding payment method at checkout closes tray | Sambath | Defect | When adding a payment method through the payment methods tray at checkout, when returning the tray closes instead of remaining open to be able to select the new payment method like Xamarin does | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24797 MSBP - MAUI - Edit payment method not working as expected | 24797 MSBP - MAUI - Edit payment method not working as expected | Gokul | Defect | Editing payment method fields like the zipcode or address and clicking Save, Its showing card updated successfully but the update is not seems to be happening. | Minor | Manual | Internal | Closed | Development | Relevantz Dev | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24796 MSBP - MAUI - iOS - meal money autopay other box is cut off on right side of screen | 24796 MSBP - MAUI - iOS - meal money autopay other box is cut off on right side of screen | Sambath | Defect | when in the meal money autopay screen the other box is off the screen and cut off. (1 Test RJ District with only 4 options) using: iphone12 | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24792 MSBP - MAUI - Value Add Student appearing when after all students are deleted from household | 24792 MSBP - MAUI - Value Add Student appearing when after all students are deleted from household | Onsite | Defect | When you delete the last student from the household, value add student pop up appears. | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24826 MSBP - MAUI - Bottom sheet closes on editing information Family Pass sign up change payment method (regression) | 24826 MSBP - MAUI - Bottom sheet closes on editing information Family Pass sign up change payment method (regression) | Sambath | Defect | After checkout when presented with family pass offer, selecting a payment method and selecting add new payment method, upon completing changes or backing out, the tray is closed (similar to 24798 and 24815 and 24823 and 24824) | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24836 MSBP - MAUI -Family Pass User_Newly added payment method is not auto-checked in payment method drawers | 24836 MSBP - MAUI -Family Pass User_Newly added payment method is not auto-checked in payment method drawers | Sambath | Defect | Family Pass- In profile while changing payment method in family pass membership, adding a new payment method is not auto selected in the payment method drawers. Same issue exists in Family pass banner while activating a Family pass for a Non FP user. | Minor | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24846 MSBP - MAUI - Registration Result Drawer Dismiss Button is not on the bottom (regression) | 24846 MSBP - MAUI - Registration Result Drawer Dismiss Button is not on the bottom (regression) | Onsite | Defect | When there is an error adding a student or requesting student ID the Dismiss button is not located at the bottom of the sheet. | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 47477 MSBP - MAUI Only - Show Declined Payment Methods on Payment Method Screen 14.5 | 47477 MSBP - MAUI Only - Show Declined Payment Methods on Payment Method Screen 14.5 | Ashwin | Bounceback/Sub-Defect | I- View payment method not navigating to the payment method screen And app is not responding when autopay and payment method from hamburger selected. I/A - Payment method declined pop up showing twice in home screen I/A - The declined payment method pop up shows everytime after refreshing/loading. I/A - Lets add phone number pop up should come first before any pop up getting showed on Homescreen | Minor | Manual | Internal | Closed | Development | Relevantz QA | Issues found during the testing phase. May be a miss from development
| 14.6 M Sprint 1 | 24644 MSBP - Maui - Drawer issues | 24644 MSBP - Maui - Drawer issues | Onsite | Defect | Drawer related issues | Minor | Manual | Internal | Closed | Development | Client Dev | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24891 MSBP - MAUI - Prior purchase is removed when the student is changed in product details (regression) | 24891 MSBP - MAUI - Prior purchase is removed when the student is changed in product details (regression) | Ashwin | Defect | Prior purchase is removed when the student is changed in product details. Screenshot attached. | Minor | Manual | Internal | Closed | Development | Relevantz Dev | Xamarin to MAUi conversion
| 14.6 M Sprint 1 | 24827 - MSBP - MAUI - Prior purchase required items messaging cut off | 24827 - MSBP - MAUI - Prior purchase required items messaging cut off | Ashwin | Defect | When a product is set up with a prior purchase required, the messaging is cut off, including the link to the product needed | Minor | Manual | Internal | Closed | Development | Client QA | Xamarin to MAUi conversion

## 14.5 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(sp) | Actual(sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 | Sambath | 44583 | 44583 MSBP - Maui - Payment Success (Receipt) | Story Completed | 3 | 4 | 17 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40918 | 2025-02-24 | 2025-02-24 | Ashwin | NA | NA | NA | NA | NA | NA | Bounce back issue fixed
2 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 | Sambath | 24707 | 24707 MSBP - MAUI - iOS - Navigation icons disappear after navigating back to home screen | Defect Fixed | 1 | 1 | 6 | [15 empty] | Not able to reproduce on latest build so we are closing this defect
3 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 | Vaishnavi | 47075 | MSBP - MAUI - Login As Support | Story Completed | 2 | 2 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 | Gokul | 24660 | MSBP - MAUI - MFA Sizing Changes | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40891 | 2025-02-21 | 2025-02-21 | Ashwin | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 | Vaishnavi | 47155 | MSBP - Supplemental Fee(TEST) | Story Completed | 3 | 3 | 14 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40898 | 2025-02-21 |  | Client | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 | Vaishnavi | 47316 | REG - MSBP - 14.5 Regression | Story Completed | 5 | 5 | 19 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 | Vaishnavi | 47321 | MSBP / MSBA - Automation - Manual Run of Automation Tests | Story Completed | 3 | 3 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 | Gokul | 24638 | MSBP - MAUI - 3rd Party Login - Homepage Not Loading | Defect Fixed | 3 | 2.5 | 14 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40972 | 2025-02-27 | 2025-02-27 | Ashwin | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Sambath | 47306 | 47306 MSBP - Maui - Profile - Delete Account to Delete MySchoolBucks Account | Story Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40936 | 2025-02-25 |  | Ashwin | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 Stretch | Ashwin | 24721 | MSBP - MAUI - iOS - purchase controls not showing on add student | Defect Fixed | 1 | 1 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40962 | 2025-02-25 |  | Client | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 Stretch | Sambath | 24750 | 24750 MSBP - MAUI - Android - On first install do not get donations if only product in cart | Defect Fixed | 1 | 1 | 4 | [5 empty] | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40980 | 2025-02-26 | 2025-02-26 | Ashwin | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Sambath | 24755 | 24755 MSBP - MAUI - Payment history taking 9-12 seconds to open menu | Defect Fixed | 1 | 1 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40994 | 2025-02-27 | 2025-02-27 | Ashwin | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Gokul | 24754 | MSBP - MAUI - when selecting back on security question answer in profile, getting an error | Defect Fixed | 1 | 1 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41001?_a=files | 2025-02-27 | 2025-02-27 | Ashwin | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Ashwin | 24761 | MSBP - MAUI - iOS - Store page missing "no image" icon | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40994 | 2025-02-27 | 2025-02-27 | Ashwin | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Gokul | 24774 | MSBP - MAUI - iOS - Navigation bar icons are a different color when on the invoices tab | Defect Fixed | 2 | 2 | 13 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41066?_a=files | 2025-03-04 | 2025-03-04 | Ashwin | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Gokul | 24770 | MSBP - MAUI - Profile Security question 1 edit not saving the answer | Defect Fixed | 2 | 1 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41028 | 2025-02-28 | 2025-02-28 | Ashwin | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Sambath | 24791 | 24791 MAUI - Allows to Enter the Threshold Amount in Meal Money Settings Page Instead Input modal page | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41101?_a=files | 2025-03-05 | 2025-03-05 | Ashwin | NS | NA | NA | NA | NA | NA
16 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Gokul | 24797 | MSBP - MAUI - Edit payment method not working as expected | Defect Being Tested | 0.5 | 1 | 7 | NA | NA | NA | NA | NA |  | 2025-03-05 | 2025-03-05 | Ashwin | NS | NA | NA | NA | NA | NA
17 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Sambath | 24797 | 24796 MSBP - MAUI - iOS - meal money autopay other box is cut off on right side of screen | Defect Peer Review | 2 | 1 | 4 | NA | NA | NA | NA | NA |  | 2025-03-06 | 2025-03-06 | Ashwin | NS | NA | NA | NA | NA | NA
18 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 3 Stretch | Ashwin | 24780 | Back button on the input model is saving the amount on Invoice Partial payment field | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41059 | 2025-03-03 | 2025-03-03 | Client | NA | NA | NA | NA | NA | NA
19 | MSB Mobile | 2025-02-21 | 2025-03-06 | 14.5 M Sprint 3 Stretch | Ashwin | 24787 | ProductDeatils no image is cut off | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41085 | 2025-03-04 | 2025-03-04 | Client | NA | NA | NA | NA | NA | NA

## 14.5 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Who Reported It? | Comments
| 1 | 24780 MSBP - MAUI - Back button on the input model is saving the amount on Invoice Partial payment field | 24780 MSBP - MAUI - Back button on the input model is saving the amount on Invoice Partial payment field | Ashwin | Defect | Back button on the input model is saving the amount on Invoice Partial payment field | Significant | Manual | Internal | Closed | Development | Relevantz Dev | Xamarin to Maui conversion
| 2 | 24770 MSBP - MAUI - Profile Security question 1 edit not saving the answer | 24770 MSBP - MAUI - Profile Security question 1 edit not saving the answer | Gokul | Defect | Profile Security question 1 edit not saving the answer | Significant | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 3 | 24761 MSBP - MAUI - iOS - Store page missing "no image" icon | 24761 MSBP - MAUI - iOS - Store page missing "no image" icon | Ashwin | Defect | On the store page items with no image are missing the no image icon on the main store page (showing on all subsequent pages throughout checkout) | Significant | Manual | Internal | Closed | Development | Client QA | Xamarin to Maui conversion
| 4 | 24786 MSBP - MAUI - Request Student ID from Hamburger Menu not navigating as expected | 24786 MSBP - MAUI - Request Student ID from Hamburger Menu not navigating as expected | Onsite | Defect | When navigating to Request Student ID from the hamburger menu, instead of going directly into the request student workflow, use is presented with the "Add a student to your MySchoolBucks household" screen instead. | Significant | Manual | Internal | Closed | Development | Client Dev | Xamarin to Maui conversion
| 5 | 24787 MSBP- Maui - In Product screen, product with 'no image' is not showing the complete 'no image' icon. | 24787 MSBP- Maui - In Product screen, product with 'no image' is not showing the complete 'no image' icon. | Ashwin | Defect | MAUI- When user selects a product from store which has no image, the product screen is not showing the 'no image' icon fully. It is displaying only half of the 'no image' icon. | Significant | Manual | Internal | Closed | Development | Relevantz QA | Xamarin to Maui conversion

## 14.5 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 | Sambath | 44583 | 44583 MSBP - Maui - Payment Success (Receipt) | Story Being Developed | 5 | 18 | 18 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40701?_a=files | 2025-02-14 | 2025-02-14 | Ashwin | commented code removed | NA | NA | NA | NA | NA | story is get carried due to crash issues and testing feedback Tried to fix the calendar event issue in android. but it is not working. so i reverted back Working on Bounce backs Products with add on fees cause app to crash iOS- missing thumbs up icon on receipt Android- missing school indication under student name for meal money should be additional space between thank you and order # crash when there is a broken gateway instead of directing to receipt page with error message crash when there are certain items in cart (at one District No Amex is causing crash as well as ApprovalDonation)
2 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 | Vaishnavi/Ashwin | 46407 | MSBP - MAUI - Checkout - TEST | Story Completed | 3 | 6 | 29 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40714 | 2025-02-12 | 2025-02-12 | Client |  | NA | NA | NA | NA | NA | Bounce backs added
3 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 | Gokul | 44575 | MSBP - Maui - GL Sign Up | Story Completed | 2 | 1 | 6 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40699?_a=files | 2025-02-07 | 2025-02-07 | Ashwin | Add missing resource values | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 | Gokul | 45093 | [FAMILYPASS] MSBP - MAUI - FamilyPass | Story Completed | 8 | 7 | 39 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40777 https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40863 | 2025-02-14 | 2025-02-14 | Ashwin | NA | NA | NA | NA | NA | NA | Bouncebacks added
5 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 | Ashwin | 46331 | MSBP - Maui - Shopping Cart screen | Story Completed | 3 | 3 | 17 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40775 | 2025-02-13 |  |  |  | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Vaishnavi | 47177 | MSBP - MAUI - Test Current 'Needs Testing' ITEMS to Verify Fixes | Story Completed | 3 | 5 | 5.2
7 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Vaishnavi | 47155 | MSBP - Supplemental Fee(TEST) | Story Being Developed | 2 | 2 | 13 | [15 empty] | The PI team is working on Defect 24598 MSBP - API - Supplemental Fee not applied in basket. It seems like the change they are making will need a code change in the mobile app. So testing for this story will have to be put on hold.
8 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Sambath | 24694 | 24694 MSBP - Maui - Delete Account on profile screen not centered within white box | Story Completed | 1 | 4 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40792 | 2025-02-17 | 2025-02-17 | Sean Jacquelin | NA | NA | NA | NA | NA | NA
9 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Sambath | 24661 | 24661 MSBP - MAUI - Android - Cart Icon Badge is offset | Defect Fixed | 1 | 4 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40826 | 2025-02-18 | 2025-02-18 | Sean Jacquelin | NA | NA | NA | NA | NA | NA | Defect has been tested by Client after the sprint meeting and closed it.
10 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Sambath | 24706 | 24706 MSBP - Maui - Cart reorder when donation is added on multidistrict (pre-existing) | Defect Being Fixed | 2 |  | 5
11 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Sambath | 24707 | 24707 MSBP - MAUI - iOS - Navigation icons disappear after navigating back to home screen | Defect Being Fixed | 2 | 4 | 5
12 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Vaishnavi | 46596 | MSBP - Maui - Test Languages | Defect Fixed | 2 | 2 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Gokul | 24705 | MSBP - Maui - Hamburger menu in different styles within tabs | Defect Fixed | 1 | 1 | 3 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40849 | 2025-02-19 | 2025-02-19 | Ashwin | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Gokul | 24640 | MSBP - MAUI - Add Meal Money - Other Amount - Disappears | Defect Fixed | 0.5 | 1 | 6 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40811 | 2025-02-18 | 2025-02-18 | Ashwin | NA | NA | NA | NA | NA |  | Defect has been tested by Client after the sprint meeting and closed it.
15 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Gokul | 24709 | MSBP - MAUI - iOS - Meal money preset amounts > 8 or having more than 2 rows not scrollable | Defect Fixed | 0.5 | 0.5 | 3 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40838 | 2025-02-19 | 2025-02-19 | Ashwin | NA | NA | NA | NA | NA | NA | Defect has been tested by Client after the sprint meeting and closed it.
16 | MSB Mobile | 2025-02-07 | 2025-02-20 | 14.5 M Sprint 2 Stretch | Gokul | 24654 | MSBP-Maui- Quicklinks_Bluebar is not showing under the corresponding page | Defect Fixed | 0.5 | 0.5 | 3 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40869 | 2025-02-20 | 2025-02-20 | Ashwin | NA | NA | NA | NA | NA | NA | Defect has been tested by Client after the sprint meeting and closed it.

## 14.5 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| 14.5 M Sprint 2 | 46407 MSBP - MAUI - Checkout - TEST | 46407 MSBP - MAUI - Checkout - TEST | Ashwin | Bounceback/Sub-Defect | 1.Maui-I/A- Headers like Product, Meal money and invoices are not left aligned. It is center aligned 2.Maui-I/A- Promocode- 'Enter Text' is not center aligned in the textbox. Space between promocode textbox and apply button 3.Maui-I/A- Payment method tray not showing the program fee and TBD text when opening 4.Maui-I/A- after adding new payment method from the drawer, the payment drawer closes | Significant | Manual | Internal | Defect Fixed | Existing_Issues | Due to Xamarin to Maui conversion, facing these issues
| 14.5 M Sprint 2 | 44575 MSBP - Maui - GL Sign Up | 44575 MSBP - Maui - GL Sign Up | Gokul | Bounceback/Sub-Defect | Prices not updated to 5.99 A- missing the carousel navigation to indicate there are multiple pages missing the & replacement instead of "and" in the carousel i- presented with the tray to link card twice on return to app from sign up Assign GL card tray is showing on top of the update profile screen | Significant | Manual | Internal | Defect Fixed | Development | minor issues missed during development
| 14.5 M Sprint 2 | 45093 - [FAMILYPASS] MSBP - MAUI - FamilyPass | 45093 - [FAMILYPASS] MSBP - MAUI - FamilyPass | Gokul | Bounceback/Sub-Defect | Maui-I/A- App crash while doing checkout( Mealmoney+Product+Invoice) Maui-I/A- FP is not maximized in Homescreen when logged in as a Family Pass activated user. It is minimized. Whereas in Xamarin, it is maximized while logged in | Significant | Manual | Internal | Defect Fixed | Existing_Issues | Configuration issues
| 14.5 M Sprint 2 Stretch | 24640 MSBP - MAUI - Add Meal Money - Other Amount - Disappears | 44576 MSBP - Maui - Meal Money - Add Money screens | Gokul | Defect | when using other amount, the amount disappears on return to add meal money screen | Significant | Manual | Internal | Defect Fixed | Existing_Issues | Issues caused during Maui to Xamarin conversion
| 14.5 M Sprint 2 Stretch | 24709 MSBP - MAUI - iOS - Meal money preset amounts > 8 or having more than 2 rows not scrollable | MAUI Conversion | Gokul | Defect | iOS specific issue in Cart page edit meal money | Significant | Manual | Internal | Defect Fixed | Existing_Issues | Issues caused during Maui to Xamarin conversion
| 14.5 M Sprint 2 Stretch | 24705 MSBP - Maui - Hamburger menu in different styles within tabs | MAUI Conversion | Gokul | Defect | Home and Add funds page have smaller hamburger menu size | Significant | Manual | Internal | Defect Fixed | Existing_Issues | Issues caused during Maui to Xamarin conversion
| 14.5 M Sprint 2 Stretch | 24654 MSBP-Maui- Quicklinks_Bluebar is not showing under the corresponding page | MAUI Conversion | Gokul | Defect | Switch tab to corresponding pages | Significant | Manual | Internal | Defect Fixed | Existing_Issues | Issues caused during Maui to Xamarin conversion
| 14.5 M Sprint 2 Stretch | 24665 MSBP - MAUI - Scheduled Payments - Long Names Cut off in Scheduled Payments (Small phone issue) | 24665 MSBP - MAUI - Scheduled Payments - Long Names Cut off in Scheduled Payments (Small phone issue) | Vaishnavi | Defect | Scheduled Payments: Saw this on a particular pixel - long names and short screens are cut off | Significant | Manual | Internal | Defect Fixed | Existing_Issues | Issues caused during Maui to Xamarin conversion
| 14.5 M Sprint 2 Stretch | 24659 - MSBP - MAUI - Meal Money Settings - Done Button Wrong Size | MAUI Conversion | Ashwin | Defect | Done Button Wrong Size and alignment issues | Significant | Manual | External | Defect Fixed | Existing_Issues | Issues caused during Maui to Xamarin conversion
| 14.5 M Sprint 2 Stretch | 24694 MSBP - Maui - Delete Account on profile screen not centered within white box | 44558 MSBP - Maui - Profile | Vaishnavi | Defect | On the profile screen the delete account is at the top of the white box instead of centered (note: tested on non-family pass account if it matters) | Significant | Manual | External | Defect Fixed | Existing_Issues | Issues caused during Maui to Xamarin conversion
| 14.5 M Sprint 2 Stretch | 24708 MSBP - MAUI - iOS - Clicking Other amount in Edit meal amount from cart page not opening the Input page | MAUI Conversion | Ashwin | Defect | Clicking Other amount in Edit meal amount from cart page, it is not opening the Input page where we enter the amount | Significant | Manual | External | Defect Being Fixed | Existing_Issues | Issues caused during Maui to Xamarin conversion

## 14.5 M Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Hours Worklog | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2025-01-24 | 2025-02-06 | 14.5 M Sprint 1 | Sambath | 44571 | 44571 MSBP - Maui - AutoPay Settings screen / Meals Auto Pay | Story Completed | 2 | 2 | 13 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40520?_a=files | 2025-01-28 | 2025-01-28 | NA | NA | NA | NA | NA | NA | NA | Bounce back issue is got fixed
2 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 1 | Ashwin | 46406 | MSBP - MAUI - Checkout (Dev Only) | Story Completed | 3 | 3 | 39 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40596 | 2025-01-31 | 2025-02-03 | Client | 1.We should split these up into their respective classes at some point e.g. StudentExtension 2.Null check all the things, BasketPreview 3.Do we need to carry this around on the AppSession? | NA | NA | NA | NA | NA | Had to work on additional functionalities like building the data for receipts and supplemental fees. Also had local environment and firbase nuget package restore issues which consumed lot of effort.
3 | MSB Mobile | 2025-01-24 | 2025-02-06 | 14.5 M Sprint 1 | Vaishnavi | 46879 | MSBP - Smoke Test Prod apps against MSB 14.4 RC in Staging | Story Completed | 1 | 1 | 3.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2025-01-24 | 2025-02-06 | 14.5 M Sprint 1 | Vaishnavi | 44555 | MSBP - Maui - Suggested students drawer (New suggested students detected) | Story Completed | 2 | 2 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2025-01-24 | 2025-02-06 | 14.5 M Sprint 1 | Vaishnavi | 44556 | MSBP - Maui - Student Drawer | Story Completed | 2 | 2 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2025-01-24 | 2025-02-06 | 14.5 M Sprint 1 | Vaishnavi | 44567 | MSBP - Maui - Edit image on home screen | Story Completed | 2 | 2 | 6.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 1 Stretch | Gokul | 44575 | MSBP - Maui - GL Sign Up | Story Being Developed | 2 | 2 |  | NA | NA | NA | Sambath | Remove commented code in Homepage | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40476 | 2025-01-24 | NA | NA | NA | NA | NA | NA | NA | NA | Working on the bouncebacks.
8 | MSB Mobile | 2025-01-24 | 2025-02-06 | 14.5 M Sprint 1 Stretch | Gokul | 46346 | MSBP - Maui - GL Landing Screen | Story Completed | 5 | 5 | 32 | NA | NA | NA | Ashwin | Add Null check GreenlightStudentBalances | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40592 | 2025-01-31 | 2025-02-04 | Sean | - Use the ValueCompletionSource - Use the return type of the sheet instead of using a message - Use RadCollectionView instead of RadListView - Remove ContentView | NA | NA |  |  |  | Worked on Code review comments after PR is created.
9 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 1 Stretch | Gokul | 44575 | [FAMILYPASS] MSBP - MAUI - FamilyPass | Story Being Developed | 8 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 1 Stretch | Sambath | 44583 | 44583 MSBP - Maui - Payment Success (Receipt) | Story Being Developed | 5 | 5 | 22 | NA | NA | NA | [12 empty] | Most of dev has been completed, and currently fixing the UI issues
11 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.5 M Sprint 1 Stretch | Ashwin | 45879 | MSBP - MAUI - Supplemental Fee(Dev Only) | Story Completed | 3 | 3 | 10 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40596 | 2025-02-05 | 2025-02-06 | Client | NA | NA | NA | NA | NA | NA | Dev completed and
12 | MSB Mobile | 2025-01-24 | 2025-02-06 | 14.5 M Sprint 1 Stretch | Vaishnavi | 46407 | MSBP - MAUI - Checkout - TEST | Story Ready For Testing | 3 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Test Cases modified based on the review comments.
13 | MSB Mobile | 2025-01-24 | 2025-02-06 | 14.5 M Sprint 1 Stretch | Vaishnavi | 46596 | MSBP - Maui - Test Languages | Story Being Tested | 2 | 0.75 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 14.5 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Reason * | Comments
1 | 14.5 Sprint 1 | 44555 MSBP - Maui - Suggested students drawer (New suggested students detected) | Onsite | Bounceback | Maui -I/A - Suggested student drawers not getting displayed after login in Maui version 14.4.0.87 | Significant | Internal | Closed | Development | Some issues with deploying the code in the Maui version
2 | 14.5 Sprint 1 | 44567 MSBP - Maui - Edit image on home screen | Onsite | Bounceback | 1.Maui-I/A:Adding or Removing or editing from student menu does not update in student drawer but in homepage it is getting updated(When student drawer is minimised to half ) 2.Maui- I : student drawer- After taking photo, screen is not redirected to the next step(Crop/ save photo screen) | Significant | Internal | Closed | Development | Development related. Maui version not working as Xamarin.
3 | 14.5 Sprint 1 | 44571 MSBP - Maui - AutoPay Settings screen / Meals Auto Pay | Sambath | Bounceback | 1.Maui-I/A- Autopay toggle button not showing in Meal money autopay screen 2.Maui-A- App crash while selecting dates from date picker in a meal money autopay screen 3 .Maui-I/A- When a new payment method is added for a new user from the Mealmoney autopay screen, the added payment method is not showing. 4..Maui-I- Meal money autopay settings-Date picker field is not showing the labels | Significant | Internal | Closed | Development | Issue occured Due to continous deployment. It was working fine in previous versions and Refresh issue
4 | 14.5 Sprint 1 | 44575 MSBP - Maui - GL Sign Up | Gokul | Bounceback | 1. Prices not updated to 5.99 2. A- missing the carousel navigation to indicate there are multiple pages missing the & replacement instead of "and" in the carousel 3. i- presented with the tray to link card twice on return to app from sign up 4. Assign GL card tray is showing on top of the update profile screen | Significant | External | Inprogress | Existing_Issues | Issue related to telerik control. Also latest changes in Xamarin has to be updated in MAUI.
5 | 14.5 Sprint 1 Stretch | 46596 MSBP - Maui - Test Languages | Onsite | Bounceback | Maui-I/A- MSBP application is not showing the language in arabic/vietnamese when language is set in phone settings | Significant | External | Inprogress | Development | Already this change was working in Xamarin, In maui not working.

## 14.4 M Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 3 | Vaishnavi | 46877 | REG - MSBP - 14.4 Regression | Story Completed | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 3 | Vaishnavi | 46880 | MSBP / MSBA - Automation - Update, Run, Check & Fix Any Automation Failures | Story Completed | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 3 | Ashwin | 46768 | MSBP - Profile - Do Not Save Phone When Already In Use | Story Completed | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 3 Stretch | Ashwin | 46406 | MSBP - MAUI - Checkout (Dev Only) | Story Being Developed | 5 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Dev in Progress
5 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 3 Stretch | Gokul | 44575 | MSBP - Maui - GL Sign Up | Story Being Developed | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Edit GL account page header image to be centered. | Development completed and POV has been shown. But when merging to latest lot of conflict occured and after merging there is lot of reference issue & build issues. Working in progress.(Issues caused by changes implemented for Firebase analytics).
6 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 3 Stretch | Sambath | 46893 | 46893 MSBP - Maui - Shopping Cart Screen - .NET9 Fixes (Dev Only) | Story Peer Review | 3 |  | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40455?_a=files | 2025-01-23 | 2025-01-23 | NA | NA | NA | NA | NA | NA | NA | Dev completed
7 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 3 Stretch | Vaishnavi | 44570 | MSBP - Maui - AutoPay drawer activated via Meals card | Story Completed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 14.4 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Reason * | Comments
1 | 14.4 M Sprint 3 | 24520 MSBP - iOS/Android - Login fails when user tries to use newly updated password from profile menu (regression) | Onsite Developer | Defect | Issues identified during regression | Significant | Internal | Closed | Environment_Related | API related issue. This issue has been fixed by PI team.
2 | 14.4 M Sprint 3 | 24521 MSBP - iOS/Android - User is not getting listed under in Push notification registration screen in Staging web (regression) | Onsite Developer | Defect | Issues identified during regression | Minor | Internal | Open | Environment_Related | Issue is not working in the deployed version. Previous versions it worked
3 | 14.4 M Sprint 3 | 24522 MSBP - iOS/Android - When new user logins, page is not directed to the Add phone number screen (regression) | Onsite Developer | Defect | Issues identified during regression | Minor | Internal | Open | Environment_Related | Issue is not working in the deployed version. Previous versions it worked
4 | 14.4 M Sprint 3 | 24538 MSBP - Android - Autopay subscription screen- Student name is broken(regression) | Onsite Developer | Defect | Issues identified during regression | Minor | Internal | Open | Existing_Issues | In Android Pixel 4a, this issue exists. Mostly a screensize issue
5 | 14.4 M Sprint 3 Stretch | 24571-MSBP - Maui - AutoPay Settings screen / Meals Auto Pay | Sambath | Bounceback | iOS- While selecting payment method from meal money autopay settings screen, it is not navigating to the add payment method screen | Minor | Internal | Open | Development

## 14.4 M Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 | Vaishnavi | 44559 | MSBP - Maui - Payment history | Closed | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed
2 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 | Sambath | 44581 | MSBP - Maui - Invoices - Invoice Payment options screens | Closed | 3 | 3 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40237?_a=files | 2025-01-08 | 2025-01-08 | Sean | Repalced wtih Vertical and HorizotalLayout instead of StackLayout | NA | NA | NA | NA | NA
3 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 | Gokul | 46294 | MSBP - Maui - Meal Money Notification Settings | Closed | 2 | 2 | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 | Gokul | 44563 | MSBP - Maui - Request balance transfer - Bounceback Issues fix | Closed | 2 | 2 | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40141 | 2024-12-23 | 2024-12-23 | Ashwin | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 | Ashwin | 46774 | MSBP - GL - Text Update Carousel - Update Price in Text | Closed | 1 | 1 | Done | NA | NA | Client | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/40095 | 2024-12-17 | 2024-12-17 | Sean | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 Stretch | Gokul | 44560 | MSBP - Maui - Scheduled Payments | Closed | 5 | 6 | Done | NA | NA | Ashwin | Remove commented and unused code | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40167 | 2025-01-06 | 2025-01-06 | Sean | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 Stretch | Sambath | 44571 | MSBP - Maui - AutoPay Settings screen / Meals Auto Pay | Inprogress | 5 | 5 | NA | NA | NA | Ashwin |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/39236 | 2025-01-09 | 2025-01-09 | Sean | Replaced wtih Vertical and HorizotalLayout instead of StackLayout | [5 empty] | Development completed, Testing is Inporgress.
8 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 Stretch | Ashwin | 44570 | MSBP - Maui - AutoPay drawer activated via Meals card | Inprogress | 3 | 3 | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40208 | 2025-01-06 | 2025-01-06 | Sean | Replace stacklayout with horizontal/vertical | NA | NA | NA | NA | NA
9 | MSB Mobile | 2026-05-15 | 2026-05-28 | 14.4 M Sprint 2 Stretch | Gokul | 44575 | MSBP - Maui - GL Sign Up | Inprogress | 5 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 14.4 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Reason * | Comments
1 | 14.4 M Sprint 2 | 44563 MSBP - Maui - Request balance transfer | Ashwin | Bounceback | 1.Maui-ios/android.- Allows user to update amount when 'From' account is 0. 2.Maui-iOS- Not receiving any warning message in Maui ios as in Xamarin. | Minor | Internal | Closed | Existing_Issues | Testing by comparing the older version Xamarin and newer Maui version, found these issues in the new version | Issues occuring with newer versions in MUAI when comparing with Xamarin on the devices
2 | 14.4 M Sprint 2 | 44581 MSBP - Maui - Invoices - Invoice Payment options screens | Sambath | Bounceback | 1.Maui-I/A- Payment option- After selecting payment option drop down, a drawer opens. While tapping in the background, it does not closes the drawers. 2.Maui-I/A- Installment plan drawer does not shows the header as "Installment Plan" 3.Maui-I/A-Payment amount field shows inside text as "Payment amount". whereas in xamarin it shows $0.00 4.Maui-I/A- If Invoice name has more characters, while displaying in the 'Pay Invoice' Screen, the name is overlapped. | Minor | Internal | Closed | Development | Testing by comparing the older version Xamarin and newer Maui version, found these issues in the new version | Issues occuring with newer versions in MUAI when comparing with Xamarin on the devices
3 | 14.4 M Sprint 2 Stretch | 44570 MSBP - Maui - AutoPay drawer activated via Meals card | Ashwin | Bounceback | Maui-I/A - While selecting the expired meal money icon from Student meal card, the expired icon in the drawer is not aligned properly. | Minor | Internal | Closed | Development | Alignment issue | Issues occuring with newer versions in MUAI when comparing with Xamarin on the devices
4 | 14.4 M Sprint 2 Stretch | 44560 MSBP - Maui - Scheduled Payments | Gokul | Bounceback | 1.Maui - I/A - No pop ups with 'Dismiss' button when pop up with dismiss button after successful payment method update. 2.Maui - I/A - While selecting Expired CC payment method, screen directed to "Edit payment method' screen. User unable to go back while tapping the back arrow | Minor | Internal | Closed | Existing_Issues | Testing by comparing the older version Xamarin and newer Maui version, found these issues in the new version | Bouncebacks are acceptable as discussed with client and story has been closed.

## 14.4 M Sprint 1-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 14.4 M Sprint 1 | Vaishnavi | 46638 | MSBP / MSBA - Automation - Update, Run, Check & Fix Any Automation Failures | Closed | 8 | 8.3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | 14.4 M Sprint 2 | Sambath | 44581 | MSBP - Maui - Invoices - Invoice Payment options screens | Inprogress | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Client decided to go with MAUI controls instead of telerik for Datepicker and Input Modal entry control due to the long time blocker. so based on that completed the devlopment and shown POV. Code Cleanup and Code Review Pending
3 | 14.4 M Sprint 1 Stretch | Gokul | 46294 | MSBP - Maui - Meal Money Notification Settings | Inprogress | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Due to input model change, app crashing in Ios/android device in the latest maui version. Also the mentioned bounceback issue is not reproduced when Ashwin tested on his end.
4 | 14.4 M Sprint 1 Stretch | Sambath | 44571 | 44571 MSBP - Maui - AutoPay Settings screen / Meals Auto Pay | Inprogress | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Client decided to go with MAUI control Datepicker instead of Telerick. the Datepicker implemented in 44581 story. so once the Invoice payment options story (44581) is moved to main branch then, will continue to work on this story.
5 | 14.4 M Sprint 1 Stretch | Gokul | 44560 | MSBP - Maui - Scheduled Payments | Inprogress | 8 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | 14.4 M Sprint 1 Stretch | Vaishnavi | 44564 | MSBP - Maui - Request Refund | Closed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Scope is only for Testing in this sprint. Testing completed.
7 | 14.4 M Sprint 1 Stretch | Ashwin | 46562 | GSOC - Parent App - Confirmation, Text Update | Closed | 2 | 2
8 | 14.4 M Sprint 1 Stretch | Vaishnavi | 44559 | MSBP - Maui - Payment history | Inprogress | 2 |  | NA | NA | Bouncebacks added | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Due to input model change, drawers and filters are not behaving as expected.

## 14.4 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Reason * | Comments
1 | 14.4 M Sprint 1 Stretch | 46294-MSBP - Maui - Meal Money Notification Settings | Gokul | Bounceback | Maui- I/A Warning message continuously throwing while saving the amount on low balance field, daily and weekly spending amount field, also while Disabling all the fields. | Significant | Internal | Open | Environment_Related | Issue is partially reproduced and possible reason may be latency. Because when checked from US it didn't show the exception popup.
2 | 14.4 M Sprint 1 Stretch | 44563 MSBP - Maui - Request balance transfer | Ashwin | Bounceback | 1.Maui-iOS- Not receiving any warning message in Maui ios as in Xamarin. 2.Maui-iOS- Upon selecting 'Transfer Now' and when user selects 'No,Go back' , directed to Homepage instead of Meal money screen 3.Maui-iOS, Upon selecting 'Transfer Now' and when user selects 'Yes,Make transfer request' , directed to Home screen instead of showing the balance transfer successful screen 4.Maui-Android- The warning message content differs in Maui and Xamarin. Attached screenshot for reference | Significant | Internal | Open | Environment_Related | There are issues related to nput modal page being crashed due to dotnet 9 and telerik update.
3 | 14.4 M Sprint 1 Stretch | 44559 MSBP - Maui - Payment history | Gokul | Bounceback | Maui-I/A- Drawers in payment history shows extra space in iOS and Android devices. | Significant | Internal | Open | Environment_Related | Bottomsheet related issues.

## 14.3 M Sprint 3-Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 14.3 M Sprint 3 | Vaishnavi | 46484 | REG - MSBP - 14.3 Regression | Inprogress | 13 | 5 | NA | NA |  | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Blocked due to an Greenlight issue reported by Letashia.
2 | 14.3 M Sprint 3 | Ashwin | 44564 | MSBP - Maui - Request Refund | Inprogress | 1 |  | Done |  |  |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39773 | [9 empty] | Blocked due to Dotnet9 update causing the bottom sheet issues
3 | 14.3 M Sprint 3 | Gokul | 46230 | [GSOC] MSBP - OTP - Profile - Edit Phone Number Workflow (Xamarin) | Closed | 3 | 3 | Done | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/39756 | 2024-11-15 | 2024-11-15 | Ashwin | NA | Sean | NA | NA | NA | NA
4 | 14.3 M Sprint 3 | Gokul | 46531 | MSBP - GSOC - Delete Phone number - Hook up to API | Closed | 1 | 1 | Done | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/39756 | 2024-11-15 | 2024-11-15 | Ashwin | NA | Sean | NA | NA | NA | NA
5 | 14.3 M Sprint 3 Stretch | Sambath | 44581 | MSBP - Maui - Invoices - Invoice Payment options screens | Inprogress | 8 |  | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | Blocked due to Dotnet9 update causing the bottom sheet issues
6 | 14.3 M Sprint 3 Stretch | Ashwin | 44563 | MSBP - Maui - Request balance transfer | Inprogress | 2 |  | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39773 | 2024-11-20 |  | Client | NA | NA | NA | NA | NA | NA | Blocked due to Dotnet9 update causing the bottom sheet issues
7 | 14.3 M Sprint 3 Stretch | Sambath | 44571 | 44571 MSBP - Maui - AutoPay Settings screen / Meals Auto Pay | Inprogress | 3 | [16 empty] | Bottom sheet and some custom control is not working due to the .Net 9 update, so this story is got blocked
8 | 14.3 M Sprint 3 Stretch | Gokul | 46294 | MSBP - Maui - Meal Money Notification Settings | Inprogress | 5 |  | Done | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39887 | 2024-11-27 | 2024-11-28 | Sean | JSON prop names need to match with case sensitivity to the return | Avery | 2024-11-28 | Remove commented code. | NA | NA | Dev completed, but holded in testing due to release issue in azure pipeline.
9 | 14.3 M Sprint 3 Stretch | Gokul | 44559 | MSBP - Maui - Payment history | Inprogress | 5 |  | Done | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39887 | 2024-12-02 |  | Ashwin | Remove commented code | NA | NA | NA | NA | NA | Blocked due to Dotnet9 update causing the bottom sheet issues
10 | 14.3 M Sprint 3 Stretch | Gokul | 44560 | MSBP - Maui - Scheduled Payments | Inprogress | 5

## 14.3 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.3 M Sprint 3 | 24304-MSBP - iOS/Android - Cannot load profile after removing autopay on family pass enabled account (regression) | Ashwin | regression | When user is a family pass member, but disables the auto renew, the profile page gets stuck with loading symbol | Major | External | Closed | Design
2 | 14.3 M Sprint 3 | 24305-MSBP - iOS/Android - Cannot select any fields in meal money autopay if not enabled | Ashwin | regression | Toggle at top of the page which is present on accounts with active autopay which shows enabled/disabled appears to be missing | Major | External | Closed | Development
3 | 14.3 M Sprint 3 | 44564 MSBP - Maui - Request Refund | Ashwin | Bounceback | 1.Maui-I: User trying to submit a refund request for a student whose transfers are limited in not showing the error message as expected. Instead a generic "District not accepting refund request" message is getting displayed. 2.Maui- A: App crashes when user select 'Student' on Refund Request screen | Significant | External | Inprogress | Development | These issues are due to bottomsheet not working after .net9 update
4 | 14.3 M Sprint 3 | 24330 MSBP - iOS/Android - User is not redirected to MFA screen when tries to login after password reset(regression) | Vaishnavi | regression | When user reset the password using 'Forgot username or password' and tries to login using the username and newly created password, it is not redirected to MFA process. Directly allows user to login. | Significant | External | Open

## 14.3 M Sprint 2- Status
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 14.3 M Sprint 2 | Vaishnavi | 44572 | MSBP - Maui - Meals Money from student card | Closed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | 14.3 M Sprint 2 | Sambath | 44580 | MSBP - Maui - Invoices - Pay Invoices | Closed | 5 | 5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39645 | 2024-11-08 | 2024-11-08 | NA | NA | NA | NA | NA | NA | NA
3 | 14.3 M Sprint 2 | Gokul | 46202 | [GSOC] MSBP - OTP - Add Phone Number Workflow (demo mode) (Xamarin) | Closed | 0.5 | 0.5 | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/39579 | 2024-11-04 | 2024-11-04 | Ashwin | NA | NA | NA | NA | NA | NA | Bounceback fixed and moved to testing
4 | 14.3 M Sprint 2 | Gokul | 46435 | MSBP - GSOC - API hookup to Verification (Missing phone Number workflow) | Inprogress | 3 | 3 | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/39656 | 2024-11-08 | 2024-11-08 | Ashwin | NA | NA | NA | NA | NA | NA | Development completed and moved to testing Bouncebacks: - Missing security questions and phone number should come before add student workflow - Appears to be a race condition- when I received add student before missing security question, never got missing security question at all - "message and data rates...." message appears to be the same size as "secure your account.." instead of a smaller size - "Do Not Show Again" button does not respond/ do anything BB issues are fixed and moved to testing.
5 | 14.3 M Sprint 1 Stretch | Sambath | 44581 | MSBP - Maui - Invoices - Invoice Payment options screens | Inprogress | 8 | 8 | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA | NA | NA | NA | Development completed, but naviagtion service not wokring as expected so client looking the issue
6 | 14.3 M Sprint 2 | Gokul | 46230 | [GSOC] MSBP - OTP - Profile - Edit Phone Number Workflow (Xamarin) | Inprogress | 5 | 5 | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/39671 | 2024-11-13 | 2024-11-13 | Ashwin | NA | NA | NA | NA | NA | NA | Development completed Bouncebacks: - when editing an existing phone to opt in, toggle is enabled but dont get the text yes to join - when going through new account in profile to add phone number, selecting opt in is not toggling the text alerts button - if using the toggle to turn on text alerts it should be directed to the edit mobile number screen instead of enter mobile number Existing BB fixed, but due to some pending clarifications required, development will be continued on next sprint
7 | 14.3 M Sprint 2 | Ashwin | 44564 | MSBP - Maui - Request Refund | Inprogress | 5 | [6 empty] | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39715 | 2024-11-13 | 2024-11-13 | Client | NA | NA | 2024-11-13 | NA | NA | NA | Testing has been delayed due to a deployment issue in the build pipeline, and testing is now awaiting.
9 | 14.3 M Sprint 2 Stretch | Gokul | 46294 | MSBP - Maui - Meal Money Notification Settings | Inprogress | 5 | 1 | InProgress | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Due to GSOC priority story, development for this story will be continued to next sprint

## 14.3 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.3 M Sprint 2 | 44572-MSBP - Maui - Meals Money from student card | Vaishnavi | Bounceback | Maui-IOS/Android- Cafeteria history data is not getting displayed in Meal Money screen. Attached screenshot for reference. | Significant | External | Closed |  | Bounceback retested and closed.
2 | 14.3 M Sprint 2 | 46202 - [GSOC] MSBP - OTP - Add Phone Number Workflow (demo mode) (Xamarin) | Gokul | Bounceback | Save and confirm button click not redirecting to home page | Significant | Enternal | InProgress |  | BB fixed and moved to testing
3 | 14.3 M Sprint 2 | 44564-MSBP - Maui - Request Refund | Ashwin | Bounceback | 1.Maui-IOS- version 14.3.0.22. After submitting the refund request, in the "Refund request successfully submitted'' message, the "thumbsup" icon is not showing. In android it is showing. 2.Maui-I/A : User trying to submit a refund request for a student who is not eligible for refund request is not showing any error message as expected | Significant | Enternal | InProgress
4 | 14.3 M Sprint 2 | 44580-MSBP - Maui - Invoices - Pay Invoices | Sambath | Bounceback | Maui -Android - version 14.3.0.23 In android phone, the 'Add to cart ' button is not completely displayed as in Xamarin. | Significant | Enternal | Closed
5 | 14.3 M Sprint 2 | 46435 - MSBP - GSOC - API hookup to Verification (Missing phone Number workflow) | Gokul | Bounceback | Save and confirm button click not redirecting to home page | Significant | Enternal | InProgress |  | BB fixed and moved to testing
6 | 14.3 M Sprint 2 | 46230 - [GSOC] MSBP - OTP - Profile - Edit Phone Number Workflow (Xamarin) | Gokul | Bounceback | Save and confirm button click not redirecting to home page | Significant | Enternal | InProgress |  | Existing BB fixed, but due to some pending clarifications required, development will be continued on next sprint

## 14.3 M Sprint 1- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.3 M Sprint 1 | Sambath | S-44561 | 44561 MSBP - Maui - Payment Methods | 3 | 3 | NA | NA | NA | Gokul | 1. Remove the code: var responseStr = await msg.Content.ReadAsStringAsync(); in RemoteEndpoint.cs 2. Remove MainThread.BeginInvokeOnMainThread in Before() logic in API calls. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39462 | 25-10-2024 | 24-10-2024 | Ashwin | NA | NA | NA | NA | NA | NA | Closed
2 | 14.3 M Sprint 1 Stretch | Gokul | S-46202 | [GSOC] MSBP - OTP - Add Phone Number Workflow (demo mode) (Xamarin) | 5 | 5 | Done | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/39526 | 29-10-2024 | 30-10-2024 | Ashwin | Add required resource | NA | NA | NA | NA | Add error validation in phone number entry field(Additional change) | Inprogress | Dev completed and testing pending
3 | 14.3 M Sprint 1 Stretch | Sambath | S-44580 | MSBP - Maui - Invoices - Pay Invoices | 5 | 5 | [15 empty] | Inprogress | continue to working on MAUI. Bussiness logics completed, working on UI Binidngs
4 | 14.3 M Sprint 1 | Vaishnavi | S-44572 | MSBP - Maui - Meals Money from student card | 3 | 3 | NA | Vaishnavi | Maui-IOS/Android- Cafeteria history data is not getting displayed in Meal Money screen. Attached screenshot for reference. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress
5 | 14.3 M Sprint 1 Stretch | Ashwin | S-44564 | 44564 MSBP - Maui - Request Refund | 5 |  | Done |  |  |  | NA | [10 empty] | Inprogress
6 | 14.3 M Sprint 1 | Ashwin | S-44576 | 44576 MSBP - Maui - Meal Money - Add Money screens | 2 | 2 | Done | [14 empty] | Closed
7 | 14.3 M Sprint 1 | Vaishnavi | S-46191 | MSBA - Smoke Test Prod apps against MSB 14.2 RC in Staging | 2 | 2 | NA | Vaishnavi | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
8 | 14.3 M Sprint 1 | Vaishnavi | S-46192 | MSBP CA - Smoke Test Prod apps against MSB 14.2 RC in Staging | 2 | 2 | NA | Vaishnavi | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
9 | 14.3 M Sprint 1 | Vaishnavi | S-46193 | MSBP CA - Regression/Smoke Test 14.2 against MSB RC in Staging | 2 | 2 | NA | Vaishnavi | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
10 | 14.3 M Sprint 1 | Vaishnavi | S-44577 | MSBP - Maui - Store - Landing screen | 3 | 4.75 | NA | Vaishnavi | IOS/Android- After landing to Store screen, user has to refresh one time to get the School data to display in the Store Screen. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
11 | 14.3 M Sprint 1 | Gokul | S-44558 | MSBP - Maui - Profile | 2 | 2 | Done | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39552?_a=commits https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39479 | 25-10-2024 30-10-2024 | 25-10-2024 30-10-2024 | Ashwin | NA | NA | NA | NA | NA | Move the password blacklist validation api call from entry control unfocus event to save event so that the issue with Android - confirm password entry is fixed. | Inprogress | Dev completed and moved to testing

## 14.3 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.3 M Sprint 1 | 44577 MSBP - Maui - Store - Landing screen | Vaishnavi | Bounceback | IOS/Android- After landing to Store screen, user has to refresh one time to get the School data to display in the Store Screen. | Significant | External | Closed | Design
2 | 14.3 M Sprint 1 | 44572-MSBP - Maui - Meals Money from student card | Ashwin | Bounceback | Maui-IOS/Android- Cafeteria history data is not getting displayed in Meal Money screen. Attached screenshot for reference. | Significant | External | Inprogress
3 | 14.3 M Sprint 1 | 44558 MSBP - Maui - Profile | Gokul | Bounceback | Crash on update password page if confirm password input happens first A- cannot delete characters in confirm password field Crash on update password page if there is an entry in confirm password field i-On hitting the ? next to text alerts the button reads "Resource not found" instead of "got it" upon selecting security questions and choosing a new one, profile pages stack. Hitting back to exit profile page shows another profile page the unable to change username error and the phone already exists error should be "Dismiss" not "Ok" A- when clicking confirm password the keyboard opens then closes, then needs another selection to open A-getting passwords do not match error everytime. Unsure what is causing but cannot delete to troubleshoot per BB2 The header on the ? next to text alerts is populating "resource not found" occasionally (seems to happen after making a phone # update) When turning on the text alert toggle, to an existing account number (585-944-6156) the error message says [ok] instead of [dismiss] | Significant | External | Inprogress |  | Fixed the issues and moved to testing

## 14.2 M Sprint 3- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.2 M Sprint 3 Stretch | Gokul | S-44574 | MSBP - Maui - Invoice Landing screen | 3 | 1 | Done |  |  |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39205?_a=files | 2024-10-04 | 2024-10-04 | Ashwin | NA | NA | NA | NA | NA | NA | Inprogress | Development is completed and moved to testing
2 | 14.2 M Sprint 3 Stretch | Gokul | S-44558 | MSBP - Maui - Profile | 5 | 5 | Done |  |  | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39370 | 2024-10-16 | 2024-10-16 | Ashwin | NA | NA | NA | NA | NA | 1. Android - Save button not moving up on keyboard open in input modal page when soft keyboard appears 2. iOS - Save button in Input modal page is hiding at the bottom of the page and only small portion of it is visible 3. Text alerts popup bottom part is transparent | Inprogress | 1. Android - Save button not moving up on keyboard open in input modal page when soft keyboard appears (This issue is in common page and not related to story. Hence logged in blockers sheet and didn't fix right now) 2. iOS - Save button in Input modal page is hiding at the bottom of the page and only small portion of it is visible (When tested in device the save button is not hiding, seems to be issue with Simulator) 3. Text alerts popup bottom part is transparent (Replaced the drawer controls with Sheet and the issue is fixed) Development is completed and moved to testing
3 | 14.2 M Sprint 3 Stretch | Ashwin | S-44576 | MSBP - Maui - Meal Money - Add Money screens | 5 | [16 empty] | Inprogress
4 | 14.2 M Sprint 3 Stretch | Sambath | S-44561 | 44561 MSBP - Maui - Payment Methods | 5 | [16 empty] | Inprogress | This story is carried to next sprint for UI issue fixes
5 | 14.2 M Sprint 3 | Vaishnavi | S-46188 | REG - MSBP - 14.2 Regression | 8 | 8.25 |  | Vaishnavi | Defect 24180 created for autopay disabled issue in parent app. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
6 | 14.2 M Sprint 3 | Vaishnavi | S-46197 | MSBA/MSBP - UI Automation - Update and Fix failures (14.2) | 5 | 4.25 |  | Vaishnavi | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
7 | 14.2 M Sprint 3 Stretch | Sambath | S-42144 | 42144 MSBA - Maui - Add to Cart / Cart Page | 1 | 1 |  | Samuel | Bouncebacks: (iPad) Scroll issue in the cart page (Android Tablet) Delay in refresh while trying to swipe and delete the store products from the cart page | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Except the below mentioned known issue, all the other bouncebacks are fixed. Know Issue: (updated in the Maui know issue excel sheet) Android Tablet: Delay happens while trying to swipe and delete the products from the cart
8 | 14.2 M Sprint 3 Stretch | Gokul | S-42127 | MSBA - Maui - TRX History | 1 | 1 |  | Samuel | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | POV mentioned changes: - Changed the order of the buttons i.e, moved the Sync button next to the Refund and Email buttons Known Issues / blockers: - The "Options" buttons is available in Xamarin forms app, but not available in MAUI's Grid control. - The filter button and it's UI looks quite different compared to Xamarin forms app. - IOS specific: The last column in both grids i.e, “Total” header is hidden when we switch the tab to landscape mode. But it appears when switched back to portrait or any transaction is selected.
9 | 14.2 M Sprint 3 Stretch | Vaishnavi | S-46190 | MSBP - Smoke Test Prod apps against MSB 14.2 RC in Staging | 1 | 1 |  | Vaishnavi | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed

## 14.2 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.2 M Sprint 3 | Defect-24146 | Ashwin | Defect | MSBP - iOS/Android - Store product is missing in the app vs web (regression) | Significant | Internal | Open | QA
2 | 14.2 M Sprint 3 Stretch | S-42144 | Sambath | Bounceback | (iPad) Scroll issue in the cart page (Android Tablet) Delay in refresh while trying to swipe and delete the store products from the cart page | Significant | Internal | Closed | Development | Except the below mentioned known issue, all the other bouncebacks are fixed. Know Issue: (updated in the Maui know issue excel sheet) Android Tablet: Delay happens while trying to swipe and delete the products from the cart
3 | 14.2 M Sprint 3 | S-24180 | Vaishnavi | Defect | MSBP-Android- Autopay is disabled in MealMoney still allows user to edit the disabled fields(regression) | Significant | Internal | Closed | Existing_Issues

## 14.2 M Sprint 2- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.2 M Sprint 2 Stretch | Sambath | S-42144 | 42144 MSBA - Maui - Add to Cart / Cart Page | 5 |  |  | Samuel | (Android/iOS - Phone/Tablet) - Product with stock option quantity is 1, then the product quantity is empty in cart (Ex: Pretzel) - Fixed (Android/iOS - Phone/Tablet) - Promo Code entry and Total fields are placed lower down of the page when the cart is not full - Fixed (Android/iOS - Phone/Tablet) - When the cart is full, the Cart Total labels are not in the scroll - Fixed (Android/iOS - Phone/Tablet) - Invalid promo code error text is incorrect, starts with the word ‘Given’, instead of ’The’ - Fixed (Android/iOS - Phone Landscape) - Unable to scroll the cart page - Fixed (iPhone) - Switching to landscape mode and coming back to portrait, the quantity and product amount is erased from the cart page - Fixed (Android/iOS - Phone/Tablet) - Space between the Cart Tatal, Tatal Savings, Subtotal, Tax and Total is less - Fixed (Android/iOS - Phone/Tablet) - Header label near the expand and collapse button ‘Products’, ‘Invoices’ and ‘Meals’ are missing - Fixed (Android/iOS - Phone/Tablet) - Unlike the xamarin app, a different error message is displayed for an invalid promo codes - Fixed (Android/iOS - Phone) - Cart count is added in the cart icon, but the search icon is missing in the store page - Not Fixed (Android/iOS - Phone/Tablet) - Product quantity should not be edited using the keyboard - Not Fixed (iPhone) - ‘Promo Code’ Watermark text and the entered promo code text are having white background - Not Fixed (iPhone) - When the cart is full, Cart header label and its icon are not visible - Not Fixed (iOS - Phone/Tablet) - Empty space between the header label and product expand collapse label in the cart page - Not Fixed (Android/iOS - Tablet) - Space for Promo Code entry field is less - Not Fixed (Android/iOS - Phone/Tablet) - Hamburger icon is missing |  | NA | [10 empty] | Closed | Devlopment completed, testing is In-Progress
2 | 14.2 M Sprint 2 Stretch | Gokul | S-42150 | MSBA - Maui - Close Out Workflow (UI & Logic Hookup) | 3 | 3 | Done | Samuel | iOS (Phone and Tablet): AppCrashes- select shift user and navigate through the close out workflow, tap the confirm button in the ‘Are you sure?’ pop up AppCrashes- No shift user, Tap shift user drop down, Tap Done button Android: Tablet - Count page: Amount value is cut off Phone/Tablet - Close out confirm pop up UI is incorrect (refer the attached screenshot) Phone/Tablet - Count page : Keyboard is not opened while trying to enter amount in the same page iOS (Phone/Tablet) :Set Up page- AppCrashes while tapping the done button of the empty shift user drop down Android/iOS (Phone/Tablet) : Start Page- Unable to enter starting cash amount and the app freezes |  | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/39015 | 2024-09-23 | 2024-09-23 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Bouncbacks are fixed and closed the story.
3 | 14.2 M Sprint 2 Stretch | Gokul | S-42147 | MSBA - Maui - TRX History | 3 | 3 | Done | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/39179 | 2024-10-01 | 2024-10-01 | Ashwin | NA | NA | NA | NA | NA | NA | Inprogress | Development completed and testing in progress
4 | 14.2 M Sprint 2 | Ashwin | S-45935 | MSBA - Transaction History - Enable and Test Email feature | 2 | 2 | NA | NA |  | NA | NA
5 | 14.2 M Sprint 2 Stretch | Gokul | S-44574 | MSBP - Maui - Invoice Landing screen | 3 | 1 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39205?_a=files | 2024-10-03 | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Development started at the ending day of sprint. Almost completed the changes, yet to test on device. So continuing on the next sprint.
6 | 14.2 M Sprint 2 Stretch | Ashwin | S-44573 | MSBP - Maui - Meal Money landing screen from Bottom Nav | 3 | 3 | Done | NA | NA | Client |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/39187 | 2024-10-01 | 2024-10-02 | Client | NA | NA | NA | NA | NA | NA | Closed
7 | 14.2 M Sprint 2 | Ashwin | 24018 | MSBA - Android - Transaction History all text is white on white (14.2) | 2 | 2 | Done | NA | NA | Client

## 14.2 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.2 M Sprint 2 Stretch | Story-42150 | Gokul | Bounceback | iOS (Phone and Tablet): AppCrashes- select shift user and navigate through the close out workflow, tap the confirm button in the ‘Are you sure?’ pop up AppCrashes- No shift user, Tap shift user drop down, Tap Done button Android: Tablet - Count page: Amount value is cut off Phone/Tablet - Close out confirm pop up UI is incorrect (refer the attached screenshot) Phone/Tablet - Count page : Keyboard is not opened while trying to enter amount in the same page iOS (Phone/Tablet) :Set Up page- AppCrashes while tapping the done button of the empty shift user drop down Android/iOS (Phone/Tablet) : Start Page- Unable to enter starting cash amount and the app freezes | Significant | Internal | Closed | Development | Bouncebacks are fixed, story is closed
2 | 14.2 M Sprint 2 Stretch | Defect - 24018 | Ashwin | Bounceback | [Dark mode] Above mentioned issue is now reproduced only in the first login after the install and navigating to the Transaction History page, once the app is closed from the background and reopened again, login it works as expected. | Significant | Internal | Closed | Development | Bouncebacks are fixed, Defect is closed
2 | 14.2 M Sprint 2 Stretch | Story - 42144 | Sambath | Bounceback | (Android/iOS - Phone/Tablet) - Product with stock option quantity is 1, then the product quantity is empty in cart (Ex: Pretzel) - Fixed (Android/iOS - Phone/Tablet) - Promo Code entry and Total fields are placed lower down of the page when the cart is not full - Fixed (Android/iOS - Phone/Tablet) - When the cart is full, the Cart Total labels are not in the scroll - Fixed (Android/iOS - Phone/Tablet) - Invalid promo code error text is incorrect, starts with the word ‘Given’, instead of ’The’ - Fixed (Android/iOS - Phone Landscape) - Unable to scroll the cart page - Fixed (iPhone) - Switching to landscape mode and coming back to portrait, the quantity and product amount is erased from the cart page - Fixed (Android/iOS - Phone/Tablet) - Space between the Cart Tatal, Tatal Savings, Subtotal, Tax and Total is less - Fixed (Android/iOS - Phone/Tablet) - Header label near the expand and collapse button ‘Products’, ‘Invoices’ and ‘Meals’ are missing - Fixed (Android/iOS - Phone/Tablet) - Unlike the xamarin app, a different error message is displayed for an invalid promo codes - Fixed (Android/iOS - Phone) - Cart count is added in the cart icon, but the search icon is missing in the store page - Not Fixed (Android/iOS - Phone/Tablet) - Product quantity should not be edited using the keyboard - Not Fixed (iPhone) - ‘Promo Code’ Watermark text and the entered promo code text are having white background - Not Fixed (iPhone) - When the cart is full, Cart header label and its icon are not visible - Not Fixed (iOS - Phone/Tablet) - Empty space between the header label and product expand collapse label in the cart page - Not Fixed (Android/iOS - Tablet) - Space for Promo Code entry field is less - Not Fixed (Android/iOS - Phone/Tablet) - Hamburger icon is missing | Significant | Internal | Inprogress | Development

## 14.2 M Sprint 1- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.2 M Sprint 1 Stretch | Sambath | S-42144 | 42144 MSBA - Maui - Add to Cart / Cart Page | 5 | 5 |  |  |  |  | NA | [10 empty] | Inprogress | NumericInputButton Control is causing the issue in MAUI so as per client suggesion creating custom control against the Quantity increase and Descress functinaliies. and there lot of UI the so continue to fixng this.
2 | 14.2 M Sprint 1 Stretch | Gokul | S-42150 | 42150 MSBA - Maui - Close Out Workflow (UI & Logic Hookup) | 8 | 8 | NA | Samuel | Dev testing bouncebacks, (iPad)-Count page: Unlike the xamarin app, the 'x' icon in the amount entry field is seen while entering the amount (Refer the screenshot) (iPad)-Count page: In amount field empty value is not showing ‘0’ (Refer the screenshot) (iPad)-Summary page: App Crashes while tapping the confirm button in the ‘Are you sure?’ pop up (iPad)-After ending the shit, shift name is not populated in the close out page 'select a shift' drop down. (Android :Tablet/ Phone) -Count page: Amount value and the text ('0 Checks to Reconcile') is cut off (Android :Tablet/ Phone) -Count page: Keyboard is not opened while trying to enter amount (Android :Tablet/ Phone) -Start, Count and Summary page: Arrow back button in the left corner of the header is missing (Android :Tablet/ Phone) -Count page: Total number of letters entered out of 1000 (Ex: 976/1000) is missing below the message entry field (Android :Tablet/ Phone) -Newly created shifts are not reflected at once in the Close day page's select shift drop down | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38885?_a=files | 2024-09-18 | 2024-09-18 | Ashwin | NA | NA | NA | NA | NA | NA | Inprogress | Fixed following bouncebacks: (iPad)-Count page: Unlike the xamarin app, the 'x' icon in the amount entry field is seen while entering the amount (Refer the screenshot) (iPad)-Summary page: App Crashes while tapping the confirm button in the ‘Are you sure?’ pop up (Android :Tablet/ Phone) -Count page: Amount value and the text ('0 Checks to Reconcile') is cut off (Android :Tablet/ Phone) -Start, Count and Summary page: Arrow back button in the left corner of the header is missing (Android :Tablet/ Phone) -Count page: Total number of letters entered out of 1000 (Ex: 976/1000) is missing below the message entry field (Android :Tablet/ Phone) -Newly created shifts are not reflected at once in the Close day page's select shift drop down Continuing remaining issues in next sprint.
3 | 14.2 M Sprint 1 | Samuel | S-45821 | MSBP - 14.1 Regression | 5 | 5 | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress
4 | 14.2 M Sprint 1 | Ashwin | D-23891 | MSBA - iOS/Android - Webform issues (EMV checkout and crash on edit) (14.1) | 0.5 | 0.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/38796?_a=commits | 2024-09-06 | 2024-09-06 | Avery | NA | NA | NA | NA | NA | NA | Closed
4 | 14.1 M Sprint 3 Stretch | Sambath | S-42134 | MSBA - Maui - Invoices Details | 3 | 3 | NA | Samuel | (iOS - Phone and Tablet) App Crashes after tapping the Partial Amount checkbox - Fixed (Android - Phone) ‘X’ icon in the payment options pop up is not fully visible - Fixed (iOS-(Phone and Tablet)) Unable to enter the Partial Amount in the entry field - Fixed (iPhone) Partial Amount entry field is hidden - Fixed (iOS - (Phone and Tablet)) Invoice details page blinks while trying to Add or Remove the invoice(s) from the cart - Fixed (Android/iOS-(Phone and Tablet)) Able to add invoice to the cart from Payment Options pop up when the Add To Cart button is disabled - Fixed (Android/iOS-Phone/Tablet) Invoice ‘Schedule Dates’ are not displayed in the payment options pop up - Fixed (Android-Phone Landscape) ‘Add an invoice to cart’ button in the payment options pop up is hidden - Fixed (Android-Phone Landscape) tapping the ‘X’ icon in the payment options pop up fails to close it - Fixed (Android/iOS-(Phone and Tablet)) Bottom tab bar is missing in the Invoice details page - Fixed (Android/iOS-(Phone and Tablet)) Unable to remove invoices from the cart through the payment options pop up when full amount is paid as the partial amount - Fixed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Bounce back issues are fixed and closed the story with few know issues as discussed with the dev team. Know Issues: (Android - (Phone and Tablet)) Keyboard is not opened after selecting the Partial Amount checkbox (Android-Phone/Tablet) Able to tap the (Add To Cart, Payment Options and Add/Remove all to cart) buttons when payment options pop up is open (iPhone) More space between Partial Amount checkbox label and the amount entry field (iPad) Able to enter alphabets and special characters in the amount entry field (unlike the Xamarin app, per Dev this is a common issue found in iPad across the Maui application for the amount entry fields Ex: product details page ‘Price’ entry field ) (iOS - Phone/Tablet) - Watermark text ‘Amount’ in the Partial Amount entry field is not aligned along with the cursor
3 | 14.2 M Sprint 1 | Samuel | S-45965 | MSBP/MSBA - UI Automation- Update and Fix failures | 1 | 1 | NA | Samuel | 10 UI automaiton failures are due to the open defects mentioned below: 23745 - MSBP - iOS/Android - Closing Greenlight card tray also closes associated students tray (Staging environment) 24029 - MSBP - iOS/Android - GL banner is missing in the home page (demo mode) 24028 - MSBP - iOS/Android - For a no student login, two blue pages for adding a new student is missing (demo mode) 24030 - MSBP - iOS/Android - CVV entry box is missing for visa cc in the payment method drawer (demo mode) | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress

## 14.2 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.2 M Sprint 1 | 23891 | Ashwin | Defect | AppCrashes while trying to edit and save a webform product or any other product from the cart. | Major | External | Closed | QA | Bounceback is fixed, tested (Android/iOS) and closed the defect.
2 | 14.2 M Sprint 1 | 23912 | Ashwin | Defect | [FAMILYPASS] MSBP - iOS/Android - profile page will not load if in canceled state (14.1) | Significant | Internal | Closed | Design | Tested (Android/iOS) and closed the defect.
3 | 14.2 M Sprint 1 | 22523 | Ashwin | Defect | MSBP - Available meal balance mismatch - Web vs Parent app (14.1) | Significant | External | Closed | Existing_Issues | Tested (Android/iOS) and closed the defect.
4 | 14.2 M Sprint 1 | 24011 | Ashwin | Defect | MSBP - iOS/Android - AppCrashes after tapping the toggle buttons in the meal control page while adding students using suggested match (regression) | Major | Internal | Closed | Design
5 | 14.2 M Sprint 1 | 24012 | Ashwin | Defect | MSBP - iOS/Android - MFA page is missing after resetting the password of an user and then trying to login (regression) | Significant | Internal | Inprogress | Design | Its blocked as its depended on a fix from DS.
5 | 14.2 M Sprint 1 - Stretch | 42150 | Gokul | Bounceback | Dev testing bouncebacks, (iPad)-Count page: Unlike the xamarin app, the 'x' icon in the amount entry field is seen while entering the amount (Refer the screenshot) (iPad)-Count page: In amount field empty value is not showing ‘0’ (Refer the screenshot) (iPad)-Summary page: App Crashes while tapping the confirm button in the ‘Are you sure?’ pop up (iPad)-After ending the shit, shift name is not populated in the close out page 'select a shift' drop down. (Android :Tablet/ Phone) -Count page: Amount value and the text ('0 Checks to Reconcile') is cut off (Android :Tablet/ Phone) -Count page: Keyboard is not opened while trying to enter amount (Android :Tablet/ Phone) -Start, Count and Summary page: Arrow back button in the left corner of the header is missing (Android :Tablet/ Phone) -Count page: Total number of letters entered out of 1000 (Ex: 976/1000) is missing below the message entry field (Android :Tablet/ Phone) -Newly created shifts are not reflected at once in the Close day page's select shift drop down | Significant | Internal | Inprogress | Design
5 | 14.2 M Sprint 1 | 24029 |  | Defect | MSBP - iOS/Android - GL banner is missing in the home page (demo mode) | Significant | Internal | Open | QA
5 | 14.2 M Sprint 1 | 24028 |  | Defect | MSBP - iOS/Android - For a no student login, two blue pages for adding a new student is missing (demo mode) | Significant | Internal | Open | QA
5 | 14.2 M Sprint 1 | 24030 |  | Defect | MSBP - iOS/Android - CVV entry box is missing for visa cc in the payment method drawer (demo mode) | Significant | Internal | Open | QA

## 14.1 M Sprint 3- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.1 M Sprint 3 Stretch | Sambath | S-42144 | 42144 MSBA - Maui - Add to Cart / Cart Page | 8 | 3.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Continuing development on next sprint
2 | 14.1 M Sprint 3 Stretch | Gokul | S-42150 | 42150 MSBA - Maui - Close Out Workflow (UI & Logic Hookup) | 8 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | - Freeze the closeout screen to landscape orientation in MAUI. - Fix the spacing | Inprogress | Continuing development on next sprint
3 | 14.1 M Sprint 3 | Samuel | S-45831 | MSBP / MSBA - Automation - Update, Run, Check & Fix Any Automation Failures | 8 | 6 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/38752 https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/38765 | 9/4/2024 9/5/2024 | 9/4/2024 9/5/2024 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Completed the UI automation fixes for MSBA and MSBP applications and created pull request for the same.
4 | 14.1 M Sprint 3 Stretch | Sambath | S-42134 | MSBA - Maui - Invoices Details | 5 | 8 | NA | Samuel | Bouncebacks, iOS- AppCrashes after tapping the ‘Next’ button in the Invoice page after selecting the invoice(s). - Unable to navigate to the Invoice details page after scanning the student ID barcode (page keeps loading) Android - Unable to navigate to the Invoice details page after selecting the invoice(s) and tapping the ‘Next’ button or scanning the student ID barcode(page keeps loading). (Android/iOS-(Phone and Tablet)) Keyboard is not opened after selecting the Partial Amount checkbox (iOS-(Phone and Tablet)) Unable to enter the Partial Amount in the entry field (iPhone) Partial Amount entry field is hidden (Refer to the screenshot) (Android (Phone and Tablet)) In ‘Remove All From Cart’ button text, the word ‘cart’ is missing from the Invoice details page (iOS - (Phone and Tablet)) Invoice details page blinks while trying to Add or Remove the invoice(s) from the cart (iPad) Payment Options pop up - need more space between Invoice Amount and Payment Amount (Refer to the screenshot) - (Android/iOS-(Phone and Tablet)) Able to add invoice to the cart from Payment Options pop up when the Add To Cart button is disabled - (Android - Phone) ‘X’ icon in the payment options pop up is not fully visible (refer to the screenshot) | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38767 https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38707 | 2024-09-05 | 2024-09-05 | Ashwin | NA | NA | NA | NA | NA | NA | Inprogress | Added bouncebacks to the story
5 | 14.1 M Sprint 3 | Ashwin | D-23878 | [FAMILYPASS] - iOS/Android - when account is made on web, causing errors re-enabling family pass auto renew | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | When we try to activate a cancelled FP membership by adding a new payment method we are getting an error from the API "java.lang.Exception: Missing required parameter: acctKey". This is only happening for users that have no zipcode/address/city on parent profile. Once we update the zipcode/address/city on parent profile it works as expected

## 14.1 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.1 Sprint 3 - Stretch | S-42134 | Sambath | Bounceback | Bouncebacks, (Android/iOS-(Phone and Tablet)) Keyboard is not opened after selecting the Partial Amount checkbox (iOS-(Phone and Tablet)) Unable to enter the Partial Amount in the entry field (iPhone) Partial Amount entry field is hidden (Refer to the screenshot) (Android (Phone and Tablet)) In ‘Remove All From Cart’ button text, the word ‘cart’ is missing from the Invoice details page (iOS - (Phone and Tablet)) Invoice details page blinks while trying to Add or Remove the invoice(s) from the cart (iPad) Payment Options pop up - need more space between Invoice Amount and Payment Amount (Refer to the screenshot) - (Android-Phone/Tablet) Able to tap the (Add To Cart, Payment Options and Add/Remove all to cart) buttons when payment options pop up is open - (Android/iOS-Phone/Tablet) ‘ChrisAllen -Inv43’ does not work as expected, unable to remove the invoice from payment options pop up, added to the cart with remaining amount but shows as partial amount in the payment options pop up - (Android Phone Landscape) Add an invoice to cart button from the payment options pop up is hidden (refer to the screenshot) - (Android Phone Landscape) ‘X’ icon to close the payment options pop up does not work - (Android/iOS-(Phone and Tablet)) Able to add invoice to the cart from Payment Options pop up when the Add To Cart button is disabled - (Android - Phone) ‘X’ icon in the payment options pop up is not fully visible (refer to the screenshot) | Major | External | Inprogress | QA
2 | 14.1 Sprint 2 - Stretch | 23912 | Ashwin | Defect | [FAMILYPASS] MSBP - iOS/Android - profile page will not load if in canceled state (14.1) | Significant | Internal | Inprogress | QA

## 14.1 M Sprint 2- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.1 M Sprint 2 Stretch | Samuel | S-44624 | MSBA - UI Automation - Update and Fix failures | 5 | 7 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/38578 | 2024-08-22 | 2024-08-28 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Completed the execution of UI automation tests in the local environment, added the test results in the comment section and closed the story.
2 | 14.1 M Sprint 2 Stretch | Sambath | S-42134 | 42134 MSBA - Maui - Invoices Details | 5 |  | NA | Samuel | Bouncebacks, iOS- AppCrashes after tapping the ‘Next’ button in the Invoice page after selecting the invoice(s). - Unable to navigate to the Invoice details page after scanning the student ID barcode (page keeps loading) Android - Unable to navigate to the Invoice details page after selecting the invoice(s) and tapping the ‘Next’ button or scanning the student ID barcode(page keeps loading). | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38395 | 2024-08-19 | 2024-08-19 | Ashwin | NA | NA | 2024-08-19 | NA | NA | For both IOS/Android: If selecting one or more students is going to take a while to return invoices, we should input a loading animation. Is this alot more effort? The device doesn't look like it's responding at all, that's not a good experience Additional on the tablet the selector next to Remaining or Partial amount is not the right size or is off center | Inprogress | Bounce back issue fixed. Testing is Inprogress
3 | 14.1 M Sprint 2 Stretch | Sambath | S-42144 | 42144 MSBA - Maui - Add to Cart / Cart Page | 5 | [5 empty] | NA | [10 empty] | Inprogress
4 | 14.1 M Sprint 2 Stretch | Sambath | D-23778 | 23778 MSBP - Android- If suggested student tray closed, no add student button on home page (regression) (14.0) | 2 | 2 | NA | NA | Bounceback, Add student button is still missing on iOS and android. It appears that iOS is no longer unresponsive, but the greenlight banner is now missing | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/38282?_a=files | 2024-08-08 | 2024-08-08 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Bounceback issue is fixed and the defect is closed.
5 | 14.1 M Sprint 2 Stretch | Ashwin, Gokul | S-42150 | 42150 MSBA - Maui - Close Out Workflow | 8 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | UI binding not working as expected, so continue to looking that issue

## 14.1 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.1 Sprint 2 - Stretch | S-42134 | Sambath | Bounceback | Bouncebacks, iOS- AppCrashes after tapping the ‘Next’ button in the Invoice page after selecting the invoice(s). - Unable to navigate to the Invoice details page after scanning the student ID barcode (page keeps loading) Android - Unable to navigate to the Invoice details page after selecting the invoice(s) and tapping the ‘Next’ button or scanning the student ID barcode(page keeps loading). | Major | External | Inprogress | QA | Added bouncebacks and assigned to development
1 | 14.1 Sprint 2 | D-23778 | Sambath | Bounceback | Bounceback, Add student button is still missing on iOS and android. It appears that iOS is no longer unresponsive, but the greenlight banner is now missing | Major | External | Inprogress | QA | Bounceback and the defect is fixed.

## 14.1 M Sprint 1- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.1 M Sprint 1 Stretch | Gokul | S-44880 | MSBA - Maui - Product Details - Testing | 3 | 4 | NA | Samuel | Bouncebacks, Android/iOS : when hitting back out of the product details the app is crashing (in xamarin this has a pop up to confirm that item has not been added to cart,and provides options stay/leave) Android/iOS : logic for updating stock options is missing. related to defect 23515 for xamarin. On a student required item with multiple stock options that have eligibility requirements, eligibility is checked and stock options returned upon adding of student. Currently it is not updating stock options at all during mixed eligibility setups on product iOS phone: cannot add student to student line on products. Upon searching by name or id it states "not found". If scanning with camera, it closes camera as if input was accepted, but no student name populated in line Android- stock option box has a second line under the price/name Android-in user set price, the numbers are cut off at the top on the price line Android- in user set price (most likely any free-form insert field) when deleting all numbers, after entering the first digit, the cursor moves to the front of price(delete all enter a 5, then a 2- price will show as 20.05- xamarin/iOS keep this as .52) Android (Phone/Tablet) : AppCrashes while tapping the product ‘AllWebformsProduct’ Android Phone : Stock Option name along with its price, the font size is large Android Tablet: Quantity value is cut off at the top Android Phone: Device camera and library is not opened to upload or capture image in the product details page | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38071 https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38251 | 2024-08-01 | 2024-08-01 | Ashwin | NA | NA | 2024-08-01 | NA | NA | NA | Closed | In Xamarin forms when a image is captured in products detail page, it rotates the image to portrait by default no matter in which orientation the device is kept. But in MAUI it is not handled automatically, instead need to write code foor it handle manually.
2 | 14.1 M Sprint 1 Stretch | Gokul | S-42136 | MSBA - Maui - Meal Payments Detail | 3 | 3 | NA | Samuel | Bouncebacks, (Android/iOS) - Student ID barcode scanning in the meal payments page is not working in the portrait mode (iOS) - Camera image in the landscape mode remains in portrait | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38218 https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38250 | 2024-08-06 | 2024-08-07 | Ashwin | NA | NA | 2024-08-07 | NA | NA | NA | Closed | Moved to testing
3 | 14.1 M Sprint 1 | Samuel | S-45474 | MSBP - UI Automation - Update and Fix failures | 5 | 5 |  | Samuel | New Defect added: 23732 MSBP-iOS/Android-‘Request Balance Transfer’ and ‘Request a Refund’ page links are missing in the hamburger menu | NA | NA | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | Closed | Completed the UI automation test execution in the local environment (Android/iOS) Updated the results in Axosoft . Newly added defect 23732 will be fixed in 14.1 Sprint 2.
4 | 14.1 M Sprint 1 Stretch | Sambath | S-42134 | 42134 MSBA - Maui - Invoices Details | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Dev Completed, Testing In-Progress
5 | 14.1 M Sprint 1 Stretch | Ashwin | S-42150 | 42150 MSBA - Maui - Close Out Workflow | 13 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Continue to working on the strech story

## 14.1 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.1 M Sprint 1 - Stretch | S-44880 | Gokul | Bounceback | Android/iOS : when hitting back out of the product details the app is crashing (in xamarin this has a pop up to confirm that item has not been added to cart,and provides options stay/leave) Android/iOS : logic for updating stock options is missing. related to defect 23515 for xamarin. On a student required item with multiple stock options that have eligibility requirements, eligibility is checked and stock options returned upon adding of student. Currently it is not updating stock options at all during mixed eligibility setups on product iOS phone: cannot add student to student line on products. Upon searching by name or id it states "not found". If scanning with camera, it closes camera as if input was accepted, but no student name populated in line Android- stock option box has a second line under the price/name Android-in user set price, the numbers are cut off at the top on the price line Android- in user set price (most likely any free-form insert field) when deleting all numbers, after entering the first digit, the cursor moves to the front of price(delete all enter a 5, then a 2- price will show as 20.05- xamarin/iOS keep this as .52) Android (Phone/Tablet) : AppCrashes while tapping the product ‘AllWebformsProduct’ Android Phone : Stock Option name along with its price, the font size is large Android Tablet: Quantity value is cut off at the top Android Phone: Device camera and library is not opened to upload or capture image in the product details page | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
2 | 14.1 M Sprint 1 - Stretch | S-42136 | Gokul | Bounceback | Bouncebacks, (Android/iOS) - Student ID barcode scanning in the meal payments page is not working in the portrait mode (iOS) - Camera image in the landscape mode remains in portrait | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
3 | 14.1 Sprint 1 | D-23732 | Ashwin | Defect | MSBP-iOS/Android-‘Request Balance Transfer’ and ‘Request a Refund’ page links are missing in the hamburger menu | Major | External | Closed | QA | Defect is fixed and closed

## 14.0 M Sprint 3- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.0 Sprint 3 - Stretch | Sambath | S-44881 | 44881 MSBA - Maui - Shifts (Start/End) - Testing | 3 | 4 | NA | Samuel | Bouncebacks, (iOS) - Text inputs boxes instead of lines (iOS) - Maui has a clear option for sales tag that does not exist in xamarin (Android / iOS) - Select and clear the shift user name, but still able to delete the shift user (Android / iOS) - Admin User: Add user pop up does not close after adding a new shift user (Android / iOS) - Clerk User: Admin pop up does not close after adding a new shift user (iOS) - App Crashes after adding new shift user and tapping the OK button of the success pop up (iOS) - Able to clear, edit and change the shift user name while ending the shift (iOS) - Maui has a clear option for sales tag that does not exist in xamarin (Android / iOS) - Select and clear the shift user name, but still able to delete the shift user (iOS) - Able to clear, edit and change the shift user name while ending the shift (Android/iOS) Landscape mode - Shift user name 1st value is cut-off in the drop down (Android/iOS) Landscape mode - Clerk User: Unable to enter Password and tap Validate button in the admin pop up (Android/iOS) - Admin user- ‘User deleted successfully’ pop up is not showing after deleting a shift user (iOS) - Sales Tag option value is displayed in box instead of line (iOS) - ‘Entered name already exists’, ‘Invalid Admin Credentials’, warning messages are displayed behind the pop up (Android/iOS) - Shift user drop down text mis-match when no user found, ‘Not Found.’ Instead of ‘No Results Found.’ (Android/iOS) Clerk User- Add & Delete Shift users - Warning error message does not match with the xamarin app after entering an incorrect admin username and password (iOS) Clerk User- Delete Shift users - Warning message text is not correct and it is displayed behind the admin pop up (Android Tablet) - Word ‘task.’ is missing in the admin pop up header title Accepted known issues after the discussion between Ashwin and Jason: (Android/iOS) Landscape mode - Clerk User: Unlike the Xamarin app, 'Password' entry field and 'Validate' button of the admin pop up is hidden by the keyboard (Android/iOS) Landscape mode - Unlike the Xamarin app, Add user 'Last Name' entry field and 'Add' button are hidden by the keyboard (iOS) - In the Shit Username drop down, ‘No Results Found.’ text is not aligned in the top left corner of the drop down | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/38016 | 2024-07-24 | 2024-07-24 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Bouncebacks are fixed, executed the test cases and closed this story with comments.
2 | 14.0 Sprint 3 Stretch | Ashwin | S-45314 | 45314 [FAMILYPASS] MSBP - API - Profile Status (Cancel, edit, update) | 5 | 5 | NA | Samuel | Bouncebacks: functionality (to be addressed now) -ability to add echeck on add payment method window (though it does throw a system error when applied) -after adding a new card it is not auto selected on Android- it remains on old card -system error encountered when entering CVV -possibly related to the above error: when disabling the auto renew and turning it back on, it is showing both the initial payment and the one that we attempted to error checked simultaneously. This does allow us to hit save with both checked. Per Jason since we are re-enabling we can have the prior payment auto selected (but it should only be the one) UI (notated but to be resolved at a later time) -there are extra spaces under the buttons making them float significantly above the bottom of the screen in iOS -Android the font size is small for the "Are you sure you want to disable auto-renew" tray this may be related to the CVV API issue, however upon entering a new card we are prompted for a cvv and can enter and save it, but the new payment method does not show in the profile page. When selecting "change payment method" it then has both the previously selected/verified card and the new card we attempted to add and verify. | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37864 | 2024-07-18 | 2024-07-18 | Avery | NA | NA | NA | NA | NA | NA | Closed | This story is now in onsite-testing
3 | 14.0 M Sprint 3 Stretch | Gokul | S-44880 | MSBA - Maui - Product Details - Testing | 5 | 5 | NA | Samuel | Bouncebacks, Android (Phone/Tablet) : AppCrashes while tapping the product ‘AllWebformsProduct’ Android Phone : Stock Option name along with its price, the font size is large Android Tablet: Quantity value is cut off at the top Android Phone: Device camera and library is not opened to upload or capture image in the product details page | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/37882 | 2024-07-16 | 2024-07-16 | Ashwin | NA | NA | NA | NA | NA | NA | Inprogress | Android storage permission is denied for the version above Android 13 in MAUI, looking for the fix.
4 | 14.0 M Sprint 3 Stretch | Samuel | S-42144 | MSBA - Maui - Add to Cart / Cart Page (Adding Only the Test Cases) | 0 | 0 | NA | Samuel | Completed addding the test cases | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Completed the test cases
5 | 14.0 M Sprint 3 Stretch | Gokul | S-42136 | MSBA - Maui - Meal Payments Detail | 5 | 5 | NA | Samuel | Completed addding the test cases | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | There are challenges in Tab/ipad devices regarding the trigger conditions not responding with device orientations. Several conditions are written in existing xamarin code depending on these conditions. Hence checking on these issues.
6 | 14.0 M Sprint 3 Stretch | Sambath | S-42134 | MSBA - Maui - Invoices Details | 8 | 4 | NA | Samuel | Completed addding the test cases | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | I picked this story at the end of the sprint, so it will carry on into the next sprint.

## 14.0 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.0 Sprint 3 - Stretch | S-44880 | Gokul | Bounceback | Bouncebacks, Android (Phone/Tablet) : AppCrashes while tapping the product ‘AllWebformsProduct’ Android Phone : Stock Option name along with its price, the font size is large Android Tablet: Quantity value is cut off at the top Android Phone: Device camera and library is not opened to upload or capture image in the product details page | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
2 | 14.0 Sprint 3 - Stretch | S-45314 | Ashwin | Bounceback | Bouncebacks: functionality (to be addressed now) -ability to add echeck on add payment method window (though it does throw a system error when applied) -after adding a new card it is not auto selected on Android- it remains on old card -system error encountered when entering CVV -possibly related to the above error: when disabling the auto renew and turning it back on, it is showing both the initial payment and the one that we attempted to error checked simultaneously. This does allow us to hit save with both checked. Per Jason since we are re-enabling we can have the prior payment auto selected (but it should only be the one) UI (notated but to be resolved at a later time) -there are extra spaces under the buttons making them float significantly above the bottom of the screen in iOS -Android the font size is small for the "Are you sure you want to disable auto-renew" tray this may be related to the CVV API issue, however upon entering a new card we are prompted for a cvv and can enter and save it, but the new payment method does not show in the profile page. When selecting "change payment method" it then has both the previously selected/verified card and the new card we attempted to add and verify. | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
3 | 14.0 Sprint 3 - Stretch | S-42133 | Gokul | Bounceback | Bounceback, Android/iOS : MSBAnywhere header logo size does not match with the Xamarin app. iOS: ‘Cancel’ button is seen beside the clear search text ‘x’ icon. iOS: AppCrashes while tapping the cart icon | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
4 | 14.0 Sprint 3 - Stretch | S-44881 | Sambath | Bounceback | Bouncebacks, (iOS) - Text inputs boxes instead of lines (iOS) - Maui has a clear option for sales tag that does not exist in xamarin (Android / iOS) - Select and clear the shift user name, but still able to delete the shift user (Android / iOS) - Admin User: Add user pop up does not close after adding a new shift user (Android / iOS) - Clerk User: Admin pop up does not close after adding a new shift user (iOS) - App Crashes after adding new shift user and tapping the OK button of the success pop up (iOS) - Able to clear, edit and change the shift user name while ending the shift (iOS) - Maui has a clear option for sales tag that does not exist in xamarin (Android / iOS) - Select and clear the shift user name, but still able to delete the shift user (iOS) - Able to clear, edit and change the shift user name while ending the shift (Android/iOS) Landscape mode - Shift user name 1st value is cut-off in the drop down (Android/iOS) Landscape mode - Clerk User: Unable to enter Password and tap Validate button in the admin pop up (Android/iOS) - Admin user- ‘User deleted successfully’ pop up is not showing after deleting a shift user (iOS) - Sales Tag option value is displayed in box instead of line (iOS) - ‘Entered name already exists’, ‘Invalid Admin Credentials’, warning messages are displayed behind the pop up (Android/iOS) - Shift user drop down text mis-match when no user found, ‘Not Found.’ Instead of ‘No Results Found.’ (Android/iOS) Clerk User- Add & Delete Shift users - Warning error message does not match with the xamarin app after entering an incorrect admin username and password (iOS) Clerk User- Delete Shift users - Warning message text is not correct and it is displayed behind the admin pop up (Android Tablet) - Word ‘task.’ is missing in the admin pop up header title (Android/iOS) Landscape mode - Clerk User: Unlike the Xamarin app, 'Password' entry field and 'Validate' button of the admin pop up is hidden by the keyboard (Android/iOS) Landscape mode - Unlike the Xamarin app, Add user 'Last Name' entry field and 'Add' button are hidden by the keyboard (iOS) - In the Shit Username drop down, ‘No Results Found.’ text is not aligned in the top left corner of the drop down | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.

## 14.0 M Sprint 2- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.0 Sprint 2 | Sambath | S-45181 | 45181 [FAMILYPASS] MSBP - FamilyPass - Profile updates - Membership - Toggle button explanation | 3 | 3 | NA | Samuel | Bounceback, Switching OFF the auto-renew and switching ON again, the auto-renew ON text is displayed incorrect in the Family Pass Membership section Switching OFF the auto-renew for the second time, auto-renew OFF text is displayed incorrectly in the Family Pass Membership section | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37611 | 2024-07-02 | 2024-07-02 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Restesting, bouncebacks are fixed, executed the test cases and closed the story
2 | 14.0 Sprint 1 - Stretch | Sambath | S-44881 | 44881 MSBA - Maui - Shifts (Start/End) - Testing | 2 | 4 | NA | Samuel | Dev testing support, Bouncebacks, (iOS) - Text inputs boxes instead of lines (iOS) - Maui has a clear option for sales tag that does not exist in xamarin (Android / iOS) - Select and clear the shift user name, but still able to delete the shift user (Android / iOS) - Admin User: Add user pop up does not close after adding a new shift user (Android / iOS) - Clerk User: Admin pop up does not close after adding a new shift user (iOS) - App Crashes after adding new shift user and tapping the OK button of the success pop up (iOS) - Able to clear, edit and change the shift user name while ending the shift | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Continue to working Bounce back issues
3 | 14.0 Sprint 1 - Stretch | Ashwin | D-23515 | MSBA - iOS/Android - Student required with multiple stock options issue | 0.5 | 1 | NA | NA | No bouncebacks in this defect | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/37757 | 2024-07-10 | 2024-07-10 | Avery | NA | NA | NA | NA | NA | NA | Closed | Fixed and closed this defect.
4 | 14.0 Sprint 2 | Gokul | S-44733 | [FAMILYPASS] MSBP - FAMILYPASS - Confirmation and Update to Homepage 2 - (Demo Mode) | 8 | 8 | NA | Samuel | MSBP (Android/iOS) - App Crashes while logging in to the demo mode. Login works in test environment (Android/iOS) - System message pop up and Greenlight drawer is opened while navigating back to the home page (Left screenshot) - Bottom tab bar is not highlighted to the home page (Right screenshot) | Sambath | Remove unwanted code | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37745 | 2024-07-10 | 2024-07-10 | Ashwin | NA | NA | 2024-07-10 | NA | NA | Remove extra space after payment method, i.e. mastercard" " on payment confirmation screen. Update grey background on home page behind banner to White. | Closed | Fixed the issues mentioned in testing
5 | 14.0 Sprint 2 - Stretch | Gokul | S-45084 | MSBA - Maui - Meal Payments - TEST UI | 2 | 0.5 | NA | Samuel | Bounceback, After the text search for student ’981’, ‘9988’,etc,,, $0.00 dollar label shows blank. MSBAnywhere logo size does not match with the Xamarin app. In Landscape mode, the page texts should be centre aligned similar to the Xamarin app. iOS devices: ‘Cancel’ button is seen beside the clear search text ‘x’ icon. iOS devices: AppCrashes while tapping the cart icon | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/37613 | 2024-06-27 | 2024-06-27 | Sean | Move color code to resouce | NA | 2024-06-27 | NA | NA | NA | Closed | Restesting, bouncebacks are fixed, executed the test cases and closed the story
6 | 14.0 Sprint 2 - Stretch | Gokul | S-42133 | MSBA - Maui - Invoices | 2 | 2 | NA | Samuel | Bounceback, Android/iOS : MSBAnywhere header logo size does not match with the Xamarin app. iOS: ‘Cancel’ button is seen beside the clear search text ‘x’ icon. iOS: AppCrashes while tapping the cart icon | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/37561 | 2024-06-26 | 2024-06-26 | Ashwin | NA | NA | 2024-06-26 | NA | NA | NA | Closed | All issues are fixed and story completed.

## 14.0 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.0 Sprint 2 - Stretch | S-44881 | Sambath | Bounceback | Dev testing support, Bouncebacks, (iOS) - Text inputs boxes instead of lines (iOS) - Maui has a clear option for sales tag that does not exist in xamarin (Android / iOS) - Select and clear the shift user name, but still able to delete the shift user (Android / iOS) - Admin User: Add user pop up does not close after adding a new shift user (Android / iOS) - Clerk User: Admin pop up does not close after adding a new shift user (iOS) - App Crashes after adding new shift user and tapping the OK button of the success pop up (iOS) - Able to clear, edit and change the shift user name while ending the shift | Major | External | Inprogress | QA | Continue to working Bounce back issues
2 | 14.0 Sprint 2 | S-45181 | Sambath | Bounceback | Bounceback, Switching OFF the auto-renew and switching ON again, the auto-renew ON text is displayed incorrect in the Family Pass Membership section Switching OFF the auto-renew for the second time, auto-renew OFF text is displayed incorrectly in the Family Pass Membership section | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
3 | 14.0 Sprint 2 | S-44733 | Gokul | Bounceback | MSBP (Android/iOS) - App Crashes while logging in to the demo mode. Login works in test environment (Android/iOS) - System message pop up and Greenlight drawer is opened while navigating back to the home page (Left screenshot) - Bottom tab bar is not highlighted to the home page (Right screenshot) | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
4 | 14.0 Sprint 2 - Stretch | S-45084 | Gokul | Bounceback | Bounceback, After the text search for student ’981’, ‘9988’,etc,,, $0.00 dollar label shows blank. MSBAnywhere logo size does not match with the Xamarin app. In Landscape mode, the page texts should be centre aligned similar to the Xamarin app. iOS devices: ‘Cancel’ button is seen beside the clear search text ‘x’ icon. iOS devices: AppCrashes while tapping the cart icon | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
5 | 14.0 Sprint 2 - Stretch | S-42133 | Gokul | Bounceback | Bounceback, Android/iOS : MSBAnywhere header logo size does not match with the Xamarin app. iOS: ‘Cancel’ button is seen beside the clear search text ‘x’ icon. iOS: AppCrashes while tapping the cart icon | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.

## 14.0 M Sprint 1- CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 14.0 Sprint 1 | Gokul | S-42149 | MSBA - Maui - Shift Details (Old EOD Screen) - DEV Only | 2 | 3 | NA | NA | Dev only story, testing is not applicable, so no bouncebacks in this story | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/37453 | 2024-06-20 | 2024-06-20 | Ashwin | NA | NA | 2024-06-20 | NA | NA | Alignment changes Remove white space above Top bar | Closed | Development completed and closed the story
2 | 14.0 Sprint 1 Stetch | Gokul | S-42133 | MSBA - Maui - Invoices | 3 | 3 | NA | Samuel | Bounceback, MSBAnywhere logo size does not match with the Xamarin app. iOS devices: Unable to launch app in iOS devices due to provisioning profile issue iOS simulator: ‘Cancel’ button is seen beside the clear search text ‘x’ icon. iOS simulator: AppCrashes while tapping the cart icon | Sambath | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 1. In Ipad make the box's dimensions similar to xamarin forms. 2. Hide the cancel button appearing in IOS searchbar | Inprogress | Inprogress in fixing the POV comments. Cancel button issue and Msb logo issue are being fixed in the meal payments bounceback story as it is common fix
3 | 14.0 Sprint 1 | Samuel | S-44625 | MSBP- 13.8 Regression | 5 | 5 |  | Samuel | Bounceback, Android/iOS: Store icon is missing in the home page Android/iOS: Badge counter for invoices is on Quick Links Android :Did not receive Notifications iOS: Tapping the “No, skip for now" button in Adding your student(s) is super useful page does close its second blue page iOS: when a student is removed on a matching email account, instantly add student drawer is opened with the associated student account, does not wait for next login Android/iOS: -Tapping the ‘Add Selected Student’ button adds new student without navigating to the Notifications, Purchase Controls and Success page Added regression defects : 23499, 23528, 23503 and 23502 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Tested and closed the 13.8 regression defect 23499, 23528, 23503 and 23502
4 | 14.0 Sprint 1 | Sambath | S-42148 | 42148 MSBA - Maui - Shifts (Start/End) - DEV only | 1 | 3 | NA | NA | Dev only story, testing is not applicable, so no bouncebacks in this story | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/37574 | 2024-06-25 | 2024-06-25 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Development completed and closed the story
5 | 14.0 Sprint 1 | Sambath | D-23514 | 23514 MSBP - iOS - App does not respond if [+Add Student] is tapped before Update Profile displays (regression) | 1 | 1 | NA | Samuel | No bounceback in this defect | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37460 | 2024-06-13 | 2024-06-13 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Tested and closed the defect
6 | 14.0 Sprint 1 | Ashwin | D-23502 | 23502 MSBP - Android- When adding a student on new account, closes workflow (regression) | 1 | 1 | NA | Samuel | No bounceback in this defect | Sean | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37451 | 2024-06-13 | 2024-06-13 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Tested and closed the defect
7 | 14.0 Sprint 1 | Gokul | D-23499 | 23499 MSBP-iOS/Android-Remove student with matching email, instantly add student drawer is opened with the associated student account(Regression) | 1 | 1 | NA | Samuel | No bounceback in this defect | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37405 | 2024-06-11 | 2024-06-11 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Tested and closed the defect
8 | 14.0 Sprint 1 - Stretch | Sambath | S-44881 | 44881 MSBA - Maui - Shifts (Start/End) - Testing | 2 |  | NA | NA | Dev in progress, testing is not started | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | I picked this bounce back story at the end of the sprint so now continue to working on this bounce backs

## 14.0 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 14.0 Sprint 1 - Stretch | S-42133 | Gokul | Bounceback | Bounceback, MSBAnywhere logo size does not match with the Xamarin app. iOS devices: Unable to launch app in iOS devices due to provisioning profile issue iOS simulator: ‘Cancel’ button is seen beside the clear search text ‘x’ icon. iOS simulator: AppCrashes while tapping the cart icon | Major | External | Closed | QA | Bouncebacks are fixed, tested and closed the story.
2 | 14.0 Sprint 1 | D-23502 | Ashwin | Defect | Android- When adding a student on new account, closes workflow (regression) | Major | External | Closed | QA | Tested and closed the defect.
3 | 14.0 Sprint 1 | D-23499 | Gokul | Defect | MSBP - iOS/Android-Remove student with matching email, instantly add student drawer is opened with the associated student account(Regression) | Major | External | Closed | QA | Tested and closed the defect.
4 | 14.0 Sprint 1 | D-23528 | Ashwin | Defect | MSBP - iOS\Android - Home screen does not display GL banner and Quick Links after adding a student (regression) | Major | External | Closed | QA | Tested and closed the defect.
5 | 14.0 Sprint 1 | D-23512 | Ashwin | Defect | MSBP - iOS/Android - Greenlight - "Assign card to a student" tray does not display when opening the app when card(s) are not assigned (regression) | Major | External | Closed | QA | Tested and closed the defect.
6 | 14.0 Sprint 1 | D-23514 | Sambath | Defect | MSBP - iOS - App does not respond if [+Add Student] is tapped before Update Profile displays (regression) | Major | External | Closed | QA | Tested and closed the defect.

## 13.8 M Sprint 3 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.8 M Sprint 3 | Sambath | S-42148 | 42148 MSBA - Maui - Shifts (Start/End) - DEV only | 1 | 3 | [15 empty] | Inprogress | Working on Inernal testing fixes, and API's randamonly failed while fetching so i am looking the root cause.
2 | 13.8 M Sprint 3 | Gokul | S-44433 | MSBP - Login Performance - Speed up login | 2 | 2 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37245 | 2024-06-04 | 2024-06-04 | Ashwin | NA | NA | NA | NA | NA | NA | Closed
3 | 13.8 M Sprint 3 | Samuel | S-44623 | MSBP UI Automation- Update and Fix failures | 5 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
4 | 13.8 M Sprint 3 | Samuel | S-44625 | MSBP- Regression 13.8 | 5 | 5 |  | Samuel | Axosoft defects logged after executing the regression test cases: 21577, 23493, 23499 and 23502 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Completed testing and executed the test cases.Below is the test case link:https://dev.azure.com/heartlandschools/Mobile/_testPlans/define?planId=99874&suiteId=99881
5 | 13.8 M Sprint 3 | Gokul | S-42135 | MSBA - Maui - Meal Payments - Dev Only | 5 | 4.5 | NA | Samuel | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/37452 | 2024-06-18 | 2024-06-18 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Dev only story, so dev completed and POV is done
6 | 13.8 M Sprint 3 | Gokul | S-42149 | MSBA - Maui - Shift Details (Old EOD Screen) - DEV Only | 3 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Dev completeed, but need Shift story to be completed to fetch data and show POV
7 | 13.8 M Sprint 3 | Gokul | D-23499 | MSBP-iOS/Android-Remove student with matching email, instantly add student drawer is opened with the associated student account(Regression) | 2 | 2 | NA | Samuel | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37405 | 2024-06-11 | 2024-06-11 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Defect fixed and moved to testing
8 | 13.8 M Sprint 3 | Sambath | D-23493 | 23493 Android - Tapping the ‘Add Selected Student’ button adds new student without navigating to the Notifications and Success page(Regression) | 1 |  | NA | Samuel | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/37393 | 2024-06-10 | 2024-06-10 | Ashwin | NA | NA | NA | NA | NA | NA | Closed
9 | 13.8 M Sprint 3 | Ashwin | D-23301 | 23301 MSBA- iOS/Android - upon starting first shift, not directed off shift page (regression) (13.8) | 1 |  | NA | Samuel | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/37130 | 2024-05-24 | 2024-05-24 | Ashwin | NA | NA | NA | NA | NA | NA | Closed

## 13.8 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1

## 13.8 M Sprint 2 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.8 M Sprint 2 | Samuel | S-44621 | MSBP UI Automation- Update and Fix failures | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | AppCentre log analysis: Android and iOS- Due to the pipeline issues, UI automation tests for 13.8 builds were not executed in the AppCentre. Executing the UI automation tests in the local environment for the build 13.8 (iOS/Android) - In Progress
2 | 13.8 M Sprint 2 | Samuel | S-44622 | MSBA UI Automation- Update and Fix failures | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | AppCentre log analysis: Android and iOS- Due to the pipeline issues, UI automation tests for 13.8 builds were not executed in the AppCentre. Android Tablet (Passed)- completed executing the UI automation tests in the local environment for the build 13.8.
3 | 13.8 M Sprint 2 | Gokul | S-42132 | MSBA - Maui - Product Details - DEV Only | 2 |  | NA | NA | NA | Sambath | Remove commented code | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36716 | 2024-05-22 | 2024-05-23 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Development completed
4 | 13.8 M Sprint 2 | Gokul | S-42131 | MSBA - Maui - Products | 1 |  | NA | Samuel | iOS - Most recent iOS builds cannot be verified, facing “Unable to Install ‘MSB Anywhere -iOS -QA” error pop up message while trying to launch the app. | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/37048 https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/37027 | 2024-05-21 | 2024-05-22 | Ashwin | NA | NA | NA | NA | NA | NA | Closed | Development completed
5 | 13.8 M Sprint 2 | Sambath | S-43341 | 43341 MSBA - Maui - Forgot Password Workflow | 2 | 2 |  | Samuel | Bounceback, Android - Send via Email and Send via Text Message buttons failed to work and unable to navigate to the respective pages. iOS - Most recent iOS builds cannot be verified, facing “Unable to Install ‘MSB Anywhere -iOS -QA” error pop up message while trying to launch the app. | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Bounceback Android - Send via Email and Send via Text Message buttons failed to work and unable to navigate to the respective pages. iOS - Most recent iOS builds cannot be verified, facing “Unable to Install ‘MSB Anywhere -iOS -QA” error pop up message while trying to launch the app.
6 | 13.8 M Sprint 3 | Sambath | S-42148 | 42148 MSBA - Maui - Shifts (Start/End) - DEV only | 3 | [16 empty] | Inprogress | I'm looking for the root cause of the API requests that are randomly failing and fixing the internal testing issues
7 | 13.8 M Sprint 3 | Ashwin | D-23396 | 23396 MSBA - iOS/Android - forgot login text not sending 13.8 | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed
8 | 13.8 M Sprint 2 | Gokul | D-23423 | 23423 MSBP - Android - No permissions requested for notifications | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | [6 empty] | Inprogress

## 13.8 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 13.8 M Sprint 2 | S-42131 | Gokul | Bounceback | iOS- when scanning a bad barcode, error message appears as expected, but selecting OK prompts the error message to come up again. Error message only goes away if user clicks elsewhere on the screen first and then the OK on the error message Letashia James5/13/2024 12:55 PM Confirmed that the error message no longer loops, however now seeing new behavior on bad scan. If tablet is pointed at bad barcode still at time error message appears, it continuously scans the barcode, stacking the error messages. Only way to stop is to point camera elsewhere, even though camera box no longer exists on screen Letashia James5/20/2024 1:54 PM | Minor | External | Inprogress | Environment_Related | IOS barcode error message showing multiple times issue fixed. Gokul Narayanan5/19/2024 3:35 AM Issue with multiple error messages appearing and stacking on pointing the tablet at bad barcode is also fixed. Gokul Narayanan5/23/2024 8:41 AM

## 13.8 M Sprint 1 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.7 M Sprint 3 Stretch | Gokul | S-42132 | MSBA - Maui - Product Details |  |  |  | Samuel | Scanned with the barcode camera, but the barcode number is captured in the barcode number field (iPhone) x’ icon to cancel text and numeric text is not present in the Xamarin app (iPhone/iPad) Student barcode scanner does not work as expected (iPhone) Toaster message after adding product to the cart is missing ‘Successfully added ProductABC to Cart.’ (Android/iOS) Unlike the Xamarin App, ‘Add To Cart’ button is not disabled when the ‘Available Stock quantity is 0’ (Android/iOS). Required field validation warning pop up is missing (Android/iOS) | [12 empty] | Inprogress
2 | 13.7 M Sprint 3 Stretch | Sambath | S-43341 | 43341 MSBA - Maui - Forgot Password Workflow | 3 | 5 |  | Samuel | Device used - Android Tablet (Samsung Galaxy Tab A (Android 11)) App Crashes after tapping the ‘I have a Code’ button in Reset Password page App Crashes after entering the valid email address and tapping the ‘Next’ button Forgot Password- tapping Cancel button in the reset password page, login page loads Enter Email address, Validation Code,… - ‘Next’ button should not be look like enabled before entering a valid email format Closing the Enter Email address, Validation Code, pages… by tapping the ‘X’ icon and selecting Yes in the warning message shows a blue page and navigates to the login page slowly |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36803 | 2024-09-05 | 2024-09-05 | Ashwin | None | NA | NA | NA | NA | NA | Inprogress | Bouncebacks: iOS- 1)when entering phone number in the text box the first digit types properly, then the cursor jumps in front of it and typing continues there. This continues any time you attempt to click at the end of the input. 2) following this issue, if you have text in the phone number box and attempt to go back to add something in the middle, after every entry of a number, the cursor will jump to between the second to last and last digit and continue typing there. Sometimes on initial click back into text to change, the cursor will jump to second to last placement causing multiple clicks to be needed 3)when requesting a text validation code, receiving error. This then causes the app to be stuck with a loading symbol which never resolves- cannot interact with error message underneath. No error message is presented in Android in this workflow. It appears that there may not actually be a code being sent per notification hub in xamarin as well- defect 23396 has been created to resolve that underlying issue
3 | 13.8 M Sprint 1 (Stretch) | Samuel | S-44618 | MSBP UI Automation- Update and Fix failures | 5 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Executing the UI automation tests in the local environment ( Android/iOS).
4 | 13.8 M Sprint 1 (Stretch) | Samuel | S-44619 | MSBA UI Automation- Update and Fix failures | 5 | 5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/36863 | 2024-09-05 | 14/5/2024 | Ashwin | None | NA | NA | NA | NA | NA | Closed | Executed in the local environment and all the UI automation tests have passed in ( Android/iOS). 1 Failure in iOS Phone landscape mode and this is related to the Defect ( 22774 - MSBA-iOS Landscape-Unable to close the keyboard after entering UN or PWD in the add or delete shift users admin authentication pop up ) AppCentre: Android & iOS- Due to the build issue in release pipeline, UI automation tests for 13.7 builds were not executed in the AppCentre.

## 13.8 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No Defects reported

## 13.7 M Sprint 3 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.7 M Sprint 3 | Sambath | D-19537 | 19537 MSBA - iOS/Android - Honored Discounts Not Reflected In Cart/Payment Method Screens Prior to Checkout | 1 | 1 | NA | Samuel | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/36581 | 2024-04-23 | 2024-04-23 | Sean | NA | NA | NA | NA | NA | NA | Closed
2 | 13.7 M Sprint 3 | Samuel | S-44404 | MSBP UI Automation- Update and Fix failures | 5 | 6 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36627 | 2024-04-24 | 2024-04-25 | Ashwin | None | NA | NA | NA | NA | NA | Closed | In this Sprint, executed the UI automation tests in the local environment, fixed the failures, added automation for validating the labels in -GL Marketing page -Manage Payment Method page -PayInvoicesPage -RefundStudentBalanceCompletePage -ResetPasswordLandingPage -ScheduledPaymentsPage -ScheduledPaymentDetailPage and created a pull request. AppCentre log analysis: Android and iOS- Due to the pipeline issues, UI automation tests for 13.7 builds were not executed in the AppCentre.
3 | 13.7 M Sprint 3 | Samuel | S-44405 | MSBA UI Automation- Update and Fix failures | 5 | 4 | NA | NA | NA | NA | NA | [5 empty] | NA | NA | NA | NA | NA | Closed | In this sprint, executed the UI automation with checkout test steps and fixing the automation failures (Android/iOS) - In Progress AppCentre execution: Android & iOS- Due to the build issue in release pipeline, UI automation tests for 13.7 builds were not executed in the AppCentre.
4 | 13.7 M Sprint 3 | Ashwin | D-23250 | 23250 MSBP - iOS/Android- Display issue on checkout for split order/promocodes (regression) | 1 | 1 | NA | Samuel | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36637 | 2024-04-25 | 2024-04-25 | Sean | NA | NA | NA | NA | NA | NA | Closed
5 | 13.7 M Sprint 3 Stretch | Sambath | S-43928 | 43928 MSBP - AutoPay - SOS24 - Auto Prompt Parent to Make First Payment | 3 | 4 |  | Samuel | Invalid CVV code is accepted CVV code is prompted for a verified payment method which has already completed a payment once Drawer is opened for the student which has already completed a payment ECheck payment method prompts for CVV security code entry field in the drawer | Gokul |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36550 | 22-04-2024 | [8 empty] | Inprogress | Devlopment completed, and Moved to testing, after that for testing brain will assist in getting balance updated in MSB.
6 | 13.7 M Sprint 3 Stretch | Gokul | S-42131 | MSBA - Maui - Products | 1 | 0.5 |  | Samuel | None | Sambath | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36597 | 2024-04-23 | 2024-04-24 | Ashwin | None | NA | NA | NA | NA | NA | Inprogress | Development completed and moved to testing. But due to regression testing not yet done
7 | 13.7 M Sprint 3 Stretch | Gokul | S-42132 | MSBA - Maui - Product Details | 8 | 8 |  | Samuel | (Android Tablet)- Gap between Student, Stock Option, Price and Quantity is less and not similar to Xamarin app. -Unable to remove the barcode number entered by tapping the ‘X’ icon -Cancel and Save buttons are slightly hidden at the bottom | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA | NA | Inprogress | Done with most of the changes. But there are few controls like Picker, HTML view and Date picker which is customised in Xamarin forms. Working in progress to implement those controls customization in MAUI, in which implementing those controls customisation is different from Xamarin forms.
8 | 13.7 M Sprint 3 Stretch | Sambath | S-43341 | 43341 MSBA - Maui - Forgot Password Workflow | 5 | 5 | NA |  |  | NA | NA | [10 empty] | Inprogress | Full UI workflow Completed, and Continue to working on bussiness logic and cosmetic UI issues

## 13.7 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported.

## 13.7 M Sprint 2 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.7 M Sprint 2 | Ashwin | D-23037 | 23037 MSBP - Open Pricing Field Format Malfunctioning | 2 | 2 |  |  |  | Sean | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36387?_a=files | 2024-04-11 | 2024-04-11 |  | None | NA | 2024-04-11 | None |  |  | Closed
2 | 13.7 M Sprint 2 | Sambath | S-43928 | 43928 MSBP - AutoPay - SOS24 - Auto Prompt Parent to Make First Payment | 3 | 5 | [15 empty] | Inprogress | Development completed, but new AC is added at end of this sprint so this story is carried to next sprint for POV and Testing AC: Added 4/15: A payment will now be applied to your student balances below your low balance threshold. Press CANCEL to go back to your AutoPay settings Added 4/15: Combine this above message with the current "AutoPay Successfully Updated!" message if student with balance below threshold = true. Otherwise, only show "AutoPay Successfully Updated!" message instead.
3 | 13.7 M Sprint 2 | Samuel | S-44248 | MSBA - UI Automation - Update, Run, Check and Fix failures | 5 | 4 | NA | NA | NA | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/36399 | 2024-04-11 | 2024-04-12 |  | None | NA | NA | NA | NA | NA | Closed | In this Sprint, executed the UI automation tests in the local environment and fixed the failures (Android/iOS). Except the Checkout pop up related UI tests all the other UI tests are passed in the local environment, checkout pop up tests are failed due to the recent UI changes. Android and iOS- Due to the pipeline issues, UI automation tests for 13.7 builds were not executed in the AppCentre.
4 | 13.7 M Sprint 2 | Samuel | S-44247 | MSBP - UI Automation - Update, Run, Check and Fix failures | 5 | 5 | NA | NA | NA | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36437 | 2024-04-15 |  |  | None | NA | NA | NA | NA | NA | Closed | In this sprint, newly added 55 UI elements for Home page Add Student drawer, completed the UI mappings and automation steps. PR Link: https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36437 Updated MSB Parent UI Automation elements excel link: https://docs.google.com/spreadsheets/d/1H-dLzXBuZqRS5gYHS4__DRV43wQ8IYiMQoo6wWjbk6k/edit#gid=2061556741 AppCentre execution: Android & iOS- Due to the build issue in release pipeline, UI automation tests for 13.7 builds were not executed in the AppCentre.
5 | 13.7 M Sprint 2 | Ashwin | D-19537 | 19537 MSBA - iOS/Android - Honored Discounts Not Reflected In Cart/Payment Method Screens Prior to Checkout | 3 | 3 | [5 empty] | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/36446 | 2024-04-16 |  | Sean | Hi | [5 empty] | Inprogress | Development completed, and It's now in Peer Review
7 | 13.7 M Sprint 2 | Ashwin | S-44201 | 44201 MSBP - SOS24 - Remove Daily as an Option in AutoPay Meal Settings (13.7) | 3 | 3 | NA |  |  | Sean | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36313 | 2024-04-06 | 2024-04-06 | NA | NA | NA | NA | NA | NA | NA | Closed
6 | 13.7 M Sprint 2 Stretch | Gokul | S-42131 | MSBA - Maui - Products | 3 | 2 | NA | Samuel | NA | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36301 | 2024-04-08 | 2024-04-09 | Ashwin | NA | NA | NA | NA | NA | NA | Inprogress | Bounceback fixes completed and moved to external testing
8 | 13.7 M Sprint 2 Stretch | Gokul | S-42138 | MSBA - Maui - Settings | 5 | 3.5 | NA | Samuel | Android-Font size of Store search text, Address header and text entered, Port header and value entered does not match with the xamarin app Android-After selecting a printer, unable to change to any other printer. - Android/iOS: saved printer value is not retained after saving the settings and coming back to the settings page. Android Phone: Sales Tag Options- After select and saving the school number, unable to close the keyboard. | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36377 | 2024-04-08 | 2024-04-11 | Ashwin | NA | NA | NA | NA | NA | NA | Inprogress | Bounceback fixes completed and moved to external testing
9 | 13.7 M Sprint 2 Stretch | Gokul | S-42132 | MSBA - Maui - Product Details | 8 | 3 | NA | Samuel | [13 empty] | Inprogress

## 13.7 M Sprint 1 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.7 M Sprint 1 Stretch | Gokul | 42131 | MSBA - Maui - Products | 3 | 4 | NA | Samuel |  | Sambath |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36121 https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36179 | 2024-03-22 | 2024-03-22 | Ashwin | None | NA | NA | None | None | Clear sort icon cut off in the edge | Inprogress | Blockers: Running in debug mode is not replicating the issues caused during running in Release mode. Also there is challenge in running release mode in local, so got help from Sambath and resolved the crash issues in release mode. Regarding Iphone the telerik control that we use is causing certain issues. In Xamarin forms in IOS the products page loads products only on scrolling to the end of page. But in MAUI it is loading entire products on page load itself. Tried to fix this issue in the telerik control that we already used and the fix is not working. So trying with different control to fix this issue. But on replacing with other control also have challenges in MAUI as it is also causing issues. Checking on the same. Bouncebacks: "Camera opens but it does not scan the barcode messaging when clearing a filter says ""confirm"" as the header instead of ""Warning"" Android only- refresh time of page is 12 seconds vs prior 5 seconds. iOS seems to still be quick The search bar is all caps and the wrong font"
2 | 13.7 M Sprint 1 Stretch | Ashwin | 42129 | 42129 MSBA - Maui - Login Screen | 2 | 3 |  |  |  | Sean ,Avery, Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36084?_a=files https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36243 https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/36120 | 2024-03-22 | 2024-03-22 | Ashwin | None | NA | NA | None | None | None | Inprogress | Bouncebacks: -If login and enable menu items,then log out, the items remain on the login screen. Selecting them bypasses the login -font for "are you a parent" "remember me" have a font that seems to have a larger spacing than other items on the page- different font? -within mode settings there appear to be 2 sets of font/font spacing on the same page -request from Jason to add an extra space above and below login button for ease of use -Android only- mode settings the Select One is black instead of grey -A- remember me retrains and auto logs in, however there is no loading indicator (just grey screen) -i- remember me holds onto username, but does not log user into MSBA - links at the bottom are not bolded, and it doesnt appear that "get our parent app" is either (but this might be related to font issue above?) NOTE : One more issue is still pending that is loading indiator is not working, that is the foundation level issue so Sean J is looking into that.
5 | 13.7 M Sprint 1 | Sambath | D-23039 | 23039 MSBP - iOS - cannot take photo (regression) | 2 | 2 |  |  |  | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36078 https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36194 | 2020-03-20 | 2024-03-28 | Ashwin | None | NA | NA | None | None | None | Closed | Bounce Back: issue seems to be that if permissions were initially denied on the device, cannot get the photo to allow at a later time- even if permission is granted manually through phone settings
3 | 13.7 M Sprint 1 | Samuel | 44105 | MSBP - UI Automation - Update, Run, Check and Fix failures | 5 | 5 |  | NA | None | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36226 | 2024-04-01 | 2024-04-02 | Ashwin | None | NA | NA | None | None | None | Closed | In this Sprint, executed the UI automation tests in the local environment, fixed the failures and created a pull request. PR: https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36226 AppCentre log analysis: Android and iOS- Due to the pipeline issues, UI automation tests for 13.7 builds were not executed in the AppCentre.
4 | 13.7 M Sprint 1 | Samuel | 44106 | MSBA - UI Automation - Update, Run, Check and Fix failures | 5 | 5 |  | NA | None | Ashwin | None | [5 empty] | NA | NA | None | None | None | Closed | In this Sprint, executed the UI automation tests in the local environment, fixed the failures and created a pull request. AppCentre log analysis: Android and iOS- Due to the pipeline issues, UI automation tests for 13.7 builds were not executed in the AppCentre.
5 | 13.7 M Sprint 1 | Sambath | 44132 | 44132 MSBP - AutoPay - Auto Prompt Parent to Make First Payment (Research) | 2 | 2 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Following are the investicated steps for processing the first autopay meal payment. Step 1: Generate the BasketKey for the each transaction mobileapi/9.0/baskets/basketkey Step 2: Verify the Threshold value with each student balance Step 3: if the Student balance is lesser than threshold value then should be added to basket item with selected amount using the below api mobileapi/9.0/parent/basket/{BasketKey}/mealPayment Step 4: if the Payment method is not verified, then ask CVV code for verification. Step 5: Selected payment method should be check if any Program Fees or AnnualProgram Fees are available For getting the ProgramFees, AnnualProgramFees mobileapi/9.0/parent/basket/{BasketKey}/preview Step 6: Execute the basket items for processing meals payments using the below api mobileapi/9.0/parent/basket/{BasketKey}/process Step 7: we need to call this (mobileapi/9.0/parent/students) api for getting the updated meal balance, but it's not working as expected. because it has been running on Hourly bassis by using Housekeeping Task. so only we are getting the pending balance amount from this api Workaround Challanges We have to prevent the dublicate meals payment, if the parent is resubmit from the autopay setitngs.
6 | 13.7 M Sprint 1 Stretch | Gokul | 42138 | MSBA - Maui - Settings | 3 | 2 | NA | Samuel | Sales Tag Options: Sales Tag watermark text is darker School number is retained in the sales tag pop up Free text font size and entry field does not match Card Reader: C2X/C3X text is missing Configure button text is incorrect Audio Jack and Configure button colour and font size does not match. Require signature for swipe transactions: When the cursor is placed, unable to view more than 5 characters. Xamarin app displays 10 characters. ‘X’ icon does not delete any entered values. Xamarin app does not have ‘X’ icon Barcode scanner: iOS: App crashes after tapping the toggle button | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | zz
7 | 13.7 M Sprint 1 Stretch | Gokul | 19537 | 19537 MSBA - iOS/Android - Honored Discounts Not Reflected In Cart/Payment Method Screens Prior to Checkout | 3 | 1 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Since MAUI bounceback issues are in progress, this is picked up by Sambath

## 13.7 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 13.7 M Sprint 2 Stretch | S-42138 | Gokul |  | Bouncebacks: Tickets is still not showing (original issue was resolved, but new one happening?) A-when adding PAX information it bumps the no reader to the next line and then it overlaps the two fields i-missing the x on the search store box i-box under enabled auto print of receipts stays when disabled as a blank space i-if printer selection box was open and then the enable receipt toggle was turned off(able to do in iOS only) the menu stays open (previously closed when disabled) i-require signature for swipe is a full box instead of prior entry line i-sales tag options both have the entry box cut off at the corners- this was previously just an entry line though as well i- no reader is showing by default on a second line- prior versions had this all in one line when nothing was selected Letashia James 4/8/2024 11:15 AM | Significant | External | Inprogress | Development | Mentioned issues are fixed except for the below points: -> i-missing the x on the search store box - Implemented control’s close icon which will appear when any text is entered. Checked with Jason and implemented it as there’s some issue in implementing the close icon in MAUI similar to Xamarin app -> i-if printer selection box was open and then the enable receipt toggle was turned off(able to do in iOS only) the menu stays open (previously closed when disabled) - There is open issue regarding picker not closing on clicking outside https://github.com/dotnet/maui/issues/19168. Tried the workaround and it is closing the picker when I click outside controls like empty space. But if I click on any controls like toggle or checkbox the picker is still not closing as the unfocus event of Picker is not firing. -> Tickets is still not showing (original issue was resolved, but new one happening?) - Sean Will have to check if the firebase config has been set for MAUI Gokul Narayanan 4/11/2024 10:48 AM
2 | 13.7 M Sprint 2 Stretch | S-42131 | Gokul |  | Bouncebacks: Camera opens but it does not scan the barcode messaging when clearing a filter says "confirm" as the header instead of "Warning" Android only- refresh time of page is 12 seconds vs prior 5 seconds. iOS seems to still be quick The search bar is all caps and the wrong font Letashia James3/29/2024 12:47 PM | Significant | External | Inprogress | Development | Fixed the mentioned issues including the App bar store icon bold issues in Android. But unable to fix the Android refresh slow loading issue. Checked it and seems like time taken to get the data from API is almost same in both MAUI and Xamarin apps, but the time taken to render is slow in MAUI. Gokul Narayanan 4/8/2024 12:29 PM
3

## 13.6 M Sprint 3 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.6 M Sprint 3 Stretch | Gokul | 42130 | MSBA - Maui - MFA | 3 |  |  | Samuel | Android real device(Google Pixel 4a (Android 13))- Entered the MFA Code and tapping Save&Close in the settings, the App Freezes with the app launch image. Same steps in iPhone 11 real device (iOS 17.3)- App Crashes. 'Remember Me' in the login page does not work as expected, when MFA remember me is enabled first and then, followed by the login page remember me. | [12 empty] | Inprogress | Bounceback UI issues are fixed. Working on the remember me issues. Blockers: Unable to deploy the changes in actual device. This prevented us from testing out the actual changes in device & minor differences in UI between simulator and device was leading to bounceback issues. Fixed this problem in Android device but in Iphone still not able to deploy in phone/tab
2 | 13.6 M Sprint 3 Stretch | Gokul | 42131 | MSBA - Maui - Products | 5 |  | Yes | Samuel | Sort icon is missing after switching from ‘View All’ stores Unable to sort after switching from ‘View All’ stores Filter-Groups is empty In iPhone, filters drawer is cut in the top and the bottom | Sambath | Delete commented code. Refactor code changes | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/35610 | 2024-03-07 | 2024-03-08 | Ashwin | NA | NA | NA | NA | NA | IOS - Issues with load more and filters tab view in mobile not occupying full screen needs to be fixed. | Inprogress | In progress on POV comments. Blockers: While running in Android and IOS simulators the page is loading as expected. But when downloaded the release build the app is crashing in IPhone and struck in splash screen in Android when the product page is loaded. As mentioned before, since we are not able to deploy in device in our local environment not able to test the changes completely. Can check in Android only currently and working on the splash screen issue. Regarding Iphone the telerik control that we use is causing certain issues. Like the issue with loading the complete products catalog on page load itself, instead of loading certain number of products only on scrolling to page end. And issue with Filter tab not occupying complete page height. Since there's no direct fix for it in MAUI, we are checking on the workaround fix, leading to the time consumption.
3 | 13.6 M Sprint 3 | Sambath | 22967 | DEFECT 22967 MSBP - Android/iOS - Quicklinks in student card open in web | 3 | 4 |  | Samuel | Error pop up while navigating to the '1 All Product (District Wide)' from Student drawer and through the Quicklinks page | Gokul | No | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35851 | 2024-03-07 | 2024-03-07 | Avery | NA | NA | NA | NA | NA | No | Closed
4 | 13.6 M Sprint 3 Stretch | Ashwin | 42129 | 42129 MSBA - Maui - Login Screen | 5 | [16 empty] | Inprogress | Permission code foundation is not working as excpected, so waiting for permission changes from the client side, Meanwhile checking with our side to handle the permissions
5 | 13.6 M Sprint 3 | Samuel | 43885 | MSBP - UI Automation - Update, Run, Check and Fix failures | 5 | 5 | NA | Samuel | None | Ashwin | No | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/36061 | 2024-03-19 |  | NA | NA | NA | NA | NA | NA | NA | Closed | In this Sprint, completed the UI mappings for Add Student drawer and added the UI automation steps for validating the labels and texts in the Green Light pages. Upgraded the Xamarin.UI Test package from 3.2.9 to 4.3.3 version and able to execute the UI automation test in the local environment (Android/iOS) AppCentre log analysis: Android and iOS- Due to the pipeline issue, UI automation tests for 13.6 builds were not executed in the AppCentre.
6 | 13.6 M Sprint 3 | Samuel | 43886 | MSBA - UI Automation - Update, Run, Check and Fix failures | 5 | 5 | NA | Samuel | None | Ashwin | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Upgraded the Xamarin.UI Test package from 3.2.9 to 4.3.3 version and able to execute the UI automation test in the local environment (Android/iOS) AppCentre log analysis: Android and iOS- Due to the pipeline issue, UI automation tests for 13.6 builds were not executed in the AppCentre.
7 | 13.6 M Sprint 3 Stretch | Sambath | D-23039 | 23039 MSBP - iOS - cannot take photo (regression) | 2 | [16 empty] | Inprogress | this regression defect is taken at the end of sprint so it is carried to next sprint

## 13.7 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 13.7 M Sprint 1 Stretch | 42138 MSBA - Maui - Settings | Gokul | Bounceback | Bounce backs: - Setting store, meals, invoice - default - text shrinking - Settings - iOS icons for the store being white is to be included in this story as a bounceback - setting default stores not loading - messaging when clearing a filter says "confirm" as the header instead of "Warning" - The search bar is all caps and the wrong font | Minor | External | Inprogress | Development | Fixing the issues. First point is related with MAUI rendering the control elements
2 | 13.7 M Sprint 1 Stretch | 42131 MSBA - Maui - Products | Gokul | Bounceback | Camera opens but it does not scan the barcode messaging when clearing a filter says "confirm" as the header instead of "Warning" Android only- refresh time of page is 12 seconds vs prior 5 seconds. iOS seems to still be quick The search bar is all caps and the wrong font | Minor | External | Inprogress | Development | In progress
3

## 13.6 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 13.6 M Sprint 3 Stretch | 42130 | Gokul | Bounceback | -remember toggle on Android phone not fixed, it is still white and blends with background -Android tablet and phone the square for the 2 step verification is cut off on the right side (makes the shadow appear to be a sharp square) -Android tablet the 2-factor code box is cut off at the bottom, Android phone is cut off on the bottom and right side -Remember device does not work. It appears that no matter if the remember device was set or not, if using log out button, can always log back in with no MFA. If selecting the remember device on MFA and app is closed, still prompted to MFA. (strange login loop happens following the first with no remember checked using the log out: login>MFA>no remember device>TOS>Settings>log out>log in>skips MFA>TOS>back to login screen>login once more>TOS again>Settings again) | Minor | External | Inprogress | Development | UI issues were caused in dark theme, which has been fixed. But the MFA remember me issues are caused by preferences storage which is not working as expected in MAUI. Working on the issue fix.
2
3

## 13.6 M Sprint 2 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.6 M Sprint 2 | Sambath | 43394 | 43394 MSBP - Auto Detect Students - Prompt Parent to Add Student | 5 |  |  | Samuel |  | Ashwin | AutoPay drawer size is increased After selecting a student and tapping the ‘Add Selected Student’, the drawer size increases and occupies the whole page Nothing happens after tapping the question mark icon of ‘Notify me in the app’ Success message texts are missing below the thumbs up icon No more multi select of students, so ‘(s)’ can be removed from the ‘Add Selected Student(s)’ button | [10 empty] | Closed
2 | 13.6 M Sprint 2 | Samuel | 43720 | MSBP - UI Automation - Update, Run, Check and Fix failures | 5 | 5 |  | Samuel | None | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35749 | 2024-03-04 | 2024-03-04 | Ashwin | None | NA | NA | NA | NA | NA | Closed | Android & iOS- Due to the build issue in release pipeline, UI automation tests for 13.6 builds were not executed in the AppCentre. Due to the AppCentre issues, I have executed the UI automation tests in the local environment and fixing the failures and Upgraded the Xamarin.UI Test package to 4.3.3 version (Android/iOS)
3 | 13.6 M Sprint 2 | Samuel | 43721 | MSBA - UI Automation - Update, Run, Check and Fix failures | 5 | 5 |  | Samuel | None | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/35748 | 2024-03-04 | 2024-03-04 | Ashwin | None | NA | NA | NA | NA | NA | Closed | In this Sprint, worked on iPhone and iPad fixes, Reset Password page text validations. Due to the AppCentre issues, I have executed the UI automation tests in the local environment and fixing the failures and Upgraded the Xamarin.UI Test package to 4.3.3 version (Android/iOS)
4 | 13.6 M Sprint 2 | Ashwin | 43167 | 43167 MSBA - AirPrint/Cloud Print - Detect printer and scale accordingly (13.6) | 4 | [16 empty] | Closed | The story is blocked due to Star Micronics Airprinter limitations is setting the paper size. Moving to need more info state.
5 | 13.6 M Sprint 2 | Gokul | 42138 | MSBA - Maui - Settings | 3 | 2 |  | Samuel | SaleTag options, School number and Free text values are retained | Sambath |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/35661 | 2024-02-28 | 2024-02-28 | Ashwin | None | Sean | NA | This should be injected in the ctor and shouldn't need to be retrieved like this This isn't needed. There is one in the CommunityToolkit that you can use instead | NA | NA | Inprogress | This story is being tested by QA
6 | 13.6 M Sprint 2 | Gokul | 42130 | MSBA - Maui - MFA | 2 | 1 |  | Samuel | Credentials in the login page are retained after closing the MFA page or tapping switch account and navigating to the login page. (Android/iOS) | Sambath |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/35685 | 2024-02-29 | 2024-02-29 | Ashwin | None | Sean | NA | Isn't this a virtual in the base class? If not change it to a virtual and then override it instead of hiding it with new | NA | NA | Inprogress | This is tested by QA and have added bouncebacks during the last da
7 | 13.6 M Sprint 2 Stretch | Gokul | 42131 | MSBA - Maui - Products | 2 | 3 |  | Samuel | Android: Sort icon is missing after switching from ‘View All’ stores Unable to sort after switching from ‘View All’ stores Filter-Groups is empty Unable to navigate to the product details page, throwing an error pop up iOS : Found the below error pop up while trying to swap products and, Filters drawer is cut in the bottom and top | [12 empty] | Inprogress | Carried to next sprint due to difficulties in merging latest branch which is having build issues in Macbook
8 | 13.6 M Sprint 2 Stretch | Sambath | 42142 | 42142 MSBA - Maui - TOS | 2 | 2 |  |  |  | Gokul | None | [10 empty] | Inprogress | Dev Completed, Testing is pending
8 | 13.6 M Sprint 2 Stretch | Ashwin Majella | 42129 | 42129 MSBA - Maui - Login Screen | 5 | 5 | [15 empty] | Inprogress
9
10

## 13.6 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 13.6 M Sprint 2 | 42138 | Gokul | Bounceback | Android: user settings title should not be bolded text @ top should be grey, not bold black missing tickets option? text is not centered with the checkboxes checkboxes appear smaller upon selecting another enabled menu item, all options for default home page dissappear search store does not have border cannot stop cursor from flashing in search line when clicking elsewhere in app when first checkbox in stores is selected, the entire list disappears record sales tag does not open sales tag options disabling receipt leaves large gap instead of moving options up printer list is missing TSP143 enable auto print does not open number of receipts button c2x and pax do not open configuration options IOS: There is an extra < in the top left corner of settings that should not be there | Minor | External | Inprogress | Development | Most of issues in Android were not able to check because of difficulties in running in Android initially.
2 | 13.6 M Sprint 2 | 42130 | Gokul | Bounceback | IOS and Android: can't close keyboard by clicking off the box (big issue in phones which dont have an option to minimize it) the x in the upper right corner of the 2 step verification process is not bolded Android Only: no loading icon after login>2 step verification page email is cut off in the button on the 2 step verification page enter code box is cut off on the ends (but if selected the highlight seems to end the box at the expected margin of the page) remember toggle seems to be cut off since the circle is the same color as the background- the circle disappears when moving (picture in attachments) in phone the remember toggle is white and matches the background so it does not appear to exist at all | Minor | External | Inprogress | Development | Most of issues in Android were not able to check because of difficulties in running in Android initially.
3 | 13.6 M Sprint 2 | 42142 | Sambath | Bounceback | 1. Both- when adding one last/only student through the tray the success page says "You can add another student now or continue...." however there is no option to add another student in this view. Should it have "You can continue..." when there are no more to add? 2. Android- the Done button on the success screen is off the page and it is not a scrollable page (not off in iOS but it is scrollable in that view) 3. iOS- missing header information on tray "the following student(s) were found associated with email" | Minor | External | Inprogress | Development | Device Specific issues
4 | 13.6 M Sprint 2 Stretch | Ashwin Majella | 42129 | Bounceback | -Per discussion at standup links(mode settings, terms of service, privacy policy) should be in the bottom of the page -the box size does not appear to be adjusted to what it was previously- remember me and forgot login are very close as well as the text input boxes being smaller -remember me checkbox does not retain login information after app closes -missing additional popups (allow notifications, MSBA would like to use Bluetooth for new connections(when BT is off I believe this is prompted, and Would like to use bluetooth (barcodes and receipts)) pictures in attachments -on iOS the background should be blurred behind these notifications and on Android the screen should be a darker grey -neither demo nor staging log in when mode is changed -Android the checkboxes within mode settings are smaller -Mode settings icon changed | Minor | External | Inprogress | Development

## 13.6 M Sprint 1 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.6 M Sprint 1 | Sambath | 43394 | 43394 MSBP - Auto Detect Students - Prompt Parent to Add Student | 5 | 6 | [15 empty] | Inprogress | This story has been moved to next sprint due to below AC changes 1. only able to add one student at a time 2. After add student, prompt parent to set notification settings like we do in the current add student workflow. 3. Consider save and add new students on notification page. OR, after notifications are saved, bring back parent to add another student if more students detected ​4. for the note on the drawer, let's update it to "The following student(s) were found associated with email."
2 | 13.6 M Sprint 1 | Sambath | 22778 | 22778 MSBP - Android - Adding your student(s) is super useful box closing (regression) | 2 | 2 |  | Samuel | None | Gokul | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35350 | 2024-08-02 | 2024-08-02 | Ashwin | None | NA | NA | NA | NA | NA | Closed
3 | 13.6 M Sprint 1 | Samuel | 43570 | MSBP-UI Automation-Update and fixing failures | 5 | 6 |  | Samuel | None | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35418 https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35487 | 12/2/2024-16/2/2024 | 2024-12-02 | Ashwin | None | NA | NA | NA | NA | NA | Closed
4 | 13.6 M Sprint 1 | Samuel | 43571 | MSBA-UI Automation-Update and fixing failures | 5 | 6 |  | Samuel | None | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/35527 | 20-02-2024 | 20-02-2024 | Ashwin | None | NA | NA | NA | NA | NA | Closed
5 | 13.6 M Sprint 1 Stretch | Gokul | 42131 | MSBA - Maui - Products | 3 | 7
6
7
8
9
10

## 13.6 M Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 13.6 M Sprint 1 | No Defects in this sprint

## 13.5 M Sprint 3 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.5 M Sprint 3 | Sambath | D-22662 | 22662 MSBP - Webforms being cut off | 1 | 1 | Completed | Samuel | None | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35147 | 25-01-2024 | 25-01-2024 | Ashwin | None | NA | NA | NA | NA | NA | Closed
2 | 13.5 M Sprint 3 | Gokul | D-22730 | 22730 MSBP - iOS/Android - upon deleting an echeck it states a credit card has been removed | 1 | 0.5 | Completed | Samuel | None | Sambath | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35148 | 25-01-2024 | 25-01-2024 | Ashwin | None | NA | NA | NA | NA |  | Closed
3 | 13.5 M Sprint 3 Stretch | Gokul | S-42131 | 42131 MSBA - Maui - Products | 3 | 3.5 | In progress | [14 empty] | Inprogress | Development is carried to next sprint as regression defects with higher priority needs to be picked first
4 | 13.5 M Sprint 3 Stretch | Sambath | 43394 | [STRETCH] 43394 - MSBP - Auto Detect Students - Prompt Parent to Add Student | 3 | 5.1 | [15 empty] | Inprogress | this story scope is entirely changed at mid of the sprint so this story holded for regression defect and also put some effort for R&D
5 | 13.5 M Sprint 3 Stretch | Ashwin | 43432 | MSBP - Currency Symbol - Keep US $ for All Language/Region Settings | 2 | 2 | Completed | Samuel | None | Sambath | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35182 | 26-01-2024 | 26-01-2024 | Avery | None | NA | NA | NA | NA | None | Closed
6 | 13.5 M Sprint 3 | Gokul | D-22696 | 22696 MSBA - iOS/Android - Webform options do not show properly (13.5) | 3 | 4.5 | Completed | Samuel | - Security question looping is not working in Missing phone number page | Sambath | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/35271 | 2024-01-02 | 2024-01-02 | Ashwin | None | NA | NA | NA | NA | Radio button text on Android also appears to be a lighter grey than the rest of the options on the screen which are black - Letashia James1/25/2024 9:18 AM(This is being fixed on part of defect 22757) the words for the radio buttons are smaller than the rest of the words on the screen. It appears the rest of the page is set to 3mm, but Radio button options are showing as 2mm. Letashia James1/26/2024 9:17 AM In iOS the multi-select is a different color/size from radio button and multicheck, in Android- radio button is a different color than the multi check Letashia James1/30/2024 10:57 AM | Closed | Radio button text smaller size issue is reproduced in tab and working on it. Completed bouncebacks on 01-02-2024
7 | 13.5 M Sprint 3 | Samuel | S43424 | MSBP - Update, Run, Check & Fix Any Automation Failures | 5 | 5 | Completed | Samuel | None | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35298 | 2024-05-02 | 2024-05-02 | Ashwin | None | NA | NA | NA | NA | NA | Closed | AppCentre log analysis, execution and fixing failures (13.5) Newly added 2 UI automation elements and automation steps for validating the Discloure label in Checkout and Payment Method drawer
8 | 13.5 M Sprint 3 | Samuel | S43425 | MSBA - Update, Run, Check & Fix Any Automation Failures | 5 | 6 | Completed | Samuel | None | Ashwin | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/35257 | 31-01-2024 | 31-01-2024 | Ashwin | None | NA | NA | NA | NA | NA | Closed | AppCentre log analysis, execution and fixing failures (13.5) Newly added 12 UI automation elements and automation steps for Add and Delete shift users
9 | 13.5 M Sprint 3 | Sambath | D-22778 | 22778 MSBP - Android - Adding your student(s) is super useful box closing (regression) |  | 2 | NA | [14 empty] | Inprogress | Regression story. Story point haven't estimated.
10 | 13.5 M Sprint 3 | Gokul | D-22784 | 22784 MSBP - Android - Cannot access "My Scheduled Payments" after invoice checkout (regression) |  | 2 | NA | Samuel | None | [12 empty] | Inprogress | Regression story. Story point haven't estimated.

## 13.5 M Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 13.5 M Sprint 3 | D-22662 | Sambath | Bounceback | 22662 MSBP - Webforms being cut off | Significant | External | Closed | Existing_Issues
2 | 13.5 M Sprint 3 | D-22696 | Gokul | Defect | 22696 MSBA - iOS/Android - Webform options do not show properly (13.5) | Significant | External | Closed | Existing_Issues
3 | 13.5 M Sprint 3 | 22757 | Ashwin | Defect | MSBA - iOS/Android - Webform formatting issues (13.5) | Significant | External | Closed | Existing_Issues
4 | 13.5 M Sprint 3 | 22783 | Ashwin | Defect | MSBP - iOS/Android - forgot login info no code being sent(regression) | Significant | External | Inprogress | Environment_Related | Blocked as fix needed from DS team
5 | 13.5 M Sprint 3 | 22776 | Ashwin | Defect | MSBA - iOS/Android - incorrect grammar on error message on shift (regression) | Significant | External | Closed | Existing_Issues

## 13.5 M Sprint 2 - CRC
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Defects, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 13.5 M Sprint 2 | Sambath | S-42764 | 42764 MSBA - iOS/Android - Close Out - shift details page does not always refresh properly (13.5) | 1 | 1 | Completed | Samuel |  | Gokul | None |  |  |  | Ashwin | None | NA | NA | NA |  |  | Closed
2 | 13.5 M Sprint 2 | Samuel | S-43241 | MSBP - Update, Run, Check & Fix Any Automation Failures | 5 | 5 | NA | Samuel |  | Samuel |  | 35087, 35139 | 18-01-2024 |  | Ashwin | None | NA | NA | NA |  |  | Closed
3 | 13.5 M Sprint 2 | Samuel | S-43266 | MSBA - Update, Run, Check & Fix Any Automation Failures | 5 | 5 | NA | Samuel |  | Samuel |  |  |  |  | Ashwin | None | NA | NA | NA |  |  | Closed
4 | 13.5 M Sprint 2 | Gokul | D-21874 | 21874 MSBP- iOS/Android- Display issue on checkout | 3 | 4 | Completed | Samuel | None | Sambath | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/34993 | 16-01-2024 | 16-01-2024 | Ashwin | None | NA | NA | NA | NA | No comments | Closed
5 | 13.5 M Sprint 2 | Sambath | D-22662 | 22662 MSBP - Webforms being cut off | 2 | 2 | Completed | Samuel |  | Sean | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/35050?_a=files | 18-01-2024 | 18-01-2024 | Ashwin | None | NA | NA | NA | NA | No comments | Closed
6 | 13.5 M Sprint 2 | Ashwin | 42558 | MSBP - Add translations Vietnamese and Arabic 13.5 | 5 | 5 | Completed | Samuel | Issues and fixes are mentioned in the link given below: https://docs. google.com/spreadsheets/ d/12NR4ZVIcfqoKtiBE5We45H3e3bowK38qtiGczZz_TEQ/ | Sean |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/34972 | 2024-12-01 | 2024-12-01 | Sean | None | NA | NA | NA | NA |  | Closed
7 | 13.5 M Sprint 2 | Sambath | S-42973 | 42973 MSBP - Updated Disclosure in Checkout (13.5) | 2 | 2.5 | Completed | Samuel | When logged in as a user who has not payed the supplemental fees you run into the following issues: 1. Security box is small/ not visible at all for cards which have not entered the cvv in the past 2.After adding a new payment method (3 on screen in my example), selecting a payment method that has supplemental fees(but seemingly not the security code), the pay now button is pushed below the bottom of the screen | [5 empty] | Avery | None
8 | 13.5 M Sprint 2 Stretch | Gokul | D-22696 | 22696 MSBA - iOS/Android - Webform options do not show properly | 3 | 2 | Completed | Samuel | None | Sambath | None | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/35123 https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/35177 | 25-01-2024 | 25-01-2024 | Ashwin | None |  |  |  | NA | 3 new issues were introduced when radio and list issue was updated: 1.in iOS an Android phone no longer has ( ) - showing, and when selecting the box, no entry can be made and app crashes (no crash log showing) 2. iOS only- text area and date field are showing as bolded when they did not previously (This does not follow the HTML formatting which is bolded within the webform setup) 3. Android only- date is light grey like it is a watermark after selection - Letashia James 1/25/2024 7:48 AM | Inprogress | Development, internal review & testing completed. Yet to be merged and tested by QA. Checked the mentioned issues and here are the respective findings: 1. Phone field issue is reproduced - worked on it. 2. Checked on IOS version 13.5.0.120674 and the mentioned issues are present there 3. Checked on Android version 13.5.0.120449 and the mentioned issue is present there Hence 2 & 3 are existing issues - Gokul 1/25/2024 9:00 PM Development carried to next sprint as bounceback reported on EOD of sprint end
9 | 13.5 M Sprint 2 Stretch | Gokul | D-22730 | 22730 MSBP - iOS/Android - upon deleting an echeck it states a credit card has been removed | 1 | 0.5 | Completed | Samuel | None | [5 empty] | Ashwin | None | NA | NA | NA | NA | None | Inprogress | Development carried to next sprint because picked this defect and started working on the last day of the sprint.
10 | 13.5 M Sprint 2 Stretch | Gokul | S-42131 | 42131 MSBA - Maui - Products | 3 | 2 | In progress | [14 empty] | Inprogress | Development is carried to next sprint as defects with higher priority needs to be picked first

## 13.5 M Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 13.5 M Sprint 2 | D-22662 | Sambath | Defect | 22662 MSBP - Webforms being cut off | Significant | External | Inprogress | Existing_Issues
2 | 13.5 M Sprint 2 | S-42973 | Sambath | None | 42973 MSBP - Updated Disclosure in Checkout (13.5) | Significant | External | Inprogress | Enhancements
3 | 13.5 M Sprint 2 | D-22730 | Gokul | Defect | 22730 MSBP - iOS/Android - upon deleting an echeck it states a credit card has been removed | Significant | External | Inprogress | Existing_Issues

## Checklist (hidden)
Code Review Comments received from Client for 2.5 Sprint |  | S No | Execution Steps | Status
1 | index.tsx /AugustWeb/Features/ContactMaintenance/Components/index.tsx Search doesn't work on the details page. Please remove the search component from the header. | 1 | Code conflict | FALSE
2 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs If the admin doesn't set up any of the new options, then the system rejects every registration. | 2 | Coding Standard | FALSE
3 | PickEnrollmentPlanView.tsx /ParentWeb/ClientApp/src/pages/Registration/PickEnrollmentPlanView.tsx This should be filtered before this ternary statement so the "No enrollment plans" message could be shown if all plans are at capacity and closed. | 3 | Existing Functionality | FALSE
4 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs Could we add a TermEnrollmentPlanId query parameter and query for it directly instead of pulling all the plans for the term? | 4 | Acceptance Criteria coverage | FALSE
|  | 5 | Code execute | FALSE
|  | 6 | Code Performance | FALSE
|  | 7 | Code cleanup | FALSE
|  | 8 | Understandable code comments | FALSE

## Details
Root Cause category
Enhancements
Existing_Issues
Requirements
QA
Design
Documentation
Development
Project_Management
Environment_Related

## Settings
Story Completed
Story Being Tested
Story Ready For Testing
Story Peer Review
Product Owner - Verify
Story Being Developed
Story Approved
Defect Found
Defect Verified
Defect Being Fixed
Defect Peer Review
Product Owner - Verify
Defect Ready For Testing
Defect Being Tested
Defect Fixed
Defect Rejected
Defect Needs More Info
Defect Blocked
Story Needs More Info
Story Blocked
Story Requested

## ExportData
1 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 2 | Vaishnavi | 44559 | MSBP - Maui - Payment history | Closed | 2 | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed
2 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 2 | Sambath | 44581 | MSBP - Maui - Invoices - Invoice Payment options screens | Closed | 3 | 3 |  | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40237?_a=files | 45665 | 45665 | Sean | Repalced wtih Vertical and HorizotalLayout instead of StackLayout | NA | NA | NA | NA | NA
3 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 2 | Gokul | 46294 | MSBP - Maui - Meal Money Notification Settings | Closed | 2 | 2 |  | Done | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 2 | Gokul | 44563 | MSBP - Maui - Request balance transfer - Bounceback Issues fix | Closed | 2 | 2 |  | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40141 | 45649 | 45649 | Ashwin | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 2 | Ashwin | 46774 | MSBP - GL - Text Update Carousel - Update Price in Text | Closed | 1 | 1 |  | Done | NA | NA | Client | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ParentApp/pullrequest/40095 | 45643 | 45643 | Sean | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 2 Stretch | Gokul | 44560 | MSBP - Maui - Scheduled Payments | Closed | 5 | 6 |  | Done | NA | NA | Ashwin | Remove commented and unused code | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40167 | 45663 | 45663 | Sean | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 2 Stretch | Sambath | 44571 | MSBP - Maui - AutoPay Settings screen / Meals Auto Pay | Inprogress | 5 | 5 |  | NA | NA | NA | Ashwin |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/39236 | 45666 | 45666 | Sean | Replaced wtih Vertical and HorizotalLayout instead of StackLayout | [5 empty] | Development completed, Testing is Inporgress.
8 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 2 Stretch | Ashwin | 44570 | MSBP - Maui - AutoPay drawer activated via Meals card | Inprogress | 3 | 3 |  | Done | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40208 | 45663 | 45663 | Sean | Replace stacklayout with horizontal/vertical | NA | NA | NA | NA | NA
1 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 3 | Vaishnavi | 46877 | REG - MSBP - 14.4 Regression | Story Completed | 5 | 5 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 3 | Vaishnavi | 46880 | MSBP / MSBA - Automation - Update, Run, Check & Fix Any Automation Failures | Story Completed | 5 | 5 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 3 | Ashwin | 46768 | MSBP - Profile - Do Not Save Phone When Already In Use | Story Completed | 2 | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 3 Stretch | Ashwin | 46406 | MSBP - MAUI - Checkout (Dev Only) | Story Being Developed | 5 | 4.5 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Dev in Progress
5 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 3 Stretch | Gokul | 44575 | MSBP - Maui - GL Sign Up | Story Being Developed | 3 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Edit GL account page header image to be centered. | Development completed and POV has been shown. But when merging to latest lot of conflict occured and after merging there is lot of reference issue & build issues. Working in progress.(Issues caused by changes implemented for Firebase analytics).
6 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 3 Stretch | Sambath | 46893 | 46893 MSBP - Maui - Shopping Cart Screen - .NET9 Fixes (Dev Only) | Story Peer Review | 3 |  |  | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40455?_a=files | 45680 | 45680 | NA | NA | NA | NA | NA | NA | NA | Dev completed
7 | MSB Mobile | 46059 | 46072 | 14.4 M Sprint 3 Stretch | Vaishnavi | 44570 | MSBP - Maui - AutoPay drawer activated via Meals card | Story Completed | 1 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile | 45681 | 45694 | 14.5 M Sprint 1 | Sambath | 44571 | 44571 MSBP - Maui - AutoPay Settings screen / Meals Auto Pay | Story Completed | 2 | 2 | 13 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40520?_a=files | 45685 | 45685 | NA | NA | NA | NA | NA | NA | NA | Bounce back issue is got fixed
2 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 1 | Ashwin | 46406 | MSBP - MAUI - Checkout (Dev Only) | Story Completed | 3 | 3 | 39 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40596 | 45688 | 45691 | Client | 1.We should split these up into their respective classes at some point e.g. StudentExtension 2.Null check all the things, BasketPreview 3.Do we need to carry this around on the AppSession? | NA | NA | NA | NA | NA | Had to work on additional functionalities like building the data for receipts and supplemental fees. Also had local environment and firbase nuget package restore issues which consumed lot of effort.
3 | MSB Mobile | 45681 | 45694 | 14.5 M Sprint 1 | Vaishnavi | 46879 | MSBP - Smoke Test Prod apps against MSB 14.4 RC in Staging | Story Completed | 1 | 1 | 3.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 45681 | 45694 | 14.5 M Sprint 1 | Vaishnavi | 44555 | MSBP - Maui - Suggested students drawer (New suggested students detected) | Story Completed | 2 | 2 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45681 | 45694 | 14.5 M Sprint 1 | Vaishnavi | 44556 | MSBP - Maui - Student Drawer | Story Completed | 2 | 2 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45681 | 45694 | 14.5 M Sprint 1 | Vaishnavi | 44567 | MSBP - Maui - Edit image on home screen | Story Completed | 2 | 2 | 6.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 1 Stretch | Gokul | 44575 | MSBP - Maui - GL Sign Up | Story Being Developed | 2 | 2 |  | NA | NA | NA | Sambath | Remove commented code in Homepage | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40476 | 45681 | NA | NA | NA | NA | NA | NA | NA | NA | Working on the bouncebacks.
8 | MSB Mobile | 45681 | 45694 | 14.5 M Sprint 1 Stretch | Gokul | 46346 | MSBP - Maui - GL Landing Screen | Story Completed | 5 | 5 | 32 | NA | NA | NA | Ashwin | Add Null check GreenlightStudentBalances | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40592 | 45688 | 45692 | Sean | - Use the ValueCompletionSource - Use the return type of the sheet instead of using a message - Use RadCollectionView instead of RadListView - Remove ContentView | NA | NA |  |  |  | Worked on Code review comments after PR is created.
9 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 1 Stretch | Gokul | 44575 | [FAMILYPASS] MSBP - MAUI - FamilyPass | Story Being Developed | 8 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 1 Stretch | Sambath | 44583 | 44583 MSBP - Maui - Payment Success (Receipt) | Story Being Developed | 5 | 5 | 22 | NA | NA | NA | [12 empty] | Most of dev has been completed, and currently fixing the UI issues
11 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 1 Stretch | Ashwin | 45879 | MSBP - MAUI - Supplemental Fee(Dev Only) | Story Completed | 3 | 3 | 10 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40596 | 45693 | 45694 | Client | NA | NA | NA | NA | NA | NA | Dev completed and
12 | MSB Mobile | 45681 | 45694 | 14.5 M Sprint 1 Stretch | Vaishnavi | 46407 | MSBP - MAUI - Checkout - TEST | Story Ready For Testing | 3 | 1 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Test Cases modified based on the review comments.
13 | MSB Mobile | 45681 | 45694 | 14.5 M Sprint 1 Stretch | Vaishnavi | 46596 | MSBP - Maui - Test Languages | Story Being Tested | 2 | 0.75 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 | Sambath | 44583 | 44583 MSBP - Maui - Payment Success (Receipt) | Story Being Developed | 5 | 18 | 18 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40701?_a=files | 45702 | 45702 | Ashwin | commented code removed | NA | NA | NA | NA | NA | story is get carried due to crash issues and testing feedback Tried to fix the calendar event issue in android. but it is not working. so i reverted back Working on Bounce backs Products with add on fees cause app to crash iOS- missing thumbs up icon on receipt Android- missing school indication under student name for meal money should be additional space between thank you and order # crash when there is a broken gateway instead of directing to receipt page with error message crash when there are certain items in cart (at one District No Amex is causing crash as well as ApprovalDonation)
2 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 | Vaishnavi/Ashwin | 46407 | MSBP - MAUI - Checkout - TEST | Story Completed | 3 | 6 | 29 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40714 | 45700 | 45700 | Client |  | NA | NA | NA | NA | NA | Bounce backs added
3 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 | Gokul | 44575 | MSBP - Maui - GL Sign Up | Story Completed | 2 | 1 | 6 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40699?_a=files | 45695 | 45695 | Ashwin | Add missing resource values | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 | Gokul | 45093 | [FAMILYPASS] MSBP - MAUI - FamilyPass | Story Completed | 8 | 7 | 39 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40777 https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40863 | 45702 | 45702 | Ashwin | NA | NA | NA | NA | NA | NA | Bouncebacks added
5 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 | Ashwin | 46331 | MSBP - Maui - Shopping Cart screen | Story Completed | 3 | 3 | 17 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40775 | 45701 |  |  |  | NA | NA | NA | NA | NA
6 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Vaishnavi | 47177 | MSBP - MAUI - Test Current 'Needs Testing' ITEMS to Verify Fixes | Story Completed | 3 | 5 | 5.2
7 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Vaishnavi | 47155 | MSBP - Supplemental Fee(TEST) | Story Being Developed | 2 | 2 | 13 | [15 empty] | The PI team is working on Defect 24598 MSBP - API - Supplemental Fee not applied in basket. It seems like the change they are making will need a code change in the mobile app. So testing for this story will have to be put on hold.
8 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Sambath | 24694 | 24694 MSBP - Maui - Delete Account on profile screen not centered within white box | Story Completed | 1 | 4 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40792 | 45705 | 45705 | Sean Jacquelin | NA | NA | NA | NA | NA | NA
9 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Sambath | 24661 | 24661 MSBP - MAUI - Android - Cart Icon Badge is offset | Defect Fixed | 1 | 4 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40826 | 45706 | 45706 | Sean Jacquelin | NA | NA | NA | NA | NA | NA | Defect has been tested by Client after the sprint meeting and closed it.
10 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Sambath | 24706 | 24706 MSBP - Maui - Cart reorder when donation is added on multidistrict (pre-existing) | Defect Being Fixed | 2 |  | 5
11 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Sambath | 24707 | 24707 MSBP - MAUI - iOS - Navigation icons disappear after navigating back to home screen | Defect Being Fixed | 2 | 4 | 5
12 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Vaishnavi | 46596 | MSBP - Maui - Test Languages | Defect Fixed | 2 | 2 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Gokul | 24705 | MSBP - Maui - Hamburger menu in different styles within tabs | Defect Fixed | 1 | 1 | 3 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40849 | 45707 | 45707 | Ashwin | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Gokul | 24640 | MSBP - MAUI - Add Meal Money - Other Amount - Disappears | Defect Fixed | 0.5 | 1 | 6 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40811 | 45706 | 45706 | Ashwin | NA | NA | NA | NA | NA |  | Defect has been tested by Client after the sprint meeting and closed it.
15 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Gokul | 24709 | MSBP - MAUI - iOS - Meal money preset amounts > 8 or having more than 2 rows not scrollable | Defect Fixed | 0.5 | 0.5 | 3 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40838 | 45707 | 45707 | Ashwin | NA | NA | NA | NA | NA | NA | Defect has been tested by Client after the sprint meeting and closed it.
16 | MSB Mobile | 45695 | 45708 | 14.5 M Sprint 2 Stretch | Gokul | 24654 | MSBP-Maui- Quicklinks_Bluebar is not showing under the corresponding page | Defect Fixed | 0.5 | 0.5 | 3 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40869 | 45708 | 45708 | Ashwin | NA | NA | NA | NA | NA | NA | Defect has been tested by Client after the sprint meeting and closed it.
1 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 | Sambath | 44583 | 44583 MSBP - Maui - Payment Success (Receipt) | Story Completed | 3 | 4 | 17 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40918 | 45712 | 45712 | Ashwin | NA | NA | NA | NA | NA | NA | Bounce back issue fixed
2 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 | Sambath | 24707 | 24707 MSBP - MAUI - iOS - Navigation icons disappear after navigating back to home screen | Defect Fixed | 1 | 1 | 6 | [15 empty] | Not able to reproduce on latest build so we are closing this defect
3 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 | Vaishnavi | 47075 | MSBP - MAUI - Login As Support | Story Completed | 2 | 2 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 | Gokul | 24660 | MSBP - MAUI - MFA Sizing Changes | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40891 | 45709 | 45709 | Ashwin | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 | Vaishnavi | 47155 | MSBP - Supplemental Fee(TEST) | Story Completed | 3 | 3 | 14 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40898 | 45709 |  | Client | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 | Vaishnavi | 47316 | REG - MSBP - 14.5 Regression | Story Completed | 5 | 5 | 19 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 | Vaishnavi | 47321 | MSBP / MSBA - Automation - Manual Run of Automation Tests | Story Completed | 3 | 3 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 | Gokul | 24638 | MSBP - MAUI - 3rd Party Login - Homepage Not Loading | Defect Fixed | 3 | 2.5 | 14 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40972 | 45715 | 45715 | Ashwin | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Sambath | 47306 | 47306 MSBP - Maui - Profile - Delete Account to Delete MySchoolBucks Account | Story Completed | 1 | 1 | 2 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40936 | 45713 |  | Ashwin | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 Stretch | Ashwin | 24721 | MSBP - MAUI - iOS - purchase controls not showing on add student | Defect Fixed | 1 | 1 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40962 | 45713 |  | Client | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 Stretch | Sambath | 24750 | 24750 MSBP - MAUI - Android - On first install do not get donations if only product in cart | Defect Fixed | 1 | 1 | 4 | [5 empty] | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40980 | 45714 | 45714 | Ashwin | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Sambath | 24755 | 24755 MSBP - MAUI - Payment history taking 9-12 seconds to open menu | Defect Fixed | 1 | 1 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40994 | 45715 | 45715 | Ashwin | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Gokul | 24754 | MSBP - MAUI - when selecting back on security question answer in profile, getting an error | Defect Fixed | 1 | 1 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41001?_a=files | 45715 | 45715 | Ashwin | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Ashwin | 24761 | MSBP - MAUI - iOS - Store page missing "no image" icon | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/40994 | 45715 | 45715 | Ashwin | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Gokul | 24774 | MSBP - MAUI - iOS - Navigation bar icons are a different color when on the invoices tab | Defect Fixed | 2 | 2 | 13 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41066?_a=files | 45720 | 45720 | Ashwin | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Gokul | 24770 | MSBP - MAUI - Profile Security question 1 edit not saving the answer | Defect Fixed | 2 | 1 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41028 | 45716 | 45716 | Ashwin | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Sambath | 24791 | 24791 MAUI - Allows to Enter the Threshold Amount in Meal Money Settings Page Instead Input modal page | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41101?_a=files | 45721 | 45721 | Ashwin | NS | NA | NA | NA | NA | NA
16 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Gokul | 24797 | MSBP - MAUI - Edit payment method not working as expected | Defect Being Tested | 0.5 | 1 | 7 | NA | NA | NA | NA | NA |  | 45721 | 45721 | Ashwin | NS | NA | NA | NA | NA | NA
17 | MSB Mobile | 45709 | 45722 | 14.5 M Sprint 3 Stretch | Sambath | 24797 | 24796 MSBP - MAUI - iOS - meal money autopay other box is cut off on right side of screen | Defect Peer Review | 2 | 1 | 4 | NA | NA | NA | NA | NA |  | 45722 | 45722 | Ashwin | NS | NA | NA | NA | NA | NA
18 | MSB Mobile | 46059 | 46072 | 14.5 M Sprint 3 Stretch | Ashwin | 24780 | Back button on the input model is saving the amount on Invoice Partial payment field | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41059 | 45719 | 45719 | Client | NA | NA | NA | NA | NA | NA
1 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Vaishnavi | 24797 | MSBP - MAUI - Edit payment method not working as expected | Defect Fixed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Vaishnavi | 24792 | MSBP - MAUI - Value Add Student appearing when after all students are deleted from household | Defect Fixed | 1 | 0.38 | 1.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Gokul/Vaishnavi | 24799 | MSBP - MAUI - Android - cursor does not default to end on boxes with amounts in them by default | Defect Fixed | 1 | 3.75 | 15 | Done | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41166?path=/MSB.Parent/Resources/StyleControls/Entry.xaml.cs | 45726 | 45726 | Ashwin | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24796 | MSBP - MAUI - iOS - meal money autopay other box is cut off on right side of screen | Defect Fixed | 2 | 1 | 3 | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41134 | 45723 | 45723 | Ashwin | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24798 | 24798 MSBP - MAUI - Adding payment method at checkout closes tray | Defect Fixed | 3 | 3 | 11 | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41168 | 45727 | 45727 | Ashwin | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Gokul | 24810 | MSBP - MAUI - Android - Login not load all icons in navigation (regression) | Defect Needs More Info |  |  |  | NA | NA | NA | NA | NA | NA |  |  | NA | NA | NA | NA | NA | NA | NA | Attempted to reproduce the defect several times in the local environment(both device and simulator), but it occurred very rarely. Even though the icons were partially loaded first, it then took few more seconds for the remaining icons to get loaded. Unfortunately, couldn’t capture it in the local development environment, so the issue couldn’t be fixed.
7 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Gokul | 24816 | MSBP - MAUI - Greenlight carousel shows "payment method" when no echeck available (regression) | Defect Fixed |  |  |  | NA | NA | NA | Sambath | NA |  |  |  |  | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Vaishnavi | 24644 | MSBP - Maui - Drawer issues | Defect Fixed | 3 | 1.5 | 6
9 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24815 | 24815 MSBP - MAUI - GL share info drawer closing after edit information (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41222 | 45729 | 45729 | Ashwin | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Ashwin/Vaishnavi | 47477 | MSBP - MAUI Only - Show Declined Payment Methods on Payment Method Screen 14.5 | Story Completed | 3 | 0.25 | 1 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41214 | 45728 | 45729 | Client |  | NA | NA | NA | NA | NA
11 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Team | 47488 | REG - MSBP - 14.5 MAUI Regression | Story Completed | 13 | 42.5 | 170 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | All Defects Time were logged here. Client conveyed the Team to log all the work log in this story.
12 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Gokul | 24821 | MSBP - MAUI - quicklink to product very slow to load(regression) | Defect Fixed |  |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24824 | 24824 MSBP - MAUI - Bottom sheet closes on editing information Family Pass profile change payment method (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41226 | 45730 | 45730 | Ashwin | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24823 | 24823 MSBP - MAUI - Bottom sheet closes on editing information AutoPay screen (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41225 | 45729 | 45729 | Ashwin | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24826 | 24826 MSBP - MAUI - Bottom sheet closes on editing information Family Pass sign up change payment method (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41232 | 45730 | 45730 | Ashwin | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Gokul | 24822 | MSBP - MAUI - iOS - when minimizing product groups there are item names stacking (regression) | Defect Blocked |  |  |  | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Defect is blocked because of the Collection view issue in iOS related to expand / collapse grouping. Adding links to few of the open issues: https://github.com/dotnet/maui/issues/21271 https://github.com/dotnet/maui/issues/23033 https://github.com/dotnet/maui/issues/19186
17 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24836 | 24836 MSBP - MAUI -Family Pass User_Newly added payment method is not auto-checked in payment method drawers | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41257 | 45733 | 45733 | NA | NA | NA | NA | NA | NA | NA
18 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Gokul | 24835 | MSBP - MAUI - When product sections are minimized, refreshing opens them again (regression) | Defect Being Fixed |  |  |  | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA |  | Changing from Telerik collectionview control to MAUI native collectionview control to fix the issue related to controls. Since native MAUI control is lacking features of Telerik collectionview control, need to implement them manually. Hence the development is carried to next sprint.
19 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24862 | 24862 MSBP - MAUI - Basket page Swipe Delete icon is not aligned in center (regression) | Defect Fixed |  |  |  | NA | NA | NA | Gokul | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41305 | 45735 | 45735 | NA | NA | NA | NA | NA | NA | NA
20 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Sambath | 24877 | MSBP - MAUI - Android - if tap filters in store 2x in succession, filters and up arrow no longer responsive (regression) | Defect Being Fixed | [18 empty] | Still in Progress. All the Defects found were logged directly to Commit
21 | MSB Mobile | 45723 | 45740 | 14.6 M Sprint 1 | Ashwin | 24891 | 24891 MSBP - MAUI - Prior purchase is removed when the student is changed in product details (regression) | Defect Fixed |  |  |  | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41352 | 45733 | 45734 | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile | 45741 | 45750 | 14.6 M Sprint 2 | Vaishnavi | 47622 | REG - MSBP - 14.5 MAUI Regression (Formal Regression) | Story Completed | 13 | 9 | 36.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | The actual story point is 9sp as this estimated SP includes the worklog of client QA and Dev also
2 | MSB Mobile | 45741 | 45750 | 14.6 M Sprint 2 | Vaishnavi | 47679 | MSBP - MAUI - Hide Chat button | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 45741 | 45750 | 14.6 M Sprint 2 | Ashwin | 47222 | MSBA - XAM - Tickets Box Office - Android - Support for Camera In Web Browser 14.6 | Story Completed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Reserach Story. TimeBoxed
4 | MSB Mobile | 45741 | 45750 | 14.6 M Sprint 2 | Mohamed | 24917 | MSBP - MAUI - iOS - information cut off in ? sheet for scheduled payments (regression) | Defect Ready For Testing | 0 | 0 | 0 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41567 | 45750 | 45750 | Client | NA | NA | 45750 | NA | NA | NA | Development completed and PR created at the last date of sprint. Carried to the Sprint 3. Testing will be done in spirnt 3
5 | MSB Mobile | 45741 | 45750 | 14.6 M Sprint 2 | Ashwin/Vaishnavi | 24920 | MSBP - MAUI - Request balance transfer opens a Blank drawer when 'To Account' is selected | Defect Fixed | 0 | 0 | 0 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41547 | 45749 | 45749 | Client | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45741 | 45750 | 14.6 M Sprint 2 Stretch | Ashwin/Vaishnavi | 47763 | MSBA - Tickets Box Office - Android - Support for Camera in Web Browser | Story Completed | 5 | 5 | 20 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/41521 | 45747 | 45747 | Client | NA | NA | NA | NA | NA | NA | Story closed as it works as expected in Android
1 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 | Vaishnavi | 47806 | REG - MSBP - 14.4 (Xam) Regression | Story Completed | 5 | 4.5 | 18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing completed.
2 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Ashwin/vaishnavi | 47705 | MSBA - XAM - Show Product Name on Receipt - Synergy | Story Completed | 3 | 5.25 | 21 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSB.ANxt/pullrequest/41708 | 45761 | 45761 | Client | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Ashwin/Vaishnavi | 24984 | MSBP - MAUI - Android - Student Add Meal Money - Other Amount -Sheet Closes | Defect Fixed | 2 | 2 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Ashwin/vaishnavi | 24983 | MSBP - MAUI - Android - when selecting payment method for the first time, drawer closes | Defect Fixed | 2 | 3.25 | 13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Mohammed / Vaishnavi | 38007 | 38007 MSBP - Maui - Store Landing Page - Hook up to API for School Logos | Story Completed | 2 | 4.75 | 19 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41674 | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24795 | MSBA - XAM - Close Out - Check Reconciliation Stacking | Defect Fixed | 2 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24917 | MSBP - MAUI - iOS - information cut off in ? sheet for scheduled payments (regression) | Defect Fixed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24931 | MSBP - MAUI - when opening student card and closing sheet, empty warning appears (regression) | Defect Fixed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24937 | MSBP - MAUI - Notification bell icon and cart icon are not aligned properly in iOS(regression) | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24946 | MSBP - MAUI - app crash on using saved biometrics (regression) | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24972 | MSBP - MAUI - Clicking off of admin pin sheet without typing anything shows an Incorrect Pin error | Defect Fixed | 0.5 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24973 | MSBP - MAUI - Auto Pay text not centered on student meal money card | Defect Fixed | 1 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi/Ashwin | 24974 | MSBP - MAUI - Android -TOS at bottom of Meal Money AutoPay page is close to button | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Mohammed / Vaishnavi | 24976 | MSBP - MAUI - Android - Disclaimer in the payment methods does not have any margin at the edge of the screen | Defect Fixed | 1 | 1.75 | 7 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41696 | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24978 | MSBP - MAUI - when editing phone number from profile, presented with 'lets add' screen momentarily | Defect Fixed | 1 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Mohammed / Vaishnavi | 25010 | MSBP - MAUI - Total = Resource Not Found in Payment Summary | Defect Fixed | 2 | 2 | 8 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41706 | NA | NA | NA | NA | NA | NA | NA | NA | NA
17 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Vaishnavi | 24975 | MSBP - MAUI - Checkout payment methods adds a white space after selecting payment method | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
18 | MSB Mobile | 45751 | 45764 | 14.6 M Sprint 3 Stretch | Mohammed | 47675 | MSBP - Password History - Prevent using last 4 passwords | Story Being Developed | 2 | 2 | 10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Story Blocked as we are waiting for PI to complete the story
1 | MSB Mobile | 45765 | 45778 | 14.7 M Sprint 1 | Vaishnavi | 47809 | MSBP CA - Regression/Smoke Test 14.4 (Xam) against MSB RC in Staging | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 45765 | 45778 | 14.7 M Sprint 1 | Mohammed | 25040 | MSBP - MAUI - Android - When selecting area in Payment Methods sheet, drawer closes | Defect Blocked | 2 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | This defect only occurred on Android. Have to change existing workflow to fix this issue in Android. So Jason needs to confirm, and then start work on this defect in future sprint.
3 | MSB Mobile | 45765 | 45778 | 14.7 M Sprint 1 Stretch | Sambath / Mohammed/Vaishnavi | 46199 | [FAMILYPASS] MSBP - Payment Options - Cross-Sell Pop Up | Story Being Tested | 13 | 13.75 | 55 | NA | NA | NA | Mohamad | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41966 | 45777 | 45777 | Ashwin | NA | NA | NA | NA | NA | NA | Development has been completed. Story is under peer review. will be carried to the next stprint.
4 | MSB Mobile | 45765 | 45778 | 14.7 M Sprint 1 Stretch | Mohammed/Vaishnavi | 47675 | MSBP - Password History - Prevent using last 4 passwords | Story Completed | 2 | 4 | 18.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41915 | 45775 | 45775 | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45765 | 45778 | 14.7 M Sprint 1 Stretch | Ashwin | 25051 | MSBP - MAUI - Android - when approving camera permissions not directed forward | Defect Fixed | 3 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41870 | 45770 | 45771 | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45765 | 45778 | 14.7 M Sprint 1 Stretch | Ashwin | 47517 | MSBP - AutoPay Screen - Show indication that AutoPay will not be processed due to Declined | Story Being Tested | 3 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41936 | 45775 | 45777 | NA | NA | NA | NA | NA | NA | NA | Development has been completed. Story moved to ready for testing. will be carried to the next stprint.
7 | MSB Mobile | 45765 | 45778 | 14.7 M Sprint 1 Stretch | Ashwin | 24775 | MSBP - Maui/Xamarin - Supplement fee not applied for new user while adding 1st Meal/Store product | Defect Ready For Testing | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41870 | 45770 | 45771 | NA | NA | NA | NA | NA | NA | NA | Development has been completed. Story moved to ready for testing. will be carried to the next stprint.
8 | MSB Mobile | 45765 | 45778 | 14.7 M Sprint 1 Stretch | Mohammed | 46964 | MSBP - Phone Edit - Only Allow Save and Verify if Changed | Story Ready For Testing | 2 | 2.5 | 10 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/41972 | 45777 | 45778 | NA | NA | NA | NA | NA | NA | NA | Development has been completed. Story moved to ready for testing. will be carried to the next stprint.
1 | MSB Mobile | 45779 | 45792 | 14.7 M Sprint 2 | Vaishnavi | 46199 | [FAMILYPASS] MSBP - Payment Options - Cross-Sell Pop Up | Story Completed | 3 | 5.75 | 23 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42064?_a=files | 45784 | 45784 | Ashwin | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 45779 | 45792 | 14.7 M Sprint 2 | Ashwin/Vaishnavi | 24775 | MSBP - Maui/Xamarin - Supplement fee not applied for new user while adding 1st Meal/Store product | Defect Fixed | 0.5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 45779 | 45792 | 14.7 M Sprint 2 | Mohammed | 46154 | MSBP - Tickets - Add Events Card to Home Screen | Story Completed | 8 | 8 | 32 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42086 | 45785 | 45786 | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 45779 | 45792 | 14.7 M Sprint 2 | Vaishnavi | 47517 | MSBP - AutoPay Screen - Show indication that AutoPay will not be processed due to Declined | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45779 | 45792 | 14.7 M Sprint 2 | Sambath/Vaishnavi | 47753 | [FAMILYPASS] MSBP - Payment Options - Hooray Screen- Cross-Sell Pop up | Story Completed | 3 | 4.5 | 18 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42095 | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45779 | 45792 | 14.7 M Sprint 2 | Sambath/Vaishnavi | 48247 | MSBP - FamilyPass - Auto select payment method | Story Completed | 3 | 4.25 | 17 | NA | NA | NA | Mohamad | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42107 | 45786 | 45786 | Ashwin | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 45779 | 45792 | 14.7 M Sprint 2 Stretch | Vaishnavi | 25036 | MSBP - Beta - 14.5 - Name bunched up in Add Meal Money | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 45779 | 45792 | 14.7 M Sprint 2 Stretch | Ashwin | 42146 | MSBA - Maui - Tickets | Story Being Developed | 8 | 9 | 36 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint. Development still in progress.
1 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 | Vaishnavi | 48363 | REG - MSBP - Regression | Story Approved | 5 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Not started due to beta release. Beta release was blocked due to a defect found while doing smoke test
2 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 | Vaishnavi | 48313 | MSB Mobile - Invalidate Session after Password Change 14.7 | Story Completed | 2 | 1.75 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 | Sambath/Vaishnavi | 25214 | MSBA - Tickets BoxOffice - IOS/Android - Payment Options are not presented to the user 14.7 | Defect Fixed | 3 | 6.75 | 27 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 | Ashwin | 48218 | MSBA - MAUI - Screens Not Yet Developed (timebox) | Story Completed | 2 | 2 | 2 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 | Vaishnavi | 25294 | MSBP - MAUI - iOS - Payment methods never resolves (Beta) | Defect Fixed | 0 | 0.5 | 2 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 | Vaishnavi | 25293 | MSBP - MAUI - Other field in meal money and auto pay not formatted correctly every time (regression) | Defect Fixed | 0 | 0.25 | 1 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 | Vaishnavi | 25284 | MSBP - MAUI - iOS - greenlight signup is too large for the screen (14.7) | Defect Fixed | 0 | 0.25 | 1 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 | Vaishnavi | 25292 | MSBP - MAUI - Android - Upon completing transaction and closing receipt, payment methods sheet is still open (regression) | Defect Fixed | 0 | 0.25 | 1 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 Stretch | Ashwin | 42146 | MSBA - Maui - Tickets | Story Ready For Testing | 2 | 2 | 12 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42386 | 45800 |  | Ashwin | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 Stretch | Mohamed | 46155 | MSBP - Tickets - Upcoming Events Screen | Story Ready For Testing | 8 | 7 | 28 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42330 | 45798 | 45800 | Sambath | NA | Ashwin | 45800 | NA | NA | NA
11 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 Stretch | Sambath | 25203 | 25203 MSBA - MAUI - Add to Cart - Delay updating cart items | Defect Blocked | 2 | 2 | 18 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Analysis showed the control was not performant. Going to write story to replace with Rad Collection View or MAUI Collection View instead of the Rad List control.
12 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 Stretch | Amrit/Premkumar | 25192 | MSBA - MAUI -Forgot login - store tabs showing at bottom of screen | Defect Being Tested | 1 | 0.5 | 2 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing in iOS blocked as the Maui builds are not opening in iOS devices.
13 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 Stretch | Rupesh/Premkumar | 25195 | MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Defect Being Tested | 2 | 0.75 | 3 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing in iOS blocked as the Maui builds are not opening in iOS devices.
14 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 Stretch | Gursewak | 25197 | MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | Defect Blocked | 1 | 0 | 0 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Blocked due to iOS crash issue in the latest build and Mac unavailability.
15 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 Stretch | Jagdeep | 25199 | MSBA - MAUI - Invoice Details - Payment options pop up - Alignment | Defect Being Fixed | 2 | 0 | 0 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | Tested on Android devices it is working fine. Need to test it on iOS devices but due to MAUI iOS build issue not able to test. Waiting for MAUI iOS build fix.
16 | MSB Mobile | 45793 | 45806 | 14.7 M Sprint 3 Stretch | Vaishnavi | 25246 | MSBP - MAUI - some headers do not match | Defect Fixed | 0 |  | 0.5 | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Vaishnavi | 48363 | REG - MSBP - Regression | Story Completed | 5 | 3 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Vaishnavi | 42146 | MSBA - Maui - Tickets | Story Being Tested | 2 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Currently this story is on hold. As we faced iOS build issues due to that unable to test in iOS. MSBP and MSBA regression testing were prioritized so this defect was on hold
3 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Vaishnavi | 48364 | REG - MSBA - Regression | Story Being Tested | 5 | 3.25 | 13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Due to pending test cases, carried to next sprint.
4 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Mohamed/Premkumar | 48217 | MSBA - MAUI - Shake for Logs added to MSBA | Story Completed | 3 | 1.75 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Premkumar | 25192 | MSBA - MAUI -Forgot login - store tabs showing at bottom of screen | Defect Fixed | 1 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Rupesh/Premkumar | 25195 | MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Defect Peer Review | 2 | 1.5 | 6 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42789 | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
7 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Sambath/Vaishnavi | 25314 | MSBP - Maui - Store products not showing the price in checkout screen. | Defect Fixed | 1 | 2 | 8 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42506 | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Premkumar | 25196 | MSBA - MAUI - Invoice Details - buttons enabled behind payment options | Defect Fixed | 1 | 2.25 | 9 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Gursewak/Premkumar | 25181 | MSBA - MAUI - Header not Formatted Correctly | Defect Fixed | 2 | 2.25 | 9 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42498 | 45753 | 45753 | Ashwin Majjela | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Jagdeep | 25183 | MSBA - MAUI - App not force logging out on time out | Defect Fixed | 2 | 3 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
11 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Gursewak/Premkumar | 25194 | MSBA - MAUI -product details - camera not rotating | Defect Fixed | 2 | 1.25 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Rupesh | 25198 | MSBA - MAUI - Invoice Details - Payment options pop up | Story Peer Review | 2 | 2.5 | 10 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42696 | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Amrit/Premkumar | 25191 | MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Defect Being Fixed | 3 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
14 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Rupesh/Premkumar | 25193 | MSBA - MAUI -settings - after first login when re-entering settings screen loading symbol stuck | Defect Fixed | 3 | 3 | 10 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42572 | 45722 | 45753 | Ashwin Majjela | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Sambath | 25329 | 25329 MSBP- Maui -Unable to add payment method from checkout payment method drawer in iOS (Beta) | Defect Fixed | 1 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42589 | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Sambath | 25351 | 25351 MSBP - MAUI - Android - keyboard does not automatically open for district selection on account creation (14.7/15.0) | Defect Fixed | 1 | 2.25 | 9 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42698 |  | NA | NA | NA | NA | NA | NA | NA | NA
17 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Sambath | 25359 | 25359 MSBP - MAUI - checkout not respecting promocode flag (15.0) | Defect Ready For Testing | 1 | 0.5 | 2 | [5 empty] | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42736?_a=files | [7 empty] | NA | NA | Carried to next sprint
18 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Amrit Pal | 48217 | MSBA - Shake for device logs | Defect Fixed | 1 | 1 | 21 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42657 | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Jagdeep | 25190 | MSBA - MAUI - Forgot login | Defect Fixed | 2 | 5.25 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
20 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Premkumar | 25188 | MSBA - MAUI - Android - product details - ability to select today's date | Defect Fixed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | [7 empty] | NA | NA
21 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 | Vaishnavi | 25332 | MSBP - Maui - District drop down not showing the district while searching (Beta) | Defect Fixed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
22 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Mohamed | 46155 | MSBP - Tickets - Upcoming Events Screen | Story Ready For Testing | 3 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
23 | MSB Mobile | 45779 | 45792 | 15.0 M Sprint 1 Stretch | Amrit Pal | 25201 | MSBA - MAUI - Add to Cart - Android - expand/collapse only works when you drag a list item first | Defect Being Fixed | 2 | 2 | 16 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Defecct solved on Android and Ios phone, but crash happening in IPAD. working on that dnt have ipad device
24 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Premkumar | 25200 | MSBA - MAUI - Close Out Carousel - Close Out - Not Scrollable in Android | Defect Fixed | 2 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
25 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Premkumar | 25373 | MSBA - MAUI - Android/iOS - Start shift is unresponsive in Android and crashing in iOS | Defect Fixed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
26 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Vaishnavi | 48626 | REG - MSBA - Prod Smoke Test Against Staging RC | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
27 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Vaishnavi | 48627 | REG - MSBP CA - Prod Smoke Test Against Staging RC | Story Completed | 1 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
28 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Gursewak | 25380 | MSBA - MAUI - Unable to login after logout | Defect Being Fixed | 1 | 7.5 | 30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
29 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Premkumar | 25189 | 25189 MSBA - MAUI - IOS - forgot login - image background not scaling/tiling properly | Defect Fixed | 1 | 3 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42589 | NA | NA | NA | NA | NA | NA | NA | NA | NA
30 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Sambath | 46156 | 46156 MSBP - Tickets - Event Details | Story Being Developed | 8 | 3.75 | 15 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to next sprint
31 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Jagdeep Singh | 25183 | 25183 MSBA - MAUI - App not force logging out on time out | Defect Fixed | 1 | 1.5 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42733 | 45936 | 45997 | Jacquelin, Sean | 1q | NA | NA | NA | NA | NA
32 | MSB Mobile | 45807 | 45820 | 15.0 M Sprint 1 Stretch | Jagdeep Singh | 25190 | 25190 MSBA - MAUI - Forgot login | Defect Peer Review | 1 | 1.5 | 12 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42765 | 45967 |  | Ashwin Majjela | NA | NA | NA | NA | NA | NA | Carried to next sprint
1 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 48364 | REG - MSBA - Regression | Story Completed | 5 | 1.125 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Rupesh/Premkumar | 25195 | MSBA - MAUI - (Android) - Invoice Details - Keyboard is not opened after selecting the Partial Amount checkbox | Defect Fixed | 0.5 | 0.25 | 1 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42789 | 45820 | 45820 | Sean | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Jagdeep/Premkumar | 25183 | MSBA - MAUI - App not force logging out on time out | Defect Fixed | 1 | 0.5 | 2 | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Rupesh/Premkumar | 25198 | MSBA - MAUI - Invoice Details - Payment options pop up | Defect Fixed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42696 | 45817 | 45820 | Sean | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Sambath/Vaishnavi | 25359 | 25359 MSBP - MAUI - checkout not respecting promocode flag (15.0) | Story Completed | 1 | 0.125 | 0.5 | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Jagdeep | 25190 | MSBA - MAUI - Forgot login | Defect Peer Review | 0.5 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
7 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Gursewak | 25380 | MSBA - MAUI - Unable to login after logout | Defect Peer Review | 1 | 3.5 | 14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
8 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Sambath/Vaishnavi | 25414 | MSBP - MAUI - Resource not found in store filters (15.0) | Defect Fixed | 1 | 1.25 | 5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42842 | 45821 | 45821 | Sean | NA | N A | NA | NA | NA | NA
9 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Premkumar | 25202 | MSBA - MAUI - TXN History | Defect Fixed | 0.5 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Sambath/Premkumar | 25199 | 25199 MSBA - MAUI - Invoice Details - Payment options pop up - Alignment | Defect Fixed | 2 | 1.87 | 7.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42868 | 45824 | 45825 | Ashwin | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 48632 | MSBP CA - MAUI Regression | Story Completed | 1 | 0.75 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Sambath | 25427 | 25427 MSBA - Xamarin - Payment summary not showing the balance amount in receipt screen when printer is not connected (Regression) (14.7) | Defect Fixed | 2 | 5 | 20 | NA | NA | NA | NA | NA |  |  |  |  | NA | NA | NA | NA | NA | NA
13 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Sambath/Vaishnavi | 25456 | 25456 MSBP - MAUI - Filter option not working in store 15.0 | Defect Fixed | 0 | 0.6 | 2.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/42911 | 45826 | 45826 |  | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 25445 | MSBP- MAUI - Android_Total, Paid and Remaining balance field amounts are not aligned properly in Invoice payment option screen (regression) (15.0) | Defect Fixed | 0 | 0.125 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 25418 | MSBP - MAUI - iOS - sheet issue on invoice auto pay subscription(regression) (14.7) | Defect Fixed | 0 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 25416 | MSBP - MAUI - no +Add Student on homepage of suggested student type account (15.0) | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
17 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 25414 | MSBP - MAUI - Resource not found in store filters (15.0) | Defect Fixed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
18 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 25378 | MSBP - MAUI - Android - promotion code field not aligned (15.0) | Defect Fixed | 0.5 | .12`5 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 25367 | MSBP - MAUI - suggested student workflow does not reach final page if middle page navigates to inputs (15.0) | Defect Fixed | 0.5 | 0.125 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
20 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Gurserwak/Premkumar | 25197 | MSBA - MAUI - Invoice Details - Payment options pop up - add space between labels and checkbox | Defect Fixed | 1 | 2 | 8 | NA | NA | NA | NA | NA |  |  |  | NA | NA | NA | NA | NA | NA | NA
21 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 45983 | MSBP - Store - No Students on Account - Show District Wide Products | Story Being Tested | 5 | 0.5 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
24 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 25440 | MSBP CA - MAUI - Unable to enter CA Postal code while adding payment methods (Regression) | Defect Fixed | 0 | 1.125 | 4.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
23 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 | Vaishnavi | 25406 | MSBP - MAUI - Allows user to enter more values in the amount field. Maximum value limit is not been set (15.0) | Defect Fixed | 2 | 0.25 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
32 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 Stretch | Jagdeep | 25178 | MSBA - MAUI -Store screen -filters not filling the whole screen | Story Peer Review | 2 | 3 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
25 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 Stretch | Vaishnavi | 25420 | MSBP - MAUI - iOS - invoice information sheet the header/back button not at top of page (15.0) | Defect Fixed | 1 | 0.125 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
26 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 Stretch | Vaishnavi | 25431 | MSBP - MAUI - iOS - invoice screen continues to scroll for an entire page past last information (15.0) | Defect Fixed | 0 | 0.125 | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
27 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 Stretch | Amrit/Premkumar | 25191 | MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Defect Being Fixed | 2 | 0 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
28 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 Stretch | Premkumar | 25201 | MSBA - MAUI - Add to Cart - Android - expand/collapse only works when you drag a list item first | Defect Fixed | 2 | 1.75 | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
29 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 Stretch | Sambath | 46156 | 46156 MSBP - Tickets - Event Details | Story Being Developed | 5 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
30 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 Stretch | Vaishnavi | 42146 | MSBA - Maui - Tickets | Story Completed | 1 | 0.375 | 1.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
31 | MSB Mobile | 45821 | 45833 | 15.0 M Sprint 2 Stretch | Rupesh | 48807 | MSBA - Maui - Cart - Edit Product Cart Items | Story Peer Review | 3 | 1.25 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Carried to the next sprint
1 | MSB Mobile | 45834 | 45848 | 15.0 M Sprint 3 | Vaishnavi | 48938 | MSBP Maui - Full Regression | Story Completed | 5 |  | 17 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile | 45834 | 45848 | 15.0 M Sprint 3 | Vaishnavi/Chandler(onsite dev) | 45983 | MSBP - Store - No Students on Account - Show District Wide Products | Story Completed | 2 |  | 2.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 | Jagdeep/Premkumar | 25190 | MSBA - MAUI - Forgot login | Defect Fixed | 1 |  | 6 | NA | NA | NA | NA | NA | Pull Request 43051: Fixed keyboard overlap issue on Login ad forgot login screen. | 27-06-25 | 45876 | Ashwin | If this is used only for iOS can you add #if IOS condition here | Avery | 45876 | Since there's no corresponding Android handler this can go in the platforms/iOS to keep things neater and the iOS directives can be removed. Just be mindful of the namespace with for the USING in the basecontentpage | NA | NA
4 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 | Gursewak/Premkumar | 25380 | MSBA - MAUI - Unable to login after logout | Defect Fixed | 2 |  | 7.5 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42766 | 45819 | 45834 | 1
5 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 | Premkumar | 48944 | MSBP - Automation - Mappings for Automation - Messages | Story Being Developed | 5 |  | 5 | [15 empty] | Completed on adding the automation ID. And started writing the automation test cases for the same
6 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 | Gursewak | 48959 | MSBP - Automation - Mappings for Automation - Meal Money Page - Add Funds Functionality | Story Being Developed | 5 |  | 62 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43273?path=/Mobile%20Automation/src/Mobile%20Parent/MealMoney.cs https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43274?_a=files&path=/MSB.Parent/Pages/AddFundsPage.xaml | 45847 |  | 3 | Amrit, Jagdeep, Ashwin | [5 empty] | Need to change code according to aswin suggest to all developers
7 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 | Amrit | 48945 | MSBP - Automation - Mappings for Automation - Payment Methods | Story Peer Review | 5 |  | 37 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43305 | 45848 |  |  |  | OWEN | NA |  |  |  | Development completed. 2 days was blocked because of firewall, PR is create
8 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 | Jagdeep | 48943 | MSBP - Automation - Mappings for Automation - Payment History | Story Peer Review | 5 |  | 20 | NA | NA | NA | NA | NA | Pull Request 43125: Created test case for PaymentHistory. | 45840 | 45843 | Ashiwn | NA | Owen | NA | what are all these long sleeps for? Couldn't we use wait for appium element instead. | NA | NA | Start work on it again after client comments on PR.
9 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 | Rupesh | 48946 | MSBP - Automation - Mappings for Automation - Add Meal Money | Story Being Developed | 5 | 5 | 22 | NA | NA | NA | NA | NA |  | NA | NA |  | NA |  | NA |  | NA |  | Completed the Settings flow with both notifications and purchase control. Bottom sheet issue with iOS, working fine in Android.
10 | MSB Mobile | 45834 | 45848 | 15.0 M Sprint 3 | Vaishnavi | 25509 | MSBP - Maui - Unable to enter value '0' after decimal point in Mealmoney and Invoice partial amount 15.0 (Regression) | Defect Fixed | 0 |  | 0.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 | Jagdeep | 48942 | MSBP - Automation - Mappings for Automation - Contact Us | Story Peer Review | 5 |  | 17 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43170 | 45812 | 45817 | Ashwin | NA | Owen | NA | NA | NA | NA | Peer review in progress by client.
12 | MSB Mobile | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Sambath/Premkumar | 25191 | MSBA - MAUI - store screen/ invoice - device Scanner does not open a second time(Android) | Defect Fixed | 2 |  | 16.5 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43230 | 45846 | 45846 | Ashwin | NA | NA | NA | NA | NA | NA | Testing in progress.
13 | MSB Mobile | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Sambath | 46156 | 46156 MSBP - Tickets - Event Details | Story Completed | 3 | 3 | 13 | NA | NA | NA | Amirt | move to resource file | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43070 | 45840 | 45840 | Avery | NA | NA | NA | NA | NA
14 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Rupesh/Premkumar | 48807 | MSBA - Maui - Cart - Edit Product Cart Items | Story Peer Review | 2 | 3 | 15 | NA | NA | NA | Sambath | Device.StartTimer is depreciated, please use alternate suggestion | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43099 | 45840 | 45841 | Avery | Since you're using a contentview that contains these resources this isn't needed here, Comment out this HeaderTemplate, demo mode is not implemented | NA | NA |  |  |  | Bouncebacks fixed by the developer. Yet to be deployed to QA.
15 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Jagdeep/Premkumar | 25178 | MSBA - MAUI -Store screen -filters not filling the whole screen | Defect Fixed | 1 |  | 1 | NA | NA | NA | Prem | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/42996 | 24/06/2025 | 45695 | Avery | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Sambath | 46155 | 46155 MSBP - Tickets - Upcoming Events Screen | Story Completed | 2 | 2 | 19 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43161 | 45842 | 45845 | Avery | NA | NA | NA | NA | NA | NA | Testing in progress by Onsite QA.
17 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Avery/Premkumar | 48871 | MSBA - MAUI - Edit Meals in Cart | Story Completed | 2 |  | 11.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Testing completed.
18 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Amrit | 48956 | MSBP - Automation - Mappings for Automation - Profile - Additional IDs | Story Completed | 1 |  | 5 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43056?_a=files | 45835 | NA | Owen | NA | Avery | NA | NA | NA | NA | Peer review in progress by client.
19 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Jagdeep | 49063 | MSBP - Automation - Profile - Update Automation Framework to use IDs instead of XPath | Story Completed | 2 |  | 4 | NA | NA | NA | NA | NA | Pull Request 43224: Used AutomationId instead of Xpath. | 45846 | 45847 | Ashwin | NA | Owen | NA | NA | NA | NA | Tested and approved by client.
20 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Jagdeep | 49062 | MSBP - Automation - Login - Update Automation Framework to use IDs instead of XPath | Story Peer Review | 4 |  | 15 | NA | NA | NA | Sambath | NA | Pull Request 43249: 49062-Automation-Login-Update Automation Framework to use IDs instead of XPath | 45846 | 45847 | [7 empty] | Peer review in progress by client.
21 | MSB Mobile Kaleida wave | 45834 | 45848 | 15.0 M Sprint 3 Stretch | Amrit | 48965 | 48965 MSBP - Automation - Mappings for Automation - Login - Additional IDs | Story Completed | 1 |  | 7 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43056?_a=files | 45835 | NA | Owen | NA | Avery | NA | NA | NA | NA | Tested and approved by client.
1 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 | Premkumar | 48944 | MSBP - Automation - Mappings for Automation - Messages | Story Completed | 3 |  | 20 | 45846 | 45853 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43344 | 45852
2 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 | Gursewak | 48959 | MSBP - Automation - Mappings for Automation - Meal Money Page - Add Funds Functionality | Story Peer Review | 2 |  | 40 | 45853 | 45862 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43273 | 45853 |  | Ashwin | Can you use automation ID instead of Xpath and remove this if condition | OWEN |  | 1.This method you pass in the amount you want to add. Looking through this, it appears the tests is just pressing on everything. If we want to add $10. It should find the student, add just $10 and save. Then verify it was done.
3 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 | Amrit | 48945 | MSBP - Automation - Mappings for Automation - Payment Methods | Story Peer Review | 3 |  | 29 | 45845 | 45853 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43305 | 45848 | 45856 | Ashwin | NA | OWEN | First Approval (19-07-2025) | Replace it with WaitForElement on all Thread.sleeps in the PR - We should not be checking in this. Leave the appPath empty. | NA
4 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 | Jagdeep | 48943 | MSBP - Automation - Mappings for Automation - Payment History | Story Completed | 3 |  | 10 | 45838 | 45859 | NA | NA | NA | NA | NA | Pull Request 43125: Created test case for PaymentHistory. | 45840 | 45854 | Ashwin | Resolved The dictionary should be formed by getting the text from the UI and not hardcoded like Jane0001 | OWEN | 45860 | This does not look correct com.hss.enterprise.msb:id/NavigateBack is the id for the back button. | Completed
5 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Rupesh | 48946 | MSBP - Automation - Mappings for Automation - Add Meal Money | Story Peer Review | 3 |  | 21 | 45840 | 45853 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43391 | 45854 | 45854 | Ashwin | NA | OWEN | NA | com.hss.enterprise.msb:id/NavigateBack is the id for the back button. | NA
6 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 | Jagdeep | 48942 | MSBP - Automation - Mappings for Automation - Contact Us | Story Completed | 1 |  | 9 | 45842 | 45856 | NA | NA | NA | NA | NA | Pull Request 43170: Mappings for Automation - Contact Us | 45842 | 45853 | Ashwin | NA | OWEN | 45857 |  | Completed
7 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Rupesh/Premkumar | 48807 | MSBA - Maui - Cart - Edit Product Cart Items | Story Completed | 0.5 |  | 8 | NA | NA | NA | NA | NA | Ashwin | format it so that there is space above the declaration and also indent it properly for readability. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43297 | 45695 | 45723 | Avery | NA | NA | 45853 |  | NA
8 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 | Jagdeep | 49062 | MSBP - Automation - Login - Update Automation Framework to use IDs instead of XPath | Story Completed | 0.5 |  | 4 | 45846 | 45859 | NA | NA | NA | NA | NA | Pull Request 43249: 49062-Automation-Login-Update Automation Framework to use IDs instead of XPath | 45847 | 45854 | Ashwin | Are these commented lines of code needed? | OWEN | 45854 |  | Completed
9 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Vaishnavi | 48870 | MSBA - MAUI - Edit Invoices From Cart | Story Completed | 2 |  | 7 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | NA
10 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Vaishnavi | 42140 | MSBA - Maui - Scanner Wizard - Latest Socket .NET MAUI Package Integration | Story Completed | 1 |  | 19 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Sambath | 48182 | MSBP - Tickets - Maintaining the session from the mobile app to tickets | Story Peer Review | 3 |  | 15 | 45841 | 45861 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43562 | 45861 |  | Amrit | use assert for test case success and fail |  | NA | NA | NA
12 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Rupesh | 49021 | MSBP - Automation - Mappings for Automation - Cart | Story Being Developed | 5 |  | 23 | 45853 | 45859 | NA | NA | NA | Amrit | use wait appium not thread, use assert for test case success and fail | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43509 | 45860 | 45860 | Ashwin | NA | OWEN | NA | None of the tests will execute for me. They login and fail on the main page. Please make sure they run for you. | Completed
13 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Vaishnavi | 49160 | REG - MSBP CA - Prod Smoke Test Against Staging RC | Story Completed | 1 |  | 3.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Sambath | 49060 | 49060 MSBP - Automation - Mappings for Automation - Meal Money Page - Transfer Funds Functionality | Story Peer Review | 3 |  | 45 | 45852 | 45861 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43503 | 45860 | 45861 | Ashwin | NA | OWEN | NA | The methods should be written where you pass in the students to transfer money to and from. That info is what is used to perform the actions. This appears to be all hard coded in the methods. | NA
15 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 | Vaishnavi | 25524 | MSBP - MAUI - account creation confirm password not validating on return (regression) | Story Completed | 2 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 | Gursewak | 49059 | 49059 MSBP - Automation - Mappings for Automation - Meal Money Page - AutoPay Functionality | Story Peer Review | 5 |  | 49 | 45853 | 45860 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43513?_a=files https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43514?_a=files | 45860 | NA | Ashwin |  | NA | NA | NA | Completed
17 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 Stretch | Amrit | 49043 | 49043 MSBP - Automation - Mappings for Automation - Events | Story Peer Review | 3 |  | 13 | 45856 |  | NA | NA | NA | Rupesh |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43536 | 23/7/2025 | NA | NA | Use Verify Text Method,Remove Comented Code | NA | NA | NA | NA
18 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 Stretch | Jagdeep | 49101 | MSBP - Automation - Mappings for Automation - Request a Refund | Story Peer Review | 5 |  | 32.5 | 45852 | 45861 | NA | NA | NA | Amrit | NA | Pull Request 43438: 49101-MSBP-Automation-Mappings for Automation-Request a Refund | 45855 | 45860 | Ashwin | Why are we checking ResourceNotFound here? | OWEN | NA | NA | Completed
19 | MSB Mobile Kaleida | 45849 | 45862 | 15.1 M Sprint 1 Stretch | Premkumar | 49123 | MSBP - Automation - Mappings for Automation - Quick Links | Story Being Developed | 3 |  | 21 | 45856 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
20 | MSB Mobile | 45849 | 45862 | 15.1 M Sprint 1 Stretch | Vaishnavi | 49125 | MSBP - Automation - Mappings for Automation - Greenlight | Story Being Developed | 3 |  | 18 | 45861 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Amrit | 48945 | MSBP - Automation - Mappings for Automation - Payment Methods | Story Completed | 3 |  |  | 45845 | 45876 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43305 | 45848 | 45856 | Ashwin | NA | OWEN | First Approval (19-07-2025). Second Approval (25-07-2025) | Replace it with WaitForElement on all Thread.sleeps in the PR - We should not be checking in this. Leave the appPath empty. | NA
2 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Amrit | 49043 | 49043 MSBP - Automation - Mappings for Automation - Events | Story Completed | 2 |  |  | 45856 | 45876 | NA | NA | NA | Rupesh |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43536 | 23/7/2025 | 31/7/2025 | NA | Use Verify Text Method,Remove Comented Code | NA | 31/07/2025 | NA | NA
3 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Amrit | 49019 | 49019 - MSBP - Automation - Mappings for Automation - Add Student | Story Peer Review | 8 |  |  | 45863 | 45664 | NA | NA | NA | Ashwin |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43802 | 45866 | NA | NA | Merge date picker code into appium actions | NA | NA | NA | Cover Negative case also
4 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Gursewak | 48959 | MSBP - Automation - Mappings for Automation - Meal Money Page - Add Funds Functionality | Story Completed | 2 |  |  | 45853 | 45876 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43273 | 45853 |  | Ashwin | Can you use automation ID instead of Xpath and remove this if condition | OWEN |  | 1.This method you pass in the amount you want to add. Looking through this, it appears the tests is just pressing on everything. If we want to add $10. It should find the student, add just $10 and save. Then verify it was done. | NA
5 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Gursewak | 49059 | 49059 MSBP - Automation - Mappings for Automation - Meal Money Page - AutoPay Functionality | Story Completed | 3 |  |  | 45853 | 45876 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43513?_a=files https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43514?_a=files | 45860 | NA | Ashwin |  | NA | NA | NA | Completed
6 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Jagdeep | 49101 | MSBP - Automation - Mappings for Automation - Request a Refund | Story Completed | 2 |  | 3 | 45852 | 45866 | NA | NA | NA | Amrit | NA | Pull Request 43438: 49101-MSBP-Automation-Mappings for Automation-Request a Refund | 45855 | 45860 | Ashwin | 1. Why are we checking ResourceNotFound here? 2. To Uncomment lines. | OWEN | 45868 | IF this is always going to be the current date, then this can be moved into the class method as a hardcoded date. If this is going to be adjustable, then we can put in the class method a check for this existence of this key and if it is there, use this value and if not, use current date. | Completed
7 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Jagdeep | 49042 | MSBP - Automation - Mappings for Automation - Store | Story Completed | 5 |  | 21 | 45863 | 45874 | NA | NA | NA | Amrit | add wait for appium on place of thread sleep | Pull Request 43615: 49042 MSBP-Automation-Mappings for Automation-Store | 45866 | NA | Ashwin | NA | OWEN | 45875 | NA | NA
8 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Premkumar | 49123 | MSBP - Automation - Mappings for Automation - Quick Links | Story Completed | 2 |  | 32 | 45856 | 45863 | NA | NA | NA | NA |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43574 | 45863 | 45863 | NA | NA | NA | NA | NA | NA
9 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 | Premkumar | 49131 | MSBP - Automation - Mappings for Automation - Student information (4 dots) | Story Completed | 3 |  | 26 | 45866 | 45874 | NA | NA | NA |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43702 | 45869 | 45875 | Ashwin | NA | OWEN | 45874 | NA | NA
10 | MSB Mobile | 45863 | 45876 | 15.1 M Sprint 2 | Rupesh | 48946 | MSBP - Automation - Mappings for Automation - Add Meal Money | Story Completed | 1 |  |  | 45840 |  | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43391 | 45854 | 45854 | Ashwin | NA | OWEN | NA | com.hss.enterprise.msb:id/NavigateBack is the id for the back button. | NA
11 | MSB Mobile | 45863 | 45876 | 15.1 M Sprint 2 | Rupesh | 49021 | MSBP - Automation - Mappings for Automation - Cart | Story Peer Review | 3 |  | 35 | 45853 |  | NA | NA | NA | Amrit | use wait appium not thread, use assert for test case success and fail | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43509 | 45860 | 45860 | Ashwin | NA | OWEN | NA | None of the tests will execute for me. They login and fail on the main page. Please make sure they run for you. | Completed
12 | MSB Mobile | 45863 | 45876 | 15.1 M Sprint 2 | Sambath | 48182 | MSBP - Tickets - Maintaining the session from the mobile app to tickets | Story Completed | 1 |  | 12 | 45863 | 45862 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/43562 | 45861 |  | Amrit | use assert for test case success and fail |  | NA | NA | NA
13 | MSB Mobile | 45863 | 45876 | 15.1 M Sprint 2 | Sambath | 49060 | 49060 MSBP - Automation - Mappings for Automation - Meal Money Page - Transfer Funds Functionality | Story Completed | 3 |  | 18 | 45852 | 45869 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43503 | 45860 | 45861 | Ashwin | NA | OWEN | NA | The methods should be written where you pass in the students to transfer money to and from. That info is what is used to perform the actions. This appears to be all hard coded in the methods. This should be so consolidated into one class method | NA
14 | MSB Mobile | 45863 | 45876 | 15.1 M Sprint 2 | Vaishnavi | 49125 | MSBP - Automation - Mappings for Automation - Greenlight | Story Peer Review | 3 |  | 30 | 45861 |  | NA | NA | NA | Jagdeep | 1. fix the formatting here. (alignment of lines)2. These lines should be uncommented. | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43728 | 45870 |  | Ashwin |  | NA | NA | NA | Completed
15 | MSB Mobile | 45863 | 45876 | 15.1 M Sprint 2 | Rupesh | 49039 | MSBP - Automation - Mappings for Automation - Pay Invoices | Story Completed | 5 |  | 26 | 45867 | 45874 | NA | NA | NA | Gursewak | 1: Remove extra spaces 2: Use "!" for remove warning messages after ToString() | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43776 | 45874 | 45874 | Ashwin | NA | OWEN | 45875 | NA | Completed
16 | MSB Mobile Kaleida | 45863 | 45876 | 15.1 M Sprint 2 Stretch | Jagdeep | 49129 | MSBP - Automation - Mappings for Automation - Suggested Students workflow | Story Being Developed | 8 |  | 29 | 45868 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
17 | MSB Mobile | 45863 | 45876 | 15.1 M Sprint 2 Stretch | Sambath | 49041 | 49041 MSBP - Automation - Mappings for Automation - Scheduled Payments | Story Peer Review | 3 |  | 32 | 45867 | 45875 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43754?_a=files | 45875 | 45876 | Ashwin | NA | OWEN | NA | NA | NA
1 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 | Amrit | 49019 | 49019 - MSBP - Automation - Mappings for Automation - Add Student | Story Peer Review | 3 |  | 56 | 45863 | 45664 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43802 | 45866 | NA | Sambath | Merge date picker code into appium actions | NA | NA | NA | Cover Negative case also
2 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 | Rupesh | 49021 | MSBP - Automation - Mappings for Automation - Cart | Story Completed | 1 |  | 4 | 45853 | 45877 | NA | NA | NA | Amrit | use wait appium not thread, use assert for test case success and fail | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43509 | 45860 | 45860 | Ashwin | NA | OWEN | NA | None of the tests will execute for me. They login and fail on the main page. Please make sure they run for you. | Completed
3 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 | Vaishnavi | 49125 | MSBP - Automation - Mappings for Automation - Greenlight | Story Completed | 2 |  | 8 | 45861 | 45876 | NA | NA | NA | Jagdeep | 1. fix the formatting here. (alignment of lines)2. These lines should be uncommented. | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43728 | 45870 | 45883 | Ashwin | 1. Rename this method to something like DontShareAndRegister and move the collapse functionality as a separate method. Also the edit could be a separate method or check it only in one of the follows. No need to check the edit in both share and dont share flow. | OWEN | 45887 | NA | Completed
4 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 | Jagdeep | 49129 | MSBP - Automation - Mappings for Automation - Suggested Students workflow | Story Being Developed | 3 |  | 0 | 45868 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 | Sambath | 49041 | 49041 MSBP - Automation - Mappings for Automation - Scheduled Payments | Story Completed | 3 |  | 0 | NA | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43754?_a=files | 45875 | 45876 | Ashwin | NA | OWEN | NA | NA | NA
6 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 | Premkumar | 49384 | MSBP - Automation - Mappings for Automation - Special Links | Story Completed | 3 |  | 20 | 45873 | 45880 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43887?_a=files | 45880 | 45887 | Ashwin | NA | OWEN | 45887 | NA | NA
7 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 | Vaishnavi | 49130 | MSBP - Automation - Mappings for Automation - Greenlight card | Story Peer Review | 3 |  | 23 | 45873 | 45882 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43890 | 45880 | NA | Ashwin | NA | OWEN | NA | NA | Completed
8 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 | Sambath/Premkumar | 25545 | 25545 MSBA - MAUI - store tiles overlap when cart preview is on | Defect Fixed | 3 |  | 14 | 45877 | 45880 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43913 | 45881 | 45882 | Ashwin | NA | Sean | NA | NA | NA
9 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 | Vaishnavi/Premkumar | 25541 | MSBA - MAUI - student search in product doing a double search | Defect Fixed | 2 |  | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 | Amrit | 25544 | MSBA - MAUI - iOS - filter sidebar in store does not change for groups or filters | Defect Being Fixed | 2 |  | 19 | 45877 | 45888 | NA | NA | NA | NA |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43963 | 45887 | 45889 | ashwin | NA | NA | NA | NA | Cover Negative case also
11 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Jagdeep/Vaishnavi | 25664 | MSBA - MAUI - Close day unable to move forward with shift user selected after toggling entire day | Defect Fixed | 3 |  | 9 | 45877 | 45877 | NA | NA | NA | NA | NA | Pull Request 43861: jagdeep.singh/25664 MSBA-MAUI-Close day unable to move forward with shift use... | 45877 | 45878 | NA | NA | NA | NA | NA | Completed
12 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Jagdeep/Prem | 25667 | MSBA - MAUI - Android - Close day keyboard deleting values crashes | Defect Fixed | 3 |  | 15 | 45880 | 45882 | NA | NA | NA | NA | NA | Pull Request 43943: jagdeep.singh/25667 MSBA-MAUI- Android Close day keyboard deleting values cra... | 45882 | NA | NA | NA | NA | NA | NA | Completed
13 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Gursewak | 25624 | MSBA - MAUI - close day has no data populated | Defect Being Tested | 2 |  | 39 | 45880 | 45888 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44019?_a=files | 45888 | NA | NA | NA | NA | 45889 | NA | Completed
14 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Rupesh/Prem | 25560 | MSBA - MAUI - Android - unable to load student in meals menu | Defect Fixed | 2 |  | 19 | 45881 | 45888 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43970 | 45888 | 45888 | Ashwin | NA | Avery | 45889 | NA | Completed
15 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Sambath | 25596 | 25596 MSBA - MAUI - remember me not logging back in | Defect Fixed | 2 |  | 5 | 45882 | 45882 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Jagdeep/Prem | 25557 | MSBA-MAUI - Android - Student name displays in cut off view for both Product Detail and Edit Product Detail Page | Defect Fixed | 1 |  | 4 | 45883 | 45883 | NA | NA | NA | NA | NA | Pull Request 43961: jagdeep.singh/MSBA-MAUI-Android-Student name displays in cut off view for bot... | 45883 | 45888 | Ashwin | NA | Avery | 45888 | Since the issue was for Android only, would the tablet padding negatively affect an iPad? | Completed
17 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Sambath/Prem | 25539 | 25539 MSBA - MAUI - promocode field missing in cart | Defect Fixed | 2 |  | 9 | 45883 | 45887 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44002 | 45887 | 45887 | Ashwin | NA | Sean | 45887 | NA | Completed
18 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Rupesh | 25644 | MSBA - MAUI - Close day checks do not show for check reconciliation | Story Being Tested | 2 |  | 5 | 45882 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Sambath/Vaishnavi | 25540 | 25540 MSBA - MAUI - cart total section formated incorrectly | Defect Fixed | 2 |  | 8 | 45883 | 45887 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44002 | 45887 | 45887 | Ashwin | NA | Sean | NA | NA | Completed
20 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Premkumar | 25643 | MSBA - MAUI - shift start unresponsive | Defect Fixed | 3 |  | 2 | 45887 | 45887 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44002 | 45887 | 45887 | Ashwin | NA | NA | NA | NA | NA
21 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Jagdeep/Prem | 25563 | MSBA - MAUI - cart preview/cart missing tax | Defect Fixed | 2 |  | 12 | 45883 | 45888 | NA | NA | NA | Sambath | NA | Pull Request 44032: jagdeep.singh/25563 MSBA-MAUI- cart preview/cart missing tax | 45888 | 45889 | Ashwin | NA | NA | NA | NA | Completed
22 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Gursewak | 25618 | MSBA - MAUI - Android - Close day count screen issues | Defect Being Tested | 2 |  | 8 | 45888 | 45889 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44059 | 45889 | NA | NA | NA | NA | 45889 | NA | Completed
23 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Jagdeep | 25626 | MSBA - MAUI - close day summary offset/short box is white | Defect Peer Review | 1 |  | 2 | 45889 | 45889 | NA | NA | NA | Rupesh | NA | Pull Request 44060: jagdeep.singh/25626-MSBA-MAUI-close day summary offsetshort box is white | 45889 | NA | NA | NA | NA | NA | NA | Completed
24 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Sambath/Prem | 25623 | 25623 MSBA - MAUI - if shift mode activated, badge appears behind clock for products added | Defect Being Tested | 2 |  | 9 | 45889 | 45889 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44050 | 45889 | 45889 | Ashwin | NA | Sean | NA | NA | Completed
25 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Jagdeep/Prem | 25627 | MSBA - MAUI - Android - text cut off on Close day screen | Defect Fixed | 1 |  | 7 | 45889 | 45889 | NA | NA | NA | NA | NA | Pull Request 44051: jagdeep.singh/25627 MSBA-MAUI-Android-text cut off on Close day screen | 45889 | NA | NA | NA | NA | NA | NA | Completed
26 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Jagdeep | 25570 | MSBA - MAUI - Android - Product page formatting issues | Defect Being Fixed | 2 |  | 7 | 45890 | 45890 | NA | NA | NA | NA | NA | Pull Request 44086: jagdeep.singh/25570 MSBA-MAUI-Android-Product page formatting issues | 45889 | NA | NA | NA | NA | NA | NA | Completed
27 | MSB Mobile | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Rupesh | 25564 | MSBA - Android - transaction history page goes under device heading and navigation | Story Being Developed | 3 |  | 10 | 45890 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
28 | MSB Mobile Kaleida | 45877 | 45890 | 15.1 M Sprint 3 Stretch | Amrit | 25491 | MSBA - MAUI - Icon Missing on Ters & Condition | Defect Peer Review | 1 |  | 0 | 45890 | 45891 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44076 | 45890 | 45891 | ashwin | NA | NA | NA | NA | NA
1 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Amrit | 49019 | 49019 - MSBP - Automation - Mappings for Automation - Add Student | Story Completed | 1 |  | 56 | 45863 | 45664 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43802 | 45866 | 45725 | Sambath | Merge date picker code into appium actions | OWEN | 45725 | NA | Cover Negative case also
2 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Jagdeep | 49129 | MSBP - Automation - Mappings for Automation - Suggested Students workflow | Story Peer Review | 3 |  | 18 | 45868 | 45898 | NA | NA | NA |  | NA | Pull Request 44354: 49129- Automation - Mappings for Automation - Suggested Students workflow | 45898 |  | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 | Vaishnavi | 49130 | MSBP - Automation - Mappings for Automation - Greenlight card | Story Completed | 0.5 |  | 40 | 45873 | 45882 | NA | NA | NA | Sambath | Use TestCategory("OWEN"), remove other TestCategory | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/43890 | 45880 | 45888 | Ashwin | NA | OWEN | 45538 | NA | Completed
4 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Gursewak/Vaishnavi | 25624 | MSBA - MAUI - close day has no data populated | Defect Fixed | 1 |  | 39 | 45880 | 45888 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44019?_a=files | 45888 | 45890 | Ashwin | NA | Avery | 45890 | NA | Completed
5 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 | Rupesh/Vaishnavi | 25644 | MSBA - MAUI - Close day checks do not show for check reconciliation | Defect Fixed | 1 |  | 13 | 45882 | 45889 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44019?_a=files | 45888 | 45890 | Ashwin | NA | Avery | 45890 | NA | Completed
6 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Gursewak/Vaishnavi | 25618 | MSBA - MAUI - Android - Close day count screen issues | Defect Fixed | 0.5 |  | 10 | 45888 | 45889 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44059 | 45889 | 45890 | Ashwin | NA | Avery | 45890 | NA | Completed
7 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Jagdeep/Prem | 25626 | MSBA - MAUI - close day summary offset/short box is white | Defect Fixed | 0.5 |  | 4 | 45889 | 45889 | NA | NA | NA | Rupesh | NA | Pull Request 44060: jagdeep.singh/25626-MSBA-MAUI-close day summary offsetshort box is white | 45889 | 45889 | Ashwin | NA | Avery/Sean | 45890 | NA | Completed
8 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Sambath/Prem/Vaishnavi | 25623 | 25623 MSBA - MAUI - if shift mode activated, badge appears behind clock for products added | Defect Fixed | 1 |  | 9 | 45889 | 45889 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44050 | 45889 | 45889 | Ashwin | NA | Sean |  | NA | Completed
9 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Jagdeep/Prem | 25570 | MSBA - MAUI - Android - Product page formatting issues | Defect Fixed | 1 |  | 12 | 45890 | 45890 | NA | NA | NA | Amrit | NA | Pull Request 44088: jagdeep.singh/25570-MSBA-MAUI-Android-Product page formatting | 45890 | 45892 | Ashwin | NA | Avery | 45892 | Add a fallback to the default font size (e.g., 14) in case FontSize isn’t set or is invalid. | Completed
10 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 | Rupesh/Prem | 25564 | MSBA - Android - transaction history page goes under device heading and navigation | Defect Fixed | 2 |  | 18 | 45890 | 45894 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44116 | 45891 | 45894 | Ashwin | NA | Sean |  | NA | Completed
11 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Amrit/Vaishnavi | 25491 | MSBA - MAUI - Icon Missing on Ters & Condition | Defect Fixed | 0.5 |  | 2 | 45890 | 45891 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44076 | 45890 | 45891 | ashwin | NA | Avery | 45666 | NA | Completed
12 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Gursewak/Vaishnavi | 25583 | MSBA - MAUI - on opening edit meal payment and saving, it clears amount | Defect Fixed | 1 |  | 15.3 | 45890 | 45891 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44105?_a=files | 45891 | 45894 | ashwin | NA | Sean | 45894 | NA | Completed
13 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Amrit/Prem | 25544 | MSBA - MAUI - iOS - filter sidebar in store does not change for groups or filters | Defect Fixed | 1 |  | 3.5 | 45877 | 45888 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/43963 | 45887 | 45889 | ashwin | NA | Avery | 29/8/2025 | NA | Cover Negative case also
14 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Gursewak | 25479 | MSBP - MAUI - image missing on add payment method screen | Defect Fixed | 1 |  | 6.5 | 45891 | 45894 | Na | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44138?_a=files | 45894 | 45895 | ashwin | NA | Avery | 45895 | NA | Completed
15 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Jagdeep/Prem | 25576 | MSBA - MAUI - Add to cart button cut off when cart preview active | Defect Fixed | 2 |  | 3 | 45891 | 45891 | Na | NA | NA | Rupesh | NA | Pull Request 44108: jagdeep.singh/25576-MSBA-MAUI-Add to cart button cut off when cart preview ac... | 45891 | 45892 | Ashwin | NA | Avery | 45892 | NA | Completed
16 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 | Rupesh/Vaishnavi | 25586 | MSBA - MAUI - Android - cart difficult to enter edit screens | Defect Fixed | 1 |  | 13 | 45894 | 45898 | Na | NA | NA |  | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44142 | 45894 | 45897 | Ashwin | NA | Avery | 45898 | NA | Completed
17 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 | Jagdeep/Vaishnavi | 25640 | MSBP-MAUI - iOS - Shows white screen on accessing links more than two times in Quick Links Section | Defect Fixed | 2 |  | 6.5 | 45894 | 45894 | NA | NA | NA | NA | Please remove margin if set as 0 | Pull Request 44130: jagdeep.singh/25640 MSBP-MAUI-iOS-Shows white screen on accessing links more... | 45894 | 45897 | Ashwin | Store was also having issue. fixed | Sean | 45897 | NA | Completed
18 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 | Sambath/Vaishnavi | 49322 | 49322 MSBP - Tickets - App Token Call Update | Story Completed | 3 |  | 36.5 | 45891 | 45895 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44167 | 45895 | 45895 | Ashwin | NA | Sean | 45895 | NA | Completed
19 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Sambath/Prem | 25577 | 25577 MSBA - MAUI - promocode error message cut off | Defect Fixed | 1 |  | 5 | 45891 | 45895 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44109 | 45895 | 45902 | Ashwin | NA | NA | NA | NA | NA
20 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Jagdeep/Vaishnavi | 25629 | MSBA - MAUI - iOS - error message for clerk behind entry box | Defect Fixed | 2 |  | 4 | 45894 | 45894 | Na | NA | NA | Rupesh | NA | Pull Request 44132: jagdeep.singh/25629 MSBA-MAUI-iOS-error message for clerk behind entry box | 45894 | 45894 | Ashwin | NA | Sean | 45894 | NA
21 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Gursewak/Prem | 25616 | MSBA - MAUI - Close day Icons missing/incorrect | Defect Fixed | 1 |  | 4 | 45897 | 45897 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44234 | 45897 | 45896 | Avery | NA | Avery | 45902 | NA | Completed
22 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Amrit/Prem | 25615 | MSBA - MAUI - Android -shift mode typing phone number issue | Defect Fixed | 1 |  | 6 | 45894 | 45894 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44133 | 45894 | 45895 | Rupesh | NA | Avery | 26/8/2025 | NA
23 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Gursewak/Vaishnavi | 25572 | MSBA - MAUI - invoice add to cart/remove button does not work | Defect Fixed | 2 |  | 6 | 45895 | 45895 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44168 | 45895 | 45896 | Ashwin | NA | NA | NA | NA | Completed
24 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Amrit/Prem | 25549 | MSBA - MAUI - phone - acknowledgements half page in landscape | Defect Fixed | 1 |  | 6 | 45895 | 45895 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44183 | 45901 | 45902 | Rupesh | NA | Avery | 45725 | NA
25 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Rupesh/Vaishnavi | 25559 | MSBA - MAUI - Android - Back arrow in product details cut off | Defect Fixed | 1 |  | 6 | 45895 | 45897 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44236 | 45897 | 45898 | Ashwin | NA | Awery | 45898 | NA | Completed
26 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Amrit/Vaishnavi | 25558 | MSBA - when signing in, if decline TOS and relog in, not presented with MFA | Defect Fixed | 2 |  | 10 | 45897 | 45898 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44281 | 45901 | 45902 | Ashwin | NA | Avery | 45697 | NA
27 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Vaishnavi/Prem | 25829 | MSBA - MAUI - no error message on bad login, can't log in after | Defect Fixed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
28 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Gursewak/Vaishnavi | 25666 | MSBA - MAUI - Android Phone - Cannot scroll to see entire Close day start page | Defect Fixed | 1 |  | 12 | 45898 | 45901 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44286?_a=files | 45901 | 45903 | Ashwin | NA | Sean | 45903 | NA | Completed
29 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Rupesh | 25565 | MSBA - MAUI - Transaction history missing () indicating refund | Defect Being Fixed | 1 |  | 22 | 45901 |  | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44335 | 45725 | 45725
30 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Jagdeep | 25840 | MSBA - MAUI - 'Successfully added invoice' message appears and disappears quickly in iOS after adding invoice to cart | Defect Peer Review | 1 |  | 4 | 45901 | 45901 |  |  |  | Amrit |  | Pull Request 44284: jagdeep.singh/25840 MSBA-MAUI-'Successfully added invoice' message appears an... | [7 empty] | Completed
31 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Sambath | 25665 | MSBA - MAUI - shift mode search bar cut off in landscape mode | Defect Being Fixed | 1 |  | 3 | 45901 | [6 empty] | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44333
32 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Sambath/Vaishnavi | 25814 | 25814 MSBP - MAUI - Events banner not showing the Event count in Homescreen | Defect Fixed | 2 | 7 | 7 | 45901 | 45902 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44307 | 45902 | 45902 | Ashwin | NA | Avery | NA | NA
33 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Jagdeep | 25622 | MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox] | Defect Needs More Info | 2 |  | 1 | 45902 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
34 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Jagdeep/Vaishnavi | 25620 | MSBA - MAUI - Android - warning messages on close day missing margins | Defect Fixed | 0.5 |  | 2 | 45902 | 45902 | NA | NA | NA | Amrit | NA | Pull Request 44303: jagdeep.singh/25620 MSBA-MAUI-Android-warning messages on close day missing margins | 45902 | 45902 | Ashwin | NA | Avery | 45902 | NA | Completed
35 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Jagdeep | 25625 | MSBA - MAUI - close day payment summary text is greyed out | Defect Peer Review | 1 |  | 4 | 45902 | 45902 | NA | NA | NA | Rupesh |  | Pull Request 44302: jagdeep.singh/25625 MSBA-MAUI-close day payment summary text is greyed out | 45902 | 45902 | Ashwin | NA |  |  |  | Completed
36 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Jagdeep/Prem | 25543 | MSBA - MAUI - Android - Camera icon cut off in store and invoice search bars | Defect Fixed | 2 |  | 6 | 45903 | 45903 | NA | NA | NA | Gursewak | NA | Pull Request 44323: jagdeep.singh/25543-MSBA-MAUI-Android-Camera icon cut off in store and invoic... | 45903 | 45904 | Ashwin | NA | Sean | 45904 | NA | Completed
37 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Vaishnavi | 49775 | MSBP - Replace MSB Lab environment with MSB Dev environment | Story Completed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
38 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Gursewak | 25571 | MSBA - MAUI - Android - adding product to cart does not redirect | Defect Needs More Info | 2 |  |  | 45903
39 | MSB Mobile Kaleida | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Jagdeep | 25493 | MSBP - MAUI - On adding second student/district with tickets available, banner not showing | Defect Peer Review | 2 |  | 3 | 45903 | 45905 | NA |  |  |  |  | Pull Request 44376: jagdeep.singh/25493 MSBP-MAUI-On adding second student district with tickets... | 45904 | NA | [5 empty] | Completed
40 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Vaishnavi | 49776 | MSBA - Replace MSB Lab environment with MSB Dev environment | Story Completed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
41 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Gursewak | 25598 | MSBA - MAUI - Android - Login page formatting issues | Defect Being Fixed | 2 |  | 3 | 45904 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
42 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Amrit | 25614 | MSBA - MAUI - Shift mode UI issues | Defect Being Fixed | 1 |  | 12 | 45904 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
43 | MSB Mobile | 45891 | 45904 | 15.2 M Sprint 1 Stretch | Rupesh | 25575 | MSBA - MAUI - meal payments screen changing formats | Defect Being Fixed | 1 |  | 3 | 45904 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Jagdeep | 49129 | MSBP - Automation - Mappings for Automation - Suggested Students workflow | Story Completed | 1 |  | 18 | 45868 | 45898 | NA | NA | NA | Gursewak | NA | Pull Request 44354: 49129- Automation - Mappings for Automation - Suggested Students workflow | 45898 | 45905 | Ashwin | NA | Owen | 45905 | NA | Completed
2 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 | Rupesh/Prem | 25565 | MSBA - MAUI - Transaction history missing () indicating refund | Defect Fixed | 0.5 |  | 30 | 45901 | 45912 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44335 | 45725 | 45725 | Ashwin | Rename one of the method | Sean | 45912 | TODO's are formatted like this //TODO: {message} | Completed
3 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Sambath/Prem | 25665 | MSBA - MAUI - shift mode search bar cut off in landscape mode | Defect Fixed | 0.5 |  | 9 | 45901 | 45912 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44532?_a=files | 45912 | 45912 | Ashwin | NA | Sean | 45912 | NA | Completed
4 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Jagdeep/Prem | 25625 | MSBA - MAUI - close day payment summary text is greyed out | Defect Fixed | 1 |  | 4 | 45902 | 45902 | NA | NA | NA | Rupesh | NA | Pull Request 44302: jagdeep.singh/25625 MSBA-MAUI-close day payment summary text is greyed out | 45902 | 45902 | Ashwin | NA | Sean | 45905 | These fields are not editable. You need to use a style or something when IsEnabled=false change the txt color | Completed
5 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Jagdeep/Prem | 25493 | MSBP - MAUI - On adding second student/district with tickets available, banner not showing | Defect Fixed | 2 |  | 13 | 45903 | 45905 | NA | NA | NA | Amrit | NA | Pull Request 44376: jagdeep.singh/25493 MSBP-MAUI-On adding second student district with tickets... | 45905 | 45909 | Ashwin | NA | Sean | 45910 | NA | Completed
6 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Gursewak/Vaishnavi | 25598 | MSBA - MAUI - Android - Login page formatting issues | Defect Fixed | 1 |  | 25 | 45904 | 45916 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44416?_a=files | 45915 | 45916 | Ashwin | NA | Sean | 45916 | NA | Completed
7 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Amrit/Vaishnavi | 25614 | MSBA - MAUI - Shift mode UI issues | Defect Fixed | 1 |  | 24 | 45905 | 45939 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44424 | 45878 | 45911 | Ashwin | NA | Avery | 45911 | NA | Completed
8 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 | Rupesh/Prem | 25575 | MSBA - MAUI - meal payments screen changing formats | Defect Fixed | 1 |  | 14 | 45904 | 45939 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44417 | 45908 | 45909 | Ashwin | NA | Sean | 45910 | Wasn't this just added? | Completed
9 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 | Sambath/Prem | 25619 | MSBA - MAUI - Close day navigation buttons cut off | Defect Fixed | 0.5 |  | 13 | 45904 | 45910 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44475 | 45910 | 45910 | Ashwin | NA | Sean | 45910 | NA | Completed
10 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 | Sambath/Prem | 25617 | MSBA - MAUI - Android - close day progress indicators cut off | Defect Fixed | 0.5 |  | 14 | 45904 | 45910 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44475 | 45910 | 45910 | Ashwin | NA | Sean | 45910 | NA | Completed
11 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Jagdeep/Vaishnavi | 25838 | MSBA-MAUI - Unable to Scroll the product/invoice/meals from Cart screen | Defect Fixed | 1 |  | 5 | 45905 | 45905 | NA | NA | NA | Amrit | NA | Pull Request 44384: jagdeep.singh/25838-MSBA-MAUI-Unable to Scroll the product and invoice and me... | 45904 | 45905 | Ashwin | NA | Sean | 45910 | Collection view already contains a scrollview. Have two scroll controls embedded is not advisable | Completed
12 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Jagdeep/Prem | 25735 | MSBP - iOS - Tickets banner missing arrow icon when no events | Defect Fixed | 2 |  | 9 | 45909 | 45909 | NA | NA | NA | Rupesh | NA | Pull Request 44446: jagdeep.singh/25735-MSBP-iOS-Tickets banner missing arrow icon when no events | 45909 | 45909 | Ashwin | NA | Sean | 45910 | NA | Completed
13 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Amrit/Vaishnavi | 25478 | MSBP - MAUI - iOS - Error Messaging Validation and Formatting | Defect Fixed | 1 |  | 23 | 45908 | 45910 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44425 | 45909 | 45910 | Ashwin | NA | Avery | 45910 | NA | Completed
14 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 | Jagdeep/Vaishnavi | 25734 | MSBP - MAUI - "Password too common" error when adding an account that already exists | Defect Fixed | 2 |  | 9 | 45908 | 45908 | NA | NA | NA | Amrit | NA | Pull Request 44418: jagdeep.singh/25734-MSBP-MAUI-Password too common error when adding an accoun... | 45908 | 45909 | Ashwin | NA | Sean | 45910 | NA | Completed
15 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 | Sambath | 25885 | MSBP - MAUI - Auto login does not work after closing the browser and selecting tickets from application for the second time | Defect Fixed | 2 |  | 6 | 45909 | 45909 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44464?_a=files | 45909 | 45909 | Ashwin | NA | Sean | 45910 | NA | NA
16 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 | Sambath | 25811 | 25811 MSBP Android - Fingerprint Plugin causing crash [Timebox] | Defect Rejected | 1 |  | 11 | 45910 | 45911 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
| MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 | Vaishnavi/Prem | 25924 | MSBP - AutoPay - Reverting to Disabled | Defect Being Tested | 0.5 |  |  | 45918
17 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Gursewak/Vaishnavi | 25562 | 25562 MSBA - MAUI - extra space on cart preview under cart items | Defect Fixed | 1 |  | 11 | 45908 | 45909 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44453 | 45909 | 45910 | Ashwin | NA | NA | 45910 | NA | Completed
18 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Vaishnavi/Prem | 49122 | MSBP - Automation - Mappings for Automation - Checkout/Receipt | Story Being Developed | 5 |  |  | 45905
19 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25830 | MSBA - MAUI - Android - Product Detail formatting issues (quantity) | Defect Fixed | 1 |  | 4 | 45910 | 45910 | NA | NA | NA | Rupesh | Margin for phone can be removed as it is 0. | Pull Request 44466: jagdeep.singh/25830 MSBA-MAUI-Android-Product Detail formatting issues quantity | 45910 | 45910 | Ashwin | NA | Sean | 45910 | NA | Completed
20 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Rupesh/Vaishnavi | 25566 | MSBA - MAUI - phones - transaction history information cut off | Defect Fixed | 2 |  | 22.5 | 45909 | 45916 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44535 | 45912 | 45916 | Ashwin | ScollBar Visibility is not needed. | Scroll View under Scroll is not advisable. | 45916 | NA | Completed
21 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25846 | MSBA - MAUI - upon logout, no message and cannot log back in | Defect Being Tested | 3 |  | 13 | 45911 | 45911 | NA | NA | NA | C | NA | jagdeep.singh/25846-MSBA-MAUI-upon-logout-no-message-and-cannot-log-back-in | 45911 | 45916 | Ashwin | NA | Sean | 45916 | NA | Completed
22 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Jagdeep/Vaishnavi | 25848 | MSBA - MAUI - product name not showing on thumbnail when no image on store page | Defect Fixed | 2 |  | 8 | 45912 | 45912 | NA | NA | NA | Rupesh | NA | Pull Request 44530: jagdeep.singh/25848-MSBA-MAUI-product name not showing on thumbnail when no i... | 45912 | 45916 | Ashwin | NA | Sean | 45916 | NA | Completed
23 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Amrit | 25849 | MSBA - Group filters not showing the products when particular category is selected | Defect Blocked | 1 |  | 13 | 45912 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
24 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Sambath/Vaishnavi | 25847 | 25847 MSBA - MAUI - products not available to be added to cart are not disabled when required field not filled | Defect Fixed | 2 |  | 8 | 45911 | 45915 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44577 | 45916 | 45916 | Ashwin | NA | Sean | NA | NA | Completed
25 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25550 | MSBA - MAUI - Android phone - unable to interact with heading | Defect Fixed | 5 |  | 14 | 45915 | 45915 | NA | NA | NA | Rupesh | NA | Pull Request 44551: jagdeep.singh/25550-MSBA-MAUI-Android phone unable to interact with heading | 45915 | 45916 | Ashwin | NA | Sean | 45916 | NA | Completed
26 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Rupesh/Vaishnavi | 25926 | MSBP - MAUI - Event banner is not clickable for a new user with no students | Defect Fixed | 3 |  |  | 45912 | 45916 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44622 | 45917 | 45917 | Ashwin | NA | Sean | 45917 | NA | Completed
27 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25845 | MSBA - MAUI - Store filters not showing the results based on the search criteria | Defect Fixed | 2 |  | 8 | 45916 | 45916 | NA | NA | NA | Gursewak | NA | Pull Request 44579: jagdeep.singh/25845-MSBA-MAUI-Store filters not showing the results based on... | 45916 | 45916 | Ashwin | NA | Sean | 45916 | NA | Completed
28 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Amrit | 25905 | MSBA - MAUI - District tax rate not applied | Defect Being Fixed | 3 |  |  | 45916
29 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Gursewak | 25892 | MSBA - MAUI - Android - Back button exists on first page of Close out | Defect Being Fixed | 1 |  |  | 45916
30 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Jagdeep/Prem | 25936 | MSBA - MAUI - iOS - after a timeout force log out, cannot manually log out | Defect Being Tested | 2 | 6 | 3 | 45917 | 45917 | NA | NA | NA | Gursewak | NA | jagdeep.singh/25846-MSBA-MAUI-upon-logout-no-message-and-cannot-log-back-in | 45917 | 45917 | Ashwin | NA | Sean | 45917 | NA | Completed
31 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Sambath | 25622 | 25622 MSBA - MAUI - iOS - cart preview cut off if tablet rotated [Timebox] | Defect Fixed | 2 |  | 8 | 45916 | 45916
32 | MSB Mobile Kaleida | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Jagdeep | 25934 | MSBA - MAUI - iOS - double loading icon on the MFA pages | Defect Being Fixed | 2 |  | 6 | 45918 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
33 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Gursewak | 25927 | MSBA - MAUI - iOS - hamburger menu not all centered | Defect Peer Review | 2 |  | 18 | 45918 | 45922 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44677?_a=files | 45922
34 | MSB Mobile | 45905 | 45918 | 15.2 M Sprint 2 Stretch | Rupesh | 25844 | MSBA - MAUI - able to open/stack transaction history/settings/close out from hamburger menu | Defect Being Fixed |  |  |  | 45918 |  | NA | NA | NA
1 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Amrit/Prem | 25905 | MSBA - MAUI - District tax rate not applied | Defect Fixed | 2 |  | 24 | 45916 | 45921 | NA | Jagdeep | NA | Ashwin | Check API before making changes | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44657 | 20/9/2025 | 22/9/2025 | Jagdeep | NA | Sean | 22/9/2025 | NA | NA
2 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Vaishnavi/Prem | 25936 | MSBA - MAUI - iOS - after a timeout force log out, cannot manually log out | Defect Fixed | 1 | 6 | 15 | 45917 | 45917 | NA | NA | NA | Gursewak | NA | jagdeep.singh/25846-MSBA-MAUI-upon-logout-no-message-and-cannot-log-back-in | 45917 | 45917 | Ashwin | NA | Sean | 45917 | NA | Completed
3 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Vaishnavi/Prem | 25846 | MSBA - MAUI - upon logout, no message and cannot log back in | Defect Fixed | 1 |  | 15.5 | 45917 | 45917 | NA | NA | NA | NA | NA | Pull Request 44612: jagdeep.singh/25846-MSBA-MAUI-upon logout, no message and cannot log back in(... | 45917 | 45917 | Ashwin | NA | Sean | 45917 | NA | Completed
4 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Sambath/Vaishnavi | 25964 | MSBA - MAUI - iOS - cart preview cut off if tablet rotated | Defect Fixed | 2 |  | 18 | 45916 | 45923 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44716 | 45923 | 45924 | Ashwin | NA | Sean | 45924 | NA | Completed
5 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep/Prem | 25934 | MSBA - MAUI - iOS - double loading icon on the MFA pages | Defect Fixed | 1 |  | 12.5 | 45918 | 45919 | NA | NA | NA | Amrit | NA | Pull Request 44653: jagdeep.singh/25934-MSBA-MAUI-iOS-double loading icon on the MFA pages | 45919 | 45923 | Ashwin | NA | Sean | 45924 | NA | Completed
6 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Gursewak/Prem | 25927 | MSBA - MAUI - iOS - hamburger menu not all centered | Defect Fixed | 2 |  | 15.5 | 45918 | 45923 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44677?_a=files | 45923 | 45923 | Ashwin | NA | Sean | 45923 | NA | Completed
7 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Rupesh | 25844 | MSBA - MAUI - able to open/stack transaction history/settings/close out from hamburger menu | Defect Fixed | 2 |  | 20 | 45918 |  | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44649 | 45918 | 45924 | Ashwin | NA | Sean | 09/25/205 | Instead of doing all this just use the the CanExecute function on the AsyncCommand. You won't need to mess with any of the UI | Completed
8 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Vaishnavi/Prem | 50147 | MSBP Maui - Full Regression 15.2 | Story Completed | 13 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep | 50127 | MSB - Automation - Develop a strategy to handle iOS bottom sheet automation | Story Completed | 5 |  | 8 | 45919 | 45922 | NA | NA | NA | Gursewak | NA | Pull Request 44678: jagdeep.singh/50127-MSB-Automation-Develop a strategy to handle iOS bottom sh... | 45922 | 45923 | Ashwin | NA | Sean | 45924 | NA | Completed
10 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Amrit | 50126 | MSB - Automation - Investigate and fix 7 broken automation tests | Story Completed | 5 |  | 30 | 22/9/2025 | 28/9/2025 | NA | NA | NA | Jagdeep | NA | MSBP MAUI , PR 1 . | 45926 | 30/9/2025 | Ashwin | NA | Owen | 30/9/2025 | NA | NA
11 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep | 49122 | MSBP - Automation - Mappings for Automation - Checkout/Receipt | Story Completed | 5 |  | 20 | 45922 | 45926 | NA | NA | NA | Amrit | NA | Pull Request 44814: jagdeep.singh/49122-MSBP-Automation-Mappings for Automation-Checkout/Receipt | 45926 | 45931 | Ashwin | NA | Owen | 45931 | NA | Completed
12 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep | 25986 | MSBP - GA - MSB.Parent.ViewModels.MealMoneyAutoPaySettingsViewModel | Defect Fixed | 0.5 |  | 2.75 | 45923 | 45923 | NA | NA | NA | Sambath | NA | Pull Request 44699: jagdeep.singh/25986-MSBP-GA-MSB.Parent.ViewModels.MealMoneyAutoPaySettingsVie... | 45923 | 45923 | Ashwin | NA | Sean | 45924 | NA | NA
13 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep | 25989 | MSBP - GA - MSB.Parent.ViewModels.StudentDetailViewModel | Defect Fixed | 0.5 |  | 2 | 45923 | 45923 | NA | NA | NA | Sambath | NA | jagdeep.singh/MSBP-GA-MSB.Parent.ViewModels.StudentDetailViewModel | 45923 | 45923 | Ashwin | NA | Sean | 45924 | NA | NA
14 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep | 25997 | MSBP - GA - MSB.Parent.Helpers.LoginHelper.RestoreSavedSession | Defect Fixed | 0.5 |  | 1 | 45923 | 45923 | NA | NA | NA | Sambath | NA | jagdeep.singh/25997-MSBP-GA-MSBP.Parent.Helpers.LoginHelper.RestoreSavedSession | 45923 | 45923 | Ashwin | NA | Sean | 45924 | NA | NA
15 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Amrit | 25998 | MSBP - GA - MSB.Parent.Core.NavigationService.OnNavigated | Defect Fixed | 1 |  | 3 | 45923 | 45923 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44704 | 45923 | 45923 | NA | NA | Sean | 45923 | NA | NA
16 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Rupesh | 25994 | MSBP - GA - MSB.Parent.ViewModels.ReceiptViewModel | Defect Fixed | 1 |  | 6 | 45923 | 45923 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44710 | 45923 | 45923 | NA | NA | Sean | 45923 | NA | NA
17 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Gursewak | 25993 | MSBP - GA - MSB.Parent.ViewModels.StoreViewModel | Defect Fixed | 0.5 |  | 2 | 45923 | 45923 | Na | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44708 | 45923 | 45923 | NA | NA | Sean | 45923 | NA | NA
18 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep | 25995 | MSBP - GA - MSB.Parent.ViewModels.ProductDetailViewModel | Defect Fixed | 0.5 |  | 2 | 45923 | 45923 | NA | NA | NA | Ashwin | NA | Pull Request 44705: jagdeep.singh/25995-MSBP-GA-MSB.Parent.ViewModels.ProductDetailViewModel | 45923 | 45923 | NA | NA | Sean | 45924 | NA | NA
19 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep | 26004 | MSBP - MAUI - Android- Keyboard switches away from numerical after first digit entry (regression) | Defect Rejected | 0 |  | 1 | 45924 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
20 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Gursewak | 26003 | MSBP - MAUI - Entering partial amount more than the remaining balance amount, screen freezes and unable to move forward (regression) | Defect Fixed | 0 |  | 6 | 45924 | 45925 | Na | NA | Na | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44798 | 45925 | 45926 | NA | NA | Brian | 45926 | NA | NA
21 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Sambath | 25988 | 25988 MSBP - GA - Plugin.Fingerprint.FingerprintImplementation | Defect Fixed | 2 |  | 8 | 45923 | 45924 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44744 | 45924 | 45924 | Ashwin | NA | Sean | 45924 | NA | NA
22 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Vaishnavi/Prem | 25924 | MSBP - AutoPay - Reverting to Disabled | Defect Fixed | 2 |  | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
24 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Rupesh | 26022 | MSBP - MAUI - Redirecting to from empty cart freezes app (regression) | Defect Fixed | 0 |  | 4 | 45925 | 45926 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44781 | 45925 | 45925 | Ashwin | NA | Brian | 45926 | NA | Completed
25 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Gursewak | 26028 | MSBP -MAUI - Adding new payment method from Meal money autopay not prompting for cvv when autopay is saved(regression) | Defect Needs More Info | 0 |  | NA | 45926 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
26 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Sambath | 26030 | 26030 MSBP - MAUI - iOS26 - student meal payment is showing blank | Defect Fixed | 3 |  | 12 | 45926 | 45929 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44850 | 45929 | 45929 | Ashwin | NA | Sean | 45929 | NA | Completed
27 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep/Prem | 25975 | MSBP - MAUI - Family Pass discount line showing when no program fee | Defect Fixed | 0 |  | 3 | 45929 | 45929 | NA | NA | NA | Sambath | NA | Pull Request 44842: jagdeep.singh/25975-MSBP-MAUI-Family Pass discount line showing when no progr... | 45929 | 45930 | Ashwin | NA | Sean | 45930 | NA | Completed
29 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Gursewak | 26034 | MSBP-MAUI-I-Bottom sheet not showing all information, Student info(regression) | Defect Fixed | 0 |  | 3 | 45929 | 45929 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44847 | 45929 | 45930 | Ashwin | NA | Sean | 45930 | NA | Completed
30 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 | Rupesh | 26033 | MSBP-MAUI- iOS-Selecting expired payment method for an invoice transaction,screen does not redirect to Edit Payment Method screen(regression) | Defect Fixed | 0 |  | 6 | 45929 | 45929 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44846 | 45929 | 45930 | Ashwin | NA | Sean | 45929 | NA | Completed
33 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Jagdeep | 26042 | MSBP-MAUI - Negative amount showing with minus sign not in brackets( ) in Payment history(regression) | Defect Ready For Testing | 0 |  | 3 | 45929 | 45929 | NA | NA | NA | Gursewak | NA | Pull Request 44845: jagdeep.singh/26042-MSBP-MAUI-Negative amount showing with minus sign not in... | 45929 | NA | Ashwin | NA | Sean | 45932 | NA | Completed
34 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Gursewak/Vaishnavi. | 26045 | MSBP-MAUI - Amount field is not right aligned in Add Meal money screen(regression) | Defect Fixed | 0 |  | 3 | 45929 | 45929 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44847?_a=files | 45929 | 45930 | Ashwin | NA | Sean | NA | NA | Completed
35 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 Stretch | Rupesh | 49816 | MSBA - MAUI - Update Login Screen Username Fields | Story Peer Review | 1 |  | 4 | 45930 |  | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44882 | 45930 | [6 empty] | Completed
36 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 | Gursewak | 26049 | MSBP-MAUI- Payment Installment schedule is not cleared after selecting 'Pay in Full' from Payment options(regression) | Defect Fixed | 0 |  | 6 | 45930 | 45930 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44890?_a=files | 45930 | 45931 | Ashwin | NA | Sean | 45931 | Na | Completed
37 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 Stretch | Rupesh | 48146 | MSBA - MAUI - Hide Mode Settings In Prod | Story Peer Review | 1 |  | 2 | 45930 |  | NA | NA | NA |  | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44901 | 45930 |  |  | NA |  |  |  | NA
28 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 Stretch | Amrit | 46089 | MSBA - Maui - Checkout - Cash - Predefined dollar fields do not make sense against the total and cannot be used | Defect Being Fixed | 3 |  | 12 | 45929 | NA | NA | NA | NA
31 | MSB Mobile | 45919 | 45932 | 15.2 M Sprint 3 Stretch | Sambath | 50129 | 50129 MSBA - Automation - Implement MSBA automation similar to MSBP [Timebox] | Story Being Developed | 5 |  | 7 | 45924
32 | MSB Mobile Kaleida | 45919 | 45932 | 15.2 M Sprint 3 Stretch | Jagdeep | 50045 | MSBP - After Adding Student - Show Loading Symbol Until Student is Added to Homescreen | Story Peer Review | 1 |  | 4 | 45930 | 45930 | NA | NA | NA | Rupesh | NA | Pull Request 44884: jagdeep.singh/50045-MSBP-After Adding Student show loading Symbol Until Stude... | 45930 | NA | NA | NA | NA |  | NA | Completed
1 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 | Amrit/Prem/Vaishnavi | 46089 | MSBA - Maui - Checkout - Cash - Predefined dollar fields do not make sense against the total and cannot be used | Story Completed | 1 |  | 12 | 45929 | NA | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44951?_a=files | 45726 | 45971 | Jagdeep | Changes in Code | Sean | 45971 | NA | NA
2 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 | Sambath | 50129 | 50129 MSBA - Automation - Implement MSBA automation similar to MSBP [Timebox] | Story Completed | 2 |  | 7 | 45924 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/45034 | 45938 | 45944 | Ashwin | NA | Owen | 45944 | NA | NA
3 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 | Jagdeep | 50045 | MSBP - After Adding Student - Show Loading Symbol Until Student is Added to Homescreen | Story Completed | 0.5 |  | 8 | 45930 | 45933 | NA | NA | NA | Rupesh | NA | Pull Request 44884: jagdeep.singh/50045-MSBP-After Adding Student show loading Symbol Until Stude... | 45930 | NA | Ashwin | NA | Sean | 45937 | Why is the state being set to Loading here? | Completed
4 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 | Jagdeep/Vaishnavi | 26042 | MSBP-MAUI - Negative amount showing with minus sign not in brackets( ) in Payment history(regression) | Defect Fixed | 0.5 |  | 3 | 45929 | 45929 | NA | NA | NA | Gursewak | NA | Pull Request 44845: jagdeep.singh/26042-MSBP-MAUI-Negative amount showing with minus sign not in... | 45929 | NA | Ashwin | NA | Sean | 45932 | NA | Completed
5 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 | Rupesh/Vaishnavi | 49816 | MSBA - MAUI - Update Login Screen Username Fields | Story Completed | 0.5 |  | 4 | 45930 | 45932 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/44882 | 45930 | 45931 | Ashwin | NA | Sean | 45932 | NA | Completed
6 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 | Jagdeep | 24706 | MSBP - Maui - Cart reorder when donation is added on multidistrict (pre-existing) | Defect Fixed | 2 |  | 6 | 45933 | 45933 | NA | NA | NA | Amrit | NA | Pull Request 44949: jagdeep.singh/24706-MSBP-Maui-Cart reorder when donation is added on multidis... | 45726 | 45937 | Ashwin | NA | Sean | 45937 | NA | Completed
7 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 | Gursewak | 25569 | MSBP - Messages - Icon Opening In Stack | Defect Fixed | 2 |  | 6 | 45933 | 45933 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/44948?path=/MSB.Parent/ViewModels/BaseViewModel.cs&discussionId=291404&_a=files | 45933 | 45937 | Ashwin | NA | Sean | 45937 | NA | Completed
8 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 | Jagdeep/Vaishnavi | 50227 | MSBP - Donation Products - Show Only District Donation Products | Story Completed | 3 | N | 14 | 45936 | 45937 | NA | NA | NA | Gursewak | No need to required else condition,Add null check if BasketItems is null. | Pull Request 45008: jagdeep.singh/50227-MSBP-Donation Products-Show Only District Donation Products | 45938 | 45939 | Ashwin | NA | Sean | 45939 | NA | Completed
9 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 | Rupesh | 26075 | MSBA - Students returning in the invoices tab when not have active invoices | Defect Needs More Info | 2 |  | 6 | 45936 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 | Vaihnavi/Prem | 45828 | MSBA - Maui - Close Out Workflow (Logic - Test Only) | Story Completed | 2 |  | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 | Vaihnavi/Prem | 48381 | MSBA - Maui - Settings Areas that have not been tested yet | Story Completed | 3 |  | 28 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 | Gursewak | 26073 | MSBA - MAUI - unable to drag to sort | Defect Peer Review | 2 |  | 18 | 45936 | 45938 | NA | Na | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45020?_a=files | 45938
13 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 | Rupesh | 48146 | MSBA - MAUI - Gate Mode Settings In Prod | Story Peer Review | 2 |  | 15 | 45937 |  | NA | NA | Na | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45050 | 45939 | 45940 | Ashwin | Renaming few fields | Sean | 45944 | Keep the Firebase props at right place. | Completed
14 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Gursewak | 24714 | MSBP - MAUI- Error message missing when cannot verify account | Defect Rejected | 0 |  | 3 | 45939 | 45939 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Gursewak/Ashwin | 26105 | MSBA - MAUI - Enabling 'Allow oversell' toggle in settings and doing checkout for a product throws error | Defect Being Fixed | 2 |  | 6 | 45940 | 45940 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Na | NA | NA
16 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Rupesh | 26104 | MSBA - MAUI - App crash on switching between the Close out entire day toggle or select a specific shift | Defect Fixed | 2 |  | 12 | 45940 | 45943 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45086 | 45578 | 45943 | Ashwin | NA | Avery | 45944 | NA | Completed
17 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Sambath | 26117 | 26117 MSBP - PictureStorageService - Null Pointer | Defect Fixed | 0.5 |  | 3 | 45943 | 45943 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45089 | 45943 | 45943 | Ashwin | NA | Sean | NA | NA | NA
18 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Sambath | 26097 | MSBA - MAUI - App crash while editing amount in Starting cash text box in closeout | Defect Being Fixed | 2 |  | 5 | 45944 |  | NA | NA | NA | NA | NA
19 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Rupesh | 26092 | MSBA - MAUI - App crash after opening/closing Webform product | Defect Being Fixed | 2
20 | MSB Mobile Kaleida | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Amrit/Jagdeep/Sambath | 50285 | MSBP - Get Existing Automation to Run in IOS | Defect Being Fixed | 5 |  |  | 45936
21 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Vaishnavi/Prem | 26084 | MSBA - MAUI-A -Check to reconcile is cut off, going back and forth it is not showing the cut off text in 'Count' screen | Defect Fixed | 0.5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
22 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Vaishnavi/Prem | 26112 | MSBA - MAUI - Enabling product search from settings screen is not showing the product for all the student. | Defect Fixed | 2 |  | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
23 | MSB Mobile | 45933 | 45946 | 15.3 M Sprint 1 Stretch | Vaishnavi/Prem | 26083 | MSBA - MAUI - I/A - Cash & Check total is not sum up the check total. Displays only the Cash Value in the Cash & Check Totals field | Defect Fixed | 1 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 | Sambath/Prem/Vaishnavi | 26073 | MSBA - MAUI - unable to drag to sort | Defect Fixed | 2 |  | 55 | 45936 | 45938 | NA | Na | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45020?_a=files | 45938 | 45938 | Ashwin | NA | Sean | NA | NA | Completed
2 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 | Rupesh | 48146 | MSBA - MAUI - Gate Mode Settings In Prod | Story Completed | 2 |  | 15 | 45937 | 45947 | NA | NA | Na | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45050 | 45939 | 45940 | Ashwin | Renaming few fields | Sean | 45944 | Keep the Firebase props at right place. | Completed
3 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 | Sambath/Prem | 26097 | MSBA - MAUI - App crash while editing amount in Starting cash text box in closeout | Defect Fixed | 1 |  | 17 | 45944 | 45944 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 | Rupesh/Prem | 26092 | MSBA - MAUI - App crash after opening/closing Webform product | Defect Fixed | 0.5 |  | 18 | 45945 | 45947 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45152 | 45946 | 45947 | Ashwin | NA | Sean | 45947 | NA | Completed
5 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 | Amrit/Jagdeep/Gursewak/Sambath | 50285 | MSBP - Get Existing Automation to Run in IOS | Story Completed | 3 |  |  | 45936 | 45947 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/45165 | 45946 | NA | Jagdeep | NA | Ashwin | NA | Regarding Code usage of Thread.Sleep & Some conditions. Which are explained in comments and resolved | NA
6 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 | Vaishnavi | 26126 | MSBA - MAUI - Unable to do any action once entering in the Other Amount Field for the Meal Payment and later on app is getting crashed | Defect Fixed | 0.5 |  | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 | Jagdeep/Prem | 26138 | MSBA - MAUI - App crash when deleting amount from partial payment amount field in Invoice | Defect Fixed | 2 |  | 10.5 | 45947 | 45947 | NA | NA | NA | Sambath | NA | Pull Request 45186: jagdeep.singh/26138-MSBA-MAUI-App crash when deleting amount from partial pay... | 45947 | 45947 | Ashwin | NA | Avery | 45947 | NA | Completed(Ashwin)
8 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 | Gursewak/Prem | 24829 | MSBP - MAUI - long entry information on webform does not wrap to a second line | Defect Fixed | 3 |  | 23 | 45947 | 45953 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45235?_a=files | 45953 | 45953 | Ashwin | NA | Avery | 45954 | NA | Done
9 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 | Prem/Avery | 26061 | MSBA - MAUI - filters resetting on refresh page | Defect Fixed | 0.5 |  | 5 | 45944 | 45945 | NA | Na | NA | Jagdeep | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 | Prem/Avery | 26085 | MSBA-MAUI-A- Clicking on the dropdown icon in 'Select a shift text box' is not opening the shifts | Defect Fixed | 2 |  | 7 | 45945 | 45946 | NA | Na | NA | Jagdeep | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 | Vaishnavi/Chandler/Prem | 50414 | MSBP – Meal Money – Navigation from Home Picture Box to Meal Money Screen and Add Photo Functionality | Story Being Developed | 2
12 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 | Amrit | 26087 | MSBA-MAUI- A - Select i icon from shift details from closeout, Dismiss is not showing in Blue displays as Black. | Defect Rejected | 0.5 |  | NA | 21/10/2025 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 | Jagdeep | 26090 | MSBA - MAUI - Close day step 2 not populate information for non-shift users | Defect Rejected | 2 | N | 4 | 21/10/2025 | 21/10/2025 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 | Rupesh/Vaishnavi | *5 | MSBA-MAUI- A - Button Text is not shown as Reconciled, once the reconciled done. Displays only on clicking back and forth. | Defect Ready For Testing | 1 |  | 13 | 45951 | 45954 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45229 | 45952 | 42301 | Jagdeep | NA | Avery | 45954 | Use data triggers, instaed implementing in view model. | Completed
15 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 | Amrit/Prem | 26086 | MSBA - MAUI -iOS- In iphone 'i' icon is not showing in the shift details in closeout | Defect Fixed | 0.5 |  | 6.5 | 21/10/2025 | 21/10/2025 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45212 | 21/10/2025 | 22/10/2025 | Ashwin | NA | NA | 22/10/2025 | NA | NA
16 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 | Jagdeep/Prem | 26091 | MSBA - MAUI - Close Day step 4 offset/short box missing () when negative | Defect Fixed | 1 |  | 8.5 | 45951 | 45952 | NA | NA | NA | Rupesh | NA | Pull Request 45225: jagdeep.singh/26091-MSBA-MAUI-Close Day step 4 offset short box missing () wh... | 45952 | 45952 | Ashwin | NA | Avery | 45954 | NA | Completed
17 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Amrit | 26168 | Mobile - MSBP - AddFundsMainViewModel Null Pointer | Defect Fixed | 1 |  | 1 | 22/10/2025 | 23/10/2025 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45227 | NA | NA | Ashwin | NA | NA | 24/10/2025 | NA | Completed
18 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Jagdeep | 23799 | MSBP - Cart Clears After Updating Expired Payment Method | Defect Needs More Info | 3 |  | 1 | 45952 | NA | NA | NA | NA | NA | NA |  | NA | NA | NA | NA | NA | NA | NA | NA
19 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Amrit/Prem | 25179 | MSBA - MAUI -Store screen - filters not showing all headers | Defect Fixed | 2 |  | 13 | 22/10/2025 | 23/10/2025 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45256 | 23/10/2025 | NA | Ashwin | NA | NA | 27/10/2025 | NA | NA
20 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Jagdeep/Prem | 26146 | MSBA - MAUI - After entering and deleting the custom amount, predefined values are not getting enabled in Cash Payment | Defect Fixed | 2 |  | 9 | 45952 | 23/10/2025 | NA | NA | NA | Gurusewak | NA | Pull Request 45257: jagdeep.singh/26146-MSBA-MAUI-After entering and deleting the custom amount,... | 45953 | NA | Ashwin | NA | Avery | 45955 | NA | Completed
21 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Rupesh | 26128 | MSBA - MAUI - iOS - rotating from portrait to landscape back to portrait removes information at bottom | Defect Ready For Testing | 2 |  | 18 | 45952 | 45957 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45310 | 45957 | 45957 | Ashwin | NA |  |  | NA | Completed
22 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Gursewak/Vaishnavi | 49298 | MSBA - Display No Invoices on Students without Invoices - Post GA | Story Completed | 1 |  | 4 | 45957 | 45957 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45309?_a=files | 45957 | 45957 | Ashwin | NA | Avery | 45957 | NA | Completed
23 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Gursewak | 26057 | MSBP - MAUI - iOS - AutoPay information sheet not sized to text | Defect Peer Review | 0 |  |  | 45957 | 45958 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45337?_a=files | 45958 | 45958 | Ashwin | NA
24 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Jagdeep | 26107 | MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered | Defect Peer Review | 0.5 |  | 4 | 45958 | 45958 | NA | NA | NA | Gursewak | NA | Pull Request 45332: jagdeep.singh/MSBP-MAUI-Meal Money Settings in Add student workflow heading n... | 45958 | NA | Ashwin | NA | NA | NA |  | Completed
25 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Rupesh | 26056 | MSBP- MAUI - iOS - Autopay subscription terms sheet not sized to text | Defect Being Fixed | 0.5 |  |  | 45957
26 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Jagdeep | 26213 | MSBP - White Header - Android - Cannot See Icons or Top Bar | Defect Being Fixed | 2 |  | 2 | 45958 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
27 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Avery/Prem | 25645 | MSBA - MAUI - Android - In close day while opening the keyboard, see splash screen [Timebox] | Defect Fixed | 0.5 |  | 3.5 | 45958 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
28 | MSB Mobile Kaleida | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Prem | 26075 | MSBA - Students returning in the invoices tab when not have active invoices | Defect Fixed | 2 |  | 8.5 | 45958
29 | MSB Mobile | 45947 | 45960 | 15.3 M Sprint 2 Stretch | Vaishnavi | 49292 | MSBA - Maui - Remove Required * from Close Out Starting Cash | Story Completed | 0.5
30 | MSB Mobile |  |  | 15.3 M Sprint 2 Stretch | Amrit | 26107 | MSBP - MAUI - Meal Money Settings in Add student workflow heading not centered (15.3) | Defect Being Fixed | 0.5 |  |  | 31/10/2025 | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile Kaleida | 45975 | 45987 | 26.1 M Sprint 1 | Jagdeep | 50462 | MSBA - Automation - Meals Page | Story Peer Review | 2 |  | 14 | 45972 | 45986 | NA | NA | NA | Sambath | NA | Pull Request 45696: jagdeep.singh/50462-MSBA-Automation-Meals Page | 45974 | NA | Ashwin | NA | NA | NA | NA | NA
2 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 | Rupesh | 50460 | MSBA - Automation - User Settings – Edit and Verify | Story Completed | 1 |  | 37 | 45961 | 45980 | NA | NA | NA | Sambath | estContext.TestException params is missing like below code, please add it, IsSave = false, make as default params, why this identifier are passing as args? | https://dev.azure.com/heartlandschools/Mobile/_git/MobileAutomation/pullrequest/45673 | 45975 | 45980 | Ashwin | NA | Owen | 45980 | NA | Completed
3 | MSB Mobile Kaleida | 45975 | 45987 | 26.1 M Sprint 1 | Gursewak/vaishnvi | 50876 | MSBP - Store - Dual Enrollment - Not Displaying Expected Stores | Story Completed | 2 |  | 33 | 45975 | 45980 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45733 | 45979 | 45979 | Ashwin | NA | Avery | 45981 | Add a check for enrollment status at the beginning of the Where condition to filter out inactive enrollments before checking school matches. Reuse the district variable to avoid unnecessary repeated lookups Extract the logo query to a variable so it's only executed once per enrollment. | NA
4 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 | Rupesh/Vaishnavi | 23091 | MSBP - Announcements/Notifications - Showing as Received on Mon Jan 1 | Defect Fixed | 0.5 |  | 18.25 | 45974 | 45975 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45701 | 45975 | 45978 | Ashwin | NA | Awery | 45978 | NA | Completed
5 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 | Sambath | 49777 | MSBP - Retain Meal Money Selection | Story Being Developed | 1 |  | 12 | 45974 | NA | NA | NA | NA | Gurwewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45785 | 18/11/2025 | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 | Vaishnavi/Prem | 50880 | MSBP CA - Regression/Smoke Test Against Staging 15.3 RC | Story Completed | 1 |  | 4 | 45975 | 45975 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile Kaleida | 45975 | 45987 | 26.1 M Sprint 1 | Jagdeep | 50869 | MSBP - Get Existing Automation to Run in IOS: AssignGreenlight | Story Completed | 2 |  | 8 | 45975 | 45978 | NA | NA | NA | Sambath | NA | Pull Request 45726: jagdeep.singh/50869-MSBP-Get Existing Automation to Run in IOS AssignGreenlight | 45975 | 45979 | Ashwin | NA | Owen | 45979 | NA | Completed(With Ashwin)
8 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 | Sambath | 26316 | 26316 MSBAnywhere Android Version 14.7.1.147377 Missing Expected Cash on MSBA Close Out Report | Defect Being Fixed | 3 |  | 12 | 45975 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile Kaleida | 45975 | 45987 | 26.1 M Sprint 1 | Prem/Chandler/Vaishnavi | 50418 | MSBP - Deep linking - Finish Remaining App Intent Links (15.4) | Story Completed | 1 |  | 31.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile Kaleida | 45975 | 45987 | 26.1 M Sprint 1 | Amrit | 26327 | MSBP - MAUI - iOS -Contact info drawer not showing in Greenlight when selecting Contact Greenlight Support | Defect Being Fixed | 2 |  | 13 | 19/11/2025 | NA | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45865 | 21/11/2025 | NA | NA | NA | NA | NA | NA | Na
11 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 | Sambath/Prem | 50841 | MSBP - AgentForce - Web View | Defect Needs More Info | 3 |  | 6 | 45981 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile Kaleida | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Jagdeep | 26324 | MSBP - MAUI - Homescreen not loading the data when assigning/un-assigning GL and relogging in again. | Defect Fixed | 1 |  | 6 | 45981 | 45981 | NA | NA | NA | Rupesh | NA | Pull Request 45835: jagdeep.singh/26324-MSBP-MAUI-Homescreen not loading the data when assigning... | 45981 | 45983 | Ashwin | NA | Sean | 45983 | NA | Completed
13 | MSB Mobile Kaleida | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Gursewak | 50970 | MSBP - Tickets - MyTickets update in Hamburger and Events Card | Story Peer Review | 2 |  | 23 | 45981 | 45987 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45944 | 45987 | 45993 | Sambath | NA | Avery | 45993 | NA | NA
14 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Rupesh | 50972 | MSBP - Tickets - My Tickets Drawer | Story Being Developed | 8 |  | 20 | 45982 |  | NA | NA | NA
15 | MSB Mobile Kaleida | 45975 | 45987 | 20.1 M Sprint 1 Stretch | Jagdeep | 50971 | MSBP - Tickets - Update Events Screen with My Tickets | Story Being Developed | 5 | 0 | NA | 45982 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Rupesh /vaishnavi | 26132 | MSBP - MAUI - Checkout districts not in the same order as the cart districts | Defect Fixed | 1 |  | 9 | 45980 | 45982 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45847 | 45982 | 45982 | Ashwin | NA | Sean | 45982 | NA | Completed
17 | MSB Mobile Kaleida | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Gursewak | 23901 | MSBA - Sales Tag - Close Out - Not showing on reports when Shift Mode is not used | Defect Fixed | 1 |  | 6 | 45981 | 45981 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45846 | 45981 | 45981 | Ashwin | NA | Avery | 45982 | NA | NA
18 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Rupesh/Prem | 26264 | MSBA MAUI - Iphone - Cancel button alignment is not proper in Close Out - Step 1 Screen | Defect Fixed | 1 |  | 7 | 45975 | 45978 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45730 | 45975 | 45978 | Ashwin | NA | Awery | 45978 | NA | Completed
19 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Rupesh/Prem | 26323 | MSBP MAUI - I/A - Info Message shows in cut off mode, when there are no students in Add Meal Money Page | Defect Fixed | 1 |  | 13 | 45978 | 45981 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45816 | 45980 | 45981 | Ashwin | NA | Awery | 45981 | NA | NA
20 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Amrit | 26335 | MSBA - MAUI - District name overlapping when it is greater than 43 characters | Defect Peer Review | 0.5 |  | 8 | 45982 | 45985 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/45917 | NA | NA | NA | NA | NA | NA | NA | NA
21 | MSB Mobile | 45975 | 45987 | 26.1 M Sprint 1 Stretch | Amrit | 26147 | MSBP - MAUI - Stock options in Donation is not showing when it is added. Going back and front it is showing | Defect Being Fixed | 0 |  | 7 | 45986 | 45987 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45930 | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 | Jagdeep | 50462 | MSBA - Automation - Meals Page | Story Completed | 3 |  | 19 | 45972 | 45986 | NA | NA | NA | Sambath | Total PR Comments: 5 1. EnableCartPreviewBeforeCheckout().SettingsPageSaveButtonAction() method is there in SettingsPage, please use that method 2. remove this method, Use settings page 3. removed this loop, use FindByText() 4. remove the try catch block, and use FindUntilElementFound() 5. User Assert.Fail("") instead of Exception | Pull Request 45696: jagdeep.singh/50462-MSBA-Automation-Meals Page | 45974 | NA | Ashwin | NA | Owen | 46001 | NA | NA
2 | MSB Mobile | 45988 | 46002 | 26.1 M Sprint 2 | Sambath/Gursewak/Jagdeep/Prem | 49777 | MSBP - Retain Meal Money Selection | Story Completed | 5 |  | 97.5 | 45974 | 45996 | NA | NA | NA | Sambath | Total PR Comments: 5 1. Why this amount.Parent = this ? 2. Why this prop? 3. No need to get from each, you can delete all cart items from the MealBasketItems 4. use GetExistingMealMoneyFromCart() method for basket Meal item 5. Move the logic for deleting basket items to a common place in the BaseViewModel, as this code is duplicated multiple times. | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45785 | 45974 | 45996 | Ahwin | NA | Avery | 45996 | Total PR Comments: 24 1. The nested loop through FundingAmountList is unnecessary. You already have the amount from the cart, just check if it matches a preset button, and if not, set the 'Other' field. The current implementation processes the IsOtherAmount block multiple times per student when it should only run once. 2. This PR adds cart retention to AddFundsViewModel, but StudentDetailViewModel also has meal money functionality and lacks similar cart restoration logic. Should that be addressed in this PR or tracked separately for consistency? 3. Can you clarify? I don't see cart restoration logic in StudentDetailViewModel. When a user adds meal money from StudentDetailViewModel, navigates to the cart, then clicks 'Continue Shopping', does the selected amount get restored on StudentDetailViewModel like it now does on AddFundsViewModel? If yes, where is that code? If no, we need to add it for consistency. 4. Remove this null check - it's redundant since selectedStudents is already filtered by a LINQ .Where() clause that ensures non-null results. 5. This triple-nested loop has a fundamental logic issue. The innermost filter fundingAmounts.Where(x=> x.StudentKey == item.StudentKey) doesn't work as intended because all items in selectedStudent.FundingAmountList share the same StudentKey. This makes the filter redundant and causes all fundingAmounts for that student to be processed repeatedly for each preset amount button. The logic needs to be refactored to properly match cart items with their corresponding UI elements. 6. Why are you setting IsBusy = false here? This seems unrelated to the meal money retention requirement. Is this fixing a separate bug or could this cause issues if something is actually busy? 7. Is this early return behavior intentional for this feature, or should the deletion continue attempting remaining items even if one fails? 8. The outer parentheses wrapping the entire expression ((FundStudent?.FundAmount > 0) ¦¦ IsEditMealMoneyFromCart) are unnecessary and should be removed for cleaner code. 9. Change FundStudent?.FundingAmountList - to FundStudent.FundingAmountList 10. This checks if (FundStudent?.StudentKey == cartItem.StudentKey) but you already verified FundStudent != null at line 349 inside the outer if condition. Remove the null-conditional. 11. basketItemKeys can be null when GetExistingMealMoneyFromCart() returns null. Add null-conditional: if (basketItemKeys?.Any() ?? false) or check if (basketItemKeys != null && basketItemKeys.Any()) 12. studentsToDelete.Select(s => s.Student.StudentSID) is executed on every iteration of the Where() clause. Move it outside: var studentSIDs = studentsToDelete.Select(s => s.Student.StudentSID).ToList(); then use studentSIDs.Contains(x.StudentKey). 13. The else block is unnecessary - when FundAmount == 0, the code returns at line 245, so the else is redundant. Remove it to reduce nesting. 14. The BackgroundColor value was changed from {x:StaticResource SecondaryDisabledButtonBackgroundColor} to the hardcoded hex value #EAEBEE. This breaks the theming pattern used throughout the app and makes the color unmaintainable. Please restore the StaticResource or explain why it needed to change 15. This property unconditionally returns true. However, AddFundsViewModel and StudentDetailViewModel both check FundAmount > 0 OR if in edit mode. The current implementation allows users to submit with $0. The OnAmountChangedCommand at line 703 calls RaisePropertyChanged(() => IsFundAmountSelect) expecting the property to react to amount changes, but it's hardcoded to true. Compare with the pattern used in the other ViewModels. 16. Returning null instead of an empty list is inconsistent with standard C# patterns and forces all callers to perform null checks. Either change to return new List<MealBasketItem>(); or update the method signature to List<MealBasketItem>? to make the nullable intent explicit. 17. GetExistingMealMoneyFromCart() can return null, but you're calling .FirstOrDefault() directly on it without a null check. Add a null-conditional operator 18. You moved the validation check after creating two lists and iterating through FundStudentList. If validation fails (no amounts selected and not in edit mode), the list creation and loop execution were completely wasted. The original placement was correct - it followed the "fail fast" principle. 19. The ternary operator ? true : false is redundant. The equality comparison already returns a boolean. 20. Remove unnecessary outer parentheses around GetExistingMealMoneyFromCart()?.Any() == true - they serve no purpose. 21. Setting BackgroundColor directly may not trigger UI update. If this doesn't work in testing, you may need RaisePropertyChanged() or a bindable property. Also, cache the resource lookup outside the loop: var whiteColor = (Color)Application.Current.Resources["PrimaryWhiteColor"]; to avoid repeated dictionary lookups. 22. Variable name "item" is too generic. Rename to matchingPresetAmount or presetAmount to clarify what it represents in this context. 23. Excessive nesting (3 levels deep). Use early returns to flatten. This significantly improves readability. 24. Inconsistent brace placement. Fix this formatting. | NA
3 | MSB Mobile | 45988 | 46002 | 26.1 M Sprint 2 | Sambath | 26316 | 26316 MSBAnywhere Android Version 14.7.1.147377 Missing Expected Cash on MSBA Close Out Report | Defect Fixed | 5 |  | 30 | 45975 | 45995 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46030?_a=files | 45994 | 45995 | Ahwin | NA | Avery | 45995 | NA | NA
4 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 | Sambath/Prem | 26327 | MSBP - MAUI - iOS -Contact info drawer not showing in Greenlight when selecting Contact Greenlight Support | Defect Fixed | 1 |  | 73 | 45980 | 45999 | NA | Gursewak | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46082 | 21/11/2025 | NA | Ahwin | NA | Avery | 46001 | Total PR Comments: 4 Use null-conditional operator for consistency with codebase patterns, Extract magic number 600 to named constant, Remove cast by adding GreenlightCards property to ISession interface. GreenlightSupport recreated on every tap. Initialize once in InitializeGreenlightComponents() instead. | Na
5 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 | Gursewak/Rupesh/Vaishnavi | 50970 | MSBP - Tickets - MyTickets update in Hamburger and Events Card | Story Completed | 1 |  | 17.5 | 45981 | 45987 | NA | NA | NA | Sambath | Total 2 1. move to resource file 2. remove this code, no need here | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45944 | 26/11/2025 | 26/11/2025 | Ahwin | NA | Avery | 45993 | NA | NA
6 | MSB Mobile | 45988 | 46002 | 26.1 M Sprint 2 | Rupesh/Prem | 50972 | MSBP - Tickets - My Tickets Drawer | Story Being Developed | 3 |  | 86 | 45982 | 46001 | NA | Amrit | NA | Sambath | Total PR Comments: 5 • remove this comment • where is this logic? • move to resource "Virtual" • rename it as GetTicketEventOrdersResponse • remove this set | Pull Request 46114: 50972-MSBP - Tickets - My Tickets Drawer | 46000 | 46001 | Sambath | NA | Avery | 46001 | Total PR Comments: 3 • This could cause a race condition - Multiple carousel swipes can trigger OnImageLoadedAsync() simultaneously for the same TicketEvent, causing the image to be downloaded and processed multiple times. Wrap the IsImageProcessed check and processing logic in a SemaphoreSlim to ensure only one thread processes each image. Also fix spacing: "if(" should be "if (". • Creating new HttpClient() for each image causes socket exhaustion. Replace with IoC.Current.Resolve<ParentHttpClient>().Client or use a static readonly HttpClient field to reuse connections. • SelectUpcomingEventsTabCommand should use Command instead of AsyncCommand since it only contains synchronous property assignments (no await operations). Change back to: new Command(() => { ... }); and remove async keyword. As an aside, for SelectMyTicketsTabCommand - good catch fixing the pre-existing bug since it contains await Refresh(). | NA
7 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 | Jagdeep/Prem | 50971 | MSBP - Tickets - Update Events Screen with My Tickets | Story Completed | 2 |  | 15 | 45982 | 45989 | NA | NA | NA | Sambath | Total PR Comments: 5 1. You don’t need DataMember at all. If the property name is different, then use [JsonPropertyName("result")] 2. DataContract no need for MAUI 3. MaxPrice is not getting from api, then why you use it here? 4. My Tickets is already available with latest code, please re use it, and remove this resource 5. Do we need min and Max to be assigned a value her | Pull Request 45966: jagdeep.singh/50971-MSBP-Tickets-Update Events Screen with My Tickets | 45988 | NA | Ashwin | Do we need min and Max to be assigned a value here? | Avery | 45996 | Total PR Comments: 6 1. Add a null check for UpdatedTicketsData in the condition: if (eventName != null && UpdatedTicketsData != null). Currently, if UpdatedTicketsData is null when the user taps the ticket indicator, they'll be switched to an empty My Tickets tab which is confusing. 2. Nearly identical CollectionView markup is duplicated here from lines 117-259. The structures differ only in ItemsSource binding (Events vs Tickets), IsVisible binding, AutomationId values, and the My Tickets version is missing the TapGestureRecognizer. This creates maintenance overhead - any UI changes must be applied twice. Consider consolidating with a single CollectionView or extracting the common template. 3. Null-handling with x.Name ?? string.Empty in TryGetValue may not behave as expected when x.Name is null (empty string won't match existing dictionary keys). Consider: !string.IsNullOrEmpty(x.Name) && purchasedTicketCounts.TryGetValue(x.Name, out var count) ? count : 0. 4. EventLocation mapping is incomplete - the Coordinates property is not being populated. This will cause the directions feature to fail since EventDetailsSheet.xaml.cs checks for latitude and longitude values. Compare with the complete mapping in TicketService.cs 5. Can you fix this typo in TicketEvents.cs please, it's "ShoolNumber" but should be "SchoolNumber" 6. This is declared but never used anywhere in the codebase. Consider removing to reduce code clutter. | NA
8 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 | Amrit/Prem | 26335 | MSBA - MAUI - District name overlapping when it is greater than 43 characters | Defect Fixed | 0.5 |  | 35 | 45982 | 45985 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46010 | 45993 | 45728 | Rupesh | NA | Avery | 45789 | Total PR Comments - 3 1 - change to VerticalOptions="Fill". 2 - Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" /> change to VerticalOptions="Fill". Unnecessary nested StackLayout The outer StackLayout with x:Name="TitleGrid" only contains a single HorizontalStackLayout child and provides no layout value. Remove this StackLayout and move its properties (Grid.Column, x:Name, Margin) to the HorizontalStackLayout directly. Also update HorizontalOptions="CenterAndExpand" to HorizontalOptions="Center" on the updated HorizontalStackLayout. 3- Unnecessary Label closing tag The DistrictLabel doesn't have any child content, so it should use a self-closing tag instead of separate opening/closing tags: VerticalOptions="Center" /> | NA
9 | MSB Mobile | 45988 | 46002 | 26.1 M Sprint 2 | Amrit /Gursewak/Prem | 26147 | MSBP - MAUI - Stock options in Donation is not showing when it is added. Going back and front it is showing | Defect Fixed | 1 |  | 21.75 | 45986 | 45987 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/45930 | 45759 | 45820 | Ashwin | NA | Avery | 45820 | NA | NA
10 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 | Gursewak/Sambath | 25751 | MSBP - When selecting a list box there is a delay which does not always select option (regression) | Defect Rejected | 3 |  | 4 | 45987 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 Stretch | Chandler/Prem | 51025 | MSBP – Update MSB Activities Icon to Avoid Duplication with Tickets Icon | Story Completed | 0.5 |  | 1.75 | 45987 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 Stretch | Jagdeep/Vaishnavi | 45174 | MSBA - Searching for students with Scanner does not add them to recent student list (hardware) | Story Completed | 2 |  | 6 | 45992 | 45992 | NA | NA | NA | Gursewak | NA | Pull Request 45977: jagdeep.singh/45174-MSBA-Searching for students with Scanner does not add the... | 45992 | NA | Ashwin | NA | Avery | 46001 | NA | NA
13 | MSB Mobile | 45988 | 46002 | 26.1 M Sprint 2 Stretch | Vaishnavi | 51132 | MSBA - Enabling Allow Oversell toggle in settings and doing checkout for product throws error (Xamarin) | Story Completed | 1 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 Stretch | Amrit/Gursewak | 50197 | MSBP - Make Links Clickable in Notifications | Story Peer Review | 3 |  | 12 | 45942 | 46003 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46172 | 45669 | NA | NA | NA | NA | NA | NA | NA
15 | MSB Mobile Kaleida | 45988 | 46002 | 26.1 M Sprint 2 Stretch | Jagdeep/Rupesh | 51114 | Mobile - SHA2 Update | Story Completed | 2 |  | 4 | 46002 | 46002 | NA | NA | NA | NA | NA | Pull Request 46164: jagdeep.singh/51114-Mobile-SHA2 Update | 46002 | 46002 | Sambath | NA | Sean | 46002 | NA | NA
16 | MSB Mobile | 45988 | 46002 | 26.1 M Sprint 2 Stretch | Sambath | 50984 | 50984 MSBA - .NET10 & Package Updates | Story Being Developed | 3 |  | 5 | 46002 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile | 46003 | 46030 | 26.1 M Sprint 3 | Rupesh/Gursewak/Prem/Vaishnavi | 50972 | MSBP - Tickets - My Tickets Drawer | Story Completed | 3 |  | 86 | 45982 | 46001 | NA | Amrit | NA | Sambath | move to resource "Virtual" rename it as GetTicketEventOrdersResponse remove this set remove this comment | Pull Request 46114: 50972-MSBP - Tickets - My Tickets Drawer | 46000 | 46001 | Sambath | Total: 4 1: remove this comment 2: move to resource "Virtual" 3: rename it as GetTicketEventOrdersResponse 4: remove this set | Avery | 46001 | Total: 3 1: SelectUpcomingEventsTabCommand should use Command instead of AsyncCommand since it only contains synchronous property assignments (no await operations). Change back to: new Command(() => { ... }); and remove async keyword. As an aside, for SelectMyTicketsTabCommand - good catch fixing the pre-existing bug since it contains await Refresh(). 2: Creating new HttpClient() for each image causes socket exhaustion. Replace with IoC.Current.Resolve<ParentHttpClient>().Client or use a static readonly HttpClient field to reuse connections. 3: This could cause a race condition - Multiple carousel swipes can trigger OnImageLoadedAsync() simultaneously for the same TicketEvent, causing the image to be downloaded and processed multiple times. Wrap the IsImageProcessed check and processing logic in a SemaphoreSlim to ensure only one thread processes each image. Also fix spacing: "if(" should be "if (". | NA
2 | MSB Mobile | 46003 | 46030 | 26.1 M Sprint 3 | Sambath/Rupesh/Jagdeep | 50984 | 50984 MSBA - .NET10 & Package Updates | Story Being Developed | 3 |  | 206 | 45973 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | working on it, fixing the biding issues | NA
3 | MSB Mobile | 46003 | 46030 | 26.1 M Sprint 3 | Vaishnavi/Prem | 51219 | MSBP - Full Regression 26.1 | Story Completed | 8 |  | 75.5 | 46003 | 46021 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | MSB Mobile Kaleida | 46003 | 46030 | 26.1 M Sprint 3 | Amrit/Gursewak/Prem | 50197 | MSBP - Make Links Clickable in Notifications | Story Completed | 3 |  | 38 | 45942 | 46003 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46172 | 45669 | 17/12/2025 | Sambath | NA | NA | 17/12/2025 | NA | NA
5 | MSB Mobile Kaleida | 46003 | 46030 | 26.1 M Sprint 3 | Gursewak/Amrit/Prem | 26105 | MSBA - MAUI - Enabling 'Allow oversell' toggle in settings and doing checkout for a product throws error | Defect Fixed | 2 |  | 33 | 45942 | 16/12/2025 | NA | Sambath | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46247 | 15/12/2025 | 18/12/2025 | Sambath | NA | Sean | 18/12/2025 | NA | NA
6 | MSB Mobile Kaleida | 46003 | 46030 | 26.1 M Sprint 3 | Jagdeep/Vaishnavi | 26440 | MSBA - MAUI - Recent student list showing the same student multiple times | Defect Fixed | 2 |  | 6 | 46006 | 46006 | NA | NA | NA | Sambath | NA | Pull Request 46221: jagdeep.singh/26440-MSBA-MAUI-Recent student list showing the same student mu... | 46006 | 46007 | NA | NA | Sean | 46007 | NA | Completed
7 | MSB Mobile Kaleida | 46003 | 46030 | 26.1 M Sprint 3 | Vaishnavi/Gurusewak/Amrit | 51005 | MSBP - Tickets - Redeemed Ticket UI Update (26.2) | Story Completed | 3 |  | 14 | 46015 | 46017 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46370 | 46017 | 46017 | NA | NA | Sean | 46019 | NA | Completed
8 | MSB Mobile Kaleida | 46003 | 46030 | 26.1 M Sprint 3 | Jagdeep | 51029 | MSBA - Automation - Store Page | Story Completed | 5 |  | 18 | 46007 | 46009 | NA | NA | NA | Sambath | NA | Pull Request 46295: jagdeep.singh/51029-MSBA-Automation-Store Page | 46009 | NA | Sambath | NA | Owen | 46028 | I changed this to show how these methods should be addressed. We should be able to run all these methods by themselves. I had to change one from private to public. Please check the rest and make sure they follow this approach. | Completed
9 | MSB Mobile Kaleida | 46003 | 46030 | 26.1 M Sprint 3 | Amrit/Prem | 49011 | MSBP - Tickets - Share Ticket Info (26.2) | Story Completed | 3 |  | 31.5 | 46008 | 22/12/2025 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46335 | 46013 | 23/12/2025 | Jagdeep | PR Internal Comments - 3 -We have already resource value for Event Details Please remove new one and use existing "EventDetails". -Please remove Padding="0". -Please use TextColor="{StaticResource TitleBlackColor}"> Instead of color code. | Sean | 23/12/2025 | NA
10 | MSB Mobile | 46003 | 46030 | 26.1 M Sprint 3 | Vaishnavi | 51220 | MSBA - Smoke Test | Story Completed | 2 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | MSB Mobile | 46003 | 46030 | 26.1 M Sprint 3 | Vaishnavi | 51221 | MSBP CA - Regression/Smoke Test Against Staging 26.1 RC | Story Completed | 1 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | MSB Mobile | 46003 | 46030 | 26.1 M Sprint 3 | Amrit | 50973 | MSBP - Tickets - My Tickets - QR Code/Barcode Ticket (26.1) | Story Completed | 3 |  | 10.5 | 23/12/2025 | 23/12/2025 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46348 | 23/12/2025 | 23/12/2025 | Jagdeep | NA | Sean | 23/12/2025 | NA | NA
12 | MSB Mobile | 46003 | 46030 | 26.1 M Sprint 3 | Amrit/Rupesh/Prem | 26498 | MSBP - Android - Tickets - Sheets stack when multiple taps occur (regression) | Defect Fixed | 0 |  | 0 | 26/12/2025 | 46023 | Na | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46389 | 31/12/2025 | 46143 | Ashwin | NA | Sean | 46143 | NA | NA
13 | MSB Mobile | 46003 | 46030 | 26.1 M Sprint 3 | Sambath/Gursewak/Amrit/Vaishnavi | 50983 | 50983 MSBP - .NET10 & Package Updates (26.2) | Story Completed | 3 |  | 63.5 | 26/12/2025 | 46174 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46398 | 31/1/2026 | 46174 | Ashwin | NA | Sean | 46174 | NA | NA
14 | MSB Mobile Kaleida | 46003 | 46030 | 26.1 M Sprint 3 | Gursewak/Rupesh/Vaishnavi | 26502 | 26502 MSBP - MAUI - Single tickets are allowing to scroll horizontally and multiple tickets not showing the scroll (regression) | Defect Fixed | 0 |  | 6 | 29/12/2025 | 29/12/2025 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46409 | 29/12/2025 | 29/12/2025 | Amrit | NA | Sean | 46024 | NA | NA
15 | MSB Mobile Kaleida | 46003 | 46030 | 26.1 M Sprint 3 | Gursewak/Vaishnavi | 26504 | 26504 MSBP - iOS- Pay for More students - Add to cart button color is not displaying in a disabled state in iOS (regression) | Defect Fixed | 0 |  | 6 | 30/12/2025 | 30/12/2025 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46408 | 30/12/2025 | 30/12/2025 | Sambath | NA | Sean | 46025 | NA | NA
1 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 | Sambath/Rupesh/Jagdeep/Prem | 50984 | 50984 MSBA - .NET10 & Package Updates | Story Completed | 3 |  | 21 | 46002 | 46031 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46379 | 46022 | 46034 | Ashwin | NA | NA | NA | NA | NA
2 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 | Gursewak/Amrit/Prem | 26482 | MSBA - MAUI - Meal Payment Page other box is blank/white when typing | Defect Fixed | 2 |  | 8.5 | 46030 | 46034 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46575 | 46034 | 46034 | Sambath | NA | Sean | 46034 | NA | NA
3 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 | Amrit/Vaishnavi | 26552 | MSBP - MAUI - iOS - .net10 - My Tickets -Tickets showing in vertical box instead of showing the ticket details | Defect Fixed | 2 |  | 8 | 46031 | 46031 | NA | NA | NA | Sambarth | Na | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46543 | 46031 | 46031 | Sambath | NA | NA | 46031 | NA | NA
4 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 | Prem/Chandler | 26514 | MSBP - My tickets - Multiple Buttons greyed out when selecting a single button (regression) | Defect Fixed | 0.5 |  | 5.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 | Rupesh/Prem | 26555 | MSBP - MAUI - iOS - .net10 - Promocode text box is not showing any validation error when invalid code is entered | Defect Fixed | 2 |  | 7 | 46031 | 46031 | NA | NA | NA | Sambath | FillAndExpand is depreciated, Please use "Fill" | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46544 | 46031 | 46031 | Ashwin | NA | Sean | 46031 | NA | NA
6 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 | Jagdeep | 26553 | MSBP - MAUI - iOS - .net10 - Hamburger menu Header disappears when navigating back to Homescreen from Tickets screen | Defect Blocked | 3 |  | 11 | 46031 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 | Sambath | 20562 | 20562 MSBP - Unable to Pay Installment Plan after Due Date Passes(verify | Defect Fixed | 1 |  | 19.5 | 46034 | 46036 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 | Sambath/Prem | 26549 | MSBP - MAUI - Android - .net10 - No spacing between the text and the save button in Partial Payment and Meal money Other amount field | Defect Fixed | 2 |  | 12 | 46034 | 46036 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46618 | 46035 | 46037 | Ashwin | NA | Ashwin | 46035 | NA | NA
9 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Gursewak/Prem | 26548 | MSBP - MAUI - iOS - .net10 - Program Fees shows in cut off mode after credit card selection | Defect Fixed | 1 |  | 10 | 46034 | 46034 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46578 | 46034 | 46034 | Sambath | NA | Sean | 46034 | NA | NA
10 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Gursewak/vaishnavi | 26551 | MSBP - MAUI - iOS/Android - .net10 - When photo is captured, cropping/saving screen is displaying in blue/white background [Timebox] | Defect Fixed | 2 |  | 13 | 46035 | 46038 | NA | NA | NA | Na | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46673 | 46037 | 46038 | Ashwin | NA | Avery | 46038 | NA | NA
11 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Rupesh | 26557 | MSBA - MAUI - iOS - Closeout screen not auto-rotated to Landscape mode | Defect Rejected | 2 |  | 6 | 46035 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Amrit/Prem | 26550 | MSBP - MAUI - Android - .net10 - Cart icon and notification bell icon are not aligned in a straight line | Defect Fixed | 2 |  | 11 | 46035 | 14/1/2026 | NA | NA | NA | Gursewak | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46641 | 46036 | 46038 | Sambath | NA | Sean | 46036 | NA | NA
13 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Jagdeep | 26556 | MSBA - MAUI- Android -Meals and Ticket tabs are not displaying when selecting Store,Invoice,Meals and Tickets under Enabled Menu item in User Settings | Defect Ready For Testing | 3 |  | 14 | 46035 | 46038 | NA | NA | NA | Gursewak | NA | Pull Request 46694: jagdeep.singh/26556-MSBA-MAUI-Android-Meals and Ticket tabs are not displayin... | 46038 | NA | Ashwin | NA | Avery | 46044 | These routes are already defined in AppShell.xaml as ShellContent elements with Route attributes (Store, Invoices, Meals, InPerson). When routes are declared in XAML, you don't need to register them again in code. Routing.RegisterRoute() is only needed for pages that are NOT declared in the Shell XAML. | NA
14 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 | Rupesh/Vaishnavi | 26591 | MSBP- iOS/Android - All Webforms Product causes a crash (.net10/datepicker?) | Defect Fixed | 2 |  | 8 | 46036 | 46036 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46654 | 46036 | 46038 | Ashwin | NA | Sean | 46037 | NA | NA
15 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 | Amrit/Vaishnavi | 26593 | MSBP - Android - Add Another Student is causing resource not found on several sections | Defect Fixed | 2 |  | 10 | 46038 | 46041 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46719 | 46041 | 46043 | Ashwin | NA | Sean | 46043 | NA | NA
16 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Gursewak/Vaishnavi | 26547 | MSBP - MAUI - Android - .net10 - Shopping cart, checkout, Refund request , Meal money transfer Headers are not center aligned | Defect Fixed | 3 |  | 15 | 46038 | 46042 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46721?_a=files | 46042 | 46042 | Ashwin | NA | Sean | 46042 | NA | NA
17 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Jagdeep | 26506 | MSBA - MAUI - phones - UI issue card reader status and card mode overlap | Defect Blocked | 2 |  | 10 | 46038 | 46041 | NA | NA | NA | Rupesh | NA | jagdeep.singh/26506-MSBA-MAUI-phones-UI-issue-card-reader-status-and-card-mode-overlap | 46041 | 46043 | Ashwin | NA | Avery | 46043 | NA | NA
18 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Prem | 26596 | MSBP - iOS26 - System message and information boxes style change | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Prem | 26597 | MSBP - iOS26 - Keyboard and selector Done indicator changed to checkmark and formatting differences | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
20 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Sambath | 26505 | 26505 MSBA - MAUI - iphone + iPhone/Android- Card Reader Configure UI hard to interact with | Defect Being Fixed | 2 |  | 18 | 46041 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
21 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Prem | 26598 | MSBP - iOS26 - Store Search Bar Formatting differences | Defect Verified | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
22 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Prem | 26599 | MSBP - iOS26 - toggle shape and size has changed | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
23 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Amrit | 26534 | MSBP - Tickets - Event Details Drawer - Event Name not Wrapping | Defect Being Fixed | 0 |  | 18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
24 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Vaishnavi | 26595 | MSBP - iOS26 - Student card sheet is semi opaque | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
25 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Jagdeep/Prem | 51560 | MSBP - Android - Payment Receipt - Block Back Button in OS | Story Completed | 0 |  | 8.5 | 46042 | 46042 | NA | NA | NA | Ashwin | NA | Pull Request 46730: jagdeep.singh/51560-MSBP-Android-Payment Receipt-Block Back Button in OS | 46042 | 46043 | Ashwin | NA | Sean | 46043 | NA | NA
26 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Rupesh | 51561 | MSBP - AutoPay - Land on Home Screen After Successful Top Off | Story Being Developed | 0 |  | 12 | NA | NA | NA | NA
27 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Gursewak | 51564 | MSBP - Forgot Password - Update Text on Forgot Login Info Page | Story Peer Review | 0 |  | 12 | 46042 | 46043 | NA | NA | NA |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46760 | 46043
29 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Jagdeep | 26507 | MSBA - MAUI - iphone - UI hamburger menu version is difficult to read | Defect Ready For Testing | 1 |  | NA | 46043 | 46043 | NA | NA | NA | NA | NA | Pull Request 46768: jagdeep.singh/26507-MSBA-MAUI-iphone-UI hamburger menu version is difficult t... | 46043 | NA | Ashwin | NA | Sean | 46044 | NA | NA
28 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 | Prem/Chandler | 49399 | MSBP - Kaleida - Header Bar update | Story Being Developed | 1 |  | 25.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
30 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 | Prem/Avery | 49398 | MSBP - Kaleida - Bottom Navigations Icons update | Story Completed | 5 |  | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
31 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 | Vaishnavi/Chandler | 49363 | MSBP - Kaleida - Hamburger Menu Enhancements | Story Being Developed | 1
32 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Gursewak | 26590 | MSBP - iOS/Android - Meal Money AutoPay Payment methods has an extra space above header | Defect Peer Review | 1 |  | 4 | 46044 | 46044 | NA | NA | NA | NA |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46796 | 46044
33 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Rupesh | 26608 | MSBA - Checkout Pay button gets disabled after entering a custom amount and then deleting it | Defect Being Fixed | 2 |  |  | 46044
34 | MSB Mobile Kaleida | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Jagdeep | 26588 | MSBA - .NET10 - A - Values are getting retained in step 3, on choosing different shift/turning off and on the closeout entire day | Defect Being Fixed | 3 |  | 4 | 46044 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
35 | MSB Mobile | 46031 | 46044 | 26.3 M Sprint 1 Stretch | Vaishnavi | 26579 | MSBP - iOS - Navigation bars and icons changed with iOS26 | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 | Jagdeep/Vaishnavi | 26556 | MSBA - MAUI- Android -Meals and Ticket tabs are not displaying when selecting Store,Invoice,Meals and Tickets under Enabled Menu item in User Settings | Defect Fixed | 1 |  | 2 | 46035 | 46038 | NA | NA | NA | Gursewak | NA | Pull Request 46694: jagdeep.singh/26556-MSBA-MAUI-Android-Meals and Ticket tabs are not displayin... | 46038 | 46044 | Ashwin | NA | Avery | 46044 | These routes are already defined in AppShell.xaml as ShellContent elements with Route attributes (Store, Invoices, Meals, InPerson). When routes are declared in XAML, you don't need to register them again in code. Routing.RegisterRoute() is only needed for pages that are NOT declared in the Shell XAML. | NA
2 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 | Sambath/Vaishnavi | 26505 | 26505 MSBA - MAUI - iphone + iPhone/Android- Card Reader Configure UI hard to interact with | Defect Fixed | 1 |  | 6 | 46041 | 46045 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46819 | 46045 | 46046 | Ashwin | NA | Avery | NA | NA | NA
3 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 | Amrit | 26534 | MSBP - Tickets - Event Details Drawer - Event Name not Wrapping | Defect Fixed | 3 | NA | 9 | 46041 | 23/1/2026 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46853?_a=files | 23/1/2026 | 23/1/2026 | Ashwin | NA | Avery | 23/1/2026 | NA | NA
4 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 | Rupesh/Vaishnavi | 51561 | MSBP - AutoPay - Land on Home Screen After Successful Top Off | Story Completed | 1 | NA | 3 | 46042 | NA | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46743 | 46042 | 46044 | Ashwin | NA | Sean | 46044 | NA | NA
5 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 | Gursewak/Vaishnavi/Prem | 51564 | MSBP - Forgot Password - Update Text on Forgot Login Info Page | Story Completed | 1 | NA | 6 | 46042 | 46043 | NA | NA | NA | Amrit | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46760 | 46043 | 46044 | Ashwin | NA | Sean | 46044 | NA | NA
6 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 | Jagdeep/Vaishnavi | 26507 | MSBA - MAUI - iphone - UI hamburger menu version is difficult to read | Defect Fixed | 0.5 | NA | 2 | 46043 | 46043 | NA | NA | NA | NA | NA | Pull Request 46768: jagdeep.singh/26507-MSBA-MAUI-iphone-UI hamburger menu version is difficult t... | 46043 | 46044 | Ashwin | NA | Sean | 46044 | NA | NA
7 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 | Prem/Chandler | 49399 | MSBP - Kaleida - Header Bar update | Story Completed | 0.5 | NA | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 | Vaishnavi/Chandler/Prem | 49363 | MSBP - Kaleida - Hamburger Menu Enhancements | Story Completed | 2 |  | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 | Gursewak/Letashia | 26590 | MSBP - iOS/Android - Meal Money AutoPay Payment methods has an extra space above header | Defect Fixed | 0.5 |  | 4 | 46044 | 46044 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46796 | 46044 | 46044 | Ashwin | NA | Sean | 46045 | Remove the StackLayout and replace it with HorizontalStackLayout | NA
10 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 | Rupesh/Prem | 26608 | MSBA - Checkout Pay button gets disabled after entering a custom amount and then deleting it | Defect Fixed | 1 | NA | 7.5 | 46044 | 46045 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46823 | 46045 | 46045 | Ashwin | NA | Avery | 46045 | please restore the blank line between properties | NA
11 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 | Jagdeep/Prem | 26588 | MSBA - .NET10 - A - Values are getting retained in step 3, on choosing different shift/turning off and on the closeout entire day | Defect Fixed | 2 |  | 6 | 46044 | 46045 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46828 | 46045 | 46045 | Ashwin | NA | Sean | 46045 | NA | NA
12 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 | Gursewak/Prem | 26598 | MSBP - iOS26 - Store Search Bar Formatting differences | Defect Fixed | 2 |  | 6.5 | 46045 | 46045 | NA | Na | NA | Sambath | Remove this handler and move to SearchBarHandler.Mapper.AppendToMapping("CancelButtonColor") | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46838 | 46045 | 46045 | Ashwin | Change FillAndExpand to Fill as its not supported | Avery | 46051 | NA | NA
13 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 | Rupesh | 26520 | MSBP - .NET 10 - Nav bar Doesn't Appear | Defect Fixed | 2 |  | 2 | 46045 | 46045 | NA | NA | NA | Ashwin | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46851 | 46045 | 46045 | Ashwin | NA | Avery | NA | NA | NA
14 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 | Jagdeep/Vaishnavi | 26506 | MSBA - MAUI - phones - UI issue card reader status and card mode overlap | Defect Fixed | 1 |  | 9 | 46038 | 46051 | NA | NA |  | Rupesh |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47004 | 46041 | 46043 | Ashwin | NA | Avery | 46052 | I checked this change on android tablet and it looks weird. Please fix the reconnect button to be centered and ensure it looks good on all platforms. | NA
15 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 | Vaishnavi/Chandler | 48982 | MSBP - Remove Opt In and Update Text (26.3) | Story Completed | 1 |  | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
16 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 | Vaishnavi/Avery | 51191 | MSBA - Readers - Handle Busy State (MAUI Build) | Story Being Developed | 2 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
17 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Jagdeep/Prem | 26631 | MSBA - .NET10 - Android - Blue color Header bar is too tall | Defect Fixed | 2 |  | 10.5 | 46049 | 46049 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46881 | 46049 | 46050 | Ashwin | NA | Sean | 46050 | NA | NA
18 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Amrit/Vaishnavi | 26624 | MSBA - iOS26 - Meals/invoice - Placing cursor on the search field , camera icon and cancel icon overlaps when keyboard displays | Defect Fixed | 2 |  | 13 | 46049 | 46050 | NA | NA | NA | Sambath | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46938 | 46050 | 46051 | Ashwin | NA | Sean | 46051 | NA | NA
19 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Rupesh/Prem | 26625 | MSBA - iOS26 - Searching in Invoice search text box, the search results student data is partially cut off | Defect Fixed | 2 |  | 11 | 46049 | 46050 | NA | NA | NA | Jagdeeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46909 | 46050 | 46050 | Ashwin | NA | Avery | 46050 | NA | NA
20 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Sambath/Prem | 26609 | 26609 MSBA - iOS - Promo-code field is getting displayed for meals/invoice when cart preview is enabled | Defect Fixed | 2 |  | 22 | 46049 | 46052 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46983 | 1//30/2026 | 46053 | Ashwin | NA | Avery | 46053 | NA | NA
21 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Jagdeep/Prem | 26601 | MSBA - Android - Bottom of screen cut off by system navigation and app navigation bar if enabled .net10 | Defect Fixed | 1 |  | 5.5 | 46049 | 46050 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46881 | 46050 | 46050 | Ashwin | NA | Sean | 46050 | NA | NA
22 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Gursewak/Prem | 51675 | MSBP - Privacy Notice Label Update | Story Completed | 2 |  | 11.5 | 46050 | 46051 | NA | NA | NA | NA | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46946 | 46051 | 46051 | Ashwin | NA | Avery | 46051 | NA | NA
23 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Rupesh/Vaishnavi | 51676 | MSBA - Privacy Notice - Label Update | Story Completed | 2 |  | 8 | 46051 | 46051 | NA | NA | NA | Jagdeeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/46952 | 46051 | 46051 | Ashwin | NA | Avery | 46051 | NA | NA
24 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Jagdeep/Prem | 48597 | [WAVE] MSBA - Kaleida - Hamburger Menu Enhancements | Story Peer Review | 8 |  | 27 | 46052 | 46057 | NA | NA | NA | Sambath | 1. Use FontAwesomeHelper.cs for all awesome fonts, 2. move the all color code to resource 3. Use Fill, don't use FillAndExpand | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47037 | 46058 | NA | NA | NA | NA | NA | NA | NA
25 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Amrit/Prem | 26668 | MSBP - Android - Event description in my tickets is not showing line breaks properly | Defect Fixed | 2 |  | 13.5 | 46052 | 46055 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46999 | 46055 | 46083 | Ashwin | NA | Sean | 46083 | NA | NA
26 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Gursewak/Prem | 26673 | MSBP - I/A - Forgot Login Info - Next button shows enable even if no mobile number is entered. | Defect Fixed | 2 |  | 8.25 | 46052 | 46052 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46984 | 46052 | 46052 | Ashwin | NA | Avery | 46055 | NA | NA
27 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Vaishnavi | 26623 | MSBA - iOS26 - Navigation bars and icon style changed with iOS26(Test Only) | Defect Fixed | 0.5 |  | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
28 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Rupesh/Prem | 26663 | MSBP - iOS/Android - Nav bar persists in store and product screens (.net10) | Defect Fixed | 2 |  | 7.5 | 46052 | 46052 | NA | NA | NA | Jagdeeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBP.MAUI/pullrequest/46982 | 46052 | 46052 | Ashwin | NA | Sean | 46052 | NA | NA
29 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Rupesh/Prem | 48599 | [WAVE] MSBA - Kaleida - New Header Bar (Cart + Help Icon) | Story Being Developed | 8 |  |  | 46055 |  | NA | NA | NA
30 | MSB Mobile | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Sambath/Gursewak/Amrit | 51700 | 51700 MSBA - Transaction History UI Update (Conversion without updated API Endpoints) | Story Being Developed | 13 |  | 32 | 46055 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
31 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Jagdeep | 26717 | MSBA MAUI - Student name field gets hidden behind keyboard in landscape mode on Product detail screen | Defect Peer Review | 2 |  | 6 | 46058 | 46058 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47097 | 46058 | NA | NA | NA | NA | NA | NA | NA
32 | MSB Mobile Kaleida | 46045 | 46058 | 26.3 M Sprint 2 Stretch | Gursewak/Amrit | 26718 | MSBA MAUI - Search bar input box not visible in store screen is not grey active (IOS26) | Defect Peer Review | 1 |  | 9 | 46058 | 46059 | NA | NA | NA | Jagdeep | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47094 | 46059 | 46059
1 | MSB Mobile | 46059 | 46072 | 26.3 M Sprint 3 | Vaishnavi/Avery | 51191 | MSBA - Readers - Handle Busy State (MAUI Build) | Story Being Tested | 2 |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | MSB Mobile Kaleida | 46059 | 46072 | 26.3 M Sprint 3 | Jagdeep/Prem | 48597 | [WAVE] MSBA - Kaleida - Hamburger Menu Enhancements | Story Peer Review | 2 |  | 0 | 46052 | 46057 | NA | NA | NA | Sambath | 1. Use FontAwesomeHelper.cs for all awesome fonts, 2. move the all color code to resource 3. Use Fill, don't use FillAndExpand | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47037 | 46058 | NA | NA | NA | NA | NA | NA | NA
3 | MSB Mobile | 46059 | 46072 | 26.3 M Sprint 3 | Rupesh/Prem | 48599 | [WAVE] MSBA - Kaleida - New Header Bar (Cart + Help Icon) | Story Peer Review | 1 |  |  | 46055 |  | NA | NA | NA |  |  | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47105 | 46058
4 | MSB Mobile | 46059 | 46072 | 26.3 M Sprint 3 | Sambath | 51795 | MSBA - Kaleida - Transaction History UI Update (V2) | Story Approved |  |  |  | 46055 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | MSB Mobile Kaleida | 46059 | 46072 | 26.3 M Sprint 3 | Jagdeep | 26717 | MSBA MAUI - Student name field gets hidden behind keyboard in landscape mode on Product detail screen | Defect Peer Review | 1 |  | 0 | 46058 | 46058 | NA | NA | NA | Rupesh | NA | https://dev.azure.com/heartlandschools/Mobile/_git/MSBA.MAUI/pullrequest/47097 | 46058 | NA | NA | NA | NA | NA | NA | NA
6 | MSB Mobile Kaleida | 46059 | 46072 | 26.3 M Sprint 3 | Jagdeep/Prem | 48598 | [WAVE] MSBA - Kaleida - Update Bottom Navigation Icons | Story Being Developed | 2 |  | NA | 46059 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | MSB Mobile Kaleida | 46059 | 46072 | 26.3 M Sprint 3 | Amrit | 26716 | MSBA - Shift Mode - Problem Getting Shift | Defect Ready For Testing
8 | MSB Mobile | 46059 | 46072 | 26.3 M Sprint 3 | Rupesh | 46804 | [WAVE] MSBA - Kaleida - Background Color Update | Story Being Developed | 1 |  |  | 46058