## Dashboard-2025
Current Sprint | #N/A | Current Sprint Sheet | #N/A | Sprint Start Date | #N/A | Sprint End Date |  | #N/A | Application Name | FOH Wave | Users | sabir.shaikh@relevantz.com;subbulakshmi.namasivayam@relevantz.com;vidhya.subramani@relevantz.com;balamurugan.kandasamy@relevantz.com | Teams Name
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story points introduced/removed | Sprint Summary | Accomplishments | Remarks | Retro Points (Internal & External) | Planned Leave | Total Leave | Data sanity Audit Status | AuditDate
#N/A | 4.22 - Sprint 2 | 2025-05-09 | 2025-05-22 | 30 | 38 | Introduced - 8 |  | Adding new templates to Custom Reports, Tier Model, State Level EIG updates, and Admin View of Real Time Transactions updates. | CRC Internal -- 1 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 0 | Internal: External:
#N/A | 4.22 - Sprint 3 | 2025-05-23 | 2025-06-05 | 40 | 37.75 | Nil |  | Cutom Report for Eligibility Student Listing | CRC Internal -- 0 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 3 | Internal: External:
#N/A | 4.23 - Sprint 1 | 2025-06-06 | 2025-06-18 | 10 | 10 | Introduced - 21 |  |  | CRC Internal -- 2 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 4 | Internal: External:
#N/A | 4.23 - Sprint 2 | 2025-06-19 | 2025-07-03 | 20 | 20 | Introduced - 16 |  | Supplemental Programs Claim Report | CRC Internal -- 1 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 3 | Internal: External:
#N/A | 4.23 - Sprint 3 | 2025-07-04 | 2025-07-17 | 14 | 14 | Introduced-7 |  | Custom Report for Transaction History, Modifications to Louisiana SFS-8C Report | CRC Internal -- 4 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 4 | Internal: External: What went well: Successfully completed the assigned stories What didn't go well: Nil
#N/A | 4.23 - Sprint 4 | 2025-07-18 | 2025-07-31 | 14 | 16 | Introduced - 17 |  | Defect fixes and 4.23 Regression testing | CRC Internal -- 2 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 7 | Internal: External: What went well: Successfully completed the Regression testing, Completed the assigned stories What didn't go well: Nil
#N/A | 4.24 - Sprint 1 | 2025-08-01 | 2025-08-14 | 12 | 15 | Introduced - 15 |  | Support for Credit Card in Additional Meal Programs for Reports,Delete functionality for User Custom Report | CRC Internal -- 11 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 6 | Internal: External: What went well: Successfully completed the assigned stories What didn't go well: Nil
#N/A | 4.24 - Sprint 2 | 2025-08-15 | 2025-08-28 | 10 | 13 | Introduced - 22 |  | Dashboard feature for copy and enlarge wiidgets, implemented new datasource in custom report. | CRC Internal -- 1 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 5 | Internal: External: What went well: Successfully completed the assigned stories. Successfully completed the dashboard related features. What didn't go well: Nil
#N/A | 4.24 - Sprint 3 | 2025-08-29 | 2025-09-11 | 8 | 18 | Introduced - 28 |  | New Template for Daily Sales Summary Report,Daily Sales By Serving Line Report,Dashboard UI Enhancement and Other Reports Improvements, Automation | CRC Internal -- 1 CRC External -- 0 Peer Testing - 1 POV Comments - 4 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 7 | Internal: External: What went well: Completed Forecast and lot more, Automation progress, Hosted platforms - SYSU, All schools back in session, Esclation down from previous years (Note: Esclations from coustomer support are handled by client developer Steve) What didn't go well: Lost Ying to BOH team Esclations
#N/A | 4.24 - Sprint 4 | 2025-09-12 | 2025-09-25 | 14 | 15 | Introduced - 11 |  | Defect fixes and 4.24 Regression testing | "CRC Internal --0 CRC External -- 0 Peer Testing - 3 POV Comments - QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 4" | Internal: External: What went well: Offshore Completed regression and defects including testing, Completed Forecast and more, Defects fixed into releases What didn't go well: Esclations (Note: Esclations from coustomer support are handled by client developer Steve), Added items in last minute to include in release
#N/A | 4.25 - Sprint 1 | 2025-09-26 | 2025-10-09 | 13 | 13 | Introduced - 16 |  | Modifications to Operating Days, new filter for ‘Participation by’ to Standard Claim Report, and New Template to ‘Daily Sales By Serving Line Report’. | CRC Internal -- 3 CRC External -- 0 Peer Testing - 2 POV Comments - 4 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 4 | Internal: External: What went well: Completed more than Forecast , Esclations (not too bad this week), mike completed testing before PTO, Team completed rest of testing after Mike PTO What didn't go well: Apigee issue (platformops and apigee team)
#N/A | 4.25 - Sprint 2 | 2025-10-10 | 2025-10-23 | 15 | 21 | Introduced - 18 | New Dashboard Widgets, Ability to flip between Apigee & Existing endpoints, ‘Participation By’ filter to Supplemental Programs Claim Report, Tyler Munis Export Modifications, update to VA SNP-12 Report, Add Active Flag to Student Export Setup, and 4.24 Release Prep | New Dashboard Widgets, ‘Participation By’ filter to Supplemental Programs Claim Report, Updating report format to meet Mosaic standards | CRC Internal -- 0 CRC External -- 0 Peer Testing - 6 POV Comments - 6 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 6 | Internal: External: What went well: Completed more than Forecast What didn't go well: NA
#N/A | 4.25 - Sprint 3 | 2025-10-24 | 2025-11-06 | 12 | 23 | Introduced - 23 | Adding a Student Debt Chart to the Dashboard, Replacing Master Serving Period with Serving Period Program, New ‘Group By School’ filter to Students w/out an Elig. Determination Report, DC Import Improvements, and NJ Master Eligibility List report Modifications | Export 'User Created Custom Reports', 'User Assignments Report' to meet Mosaic Standard, Legacy imports are moved to Utilities | CRC Internal -- 0 CRC External -- 0 Peer Testing - 1 POV Comments - 6 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 10 | Internal: External: What went well: Releases, Exceeded Forecast What didn't go well: Esclations (Note: Esclations from coustomer support are handled by client developer Steve)
#N/A | 4.25 - Sprint 4 | 2025-11-07 | 2025-11-20 | 10 | 12 | Introduced - 36 | IL WINS Export Scheduler Task, Importing Custom Report Format, Added new data source to report designer | IL WINS Export Scheduler Task, Importing Custom Report Format, NSS ID in Visual Report, Added new datasource to the Report designer | CRC Internal -- 15 CRC External -- 1 Peer Testing - 3 POV Comments - 2 QA Defects -- 2 Escaped Defects -- 0 Stretch Story: 10 | Internal: External: What went well: Hit Forecast, SNYK progress in stretch What didn't go well: CPS Release, Apigee work, MSB Endpoint Change.
#N/A | 4.25 - Sprint 5 | 2025-11-21 | 2025-12-18 | 23 | 37 | Introduced - 37 | New Templates for Custom Reports, New Data Sources for Report Designer, and 4.25 Regression Testing | Completed 4.25 regression testing with defect fixes. | CRC Internal -- 2 CRC External -- 0 QA Defects -- 2 Escaped Defects -- 0 Stretch Story: 8 Defects RC: 1. Calculation mismatch not captured in unit testing. 2. It is the data issue which occurred in other developer's DB. It is handled now. Internal CRC comments RC: 1. Missed to ensure SQL script file naming standards 2. Misunderstood the acceptance criteria | Internal: External: What went well: Insane no.of stories completed(Sp's), started using Browser Stack for automation. What didn't go well: Escalations, MSB Endpoint Change.

## Defect-template
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## Dashboard
Current Sprint | 26.07 Sprint 1 | Current Sprint Sheet | 26.07 Sprint 1-Status | Sprint Start Date | 2026-04-24 | Sprint End Date | 2026-05-21 | Application Name | FOH Wave | Users | sabir.shaikh@relevantz.com;subbulakshmi.namasivayam@relevantz.com;vidhya.subramani@relevantz.com;balamurugan.kandasamy@relevantz.com | Teams Name(GP - FOH Acceleration Initiative) | 19:e340939441a74ca5938ca3ad602ee553@thread.v2
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story points introduced/removed | Sprint Summary | Accomplishments | Remarks | Retro Points (Internal & External) | Planned Leaves | Total Leaves | Data sanity Audit Status | AuditDate | Backlog Health
NA | 26.1 - Sprint 1 | 2025-12-19 | 2026-01-15 | 27 | 32 | Introduced - 30 | Support for Multiple Languages in SL, Automation, Meal Count Entry Audit Report, Feature flag changes | Completed Support for Multiple Languages in SL, Automation, Meal Count Entry Audit Report, Feature flag changes | CRC Internal -- 24 CRC External -- 2 QA Defects -- 4 Escaped Defects -- 0 Stretch Story: 9 Defects RC: 1. Missed UI validation for the textbox. 2. Missed to handle the scenario of enable/disable Language feature flag. 3. Missed to test around the UI changes 4. Missed to check Parent table column's lenght and Language tables column's length Internal CRC comments RC: 1. Missed UI validations 2. Missed SQL script file standards 3. Missed to ensure date format 4. Not keeping common table name in SQL script 5. Some implicit stuff needs to be incorporated as part of the requirement which I'm not aware of 6. I missed to clean up or refactor some portion of the SQL code | What went well: Completed the forecast and almost the same in the stretch. 2. Holidays. 3. 502 gateway Apigee issues solving (prod) What didn't go well: 365 migration, MSB from www to etransfer issue.
NA | 26.1 - Sprint 2 | 2026-01-16 | 2026-01-29 | 17 | 17 | Introduced - 0 | Updates to Meal Report and User Report, Mosaic BOH Knowledge transfer | Completed the Mosaic Standards for User Reports and Meals Reports, Mosaic BOH Knowledge transfer | CRC Internal -- 0 CRC External --0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 0 Defects RC: 1. Pre existing UI design which was there originally. PO wanted to fix it as part of this story hence it was fixed. Internal CRC comments RC: None | Internal: External: What went well: Completed commit and stretch items. 2. 4.24 Hot fix/4.25 Beta 3. BOH KT What didn't go well: 1. Vending QA, 2. Missing App switcher script in 4.25 Beta 3. App switcher button is not always working. Recieved appretiaton from QA during retro that offshore helped to close the testing stories during the sprint end.
NA | 26.1 - Sprint 3 | 2026-01-30 | 2026-02-12 | 5 | 16 | Introduced - 30 | Modified Prepay Report to Mosaic Standard, Defect Fixes, Hide Tier Feature from UI BOH Reverse KT, Automation | Completed the Prepay Report to meet Mosaic Standard, BOH Reverse KT | CRC Internal -- 0 Peer testing - 1 CRC External -- 0 QA Defects -- 2 Escaped Defects -- 0 POV Comments - 5 Stretch Story: 13 CRC RC: Nil Defects RC: 1. css styling not handled and so improper visual spacing between UI components occured 2. Missed to show proper version format | "Internal: External: What went well: 1. Exceeded the forcast story points. 2. 4.25 release. What didn't go well: 1. Escalations, 2. 4.25 rused out(App switcher not working), 3. Dashboard issues." | 0 | 1
NA | 26.1 - Sprint 4 | 2026-02-13 | 2026-02-26 | 2 | 4 | Introduced - 26 | Add New Security page for Report Designer, Edit Report button to the Custom Reports UI, Automation | Completed the Report Designer feature in Security Page | CRC Internal -- 0 Peer testing - 0 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 POV Comments - 0 Stretch Story: 4 CRC RC: Nil Defects RC: Nil | Internal: External: What went well: 1. Offshore work on regression, 2. Hosted Test environment(Mike getting builds up) What didn't go well: 1. SQL cypher(Not working with .460) | 1 | 5
NA | 26.05 Sprint 1 | 2026-02-27 | 2026-03-12 | 6 | 8 | Introduced - 20 | User Tasks Maintenance and Setup, Automation | Added User Tasks Maintenance and Setup screen, Automation | CRC Internal -- 5 Peer testing - 3 CRC External -- 0 QA Defects -- 15 Escaped Defects -- 0 POV Comments - 6 Stretch Story: 4 CRC RC: 1. Missed to follow localization support (2) 2. Missed to follow exsiting coding standards (1) 3. unwanted code (1) 4. returning entity directly (1) Defects RC: 1. UI validations should be added properly (4) 2. UI design issues (8) 3. Data issue (3) | Internal: External: What went well: 1. Exceeded commit, 2. SQLCypher progress, 3. Regression completed on time | 3 | 5
NA | 26.05 Sprint 2 | 2026-03-13 | 2026-03-26 | 13 | 13 | Introduced - 27 | User Assignment in User Task, Mosaic BOH - Transfers - Bulk Replace, Automation | User Assignment in User Task, Mosaic BOH - Transfers - Bulk Replace, Add, Delete | "CRC Internal -- 1 Peer testing - 4 CRC External -- 0 QA Defects -- 3 Escaped Defects -- 0 POV Comments - 11 Stretch Story: 6 CRC RC: 1. Missed to remove the unwanted code Defects RC: 1. UI design issues 2. Backend validation did not match the UI validation. (2) POV RC: Cosmetic changes (4) Sugeestions (3) Data issue (2) | Internal: External: What went well: 1. 26.1 Release 2. Exceeded commit What didn't go well: Apigee & WAF issues | 3 | 4.5
NA | 26.05 Sprint 3 | 2026-03-27 | 2026-04-09 | 20 | 12 | Introduced - 16 | Review Task in User Task,Bidding - Allow vendors to indicate "No Response",ER Improve the Search functionality,Automation | Review Task in User Task,Bidding - Allow vendors to indicate "No Response",ER Improve the Search functionality | "CRC Internal -- 0 Peer testing - 1 CRC External -- 0 QA Defects -- 4 Escaped Defects -- 0 POV Comments - 3 Stretch Story: 2 CRC RC: NIL Defects RC: 1. UI design issues 2. Add more than 40 user then it gives an error in QA envirornment POV RC: Missed adding logic for bottom-line bidding and checkbox visibility control (2) Data issue (2) Missed to save the value of checkebox | What went well: 1. Exceeded Commit 2. Migration Work 3. Multi Language on POS 4. Offshore Support on QA 5. Defect fixes for 26.1 What didn't go so well? 1. AG's workable | 2 | 2
NA | 26.05 Sprint 4 | 2026-04-10 | 2026-04-23 | 9 | 20 | Introduced - 40 | Review Task in User Task, Ingredients - Search Functionality, 26.5 Regression Testing, Bidding | Completed 26.5 Regression Testing for Setup, User Tasks for Review Task, Ingredients - Search Functionality, Bidding Issues, Transfers - Bulk Add - UI | CRC Internal -- 0 Peer testing - 0 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 POV Comments - 0 Stretch Story: 5 CRC RC: Nil Defects RC: Nil POV RC: Nil | What went well: 1. Completed Regression stories assigned in the sprint 2. Fixed all the regression defects 3. No review comments What didn't go well: Nil | 2 | 2
NA | 26.07 Sprint 1 | 2026-04-24 | 2026-05-21

## 26.07 Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Story Being Developed | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 | Balamurugan | 52062 | [Wave]Mosaic BOH - Transfers - Bulk Add (2) - UI Only | Story Being Tested | 8 | 7.5 | 30 | 2026-04-30 | 2026-05-07 | Balamurugan | Rajiv Gandhi Sugumaran | NA | Rajiv Gandhi Sugumaran | NA | 48943 | 2026-05-08 | 2026-05-12 | Charles | NA | NA | NA | NA | NA | NA
2 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 | Sabir | 47770 | [WAVE] Mosaic BOH - (7) User Task List - End User UI | Story Peer Review | 8 | 7.5 | 30 | 2026-04-24 | 2026-05-07 | Sabir | Krupa Bhatkar |  | Krupa Bhatkar |  | 49014 | 2026-05-12
3 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 | Balamurugan | 52178 | [Wave]Mosaic BOH - Transfers - Bulk Add (2) - Data Retrieval | Story Being Tested | 8 | 7.5 | 30 | 2026-04-24 | 2026-05-07 | Balamurugan | Rajiv Gandhi Sugumaran | NA | Rajiv Gandhi Sugumaran | NA | 48943 | 2026-05-08 | 2026-05-12 | Charles | NA | NA | NA | NA | NA | NA
4 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 | Subbulakshmi | 52915 | Add an 'Aramark Financial Export' Scheduler Task Step | Story Completed | 2 | 1 | 4 | 2026-04-27 | 2026-05-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 | Subbulakshmi | 52827 | Update Federal IEGs (2026-27) | Story Completed | 1 | 1 | 4 | 2026-04-28 | 2026-04-28 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 Stretch | Pradeepa | 47412 | [WAVE] Mosaic BOH - Vendor Invoice Management - Create new Vendor Invoice Import Template 1 | Story Being Developed | 8 | 12 | 48 | 2026-04-28
7 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 | Subbulakshmi | 52256 | Open Previous Day Maintenance - Add Multiselect Site & Convert Screen to Vega | Story Being Tested | 1 | 1 | 4 | 2026-04-29 | [16 empty] | Need to test in Hosted Environment
8 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 Stretch | Subbulakshmi | 53098 | MFOH [BAU] - Automation (46670) | Story Being Developed | 2 | 2 | 8 | 2026-04-30
9 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 Stretch | Sabir | 29833 | [WAVE] Mosaic BOH - Recipes - Search for Recipes that Contain or Do Not Contain Specified Allergens (CPS C0030) | Story Being Developed | 8 | 7.5 | 30 | 2026-05-05
10 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 Stretch | Subbulakshmi | 53138 | MFOH - Automation (51180) | Story Completed | 2 | 2 | 8 | 2026-05-05 | 2026-05-05 | Subbulakshmi | NA | NA | NA | NA | 48897 | 05/072026 | 2026-05-05 | NA | NA | Steve | NA | NA | NA | NA | NA | NA
11 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 Stretch | Balamurugan | 45251 | Mosaic BOH - Vendors - Add a setting to make invoice # mandatory on receiving orders | Story Peer Review | 5 | 4.5 | 18 | 2026-05-08 | 2026-05-13 | Balamurugan | Rajiv Gandhi Sugumaran | 1. Add the below script in Script.PostDeployment1.Sql - A script for adding a new column has been included in PostDeployment1.sql. | Rajiv Gandhi Sugumaran | NA | 49027 | 05/132026 | [6 empty] | NA | NA
12 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 Stretch | Subbulakshmi | 53172 | MFOH [WAVE] - Automation (51785) | Story Completed | 1 | 1 | 4 | 2026-05-12 | 2026-05-13 | Subbulakshmi | NA | NA | NA | NA | 49052 | 2026-05-14 | 2026-05-14 | NA | NA | Ying | NA | NA | NA | NA | NA | NA
13 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 Stretch | Sabir | 52731 | [WAVE] Mosaic BOH - Ingredients - Contains no known Allergens impacts | Story Being Developed | 8 | 3 | 12 | 2026-05-13
14 | FOH Wave | 2026-04-24 | 2026-05-21 | 26.07 Sprint 1 Stretch | Balamurugan | 52146 | Mosaic BOH - Transfers - Bulk Remove Item (3) | Story Approved | 13 |  |  | 2026-05-13

## 26.07 Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 26.07 Sprint 1 | 52256 | 52256 | Venkatesan | Bounceback/Sub-Defect | Schools listed based on School Group (1-All Schools), but School Group is not available in Open Previous day Maintenance screen. | Significant | Manual | Internal | Story Being Developed | 2026-04-29 |  | Data Issue
| 26.07 Sprint 1 | 52062 | 52062 | Balamurugan | Bounceback/Sub-Defect | 1. Asterisk symbol is missing in Sending Site Field 2. If I click on Find and select a product, then reset and cancel it, the Products popup appears again. | Minor | Manual | Internal | Story Being Developed | 2026-05-14 |  | Design Issue

## 26.05 Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Story Being Tested | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2026-04-10 | 2026-04-23 | 26.05 Sprint 4 | Subbulakshmi | 51845 | [WAVE] Mosaic BOH - (6) User Tasks - Review Task Setup | Story Completed | 1 | 1 | 4 | 2026-04-10 | 2026-04-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH Wave | 2026-04-10 | 2026-04-23 | 26.05 Sprint 4 | Subbulakshmi | 52797 | Mosaic - FOH 26.5(Regression) - Setup | Story Completed | 8 | 5.75 | 23 | 2026-04-13 | 2026-04-17 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | FOH Wave | 2026-04-10 | 2026-04-23 | 26.05 Sprint 4 Stretch | Balamurugan | 52062 | [Wave]Mosaic BOH - Transfers - Bulk Add (2) - UI Only | Story Being Developed | 8 | 6 | 24 | 2026-04-10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | FOH Wave | 2026-04-10 | 2026-04-23 | 26.05 Sprint 4 Stretch | Sabir | 52044 | [WAVE] Mosaic BOH - Ingredients - Search for Ingredients that Do Not Contain Specified Allergens | Story Completed | 8 | 4 | 16 | 2026-04-10 | 2026-04-15 | Sabir | Rajiv | NA | Rajiv | NA | 48420 | 2026-04-15 | 2026-04-17 | Charles | NA | NA | 2026-04-17 | NA | NA | NA | NA | meet expectation
5 | FOH Wave | 2026-04-10 | 2026-04-23 | 26.05 Sprint 4 Stretch | Balamurugan | 27176 | MFOH - BOH WAVE - Fix the issues in bidding that showed up from the changes done in 52172 | Defect Fixed | 3 | 3 | 12 | 2026-04-13 | 2026-04-17 | Balamurugan | NA | NA | NA | NA | 48489 | 2026-04-17 | 2026-04-20 | Charles | NA | NA | NA | NA | NA | NA | NA | NA
6 | FOH Wave | 2026-04-10 | 2026-04-23 | 26.05 Sprint 4 Stretch | Sabir | 47770 | [WAVE] Mosaic BOH - (7) User Task List - End User UI | Story Being Developed | 13 | 5 | 20 | 2026-04-16 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | FOH Wave | 2026-04-10 | 2026-04-23 | 26.05 Sprint 4 Stretch | Balamurugan | 52178 | [Wave]Mosaic BOH - Transfers - Bulk Add (2) - Data Retrieval | Story Being Developed | 8 | 4.5 | 18 | 2026-04-21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 26.05 Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments

## 26.5 - Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Story Being Tested | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 | Subbulakshmi | 26993 | [Wave]Mosaic BOH - Fix the alignment issues with the User Tasks List Search Screen | Defect Fixed | 1 | 0.5 | 2 | 2026-03-27 | 2026-04-06 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 | Subbulakshmi | 52329 | MFOH - Automation - Kaleida changes update to the Setup - Annual Setup - Nondiscrimination Statement | Story Completed | 1 | 1 | 4 | 2026-03-27 | 2026-03-31 | Subbulakshmi | NA | NA | NA | NA | 48145 | 2026-03-31 | 2026-03-31 | NA | NA | Steve | 2026-03-31 | NA | NA | NA | NA | NA
3 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 | Sabir | 43501 | [WAVE] Mosaic BOH - ER - Improve the Search functionality | Story Completed | 1 | 0 |  | 2026-03-27 | 2026-03-27 | Sabir | Deepika | NA | Deepika | NA | 48014 | 2026-03-31 | 2026-03-31 | Charles | NA | NA | 2026-03-31 | NA | NA | NA | NA | meet expectation
4 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 | Balamurugan | 52172 | [WAVE] Mosaic BOH - Bidding - Allow vendors to indicate "No Response" on line items | Story Completed | 5 | 7.5 | 30 | 2026-03-27 | 2026-04-02 | Balamurugan | Deepika | NA | Deepika | NA | 48197 | 2026-04-02 | 2026-04-07 | Charles | NA | NA | 2026-04-07 | NA | POV Comments: 1. If decline to respond -> yes -> though data is filled, then the check box should not be visible in bid analysis 2. Bottom Line -> When declined to respond is checked, though the vendor quoted price is added, it should not consider that item for responded items | NA | NA | NA
5 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 | Vidhya | 51845 | [WAVE] Mosaic BOH - (6) User Tasks - Review Task Setup | Story Being Tested | 8 | 5.5 | 22 | 2026-03-27 | 2026-04-02 | Sabir | Deepika | User list grid doen't retain the checked specific User's | Deepika | NA | 48240 | 2026-04-07 | 2026-04-07 | Charles | NA | NA | 2026-04-07 | NA | NA | NA | NA | meet expectation
6 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 | Sabir | 52169 | [WAVE] Mosaic BOH - Ingredient Allergens - Add "Contains No Allergens" option | Story Completed | 3 | 2 | 8 | 2026-03-27 | 2026-03-30 | Sabir | Mohammad Zawahir | None | Mohammad Zawahir | None | 48091 | 2026-05-31 | 2026-04-02 | Charles | None | NA | 2026-04-02 | None | POV Comments: Saved changes are not reflected for the checkbox "This ingredient contains no known allergens." |  | NA | meet expectation
7 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 | Subbulakshmi | 51891 | MFOH [WAVE] - Modify the Dashboard Setup Maintenance (Allow to add Widgets one by one) | Story Completed | 1 | 0.5 | 2 | 2026-03-27 | 2026-04-01 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 Stretch | Balamurugan | 52062 | [Wave]Mosaic BOH - Transfers - Bulk Add (2) - UI Only | Story Being Developed | 8 | 6 | 24 | 2026-04-06 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | FOH Wave | 2026-03-27 | 2026-04-09 | 26.5 - Sprint 3 Stretch | Sabir | 52044 | [WAVE] Mosaic BOH - Ingredients - Search for Ingredients that Do Not Contain Specified Allergens | Story Approved | 8 | 3 | 12 | 2026-04-06 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 26.5 - Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 26.5 - Sprint 3 | 51845 | 51845 | Vidhya/Sabir | Bounceback/Sub-Defect | 1. Task Type tool tip is showing incorrectly 2. Tool tip issue in Task Name 3. End Date is not showing for Daily Recurrence 4. Getting on Exception error while Added more than 40 Users(Workking fine in Local, issue only is QA Test) | Minor | Manual | Internal | Story Completed | 2026-04-08 | 2026-04-09 | UI Issue | Tool tip issues in Task Type, Task Name, Recurrence

## 26.5 - Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 | Vidhya | 47929 | [WAVE] Mosaic BOH - (5) User Tasks - Assigning Users | Story Completed | 8 | 9 | 36 | 2026-03-13 | 2026-03-20 | Vidhya | Mohammed Jawahir | 1. After pagination, continue button turned disable mode. 2. Show Selected Only is not working correctly 3. I was added task with due date 23rd, then edit the same task it shows 22nd. 4. I can able to add task for past dates. | Jawahir | None | 47942 | 2026-03-20 | 2026-03-24 | Charles | None | NA | 2026-03-24 | None | POV comments: 1. Either Site Group/ site should be selected to apply filters 2. User Assignment - space required 3. Uncheck any selected users when selecting yes in the pop-up | NA | NA | NA
2 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 | Subbulakshmi | 52330 | Kaleida changes update to the Global Report Layout File for Kaleida Reports | Story Completed | 2 | 2.25 | 9 | 2026-03-13 | 2026-03-17 | Subbulakshmi | NA | NA | NA | NA | 47876 | 2026-03-18 | 2026-03-18 | NA | NA | NA | 2026-03-18 | NA | NA | NA | NA | NA
3 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 | Balamurugan | 52099 | [Wave]Mosaic BOH - Transfers - Bulk Replace (1) | Story Completed | 3 | 6.5 | 26 | 2026-03-13 | 2026-03-18 | Balamurugan | Mohammed Jawahir | None | Mohammed Jawahir | 1. Please remove unused variables | 47875 | 2026-03-18 | 2026-03-19 | Charles Antonysamy | NA | NA | 2026-03-20 | NA | 1) Parent Menu -> Icon and underline 2) add, remove -> Add “Coming soon” text 3) Replace position edit.. in view only mode 4) comment box position -> check image 5) append the existing comments | NA | Internal POV done on 03/17/2026. Working on POV 4 design comments and one 1 suggestion. Get POV confirmation after share the screen shot design changes on 03/17/2026 Reasons for story points exceeded: Since this is first story with BOH, it took time to align with existing application's coding standards and structure | NA
4 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 Stretch | Sabir | 26993 | [Wave]Mosaic BOH - Fix the alignment issues with the User Tasks List Search Screen | Defect Being Tested | 3 | 2 | 12 | 2026-03-16 | 2026-03-18 | Sabir | Krupa Bhatkar | NA | Krupa Bhatkar | NA | 47865 | 2026-03-18 | 2026-03-24 | Charles Antonysamy | NA | NA | 2026-03-24 | NA | POV comments: 1. Tool tip Do not Repeat- Due on June 28- correction show the exact date in saved format 03/25/2026 Daily - Every 5 Days until 03/18/2026 Weekly - On Monday, Tuesday until 03/18/2026 Monthly - On the 1st Sunday until 09/22/2029 Annually - On June 28 until 09/22/2030 2. When opening a task from the search screen, the saved selection is not retained 3. Security Group, Site Group, and Site - List all the values | NA | NA | NA
5 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 Stretch | Subbulakshmi | 52329 | MFOH - Automation - Kaleida changes update to the Setup - Annual Setup - Nondiscrimination Statement | Story Being Developed | 1 | 1 | 4 | 2026-03-18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | None | NA | NA | NA
6 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 Stretch | Sabir | 43501 | [WAVE] Mosaic BOH - ER - Improve the Search functionality | Story Being Developed | 5 | 3 | 12 | 2026-03-18 | 2026-03-24 | Sabir | Rajiv | NA | Rajiv | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 Stretch | Balamurugan | 52172 | [WAVE] Mosaic BOH - Bidding - Allow vendors to indicate "No Response" on line items | Story Being Developed | 8 | 8 | 32 | 2026-03-19 | 2026-03-26 | Balamurugan | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 Stretch | Vidhya | 51845 | [WAVE] Mosaic BOH - (6) User Tasks - Review Task Setup | Story Being Developed | 5 | 4 | 16 | 2026-03-25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | FOH Wave | 2026-03-13 | 2026-03-26 | 26.5 - Sprint 2 Stretch | Sabir | 52169 | [WAVE] Mosaic BOH - Ingredient Allergens - Add "Contains No Allergens" option | Story Being Developed | 5 | 2 | 8 | 2026-03-25 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Na

## 26.5 - Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 26.5 - Sprint 1 | 52099 | 52099 | Balamurugan | Bounceback/Sub-Defect | 1. Comment is not appended when I added the text length is 4000 2. UI issue in Comment text box scroll 3. Getting an Exception error while I replace the transfer in MenuPlanningPlannedMenu file | Minor | Manual | Internal | Story Completed | 2026-03-13 | 2026-03-18 | UI Validations
| 26.5 - Sprint 2 Stretch | 26993 | 26993 | Sabir | Bounceback/Sub-Defect | 1. If I open the Task in new tab, data is not showing for Annually and Monthly Recurrence 2. Space needed between Custom and Link/Simple and Task – Previously showing correctly. 3. Fluctuation issue in Assigned To User tooltip 4. Continue button is enabled when I’m not filling the Mandatory field – Previously its working 5. Need to Display all the Site Groups and Site Name irrespective of the logged in User | Minor | Manual | Internal | Story Completed | 2026-03-23 | 2026-03-25 | UI Validations

## 26.5 - Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2026-02-27 | 2026-03-12 | 26.5 - Sprint 1 | Vidhya | 51349 | [WAVE] Mosaic BOH - (3) User Tasks - Add/Edit Tasks | Story Completed | 3 | 10.5 | 42 | 2026-02-27 | 2026-03-06 | Vidhya | Deepika (BOH) | 1. At first time without any clicks on the submenus, there is an spacing at right side 2. When O&I is disabled.. Inventory has different submenu’s | Deepika (BOH) | 1. Remove the hard-coded value in controller instead use resource files 2. Revert this blank Line | 47641 | 2026-03-06 | 2026-03-11 | Charles (BOH) | Suggested to cover unit test cases. Should add dedicated files for scripts and styles | NA | 2026-03-11 | None | 1. Custom Url is empty -> Click eye icon. Navigating to empty page 2. Daily recurrence - Set default value to 1 3. Monthly recurrence - Change 5th to Last 4. Breadcrumb - Change Add Task to Edit task after save | NA | Internal POV done on 03/04/2026. Working on POV comments. Next POV happened on 06/04/2026. Reasons for story points exceeded: 1. Initially, development started using Kendo controls, but later it was confirmed to proceed with Vega controls which causes revisiting part of the implementations again 2. As this was the first time implementing Vega controls, some additional time was required to understand it. 3. The requirement included a specific dropdown behavior that needed customization using Vega controls to match the expected UI design 4. Additional effort was spent ensuring the UI matched the design specifications 5. Since this is first story with BOH, it took time to align with existing application's coding standards and structure | NA
2 | FOH Wave | 2026-02-27 | 2026-03-12 | 26.5 - Sprint 1 | Sabir | 21786 | [WAVE] Mosaic BOH - (2) User Tasks - Add to the Setup - UI Implementation | Story Completed | 3 | 7.5 | 30 | 2026-02-27 | 2026-03-09 | Sabir | Rajiv (BOH) | When O&I is disabled.. Inventory has different submenu’s | Rajiv (BOH) | 1. Remove the hard-coded value in controller instead use resource files 2. Revert this blank Line 3. Remove the hard-coded value in contants instead use resource files 4. Lable name should displayed from resource file. 5. use seperate css file from styles. | 47657 | 2026-03-09 | 2026-03-10 | Charles (BOH) | None | NA | 2026-03-10 | None | 1. User Task list under setup - need to change the position 2. "Links User To" - Rename it | NA | Reasons for story points exceeded: 1. Initially, development started using Kendo controls, but later it was confirmed to proceed with Vega vontrols which causes revisiting part of the implementations again 2. As this was the first time implementing Vega controls, some additional time was required to understand it. 3. The requirement included a specific dropdown behavior that needed customization using Vega controls to match the expected UI design 4. Additional effort was spent ensuring the UI matched the design specifications 5. Since this is first story with BOH, it took time to align with existing application's coding standards and structure | NA
3 | FOH Wave | 2026-02-27 | 2026-03-12 | 26.5 - Sprint 1 Stretch | Subbulakshmi | 51803 | MFOH - Automation (Smoke) - Kaleida changes update to the close day search screen & close day maintenance screen | Story Completed | 2 | 3.5 | 14 | 2026-03-06 | 2026-03-10 | NA | NA | NA | NA | NA | 47738 | 2026-03-10 | 2026-03-11 | NA | NA | NA | 2026-03-11 | NA | NA | NA | None | NA
4 | FOH Wave | 2026-02-27 | 2026-03-12 | 26.5 - Sprint 1 Stretch | Balamurugan | 52099 | [Wave]Mosaic BOH - Transfers - Bulk Replace (1) | Story Being Developed | 5 | 7 | 28 | 2026-03-06 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | None | NA
6 | FOH Wave | 2026-02-27 | 2026-03-12 | 26.5 - Sprint 1 Stretch | Vidhya | 47929 | [WAVE] Mosaic BOH - (5) User Tasks - Assigning Users | Story Being Developed | 5 | 2.25 | 9 | 2026-03-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | None | NA
7 | FOH Wave | 2026-02-27 | 2026-03-12 | 26.5 - Sprint 1 Stretch | Sabir | 52062 | [Wave]Mosaic BOH - Transfers - Bulk Add (2) - UI Only | Story Being Developed | 8 | 1.5 | 6 | 2026-03-12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | None | NA

## Dashboard (2) (hidden)
Current Sprint | #N/A | Current Sprint Sheet | #N/A | Sprint Start Date | #N/A | Sprint End Date |  | #N/A | Application Name | FOH Wave | sabir.shaikh@relevantz.com;subbulakshmi.namasivayam@relevantz.com;vidhya.subramani@relevantz.com;balamurugan.kandasamy@relevantz.com |  | hemanath.jayaraman@relevantz.com;sabir.shaikh@relevantz.com;subbulakshmi.namasivayam@relevantz.com;vidhya.subramani@relevantz.com | satarupa.mohanty@relevantz.com;ashwin.majella@relevantz.com;ganapathiraman.balasubramanian@relevantz.com;subhasri.ponnappan@relevantz.com;hemanath.jayaraman@relevantz.com;subbulakshmi.namasivayam@relevantz.com;vidhya.subramani@relevantz.com;sabir.shaikh@relevantz.com
Sprint Type | Sprint # | Sprint Start Date | Sprint End Date | Assigned | Completed | Story points introduced/removed | Sprint Summary | Accomplishments | Remarks | Retro Points (Internal & External) | Planned Leave | Total Leave | Data sanity Audit Status | AuditDate
#N/A | 4.15 - Sprint 4 | 2024-01-05 | 2024-01-18 | 28 | 28 | 0 |  |  | Regression Sprint so completed all the modules testing, No code review comments / Defects applicable. Also we fixed few regression defects. | Internal: External:
#N/A | 4.16 - Sprint 1 | 2024-01-19 | 2024-02-01 | 26 | 23 | 0 |  |  | Developers supported to clear the QA backlogs. [Testing Stories = 18, Development Stories = 8 Total Sprint Stories =20 completed = 20; Stretch Stories = 6 completed = 3] | Internal: External:
#N/A | 4.16 - Sprint 2 | 2024-02-02 | 2024-02-15 | 41 | 39 | 0 |  |  | Developers supported to clear the QA backlogs. | Internal: External:
#N/A | 4.16 - Sprint 3 | 2024-02-16 | 2024-02-29 | 35 | 35 | 0 |  |  | Got appreciation for a feature developed in the sprint and also in the sprint review demo from stake holder (#42670) | Internal: External:
#N/A | 4.16 - Sprint 4 | 2024-03-01 | 2024-03-14 | 19 | 30 | 0 |  |  | Stretch Story: 11-SP | Internal: External:
#N/A | 4.16 - Sprint 5 | 2024-03-15 | 2024-03-28 | 38 | 38 | 0 |  |  | Regression Sprint so completed all the modules testing, No code review comments / Defects applicable. Also we fixed few regression defects. Appreciation on Retro:Regression went well | Internal: External:
#N/A | 4.17 - Sprint 1 | 2024-03-29 | 2024-04-11 | 32 | 32 |  |  |  | Regression wrap up was done in this sprint and along with that completed few stretch stories(Sprint Story only 13SP for the regression wrap up). | Internal: External:
#N/A | 4.17 - Sprint 2 | 2024-04-12 | 2024-04-25 | 21 | 39 | 0 |  |  | Completed all the assigned stories and addition to that completed Stretch Stories - 18 SP. | Internal: External:
#N/A | 4.17 - Sprint 3 | 2024-04-26 | 2024-05-09 | 29 | 10 | 0 |  |  | Completed all the stories - 29 SP in Sprint and 10 SP in stretch. Onsite team was on PTO, so no one there to approve the PR. Carryforwading 21 SP in sprint and 8 SP in stretch to next sprint as per Gary's suggestion. | Internal: External:
#N/A | 4.17 - Sprint 4 | 2024-05-10 | 2024-05-23 | 13 | 13 | 0 |  |  | Regression Sprint(Targeted) so completed all the modules testing, Also we fixed few regression defects. Stretch Story: 5-SP Appreciation on Retro:Regression went well | Internal: External:
#N/A | 4.18 - Sprint 1 | 2024-05-24 | 2024-06-06 | 40 | 32 | 0 |  |  | Carryforwaded one story 8 SP, as POV with onsite team need to done. | Internal: External:
#N/A | 4.18 - Sprint 2 | 2024-06-07 | 2024-06-20 | 13 | 21 | 0 |  |  | Completed all the committed stories. Stretch Story: 8-SP | Internal: External:
#N/A | 4.18 - Sprint 3 | 2024-06-21 | 2024-07-18 | 44 | 44 | 22 |  |  | Completed all the committed stories. Supported to clear the QA backlogs. Stretch Story: 22-SP. Appreciation on Retro: For helping on QA backlogs | Internal: External:
#N/A | 4.18 - Sprint 4 | 2024-07-19 | 2024-08-01 | 37 | 37 | 37 |  |  | No delevopment stories added to sprint. Supported to clear the QA backlogs. Stretch Story: 37-SP. | Internal: External:
#N/A | 4.18 - Sprint 5 | 2024-08-02 | 2024-08-15 | 15 | 15 | 3 |  |  | Completed the committed stories. Supported to clear the QA backlogs. 14-SP completed development and waiting to raise PR. Stretch Story: 3-SP. | Internal: External:
#N/A | 4.18 - Sprint 6 | 2024-08-16 | 2024-08-29 | 21 | 21 | 7 |  |  | Completed the committed stories. Supported to clear the QA backlogs. Stretch Story: 11-SP. | Internal: External:
#N/A | 4.18 - Sprint 7 | 2024-08-30 | 2024-09-12 | 38 | 38 | 8 |  |  | Note: 1. Related to fix for 4.17: There was an issue with Student Import potential match catch logic. From Steve: a parsing issue - the birthdate of 09112009 fails to parse w/the code being used. It's trying to parse with only this pattern MM/dd/yyyy (hardcoded) 2. Related to hotfix for CPS: There was an issue found at MSB end in their API. Data is not being sent to Mosaic due an issue with the date. It can be fixed at either end (MSB or Mosaic) but if is fixed in Mosaic it will be a simple fix because if MSB team fix it may take much more time. The real issue is MSB is expecting for a date time for start and end date. Currently we send only date and due to that data is not pulled properly. Completed all regression stories in sprint. Stretch Story: 8-SP | Internal: External:
#N/A | 4.19 - Sprint 1 | 2024-09-13 | 2024-09-26 | 31 | 31 | 0 |  |  | CRC Internal -- 2 CRC External -- 0 QA Defects -- 3 (1-Rejected) Escaped Defects -- 0 Completed all the committed stories. Supported to clear the QA backlogs. Stretch Story: 18-SP. 45834 is POC which is Carry Forwarded | Internal: External: Appreciation on Retro: For helping on QA backlogs
#N/A | 4.19 - Sprint 2 | 2024-09-27 | 2024-10-24 | 33 | 45.5 | Introduced - 12.5 |  |  | CRC Internal -- 4 CRC External -- 0 QA Defects -- 8 (2-Rejected) Escaped Defects -- 0 Supported to clear the QA backlogs. Stretch Story: 20-SP. | Internal: Alpha recieved appreciation for support in dashboard. Jagan and Arvinth recieved appreciation for good presentation in sprint review. External: Recieved appreciation from Tino for Dashbord Story done by Subha. Appreciation on Retro: For helping on QA backlogs
#N/A | 4.19 - Sprint 3 | 2024-10-25 | 2024-11-07 | 16 | 35 | Introduced - 19 |  | Feature Flags, Student Barcode Report Update, Louisiana SFS-8A Report update, and Defects | CRC Internal -- 0 CRC External -- 1 QA Defects -- 2 Escaped Defects -- 0 Supported to clear the QA backlogs. Stretch Story: 19-SP. | Internal: External:
#N/A | 4.19 - Sprint 4 | 2024-11-08 | 2024-11-21 | 25 | 33 | Introduced - 8 |  | Improvements to Scheduler Task, Showing Actual Bank Deposit Amount in Online Payment Detail Report, Update to Alachua Meal Count export(2 decimal places to labor hours), and Defects | CRC Internal -- 0 CRC External -- 0 QA Defects -- 3 (2-Rejected) Escaped Defects -- 0 Stretch Story: 8-SP. | Internal: Online payment report story done without any deviation. External:
#N/A | 4.19 - Sprint 5 | 2024-11-22 | 2024-12-19 | 60 | 70 | Introduced - 10 |  | Add Ability to Print Machine Info, Add date of inactive to Student Maintenance, Add Notes to Elig Record Report, Add Active Filter to User Assignments Report, Defects, and then begin 4.19 Regression Testing. | CRC Internal -- 2 CRC External -- 1 QA Defects -- 3 Escaped Defects -- 0 Stretch Story: 10-SP. | Internal:Change comment,Change in adding the SQL paramer External:Merge conflict with revision history
#N/A | 4.20 - Sprint 1 | 2024-12-20 | 2025-01-16 | 35 | 46 | Introduced - 12 |  | multiple Defects for 4.19 and complete 4.19 Regression, Add report for “Schools not in School Group”, and Add new report type to POS Roster Reports | Release Date - March 2025 (Tentative) CRC Internal -- 1 CRC External -- 0 QA Defects -- 15 (1-Rejected) Escaped Defects -- 0 Stretch Story: 12-SP. | Internal: External: Appreciation on Retro: For helping on QA backlogs
#N/A | 4.20 - Sprint 2 | 2025-01-17 | 2025-01-30 | 22 | 27 | Introduced - 5 |  | Menu Management Improvements(Assign POS Menus to multiple POS numbers & Re-Alphabetize Menu Products), Dashboard update(CPS), Speed-e Mode option to fulfill Meal Order or not, and use CEP Reimbursement Calculations in Claim Report(KDE) | Release Date - March 2025 (Tentative) CRC Internal -- 0 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 5-SP. | Internal: External: Appreciation on Retro: Mike(QA) appreciated for helping on QA backlogs
#N/A | 4.20 - Sprint 3 | 2025-01-31 | 2025-02-13 | 25 | 31 | Introduced - 6 |  | Add Student Effective Date and Eligibility Reason to Student Maint., Attaching Verification Reports, Add Serving Period Program and Serving Period droplist to Special Provision Edit Check Report, Performance Improvements to Imports(CPS), and Defect Fixes | Release Date - March 2025 (Tentative) CRC Internal -- 0 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 6-SP. | Internal: External: Appreciation on Retro: Mike(QA) appreciated for helping on QA backlogs
#N/A | 4.20 - Sprint 4 | 2025-02-14 | 2025-02-27 | 38 | 38 | Introduced - 0 |  | 4.20 Regression Testing | Release Date - March 2025 (Tentative) CRC Internal -- 0 CRC External -- 0 QA Defects -- 13 Escaped Defects -- 0 Stretch Story: 0 | Internal: External: Appreciation on Retro: Mike(QA) appreciated for helping on QA backlogs and Regression Testing completion
#N/A | 4.21 - Sprint 1 | 2025-02-28 | 2025-03-13 | 26 | 31 | Introduced - 5 |  | Tyler-MUNIS Financial Export(NC), Adding Checks to Student Account Summary Report, Label Format Options to Barcode Report | CRC Internal -- 4 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 0 | Internal: External:
#N/A | 4.21 - Sprint 2 | 2025-03-14 | 2025-03-27 | 32 | 32 | Introduced - 0 |  | North Carolina Export, Ability to see transactions marked for review(SL), A La Carte Report Update, Ability to Add Transactions after Re-opening a day, and adding CEP ISP calculations to Chartwell’s Export | CRC Internal -- 1 CRC External -- 2 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 0 | Internal: External: Appreciation on Retro: Mike(QA) appreciated for helping on QA backlogs
#N/A | 4.21 - Sprint 3 | 2025-03-28 | 2025-04-10 | 31 | 34 | Introduced - 3 |  | CPS Dashboard Improvements, IEG Updates, ‘Carryover Expiration Date’ added as Import field, adding, NC SFS-4 Export update, and Adding ISP values for Mult schools. | CRC Internal -- 3 CRC External -- 1 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 0 | Internal: External:
#N/A | 4.21 - Sprint 4 | 2025-04-11 | 2025-04-24 | 41 | 33 | Introduced - 0 |  | 4.21 Regression Testing | CRC Internal -- 1 CRC External -- 0 QA Defects -- 3 Escaped Defects -- 0 Stretch Story: 0 | Internal: External: Appreciation for completing most of the regression stories eventhough it is a full regression
#N/A | 4.22 - Sprint 1 | 2025-04-25 | 2025-05-08 | 35 | 31 | Introduced - 3 |  | Wrap up 4.21 Regression(Defects found), Adding new templates to Custom Reports, Tier Model, Add Menu Product Sold Qtys to Daily Sales Preview, and MSB Reconciliation. | CRC Internal -- 5 CRC External -- 0 QA Defects -- 2 Escaped Defects -- 0 Stretch Story: 0 | Internal: External:
#N/A | 4.22 - Sprint 2 | 2025-05-09 | 2025-05-22 | 30 | 38 | Introduced - 8 |  | Adding new templates to Custom Reports, Tier Model, State Level EIG updates, and Admin View of Real Time Transactions updates. | CRC Internal -- 1 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 0 | Internal: External:
#N/A | 4.22 - Sprint 3 | 2025-05-23 | 2025-06-05 | 40 | 37.75 | Nil |  | Cutom Report for Eligibility Student Listing | CRC Internal -- 0 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 3 | Internal: External:
#N/A | 4.23 - Sprint 1 | 2025-06-06 | 2025-06-18 | 10 | 10 | Introduced - 21 |  |  | CRC Internal -- 2 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 4 | Internal: External:
#N/A | 4.23 - Sprint 2 | 2025-06-19 | 2025-07-03 | 20 | 20 | Introduced - 16 |  | Supplemental Programs Claim Report | CRC Internal -- 1 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 3 | Internal: External:
#N/A | 4.23 - Sprint 3 | 2025-07-04 | 2025-07-17 | 14 | 14 | Introduced-7 |  | Custom Report for Transaction History, Modifications to Louisiana SFS-8C Report | CRC Internal -- 4 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 4 | Internal: External: What went well: Successfully completed the assigned stories What didn't go well: Nil
#N/A | 4.23 - Sprint 4 | 2025-07-18 | 2025-07-31 | 14 | 16 | Introduced - 17 |  | Defect fixes and 4.23 Regression testing | CRC Internal -- 2 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 7 | Internal: External: What went well: Successfully completed the Regression testing, Completed the assigned stories What didn't go well: Nil
#N/A | 4.24 - Sprint 1 | 2025-08-01 | 2025-08-14 | 12 | 15 | Introduced - 15 |  | Support for Credit Card in Additional Meal Programs for Reports,Delete functionality for User Custom Report | CRC Internal -- 11 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 6 | Internal: External: What went well: Successfully completed the assigned stories What didn't go well: Nil
#N/A | 4.24 - Sprint 2 | 2025-08-15 | 2025-08-28 | 10 | 13 | Introduced - 22 |  | Dashboard feature for copy and enlarge wiidgets, implemented new datasource in custom report. | CRC Internal -- 1 CRC External -- 0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 5 | Internal: External: What went well: Successfully completed the assigned stories. Successfully completed the dashboard related features. What didn't go well: Nil
#N/A | 4.24 - Sprint 3 | 2025-08-29 | 2025-09-11 | 8 | 18 | Introduced - 28 |  | New Template for Daily Sales Summary Report,Daily Sales By Serving Line Report,Dashboard UI Enhancement and Other Reports Improvements, Automation | CRC Internal -- 1 CRC External -- 0 Peer Testing - 1 POV Comments - 4 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 7 | Internal: External: What went well: Completed Forecast and lot more, Automation progress, Hosted platforms - SYSU, All schools back in session, Esclation down from previous years (Note: Esclations from coustomer support are handled by client developer Steve) What didn't go well: Lost Ying to BOH team Esclations
#N/A | 4.24 - Sprint 4 | 2025-09-12 | 2025-09-25 | 14 | 15 | Introduced - 11 |  | Defect fixes and 4.24 Regression testing | "CRC Internal --0 CRC External -- 0 Peer Testing - 3 POV Comments - QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 4" | Internal: External: What went well: Offshore Completed regression and defects including testing, Completed Forecast and more, Defects fixed into releases What didn't go well: Esclations (Note: Esclations from coustomer support are handled by client developer Steve), Added items in last minute to include in release
#N/A | 4.25 - Sprint 1 | 2025-09-26 | 2025-10-09 | 13 | 13 | Introduced - 16 |  | Modifications to Operating Days, new filter for ‘Participation by’ to Standard Claim Report, and New Template to ‘Daily Sales By Serving Line Report’. | CRC Internal -- 3 CRC External -- 0 Peer Testing - 2 POV Comments - 4 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 4 | Internal: External: What went well: Completed more than Forecast , Esclations (not too bad this week), mike completed testing before PTO, Team completed rest of testing after Mike PTO What didn't go well: Apigee issue (platformops and apigee team)
#N/A | 4.25 - Sprint 2 | 2025-10-10 | 2025-10-23 | 15 | 21 | Introduced - 18 | New Dashboard Widgets, Ability to flip between Apigee & Existing endpoints, ‘Participation By’ filter to Supplemental Programs Claim Report, Tyler Munis Export Modifications, update to VA SNP-12 Report, Add Active Flag to Student Export Setup, and 4.24 Release Prep | New Dashboard Widgets, ‘Participation By’ filter to Supplemental Programs Claim Report, Updating report format to meet Mosaic standards | CRC Internal -- 0 CRC External -- 0 Peer Testing - 6 POV Comments - 6 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 6 | Internal: External: What went well: Completed more than Forecast What didn't go well: NA
#N/A | 4.25 - Sprint 3 | 2025-10-24 | 2025-11-06 | 12 | 23 | Introduced - 23 | Adding a Student Debt Chart to the Dashboard, Replacing Master Serving Period with Serving Period Program, New ‘Group By School’ filter to Students w/out an Elig. Determination Report, DC Import Improvements, and NJ Master Eligibility List report Modifications | Export 'User Created Custom Reports', 'User Assignments Report' to meet Mosaic Standard, Legacy imports are moved to Utilities | CRC Internal -- 0 CRC External -- 0 Peer Testing - 1 POV Comments - 6 QA Defects -- 0 Escaped Defects -- 0 Stretch Story: 10 | Internal: External: What went well: Releases, Exceeded Forecast What didn't go well: Esclations (Note: Esclations from coustomer support are handled by client developer Steve)
#N/A | 4.25 - Sprint 4 | 2025-11-07 | 2025-11-20 | 10 | 12 | Introduced - 36 | IL WINS Export Scheduler Task, Importing Custom Report Format, Added new data source to report designer | IL WINS Export Scheduler Task, Importing Custom Report Format, NSS ID in Visual Report, Added new datasource to the Report designer | CRC Internal -- 15 CRC External -- 1 Peer Testing - 3 POV Comments - 2 QA Defects -- 2 Escaped Defects -- 0 Stretch Story: 10 | Internal: External: What went well: Hit Forecast, SNYK progress in stretch What didn't go well: CPS Release, Apigee work, MSB Endpoint Change.
#N/A | 4.25 - Sprint 5 | 2025-11-21 | 2025-12-18 | 23 | 37 | Introduced - 37 | New Templates for Custom Reports, New Data Sources for Report Designer, and 4.25 Regression Testing | Completed 4.25 regression testing with defect fixes. | CRC Internal -- 2 CRC External -- 0 QA Defects -- 2 Escaped Defects -- 0 Stretch Story: 8 Defects RC: 1. Calculation mismatch not captured in unit testing. 2. It is the data issue which occurred in other developer's DB. It is handled now. Internal CRC comments RC: 1. Missed to ensure SQL script file naming standards 2. Misunderstood the acceptance criteria | Internal: External: What went well: Insane no.of stories completed(Sp's), started using Browser Stack for automation. What didn't go well: Escalations, MSB Endpoint Change.
#N/A | 26.1 - Sprint 1 | 2025-12-19 | 2026-01-15 | 27 | 32 | Introduced - 30 | Support for Multiple Languages in SL, Automation, Meal Count Entry Audit Report, Feature flag changes | Completed Support for Multiple Languages in SL, Automation, Meal Count Entry Audit Report, Feature flag changes | CRC Internal -- 24 CRC External -- 2 QA Defects -- 4 Escaped Defects -- 0 Stretch Story: 9 Defects RC: 1. Missed UI validation for the textbox. 2. Missed to handle the scenario of enable/disable Language feature flag. 3. Missed to test around the UI changes 4. Missed to check Parent table column's lenght and Language tables column's length Internal CRC comments RC: 1. Missed UI validations 2. Missed SQL script file standards 3. Missed to ensure date format 4. Not keeping common table name in SQL script 5. Some implicit stuff needs to be incorporated as part of the requirement which I'm not aware of 6. I missed to clean up or refactor some portion of the SQL code | What went well: Completed the forecast and almost the same in the stretch. 2. Holidays. 3. 502 gateway Apigee issues solving (prod) What didn't go well: 365 migration, MSB from www to etransfer issue.
#N/A | 26.1 - Sprint 2 | 2026-01-16 | 2026-01-29 | 17 | 17 | Introduced - 0 | Updates to Meal Report and User Report, Mosaic BOH Knowledge transfer | Completed the Mosaic Standards for User Reports and Meals Reports, Mosaic BOH Knowledge transfer | CRC Internal -- 0 CRC External --0 QA Defects -- 1 Escaped Defects -- 0 Stretch Story: 0 Defects RC: 1. Pre existing UI design which was there originally. PO wanted to fix it as part of this story hence it was fixed. Internal CRC comments RC: None | Internal: External: What went well: Completed commit and stretch items. 2. 4.24 Hot fix/4.25 Beta 3. BOH KT What didn't go well: 1. Vending QA, 2. Missing App switcher script in 4.25 Beta 3. App switcher button is not always working. Recieved appretiaton from QA during retro that offshore helped to close the testing stories during the sprint end.
#N/A | 26.1 - Sprint 3 | 2026-01-30 | 2026-02-12 | 5 | 16 | Introduced - 30 | Modified Prepay Report to Mosaic Standard, Defect Fixes, Hide Tier Feature from UI BOH Reverse KT, Automation | Completed the Prepay Report to meet Mosaic Standard, BOH Reverse KT | CRC Internal -- 0 Peer testing - 1 CRC External -- 0 QA Defects -- 2 Escaped Defects -- 0 POV Comments - 5 Stretch Story: 13 CRC RC: Nil Defects RC: 1. css styling not handled and so improper visual spacing between UI components occured 2. Missed to show proper version format | "Internal: External: What went well: 1. Exceeded the forcast story points. 2. 4.25 release. What didn't go well: 1. Escalations, 2. 4.25 rused out(App switcher not working), 3. Dashboard issues." | 0 | 1
#N/A | 26.1 - Sprint 4 | 2026-02-13 | 2026-02-26 | 2 | 4 | Introduced - 26 | Add New Security page for Report Designer, Edit Report button to the Custom Reports UI, Automation | Completed the Report Designer feature in Security Page | CRC Internal -- 0 Peer testing - 0 CRC External -- 0 QA Defects -- 0 Escaped Defects -- 0 POV Comments - 0 Stretch Story: 4 CRC RC: Nil Defects RC: Nil | Internal: External: What went well: 1. Offshore work on regression, 2. Hosted Test environment(Mike getting builds up) What didn't go well: 1. SQL cypher(Not working with .460) | 1 | 5
#N/A | 26.5 - Sprint 1 | 2026-02-27 | 2026-03-12 | 6 | 8 | Introduced - 20 | User Tasks Maintenance and Setup, Automation | Added User Tasks Maintenance and Setup screen, Automation | CRC Internal -- 5 Peer testing - 3 CRC External -- 0 QA Defects -- 15 Escaped Defects -- 0 POV Comments - 6 Stretch Story: 4 CRC RC: 1. Missed to follow localization support (2) 2. Missed to follow exsiting coding standards (1) 3. unwanted code (1) 4. returning entity directly (1) Defects RC: 1. UI validations should be added properly (4) 2. UI design issues (8) 3. Data issue (3) | Internal: External: What went well: 1. Exceeded commit, 2. SQLCypher progress, 3. Regression completed on time | 3 | 5
#N/A | 26.5 - Sprint 2 | 2026-03-13 | 2026-03-26 | 13 | 13 | Introduced - 27 | User Assignment in User Task, Mosaic BOH - Transfers - Bulk Replace, Automation | User Assignment in User Task, Mosaic BOH - Transfers - Bulk Replace, Add, Delete | "CRC Internal -- 1 Peer testing - 4 CRC External -- 0 QA Defects -- 3 Escaped Defects -- 0 POV Comments - 11 Stretch Story: 6 CRC RC: 1. Missed to remove the unwanted code Defects RC: 1. UI design issues 2. Backend validation did not match the UI validation. (2) POV RC: Cosmetic changes (4) Sugeestions (3) Data issue (2) | Internal: External: What went well: 1. 26.1 Release 2. Exceeded commit What didn't go well: Apigee & WAF issues | 3 | 4.5
#N/A | 26.5 - Sprint 3 | 2026-03-27 | 2026-04-09

## 26.5 - Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 26.5 - Sprint 1 | 51349 | 51349 | Vidhya | Bounceback/Sub-Defect | 1. Alert message coming for Simple Task 2. Continue button is disabled / Continue button is not enabled when I Edit the details from Simple Task to Custom Link 3. Getting popup without edit details 4. Getting an error when editing the details from Custom link to Simple Task | Minor | Manual | Internal | Story Being Developed | 2026-03-12 |  | UI Validations
| 26.5 - Sprint 1 | 21786 | 21786 | Sabir | Bounceback/Sub-Defect | 1. Alignment Issues in User Task Search Screen 2. Lengthy text for Task Name / Test Description 3. Data showing incorrectly 4. If I click the Hide Filters, Reset is not working 5. Selected Value is not updated 6. When O&I is disabled, still User task created using O& I, I think it should not come 7. Recurrence is showing Yearly instead of Annually 8. Newly added record should be showing in first but now it shows last 9. Data is not showing based on filters 10.Assigned To should show only Name not Username 11. Text wrap issue in Status column | Significant | Manual | Internal | Story Being Developed

## 26.1 - Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2026-02-13 | 2026-02-26 | 26.1 - Sprint 4 - Stretch | Vidhya | 51349 | [WAVE] Mosaic BOH - (3) User Tasks - Add/Edit Tasks | Story Being Developed | 13 | 12 | 48 | 2026-02-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH Wave | 2026-02-13 | 2026-02-26 | 26.1 - Sprint 4 | Subbulakshmi | 51456 | MFOH (WAVE) - Add a new security page for Report Designer | Story Completed | 1 | 1 | 4 | 2026-02-13 | 2026-02-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | FOH Wave | 2026-02-13 | 2026-02-26 | 26.1 - Sprint 4 | Subbulakshmi | 51457 | MFOH (WAVE) - Add an Edit Report button to the Custom Reports UI | Story Completed | 1 | 1 | 4 | 2026-02-13 | 2026-02-16 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | FOH Wave | 2026-02-13 | 2026-02-26 | 26.1 - Sprint 4 - Stretch | Subbulakshmi | 51803 | MFOH - Automation (Smoke) - Kaleida changes update to the close day search screen & close day maintenance screen | Story Being Developed | 3 | 2.5 | 10 | 2026-02-17 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | FOH Wave | 2026-02-13 | 2026-02-26 | 26.1 - Sprint 4 - Stretch | Subbulakshmi | 51804 | MFOH - Automation (Smoke) - Kaleida changes update to the close day report search screen & close day report maintenance screen | Story Completed | 2 | 3 | 12 | 2026-02-16 | 2026-02-19 | Subbulakshmi | NA | NA | NA | NA | 47411 | 2026-02-20 | 2026-02-20 | Subha | NA | NA | 2026-02-20 | NA | NA | NA | NA | NA
6 | FOH Wave | 2026-02-13 | 2026-02-26 | 26.1 - Sprint 4 - Stretch | Sabir | 21786 | [WAVE] Mosaic BOH - (2) User Tasks - Add to the Setup - UI Implementation | Story Being Developed | 8 | 10.5 | 42 | 2026-02-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Nested Menu dropdown using Vega control is new for FOH and BOH team also. we ask help for Vega technical team. They sent link for refrence. Based on that reference i am trying to implement Nested Menu dropdown. that is the reason story points exceed. | NA

## 26.1 - Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments

## 26.1 - Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 | Subbulakshmi / Hemanath Jayaraman / Sabir / Vidhya | 51719 | MFOH [WAVE] - Knowledge Transfer from Mosaic BOH Team (Continuation Story) | Story Completed | 5 | 14.75 | 59 | 2026-01-30 | 2026-02-06 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Sabir | 51647 | MFOH [WAVE] - Add a School as an Order By option to the Custom Student Report (New Hanover) | Story Need More Info | 2 | 0.5 | 2 | 2026-01-30 | 2026-01-30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | None | NA | NA | needs clarification with gary(client) | NA
3 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Vidhya | 51456 | MFOH (WAVE) - Add a new security page for Report Designer | Story Ready For Testing | 3 | 4 | 16 | 2026-01-30 | 2026-02-04 | Vidhya | Sabir | None | Sabir | None | 47222 | 2026-02-12 | 2026-02-12 | Subha | None | Steve | 2026-02-12 | None | 1) POV Date: 02/09/2025 The field level security wasn't working 2) POV Date: 02/10/2025 The Main security setting for report designer was unchecked in both central and local, but still the report designer is visible in the reports menu. | NA | Exceeded the given time because there is some issue with the existing Custom Report node which has been discussed to be fixed along with this story. Actual implementation for this story was done and finished the POV on 02/04/2026 | Meets Expectation
4 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Hemanath / Vidhya | 51704 | MFOH [WAVE] - Hide Tier Feature from Mosaic Screens | Story Completed | 3 | 3.375 | 13.5 | 2026-02-02 | 2026-02-03 | Hemanath | Vidhya | Security field popup spacing needs to be adjusted | Vidhya | None | 47180 | 2026-02-10 | 2026-02-10 | Subha | None | Steve | 2026-02-10 | None | None | None | None | Meets Expectation
5 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Subbulakshmi | 51751 | MFOH [WAVE] - Automation (50749) | Story Completed | 2 | 2 | 8 | 2026-02-03 | 2026-02-05 | Subbulakshmi | NA | NA | NA | NA | 47153 | 2026-02-09 | 2026-02-09 | Subha | None | None | 2026-02-09 | None | NA | NA | None | Meets Expectation
6 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Sabir | 51755 | MFOH [WAVE] - Modify the 'Prepay Report' to meet Mosaic Standard | Story Completed | 3 | 3 | 12 | 2026-02-04 | 2026-02-05 | Sabir | Ashwin | NA | Ashwin | NA | 47176 | 2026-02-10 | 2026-02-10 | Subha | None | None | 2026-02-10 | None | POV Date: 02/05/2025 1) Serving date header was misplaced 2) There was an empty column added for the totals 3) Alignment issue with the serving period header | NA | None | Meets Expectation
7 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Hemanath / Vidhya | 51785 | MFOH [WAVE] - Add a Homeroom filter to NJ Master Eligibility List Report | Story Completed | 3 | 3.375 | 13.5 | 2026-02-04 | 2026-02-05 | Hemanath | Vidhya | None | Vidhya | None | 47165 | 2026-02-10 | 2026-02-10 | Subha | None | Steve | 2026-02-10 | None | None | NA | None | Meets Expectation
8 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Vidhya | 26732 | MFoH - Reports - Custom - Daily Sales and A la Carte report templates broken | Defect Fixed | 0 | 0 | 6 | 2026-02-05 | 2026-02-05 | Vidhya | Subbulakshmi | None | Hemanath | None | 47108 | 2026-02-05 | 2026-02-05 | Subha | None | Steve | 2026-02-05 | None | None | None | None | Meets Expectation
9 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Subbulakshmi | 51803 | MFOH - Automation (Smoke) - Kaleida changes update to the close day search screen & close day maintenance screen | Story Being Developed | 5 | 1.5 | 6 | 2026-02-09 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Vidhya | 51457 | MFOH (WAVE) - Add an Edit Report button to the Custom Reports UI | Story Ready For Testing | 1 | 0.75 | 3 | 2026-02-06 | 2026-02-06 | Vidhya | Sabir | None | Sabir | None | 47223 | 2026-02-12 | 2026-02-12 | Subha | None | Steve | 2026-02-12 | None | None | NA | There was an issue in the Custom Report when we create it with the name "Student Listing Report" due to name conflicts in Kaleida changes. We have fixed it along with this story | Meets Expectation
11 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Sabir | 51829 | MFOH [WAVE] Mosaic BOH - User Tasks - Add to Security Group - (1) | Story Being Developed | 3 | 3 | 12 | 2026-02-06 | 2026-02-10 | Sabir | NA | NA | NA | NA | NA | NA | NA | NA | None | NA | NA | NA | none |  | POV is completed. waiting for peer testing and code review
12 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Subbulakshmi | 51804 | MFOH - Automation (Smoke) - Kaleida changes update to the close day report search screen & close day report maintenance screen | Story Being Developed | 3 | 1.5 | 6 | 2026-02-10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
13 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Vidhya | 26760 | MFOH [WAVE] - Fix the error when exporting the dashboard widget | Defect Ready For Testing | 2 | 1.5 | 6 | 2026-02-10 | 2026-02-10 | Vidhya | Subbulakshmi | None | Subha | None | 47179 | 2026-02-10 | 2026-02-10 | Subha | None | Steve | 2026-02-10 | None | NA | NA | None | Meets Expectation
14 | FOH Wave | 2026-01-30 | 2026-02-12 | 26.1 - Sprint 3 - Stretch | Vidhya | 26749 | MFOH [WAVE] - Fix the console error that blocks the save and retrieval of the dashboard | Defect Being Fixed | 0 | 0 | 12 | 2026-02-09 | 2026-02-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation

## 26.1 - Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 26.1 - Sprint 3 - Stretch | 51704 | 51704 | Hemanath | Bounceback/Sub-Defect | Spacing issue in District Maintenance screen - Others tab | Minor | Manual | Internal | Story Completed | 2026-02-11 | 2026-02-12 | Design Issue | Spacing issue in District Maintenance screen - Others tab
| 26.1 - Sprint 3 - Stretch | 51755 | 51755 | Sabir | Bounceback/Sub-Defect | Reports generated by the Mosaic POS system are showing "0.0.0.0" in the footer instead of displaying the correct version number like Mosaic POS v0.0.0.0 | Minor | Manual | Internal | Story Completed | 2026-02-12 | 2026-02-12 | Design Issue | Reports generated by the Mosaic POS system are showing "0.0.0.0" in the footer instead of displaying the correct version number like Mosaic POS v0.0.0.0

## 26.1 - Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2026-01-16 | 2026-01-29 | 26.1 - Sprint 2 | Subbulakshmi | 51358 | MFOH [WAVE] - Automation (50441) | Story Completed | 1 | 0.75 | 3 | 2026-01-16 | 2026-01-21 | NA | NA | NA | NA | NA | 46772 | 2026-01-21 | 2026-01-21 | Subha | None | Steve | 2026-01-21 | None | None | None | None | Meets Expectation
2 | FOH Wave | 2026-01-16 | 2026-01-29 | 26.1 - Sprint 2 | Hemanath Jayaraman | 51469 | MFOH - Modify the 'Meal Report' to meet Mosaic Standard | Story Completed | 1 | 3 | 12 | 2026-01-16 | 2026-01-29 | Hemanath | Sabir | None | Sabir | None | 46737 | 2026-01-20 | 2026-01-20 | Subha | None | Steve | 2026-01-20 | None | None | None | This is a testing only story. Testing started from 23rd Jan and found some observations. Afterweekend and few days of planned PTO this story has been tested and closed on 29th Jan as per the plan | Meets Expectation
3 | FOH Wave | 2026-01-16 | 2026-01-29 | 26.1 - Sprint 2 | Sabir Shaikh | 51470 | MFOH [WAVE] - Modify the 'User Report' to meet Mosaic Standard | Story Completed | 1 | 1 | 4 | 2026-01-16 | 2026-01-16 | Sabir | Vidhya | None | Vidhya | None | 46739 | 2026-01-20 | 2026-01-20 | Subha | None | Steve | 2026-01-20 | None | None | None | None | Meets Expectation
4 | FOH Wave | 2026-01-16 | 2026-01-29 | 26.1 - Sprint 2 | Vidhya | 51458 | Change common table with category for Serving Period, Menu products, Void Reason, Medical alert (Default Language) | Story Completed | 1 | 1.75 | 7 | 2026-01-16 | 2026-01-21 | Vidhya | Hemanath | None | Hemanath | None | 46741 | 2026-01-20 | 2026-01-20 | Subha | None | Steve | 2026-01-20 | None | None | NA | None | Meets Expectation
5 | FOH Wave | 2026-01-16 | 2026-01-29 | 26.1 - Sprint 2 | Subbulakshmi / Hemanath / Sabir / Vidhya | 51125 | [WAVE] Mosaic FOH - Knowledge Transfer from Mosaic BOH Team | Story Completed | 13 | 41.125 | 164.5 | 2026-01-14 | 2026-01-29 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA

## 26.1 - Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 26.1 - Sprint 2 | 51469 | 51469 | Hemanath | Bounceback/Sub-Defect | 1. The serving period header in the first page has lot of empty spaces above and below the header 2. The next serving period header has no space after the 1st serving period grid | Minor | Manual | Internal | Defect Fixed | 2026-01-27 | 2026-01-27 | Design Issue | Pre existing one which was there originally. PO wanted to fix it as part of this story hence it was fixed.

## 26.1 - Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Hemanath Jayaraman | 51249 | [WAVE] Mosaic FOH - Add "App Switcher" to Feature Flag | Story Completed | 1 | 1 | 4 | 2025-12-18 | 2025-12-18 | Hemanath | Vidhya | None | Vidhya | None | 46319 | 2025-12-19 | 2025-12-19 | Subha | None | Ying | 2025-12-19 | None | None | None | None | Meets Expectation
2 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Hemanath Jayaraman | 51110 | MFOH [WAVE] - Add 'Default Language' to the User Maintenance screen | Story Completed | 3 | 2.5 | 10 | 2025-12-19 | 2025-12-22 | Hemanath | Vidhya | None | Vidhya | None | 46445 | 2026-01-06 | 2026-01-06 | Subha | We don't need to add extended property for the foreign key, which is needed for new columns or altered columns in the script. Remove that in the script. | Steve | 2026-01-06 | None | None | None | None | Meets Expectation
3 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Vidhya | 50856 | MFOH [WAVE] - Add a new template 'Extended Sales Report' to Custom > Report Templates | Story Completed | 1 | 0.5 | 2 | 2025-12-19 | 2025-12-19 | Vidhya | Hemanath | None | Hemanath | None | 46316 | 2025-12-19 | 2025-12-19 | Subha | None | Ying | 2025-12-19 | None | None | None | None | Meets Expectation
4 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Vidhya | 48154 | MFOH [WAVE] - Add a Language tab to POS Menu Products | Story Completed | 5 | 6 | 24 | 2025-12-22 | 2025-12-26 | Vidhya | Hemanath | None | Hemanath | None | 46484 | 2026-01-07 | 2026-01-07 | Subha | 1. Add 1_ and 2_ or the scripts in the order of execution | Steve | 2026-01-07 | None | POV Date: 12/26/2025 Pov Comment 1: The POS Display Name field (textbox) inside the add language pop up allows to save the language record only with blank spaces. POV Comment 2: During edit of a menu product, the language tab goes to the second line POV Comment 3: In the Add Language popup, there is a mismatch between the width of the Language and POS Display Name fields. | NA | None | Meets Expectation
5 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Subbulakshmi | 50857 | MFOH [WAVE] - Add a new template 'Revenue Report' to Custom > Report Templates | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | None | NA | NA | NA | NA | NA | NA | NA | NA | None | NA | None | Meets Expectation
6 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Sabir Shaikh | 51323 | MFOH [WAVE] - Add a Language tab to Void Reasons | Story Completed | 5 | 4 | 16 | 2025-12-29 | 2026-01-06 | Sabir | Vidhya | None | Vidhya | None | 46627 | 2026-01-13 | 2026-01-13 | Subhasri | 1.In this story, Mosaic.Web.csproj this file doesn't have any changes. If no changes required then remove this file. | Steve | 2026-01-13 | Remove instance of VoidReasonLanguage List in VoidReasonsWCF.cs | POV Date: 01/06/2026 POV Comment 1: There was an error message that shows up during the save of a void reason record (after sorting the column headers in the language tab and try clicking save). | NA | NA | Meets Expectation
7 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Sabir Shaikh | 51321 | MFOH [WAVE] - Add a Language tab to Medical Alerts | Story Completed | 3 | 2 | 8 | 2026-01-07 | 2026-01-08 | Sabir | Vidhya | None | Vidhya | None | 46594 | 2026-01-12 | 2026-01-12 | Subhasri | None | Steve | 2026-01-12 | None | None | NA |  | Meets Expectation
8 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Subbulakshmi | 51077 | MFOH [WAVE] - Add 'Default Language' to Feature Flag | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | None | NA | NA | NA | NA | NA | NA | NA | NA | None | NA | None | Meets Expectation
9 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Vidhya | 48514 | MFOH [WAVE] - Add a Language tab to Serving Period | Story Completed | 3 | 4.25 | 17 | 2026-01-02 | 2026-01-05 | Vidhya | Sabir | None | Sabir | None | 46480 | 2026-01-07 | 2026-01-07 | Subha | 1. Add 1_ and 2_ or the scripts in the order of execution 2. DB length is 50, but why is it restricted to 15 in the UI 3. Wrong date format | Steve | 2026-01-07 | None | POV Date: 01/05/2026 POV Comment 1: The font size of the values between the Language droplist and POS Display Name is mismatching. | NA | None | Meets Expectation
10 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Vidhya | 51322 | MFOH [WAVE] - Add a Language tab to POS Menu | Story Completed | 3 | 3.75 | 15 | 2026-01-06 | 2026-01-07 | Vidhya | Ashwin | Getting exception when click OK for the existing languages | Sabir | None | 46562 | 2026-01-09 | 2026-01-09 | Subha | It doesn’t have any changes, so remove this file. | Steve | 2026-01-09 | it's checking for if exits for name POSMenuLanguage, but it creates the table with name ServingLineMenuLanguage. So if you re-run the script it throws an error. | POV Date: 01/07/2026 POV Comment 1: There was an error message that shows up during the save of a POS Menu r record (after sorting the column headers in the language tab and try clicking save). | NA | None | Meets Expectation
| FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 | Vidhya | 51156 | MFOH [WAVE] - Add a new System Setting 'Default Language' | Story Completed | 1 | 0.5 | 2 | 2026-01-09 | 2026-01-09 | Vidhya | Sabir | None | Sabir | None | 46563 | 2026-01-09 | 2026-01-09 | Subha | None | Steve | 2026-01-09 | None | None | NA | None | Meets Expectation
11 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Hemanath Jayaraman | 50645 | [WAVE] Mosaic FOH(CPS C0224) - Meal Count Entry Audit Report | Story Completed | 13 | 18.5 | 74 | 2025-12-23 | 2026-01-13 | Hemanath | Arvinth | 1. If the selected month is current month or future month the data should not show for the future dates. 2.If a date has only non reimbursable meal count, that date should display in the report. 3. If a date has only ala carte or dept. count, that date should display in the report. | Arvinth | In the SPROC , 1.This condition is not required as the future year will not list down in the year dropdown. 2. We don’t need separate query for both NR meal and Alacarte/Dept 3. Add all the school name in actual query, instead of updating it separately. | 46628 | 2026-01-13 | 2026-01-13 | Subha | 1. A New method is added only for sorting the result set. This can be handled in the .cshtml file 2.Give a clear view of naming conventions for the script files as follows: InsertMealCountEntryAuditReport to Insert_MealCountEntryAudit_Report 3.[dbo].POSTransaction table is used in if NOT exists conditions, which is not recommended, as this will cause performance or screen freeze issues if it is a large district like CPS. Use any alternate way. 4.As discussed already in the catch-up call to use close day summary tables, I don’t see any summary table for the condition 5.I don’t see any query for a serving date that is closed and had 0 meal counts. | Steve | 2026-01-13 | None | POV Date: 01/09/2026 POV Comment 1: After performing a close day for a transaction (dated 1/9/26 and Breakfast Serving Period) done through Serving In the Classroom for a school, the report shows that particular school, that serving date, and that serving period in the report POV Comment 2: When the report is run for a school, the school is not showing in the display parameter section Once the above 2 gets fixed, please proceed to peer testing, code review, and PR. Its a basic standard that we follow for the mosaic reports and it will not be mentioned in the AC. | NA | None | Meets Expectation
12 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51353 | MFOH [WAVE] - Automation (50851) | Story Completed | 1 | 1 | 4 | 2025-12-26 | 2026-01-06 | None | NA | NA | NA | None | 46448 | 2026-01-06 | 2026-01-06 | Subha | None | Steve | 2026-01-06 | None | NA | NA | None | Meets Expectation
13 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51355 | MFOH [WAVE] - Automation (50854) | Story Completed | 1 | 1 | 4 | 2025-12-26 | 2026-01-06 | None | NA | NA | NA | None | 46449 | 2026-01-06 | 2026-01-06 | Subha | None | Steve | 2026-01-06 | None | NA | NA | None | Meets Expectation
14 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51354 | MFOH [WAVE] - Automation (50853) | Story Completed | 1 | 1 | 4 | 2025-12-29 | 2026-01-06 | None | NA | NA | NA | None | 46452 | 2026-01-06 | 2026-01-06 | Subha | None | Steve | 2026-01-06 | None | NA | NA | None | Meets Expectation
15 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51356 | MFOH [WAVE] - Automation (49952) | Story Completed | 2 | 2 | 8 | 2025-12-29 | 2026-01-06 | None | NA | NA | NA | None | 46451 | 2026-01-06 | 2026-01-06 | Subha | Suggested to add the Dashboard Testcases in Regression Test folder | Steve | 2026-01-06 | None | NA | NA | None | Meets Expectation
16 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51358 | MFOH [WAVE] - Automation (50441) | Story Being Developed | 3 | 4 | 16 | 2026-01-02 | None | None | None | None | None | None | None | None | None | None | Suggested to use string.empty instead of "" | None | None | None | None | None | None | None
17 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Hemanath Jayaraman | 51469 | MFOH - Modify the 'Meal Report' to meet Mosaic Standard | Story Being Developed | 3 | 2 | 8 | 2026-01-12 | [17 empty] | Meets Expectation
18 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Sabir Shaikh | 51470 | MFOH [WAVE] - Modify the 'User Report' to meet Mosaic Standard | Story Being Developed | 3 | 2 | 8 | 2026-01-12 | 2026-01-13
19 | FOH Wave | 2025-12-19 | 2026-01-15 | 26.1 - Sprint 1 Stretch | Vidhya | 51458 | Change common table with category for Serving Period, Menu products, Void Reason, Medical alert (Default Language) | Story Being Developed | 3 | 1.5 | 6 | 2026-01-13

## 26.1 - Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 26.1 - Sprint 1 | 48514 | 48514 | Vidhya | Bounceback/Sub-Defect | MFOH [WAVE] - Add a Language tab to Serving Period Getting on Error popup while I'm entered the POS Display name more than 20 Characters in Language tab Reproduction Steps: 1. Go to Setup> Initial Setup> Serving Period Search> Serving Period Maintenance 2. Go to Language tab 3. Click on Add Language and Select the Language from dropdown 4. Enter the POS Display Name more than 20 characters 5. Click on Save 6. Observe the Exception error | Minor | Manual | Internal | Story Completed | 2026-01-08 | 2026-01-09 | Validation is missing | Getting on Error popup while I'm entring the POS Display name more than 20 Characters in Serving Period Language tab
| 26.1 - Sprint 1 | 48514 | 48514 | Vidhya | Bounceback/Sub-Defect | MFOH [WAVE] - Add a Language tab to Serving Period Added Languages are not showing in Language tab after updating the Serving Period details when show and Hide the Default Language in Feature Flag Reproduction Steps: 1. Go to Setup> Initial Setup> Serving Period Search> Serving Period Maintenance 2. Go to Language tab 3. Click on Add Language and Select the Language from dropdown and Enter the POS Display Name 4. Click on Save 5. Login with Level 1 Support User(Terri) 6. Go to Setup> Initial Setup> District Search>District Maintenance>Other tab 7. Delete the Default Language in Feature Flag and Save it 8. Login with Level 2 User(Debbie) 9. Go to Setup> Initial Setup> Serving Period Search> Serving Period Maintenance 10. Update the Serving Period Name and Save it 11. Login with Level 1 Support User(Terri) 12. Go to Setup> Initial Setup> District Search>District Maintenance>Other tab 13. Add the Default Language in Feature Flag and Save it 14. Login with Level 2 User(Debbie) 15. Go to Setup> Initial Setup> Serving Period Search> Serving Period Maintenance 16. Click on updated Serving Period and Go to Language tab 17. Observe that issue(English Language only showing in Language tab) | Minor | Manual | Internal | Story Completed | 2026-01-08 | 2026-01-09 | Issue with Language tab data when the feature flag is enabled/disabled | Added Languages are not showing in Language tab after updating the Serving Period details when show and Hide the Default Language in Feature Flag
| 26.1 - Sprint 1 | 48154 | 48154 | Vidhya | Bounceback/Sub-Defect | MFOH [WAVE] - Add a Language tab to POS Menu Products Gettion on Exception when I choose/Upload/Remove the Menu Product Image and then default language(English) also not showing in Menu Product Language tab Reproduction Steps: 1. Go to Setup> System Settings and Options>Menu Product Search>Menu Product Maintenance 2. Click on Choose and Select Images 3. Go to Language Tab 4. Click on Save 5. Observe that Exception Error | Minor | Manual | Internal | Story Completed | 2026-01-09 | 2026-01-09 | Issue with Menu product images | Gettion on Exception when I choose/Upload/Remove the Menu Product Image and then default language(English) also not showing in Menu Product Language tab
| 26.1 - Sprint 1 | 51323 | 51323 | Sabir | Bounceback/Sub-Defect | MFOH [WAVE] - Add a Language tab to Void Reasons - Getting on Error popup while I'm entered the Void reason Description more than 50 Characters and try to save the added Languages in Language tab Reproduction Steps: 1. Go to Setup> System Settings and Options> Void Reason Search> Void Reason Maintenance 2. Enter the Void Description more than 50 characters 3. Go to Language tab 4. Click on Add Language 5. Select the Language from dropdown 6. Enter the POS Display Name 7. Click on Ok 8. Click on Save 9. Observe this Error popup message | Minor | Manual | Internal | Story Completed | 2026-01-13 | 2026-01-13 | Validation Missing | MFOH [WAVE] - Add a Language tab to Void Reasons - Getting on Error popup while I'm entered the Void reason Description more than 50 Characters and try to save the added Languages in Language tab

## 4.25 - Sprint 5-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Vidhya | 50850 | MFOH [WAVE] - Add an indication when the filters are applied in the Visual Report | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45868 | 2025-11-21 | 2025-11-21 | NA | NA | Steve | 2025-11-21 | None | NA | NA | None | Meets Expectation
2 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Sabir | 50851 | MFOH [WAVE] - Add a new Data Source 'Extended Daily Sales Summary Report' to Report Designer | Story Completed | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 45875 | 2025-11-21 | 2025-11-21 | NA | NA | Steve | 2025-11-21 | None | NA | NA | None | Meets Expectation
3 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Vidhya | 50852 | MFOH [WAVE] - Add a new Data Source 'Extended Sales Report' to Report Designer | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45867 | 2025-11-21 | 2025-11-21 | NA | NA | Steve | 2025-11-21 | None | NA | NA | None | Meets Expectation
4 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Sabir | 50855 | MFOH [WAVE] - Add a new template 'Extended Daily Sales Summary Report' to Custom > Report Templates | Story Completed | 3 | 2.5 | 10 | 2025-11-21 | 2025-11-24 | Sabir | Vidhya | None | Vidhya | None | 45989 | 2025-12-01 | 2025-12-01 | Subha | rename the script file name | Ying | 2025-12-01 | None | None | None | None | Meets Expectation
5 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Hemanath Jayaraman | 50853 | MFOH [WAVE] - Add a new Data Source 'Revenue Report' to Report Designer | Story Completed | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 45870 | 2025-11-21 | 2025-11-21 | NA | NA | Steve | 2025-11-21 | None | NA | NA | None | Meets Expectation
6 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Subbulakshmi | 50930 | MFOH [WAVE] - Automation (50722) | Story Completed | 1 | 1 | 4 | 2025-11-19 | 2025-11-21 | Subbulakshmi | NA | NA | NA | NA | 45879 | 2025-11-21 | 2025-11-21 | Subha | NA | Ying | 2025-11-21 | None | NA | NA | None | Meets Expectation
7 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Vidhya | 50728 | MFOH [WAVE] - Modify the Missing Sales Data Report to include the Sub-Site (CPS C0209) | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45869 | 2025-11-21 | 2025-11-21 | NA | NA | Steve | 2025-11-21 | None | NA | NA | None | Meets Expectation
8 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Sabir | 50721 | MFOH [WAVE] - Add a new template for Standard Claim to Custom Report | Story Completed | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 45872 | 2025-11-21 | 2025-11-21 | NA | NA | Steve | 2025-11-21 | None | NA | NA | None | Meets Expectation
9 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Vidhya / Sabir/Hemanath | 50954 | [WAVE] Mosaic - FOH 4.25(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 8 | 28 | 112 | 2025-12-03 | 2025-12-17 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
10 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Vidhya / Hemanath | 50956 | [WAVE]Mosaic - FOH 4.25(Regression) - Setup | Story Completed | 2 | 7 | 31 | 2025-12-08 | 2025-12-17 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Sabir | 50955 | [WAVE]Mosaic - FOH 4.25(Regression) - Utilities | Story Completed | 3 | 4.5 | 19 | 2025-12-08 | 2025-12-18 | Sabir | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Hemanath Jayaraman | 26441 | MFOH (4.25 Regression) - Credit Card Listing Report order by filter is not working | Defect Fixed | 0 | 0 | 0 | 2025-12-10 | 2025-12-11 | Hemanath | Vidhya | None | Vidhya | None | 46189 | 2025-12-12 | 2025-12-12 | Subha | None | Ying | 2025-12-12 | None | None | None | None | Meets Expectation
13 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Sabir | 26442 | MFOH (4.25 Regression) - Claim month is missing in Standard Claim Report Template | Defect Fixed | 0 | 0 | 0 | 2025-12-10 | 2025-12-10 | Sabir | Vidhya | None | Vidhya | None | 46199 | 2025-12-12 | 2025-12-12 | Subha | None | Ying | 2025-12-12 | None | None | None | None | Meets Expectation
14 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Sabir | 26444 | MFOH (4.25 Regression) - Mosaic Global Search textbox lists the custom sub report names | Defect Fixed | 0 | 0 | 0 | 2025-12-11 | 2025-12-11 | Sabir | Hemanath | None | Hemanath | None | 46201 | 2025-12-12 | 2025-12-12 | Subha | None | Ying | 2025-12-12 | None | None | None | None | Meets Expectation
15 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Vidhya | 26443 | MFOH (4.25 Regression) - User Maintenance Screen has a console error | Defect Fixed | 0 | 0 | 0 | 2025-12-11 | 2025-12-11 | Vidhya | Sabir | None | Sabir | None | 46186 | 2025-12-12 | 2025-12-12 | Subha | None | Ying | 2025-12-12 | None | NA | NA | None | Meets Expectation
16 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Vidhya | 26463 | MFOH (4.25 Regression) - Getting an Exception error while generating the Report using Display Type - Word/Word 2003 in Custom Report Templates | Defect Fixed | 0 | 0 | 0 | 2025-12-15 | 2025-12-15 | Vidhya | Hemanath | None | Hemanath | None | 46244 | 2025-12-16 | 2025-12-16 | Arvinth | None | Ying | 2025-12-16 | None | NA | NA | None | Meets Expectation
17 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 | Vidhya | 26464 | MFOH (4.25 Regression) - Alachua Skyward Financial Export success popup is not displayed | Defect Fixed | 0 | 0 | 0 | 2025-12-15 | 2025-12-15 | Vidhya | Hemanath | None | Hemanath | None | 46241 | 2025-12-16 | 2025-12-16 | Arvinth | None | Ying | 2025-12-16 | None | NA | NA | None | Meets Expectation
18 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 Stretch | Hemanath Jayaraman | 51249 | [WAVE] Mosaic FOH - Add "App Switcher" to Feature Flag | Story Being Developed | 1 | 1 | 4 | 2025-12-18 | 2025-12-18 | Hemanath | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | None | Meets Expectation
19 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 Stretch | Hemanath Jayaraman | 50857 | MFOH [WAVE] - Add a new template 'Revenue Report' to Custom > Report Templates | Story Being Tested | 8 | 7 | 29 | 2025-11-21 | 2025-12-01 | Hemanath | Sabir | None | Sabir | None | 46134 | 2025-12-09 | 2025-12-09 | Subha | None | Steve | 2025-12-09 | None | None | None | None | Meets Expectation
20 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 Stretch | Vidhya | 50856 | MFOH [WAVE] - Add a new template 'Extended Sales Report' to Custom > Report Templates | Story Being Developed | 13 | 13 | 56 | 2025-11-24 | 2025-12-18 | Vidhya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | None | Meets Expectation
21 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 Stretch | Sabir | 50854 | MFOH [WAVE] - Add a new Data Source 'Total Income Report' to Report Designer | Story Completed | 2 | 1.5 | 6 | 2025-11-25 | 2025-11-26 | Sabir | Vidhya | None | Vidhya | None | 46145 | 2025-12-10 | 2025-12-10 | Subha | None | Steve | 2025-12-10 | None | POV Comment: The name of the datasource is incorrect and doesn't match the name given in the AC | NA | None | Meets Expectation
22 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 Stretch | Sabir | 50858 | MFOH [WAVE] - Add a new template 'Total Income Report' to Custom > Report Templates | Story Completed | 8 | 7 | 27 | 2025-11-26 | 2025-12-02 | Sabir | Hemanath | None | Hemanath | None | 46146 | 2025-12-10 | 2025-12-10 | Subha | None | Steve | 2025-12-10 | None | None | None | None | Meets Expectation
25 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 Stretch | Hemanath Jayaraman | 51077 | MFOH [WAVE] - Add 'Default Language' to Feature Flag | Story Ready For Testing | 1 | 1 | 4 | 2025-12-17 | 2025-12-17 | Hemanath | Vidhya | None | Vidhya | None | 46277 | 2025-12-17 | 2025-12-17 | Subha | None | Ying | 2025-12-17 | None | None | None | None | Meets Expectation
23 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 Stretch | Subbulakshmi | 51041 | 51041 MFOH [WAVE] - Automation (50851) | Story Completed | 2 | 2 | 8 | 2025-11-28 | 2025-12-03 | Subbulakshmi | NA | NA | NA | NA | 46042 | 2025-12-03 | 2025-12-03 | Subha | None | Ying | 2025-12-03 | None | NA | NA | None | Meets Expectation
24 | FOH Wave | 2025-11-21 | 2025-12-18 | 4.25 - Sprint 5 Stretch | Subbulakshmi | 51042 | 51042 MFOH [WAVE] - Automation (50852) | Story Completed | 2 | 2 | 8 | 2025-12-01 | 2025-12-03 | Subbulakshmi | NA | NA | NA | NA | 46042 | 2025-12-03 | 2025-12-03 | Subha | None | Ying | 2025-12-03 | None | NA | NA | None | Meets Expectation

## 4.25 - Sprint 5-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 4.25 - Sprint 5 | 50721 | 50721 | Sabir | Bounceback/Sub-Defect | Incorrect data is showing in Participation total table in Standart Claim Report (Template) | Major | Manual | Internal | Defect Fixed | 2025-11-26 | 2025-11-28 | Design | Incorrect data is showing in Participation Total table in Standart Claim Report (Template) while I select the Filter is Participation by Entrollment
| 4.25 - Sprint 5 | 26441 | 26441 | Hemanath | Bounceback/Sub-Defect | Getting on Exception while generating the Credit card listing report when the Authorization number is empty | Minor | Manual | Internal | Defect Fixed | 2025-12-16 | 2025-12-16 | Data Issue | This is the data issue which occurred in other developer's DB. It is handled now.

## 4.25 - Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 | Vidhya | 50731 | MFOH [WAVE] - Add NSS ID to Visual Report (CPS) | Story Completed | 2 | 1.5 | 6 | 2025-11-07 | 2025-11-07 | Vidhya | Sabir | None | Sabir | None | 45692 | 2025-11-13 | 2025-11-13 | Subha | Change the procedure name properly and check in | Steve | 2025-11-13 | None | None | NA | None | Meets Expectation
2 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 | Sabir | 50722 | MFOH [WAVE] - Add a new Data Source 'Standard Claim' to Report Designer | Story Completed | 3 | 2 | 8 | 2025-11-07 | 2025-11-11 | sabir | Vidhya | NA | Vidhya | NA | 45648 | 2025-11-11 | 2025-11-11 | Subha | None | NA | 2025-11-11 | NA | POV Date: 11/11/25 1. Additional unrelated UI parameters were added to the report UI. | NA | NA | Meets Expectation
3 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 | Sabir | 50441 | MFOH [WAVE] - Import the format of the Custom Report | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45649 | 2025-11-11 | 2025-11-11 | Subha | 1.This class doesn’t have a serialize annotation 2.Change the method Name to IsCustomReportNameExists 3.Check the spelling in the method name. Also, change the method name to IsCustomReportNameExists. 4.Change the method name to IsFilePathExists | NA | 2025-11-11 | NA | NA | NA | NA | Meets Expectation
4 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 | Vidhya | 50712 | MFOH [WAVE] - Rename 'Serving Period Program' to Reimbursable Program | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45556 | 2025-11-07 | 2025-11-07 | NA | NA | Steve | 2025-11-07 | None | NA | NA | None | Meets Expectation
5 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 | Hemanath Jayaraman | 50749 | MFOH [WAVE] - Add a Scheduler Task Step for the IL WINS Export (CPS C0101) | Story Completed | 3 | 5 | 20 | 2025-11-07 | 2025-11-14 | Hemanath | Vidhya | None | Vidhya | None | 45693 | 2025-11-13 | 2025-11-14 | Subhasri | 1.You don't need any change in the SP - ILWINSExport.sql for adding a scheduler step. Please revert that change and look for an example - Alachua Meal Count Export. 2.Don't hardcode the filename in the scheduler. Use the model value using substring. | Steve | 2025-11-14 | I don't think this is the correct way to handle this. The School Group should be a scheduler task parameter. Please reach out to Jagan and Gary about this | None | None | Requirement change lead to deviation in the timeline | Meets Expectation
6 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Sabir | 50721 | MFOH [WAVE] - Add a new template for Standard Claim to Custom Report | Product Owner - Verify | 5 | 4 | 16 | 2025-11-10 | 2025-11-17 | Sabir | Vidhya | 1. The selected school name is not appearing in the report 2. Number Formating is missing 3. Font size not match with for label 'Total Reimbursement Due' | Vidhya | None | NA | NA | NA | Subhasri | 1. You're adding report parameters in the xtrareportrunner. But report parameters lines removed for standardClaimreport if condition. Why this change is required then? | NA | NA | None | None | None | None | Meets Expectation
7 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Vidhya | 50728 | MFOH [WAVE] - Modify the Missing Sales Data Report to include the Sub-Site (CPS C0209) | Product Owner - Verify | 5 | 4.5 | 18 | 2025-11-10 | 2025-11-13 | Vidhya | Hemanath | None | Hemanath | 1. In MissingSalesDataReport.Sql - Please fix the indentation and set quoted identifier like the old one on the left, please refer the screen below 2. In MissingSalesDataReport.cshtml - Is there any specific reason why the first school is loaded in the document ready below | NA | NA | NA | Subha | None | NA | NA | NA | POV Date: 11/12/25 1. The report doesn't meet the standard format requirements. | NA | None | Meets Expectation
8 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Subbulakshmi | 50553 | MFOH [WAVE] - Automation | Story Completed | 2 | 2 | 8 | 2025-11-10 | 2025-11-19 | NA | NA | NA | NA | NA | 45823 | 2025-11-19 | 2025-11-19 | Subha | None | Steve | 2025-11-19 | None | None | None | None | Meet Expectation
9 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Hemanath Jayaraman | 48356 | [WAVE] Mosaic FOH - Standard Claim Report- Replace master serving period with serving period program | Product Owner - Verify | 5 | 3.75 | 15 | 2025-11-13 | 2025-11-18 | Hemanath | Sabir | None | Sabir | None | NA | NA | NA | Subhasri | None | NA | NA | NA | None | None | This will be tested by QA in the feature branch. Its put on hold as there are some queries from Jagan that needs to be discussed with Gary | Meets Expectation
10 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Vidhya | 50850 | MFOH [WAVE] - Add an indication when the filters are applied in the Visual Report | Product Owner - Verify | 3 | 3 | 12 | 2025-11-13 | 2025-11-18 | Vidhya | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | 1. Suggeated to change the method name to isDefaultFiltersSelected 2. Correct the typo for "default" | NA | NA | NA | None | NA | None | Meets Expectation
11 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Sabir | 50851 | MFOH [WAVE] - Add a new Data Source 'Extended Daily Sales Summary Report' to Report Designer | Product Owner - Verify | 3 | 1.5 | 6 | 2025-11-17 | 2025-11-18 | Sabir | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | this should be always [axof:<Space><story ID> ] | NA | NA | NA | NA | None | None | Meets Expectation
12 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Vidhya | 50852 | MFOH [WAVE] - Add a new Data Source 'Extended Sales Report' to Report Designer | Story Being Developed | 3 | 3 | 12 | 2025-11-18 | 2025-11-19 | Vidhya | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | Should be always [axof:<Space><story ID> ] | NA | NA | NA | None | NA | None | Meets Expectation
13 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Sabir | 50855 | MFOH [WAVE] - Add a new template 'Extended Daily Sales Summary Report' to Custom > Report Templates | Story Being Developed | 5 | 2.5 | 10 | 2025-11-18 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
14 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Hemanath Jayaraman | 50853 | MFOH [WAVE] - Add a new Data Source 'Revenue Report' to Report Designer | Product Owner - Verify | 3 | 1.75 | 7 | 2025-11-18 | 2025-11-19 | Hemanath | Vidhya | None | Vidhya | None | NA | NA | NA | Subhasri | 1.Change it to display the entire report name as Name in the script. We must always consider the User's point of view. Displaying single word is not consistent in the application. | NA | NA | NA | None | None | None | Meets Expectation
15 | FOH Wave | 2025-11-07 | 2025-11-20 | 4.25 - Sprint 4 Stretch | Subbulakshmi | 50930 | MFOH [WAVE] - Automation (50722) | Story Being Developed | 2 | 1 | 4 | 2025-11-19 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | None | Meet Expectation

## 4.25 - Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 4.25 - Sprint 4 | 50441 | 50441 | Sabir | Bounceback/Sub-Defect | Success Popup is showing in Error Message | Minor | Manual | Internal | Story Ready For Testing | 2025-11-18 | 2025-11-18 | Design | Success Popup Issue
| 4.25 - Sprint 4 | 50731 | 50731 | Vidhya | Bounceback/Sub-Defect | Tool tip is not appears in when NSS Id is exactly equal to 8 characters | Minor | Manual | Internal | Product Owner - Verify | 2025-11-11 | 2025-11-11 | Design | Tool tip is not appears in when NSS Id is exactly equal to 8 characters

## 4.25 - Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 | Hemanath Jayaraman | 43944 | MFOH - Modify the 'User Assignments Report' to meet Mosaic Standard | Story Completed | 1 | 1.5 | 6 | 2025-10-24 | 2025-10-24 | Hemanath | Sabir | None | Sabir | None | 45293 | 2025-10-27 | 2025-10-27 | Subha | None | Steve | 2025-10-27 | None | None | None |  | Meets Expectation
2 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 | Hemanath Jayaraman | 48361 | [WAVE] Mosaic FOH - KY CNIPS Export NSLP - Replace master serving period with serving period program | Story Completed | 2 | 2.5 | 10 | 2025-10-27 | 2025-10-28 | Hemanath | Sabir | None | Sabir | None | NA | NA | NA | Subha | None | NA | NA | None | POV Comment: 1. The story was developed incorrectly. 2. The story development didn't meet any of the expectation. | None | This will be tested by QA using the feature branch | Meets Expectation
3 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 | Sabir Shaikh | 48339 | [WAVE] Mosaic FOH - CNPWeb Export - Replace master serving period with serving period program | Story Completed | 3 | 2 | 8 | 2025-10-24 | 2025-10-27 | Sabir | Vidhya | None | Vidhya | None | NA | NA | NA | Subha | None | NA | NA | None | NA | None | This will be tested by QA using the feature branch | Meets Expectation
4 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 | Vidhya | 50500 | MFOH[WAVE]- FOH-Legacy Imports to be moved to Utilities System setup | Story Completed | 3 | 3 | 12 | 2025-10-24 | 2025-10-27 | Vidhya | Hemanath | None | Hemanath | None | 45338 | 2025-10-28 | 2025-10-28 | Subha | None | Steve | 2025-10-28 | None | None | None | None | Meets Expectation
5 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Subbulakshmi | 50553 | MFOH [WAVE] - Automation | Story Being Developed | 2 | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None
6 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 | Sabir Shaikh | 48282 | [WAVE] Mosaic FOH - OR Est Reimb Due Report - Replace master serving period with serving period program | Story Completed | 3 | 2 | 8 | 2025-10-27 | 2025-10-28 | Sabir | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | None | NA | NA | None | None | None | This will be tested by QA using the feature branch | Meets Expectation
7 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Vidhya | 50548 | MFOH [WAVE] - Copied widgets have issues when enlarged (Dashboard) | Story Completed | 5 | 6.5 | 26 | 2025-10-28 | 2025-11-04 | Vidhya | Hemanath | None | Hemanath | None | 45473 | 2025-11-04 | 2025-11-04 | Subha | None | Steve | 2025-11-04 | None | POV Comment: 1. Mismatch of data between the Standard claim and the ADP % single value widget. | None | None | Meets Expectation
8 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Hemanath Jayaraman | 50440 | MFOH [WAVE] - Export the format of the 'User Created Custom Reports' | Story Completed | 5 | 6.5 | 26 | 2025-10-28 | 2025-11-04 | Hemanath | Vidhya | None | Vidhya | None | 45475 | 2025-11-04 | 2025-11-04 | Subha | None | Steve | 2025-11-04 | None | None | None | None | Meets Expectation
9 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Sabir Shaikh | 50441 | MFOH [WAVE] - Import the format of the Custom Report | Product Owner - Verify | 5 | 5 | 20 | 2025-10-29 | 2025-11-04 | Sabir | Vidhya | check repotname exist condition with space and without space | Vidhya | NA |  |  |  | Subha | NA |  |  |  | POV Comment: 1. The story didn't meet any of the ACs given for the UI elements. 2. In the second POV, the validation for the xml file (custom report vs some other random files) wasn't set. 3. The import and cancel button arrangement is incorrect
10 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Hemanath Jayaraman | 48360 | [WAVE] Mosaic FOH - Meals Per Labor Hour Report - Replace master serving period with serving period program | Story Need More Info | 3 | 2 | 10 | 2025-11-05
11 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Vidhya | 50712 | MFOH [WAVE] - Rename 'Serving Period Program' to Reimbursable Program | Story Being Developed | 2 | 2 | 8 | 2025-11-05 | 2025-11-06 | Vidhya | Hemanath | None | Hemanath | None |  |  |  | Subha | None |  |  |  | None | None | None | Meets Expectation
12 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Sabir Shaikh | 48333 | [WAVE] Mosaic FOH - Kentucky D3 Report - Replace master serving period with serving period program | Story Need More Info | 3 | 1 | 4 | 2025-11-05
13 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Sabir Shaikh | 50722 | MFOH [WAVE] - Add a new Data Source 'Standard Claim' to Report Designer | Story Being Developed | 3 | 1 | 4 | 2025-11-06
14 | FOH Wave | 2025-10-24 | 2025-11-06 | 4.25 - Sprint 3 Stretch | Sabir Shaikh | 48337 | [WAVE] Mosaic FOH - North Carolina SFS4 Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | 2025-11-06 | 2025-11-06 | Sabir | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | None | NA | NA | None | NA | NA | This will be tested by QA using the feature branch | Meets Expectation

## 4.25 - Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments

## 4.25 - Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 | Subbulakshmi | 50315 | MFOH [WAVE] - Add 'Participation By' filter to the Supplemental Programs Claim Report | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
2 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 | Subbulakshmi | 50182 | MFOH [WAVE] - Automation (49176) | Story Completed | 2 | 2 | 8 | 2025-10-10 | 2025-10-22 | Subbulakshmi | NA | NA | NA | NA | 45242 | 2025-10-22 | 2025-10-22 | Subha | NA | NA | 2025-10-22 | NA | NA | NA | NA | Meets Expectation
3 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 | Vidhya | 49952 | MFOH [WAVE] - Add a Numerical Widget for MPLH | Story Completed | 3 | 3 | 12 | 2025-10-10 | 2025-10-13 | Vidhya | Alpha | NA | Alpha | NA | 45123 | 2025-10-14 | 2025-10-14 | Subha | NA | Steve | 2025-10-14 | NA | POV Comment: 1. The handling for the exception when the labor hour is 0 was missing and hence throwed an error. | NA | NA | Meets Expectation
4 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 | Subbulakshmi | 48340 | [WAVE] Mosaic FOH - Wisconsin Claim Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
5 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 | Vidhya | 49953 | MFOH [WAVE] - Add a Numerical Widget for ADP% | Story Completed | 8 | 9 | 38 | 2025-10-14 | 2025-10-23 | Vidhya | Hemanath | ADP values not matching | Hemanath | NA | 45249 | 2025-10-22 | 2025-10-22 | Subha | NA | Steve | 2025-10-22 | NA | 1. Missing % symbol inside the widget and copied widget. 2. Widget value doesn't match with the standard claim report value for the school group selection. | NA | NA | Meets Expectation
5 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 Stretch | Sabir Shaikh | 50406 | MFOH - Modify Custom Student Report to meet Mosaic Standard | Story Completed | 3 | 4 | 16 | 2025-10-10 | 2025-10-16 | Sabir | Hemanath | 1.School Name is showing in Page Header 2. Decrease the space of right side of the page | Hemanath | NA | 45195 | 2025-10-17 | 2025-10-17 | Subha | NA | NA | 2025-10-17 | NA | POV Comment: 1. The color coding was missing for the rows. 2. The vertical and horizontal lines were missing. | NA | I have worked and done the changes on two reports. one is for potrait and second is landscape | Meets Expectation
6 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 Stretch | Hemanath Jayaraman | 50407 | FOH - Modify Student Attendance Import Results Report to meet Mosaic Standard | Story Completed | 3 | 3 | 12 | 2025-10-10 | 2025-10-15 | Hemanath | Vidhya | NA | Vidhya | NA | 45144 | 2025-10-15 | 2025-10-15 | Subha | NA | Steve | 2025-10-15 | NA | POV Comment: 1. The column headers were misplaced and it affected the understanding of the report. | NA | NA | Meets Expectation
7 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 Stretch | Hemanath Jayaraman | 43944 | MFOH - Modify the 'User Assignments Report' to meet Mosaic Standard | Story Being Developed | 3 | 3 | 12 | 2025-10-16 | 2025-10-22 | Hemanath | Sabir | If no parameters selected, then display parameters showing with empty borders | Sabir | NA | [8 empty] | NA | NA | NA | Meets Expectation
8 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 Stretch | Sabir Shaikh | 50453 | MFOH - Modify the 'Kershaw Condensed Daily Sales Summary' to meet Mosaic Standard | Story Ready For Testing | 3 | 2 | 8 | 2025-10-16 | 2025-10-23 | Sabir | Hemanath | Page Footer Line is missing | Hemanath | NA | 45263 | 2025-10-23 | 2025-10-23 | Subha | NA | Steve | 2025-10-23 | NA | NA | NA | NA | Meets Expectation
9 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 Stretch | Hemanath Jayaraman | 48361 | [WAVE] Mosaic FOH - KY CNIPS Export NSLP - Replace master serving period with serving period program | Story Being Developed | 3 | 1.25 | 5 | 2025-10-22 | [17 empty] | Meets Expectation
10 | FOH Wave | 2025-10-10 | 2025-10-23 | 4.25 - Sprint 2 Stretch | Sabir Shaikh | 48337 | [WAVE] Mosaic FOH - North Carolina SFS4 Export - Replace master serving period with serving period program | Story Being Developed | 3 | 2 | 8 | 2025-10-21

## 4.25 - Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments

## 4.25 - Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 | Hemanath Jayaraman | 49762 | MFOH [WAVE] - Add 'Participation By' filter to the Standard Claim Report | Story Completed | 2 | 2.25 | 9 | 2025-09-26 | 2025-09-29 | Hemanath | Alpha | NA | Alpha | NA | 44885 | 2025-09-30 | 2025-09-30 | Subhasri | 1.This is not needed in DirectorServiceClient.cs. 2. In a few pages, the revision history is still 4.24; change it to 4.25. | Steve | 2025-09-30 | NA | This story was taken for development on 9/3. POV was done twice since the development didn't meet the expected criteria during first time of POV. 2nd POV date was 9/29. Totally 63.5 hours logged in the story for development. | NA | Listed the reasons below for delay 1.I faced a technical issue wrt school grouping which took some time to figure and sort it out. 2.I missed to note a piece of stuff in the AC 3.I had to change from one to another approach due to an existing behaviour with RDLC report. 4.I don't have prior experience in RDLC reports too. 5. POV comment to add a parameter in the report is not mentioned in the AC. | Meets Expectation
2 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 | Sabir Shaikh | 49592 | MFOH [WAVE] - Add a new template 'Daily Sales By Serving Line Report' to Custom > Report Templates | Story Completed | 1 | 1 | 4 | 2025-09-26 | 2025-09-26 | Sabir | Vidhya | 1.Page number format not matching with existing report. 2. increase the space between these two fields | Vidhya | Unnecessary empty lines are added. Please remove it | 44873 | 2025-09-29 | 2025-09-29 | Subhasri | NA | Steve | 2025-09-29 | NA | NA | NA | UI Issues in Daily Sales By Serving Line Report(Template) | Meets Expectation
3 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 | Sabir Shaikh | 49989 | [WAVE] Mosaic FOH- Addition of Serving Period Program to Reimbursement Rate screen | Story Need More Info | 3 | 2 | 8 | 2025-09-26 | 2025-09-26 | Sabir | Vidhya | NA | Vidhya | NA | 44911 | 2025-09-30 | 2025-09-30 | Subhasri | NA | Steve | 2025-09-30 | NA | NA | NA | Story AC got changed after moving the story to Ready for Testing. Hold on this story since we are waiting for Gary's reply. | Meets Expectation
4 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 | Vidhya | 49997 | [WAVE] Mosaic FOH- Site level settings for SFSP Site Type | Story Completed | 3 | 3 | 12 | 2025-09-26 | 2025-09-29 | Vidhya | Hemanath | NA | Hemanath | NA | 44872 | 2025-09-29 | 2025-09-29 | Subhasri | NA | Steve | 2025-09-29 | NA | NA | NA | NA | Meets Expectation
5 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 | Hemanath Jayaraman | 49992 | [WAVE]- Mosaic FOH- Reimbursable Program field in Serving Period Maintenance | Story Completed | 1 | 1 | 4 | 2025-09-26 | 2025-09-29 | Hemanath | Sabir | NA | Sabir | NA | 44899 | 2025-09-30 | 2025-09-30 | Subhasri | NA | Steve | 2025-09-30 | NA | The story was partially developed. Had suggested comments during POV for changing the label in the serving period search grid since it was missing. Its a simple change but didn't meet the expectation during the POV. | NA | NA | Meets Expectation
6 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 | Vidhya | 50214 | MFOH - Modifications to Rhode Island Claim Export (Operating Days) | Story Completed | 2 | 2 | 8 | 2025-09-29 | 2025-09-30 | Vidhya | Sabir | NA | Arvinth | NA | 44945 | 2025-10-03 | 2025-10-03 | NA | NA | Steve | 2025-10-03 | NA | NA | NA | Arvinth did Peer review for this story since subha is on PTO | Meets Expectation
7 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 | Sabir Shaikh | 50212 | MFOH - Modifications to Colorado Claim Export (Operating Days) | Story Completed | 2 | 2 | 8 | 2025-09-29 | 2025-09-30 | Sabir | Hemanath | NA | Hemanath | NA | 44950 | 2025-10-03 | 2025-10-03 | Subhasri | NA | Steve | 2025-10-03 | NA | POV was seen on Sep 30. The data wasn't entered and was unable to show the POV for the changes. Hence, asked to work on the data and show the pov once again. 2nd POV date Oct 3. | NA | NA | Meets Expectation
8 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 | Hemanath Jayaraman | 50215 | MFOH - Modifications to Tennessee Claim Export (Operating Days) | Story Completed | 2 | 1.8 | 7.5 | 2025-09-30 | 2025-10-03 | Hemanath | Vidhya | NA | Vidhya | NA | 44967 | 2025-10-06 | 2025-10-06 | Subhasri | NA | Steve | 2025-10-06 | NA | NA | NA | NA | Meets Expectation
9 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 Stretch | Subbulakshmi | 50182 | MFOH [WAVE] - Automation (49176) | Story Being Developed | 3 | 2 | 4 | 2025-09-23 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 Stretch | Vidhya | 49952 | MFOH [WAVE] - Add a Numerical Widget for MPLH | Story Being Developed | 5 | 5 | 20 | 2025-10-03 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
11 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 Stretch | Sabir Shaikh | 48340 | [WAVE] Mosaic FOH - Wisconsin Claim Export - Replace master serving period with serving period program | Story Being Developed | 3 | 3 | 12 | 2025-10-03 | 2025-10-10 | Sabir | Hemanath | NA | NA | NA | 45065 | 2025-10-10 | 2025-10-10 | Subhasri | NA | Steve | 2025-10-10 | NA | NA | NA | NA | Meets Expectation
12 | FOH Wave | 2025-09-26 | 2025-10-09 | 4.25 - Sprint 1 Stretch | Hemanath Jayaraman | 50315 | MFOH [WAVE] - Add 'Participation By' filter to the Supplemental Programs Claim Report | Story Being Developed | 5 | 4 | 15.5 | 2025-10-06 | 2025-10-08 | Hemanath | Sabir | NA | Sabir | NA | 45064 | 2025-10-10 | 2025-10-10 | Subhasri | NA | Steve | 2025-10-10 | NA | POV date: 10/9/2025. The display parameter was not in the expected position after multiple discussions before POV and it looks wierd. Asked to fix it. | NA | NA | Meets Expectation

## 4.25 - Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 4.25 - Sprint 1 | 49592 | 49592 | Sabir Shaikh | Bounceback/Sub-Defect | UI Issues in Daily Sales By Serving Line Report(Template) | Minor | Manual | Internal | Story Completed | 2025-09-25 | 2025-09-26 | Design | UI Issue

## 4.24 - Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 | Vidhya | 50003 | MFOH [WAVE] - Apply the new improvements to the existing Dashboard Setups | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
2 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 | All | 50032 | [WAVE] Mosaic - FOH 4.24(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 8 | 16 | 65 | 2025-09-15 | 2025-09-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
3 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 | All | 50033 | [WAVE]Mosaic - FOH 4.24(Regression) - Utilities | Story Completed | 3 | 6 | 24 | 2025-09-16 | 2025-09-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
4 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 | All | 50034 | [WAVE]Mosaic - FOH 4.24(Regression) - SetUp | Story Completed | 2 | 10 | 40 | 2025-09-18 | 2025-09-24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
5 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 | Vidhya | 25981 | MFOH (WAVE) (4.24 Regression) - Multiple extra pages are getting added when there is no data (Daily Sales Summary) | Defect Rejected |  |  |  | 2025-09-22 | 2025-09-23 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
6 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 | Sabir | 25999 | MFOH [WAVE] (4.24 Regression) - POS Offline Incident Report-Data is not bounding to report even though store procedure returning data. | Defect Fixed |  |  |  | 2025-09-23 | 2025-09-23 | Sabir | Vidhya | NA | Vidhya | NA | 44764 | 2025-09-24 | 2025-09-24 | Subha | NA | Ying | 2025-09-24 | Nil | NA | NA | NA | Meets Expectation
7 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 | Vidhya | 25983 | MFOH (4.24 Regression) - When editing the price for each eligibility status in the meal price template, got a console error and couldn't change the pr | Defect Fixed |  |  |  | 2025-09-24 | 2025-09-24 | Vidhya | Sabir | NA | Sabir | NA | 44759 | 2025-09-24 | 2025-09-24 | Subha | NA | Ying | 2025-09-24 | Nil | NA | NA | NA | Meets Expectation
8 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 Stretch | Subbulakshmi | 50182 | MFOH [WAVE] - Automation (49176) | Story Being Developed | 5 | 2 | 12 | 2025-09-23 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
9 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 Stretch | Hemanath Jayaraman | 49762 | MFOH [WAVE] - Add 'Participation By' filter to the Standard Claim Report | Story Being Developed | 3 | 6.25 | 25 | 2025-09-12 |  | Hemanath | Alpha | The ADP percentage is not matching with sales overview report for one school alone. | Alpha | [11 empty] | Listed the reasons below for delay 1.I faced a technical issue wrt school grouping which took some time to figure and sort it out. 2.I missed to note a piece of stuff in the AC 3.I had to change from one to another approach due to an existing behaviour with RDLC report. 4.I don't have prior experience in RDLC reports too. | Meets Expectation
10 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 Stretch | Sabir | 49592 | MFOH [WAVE] - Add a new template 'Daily Sales By Serving Line Report' to Custom > Report Templates | Story Being Developed | 2 | 2 | 6 | 2025-09-12 |  | Sabir | Vidhya | 1. Could not open the template in Report Designer. 2. Increase the space between 'Taxable Total' and 'Total Tax Collected' | Vidhya | NA | [11 empty] | Meets Expectation
11 | FOH Wave | 2025-09-12 | 2025-09-25 | 4.24 - Sprint 4 Stretch | Subbulakshmi | 50002 | MFOH [WAVE] - Automation (49591) | Story Completed | 1 | 1 | 4 | 2025-09-11 | 2025-09-12 | Subbulakshmi | NA | NA | NA | NA | 44541 | 2025-09-12 | 2025-09-12 | Subha | NA | Steve | 2025-09-12 | NA | NA | NA | NA | Meets Expectation

## 4.24 - Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments

## 4.24 - Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 | Vidhya | 49801 | MFOH [WAVE] - Fix the alignment issues in the Dashboard | Story Completed | 5 | 8.5 | 35 | 2025-08-29 | 2025-09-03 | Vidhya | Hemanath Jayaraman | NA | Hemanath Jayaraman | NA | 44369 | 2025-09-04 | 2025-09-04 | Subha | NA | Steve | 2025-09-04 | NA | 1. Multiple POVs and given suggestions for fixes during the POV. 2. Missed the serving period wrap changes which was the main reason for adding this story. 3. Alignment issues were there during the initial POVs | NA | Exceeded the given time as there were some R&D required for the UI enhancements. Support given for different screen resolutions additionally. Changes has been done and reverted back for admin side reload functionality | Meets Expectation
2 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 | Sabir | 49591 | MFOH [WAVE] - Add a new Data Source 'Daily Sales By Serving Line Report' to Report Designer | Story Completed | 1 | 1 | 4 | 2025-08-29 | 2025-09-08 | Sabir | Vidhya | NA | Vidhya | Version history is missing | 44315 | 2025-09-02 | 2025-09-02 | Subha | NA | Steve | 2025-09-02 | NA | NA | NA | NA | Meets Expectation
3 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 | Subbulakshmi | 49687 | MFOH [WAVE] - Automation (49465) | Story Completed | 2 | 2 | 8 | 2025-08-28 | 2025-09-03 | Subbulakshmi | NA | NA | NA | NA | 44331 | 2025-09-03 | 2025-09-03 | Subha | NA | Steve | 2025-09-03 | NA | NA | NA | NA | Meets Expectation
4 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 Stretch | Hemanath Jayaraman | 49594 | MFOH [WAVE] - Add a new template 'Daily Sales Summary' to Custom > Report Templates | Story Completed | 8 | 4.5 | 18 | 2025-08-29 | 2025-09-02 | Hemanath | Sabir | NA | Sabir | NA | 44325 | 2025-09-03 | 2025-09-03 | Subha | NA | Steve | 2025-09-03 | NA | NA | NA | NA | Meets Expectation
5 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 Stretch | Sabir | 49592 | MFOH [WAVE] - Add a new template 'Daily Sales By Serving Line Report' to Custom > Report Templates | Story Being Developed | 8 | 8 | 32 | 2025-09-01 | [16 empty] | This report involves nested sub-reports where it is very new to implement in the report designer as of now. Taken some time to analyse and implement the same. Since the difficulty level is increased and was facing slight complexity to achieve it. | Meets Expectation
6 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 Stretch | Vidhya | 49923 | MFOH [WAVE] - Make the new improvements to the Dashboard affect the existing Setups (Analysis) | Story Completed |  | 3.5 | 15 | 2025-09-04 | 2025-09-09 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
7 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 Stretch | Hemanath Jayaraman | 49762 | MFOH [WAVE] - Add 'Participation By' filter to the Standard Claim Report | Story Being Developed | 5 | 7.6 | 30.5 | 2025-09-03 |  | Hemanath | [12 empty] | 1. Shown POV exceeding the planned date and after multiple followps 2. Data error and suggested to fix it. |  | Reasons for delay : 1.While unit testing found an issue which requires technical clarification from existing dev team waited for them as they were busy. 2.Missed to note a piece of stuff in the acceptance criteria resulted in the code rework. | Meets Expectation
8 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 Stretch | Subbulakshmi | 50001 | MFOH [WAVE] - Automation (49593) | Story Completed | 2 | 2 | 8 | 2025-09-10 | 2025-09-11 | Subbulakshmi | NA | NA | NA | NA | 44519 | 2025-09-11 | 2025-09-11 | Subha | NA | Steve | 2025-09-11 | NA | NA | NA | NA | Meets Expectation
9 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 Stretch | Vidhya | 50003 | MFOH [WAVE] - Apply the new improvements to the existing Dashboard Setups | Story Being Developed | 3 | 1.5 | 6 | 2025-09-10 | 2025-09-11 | Vidhya | Alpha | Getting an exception while copying the widget | [13 empty] | Meets Expectation
8 | FOH Wave | 2025-08-29 | 2025-09-11 | 4.24 - Sprint 3 Stretch | Subbulakshmi | 50002 | MFOH [WAVE] - Automation (49591) | Story Being Developed | 2 | 0.75 | 5 | 2025-09-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation

## 4.24 - Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 4.24 - Sprint 3 | 49801 | 49801 | Vidhya | Bounceback/Sub-Defect | Alignment Issue in user's global filter Text | Minor | Manual | Internal | Defect Fixed | 2025-09-08 | 2025-09-08 | Design | UI Issue

## 4.24 - Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 | Vidhya | 49176 | MFOH [WAVE] - Duplicating/copying the Dashboard Widgets | Story Completed | 3 | 4.5 | 18 | 2025-08-18 | 2025-08-25 | Vidhya | Alpha | NA | Alpha | NA | 44155 | 2025-08-25 | 2025-08-25 | Subha | NA | Ying | 2025-08-25 | NA | NA | NA | Exceeded the given time to copy the widgets filters as well | Meets Expectation
2 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 | Subbulakshmi | 49465 | MFOH [WAVE] - Add a 'Delete' option to delete the User Created Custom Reports | Story Completed | 2 | 2 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
3 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 | Subbulakshmi | 48362 | [WAVE] Mosaic FOH - MARS Claim Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
4 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 | Sabir Shaikh | 49428 | MFOH [WAVE] - Allow the users to view the Dashboard Widgets in an enlarged version | Story Completed | 3 | 5 | 20 | 2025-08-18 | 2025-08-28 | Sabir | Arvinth | NA | Arvinth | NA | 44159 | 2025-08-25 | 2025-08-25 | Subha | NA | NA | 2025-08-25 | NA | NA | NA | Taken some time for UI improvements | Meets Expectation
5 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 | Hemanath Jayaraman | 49596 | MFOH [WAVE]- Support for Credit Card in Additional Meal Programs (Extended Sales Report) | Story Completed | 1 | 1 | 6 | 2025-08-18 | 2025-08-19 | Hemanath | Vidhya | Huge amounts getting wrapped up in next line | Vidhya | NA | 44041 | 2025-08-19 | 2025-08-21 | Subha | NA | Ying | 2025-08-21 | NA | NA | NA | NA | Meets Expectation
6 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 Stretch | Hemanath Jayaraman | 49593 | MFOH [WAVE] - Add a new Data Source 'Daily Sales Summary Report' to Report Designer | Story Completed | 3 | 3 | 11 | 2025-08-20 | 2025-08-21 | Hemanath | Vidhya | NA | Vidhya | NA | 44093 | 2025-08-21 | 2025-08-21 | Subha | NA | Ying | 2025-08-21 | NA | NA | NA | NA | Meets Expectation
7 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 Stretch | Subbulakshmi | 49687 | MFOH [WAVE] - Automation (49465) | Story Being Developed | 3 | 1 | 8 | 2025-08-20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
8 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 Stretch | Hemanath Jayaraman | 49594 | MFOH [WAVE] - Add a new template 'Daily Sales Summary' to Custom > Report Templates | Story Being Developed | 8 | 3 | 12 | 2025-08-22 | [15 empty] | NA | NA | Meets Expectation
9 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 Stretch | Vidhya | 49801 | MFOH [WAVE] - Fix the alignment issues in the Dashboard | Story Being Developed | 5 | 3 | 12 | 2025-08-26 | [15 empty] | NA | NA | Meets Expectation
10 | FOH Wave | 2025-08-15 | 2025-08-28 | 4.24 - Sprint 2 Stretch | Sabir Shaikh | 49591 | MFOH [WAVE] - Add a new Data Source 'Daily Sales By Serving Line Report' to Report Designer | Story Being Developed | 3 | 3 | 12 | 2025-08-25 | [15 empty] | NA | NA | Meets Expectation

## 4.24 - Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 4.24 - Sprint 2 | 49428 | 49428 | Sabir Shaikh | Defect | Try to add more than 8 widget, scroll down and enlarge the last widget, the screen automatically scrolls up. This will be an issue if there are more widgets | Minor | Manual | Internal | Defect Fixed | 2025-08-18 | 2025-08-18 | Enhancements | Functionality Issue

## 4.24 - Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer/Tester | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 | Subbulakshmi | 48354 | [WAVE] Mosaic FOH - Tennessee Claim Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | 2025-08-01 | 2025-08-01 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing | Meets Expectation
2 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 | Subbulakshmi | 48338 | [WAVE] Mosaic FOH - Rhode Island Claim Export - Replace master serving period with serving period program. | Story Completed | 1 | 1 | 4 | 2025-08-04 | 2025-08-05 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing | Meets Expectation
3 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 | Subbulakshmi | 48336 | [WAVE] Mosaic FOH - NorthCarolina Claim Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | 2025-08-01 | 2025-08-04 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing | Meets Expectation
4 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 | Hemanath Jayaraman | 49422 | MFOH [WAVE]- Support for Credit Card in Additional Meal Programs (Condensed Daily Sales Summary Report) | Story Completed | 3 | 3 | 12 | 2025-08-01 | 2025-08-07 | Hemanath | Sabir | NA | Sabir | NA | 43838 | 2025-08-07 | 2025-08-07 | Subha | 1. Add revision history 2. Change the text lunch box to Mosaic 3. Update the SQL parameter passing syntax. | Ying | 2025-08-07 | NA | NA | NA | NA | Meets Expectation
5 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 | Vidhya | 48991 | MFOH [WAVE] - Support for Credit Card in Additional Meal Programs (Daily Sales by Serving Line Report) | Story Completed | 3 | 9 | 37 | 2025-08-01 | 2025-08-13 | Vidhya | Arvinth | NA | Arvinth | NA | 43950 | 2025-08-13 | 2025-08-13 | Subha | Serializable attribute is missing | Ying | 2025-08-13 | NA | NA | NA | Low estimated story. There is a lack of support in the DB design to get the data. Faced more technical challanges during its implementation which was unexpected. | Meets Expectation
6 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 | Sabir Shaikh | 49421 | MFOH [WAVE]- Support for Credit Card in Additional Meal Programs (Daily Sales Summary Report) | Story Completed | 3 | 3 | 12 | 2025-08-01 | 2025-08-07 | Sabir | Hemanath | NA | Hemanath | NA | 43846 | 2025-08-07 | 2025-08-07 | Subha | 1. Add revision history 2. Change the text lunch box to Mosaic 3. Update the SQL parameter passing syntax. | Ying | 2025-08-07 | NA | NA | NA | NA | Meets Expectation
7 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 Stretch | Subbulakshmi | 49475 | 49475 MFOH [WAVE] - Automation (48015) | Story Completed | 3 | 3 | 12 | 2025-08-05 | 2025-08-07 | Subbulakshmi | NA | NA | NA | NA | 43842 | 2025-08-07 | 2025-08-07 | Subha | NA | Ying | 2025-08-07 | NA | NA | NA | Automation Testing | Meets Expectation
8 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 Stretch | Sabir Shaikh | 49465 | MFOH [WAVE] - Add a 'Delete' option to delete the User Created Custom Reports | Story Ready For Testing | 3 | 4 | 16 | 2025-08-05 | 2025-08-08 | Sabir | Hemanath | NA | Hemanath | NA | 43948 | 2025-08-13 | 2025-08-13 | Subha | 1. Add ReportResultSharedRecipient table in the delete query | Ying | 2025-08-13 | NA | NA | NA | NA | Meets Expectation
9 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 Stretch | Hemanath Jayaraman | 48362 | [WAVE] Mosaic FOH - MARS Claim Export - Replace master serving period with serving period program | Story Being Tested | 3 | 3.5 | 14 | 2025-08-08 | 2025-08-11 | Hemanath | Sabir | NA | Sabir | NA | NA | NA | NA | Subha | NA | NA | NA | NA | NA | NA | QA will test this in the feature branch and close it | Meets Expectation
10 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 Stretch | Sabir Shaikh | 49428 | MFOH [WAVE] - Allow the users to view the Dashboard Widgets in an enlarged version | Story Being Developed | 3 | 3 | 12
11 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 Stretch | Hemanath Jayaraman | 49596 | MFOH [WAVE]- Support for Credit Card in Additional Meal Programs (Extended Sales Report) | Story Being Developed | 3 | 3 | 13 | 2025-08-11 | [17 empty] | Meets Expectation
12 | FOH Wave | 2025-08-01 | 2025-08-14 | 4.24 - Sprint 1 Stretch | Vidhya | 49176 | MFOH [WAVE] - Duplicating/copying the Dashboard Widgets | Story Being Developed |  | 2.5 | 10

## 4.24 - Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 4.24 - Sprint 1 | 49421 | 49421 | Sabir | Bounceback/Sub-Defect | showing StudentPaidAmount wrong value | Major | Manual | Internal | Defect Fixed | 2025-08-13 | 2025-08-13 | Enhancements | Functionality Issue

## 4.23 - Sprint 4-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Dev Start Date | Dev End Date | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 | Sabir Shaikh | 48411 | MFOH [WAVE] - Custom Report (Navigation) | Story Completed | 1 | 1 | 4 | 2025-07-21 | 2025-07-21 | Sabir | Hemanath | None | Hemanath | None | 43472 | 2025-07-18 | 2025-07-18 | Subhashri | None | Ying | 2025-07-18 | None | NA | NA | NA | Meets Expectation
2 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 | Hemanath Jayaraman | 49267 | [WAVE]Mosaic - FOH 4.23(Regression) - Setup | Story Completed | 2 | 2 | 23 | 2025-07-22 | 2025-07-25 | Hemanath | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
3 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 | Vidhya | 49266 | [WAVE]Mosaic - FOH 4.23(Regression) - Utilities | Story Completed | 3 | 3 | 27 | 2025-07-22 | 2025-07-26 | Vidhya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
4 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 | Sabir Shaikh/Subbulakshmi | 49263 | [WAVE] Mosaic - FOH 4.23(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 8 | 8 | 43 | 2025-07-22 | 2025-07-25 | Sabir/Subbu | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Meets Expectation
5 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 Stretch | Hemanath Jayaraman | 48354 | [WAVE] Mosaic FOH - Tennessee Claim Export - Replace master serving period with serving period program | Story Ready For Testing | 3 | 2.75 | 11 | 2025-07-18 | 2025-07-21 | Hemanath | Vidhya | NA | Vidhya | NA | NA | NA | NA | Subha | NA | NA | NA | NA | NA | NA | Development has been completed. Will circle back after the relase regression testing is completed since its the top priority | Meets Expectation
6 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 Stretch | Sabir Shaikh | 48338 | [WAVE] Mosaic FOH - Rhode Island Claim Export - Replace master serving period with serving period program. | Story Ready For Testing | 3 | 2 | 12 | 2025-07-18 | 2025-07-21 | Sabir | Hemanath | None | Hemanath | NA | NA | NA | NA | Subhashri | change the updateddate in SQL Script | NA | NA | NA | NA | NA | Development has been completed. Will circle back after the relase regression testing is completed since its the top priority | Meets Expectation
7 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 Stretch | Vidhya | 49176 | MFOH [WAVE] - Analysis on new widgets for Dashboard | Story Being Developed | 0 | 7.75 | 31 | 2025-07-18 | 2025-07-31 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Offshore PO going to have discussion with Onshore PO to get more details on this story
8 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 Stretch | Subbulakshmi | 49380 | 49380 MFOH [WAVE] - Automation (46542) | Story Completed | 2 | 2 | 8 | 2025-07-28 | 2025-07-29 | Subbu | NA | NA | NA | NA | 43669 | 2025-07-30 | 2025-07-30 | Subhashri | NA | YIng | 2025-07-30 | NA | NA | NA | NA | Meets Expectation
9 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 Stretch | Hemanath Jayaraman | 48362 | [WAVE] Mosaic FOH - MARS Claim Export - Replace master serving period with serving period program | Story Need More Info | 3 | 2.25 | 9 | 2025-07-28 | [16 empty] | Offshore PO going to have discussion with Onshore PO to get his approval | Meets Expectation
10 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 Stretch | Sabir Shaikh | 48363 | [WAVE] Mosaic FOH - KY CNIPS Export SSO - Replace master serving period with serving period program | Story Need More Info | 3 | 2 | 10 | 2025-07-28 | [16 empty] | Offshore PO going to have discussion with Onshore PO to get his approval | Meets Expectation
11 | FOH Wave | 2025-07-18 | 2025-07-31 | 4.23 - Sprint 4 Stretch | Sabir Shaikh | 48336 | [WAVE] Mosaic FOH - NorthCarolina Claim Export - Replace master serving period with serving period program | Story Ready For Testing | 3 | 2 | 10 | 2025-07-28 | 2025-07-29 | Sabir | Hemanath | NA | Hemanath | NA | NA | NA | NA | Subhashri | change the updateddate in SQL Script | NA | NA | NA | NA | NA | NA | Meets Expectation

## 4.23 - Sprint 4-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Dev Start Date | Dev End Date | Root Cause Category | Comments
| 4.23 - Sprint 4 | 25681 | NA | Hemanath Jayaraman | Defect | MFOH - (4.23 Regression) - Console errors while editing the cells in the grid in the provision 2 tab under school maintenance | Minor | Manual | Internal | Defect Fixed | 2025-07-29 | 2025-07-30 | Existing_Issues | Regression defect

## 4.23 - Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH Wave | 2025-07-04 | 2025-07-17 | 4.23 - Sprint 3 | Vidhya | 46542 | MFOH [WAVE] - Modifications to Louisiana SFS-8C Report if a school qualifies for CEP | Story Completed | 3 | 3 | 3 | Vidhya | Sabir/Alpha | None | Sabir/Alpha | Correct the version year and typo | 43331 | 2025-07-11 | 2025-07-11 | Subha | Set Quoted Identifier ON | Ying | 2025-07-11 | None | None | None |  | Meets Expectation
2 | FOH Wave | 2025-07-04 | 2025-07-17 | 4.23 - Sprint 3 | Sabir Shaikh | 47903 | MFOH [WAVE] - Add a new template for Transaction History to Custom Report | Story Completed | 2 | 2 | 12 | Sabir | Vidhya | ActiveDate is not showing when select DateType as ActiveDate | Vidhya | None | 43229 | 2025-07-08 | 2025-07-08 | Subhashri | Remove virtual keyword from method | Ying | 2025-07-08 | None | None | None | NA | Meets Expectation
3 | FOH Wave | 2025-07-04 | 2025-07-17 | 4.23 - Sprint 3 Stretch | Subhasri | 46537 | [WAVE] Mosaic - POS (Web) - Improvements to MA FP-9 Report (Silver Lake Regional School District) | Story Needs More Info | 3 | 2.5 | 11
4 | FOH Wave | 2025-07-04 | 2025-07-17 | 4.23 - Sprint 3 | Sabir Shaikh | 48714 | Mosaic FOH - Replace Serving Period with Serving Period Program GUID in Georgia DE0112 | Story Completed | 2 | 2 | 12 | Sabir | Ashwin | None | Ashwin | None | 43228 | 2025-07-08 | 2025-07-08 | Subhashri | None | Ying | 2025-07-08 | None | None | None | NA | Meets Expectation
5 | FOH Wave | 2025-07-04 | 2025-07-17 | 4.23 - Sprint 3 | Sabir Shaikh | 48334 | [WAVE] Mosaic FOH - Colorado Claim Export - Replace master serving period with serving period program | Story Completed | 3 | 3 | 18 | Sabir | Ashwin | None | Ashwin | None |  |  |  | Subhashri | None |  |  | None | None | None | Testing is done in feature branch by QA .Yet to create PR | Meets Expectation
6 | FOH Wave | 2025-07-04 | 2025-07-17 | 4.23 - Sprint 3 Stretch | Sabir Shaikh | 48411 | MFOH [WAVE] - Custom Report (Navigation) | Story Being Developed | 3 | 3 | 18 | [16 empty] | Meets Expectation
7 | FOH Wave | 2025-07-04 | 2025-07-17 | 4.23 - Sprint 3 Stretch | Hemanath Jayaraman | 25568 | MFOH [WAVE] - Custom and Report Designer should be accessible only by Tier 1 districts | Story Completed | 3 | 2.75 | 11 | Hemanath | Sabir | NA | Sabir | NA | 43376 | 2025-07-15 | 2025-07-15 | Subhashri | NA | Ying | 2025-07-15 | NA | NA | NA |  | Meets Expectation
8 | FOH Wave | 2025-07-04 | 2025-07-17 | 4.23 - Sprint 3 Stretch | Subbulakshmi | 48862 | MFOH Automation | Story Completed | 1 | 1 | 3 | Subbulaxmi | NA | NA | NA | NA | 43275 | 2025-07-09 | 2025-07-09 | NA | NA | Ying | 2025-07-09 | NA | NA | NA |  | Meets Expectation
9 | FOH Wave | 2025-07-04 | 2025-07-17 |  | Vidhya | 49176 | MFOH - Analysis on new widgets for Dashboard | Story Being Developed

## 4.23 - Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| Sprint - 4.23 | 47903 | 47903 | Sabir shaikh | Bounceback/Sub-Defect | Serving Period Sort Issue | Minor | Manual | Internal | Defect Fixed | Design | UI Issue

## 4.23 - Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 | Hemanath Jayaraman | 48810 | [WAVE] -Mosaic FOH-Remove HeadStart from SPP droplist | Story Completed | 3 | 3 | 12 | Hemanath | Sabir | NA | Sabir | NA | 43057 | 2025-06-27 | 2025-06-30 | Subha | 1. Please remove using ID value directly. use name to find and remove the SPP. | Ying | 2025-06-30 | None | None | None |  | Meets Expectation
2 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 | Sabir Shaikh | 48640 | [WAVE] Mosaic -FOH Change ServingPeriodProgram "AfterSchool Snack" to "AfterschoolSnack (NSLP)" | Story Completed | 1 | 1 | 6 | Sabir | Alpha |  | Alpha |  | 42914 | 2025-06-18 | 2025-06-18 | Subha |  | Ying | 2025-06-18 | None | None | None
3 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 | Sabir Shaikh | 48641 | [WAVE]-Mosaic -FOH Change SPROCS looking for "AfterSchool Snack" to look for "AfterSchoolSnack (NSLP)" | Story Completed | 3 | 3 | 12 | Sabir | Arvinth |  | Arvinth |  | 43038 | 2025-06-24 | 2025-06-24 | Subha |  | Ying | 2025-06-24 | None | None | None
4 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 | Vidhya | 48015 | [WAVE] -Mosaic-FOH-Supplemental Programs Claim report (group by schools) | Story Completed | 8 | 8 | 25 | Vidhya | Alpha |  | Alpha |  | 43075 | 2025-06-30 | 2025-06-30 | Subha |  | Ying | 2025-06-30 | None | None | None |  | Meets Expectation
5 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 | Subbulakshmi | 48192 | MFOH Automation | Story Completed | 2 | 2 | 8 | [5 empty] | 42975 | 2025-06-24 | 2025-06-26 | Subha |  | Ying | 2025-06-26 | None | None | None
6 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 | Hemanath Jayaraman | 48813 | [WAVE] -Mosaic FOH-Remove Supper from SPP droplist | Story Completed | 3 | 3 | 12 | Hemanath | Sabir | NA | Sabir | NA | 43058 | 2025-06-27 | 2025-06-30 | Subha | NA | Ying | 2025-06-30 | None | None | None |  | Meets Expectation
7 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 Stretch | Sabir Shaikh | 47903 | MFOH [WAVE] - Add a new template for Transaction History to Custom Report | Story Being Developed | 8 | 8 | 48
8 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 Stretch | Subbulakshmi | 48862 | MFOH Automation | Story Being Developed | 3 | 1.75 | 7
9 | FOH | 2025-06-19 | 2025-07-02 | 4.23 - Sprint 2 Stretch | Hemanath Jayaraman | 46542 | MFOH [WAVE] - Modifications to Louisiana SFS-8C Report if a school qualifies for CEP | Story Being Developed | 5 | 1.5 | 6 | [16 empty] | Meets Expectation

## 4.23 - Sprint 2-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| Sprint - 4.23 | 48015 |  | Vidhya | Bounceback/Sub-Defect | Serving Period name is displaying twice | Minor | Manual | Internal | Defect Fixed | Enhancements | Functional Issue

## 4.23 - Sprint 1-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH | 2025-06-06 | 2025-06-18 | 4.23 - Sprint 1 | Hemanath Jayaraman/subbulakshmi | 47907 | MFOH [WAVE] - Add a new template for Menu Products Sold to Custom Report | Story Completed | 5 | 9 | 36 | Hemanath | Vidhya | Grand total should display if the school has multiple serving lines / serving periods | Vidhya | NA | 42884 | 2025-06-17 | 2025-06-17 | Subha | NA | Ying Wang | 2025-06-17 | NA |  | Yet to Schedule | Faced some technical issues in dev express report development. Did some brain storming with the team to decide the alternate ideas. It took some time to try and decide which solution is working fine.It took some additional time to complete it due to the technical challenges faced during implementation/migration | Meets Expectation
2 | FOH | 2025-06-06 | 2025-06-18 | 4.23 - Sprint 1 | Vidhya/subbulakshmi | 47773 | [WAVE] -Mosaic-FOH- Supplemental Programs Claims report (group by programs) | Story Completed | 3 | 6 | 24 | Vidhya | Subbulakshmi |  | Arvinth | For enrolled school ADP is showing as 0 | 42843 | 2025-06-13 | 2025-06-13 |  |  |  | 2025-06-13 |  |  |  | Scope of the story got extended that requires additional story points to complete. | Meets Expectation
3 | FOH | 2025-06-06 | 2025-06-18 | 4.23 - Sprint 1 | Sabir Shaikh/Subbulakshmi | 47908 | MFOH [WAVE] - Add a new template for Edit Check to Custom Report | Story Completed | 2 | 2 | 12 |  | Vidhya |  | Vidhya |  | 42916 | 2025-06-12 | [9 empty] | Meets Expectation
4 | FOH | 2025-06-06 | 2025-06-18 | 4.23 - Sprint 1 Stretch | Subblakshmi | 48192 | MFOH Automation | Story Being Developed | 2 | 2 | 12
5 | FOH | 2025-06-06 | 2025-06-18 | 4.23 - Sprint 1 Stretch | Sabir Shaikh | 48640 | 48640-[WAVE] Mosaic -FOH Change ServingPeriodProgram "AfterSchool Snack" to "AfterschoolSnack (NSLP)" | Story Being Developed | 1 | 1 | 6 |  |  |  | Alpha |  | 42914
6 | FOH | 2025-06-06 | 2025-06-18 | 4.23 - Sprint 1 Stretch | Vidhya | 48015 | [WAVE] -Mosaic-FOH-Supplemental Programs Claim report (group by schools) | Story Being Developed | 13 | 4.5 | 18
7 | FOH | 2025-06-06 | 2025-06-18 | 4.23 - Sprint 1 Stretch | Sabir Shaikh | 48641 | 48641 [WAVE]-Mosaic -FOH Change SPROCS looking for "AfterSchool Snack" to look for "AfterSchoolSnack (NSLP)" | Story Being Developed | 5 | 5 | 30

## 4.23 - Sprint 1-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## 4.22 - Sprint 3-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH | 2025-05-23 | 2025-06-05 | 4.22 - Sprint 3 Stretch | Hemanath Jayaraman/Subblakshmi | 47907 | MFOH [WAVE] - Add a new template for Menu Products Sold to Custom Report | Story Completed | 13 | 11.75 | 47 | [15 empty] | Story development got delayed due to the following reasons 1. Its a complex story and got a technical blocker during development 2. Planned PTOs | Meets Expectation
2 | FOH | 2025-05-23 | 2025-06-05 | 4.22 - Sprint 3 Stretch | Subblakshmi | 48192 | MFOH Automation | Story Being Developed | 2 | 1 | 8 | [15 empty] | Story development got delayed due to the following reasons 1. Its a complex story and got a technical blocker during development 2. Planned PTOs | Blank
3 | FOH | 2025-05-23 | 2025-06-05 | 4.22 - Sprint 3 Stretch | Vidhya/Subbulakshmi | 47773 | MFOH [WAVE] - Supplemental Programs Claims report (group by programs) | Story Completed | 13 | 13 | 52 | [15 empty] | Story development got delayed due to the following reasons 1. Its a complex story and got a technical blocker during development 2. Planned PTOs | Meets Expectation
4 | FOH | 2025-05-23 | 2025-06-05 | 4.22 - Sprint 3 Stretch | Sabir Shaikh/Subblakshmi | 47908 | MFOH -[WAVE] - Add a new template for Edit Check to Custom Report | Story Completed | 13 | 12 | 48 | [15 empty] | Story development got delayed due to the following reasons 1. Its a complex story and got a technical blocker during development 2. Planned PTOs | Meets Expectation
5 | FOH | 2025-05-23 | 2025-06-05 | 4.22 - Sprint 3 | Sabir Shaikh/Subblakshmi | 47906 | 47906-MFOH [WAVE] - Add a new template for Eligibility Record Listing to Custom Report | Story Completed | 1 | 1 | 4 | Sabir | Hemanath |  |  |  | 42440 | 2025-05-28 | [9 empty] | Meets Expectation

## 4.22 - Sprint 3-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## 4.22 - Sprint 2-Status
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments | Does this story meet expectations?
1 | FOH | 2025-05-09 | 2025-05-22 | 4.22 - Sprint 2 | Hemanath Jayaraman/Subbulakshmi | 47905 | MFOH [WAVE] - Add a new template for Student Meal to Custom Report | Story Completed | 8 | 7.75 | 31 | Hemanath | Sabir | NA | Sabir | NA | 42272 | 2025-05-19 |  | Subha | NA |  |  |  | NA |  | The release was put on hold by client so a draft PR was created. | Meets Expectation
2 | FOH | 2025-05-09 | 2025-05-22 | 4.22 - Sprint 2 | Sabir Shaikh/Subbulakshmi | 48229 | 48229 - [WAVE] Mosaic FOH - Admin View of Real Time Transactions Modifications | Story Completed | 3 | 4.5 | 18 | Sabir | Hemanath | NA | Hemanath | [12 empty] | Blank
3 | FOH | 2025-05-09 | 2025-05-22 | 4.22 - Sprint 2 | Vidhya/Subbulakshmi | 47904 | MFOH [WAVE] - Add a new template for A La Carte to Custom Report | Story Completed | 3 | 4 | 16 | Vidhya | Ashwin | Grand Total should not come if there is only one school in the report | Ashwin | Nil | 42270 | 2025-05-19 |  | Subha | Nil |  |  |  | Alignments and Spacing should be ensured |  | Drafted PR | Meets Expectation
4 | FOH | 2025-05-09 | 2025-05-22 | 4.22 - Sprint 2 | Vidhya/Subbulakshmi | 47909 | MFOH [WAVE] - Add a new template for Student Listing to Custom Report | Story Completed | 8 | 7.5 | 29.5 | Vidhya | Hemanath | Nil | Hemanath | Nil | 42334 | 2025-05-22 |  | Subha | Nil |  |  |  | Alignments and Spacing should be ensured |  | Drafted PR | Meets Expectation
5 | FOH Wave | #N/A | #N/A | 4.22 - Sprint 2 Stretch | Hemanath Jayaraman | 47907 | MFOH [WAVE] - Add a new template for Menu Products Sold to Custom Report | Story Being Developed | 13 |  | 10 | [15 empty] | Picked it up at the end of the sprint. | Meets Expectation
7 | FOH | 2025-05-09 | 2025-05-22 | 4.22 - Sprint 2 Stretch | Sabir Shaikh | 47906 | MFOH [WAVE] - Add a new template for Eligibility Record Listing to Custom Report | Story Being Developed | 5 | 6.75 | 27 | Sabir | Hemanath | Found one bug.Resolved it. | [12 empty] | Carry forward to next sprint | Blank
8 | FOH | 2025-05-09 | 2025-05-22 | 4.22 - Sprint 2 Stretch | Subblakshmi | 48192 | MFOH Automation | Story Being Developed | 5 | 3 | 15 | [15 empty] | Carry forward to next sprint | Blank
Blank
Blank
Blank

## 4.22 - Sprint 2-FOH Wave-Defect
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## 4.22 - Sprint 1-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH Wave | #N/A | #N/A | 4.22 - Sprint 1 | Arvinth/Alpha/Subha | 47875 | Mosaic - FOH 4.21(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 5 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 | Arvinth | 47548 | MFOH - MSB Reconciliation (Batch Detail Report) | Story Completed | 3 | 3 | 6 | Arvinth | Alpha | Add footer line | Alpha | None | 42015 | 2025-05-02 | 2025-05-02 | Subha | Add summary over a class | Ying | 2025-05-02 | None | None | NA
3 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 Stretch | Atchaiah | 47817 | MFOH-Automation | Story Completed | 3 | 3 | 12 | NA | NA | NA | NA | NA | 42032 | 2025-05-05 | 2025-05-05 | NA | NA | Ying | 2025-05-05 | NA | NA | NA | 47405, 47556, 46476, 46017, 47307
4 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 | Alpha | 44984 | Mosaic FOH - MSB Reconciliation (UI + Data structure changes) | Story Completed | 8 | 8 | 26 | Alpha | Arvinth | None | Arvinth | Create table query correction, Time need to be included in received date time filter, Revision history, Remove Sql catch block. | 42060 | 2025-05-06 | 2025-05-06 | Subha | Add summary and Serializable over a class, set command timeout as 300. | Ying | 2025-05-06 | None | None | NA
5 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 | Hemanath Jayaraman | 45067 | MFOH [WAVE] - Add Supper section to Daily Performance Report | Story Completed | 7 | 3.5 | 14 | Hemanath | Subbulakshmi | None | Arvinth | 1. In the revision summary, remove the last name, and align the comments as per the previous ones and also update the updated date and copyright year to current year. 2. Update the SP DailyPerformanceReport to populate the supper meals count as per clarifications from PO. | 42013 | 2025-05-02 | 2025-05-02 | Subha | None | Ying | 2025-05-02 | None | None | NA | At the client side intended members are busy hence yet to do client POV
6 | FOH Wave | #N/A | #N/A | 4.22 - Sprint 1 | Ashwin/Arvinth/Alpha | 25068 | d | Story Completed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 41900 | 2025-04-25 | 2025-04-25 | NA | NA | Ying | 2025-04-25 | None | None | NA
7 | FOH Wave | #N/A | #N/A | 4.22 - Sprint 1 | Subhasri | 43742 | Mosaic - POS (Web) - Add Menu Product wise Sold Quantities to Daily Sales Preview | Story Completed | 5 | 4 | 20 | Subhasri | Arvinth | None | Arvinth | 1. Remove unused column Reimbursable column in SP | 42023 | 2025-05-02 | 2025-05-02 | NA | NA | Ying | 2025-05-02 | None | None | NA
8 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 | Vidhya/Subbulakshmi | 47901 | MFOH [WAVE] - Add a new template for Application Student Listing to Custom Report | Story Completed | 5 | 5 | 20 | Vidhya | Hemanath | 1. If there is no data for the selected period, then existing report shows blank page and the new report shows grand total section with 0 records. 2. When I provide temporary reason as ‘none’, getting the below exception in the code 3.If I provide group by school as ‘No’, then school wise total shouldn’t show up, only grand total should show. Here school wise total is showing with 0 records count | Hemanath | Nil | 42068 | 2025-05-07 | 2025-05-07 | Nil | Nil | Ying | 2025-05-07 | Nil | Spacing should be adjusted | Nil
9 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 Stretch | Arvinth | 45805 | Mosaic - POS (Web) - Add new field to Student Export and Custom Report | Story Being Developed | 3 | 2 | 8 | [15 empty] | Waiting for PR as per the client request
10 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 Stretch | Alpha | 48188 | MFOH - MSB Reconciliation (Add functionality for printing batch detail report from reconciliation screen) | Story Being Developed | 3 | [17 empty] | Waiting for PR as per the client request
11 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 Stretch | Subhasri/Ashwin | 45673 | Mosaic - POS (Web) - Add Bus Route filter to Student Barcode Report | Story Being Developed | 3 | [17 empty] | Waiting for PR as per the client request
12 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 Stretch | Subhasri/Ashwin | 25145 | MFOH - Issue with alternate coloring in A La Carte Report | Story Ready For Testing | 1 | 0.5 | 3 | Subhasri | Ashwin | None | Ashwin | None | 42072 | 2025-05-06 | 2025-05-06 | NA | NA | Ying | 2025-05-06 | None | None | NA
13 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 Stretch | Atchaiah | 48211 | MFOH-Automation | Story Being Developed | 8 | 3 | 12 | NA | NA | NA | [12 empty] | Started this story at the end of the sprint
14 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 Stretch | Hemanath Jayaraman | 47905 | MFOH [WAVE] - Add a new template for Student Meal to Custom Report | Story Being Developed | 5 |  |  | Hemanath | [14 empty] | Picked it up at the end of the sprint
15 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 Stretch | Arvinth | 47547 | MFOH - MSB Reconciliation (Batch Summary Report) | Story Being Developed | 8 |  | 6 | [15 empty] | Picked it up at the end of the sprint
16 | FOH | 2025-04-25 | 2025-05-08 | 4.22 - Sprint 1 | Sabir Shaikh | 47904 | MFOH [WAVE] Add a new template for A La Carte to Custom Report | Story Being Developed | 5 | 5 | 24 | sabir

## 4.22 - Sprint 1-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| 4.22 - Sprint 1 | 25068 |  | Arvinth | Defect | MFOH - (4.21 Regression) - Check Listing Report is getting 2 blank pages for the special number of data | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.22 - Sprint 1 Stretch | 25145 |  | Subhasri | Defect | MFOH - Issue with alternate coloring in A La Carte Report | Minor | Manual | Internal | Defect Fixed | Design | While Testing other report UI, cross verified this report and found this UI alternate row coloring issue.

## 4.21 - Sprint 4-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Alpha/Atchaiah | 47868 | Mosaic - FOH 4.21(Regression) - Setup | Story Completed | 5 | 6 | 24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Subhasri/Atchaiah | 47870 | Mosaic - FOH 4.21(Regression) - End of Day | Story Completed | 5 | 5.25 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Ashwin/Atchaiah | 47869 | Mosaic - FOH 4.21(Regression) - Students | Story Completed | 5 | 5.25 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Alpha/Atchaiah | 47875 | Mosaic - FOH 4.21(Regression) - Reports - (Excluding Free/Reduced) | Story Being Tested | 8 | 8.5 | 34 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Since all the regression stories are assigned in the sprint, also we had few planned PTO as well. So client too expected some of the story might get carry forwaded.
5 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Ashwin/Atchaiah | 47876 | Mosaic - FOH 4.21 (Regression) - POS(Menu Option) | Story Completed | 2 | 2 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Atchaiah | 47872 | Mosaic - FOH 4.21 (Regression) - Reports - Eligibility (F&R) | Story Completed | 3 | 3 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Subhasri/Atchaiah | 47873 | Mosaic - FOH 4.21 (Regression) - Eligibility (F&R) | Story Completed | 5 | 5.25 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Arvinth/Atchaiah | 47867 | Mosaic - FOH 4.21(Regression) - Utilities | Story Completed | 5 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Vidhya/Subbulakshmi | 47526 | MFOH [WAVE] - Custom Report Improvements (Only Disallow/Hide Save) - Acceleration Initiative | Story Completed | 3 | 1 | 6 | Vidhya Subramani | Hemanath | None | Hemanath | None | 41709 | 2025-04-11 | 2025-04-11 | Subha | Add comments for the JS functions | Ying | 2025-04-11 | None | None | None
10 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Ashwin/Atchaiah | 25070 | MFOH - (4.21 Regression) - Contacts information is removing after saving student | Defect Fixed | 0 | 0 | 0 | Arvinth | Arvinth | None | Arvinth | None | 41879 | 2025-04-24 | 2025-04-24 | Subha | None | Ying | 2025-04-24 | None | None | NA
11 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Arvinth/Atchaiah | 25065 | MFOH - (4.21 Regression) - Console errors on Update Application Address & Email | Defect Fixed | 0 | 0 | 0 | Arvinth | NA | NA | NA | NA | 41863 | 2025-04-23 | 2025-04-23 | Subha | None | Ying | 2025-04-23 | None | None | NA
12 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 | Arvinth/Atchaiah | 25069 | MFOH - (4.21 Regression) - Hitting exception when clicking on Serving Period header in Time Frames tab | Defect Fixed | 0 | 0 | 0 | Arvinth | NA | NA | NA | NA | 41862 | 2025-04-23 | 2025-04-23 | Subha | None | Ying | 2025-04-23 | None | None | NA
13 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 Stretch | Arvinth | 47548 | MFOH - MSB Reconciliation (Batch Detail Report) | Story Being Developed | 3 | 1.5 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 Stretch | Alpha | 44984 | Mosaic FOH - MSB Reconciliation (UI + Data structure changes) | Story Being Developed | 8 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 Stretch | Sabir Shaikh/Hemanath Jayaraman | 47575 | Mosaic -FOH 4.21 Admin View of Real-Time POS Transactions (Acceleration initiative) | Story Completed | 18 | 18 | 94 | Sabir/Hemanath | Vidhya | UI controls alignment issues, Console error,Items per page icon missing Pager icon missing. | Subha/Vidhya | UI controls alignment issues, Console error,Items per page icon missing Pager icon missing, Please format the stored procedure as standard followed in FOH. | 41869 | 2025-04-24 | 2025-04-25 | Subha | Please format the stored procedure as standard followed in FOH. Cashier field is username only, need to change the datatype size as like username column.Voided field - It can be Varchar (5) | Ying | 2025-04-25 | 1. Don't think you need to add single quote around the alias unless there is a space in alias. Please remove them as it's not a common practice for us . 2.change all the query parameters definition to : query.Parameters.Add(new SqlParameter("@SchoolID", SqlDbType.UniqueIdentifier) { Value = schoolID.Value}); 3.We still have customers that have sql server 2008, so can't use CONCAT, use "+" instead. | Multiple POV were conducted. Please fix the UI functionalities as per AC and per feedback suggestions | NA
16 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 Stretch | Vidhya | 47901 | MFOH [WAVE] - Add a new template for Application Student Listing to Custom Report | Story Being Developed | 8 | 7.5 | 30
17 | FOH | 2025-04-11 | 2025-04-24 | 4.21 - Sprint 4 Stretch | Hemanath Jayaraman | 45067 | MFOH [WAVE] - Add Supper section to Daily Performance Report | Story Being Developed | 7 |  | 14

## 4.21 - Sprint 4-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| 4.21 - Sprint 4 | 25070 |  | Ashwin | Defect | MFOH - (4.21 Regression) - Contacts information is removing after saving student | Minor | Automation | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.21 - Sprint 4 | 25065 |  | Arvinth | Defect | MFOH - (4.21 Regression) - Console errors on Update Application Address & Email | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.21 - Sprint 4 | 25069 |  | Arvinth | Defect | MFOH - (4.21 Regression) - Hitting exception when clicking on Serving Period header in Time Frames tab | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore

## 4.21 - Sprint 3-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 | Alpha | 47639 | Hide Student IDs in POS Serving Line(BOCES) | Story Completed | 3 | 3 | 14 | Alpha | Arvinth | System specific label alignment and POS override dropdown in system setting shows empty | Arvinth | None | 41597 | 2025-04-04 | 2025-04-07 | Subha | None | Steve/Ying | 2025-04-07 | None | None | NA
2 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 | Arvinth/Alpha | 47697 | MFOH - Modifications to NC SFS-4 Export | Story Completed | 3 | 3 | 9 | Arvinth | Alpha | None | Alpha | None | 41532 | 2025-04-01 | 2025-04-01 | Subha | None | Ying | 2025-04-01 | None | None | NA
3 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 | Alpha | 47670 | MFOH - Add NJEIE counts to Eligibility Record Listing Report | Story Completed | 3 | 3 | 11 | Alpha | Arvinth | None | Arvinth | None | 41590 | 2025-04-04 | 2025-04-04 | Subha | Revision history in one file | Ying | 2025-04-04 | None | None | NA
4 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 | Arvinth | 47669 | Add an ability to update ISP value for multiple schools | Story Completed | 5 | 5 | 17 | Arvinth | Alpha | None | Alpha | None | 41589 | 2025-04-04 | 2025-04-04 | Subha | Change naming | Ying | 2025-04-04 | None | None | NA
5 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 | Ashwin/Arvinth | 47677 | MFOH - Mosaic - POS - Update IEGs (2025-26) | Story Completed | 2 | 2 | 4 | NA | NA | NA | Arvinth | None | 41588 | 2025-04-04 | 2025-04-04 | NA | NA | Ying | 2025-04-04 | None | NA | NA
6 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 | Arvinth/Alpha | 24779 | Mosaic POS (Web) - Aramark Export - Employee Meals appearing in Employee Alacarte NR | Story Completed | 2 | 2 | 5 | Arvinth | Alpha | None | Alpha | None | 41570 | 2025-04-03 | 2025-04-03 | Subha | None | Ying | 2025-04-03 | None | None | NA
7 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 | Subhasri/Alpha | 47623 | MFOH - CPS Dashboard V3 | Story Completed | 13 | 13 | 40 | Subhasri | Alpha | 1.In the user dashboard, if we change the start date to prior date more than 30days, error pop up is blank | Alpha | None | 47623 | 2025-04-07 | 2025-04-07 |  |  | Steve | 2025-04-07 | None | None | NA
8 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 Stretch | Alpha | 47671 | MFOH - Add NJEIE counts to Eligibility Record Student Listing Report | Story Ready For Testing | 3 | 3 | 10 | Alpha | Arvinth | None | Arvinth | Date change | 41677 | 2025-04-10 | 2025-04-10 | Subha | None | Ying | 2025-04-10 | Instead of hard code the state, determine whether it's in any of the state that have income guideline | None | NA
9 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 Stretch | Atchaiah | 47817 | MFOH-Automation | Story Being Developed | 8 |  | 20 | NA | NA | NA | NA | NA |  |  |  | NA | NA |  |  |  | NA | NA
10 | FOH | 2025-03-28 | 2025-04-10 | 4.21 - Sprint 3 Stretch | Arvinth | 47548 | MFOH - MSB Reconciliation (Batch Detail Report) | Story Being Developed | 8 |  | 22

## 4.21 - Sprint 3-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| 4.21 - Sprint 3 | 24779 |  | Arvinth | Defect | Mosaic POS (Web) - Aramark Export - Employee Meals appearing in Employee Alacarte NR | Significant | Manual | External | Defect Fixed | Existing_Issues | Request from customer to change the description

## 4.21 - Sprint 2-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH Wave | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 | Subhasri | 47307 | MFOH - Allow Add Transactions only if the day is reopened from Open Previous Day option (Corey's list) | Story Completed | 3 | 3 | 15 | Subhasri | Arvinth | NA | Arvinth | None | 41267 | 2025-03-17 | 2025-03-18 | NA | NA | Steve | 2025-03-18 | Only allow to add transactions to a day that has been opened using Open Previous Day as like Serving Line application | None | NA
2 | FOH Wave | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 | Alpha | 47084 | Mosaic POS (Web) - SP Edit Check appears to be rounding based incorrectly | Story Completed | 2 | 2 | 3 | Alpha | Arvinth | None | Arvinth | None | 41280 | 2025-03-18 | 2025-03-19 | Subha | None | Ying | 2025-03-19 | None | None | NA
3 | FOH Wave | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 | Ashwin/Alpha | 46017 | Mosaic - POS (Web) - Add new columns to Logout POS User Search | Story Completed | 2 | 2 | 4 | Ashwin | Alpha | None | Alpha | None | 41252 | 2025-03-17 | 2025-03-18 | Subha | None | Ying | 2025-03-18 | User record should be returned even there is no transaction record. | None | NA
4 | FOH Wave | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 | Arvinth/Alpha | 47556 | MFOH - North Carolina SFS-4 Export | Story Completed | 8 | 8 | 27 | Arvinth | Alpha | Add datatype to SQLParameter | Alpha | None | 47556 | 2025-03-24 | 2025-03-24 | Subha | None | Ying | 2025-03-24 | None | None | None
5 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 | Ashwin/Arvinth | 46316 | Mosaic - POS (Web) - Improvements to A La Carte Report | Story Completed | 5 | 3 | 18 | Ashwin | Alpha | Generating blank page Error in close day for existing records | Alpha | Change IsSummary to ReportType | 41308 | 2025-03-20 | 2025-03-20 | Subha | None | Ying | 2025-03-20 | None | None | None
6 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 | Alpha | 46164 | Mosaic - POS (Web) - Add CEP ISP calculation to Chartwells Export | Story Being Tested | 5 | 5 | 14 | Alpha | Arvinth | None | Arvinth | None | 41329 | 2025-03-20 | 2025-03-20 | Subha | None | Ying | 2025-03-20 | None | None | NA | In QA(Mike) Bucket Mike was on PTO for last one week and once he was back he was busy in Release
7 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 | Subhasri/Alpha | 46867 | MFOH - Remove Student 2nd meals from VA SNP-12 Report | Story Completed | 2 | 2 | 7 | Subhasri | Alpha | NA | Alpha | None | 41268 | 2025-03-17 | 2025-03-17 |  |  | Ying | 2025-03-17 | None | None | NA
9 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 | Ashwin/Alpha/Arvinth | 47170 | MFOH - Add Blank option to Student Status filter in Student Maintenance (Corey's list) | Story Completed | 5 | 5 | 19 | Alpha | Arvinth | None | Arvinth | None | 41363 | 2025-03-24 | 2025-03-24 | Subha | None | Ying | 2025-03-24 | None | None | NA
8 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 Stretch | Atchaiah | 47638 | MFOH - Automation | Story Completed | 8 |  | 32 | [5 empty] | 41438 | 2025-03-27 | 2025-04-09 |  |  | Ying | 2025-04-09 |  |  |  | 45612-changes on Close Day Reports, 46987-Add Effective Date and Eligibility Reason to Student Maintenance, 46783-A La Carte & Meal-Revenue Export, 47297-Changes done on Barcode Report, 45675-Add 'Eligibility Status' filter to Disclosure Report
10 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 Stretch | Alpha | 44984 | Mosaic FOH - MSB Reconciliation (UI + Data structure changes) | Story Being Developed | 13
11 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 Stretch | Arvinth | 24779 | Mosaic POS (Web) - Aramark Export - Employee Meals appearing in Employee Alacarte NR | Story Being Developed | 3
12 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 Stretch | Subhasri | 47623 | MFOH - CPS Dashboard V3 | Story Being Developed | 13
13 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 Stretch | Alpha | 24842 | Error in Menu Product Maintenance while selecting an image | Story Ready For Testing | 1 |  | 4 | Alpha | Arvinth | None | Arvinth | None | 41254 | 2025-03-17 | 2025-03-17 | Subha | None | Ying | 2025-03-17 | None | None | NA
14 | FOH | 2025-03-14 | 2025-03-27 | 4.21 - Sprint 2 Stretch | Alpha | 24912 | MFOH - Remove unused/redundant code from Eligibility Record Report's CSV | Story Ready For Testing | 1 |  | 1 | Alpha | NA | NA | Arvinth | None | 41388 | 2025-03-25 | 2025-03-25 | Subha | None | Ying | 2025-03-25 | None | NA | NA

## 4.21 - Sprint 2-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| 4.21 - Sprint 2 Stretch | 24842 |  | Alpha | Defect | Error in Menu Product Maintenance while selecting an image | Minor | Automation | External | Open | Existing_Issues | Found through offshore automation
| 4.21 - Sprint 2 Stretch | 24912 | 41585 | Alpha | Defect | MFOH - Remove unused/redundant code from Eligibility Record Report's CSV | Minor | Manual | Internal | Open | Enhancements | Removing constructor that is not in use

## 4.21 - Sprint 1-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH Wave | #N/A | #N/A | 4.21 - Sprint 1 | Arvinth | 47405 | MFOH - Tyler-MUNIS Financial Export | Story Completed | 13 | 13 | 45 | Arvinth | Alpha | None | Alpha | Include datatype the SqlParameter | 41171 | 2025-03-10 | 2025-03-10 | Subha | None | Ying | 2025-03-10 | None | None | NA
2 | FOH Wave | #N/A | #N/A | 4.21 - Sprint 1 | Ashwin | 47362 | Mosaic FOH - Tiered Sales Model Drop List(Acceleration) | Story Completed | 3 | 3 | 6 | Ashwin | Arvinth | Code for save and Get Tier Level not added | Arvinth | None | 41118 | 2025-03-06 | 2025-03-06 | Subha | None | Ying | 2025-03-06 | None | None | NA
3 | FOH Wave | #N/A | #N/A | 4.21 - Sprint 1 | Alpha | 46783 | Mosaic - POS (Web) - A La Carte & Meal - Revenue Export | Story Completed | 2 | 2 | 3 | Alpha | Arvinth | None | Arvinth | Remove unused property. | 41094 | 2025-03-05 | 2025-03-05 | Subha | None | Ying | 2025-03-05 | None | None | NA
4 | FOH | #N/A | #N/A | 4.21 - Sprint 1 | Ashwin | 47297 | MFOH - Add Label format options to Student Maintenance > Barcode Report (Corey's list) | Story Completed | 3 | 3 | 12 | Ashwin | Alpha | Starting label row and column should not change for Listing | Alpha | None | 41170 | 2025-03-10 | 2025-03-10 | Subha | Remove unwanted display parameters | Ying | 2025-03-10 | None | None | NA
5 | FOH Wave | #N/A | #N/A | 4.21 - Sprint 1 | Subhasri/Alpha | 47077 | Mosaic FOH - Add Checks to Student Account Summary Report | Story Completed | 5 | 5 | 16 | Subhasri | Alpha | Add Cash and check payments for the a student, Report showing correctly. Then try adding the prepayments, the previous data loses from Credits > POS deposits and only prepayments showing. | Alpha | None | 41144 | 2025-03-07 | 2025-03-07 | NA | NA | Ying | 2025-03-07 | None | None | NA
6 | FOH | #N/A | #N/A | 4.21 - Sprint 1 Stretch | Alpha | 47168 | MFOH (SL) - Add the ability to see transactions that are Marked for Review | Story Ready For Testing | 5 | 5 | 17 | Alpha | Subha | None | Arvinth | None | 41198 | 2025-03-12 | 2025-03-12 | Subha | Revision history in one file | Steve | 2025-03-12 | None | None | NA | This story moved to onsite QA bucket.
7 | FOH Wave | #N/A | #N/A | 4.21 - Sprint 1 Stretch | Atchaiah | 47433 | MFOH - Automation | Story Completed | 8 |  | 32 | [5 empty] | 41215 | 2025-03-13 |  |  |  | Ying | 2025-03-18 | NA | NA | NA | 46945, 46029, 46955, 46986, 46424 and upgraded selenium 3 to 4
8 | FOH | #N/A | #N/A | 4.21 - Sprint 1 Stretch | Alpha | 47084 | Mosaic POS (Web) - SP Edit Check appears to be rounding based incorrectly | Story Being Developed | 8
9 | FOH Wave | #N/A | #N/A | 4.21 - Sprint 1 Stretch | Subhasri | 47307 | MFOH - Allow Add Transactions only if the day is reopened from Open Previous Day option (Corey's list) | Story Being Developed | 5
10 | FOH Wave | #N/A | #N/A | 4.21 - Sprint 1 Stretch | Ashwin | 46316 | Mosaic - POS (Web) - Improvements to A La Carte Report | Story Being Developed | 8 | 8 | 32 | Ashwin | Alpha | Generating blank page Error for in close day for existing records | Alpha | Change IsSummary to ReportType

## 4.21 - Sprint 1-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments

## 4.20 - Sprint 4-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 4 | Arvinth/Ashwin/Atchaiah | 47214 | Mosaic - FOH 4.20(Regression) - Setup | Story Completed | 5 | 5 | 24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
2 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 4 | Alpha/Atchaiah | 47213 | Mosaic - FOH 4.20(Regression) - Utilities | Story Completed | 5 | 5 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
3 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 4 | Subhasri/Atchaiah | 47216 | Mosaic - FOH 4.20(Regression) - End of Day | Story Completed | 5 | 5 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
4 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Arvinth/Atchaiah | 47234 | Mosaic - FOH 4.20(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 8 | 8 | 36 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
5 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Subhasri/Atchaiah | 47235 | Mosaic - FOH 4.20 (Regression) - POS(Menu Option) | Story Completed | 2 | 2 | 10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
6 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 4 | Alpha/Ashwin/Atchaiah | 47215 | Mosaic - FOH 4.20(Regression) - Students | Story Completed | 5 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
7 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Alpha/Arvinth/Atchaiah | 47219 | Mosaic - FOH 4.20 (Regression) - Eligibility (F&R) | Story Completed | 5 | 5 | 22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
8 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 4 | Subhasri/Atchaiah | 47218 | Mosaic - FOH 4.20 (Regression) - Reports - Eligibility (F&R) | Story Completed | 3 | 3 | 14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
9 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Alpha | 24732 | MFOH - (4.20 Regression) - Daily sales preview report displays school name partially | Defect Fixed | 0 | 0 | 0 | Ashwin | Alpha | None | Alpha | None | 40930 | 2025-02-25 | 2025-02-25 | NA | NA | Ying | 2025-02-25 | None | NA | NA | Regression Defects
10 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Alpha | 24733 | MFOH - (4.20 Regression) - New schools doesn't add to the school group even though Auto Include schools checkbox is checked | Defect Fixed | 0 | 0 | 0 | Ashwin | Alpha | None | Alpha | None | 40931 | 2025-02-25 | 2025-02-25 | NA | NA | Ying | 2025-02-25 | None | NA | NA | Regression Defects
11 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Alpha | 24734 | MFOH - (4.20 Regression) - Last updated date issue in Menu Product maintenance/Menu Product Import | Defect Fixed | 0 | 0 | 0 | Ashwin | Alpha | None | Alpha | None | 40932 | 2025-02-25 | 2025-02-25 | NA | NA | Ying | 2025-02-25 | None | NA | NA | Regression Defects
12 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Alpha | 24736 | MFOH - (4.20 Regression) - All Checkbox checked on deselecting grid items in School Maintenance | Defect Fixed | 0 | 0 | 0 | Ashwin | Alpha | None | Alpha | None | 40933 | 2025-02-25 | 2025-02-25 | NA | NA | Ying | 2025-02-25 | None | NA | NA | Regression Defects
13 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Arvinth | 24741 | MFOH - (4.20 Regression) - Generating 2 pages when no data in Reimbursement Due Report | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40939 | 2025-02-25 | 2025-02-25 | NA | NA | Ying | 2025-02-25 | None | NA | NA | Regression Defects
14 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Arvinth | 24739 | MFOH - (4.20 Regression) - Issue with main check box in the Student Grade Range Search screen | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | Header checked is checked when checking other grids check box | Arvinth | None | 40937 | 2025-02-25 | 2025-02-25 | NA | NA | Ying | 2025-02-25 | None | NA | NA | Regression Defects
15 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Arvinth | 24735 | MFOH - (4.20 Regression) - Delete button enabled while the name already exists on another Custom Report Setting popup shows up | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40938 | 2025-02-25 | 2025-02-25 | NA | NA | Ying | 2025-02-25 | None | NA | NA | Regression Defects
16 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Arvinth | 24737 | MFOH - (4.20 Regression) - Allergen, Allergen description and Allergen Active is disappearing during Save | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40976 | 2025-02-26 | 2025-02-26 | NA | NA | Ying | 2025-02-26 | None | NA | NA | Regression Defects
17 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Arvinth | 24740 | MFOH - (4.20 Regression) - Import Data button is present in Report as well | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40975 | 2025-02-26 | 2025-02-26 | NA | NA | Ying | 2025-02-26 | None | NA | NA | Regression Defects
18 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Arvinth | 24752 | MFOH - (4.20 Regression) - Name already exists popup enables delete button in Import & export setting | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40977 | 2025-02-26 | 2025-02-26 | NA | NA | Ying | 2025-02-26 | None | NA | NA | Regression Defects
19 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Ashwin/Arvinth | 24753 | MFOH - (4.20 Regression) - Adjustment Type drop down validation label is showing the propery name (IsDeposit) | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40974 | 2025-02-26 | 2025-02-26 | NA | NA | Ying | 2025-02-26 | None | NA | NA | Regression Defects
20 | FOH | #N/A | #N/A | 4.20 - Sprint 4 | Subhasri/Arvinth | 24756 | MFOH - (4.20 Regression) - Auto Include School clearing in School Group maintenance | Defect Fixed | 0 | 0 | 0 | Subhasri | NA | None | None | None | 40986 | 2025-02-26 | 2025-02-26 | NA | NA | Ying | 2025-02-26 | None | NA | NA | Regression Defects

## 4.20 - Sprint 4-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| 4.20 - Sprint 4 | 24732 |  | Ashwin | Defect | MFOH - (4.20 Regression) - Daily sales preview report displays school name partially | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24733 |  | Ashwin | Defect | MFOH - (4.20 Regression) - New schools doesn't add to the school group even though Auto Include schools checkbox is checked | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24734 | 46424 | Ashwin | Defect | MFOH - (4.20 Regression) - Last updated date issue in Menu Product maintenance/Menu Product Import | Minor | Manual | Internal | Defect Fixed | Development | Issue from story 46424, found during regression testing by offshore
| 4.20 - Sprint 4 | 24736 |  | Ashwin | Defect | MFOH - (4.20 Regression) - All Checkbox checked on deselecting grid items in School Maintenance | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24741 |  | Ashwin | Defect | MFOH - (4.20 Regression) - Generating 2 pages when no data in Reimbursement Due Report | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24739 |  | Ashwin | Defect | MFOH - (4.20 Regression) - Issue with main check box in the Student Grade Range Search screen | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24735 |  | Ashwin | Defect | MFOH - (4.20 Regression) - Delete button enabled while the name already exists on another Custom Report Setting popup shows up | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24737 |  | Ashwin | Defect | MFOH - (4.20 Regression) - Allergen, Allergen description and Allergen Active is disappearing during Save | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24740 |  | Ashwin | Defect | MFOH - (4.20 Regression) - Import Data button is present in Report as well | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24752 |  | Ashwin | Defect | MFOH - (4.20 Regression) - Name already exists popup enables delete button in Import & export setting | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24753 |  | Ashwin | Defect | MFOH - (4.20 Regression) - Adjustment Type drop down validation label is showing the propery name (IsDeposit) | Minor | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
| 4.20 - Sprint 4 | 24756 |  | Subhasri | Defect | MFOH - (4.20 Regression) - Auto Include School clearing in School Group maintenance | Significant | Manual | External | Defect Fixed | Existing_Issues | Existing issue in production, found during regression testing by offshore
Note on M1: Preethi Rajasekaran: Preethi Rajasekaran: 1. Whether it is Production or Testing Defect 2. Who Developed this 3. Reason for the Defect

## 4.20 - Sprint 3-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 3 | Arvinth | 45612 | Mosaic - POS (Web) - Add SPP and SP droplist to SPEC Report (Close Day Reports) | Story Completed | 8 | 8 | 29 | Arvinth | Alpha | UI Issue on changing dropdown | Alpha | None | 45612 | 2025-02-11 | 2025-02-11 | Subha | None | Ying | 2025-02-11 | None | None | NA
2 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 3 | Subhasri | 23549 | MFOH (CPS - C0221) - ADA Visual Reports vs IL NSLP WINS Export | Defect Fixed | 5 | 5 | 16 | Subhasri | Alpha | None | Alpha | None | 40700 | 2025-02-07 | 2025-02-07 | NA | NA | Ying | 2025-02-07 | None | None | None
3 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 3 | Alpha/Arvinth | 46987 | MFOH - Add Student Effective Date and Student Eligibility Reason to Student Maintenance (NJ) | Story Completed | 5 | 5 | 18.25 | Alpha | Atchaiah | None | Arvinth | None | 40655 | 2025-02-05 | 2025-02-05 | Subha | Change the declaration from "" to string.Empty | Ying | 2025-02-05 | None | None | NA
4 | FOH | #N/A | #N/A | 4.20 - Sprint 3 | Alpha | 46955 | MFOH - Add alternate pathing options to the IL WINS NSLP Export | Story Completed | 3 | 3 | 10 | Alpha | Arvinth | Sub folder without slash at end, then that value is concatenating with the file name. | Arvinth | None | 40695 | 2025-02-07 | 2025-02-07 | Suba | None | Ying | 2025-02-07 | None | None | None
5 | FOH | #N/A | #N/A | 4.20 - Sprint 3 | Subhasri/Ashwin | 24493 | Mosaic POS (Web) - Transaction Export Download Defect | Defect Fixed | 1 | 1 | 3 | Subhasri | Ashwin | None | Ashwin | None | 40681 | 2025-02-06 | 2025-02-06 | NA | NA | Ying | 2025-02-06 | None | None | NA
6 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 3 | Subhasri/Alpha | 24489 | Spartanburg District Five - Building Summary Report Miscalculation | Defect Fixed | 2 | 2 | 7 | Subhasri | NA | NA | NA | NA | 40684 | 2025-02-06 | 2025-02-06 | NA | NA | Ying | 2025-02-06 | None | None | NA
7 | FOH | #N/A | #N/A | 4.20 - Sprint 3 | Ashwin/Alpha | 46424 | Mosaic - POS (Web) - Add Tracking for Menu Products (Log user who modified it) | Story Completed | 1 | 1 | 3 | Ashwin | Arvinth | None | Arvinth | None | 46424 | 2025-02-04 | 2025-02-04 | Subha | None | Ying | 2025-02-04 | None | None | None
8 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 3 Stretch | Ashwin | 46986 | MFOH - Add Serving Period Multi Select Droplist to Schools not in School Group Report (CPS) | Story Completed | 3 | 3 | 7 | Ashwin | Arvinth | None | Arvinth | None | 40736 | 2025-02-12 | 2025-02-12 | Subha | Remove unused code and comments | Ying | 2025-02-12 | None | None | None
9 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 3 Stretch | Atchaiah | 47118 | MFOH - Automation | Story Completed | 8 |  | 32 | NA | NA | NA | NA | NA | 40759 | 2025-02-13 | 2025-02-14 | NA |  | Ying | 2025-02-14 | None | None | None | 45796,45797,46060,46111,46423,46915 and 46946
10 | FOH | #N/A | #N/A | 4.20 - Sprint 3 Stretch | Alpha | 46783 | Mosaic - POS (Web) - A La Carte vs Meal - Revenue Export (for 4.21) | Story Being Developed | 8 |  | 28 | Alpha
11 | FOH | #N/A | #N/A | 4.20 - Sprint 3 Stretch | Ashwin | 43484 | Mosaic - POS (Web) - Display count for Mapping Translation (Student Import) (4.21) | Story Being Developed | 8
12 | FOH | #N/A | #N/A | 4.20 - Sprint 3 Stretch | Subhasri/Alpha | 24621 | MFOH - POS Number is always set to ALL when editing a menu assignment | Defect Fixed | 3 | 3 | 8 | Subhasri | Arvinth | 1. When school is changed then default value is not changed 2. When adding a new menu assignment, multi select dropdown is setting a different value | Arvinth | None | 40750 | 2025-02-12 | 2025-02-12 | NA | NA | Ying | 2025-02-12 | None | None | None

## 4.20 - Sprint 3-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Parent Story | Developer | Issue Type | Issue Description | Priority | Defect Source | Type | Status | Root Cause Category | Comments
| 4.20 - Sprint 3 | 23549 |  | Subhasri | Defect | MFOH (CPS - C0221) - ADA Visual Reports vs IL NSLP WINS Export | Significant | Manual | External | Defect Fixed |  | Making some adjustments to how we are calculating attendance for subsites Working on Defect Backlog
| 4.20 - Sprint 3 | 24493 |  | Subhasri | Defect | Mosaic POS (Web) - Transaction Export Download Defect | Minor | Manual | External | Defect Fixed |  | Export Not downloading in some scenerios Working on Defect Backlog
| 4.20 - Sprint 3 | 24489 |  | Subhasri | Defect | Spartanburg District Five - Building Summary Report Miscalculation | Significant | Manual | External | Defect Fixed |  | Calculation mismatch Working on Defect Backlog
| 4.20 - Sprint 3 | 24621 |  | Subhasri | Defect | MFOH - POS Number is always set to ALL when editing a menu assignment | Minor | Manual | Internal | Defect Fixed

## 4.20 - Sprint 2-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Actual Worklog (Hours) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 2 | Arvinth | 46539 | Mosaic - POS (Web) - Modify School Export to include new columns (DBS) | Story Completed | 2 | 2 | 2 | Arvinth | Alpha | None | Alpha | None | 40368 | 2025-01-17 | 2025-01-17 | Subha | None | Ying | 2025-01-17 | None | None | NA
2 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 2 | Subhasri/Alpha | 46425 | Mosaic - POS (Web) - Add a warning popup when Deleting POS Menus | Story Completed | 3 | 3 |  | Subhasri | Atchaiah | When duplicate POS Menu is created and already exists error pop up is not closing properly | Arvinth | None | 40485 | 2025-01-24 | 2025-01-24 | NA | NA | Ying | 2025-01-24 | None | None | NA
3 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 2 | Alpha/Subhasri | 46675 | Mosaic - POS (Web) - Add the ability to assign POS Menus to multiple POS Numbers | Story Completed | 3 | 3 |  | Alpha | Arvinth | Validation and UI issues | Arvinth | None | 40542 | 2025-01-29 | 2025-01-29 | Subha | None | Ying | 2025-01-29 | None | None | None
4 | FOH | #N/A | #N/A | 4.20 - Sprint 2 | Ashwin/Alpha | 46945 | MFOH - Modify Layout and add Privacy Policy and Terms of Use link to Login Screen (Web) | Story Completed | 3 | 3 |  | Ashwin | Arvinth | None | Arvinth | None | 40420 | 2025-01-22 | 2025-01-22 | Subha | None | Ying | 2025-01-22 | None | Adjust the Mosaic logo to the perfect center of the login form | None
5 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 2 | Arvinth | 46029 | Mosaic FoH POS (KDE) - CEP Reimbursement Calculations Free/Paid "Reimbursement Due / Standard Claim" Reports | Story Completed | 5 | 5 |  | Arvinth | Alpha | None | Alpha | None | 40497 | 2025-01-27 | 2025-01-27 | Subha | None | Ying | 2025-01-27 | None | None | None
6 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 2 | Subhasri/Arvinth | 46111 | Mosaic - POS (Web) - Arrange Menu Products in Alphabetical Order (POS Menu Maintenance) (DBS) | Story Completed | 3 | 3 |  | Subhasri | Arvinth | None | Arvinth | None | 40531 | 2025-01-28 | 2025-01-28 | NA | NA | Ying | 2025-01-28 | None | None | NA
7 | FOH | #N/A | #N/A | 4.20 - Sprint 2 | Arvinth | 46060 | Mosaic - POS (Web) - Modify POS Menu Order to a droplist for Multiple Assignments | Story Completed | 3 | 3 |  | Arvinth | Alpha | None | Alpha | None | 40532 | 2025-01-28 | 2025-01-28 | Subha | None | Ying | 2025-01-28 | None | Change the POS Menu Order in Add Assignment | None
8 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 2 Stretch | Ashwin | 45797 | Mosaic - POS (Web) - Add a new report type 'Daily with Only Status' to POS Roster Report | Story Ready For Testing | 3 | 3 |  | Ashwin | Arvinth | None | Arvinth | None | 40543 | 2025-01-29 | 2025-01-29 | Subha | None | Ying | 2025-01-29 | None | None | None | Testing will be done by onsite QA - Mike in Sprint 3
9 | FOH | #N/A | #N/A | 4.20 - Sprint 2 Stretch | Ashwin | 45796 | Mosaic - POS (Web) - Add a new report type 'Daily with Only Status' to POS Roster Report (Extended) | Story Ready For Testing | 3 | 2 |  | Ashwin | Arvinth | None | Arvinth | None | 40547 | 2025-01-29 | 2025-01-29 | Subha | None | Ying | 2025-01-29 | None | None | None | Testing will be done by onsite QA - Mike in Sprint 3
10 | FOH | #N/A | #N/A | 4.20 - Sprint 2 Stretch | Atchaiah | 46973 | MFOH-Automation | Story Completed | 8 | 8 | [6 empty] | 40567 | 2025-01-30 | 2025-02-04 | Subha |  | Ying | 2025-02-04 | NA | NA | NA
11 | FOH | #N/A | #N/A | 4.20 - Sprint 2 Stretch | Ashwin | 45804 | Mosaic - POS (Web) - Add 'Include Barcode' filter to POS Roster Report | Story Peer Review | 3 |  |  | Ashwin | Arvinth | None | Arvinth | None |  |  |  | Subha |  |  |  |  | Remove the border line between Photo and Barcode |  | Story review with Onsite Lead - In Progress
12 | FOH | #N/A | #N/A | 4.20 - Sprint 2 Stretch | Ashwin | 45673 | Mosaic - POS (Web) - Add Bus Route filter to Student Barcode Report | Story Peer Review | 3 |  |  | Ashwin | [7 empty] | Subha | [6 empty] | Story review with Onsite Lead - In Progress

## FOH 4.20 - Ashwin (hidden)
S.No | Application Name | Developer | Story ID/Defect ID | Description | Status | Remarks
1 | FOH | Ashwin | 46945 | MFOH - Modify Layout and add Privacy Policy and Terms of Use link to Login Screen (Web) | Story Completed
2 | FOH | Ashwin | 45797 | Mosaic - POS (Web) - Add a new report type 'Daily with Only Status' to POS Roster Report | Story Completed
3 | FOH | Ashwin | 45796 | Mosaic - POS (Web) - Add a new report type 'Daily with Only Status' to POS Roster Report (Extended) | Story Completed
4 | FOH | Ashwin | 45804 | Mosaic - POS (Web) - Add 'Include Barcode' filter to POS Roster Report | Story Completed
5 | FOH | Ashwin | 45673 | Mosaic - POS (Web) - Add Bus Route filter to Student Barcode Report | Story Completed
6 | FOH | Ashwin | 46986 | MFOH - Add Serving Period Multi Select Droplist to Schools not in School Group Report (CPS) | Story Completed
7 | FOH | Ashwin | 43484 | Mosaic - POS (Web) - Display count for Mapping Translation (Student Import) (4.21) | Story Being Developed
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25

## 4.20 - Sprint 2-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Reason | Comments

## 4.20 - Sprint 1-Status (hidden)
S.No | Application Name | Sprint Start Date | Sprint End Date | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Column1 | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24428 | Mosaic - POS (Web) (4.19) - Delete button enables on name already exist popup while adding vending machine | Story Completed | 0.5 | 0.5 |  | Arvinth | Alpha | None | Alpha | None | 40170 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
2 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24425 | Mosaic - POS (Web) (4.19) - Delete button enables on adding local server while Name already exists popup opens | Story Completed | 0.5 | 0.5 |  | Arvinth | Alpha | None | Alpha | None | 40171 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
3 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin | 24433 | Mosaic - POS (Web) (4.19) - Name already exists popup is not showing up in POS Login Message screen | Story Completed | 0.5 | 0.5 |  | Arvinth | Alpha | None | Alpha | None | 40173 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
4 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24424 | Mosaic - POS (Web) (4.19) - Delete button enables on adding student letter while Name already exists popup opens | Story Completed | 0.5 | 0.5 |  | Arvinth | Alpha | None | Alpha | None | 40172 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
5 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24429 | Mosaic - POS (Web) (4.19) - Same name is allowing for Vending machine during edit | Story Completed | 1 | 1 |  | Subha | Arvinth | None | Arvinth | None | 40169 | 2025-01-02 | 2025-01-02 | NA | NA | Ying | 2025-01-02 | None | None | NA
6 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24431 | Mosaic - POS (Web) (4.19) - Name already exists popup is not showing up in POS Input Device screen | Story Completed | 0.5 | 0.5 |  | Subha | Arvinth | None | Arvinth | None | 40174 | 2025-01-02 | 2025-01-02 | NA | NA | Ying | 2025-01-02 | None | None | NA
7 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin | 24451 | 24451 - Mosaic - POS (Web) (4.19) - Lower limit balance and upper limit balance not working in student barcode report | Story Completed | 1 | 1 |  | Arvinth | Alpha | None | Alpha | None | 40175 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
8 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin | 24422 | Mosaic - POS (Web) (4.19) - 'This Name already exists' popup opens twice in Bus/Route Assignments | Story Completed | 0.5 | 0.5 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rejected - Code changes for 24422 and 24423 are same
9 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24427 | Mosaic - POS (Web) (4.19) - Auto Include New Schools value is not retaining in School group | Story Completed | 1 | 1 |  | Alpha | Arvinth | None | Arvinth | None | 40177 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
10 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24426 | Mosaic - POS (Web) (4.19) - Add school group Search is not working for the first time | Story Completed | 1 | 1 |  | Alpha | Arvinth | None | Arvinth | None | 40179 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
11 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin | 24432 | Mosaic - POS (Web) (4.19) - Delete button is showing during add in POS Login Message screen | Story Completed | 0.5 | 0.5 |  | Alpha | Arvinth | None | Arvinth | None | 40180 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
12 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Ashwin | 24423 | Mosaic - POS (Web) (4.19) - 'This Name already exists' popup opens twice in POS Custom Lookup | Story Completed | 0.5 | 0.5 |  | Alpha | Arvinth | None | Arvinth | None | 40176 | 2025-01-02 | 2025-01-02 | Subha | None | Ying | 2025-01-02 | None | None | NA
13 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Arvinth | 24462 | Mosaic - POS (Web) (4.19) - School not closed report doesn't shows if current day is reopened | Story Completed | 2 | 2 |  | Arvinth | Alpha | None | Alpha | None | 40263 | 2025-01-09 | 2025-01-09 | Subha | None | Ying | 2025-01-09 | None | None | NA
14 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Arvinth/Alpha | 46700 | Mosaic - POS (Web) (CPS) - Schools not in School Groups (C0204) | Story Completed | 8 | 8 |  | Arvinth | Alpha | Add comma in display parameters for school groups | Alpha | None | 40262 | 2025-01-09 | 2025-01-09 | Subha | None | Ying | 2025-01-09 | None | None | NA
15 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Alpha | 43925 | Mosaic - POS (Web) - Add a new report type to POS Roster Report (Extended) | Story Completed | 3 | 3 |  | Alpha | Atchaiah | None | Arvinth | None | 40216 | 2025-01-07 | 2025-01-07 | Subha | None | Ying | 2025-01-07 | None | None | NA
16 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Alpha | 45938 | Mosaic - POS (SL) - Modify message in Already Logged In popup (DBS) | Story Completed | 2 | 2 |  | Alpha | Arvinth | None | Arvinth | None | 40258 | 2025-01-09 | 2025-01-09 | Subha | None | Ying | 2025-01-09 | None | None | NA
17 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Alpha | 43924 | Mosaic - POS (Web) - Add a new report type to POS Roster Report | Story Completed | 3 | 3 |  | Alpha | Atchaiah | None | Arvinth | None | 40259 | 2025-01-09 | 2025-01-09 | Subha | None | Ying | 2025-01-09 | None | None | NA
18 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Subhasri | 24405 | MFOH(4.19) - NC Claim Total Monthly Attendance is using MAX Date instead of Total | Story Completed | 2 | 2 |  | Subhasri | Alpha | None | Alpha | None | 40266 | 2025-01-09 | 2025-01-09 | NA | NA | Ying | 2025-01-09 | None | None | NA
19 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Arvinth | 46611 | Mosaic - FOH 4.19 (Regression) - POS(Web) | Story Completed | 2 | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
20 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Atchai/Alpha/Arvinth | 46607 | Mosaic - FOH 4.19(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 3 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
21 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 | Subhasri | 46077 | Mosaic - FOH - Rename the import file that mosaic creates on district's SFTP Folder ( DataHub API to SFTP Folder) | Story Completed | 2 | 2 |  | Subhasri | Alpha | None | Alpha | None | 40269 | 2025-01-09 | 2025-01-09 | NA | NA | Ying | 2025-01-09 | None | None | NA
22 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 Stretch | Arvinth | 24487 | MFOH - Update Sales Demo Data SQL failing on SQL 2008 | Story Completed | 2 | 2 |  | Arvinth | Subha | None | None | None | 40312 | 2025-01-14 | 2025-01-14 | Subha | None | Ying | 2025-01-14 | None | None | NA
23 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 Stretch | Ashwin | 46423 | Mosaic - POS (Web) - Add Effective Date column to Student Search Grid | Story Completed | 2 | 2 |  | Ashwin | Arvinth | None | Arvinth | Use common method for application year | 40285 | 2025-01-09 | 2025-01-09 | Subha | None | Ying | 2025-01-09 | None | None | NA
24 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 Stretch | Subhasri | 46696 | Mosaic - POS (Web) (CPS) - Dashboard V2 | Story Ready For Testing | 8 | 7 |  | Subhasri | Alpha | None | Alpha | None | 40265 | 2025-01-09 | 2025-01-09 | [7 empty] | Testing will be done by onsite QA
25 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 Stretch | Arvinth | 46539 | Mosaic - POS (Web) - Modify School Export to include new columns (DBS) | Story Being Developed | 5 |  |  | Arvinth
26 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 Stretch | Atchaiah | 46827 | MFOH-Automation | Story Completed | 8 | 8 |  | NA | NA | NA | NA | NA | 40338 | 2025-01-16 | 2025-01-22 | NA | NA | Ying | 2025-01-22 | NA | NA | NA
27 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 Stretch | Ashwin | 46017 | Mosaic - POS (Web) - Add new columns to Logout POS User Search (DBS) | Story Being Developed | 3 |  |  | Ashwin
28 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 Stretch | Alpha | 46675 | Mosaic - POS (Web) - Add an ability to assign POS Menu to multiple POS Numbers | Story Being Developed | 3
29 | FOH Wave | #N/A | #N/A | 4.20 - Sprint 1 Stretch | Ashwin | 46424 | Mosaic - POS (Web) - Add Tracking for Menu Products (Log user who modified it) | Story Being Developed | 2 |  |  | Ashwin
| FOH Wave | #N/A | #N/A

## 4.20 - Sprint 1-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Reason | Comments
1 | 4.20 - Sprint 1 | 24428 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Delete button enables on name already exist popup while adding vending machine | Minor | External | Closed | Existing_Issues | Delete button enables on error popup
2 | 4.20 - Sprint 1 | 24425 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Delete button enables on adding local server while Name already exists popup opens | Minor | External | Closed | Existing_Issues | Delete button enables on error popup
3 | 4.20 - Sprint 1 | 24433 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Name already exists popup is not showing up in POS Login Message screen | Minor | External | Closed | Existing_Issues | Error popup not showing
4 | 4.20 - Sprint 1 | 24424 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Delete button enables on adding student letter while Name already exists popup opens | Minor | External | Closed | Existing_Issues | Delete button enables on error popup
5 | 4.20 - Sprint 1 | 24429 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Same name is allowing for Vending machine during edit | Minor | External | Closed | Existing_Issues | Error popup not showing
6 | 4.20 - Sprint 1 | 24431 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Name already exists popup is not showing up in POS Input Device screen | Minor | External | Closed | Existing_Issues | Error popup not showing
7 | 4.20 - Sprint 1 | 24451 | Ashwin | Defect | 24451 - Mosaic - POS (Web) (4.19) - Lower limit balance and upper limit balance not working in student barcode report | Minor | External | Closed | Existing_Issues | Naming were wrong
8 | 4.20 - Sprint 1 | 24422 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - 'This Name already exists' popup opens twice in Bus/Route Assignments | Minor | External | Closed | Existing_Issues | Error popup not showing
9 | 4.20 - Sprint 1 | 24427 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Auto Include New Schools value is not retaining in School group | Minor | External | Closed | Existing_Issues | Updating school group happens twice
10 | 4.20 - Sprint 1 | 24426 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Add school group Search is not working for the first time | Minor | External | Closed | Existing_Issues | Button click not works on first time
11 | 4.20 - Sprint 1 | 24432 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - Delete button is showing during add in POS Login Message screen | Minor | External | Closed | Existing_Issues | Delete button enables on error popup
12 | 4.20 - Sprint 1 | 24423 | Ashwin | Defect | Mosaic - POS (Web) (4.19) - 'This Name already exists' popup opens twice in POS Custom Lookup | Minor | External | Closed | Existing_Issues | Error popup not showing
13 | 4.20 - Sprint 1 | 24462 | Arvinth | Defect | Mosaic - POS (Web) (4.19) - School not closed report doesn't shows if current day is reopened | Minor | External | Closed | Existing_Issues | Reopened shools not handled for current day
14 | 4.20 - Sprint 1 Stretch | 24487 | Arvinth | Defect | MFOH - Update Sales Demo Data SQL failing on SQL 2008 | Significant | Internal | Closed | Existing_Issues | Function not compatable with SQL 2008
15 | 4.20 - Sprint 1 | 24405 | Subha | Defect | MFOH(4.19) - NC Claim Total Monthly Attendance is using MAX Date instead of Total | Significant | External | Closed | Existing_Issues

## 4.19 - Sprint 5-Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 4.19 - Sprint 5 | Arvinth | 43727 | Mosaic - POS (Web) - Print Machine Information (POS Menu Maintenance) (SYSU) | Closed | 8 | 8 | Arvinth | Atchaiah | Print button enables on error message | Alpha | Change comment | 39916 | 2024-12-02 | 2024-12-02 | Subha | None | Ying | 2024-12-02 | None | None | NA
1.1 | 4.19 - Sprint 5 | Alpha | 43727 | Mosaic - POS (Web) - Print Machine Information (POS Menu Maintenance) (SYSU) | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
2 | 4.19 - Sprint 5 | Alpha | 44687 | Mosaic - POS (Web) - Add date of inactive to Student Maintenance | Closed | 2 | 2 | Alpha | Atchaiah | None | Arvinth | Change in adding the SQL paramer | 39904 | 2024-12-02 | 2024-12-02 | Subha | Add default value in constructor | Ying | 2024-12-02 | None
3 | 4.19 - Sprint 5 | Alpha | 24252 | Mosaic - POS Web - User Change Password Link loses formatting | Closed | 2 | 2 | Alpha | Atchaiah | None | Arvinth | None | 39905 | 2024-12-02 | 2024-12-02 | Subha | None | Ying | 2024-12-02 | None
3.1 | 4.19 - Sprint 5 | Arvinth | 24252 | Mosaic - POS Web - User Change Password Link loses formatting | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
4 | 4.19 - Sprint 5 | Alpha | 45916 | Mosaic - POS (Web) - Add 'Active' Filter to User Assignments Report and User Report | Closed | 3 | 3 | Alpha | Atchaiah | None | Arvinth | None | 39906 | 2024-12-02 | 2024-12-02 | Subha | None | Ying | 2024-12-02 | None
4.1 | 4.19 - Sprint 5 | Arvinth | 45916 | Mosaic - POS (Web) - Add 'Active' Filter to User Assignments Report and User Report | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
5 | 4.19 - Sprint 5 | Atchaiah | 46506 | Mosaic-POS-Automation | Closed | 2 | 2 | NA | NA | NA | NA | NA | 39800 | 2024-11-20 | 2024-12-03 | NA | NA | Ying | 2024-12-03 | NA | NA | NA
7 | 4.19 - Sprint 5 | Alpha | 45214 | Mosaic - FOH - Modify District ID/POS ID Textbox to allow multiple IDs (Transfer Balance popup) | Closed | 3 | 3 | Alpha | Atchaiah | None | Arvinth | None | 39908 | 2024-12-02 | 2024-12-02 | NA | NA | Ying | 2024-12-02 | Merge conflict with revision history
8 | 4.19 - Sprint 5 | Subhasri | 24319 | Mosaic POS (Web) - Serving in the classroom - Duplicate students | Closed | 2 | 2 | Subhasri | Alpha | None | Alpha | None | 39918 | 2024-12-02 | 2024-12-02 | NA |  | Ying | 2024-12-02 | None | NA | NA
8.1 | 4.19 - Sprint 5 | Alpha | 24319 | Mosaic POS (Web) - Serving in the classroom - Duplicate students | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
9 | 4.19 - Sprint 5 | Subhasri | 24321 | Mosaic FOH - New Millford Public Schools - Serving Line Sales Report Totals Section Get Total from Previous School. | Closed | 3 | 3 | Subhasri | Arvinth | None | Arvinth | None
9.1 | 4.19 - Sprint 5 | Alpha | 24321 | Mosaic FOH - New Millford Public Schools - Serving Line Sales Report Totals Section Get Total from Previous School | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
10 | 4.19 - Sprint 5 | Subhasri | 45917 | Mosaic - POS (SL) - Add 'District ID' & 'POS ID' to Previous Transaction Box | Closed | 3 | 3 | Subhasri
11 | 4.19 - Sprint 5 | Arvinth | 46421 | Mosaic - POS (Web) - Add 'Notes' to Eligibility Record Report | Closed | 3 | 3 | Arvinth | Atchaiah | None | Alpha | None | 39947 | 2024-12-04 | 2024-12-04 | NA | NA | Ying | 2024-12-04 | None | None | NA
11.1 | 4.19 - Sprint 5 | Alpha | 46421 | Mosaic - POS (Web) - Add 'Notes' to Eligibility Record Report | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
12 | 4.19 - Sprint 5 | Alpha | 40809 | Mosaic - POS (Web) - Add Field Level Security options to Review Transactions Security Setting | Closed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
13 | 4.19 - Sprint 5 | Alpha | 46605 | Mosaic - FOH 4.19(Regression) - Setup | Closed | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
14 | 4.19 - Sprint 5 | Alpha | 46608 | Mosaic - FOH 4.19(Regression) - End of Day | Closed | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
15 | 4.19 - Sprint 5 | Alpha | 46618 | Mosaic - FOH 4.19 (Regression) - Eligibility (F&R) | Closed | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
16 | 4.19 - Sprint 5 | Arvinth | 46604 | Mosaic - FOH 4.19(Regression) - Utilities | Closed | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
17 | 4.19 - Sprint 5 | Arvinth | 46606 | Mosaic - FOH 4.19(Regression) - Students | Closed | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
18 | 4.19 - Sprint 5 | Arvinth | 46610 | Mosaic - FOH 4.19 (Regression) - Reports - Eligibility (F&R) | Closed | 3 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
6 | 4.19 - Sprint 5 Stretch | Atchaiah | 46654 | Mosaic - POS Automation | Closed | 8 | 8 | NA | NA | NA | NA | NA | 39993 | 2024-12-06 | 2024-12-06 | NA | NA | Ying | 2024-12-06 | NA | NA | NA
19 | 4.19 - Sprint 5 Stretch | Arvinth | 46611 | Mosaic - FOH 4.19 (Regression) - POS(Web) | Closed | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
20 | 4.19 - Sprint 5 Stretch | Atchaiah \ Alpha \ Arvinth | 46607 | Mosaic - FOH 4.19(Regression) - Reports - (Excluding Free/Reduced) | Inprogress | 8 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
21 | 4.19 - Sprint 5 Stretch | Subhasri | 46696 | Mosaic - POS (Web) (CPS) - Dashboard V2 | Inprogress | 13

## 4.19 - Sprint 5-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Reason | Comments
1 | 4.19 - Sprint 5 | 24252 | Alpha | Defect | Mosaic - POS Web - User Change Password Link loses formatting | Minor | External | Closed | Existing_Issues | Design Issue
2 | 4.19 - Sprint 5 | 24319 | Subhasri | Defect | Mosaic POS (Web) - Serving in the classroom - Duplicate students | Minor | External | Closed | Existing_Issues | Duplicate student were listing
3 | 4.19 - Sprint 5 | 24321 | Subhasri | Defect | Mosaic FOH - New Millford Public Schools - Serving Line Sales Report Totals Section Get Total from Previous School. | Minor | Internal | Closed | Development | Count included from previous school if the previous school has no totals
4 | 4.19 - Sprint 5 | 46421 | Arvinth | Bounceback | Mosaic - POS (Web) - Add 'Notes' to Eligibility Record Report | Minor | Internal | Closed | Design | Extra blank page showing in report for certain scenerios

## 4.19 - Sprint 4-Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any2 | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 4.19 - Sprint 4 | Arvinth | 46108 | Mosaic - POS (Web) - Improvements to Scheduler Task (Add Monthly Recurrence) (DBS) | Closed | 8 | 8 | Arvinth | Alpha | None | Alpha | None | 39764 | 2024-11-18 | 2024-11-18 | Subha | None | Steve | 2024-11-18 | None | None | None
2 | 4.19 - Sprint 4 | Alpha | 24210 | Mosaic POS (Web) - Extended Sales - Report is page breaking in the middle of meal reporting | Closed | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Defect Rejected - Working as Expected
3 | 4.19 - Sprint 4 | Alpha/Subha | 24240 | Mosaic POS (Web) - Building Summary Report - Excluding Serving in the Classroom Counts | Closed | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Defect Rejected - Couldn't able to Repro
4 | 4.19 - Sprint 4 | Alpha | 46347 | MFOH - MPLH Report - Adults sales not being included and go out to 2 decimals | Closed | 3 | 3 | Alpha | Atchaiah | None | Arvinth | None | 39760 | 2024-11-18 | 2024-11-18 | Subha | None | Steve | 2024-11-18 | None
4.1 | 4.19 - Sprint 4 | Arvinth | 46347 | MFOH - MPLH Report - Adults sales not being included and go out to 2 decimals | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | 4.19 - Sprint 4 | Subhasri | 46318 | Mosaic - POS (Web) - Add 2 decimal places to Labor Hours (Alachua Meal Count Export) | Closed | 2 | 2 | Subhasri | Atchaiah | NA | Alpha | NA | 39692 | 2024-11-12 | 2024-11-12 | NA | NA | Ying | 2024-11-12 | NA | NA | NA
6 | 4.19 - Sprint 4 | Subhasri | 46104 | Mosaic - POS (Web) - Improvements to Scheduler Task (Modify Day droplist to a Multi- Selector) (DBS) | Closed | 3 | 3 | Subhasri | Alpha | Need to set to today's date when scheduled time is less the current date and time | Alpha | NA | 39711 | 2024-11-13 | 2024-11-13 | NA | NA | Ying | 2024-11-13 | NA | NA | NA
7 | 4.19 - Sprint 4 | Subhasri | 44845 | Mosaic FOH - Show Actual Bank Deposit Amount in Online Payment Detail Report (DBS) | Closed | 5 | 5 | Subhasri | Alpha | NA | Alpha | NA | 39762 | 2024-11-18 | 2024-11-18 |  |  | Steve | 2024-11-18 | NA | NA | NA
4 | 4.19 - Sprint 4 Stretch | Atchaiah | 46506 | Mosaic - POS Automation | Inprogress | 8 |  | NA | NA | NA | NA | NA | 39800 | 2024-11-20 |  | NA | NA | Ying |  |  | NA | NA
8 | 4.19 - Sprint 4 Stretch | Arvinth | 40809 | Mosaic - POS (Web) - Add Field Level Security options to Review Transactions Security Setting | Closed | 3 | 3 | Arvinth | Atchaiah | None | Alpha | None | 39830 | 2024-11-21 | 2024-11-21 | Subha | None | Ying | 2024-11-21 | None | None | NA
9 | 4.19 - Sprint 4 Stretch | Alpha | 43663 | Mosaic - POS (Web) - Add 'Input Method' filter to Eligibility Record Student Listing Report | Closed | 3 | 3 | Alpha | Atchaiah | None | Arvinth | None | 39828 | 2024-11-21 | 2024-11-21 | Subha | None | Ying | 2024-11-21 | None
10 | 4.19 - Sprint 4 Stretch | Subhasri | 24298 | Mosaic FOH - Provo School District - Serving Line Sales Report EOD Error | Closed | 2 | 2 | Subhasri | Arvinth | NA | Arvinth | NA | 39831 | 2024-11-21 | 2024-11-21 |  |  | Ying | 2024-11-21 | NA | NA

## 4.19 - Sprint 4-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | RCA Reason | Comments
1 | 4.19 - Sprint 4 | 24210 | Alpha | Defect | Mosaic POS (Web) - Extended Sales - Report is page breaking in the middle of meal reporting | Minor | External | Closed | Existing_Issues |  | Rejected
2 | 4.19 - Sprint 4 | 24240 | Alpha/Subha | Defect | Mosaic POS (Web) - Building Summary Report - Excluding Serving in the Classroom Counts | Minor | External | Closed | Existing_Issues |  | Rejected
3 | 4.19 - Sprint 4 Stretch | 24298 | Subha | Defect | Mosaic FOH - Provo School District - Serving Line Sales Report EOD Error | Minor | External | Closed | Existing_Issues | Parameter was missing.

## 4.19 - Sprint 3 - Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Status | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 4.19 - Sprint 3 | Alpha | 45755 | Mosaic - POS (Web) - Modifications to Louisiana SFS-8A Report if a school qualifies for CEP | Closed | 5 | 5 | Alpha | Arvinth | None | Arvinth | None | 39583 | 2024-11-04 | 2024-11-04 | Subhasri | None | Ying | 2024-11-04 | None | None | None
2 | 4.19 - Sprint 3 | Atchaiah | 46047 | Mosaic - POS - Automation Code Optimization | Closed | 2 | 2 | NA | NA | NA | NA | NA | 39429 | 2024-10-23 | 2024-10-28 | NA | NA | Ying | 2024-10-28 | Some tests are failed due to data/timeout issues on Ying db |  |  | Automation Story
3 | 4.19 - Sprint 3 | Arvinth | 24047 | Mosaic POS (Web) - Student Import - Import Review Tool - Not using Field Qualifier | Closed | 2 | 1.5 | Arvinth | Alpha | None | Alpha | None | 39586 | 2024-11-04 | 2024-11-04 | Subhasri | None | Ying | 2024-11-04 | None | None | NA
4 | 4.19 - Sprint 3 | Alpha | 45940 | Mosaic - POS (SL) - Add an alert popup when exiting transaction | Closed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing
5 | 4.19 - Sprint 3 | Alpha | 24111 | Mosaic POS (Web) - Terminal Import - POS Number Max Length Bypassed | Closed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing
6 | 4.19 - Sprint 3 | Atchaiah | 43917 | Mosaic - POS (Web) - Exclude Name, Grade and Homeroom (Student Barcode Report) | Closed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing
7 | 4.19 - Sprint 3 | Subhasri | 44296 | Mosaic - POS (Web) (Before EOY 2025) - Add Active to PowerSchool SIS Import | Closed | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing
8 | 4.19 - Sprint 3 | Atchaiah | 24137 | Mosaic POS (Web) - Item Profitability Report - Not including counts from Subsites | Closed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing
9 | 4.19 - Sprint 3 | Arvinth | 24024 | Mosaic POS (Web) - Report - Student Meal report unable to schedule report | Closed | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing
10 | 4.19 - Sprint 3 Stretch | Subhasri | 24123 | Mosaic FOH - Edgewood ISD - Negative 1 in Attendance Factor Counts | Closed | 2 | 2 | Subhasri | NA | NA | NA | NA | 39508 | 2024-10-28 | 2024-10-28 | NA | NA | Ying | 2024-10-28 | NA | NA | NA
10.1 | 4.19 - Sprint 3 Stretch | Alpha | 24123 | Mosaic FOH - Edgewood ISD - Negative 1 in Attendance Factor Counts | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing
11 | 4.19 - Sprint 3 Stretch | Alpha | 46102 | Mosaic - POS (Web) - Add a new report type to Daily Sales Report | Closed | 5 | 5 | Alpha | Atchaiah/Arvinth | None | Arvinth | None | 39634 | 2024-11-07 | 2024-11-07 | Subhasri | None | Ying | 2024-11-07 | None
12 | 4.19 - Sprint 3 Stretch | Arvinth | 46079 | Mosaic - POS (SL) - Highlight Cashiers to scroll in the popup when the student has more than 4 medical alerts | Closed | 2 | 1 | Arvinth | Alpha | None | Alpha | None | 39519 | 2024-10-29 | 2024-10-29 | Subhasri | None | Ying | 2024-10-29 | None | None | NA
13 | 4.19 - Sprint 3 Stretch | Arvinth | 45754 | Mosaic - POS (Web) - Add CEP and ISP% to School Configuration Report and School Export (DBS) | Closed | 5 | 5 | Arvinth | Atchaiah | None | Alpha | None | 39587 | 2024-11-04 | 2024-11-04 | Subhasri | None | Ying | 2024-11-04 | None | None | NA
13.1 | 4.19 - Sprint 3 Stretch | Atchaiah | 45754 | Mosaic - POS (Web) - Add CEP and ISP% to School Configuration Report and School Export (DBS) | Closed |  |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual Testing
14 | 4.19 - Sprint 3 Stretch | Atchaiah | 46310 | Mosaic - POS Automation | Closed | 3 | 3 | NA | NA | NA | NA | NA | 39606 | 2024-11-05 | 2024-11-07 |  |  | Ying | 2024-11-07 | None
15 | 4.19 - Sprint 3 Stretch | Arvinth | 24256 | Weatherford Public Schools, OK - Race and Ethnicity breakdown report including Adults | Closed | 2 | 1.25 | Arvinth | Atchaiah | None | Alpha | None | 39650 | 2024-11-07 | 2024-11-07 | Subhasri | None | Ying | 2024-11-07 | None | None | NA
16 | 4.19 - Sprint 3 Stretch | Subhasri | 46104 | Mosaic - POS (Web) - Improvements to Scheduler Task (Modify Day droplist to a Multi- Selector) (DBS) | Inprogress | 5 | 4.5 | Subhasri
17 | 4.19 - Sprint 3 Stretch | Alpha | 24210 | Mosaic POS (Web) - Extended Sales - Report is page breaking in the middle of meal reporting | Inprogress | 2 | 2
18 | 4.19 - Sprint 3 Stretch | Arvinth | 46108 | Mosaic - POS (Web) - Improvements to Scheduler Task (Add Monthly Recurrence) (DBS) | Inprogress | 8 | 2.5

## 4.19 - Sprint 3 -Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.19 - Sprint 3 | 24047 | Arvinth | Defect | Mosaic POS (Web) - Student Import - Import Review Tool - Not using Field Qualifier | Minor | External | Closed | Existing_Issues
2 | 4.19 - Sprint 3 Stretch | 24123 | Subhasri | Defect | Mosaic FOH - Edgewood ISD - Negative 1 in Attendance Factor Counts | Minor | External | Closed | Existing_Issues

## 4.19 - Sprint 2 - Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Status | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 (Onsite Lead) | Code Review Comments, if any | Reviewer 2 (Client) | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Comments
1 | 4.19 - Sprint 2 | Arvinth | 44996 | Mosaic - FOH - Improvements to Student Listing as of Date Report | 3 | 3 | Closed | Arvinth | Atchai | None | Alpha | Add revision history | 39169 | 2024-10-01 | 2024-10-01 | Subha | None | Ying | 2024-10-01 | None | None | NA
2 | 4.19 - Sprint 2 | Alpha | 44692 | Mosaic FOH - Cat Elig Ext - Add the ability to track Declines (Review Decline/Save button interaction) | 8 | 8 | Closed | Alpha | Arvinth | UI issues on checkboxes check | Arvinth | Removal of the non working codes in old Sqlserver version, and removal of unused code | 39389 | 2024-10-18 | 2024-10-18 | Subha | Revision history and Sql parameter add with value | Ying | 2024-10-18 | None |  | None
3 | 4.19 - Sprint 2 | Arvinth | 46064 | Mosaic - FOH - Add a notification for Potential Duplicates (Planned for 4.19) | 5 | 4 | Closed | Arvinth | Alpha | None | Alpha | None | 39255 | 2024-10-08 | 2024-10-08 | Subha | None | Ying | 2024-10-08 | None | None | None
4 | 4.19 - Sprint 2 | Arvinth | 46082 | Mosaic - FOH - Add date time stamp to Student Export file (DBS) | 2 | 1.5 | Closed | Arvinth | Atchai | None | Alpha | Add revision history | 39290 | 2024-10-10 | 2024-10-10 | Subha | None | Ying | 2024-10-10 | None | None | NA
5 | 4.19 - Sprint 2 | Atchaiah | 46047 | AutomationCodeOptimization (QA Story) | 5 | 5 | Closed | NA | NA | NA | NA | NA | 39429 | 2024-10-23 | 2024-10-28 | NA | NA | Ying | 2024-10-28 | Some tests are failed due to data/timeout issues on Ying db |  |  | Automation Story
6 | 4.19 - Sprint 2 | Arvinth | 46128 | MFOH - Add the One-Year-Advance feature to IsDemo = Yes | 3 | 4 | Closed | Arvinth | Alpha | None | Alpha | None | 39364 | 2024-10-16 | 2024-10-16 | Subha | None | Ying | 2024-10-16 | None | None | None
7 | 4.19 - Sprint 2 | Alpha | 45355 | Mosaic - FOH - Modifications to Sales Overview Report (Add multi selector to school and a grand total page) | 1 | 1 | Closed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
8 | 4.19 - Sprint 2 | Atchaiah | 46082 | Add date time stamp to the Student Export file (DBS) | 1 | 1 | Closed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
9 | 4.19 - Sprint 2 | Atchaiah | 45357 | Add Print option to Categorical Eligibility Extension Results grid | 1 | 1 | Closed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
10 | 4.19 - Sprint 2 | Atchaiah | 44996 | Improvements to Student Listing as of Date Report | 1 | 1 | Closed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
11 | 4.19 - Sprint 2 | Atchaiah | 45674 | Add Sorting to POS Menu Maintenance - Items on menu grid (DBS) | 1 | 1 | Closed | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Manual testing
12 | 4.19 - Sprint 2 | Alpha | 23714 | STLS 2nd meals are reported under column M in CPS Meal Count Export | 2 | 1.5 | Closed | Alpha | Atchaiah | None | Arvinth | None | 39345 | 2024-10-15 | 2024-10-15 | Subha | None | Ying | 2024-10-15 | None | None | NA
13 | 4.19 - Sprint 2 Stretch | Subhasri | 45834 | Mosaic FOH - Mosaic Dashboard 2024 (CPS) | 3 | 3 | Closed | Subhasri | Alpha | Few UI allignment and refresh issues reported | Alpha | NA | 39296 | 2024-10-10 | NA | NA | NA | NA | NA
14 | 4.19 - Sprint 2 Stretch | Subhasri | 24024 | Mosaic POS (Web) - Report - Student Meal report unable to schedule report | 2 | 1.5 | Closed | Subhasri | Atchaiah | NA | Alpha | NA | 39379 | 2024-10-17 | 2024-10-17 | NA | NA | Ying | 2024-10-17 | None | None | NA
15 | 4.19 - Sprint 2 Stretch | Subhasri | 24026 | Mosaic POS (Web) - Serving in Classroom Report - Voided Meals via utilities (MEC and Data Fix) | 3 | 3 | Closed | Subhasri | Alpha | NA | Alpha | NA | 39378 | 2024-10-17 | 2024-10-17 | NA | NA | Ying | 2024-10-17 | None | None | NA
16 | 4.19 - Sprint 2 Stretch | Subhasri | 24187 | Mosaic FOH - Chandler USD 80 - Bulk Entry From Missing Items | 2 | [17 empty] | Not Reproducable
17 | 4.19 - Sprint 2 Stretch | Atchaiah | 46310 | Mosaic - POS Automation | 8 | 5 | Inprogress
18 | 4.19 - Sprint 2 Stretch | Alpha | 44296 | Mosaic - POS (Web) (Before EOY 2025) - Add Active to PowerSchool SIS Import | 2 | 2 | Closed | Alpha | Atchaiah | None | Arvinth | None | 39390 | 2024-10-18 | 2024-10-18 | Subha | None | Ying | 2024-10-18 | None | None | NA
19 | 4.19 - Sprint 2 Stretch | Arvinth | 45940 | Mosaic - POS (SL) - Add an alert popup when exiting transaction | 2 | 1.5 | Closed | Arvinth | Alpha | None | Alpha | None | 39436 | 2024-10-23 | 2024-10-23 | Subha | None | Ying | 2024-10-23 | None | None | NA
20 | 4.19 - Sprint 2 Stretch | Arvinth | 43917 | Mosaic - POS Exclude Name, Grade and Homeroom from Student Barcode Report | 3 | 2.5 | Closed | Arvinth | Alpha | Update SP comments | Alpha | None | 39432 | 2024-10-23 | 2024-10-23 | Subha | None | Ying | 2024-10-23 | None | None | NA
21 | 4.19 - Sprint 2 Stretch | Arvinth | 46079 | Mosaic - POS (SL) - Highlight Cashiers to scroll in the popup when the student has more than 4 medical alerts | 5 |  | Inprogress
22 | 4.19 - Sprint 2 Stretch | Alpha | 24137 | Mosaic POS (Web) - Item Profitability Report - Not including counts from Subsites | 2 | 2 | Closed | Alpha | Atchaiah | None | Arvinth | None | 39435 | 2024-10-23 | 2024-10-23 | Subha | None | Ying | 2024-10-23 | None | None | NA
23 | 4.19 - Sprint 2 Stretch | Alpha | 24037 | Mosaic POS (Web) - Close Day Reports - Renaming Site does not update Close Day Reports | 2 | 2 | Closed | Alpha | Atchaiah | None | Arvinth | None | 39433 | 2024-10-23 | 2024-10-23 | Subha | None | Ying | 2024-10-23 | None | None | NA
24 | 4.19 - Sprint 2 Stretch | Alpha | 23660 | Mosaic - FOH - Issues with Reimbursement Due Report | 5 | 4 |  | Alpha | NA | NA | NA | NA | [10 empty] | On Hold - Due to Multiple issues
25 | 4.19 - Sprint 2 Stretch | Arvinth | 24111 | Mosaic POS (Web) - Terminal Import - POS Number Max Length Bypassed | 1 | 1 | Closed | Arvinth | Alpha | Change the logic | Arvinth | None | 39434 | 2024-10-23 | 2024-10-23 | Subha | None | Ying | 2024-10-23 | None | None | NA

## 4.19 - Sprint 2 -Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.19 - Sprint 2 | 23714 | Alpha | Defect | STLS 2nd meals are reported under column M in CPS Meal Count Export |  | External | Closed | Existing_Issues
2 | 4.19 - Sprint 2 Stretch | 24137 | Alpha | Defect | Mosaic POS (Web) - Item Profitability Report - Not including counts from Subsites |  | External | Closed | Existing_Issues
3 | 4.19 - Sprint 2 Stretch | 24037 | Alpha | Defect | Mosaic POS (Web) - Close Day Reports - Renaming Site does not update Close Day Reports |  | External | Closed | Existing_Issues
4 | 4.19 - Sprint 2 Stretch | 24024 | Subhasri | Defect | Mosaic POS (Web) - Report - Student Meal report unable to schedule report |  | External | Closed | Existing_Issues
5 | 4.19 - Sprint 2 Stretch | 24026 | Subhasri | Defect | Mosaic POS (Web) - Serving in Classroom Report - Voided Meals via utilities (MEC and Data Fix) |  | External | Closed | Existing_Issues
6 | 4.19 - Sprint 2 Stretch | 24111 | Arvinth | Defect | Mosaic POS (Web) - Terminal Import - POS Number Max Length Bypassed |  | External | Closed | Existing_Issues
7 | 4.19 - Sprint 2 Stretch | 23660 | Alpha | Defect | Mosaic - FOH - Issues with Reimbursement Due Report |  | External | Onhold | Existing_Issues
8 | 4.19 - Sprint 2 Stretch | 24187 | Subhasri | Defect | Mosaic FOH - Chandler USD 80 - Bulk Entry From Missing Items |  | External | Not Repro | Existing_Issues

## 4.19 - Sprint 1 - Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Onsite Lead Code Review | Code Review Comments, if any | Client Code Review | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.19 - Sprint 1 | Arvinth | 45702 | Mosaic - FOH 4.18 (Regression) - Eligibility (F&R) | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Regression Testing
2 | 4.19 - Sprint 1 | Arvinth | 40170 | Mosaic - POS (Web) - Add new mail merge (Notification Letters) | 2 | 1 | Arvinth | Atchaiah | None | Alpha | None | 38936 | 2024-09-17 | 2024-09-17 | Subha | None | Ying | 2024-09-17 | None | None | NA | Closed
3 | 4.19 - Sprint 1 | Alpha | 23894 | Mosaic POS (Web) - Debt Management Report - Missing students | 1 | 1 | Alpha | Atchaiah | None | Arvinth | None | 38934 | 2024-09-17 | 2024-09-17 | Subha | None | Ying | 2024-09-17 | None | None | NA | Closed
4 | 4.19 - Sprint 1 Stretch | Atchaiah | 46047 | AutomationCodeOptimization | 5 | [16 empty] | Inprogress
5 | 4.19 - Sprint 1 Stretch | Alpha | 23940 | Mosaic POS (Web) - MEC Correction Date - Shows AT not ET when set to ET | 2 | 1.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Defect rejected - Cannot repro
6 | 4.19 - Sprint 1 Stretch | Subhasri | 45834 | Mosaic FOH - Mosaic Dashboard 2024 (CPS) | [17 empty] | Inprogress | POC - No Estimate due to POC
7 | 4.19 - Sprint 1 Stretch | Alpha | 45357 | Mosaic - FOH - Add Print option to Categorical Eligibility Extension Results grid | 5 | 7 | Alpha | Atchaiah | None | Arvinth | Release version and variable rename | 39095 | 2024-09-26 | 2024-09-26 | Subha | None | Ying | 2024-09-26 | None | None | None | Closed
8 | 4.19 - Sprint 1 Stretch | Arvinth | 45430 | Mosaic - POS (Web) - Remove delete option for Graduate grade | 1 | 0.5 | Arvinth | Atchaiah | None | Alpha | None | 39003 | 2024-09-23 | 2024-09-23 | Subha | None | Ying | 2024-09-23 | None | None | NA | Closed
9 | 4.19 - Sprint 1 Stretch | Arvinth | 45355 | Mosaic - FOH - Modifications to Sales Overview Report (Add multi selector to school and a grand total page) | 5 | 3.5 | Arvinth | Atchaiah | None | Alpha | None | 39004 | 2024-09-23 | 2024-09-23 | Subha | None | Ying | 2024-09-23 | None | None | NA | Closed
10 | 4.19 - Sprint 1 Stretch | Arvinth | 23939 | Mosaic POS (Web) - Eligibility Record Maint - Can Email without email saved to elig record | 1 | 0.5 | Arvinth | Atchaiah | None | Alpha | None | 39068 | 2024-09-25 | 2024-09-25 | Subha | None | Ying | 2024-09-25 | None | None | NA | Closed
11 | 4.19 - Sprint 1 Stretch | Arvinth | 45674 | Mosaic - POS (Web) - Add Sorting to POS Menu Maintenance - Items on menu grid (DBS) | 2 | 1.5 | Arvinth | Atchaiah | Numenric values not sorting | Alpha | Update namings for variables | 39094 | 2024-09-26 | 2024-09-26 | Subha | None | Ying | 2024-09-26 | None | None | None | Closed
12 | 4.19 - Sprint 1 Stretch | Arvinth | 45213 | Mosaic - FOH - Add new fields to Cashier Deposit Report | 2 | 1 | Arvinth | Atchaiah | None | Alpha | None | 39093 | 2024-09-26 | 2024-09-26 | Subha | None | Ying | 2024-09-26 | None | None | None | Closed
13 | 4.19 - Sprint 1 | Arvinth | 42839 | Mosaic - POS (Web) - Add Change Due to Transaction History Report | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Manual testing
14 | 4.19 - Sprint 1 | Atchai / Arvinth | 46019 | Mosaic FOH - 4.18 Regression - Fixes needed | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Manual testing
15 | 4.19 - Sprint 1 | Alpha | 44422 | Mosaic - POS (Web) (Checked in 4.19) - Don't show the password (SFTP Maintenance) | 1 | 0.75 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Manual testing
16 | 4.19 - Sprint 1 | Alpha | 45738 | Mosaic - POS (Web) (Checked in 4.19) - MM/DD/YYYY format on reports Phase 2 | 1 | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Manual testing

## 4.19 - Sprint 1 -Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.18 - Sprint 7 - Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 (Onsite Lead) | Code Review Comments, if any | Reviewer 2 (Client) | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.18 - Sprint 7 | Arvinth | 45728 | Mosaic - POS (Web) (4.18) - Updates to Serving Line Sales Report | 2 | 0 | Arvinth | Alpha | Starting Cash Duplicate issue | Alpha | No comments | 38735 | 2024-09-03 | 2024-09-03 | Subha | No comments | Ying | 2024-09-03 | No comments | No comments | NA | Closed
2 | 4.18 - Sprint 7 Stretch | Atchaiah | 45655 | Mosaic - POS Automation | 1 | 1 | [5 empty] | 38858 | 2024-09-11 | 2024-09-12 |  |  | Ying | 2024-09-12 |  |  |  | Closed
3 | 4.18 - Sprint 7 Stretch | Arvinth | 43940 | Mosaic - POS (Web) - Add School Total page to Serving Line Sales Report | 2 | 0 | Arvinth | Alpha | No comments | Alpha | No comments | 38736 | 2024-09-03 | 2024-09-03 | Subha | No comments | Ying | 2024-09-03 | No comments | No comments | No comments | Closed
4 | 4.18 - Sprint 7 | Alpha | 45698 | Mosaic - FOH 4.18(Regression) - Utilities | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Regression Testing
5 | 4.18 - Sprint 7 | Arvinth | 45699 | Mosaic - FOH 4.18(Regression) - Setup | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Regression Testing
6 | 4.18 - Sprint 7 | Alpha | 45700 | Mosaic - FOH 4.18(Regression) - Students | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Regression Testing
7 | 4.18 - Sprint 7 | Alpha | 45703 | Mosaic - FOH 4.18(Regression) - Reports - (Excluding Free/Reduced) | 8 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Regression Testing
8 | 4.18 - Sprint 7 | Arvinth | 45704 | Mosaic - FOH 4.18(Regression) - End of Day | 5 | 5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Regression Testing
9 | 4.18 - Sprint 7 Stretch | Arvinth | 45701 | Mosaic - FOH 4.18 (Regression) - Reports - Eligibility (F&R) | 3 | 3 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Regression Testing
10 | 4.18 - Sprint 7 Stretch | Arvinth | 45702 | Mosaic - FOH 4.18 (Regression) - Eligibility (F&R) | 5 | 3.5 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Inprogress | Regression Testing
11 | 4.18 - Sprint 7 Stretch | Alpha | 45970 | Mosaic - FOH 4.18 (Regression) - POS(Web) | 2 | 2 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Closed | Regression Testing

## 4.18 - Sprint 7 -Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.18 - Sprint 6 - Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.18 - Sprint 6 | Arvinth | 23785 | Mosaic - POS (Web) - Issue found in Transaction Export | 1 | 0 | Arvinth | Alpha | No comments | Alpha | No comments | 38469 | 2024-08-19 | 2024-08-19 | Subha | No comments | Ying | 2024-08-19 | No comments | No comments | NA | Closed
2 | 4.18 - Sprint 6 | Alpha | 42305 | Mosaic FOH - Aramark Export - Export all Ala Carte as Reimbursement Type = 5 | 2 | 1.5 | Alpha | Arvinth | No comments | Arvinth | No comments | 38624 | 2024-08-23 | 2024-08-23 | Subha | No comments | Ying | 2024-08-23 | No comments | No comments | NA | Closed
3 | 4.18 Sprint 6 | Alpha | 45611 | Mosaic - POS (Web) - Exclude Students from Reports (2nd set of reports) (BOCES) | 2 | 2 | Alpha | Arvinth | No comments | Arvinth | No comments | 38557 | 2024-08-21 | 2024-08-21 | Subha | No comments | Ying | 2024-08-21 | No comments | No comments | NA | Closed
4 | 4.18 - Sprint 6 | Alpha | 23706 | Mosaic POS (Web) - End of Year Execute - PreEOY/PostEOY Student Export does not enquote fields with commas. | 1 | 1 | Alpha | Arvinth | No comments | Arvinth | No comments | 38465 | 2024-08-19 | 2024-08-19 | Subhasri | No comments | Ying | 2024-08-19 | No comments | No Comments |  | Closed
5 | 4.18 - Sprint 6 | Alpha | 44280 | Mosaic - POS (Web) - Add no of serving days to Edit Check Report (Fresno) | 1 | 1 | Alpha | Arvinth | No comments | Arvinth | No comments | 38466 | 2024-08-19 | 2024-08-19 | Subhasri | No comments | Ying | 2024-08-19 | nvarchar to varchar; Revision history description change. | No Comments |  | Closed
6 | 4.18 - Sprint 6 | Alpha | 44790 | Mosaic - POS (Web) - Add CSV to Daily Eligibility Snapshot Report (Fresno) | 1 | 1 | Alpha | Atchaiah | No comments | Arvinth | Use static fields to Column names so that we can avoid SP changes | 38467 | 2024-08-19 | 2024-08-19 | Subhasri | Revision history in one file and one method | Ying | 2024-08-19 | No comments | No Comments |  | Closed
7 | 4.18 - Sprint 6 Stretch | Arvinth | 44422 | Mosaic - POS (Web) - Don't show the password (SFTP Maintenance) | 2 | 1.5 | Arvinth | Alpha | No comments | Alpha | No comments | 38699 | 2024-08-29 | 2024-08-29 | Subha | No comments | Ying | 2024-08-29 | No comments | No comments | NA | Closed
8 | 4.18 - Sprint 6 Stretch | Alpha | 42839 | Mosaic - POS (Web) - Add Change Due to Transaction History Report | 2 | 2 | Alpha | Atchaiah | No comments | Arvinth | No comments | 38703 | 2024-08-29 | 2024-08-29 | Subha | No comments | Ying | 2024-08-29 | Revision histories over methods | No comments | No comments | Closed
9 | 4.18 - Sprint 6 Stretch | Alpha | 45111 | Mosaic - FOH - Add a new custom export field to Student Export (DBS) | 2 | 2 | Alpha | Atchaiah | No comments | Arvinth | No comments | 38705 | 2024-08-29 | 2024-08-29 | Subha | No comments | Ying | 2024-08-29 | No comments | No comments | No comments | Closed
10 | 4.18 - Sprint 6 Stretch | Alpha | 44689 | Mosaic - POS (Web) - Truncate the report total (Reimbursement Due Report) | 1 | 1 | Alpha | Arvinth | No comments | Arvinth | No comments | 38702 | 2024-08-29 | 2024-08-29 | Subha | No comments | Ying | 2024-08-29 | No comments | No comments | No comments | Closed
11 | 4.18 - Sprint 6 Stretch | Arvinth | 45728 | Mosaic - POS (Web) (4.18) - Address defects found in Serving Line Sales Report | 8 | 8 | Arvinth | Alpha | Starting Cash Duplicate issue | Alpha | No comments |  |  |  | Subha | No comments | [5 empty] | Inprogress
12 | 4.18 - Sprint 6 Stretch | Atchaiah | 45655 | Mosaic-POS-Automation | 3 | [16 empty] | Inprogress
13 | 4.18 - Sprint 6 Stretch | Alpha | 23894 | Mosaic POS (Web) - Debt Management Report - Missing students | 3 | [16 empty] | Inprogress
14 | 4.18 - Sprint 6 Stretch | Arvinth | 43940 | Mosaic - POS (Web) - Add School Total page to Serving Line Sales Report | 3 | 3 | [15 empty] | Inprogress
15 | 4.18 - Sprint 6 Stretch | Arvinth | 40170 | Mosaic - POS (Web) - Add new mail merge (Notification Letters) | 3 | [16 empty] | Inprogress
16 | 4.18 Sprint 6 | Subhasri | 42305 | Mosaic FOH - Aramark Export - Export all Ala Carte as Reimbursement Type = 5 | 1 | 1 | [15 empty] | Closed | Worked QA for this story
17 | 4.18 - Sprint 6 Stretch | Subhasri | 45738 | Mosaic - POS (Web) (Checked in 4.19) - MM/DD/YYYY format on reports Phase 2 | 2 | 1 | Subhasri | Atchaiah | No comments | Alpha | No comments | 38704 | 2024-08-29 | 2024-08-29 |  |  | Ying | 2024-08-29 | No comments |  |  | Closed
18 | 4.18 - Sprint 6 | Subhasri | 43483 | Mosaic - POS (Web) (Checked in 4.19) - MM/DD/YYYY format on reports Phase 1 | 1 | 1 | Subhasri | Arvinth | No comments | Arvinth | No comments | 38518 | 2024-08-20 | 2024-08-20 |  |  | Ying | 2024-08-20 | No comments |  |  | Closed
19 | 4.18 - Sprint 6 Stretch | Subhasri | 45759 | Mosaic - POS (Web) - Analysis on CPS Dashboard | 2 | 2 | [15 empty] | Closed | Meetings and analysis story

## 4.18 - Sprint 6 -Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.18 - Sprint 5 - Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.18 Sprint 5 | Subhasri | 23716 | Mosaic POS (Web) - Report filters are not aligned. | 3 | 2.5 | Subhasri | Alpha | Few places has same UI issue other than Reports | Alpha | No comments | 38169 | 2024-08-02 | 2024-08-02 |  |  | Ying | 2024-08-02 | No comments |  |  | Closed
2 | 4.18 Sprint 5 Stretch | Alpha | 23706 | Mosaic POS (Web) - End of Year Execute - PreEOY/PostEOY Student Export does not enquote fields with commas. | 1 | 1 | Alpha | Arvinth | No comments | Arvinth | No comments | 38465 | 2024-08-19 | 2024-08-19 | Subhasri | No comments | Ying | 2024-08-19 | No comments | No Comments |  | Closed
3 | 4.18 Sprint 5 Stretch | Alpha | 44280 | Mosaic - POS (Web) - Add no of serving days to Edit Check Report (Fresno) | 3 | 2 | Alpha | Arvinth | No comments | Arvinth | No comments | 38466 | 2024-08-19 | 2024-08-19 | Subhasri | No comments | Ying | 2024-08-19 | nvarchar to varchar; Revision history description change. | No Comments |  | Closed
4 | 4.18 Sprint 5 Stretch | Atchaiah | 45486 | Mosaic-POS-Automation | 2 | 2 | [5 empty] | 38202 | 2024-08-05 | 2024-08-07 |  |  | Ying | 2024-08-07 | One test failed due to data issue and fixed it |  |  | Closed
5 | 4.18 Sprint 5 Stretch | Alpha | 44790 | Mosaic - POS (Web) - Add CSV to Daily Eligibility Snapshot Report (Fresno) | 5 | 4 | Alpha | Atchaiah | No comments | Arvinth | Use static fields to Column names so that we can avoid SP changes | 38467 | 2024-08-19 | 2024-08-19 | Subhasri | Revision history in one file and one method | Ying | 2024-08-19 | No comments | No Comments |  | Closed
6 | 4.18 Sprint 5 Stretch | Alpha | 23801 | Mosaic FOH - Spokane Public Schools - 500 Error when Extending DC Eligibility Tool | 1 | 0.5 | Alpha | NA | NA | Arvinth | Move the address as a last field | 38337 | 2024-08-12 | 2024-08-12 | Subhasri | No comments | Ying | 2024-08-12 | Show the addess as it is with Comma | No Comments |  | Closed
7 | 4.18 Sprint 5 Stretch | Arvinth | 43940 | Mosaic - POS (Web) - Add School Total page to Serving Line Sales Report | 8 | [16 empty] | Inprogress
8 | 4.18 Sprint 5 Stretch | Subhasri | 43716 | Mosaic - POS (Web) - Add POS Custom Lookup to SIC Search | 3 | 2.5 | Subhasri | Alpha | Serving In the classroom sales report is not showing up the data sometimes Reset doesn't clears up ne filter | Alpha | No comments | [10 empty] | Inprogress
9 | 4.18 Sprint 5 Stretch | Subhasri | 45496 | Mosaic - POS (Web) - Add an indicator to Visual Report while exporting csv (CPS) | 1 | 0.8 | Subhasri | Arvinth | SetProgress messages set to false in error block also | Arvinth | No comments | [10 empty] | Inprogress
10 | 4.18 Sprint 5 Stretch | Atchaiah | 45655 | Mosaic - POS Automation | 5 | [16 empty] | Inprogress
11 | 4.18 Sprint 5 Stretch | Arvinth | 23785 | Mosaic - POS (Web) - Issue found in Transaction Export | 1 | 0.75 | Arvinth | NA | NA | Alpha | No comments | [10 empty] | Inprogress
12 | 4.18 Sprint 5 Stretch | Alpha | 45611 | Mosaic - POS (Web) - Exclude Students from Reports (2nd set of reports) (BOCES) | 5 | 3 | [15 empty] | Inprogress

## 4.18 - Sprint 5 -Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.18 - Sprint 4- Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.18 Sprint 4 Stretch | Subhasri | 43059 | Mosaic FOH - Enhancement - Boyd County Public Schools, KY - Requesting the KY D3 report add Sub-Serving periods to Totals | 3 | 2.5 | Subhasri | Alpha | The count is not reflecting when the sub serving period has different Serving period program. | Alpha | NA | 37978 | 2024-07-22 | 2024-07-22 |  |  | Ying | 2024-07-22 | No Comments | No Comments | No Comments | Closed
2 | 4.18 Sprint 4 | Arvinth | 44793 | Mosaic - POS (Web) - Include offsite sales in Grade Percentile Report | 1 | 0 | Arvinth | Alpha | Empty row showing in Served report on offsite transaction | Alpha | NA | 37971 | 2024-07-22 | 2024-07-22 | Subha | No Comments | Ying | 2024-07-22 | No Comments | No Comments | No Comments | Closed
3 | 4.18 Sprint 4 Stretch | Alpha | 43919 | Mosaic - POS (Web) - Add 4 more fields to Transaction Export (Essex Westford) | 3 | 3 | Alpha | Atchaiah | No comments | Arvinth | Remove the unwanted else condition | 37985 | 2024-07-23 | 2024-07-23 | Subha | No Comments | Ying | 2024-07-23 | No Comments | No Comments | No Comments | Closed
4 | 4.18 Sprint 4 Stretch | Alpha | 43898 | Mosaic - POS (Web) - Exclude Students from Reports(BOCES) | 8 | 8 | Alpha | Arvinth | No comments | Arvinth | Add revision history for methods, remove commented code | 38124 | 2024-07-31 | 2024-07-31 | Subha | File name change, remove commented code | Ying | 2024-07-31 | No Comments | No Comments | No Comments | Closed
5 | 4.18 Sprint 4 Stretch | Arvinth | 44029 | Mosaic - POS (Web) - Add Serving Period Program to SPEC Report (NY, Fresno) | 8 | 10 | Arvinth | Alpha | No comments | Alpha | Remove commented line | 38151 | 2024-08-01 | 2024-08-01 | Subha | No Comments | Ying | 2024-08-01 |  | No Comments | No Comments | Closed
6 | 4.18 Sprint 4 Stretch | Subhasri | 44293 | Mosaic - POS (Web) - Add Serving Period Program to Edit Check Worksheet Report (Fresno) | 8 | 7 | Subhasri | Alpha | The pop up is coming in the following scenario and hence the display report button is disabled, Choose one SPP, it is clearing all the SPs. Then choose one/more SP and then try clearing the selected SP. It should allow blank and run for all SP, then the pop up is not needed. | Alpha | No comments | 38115 | 2024-07-30 | 2024-07-30 |  |  | Ying | 2024-07-30 | No Comments | No Comments | No Comments | Closed
7 | 4.18 Sprint 4 Stretch | Atchaiah | 45486 | Mosaic-POS-Automation | 8 | [16 empty] | Inprogress
8 | 4.18 Sprint 4 Stretch | Subhasri | 45508 | Mosaic - POS (Web) (MSBA) - Exception Handling (CPS) | 3 | 2 | Arvinth/Subhasri | Arvinth | No comments | Arvinth | No comments | 38150 | 2024-08-01 | 2024-08-01 |  |  | Ying | 2024-08-01 | No Comments | No Comments | No Comments | Closed
9 | 4.18 Sprint 4 Stretch | Alpha | 45510 | Mosaic - POS (Web) (MSBA) - Add a scheduler task step "MSBA Communication" | 3 | 2 | Alpha/Subhasri | Alpha | No comments | Subhasri | No comments | 38158 | 2024-08-01 | 2024-08-01 | Subha | No Comments | Ying | 2024-08-01 | No Comments | No Comments | No Comments | Closed

## 4.18 - Sprint 4-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.18 - Sprint 3 - Status (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.18 - Sprint 3 | Arvinth | 44967 | Mosaic - POS (Web) - Add a new Import Field (Import Setting Maintenance) - 'Exclude from Pre-Import Deactivate' | 2 | 1 | Arvinth | Atchai | None | Alpha | None | 37570 | 2024-06-24 | 2024-06-24 | None | None | Ying | 2024-06-24 | None | None | N/A | Closed
2 | 4.18 - Sprint 3 | Alpha | 23505 | Lakeland Central School - POS Roster Report Extended Missing Homeroom Headers | 1 | 1 | Alpha | Atchai | None | Arvinth | None | 37608 | 2024-06-26 | 2024-06-26 | None | None | Ying | 2024-06-26 | None | None | N/A | Closed
3 | 4.18 - Sprint 3 | Alpha | 44292 | Default Temporary Reason to None (Notification letters) | 2 | 1.5 | Alpha | Atchaiah | None | Arvinth | None | 37637 | 2024-06-28 | 2024-06-28 | None | None | Ying | 2024-06-28 | None | None | N/A | Closed
4 | 4.18 - Sprint 3 | Alpha | 43713 | Add new export fields to Student Export (Pre-Import & Duplicate Review) | 3 | 2.5 | Alpha | Atchaiah, Arvinth | None | Arvinth | Export fields changes needs to be done in the Mappings and filters as well. Sow tooltip based on the length. | 37674 | 2024-07-02 | 2024-07-02 | None | None | Ying | 2024-07-02 | None | None | N/A | Closed
5 | 4.18 - Sprint 3 | Arvinth | 43921 | Mosaic - POS (Web) (DBS) - Add a new mail merge (Notification letter setup) - Student Name List - Horizontal | 3 | 2 | Arvinth | Atchaiah, Alpha | None | Alpha | None | 37630 | 2024-06-27 | 2024-06-27 | None | None | Ying | 2024-06-27 | None | None | N/A | Closed
6 | 4.18 - Sprint 3 | Arvinth | 44978 | Mosaic - POS (Web) - Data Lake Improvements | 3 | 2 | Arvinth | Alpha | None | Alpha | Remove unused variables, remove comments | 37730 | 2024-07-08 | 2024-07-08 | None | None | Ying | 2024-07-08 | None | None | None | Closed
7 | 4.18 - Sprint 3 Stretch | Alpha | 44688 | Add 'Active' column to Student Listing Report | 3 | 3 | Alpha | Atchaiah | None | Arvinth | None | 37676 | 2024-07-02 | 2024-07-02 | None | None | Ying | 2024-07-02 | None | None | N/A | Closed
8 | 4.18 - Sprint 3 Stretch | Alpha | 23553 | Date in Transaction history report is not showing 'Actual Date' | 3 | 2.5 | Alpha | Atchaiah | None | Arvinth | None | 37690 | 2024-07-03 | 2024-07-03 | None | None | Steve | 2024-07-03 | None | None | N/A | Closed
9 | 4.18 - Sprint 3 Stretch | Alpha | 41581 | A new report to identify students leaving school who have siblings to transfer money | 3 | 3.5 | Alpha | Atchaiah | None | Arvinth | None | 37717 | 2024-07-08 | 2024-07-08 | None | None | Ying | 2024-07-08 | None | None | N/A | Closed
10 | 4.18 - Sprint 3 Stretch | Alpha | 42114 | ​Tamalpais Union High School District, CA - Student Account Summary Report Enhancement | 5 | 4 | Alpha | Atchaiah | None | Arvinth | None | 37808 | 2024-07-11 | 2024-07-11 | None | None | Ying | 2024-07-11 | None | None | N/A | Closed
11 | 4.18 - Sprint 3 Stretch | Arvinth | 44109 | Mosaic - POS (Web) (SYSU) - Attach uploaded files to DC Import Result Records | 5 | 6.5 | Arvinth | Atchaiah | File download failed | Alpha | Add Acces Role to DownloadFile method | 37694 | 2024-07-03 | 2024-07-03 | None | None | Steve | 2024-07-03 | None | None | None | Closed
12 | 4.18 - Sprint 3 Stretch | Alpha | 23590 | Mosaic FoH - Reports - Other - User Report - Not reporting on some users in the User Search results. | 3 | 2.5 | Alpha | Atchaiah | None | Arvinth | None | 37828 | 2024-07-12 | 2024-07-12 | None | None | Ying | 2024-07-12 | None | None | None | Closed
13 | 4.18 - Sprint 3 | Atchaiah | 45165 | Mosaic - POS Automation | 8 | 8 | N/A | N/A | N/A | N/A | N/A | 37851 | 2024-07-15 | 2024-07-15 | N/A | N/A | Ying | 2024-07-15 | One test failed after running again got passed without any changes | N/A | N/A | Closed

## 4.18 - Sprint 3-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.18 - Sprint 3 Stretch | 41581 | Alpha | Bounceback | Woking on Student listing report affected close year report | Significant | Internal | Closed | Development | Made some code changes on close year report to resolve the issue.

## 4.18 - Sprint 2-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.18 - Sprint 2 | Arvinth | 42058 | Mosaic FOH (CPS ONLY) - Ability to Soft Delete or Hide Schools | 3 | 1 | Arvinth | Alpha | None | Alpha | None | 37422 | 2024-06-11 | 2024-06-11 | None | None | Ying | 2024-06-11 | Remove SiteDeleted = 0 in a query | None | None | Closed
2 | 4.18 - Sprint 2 | Alpha | 45002 | Mosaic - FOH - (CPS only) - MSBA Integration (Add a UI for MSB communication) | 3 | 2.5 | Alpha | Alpha | None | Arvinth | Build error due to property name change. | 37487 | 2024-06-14 | 2024-06-14 | None | None | Ying | 2024-06-14 | None | None | None | Closed
3 | 4.18 - Sprint 2 | Alpha | 44844 | Mosaic FOH (CPS only) - MSBA Integration | 5 | 5 | Alpha | Arvinth | None | Arvinth | "Using" keyword, removing unwanted catch/code, revision history | 37540 | 2024-06-20 | 2024-06-20 | None | None | Ying, Steve | 2024-06-20 | Steve: Index needs to be added to new table. | None | None | Closed
4 | 4.18 Sprint 2 | Atchaiah | 44889 | Mosaic - POS Automation | 2 | 2 | N/A | N/A | N/A | N/A | N/A | 37419 | 2024-06-11 | 2024-06-11 | N/A | N/A | Ying | 2024-06-11 | None | N/A | N/A | Closed
5 | 4.18 - Sprint 2 Stretch | Arvinth | 43901 | Mosaic - POS (Web) - Add additional columns to Disclosure export | 3 | 2.5 | Arvinth | Alpha | None | Alpha | None | 37447 | 2024-06-14 | 2024-06-14 | None | None | Ying | 2024-06-14 | None | None | None | Closed
6 | 4.18 - Sprint 2 Stretch | Atchaiah | 45030 | Mosaic - POS Automation | 5 | 5 | N/A | N/A | N/A | N/A | N/A | PR#37534 | 2024-06-20 | 2024-06-20 |  |  | Ying | 2024-06-20 |  | N/A | N/A | Closed

## 4.18 - Sprint 2-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.18 Sprint 2 | 42058 | Arvinth | None | Schools still displayed for support user after soft delete | Minor | Internal | Closed | Development | Query need to updated for Support user, so that it won't display

## 4.18 - Sprint 1-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.18 Sprint 1 | Alpha | 43609 | Mosaic - POS (Web) - Scheduling reports to be emailed as XLS is sending with an extension of PDF | 3 | 2.5 | Alpha | Arvinth | None | Arvinth | None | 37149 | 2024-05-27 | 2024-05-27 | Subha | None | Steve | 2024-05-28 | None | None | N/A | Closed
2 | 4.18 Sprint 1 | Alpha | 44850 | Mosaic FOH - (Sioux Falls) Eligibility History Export modifications (Synergy Export Type) | 3 | 2.5 | Alpha | Arvinth | None | Arvinth | None | 37184 | 2024-05-29 | 2024-05-29 | Subha | None | Steve | 2024-05-29 | None | None | None | Closed
3 | 4.18 Sprint 1 | Alpha | 22831 | Mosaic POS (Web) - Utilities - Exports - Chartwells Export - Adult Alacarte Number of items being exported to Lunch Prepaid Alacarte | 3 | 2.5 | Alpha | Arvinth | None | Arvinth | None | 37190 | 2024-05-29 | 2024-05-29 | Subha | None | Steve | 2024-05-29 | None | None | N/A | Closed
4 | 4.18 Sprint 1 | Alpha | 21887 | Mosaic POS - Student Export - Changing a field Name will not change the Header Name | 3 | 3 | Alpha | Arvinth | None | Arvinth | None | 37256 | 2024-06-03 | 2024-06-03 | Subha | None | Ying | 2024-06-03 | None | None | N/A | Closed
5 | 4.18 Sprint 1 | Subha | 44205 | Mosaic - POS (Web) (CPS) - Show summed up data for Master Sites (Visual Report) | 5 | 5 | Subha | Arvinth | Want to update day wise total | Arvinth | None | 37257 | 2024-06-03 | 2024-06-03 | N/A | N/A | Ying | 2024-06-03 | Update Version Number | None | None | Closed
6 | 4.18 Sprint 1 | Arvinth | 43874 | Mosaic - POS (Web) - Save PDF as an attachment on Eligibility Record | 3 | 3 | Arvinth | Alpha | None | Alpha | None | 37187 | 2024-06-29 | 2024-05-29 | Subha | None | Steve | 2024-05-29 | None | None | None | Closed
7 | 4.18 Sprint 1 | Arvinth | 42058 | Mosaic FOH (CPS ONLY) - Ability to Soft Delete or Hide Schools | 8 | 8 | Arvinth | Alpha | None | Alpha | None |  |  |  | None | None |  |  |  | None | None | Inprogress | As POV need to done with onsite team carryforwading to next sprint
8 | 4.18 Sprint 1 | Atchaiah | 44537 | Mosaic - POS Automation | 1 | 1 |  | N/A | N/A | N/A | N/A | 37208 | 2024-05-30 | 2024-05-30 | N/A | N/A | Ying | 2024-05-30 | None | N/A | N/A
9 | 4.18 Sprint 1 | Atchaiah | 44792 | Mosaic - POS Automation | 1 | 1 |  | N/A | N/A | N/A | N/A | 37215 | 2024-05-30 | 2024-05-30 | N/A | N/A | Ying | 2024-05-30 | None | N/A | N/A | Closed
10 | 4.18 Sprint 1 | Alpha | 44941 | Mosaic - POS (Web) (CPS only) - MSBA Integration (Mapping Store to a Site in School Maintenance) | 2 | 2 | Alpha | Arvinth | None | Arvinth | None | 37255 | 2024-06-03 | 2024-06-03 | None | None | Ying | 2024-06-03 | Merge conflicts with other PR |  |  | Closed

## 4.18 - Sprint 1-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.18 Sprint 1 | 43874 | Arvinth | Bounceback | Image path can't be accessed in the hosted environment. | Significant | Internal | Closed | Environment_Related | The image was picked up in local and it doesn't works in hosted environment. As we don't have access to octopus server path detials we couldn't figure out the issue on our own. So with the help of onsite team we found the actual issue and fixed it. The fix is to change the image property, as the relative path changes totally when it is deployed.

## 4.17 - Sprint 4-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.17 Sprint 4 | Alpha | 43509 | Mosaic - POS (SL) - Changes to Serving Period Totals (Show Menu Product wise Sold Quantities) | 2 | 0.5 | Alpha | Arvinth | Bold issue for second page when the number of Alacarte items are less | Arvinth | None | 36906 | 2024-05-13 | 2024-05-13 | Subha | Reference update | Steve | 2024-05-13 | None | None | N/A | Closed
2 | 4.17 Sprint 4 | Subha | 43847 | Mosaic - POS (Web) - Student Import Review Process (Develop functionality) | 3 | 1 | Subha | Arvinth | Duplicate Rows | Arvinth | Code Cleanup | 36888 | 2024-05-10 | 2024-05-13 | N/A | N/A | Steve | 2024-05-13 | None | None | None | Closed
3 | 4.17 Sprint 4 | Arvinth | 42908 | Mosaic - POS (Web) (4.17) - Add 'Paid' Student Counts to Oklahoma Low Income Report | 2 | 1.5 | Arvinth | Alpha | None | Alpha | None | 36886 | 2024-05-10 | 2024-05-10 | Subha | None | Steve | 2024-05-10 | None | None | N/A | Closed
4 | 4.17 Sprint 4 | Subha | 23358 | Mosaic - POS (Web) (4.17) - Colorado and Tennessee Claim Export enrollment numbers are lower than they should be | 1 | 0.5 | Subha | Arvinth | None | Arvinth | None | 36887 | 2024-05-10 | 2024-05-10 | N/A | N/A | Steve | 2024-05-10 | None | None | N/A | Closed
5 | 4.17 Sprint 4 Stretch | Atchaiah | 44792 | Mosaic - POS Automation | 3 | 3 | Atchaiah | [14 empty] | Open | Kept on hold due to Ying on PTO
6 | 4.17 Sprint 4 Stretch | Arvinth | 42844 | Mosaic - POS (Web) - Add 'Number of Serving Days' to Serving Line Sales Report | 2 | 2 | Arvinth | Alpha | None | Alpha | None | 37115 | 2024-05-23 | 2024-05-23 | Subha | None | Steve | 2024-05-23 | None | None | N/A | Closed
7 | 4.17 Sprint 4 Stretch | Alpha | 44740 | Mosaic POS (Web) (May be 4.17) - Enable re-opening a day after a bulk entry transaction is voided | 3 | 3 | Alpha | Arvinth | None | Arvinth | Removed the condition from JOIN and added on the WHERE condition | 36935 | 2024-05-14 | 2024-05-15 | Subha | None | Steve | 2024-05-15 | AC change for Current close day | None | N/A | Closed

## 4.17 - Sprint 4-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.17 - Sprint 3-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.17 Sprint 3 | Arvinth | 44516 | Mosaic - POS (Web) - Auto Populate Bank Bag to Daily Sales By Serving Line Report | 1 | 0.5 | Arvinth | Atchai | None | Alpha | None | 36676 | 2024-04-26 | 2024-04-26 | Subha | None | Ying | 2024-04-26 | None | None | N/A | Closed
2 | 4.17 Sprint 3 | Arvinth | 44376 | Mosaic - POS - Update IEGs, EIG and NJEIE (2024-25) | 2 | 1.5 | Arvinth | Alpha | None | Alpha | None | 36700 | 2024-04-29 | 2024-04-29 | Subha | Change Select to set in query | Ying | 2024-04-29 | None | None | N/A | Closed
3 | 4.17 Sprint 3 | Arvinth | 43664 | Mosaic - POS (Web) - Pass Name Value for Report Parameters (Scheduled reports) | 5 | 4 | Arvinth | Atchai | None | Alpha | None | 36780 | 2024-05-03 | 2024-05-03 | Subha | None | Ying | 2024-05-03 | None | None | N/A | Closed
4 | 4.17 Sprint 3 | Alpha | 43509 | Mosaic - POS (SL) - Changes to Serving Period Totals (Show Menu Product wise Sold Quantities) | 8 | 8 | Alpha | Arvinth | [13 empty] | Open | Onsite team was on PTO, so no one there to approve the PR. Carryforwading to next sprint as per Gary's suggestion.
5 | 4.17 Sprint 3 | Subha | 43847 | Mosaic - POS (Web) - Student Import Review Process (Develop functionality) | 13 | 13 | Subha | Arvinth | Duplicate Rows | Arvinth | Code Cleanup | [8 empty] | None |  | Open | Onsite team was on PTO, so no one there to approve the PR. Carryforwading to next sprint as per Gary's suggestion.
6 | 4.17 Sprint 3 Stretch | Alpha | 44287 | Mosaic POS(Web) - Categorical Eligibility Extension Results Detail Report - Add Primary DC First and Last Names | 1 | 1 | Alpha | Atchai | None | Arvinth | Change Create keyword to Alter in SP | 36701 | 2024-04-29 | 2024-04-29 | Subha | None | Ying | 2024-04-29 | None | None | N/A | Closed
7 | 4.17 Sprint 3 Stretch | Subha | 23284 | Mosaic - POS (Web) (4.17) - No Transactions found message after transactions are successfully voided (Void All Transactions) | 1 | 0.75 | Subha | Arvinth | None | Arvinth | None | 36681 | 2024-04-29 | 2024-04-29 | N/A | N/A | Ying | 2024-04-29 | None | None | N/A | Closed
8 | 4.17 Sprint 3 Stretch | Atchaiah | 44537 | Mosaic - POS Automation | 8 | 8 | Atchaiah |  | None |  | None |  |  |  | N/A | None |  |  | None | None | None | Open | Kept on hold, Due to Ying on PTO

## 4.17 - Sprint 3-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.17 - Sprint 2-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.17 Sprint 2 | Atchaiah | 43915 | Mosaic - POS (Web) - Exclude e-hps users from User Report | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual Testing
2 | 4.17 Sprint 2 | Atchaiah | 23132 | Mosaic FOH - Eligibility - Eligibility History Export (Aeries) timeout | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual Testing
3 | 4.17 Sprint 2 | Atchaiah | 23180 | Mosaic - POS(Web) - Inactivate Eligibility Records - String Truncate Error | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual Testing
4 | 4.17 Sprint 2 | Atchaiah | 43650 | Mosaic - POS (Web) (SYSU) - Student Grade Search UI Modification (Add Hyperlink to Counts) | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual Testing
5 | 4.17 Sprint 2 | Atchaiah | 44115 | Berkeley County School District - Mosaic FOH - Reports - Sales - Sales Overview - report Timeout | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual Testing
6 | 4.17 Sprint 2 | Atchaiah | 44168 | Berkeley County School District - Long reporting wait times | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual Testing
7 | 4.17 Sprint 2 | Arvinth | 43915 | Mosaic - POS (Web) - Exclude e-hps users from User Report | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual Testing
8 | 4.17 Sprint 2 | Arvinth | 44153 | Mosaic - POS (Web) - Add 'Preferred Name' field to Student Import and Export and Custom Report | 3 | 2.5 | Arvinth | Alpha | Include Preferred name in constructor | Alpha | None | 36477 | 2024-04-17 | 2024-04-17 | Subha | None | Ying | 2024-04-17 | None | None | None | Closed
9 | 4.17 Sprint 2 | Alpha | 23109 | Mosaic - POS (Web) - Schools That Did Not Close Report' showing incorrect data | 3 | 2.5 | Alpha | Arvinth | None | Arvinth | None | 36500 | 2024-04-18 | 2024-04-18 | Subha | None | Ying | 2024-04-17 | None | None | N/A | Closed
10 | 4.17 Sprint 2 | Alpha | 23167 | Mosaic POS (Web) - Reports - Daily Eligibility Snapshot - Filter counts vs Report counts | 5 | 5.5 | Alpha | Arvinth | Temporary Date check with start date | Arvinth | None | 36543 | 2024-04-19 | 2024-04-19 | Subha | None | Ying | 2024-04-19 | Remodified the Eligibility record Count logic in the SP | None | N/A | Closed
11 | 4.17 Sprint 2 | Subhashri | 43846 | Mosaic - POS (Web) - Student Import Review Process (UI) | 3 | 3 | Subhashri | Arvinth | if fields are less than 11 then display additional fields with empty rows. Also check for duplicates in header display | Arvinth | None | 36575 | 2024-04-22 | 2024-04-22 | N/A | N/A | Ying | 2024-04-22 | None | None | N/A | Closed
12 | 4.17 Sprint 2 Stretch | Arvinth | 44049 | Mosaic - POS (Web) (SYSU) - Add an ability to delete all student status translations (HSS Users only) | 3 | 2.5 | Arvinth | Alpha | None | Alpha | None | 36567 | 2024-04-22 | 2024-04-22 | Subha | None | Ying | 2024-04-22 | None | None | N/A | Closed
13 | 4.17 Sprint 2 Stretch | Atchaiah | 44461 | Mosaic - POS Automation | 8 | 8 | Atchaiah | N/A | N/A | N/A | N/A | 36654 | 2024-04-25 | 2024-04-25 |  |  | Ying | 2024-04-25 | None | N/A | N/A | Closed
14 | 4.17 Sprint 2 Stretch | Alpha | 23089 | Mosaic - POS (Web) - Serving Line Sales Report errored | 2 | 1.5 | Alpha | Arvinth | None | Arvinth | For adding if condition to Drop table | 36590 | 2024-04-23 | 2024-04-23 | Subha | None | Ying | 2024-04-23 | Comment description change | None | N/A | Closed
15 | 4.17 Sprint 2 Stretch | Arvinth | 44099 | Mosaic - POS (Web) (SYSU) - Track District ID Changes | 5 | 4 | Arvinth | Alpha | None | Alpha | None | 36619 | 2024-04-24 | 2024-04-24 | Subha | None | Ying | 2024-04-24 | None | None | N/A | Closed

## 4.17 - Sprint 2-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.17 - Sprint 1-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.17 Sprint 1 | Subha | 44222 | Mosaic POS Web - 4.16 Regression Wrap Up | 8 | 8 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Scope of this Story is for Regression Defect testing.
2 | 4.17 Sprint 1 Stretch | Alpha | 43649 | Mosaic - POS (Web) (SYSU) - Student Grade Search UI Modification | 5 | 4 | Alpha | Arvinth | None | Arvinth | Adjust the column width of the grid | 36326 | 2024-04-08 | 2024-04-08 | Subha | None | Ying | 2024-04-08 | None | None | None | Closed
3 | 4.17 Sprint 1 Stretch | Alpha | 43650 | Mosaic - POS (Web) (SYSU) - Student Grade Search UI Modification (Add Hyperlink to Counts) | 5 | 5 | Alpha | Arvinth | Report header should show the school name | Arvinth | None | 36396 | 2024-04-11 | 2024-04-11 | Subha | None | Ying | 2024-04-11 | None | None | None | Closed
4 | 4.17 Sprint 1 Stretch | Atchaiah | 44279 | Mosaic-POS Automation (Code Cleanup) | 5 | 5 | N/A | N/A | N/A |  |  | 36352 | 2024-04-09 | 2024-04-09 | Subha | None | Ying | 2024-04-09 | None | N/A | N/A | Closed
5 | 4.17 Sprint 1 Stretch | Arvinth | 43502 | Mosaic - POS (Web) - Item Sales Summary By Grade Report | 8 | 8 | Arvinth | Alpha | Remove start date and end date from report parameters | Alpha | None | 36395 | 2024-04-11 | 2024-04-12 | Subha | Add version History | Ying | 2024-04-11 | Add code for NOLOCK in SP | None | None | Closed
6 | 4.17 Sprint 1 Stretch | Arvinth | 23203 | Mosaic - POS(Web) - Running Close Day - POSTransactionEndOfDayBAMProductStatusCount Error | 1 | 0.5 | Arvinth | Alpha | None | Alpha | None | 36398 | 2024-04-11 | 2024-04-11 | Subha | None | Ying | 2024-04-11 | None | None | None | Closed
7 | 4.17 Sprint 1 Stretch | Atchaiah | 23001 | Mosaic POS (Web) - Utilities - Student Balance Import Undo - Display issues with Undo List | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual testing
8 | 4.17 Sprint 1 Stretch | Atchaiah | 22995 | Mosaic that is Bulk Entry - Print Form not respecting order of sections | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual testing
9 | 4.17 Sprint 1 Stretch | Atchaiah | 23002 | Mosaic FOH - Reports - Daily Eligibility Snapshot - Direct Certified Student numbers are 0 | 1 | 0.5 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Closed | Manual testing

## 4.17 - Sprint 1-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
No defects reported

## 4.16 - Sprint 1-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.16 Sprint 1 | Alpha | 22571 | Barrow County Schools - Blank first Page with the Sales Overview Report Revenue Only | 3 | 3 | Alpha | Arvinth | None | Arvinth | None | 35055 | 2024-01-18 | 2024-01-18 | Subha | None | Ying | 2024-01-18 | None | None | NA | Closed
2 | 4.16 Sprint 1 | Arvinth | 22492 | Mosaic - POS (Web) - Issue with Notification letters (Email Sent Event) | 3 | 3 | Arvinth | Alpha | None | Alpha | None | 35057 | 2024-01-18 | 2024-01-18 | Subha | None | Ying | 2024-01-18 | None | None | NA | Closed
3 | 4.16 Sprint 1 | Alpha | 42909 | Mosaic - POS (Web) - Exclude Support Users from User Activity Log Report | 3 | 3 | Alpha | Arvinth | None | Arvinth | None | 35056 | 2024-01-18 | 2024-01-18 | Subha | Need to remove HtmlExtension code. | Ying | 2024-01-18 | None | None | None | Closed
4 | 4.16 Sprint 1 | Subhashri | 42925 | Mosaic - POS (Web) (SYSU) - Add Graduate SY**-** to Next Grade List (Student Grade Maintenance) | 2 | 1.5 | Subhashri | Arvinth | None | Arvinth | Revision History needs to be added to StudentWCF.cs | 35088 | 2024-01-19 | 2024-01-19 | NA | NA | Ying | 2024-01-19 | None | None | None | Closed
5 | 4.16 Sprint 1 | Subhashri | 22645 | Mosaic POS (Web) - Sales Tax Report - Taxable Sales Column | 2 | 1.5 | Subhashri | Subhashri | None | Subhashri | None | 35090 | 2024-01-19 | 2024-01-19 | NA | NA | Ying | 2024-01-19 | None | None | None | Closed
6 | 4.16 Sprint 1 | Subhashri | 22689 | Mosaic - POS (Web) (4.15 Regression) - Value entered in Amount Collected is not saving in Bulk Entry Form | 2 | 1 | Subhashri | Alpha | None | Alpha | None | 35083 | 2024-01-19 | 2024-01-19 | NA | NA | Ying | 2024-01-19 | None | None | NA | Closed
7 | 4.16 Sprint 1 | Subhashri | Defect - 22628 | Mosaic POS - Review Transaction - Add Transaction Select Student Status popup not honoring Overrides | 2 | 2 | Subhashri | Arvinth | When Override is set to No then need to remove that status | Arvinth | Revision History needs to be added, Remove reduntant code lines | 35266 | 2024-01-31 | 2024-01-31 | NA | NA | Ying | 2024-01-31 | None | None | NA | Closed
8 | 4.16 Sprint 1 | Subhashri | Defect - 22770 | Mosaic POS (Web) - Transaction History CSV Export Using wrong Time Zone | 2 | 1 | Subhashri | Alpha | None | Alpha | Revision History needs to be added | 35265 | 2024-01-31 | 2024-01-31 | NA | NA | Ying | 2024-01-31 | None | None | NA | Closed
9 | 4.16 Sprint 1 | Subhashri | 43077 | Mosaic POS(CPS) - Revert (deprecate) the 'End Open Previous Day' feature | 5 | 5 | Subhashri | Arvinth | None | Arvinth | None | 35183 | 2024-01-25 | 2024-01-25 | NA | NA | Ying | 2024-01-25 | None | None | None | Closed

## 4.16 - Sprint 1-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.16 Sprint 1 | 42835 | Alpha | Bounceback | Decimal formatting mismatch | Minor | Internal | Closed | QA | PR Merge Issue
|  |  |  | Bounceback |  | Significant | External | Closed | Development | Development
|  |  |  | Bounceback |  | Significant | External | Closed | Development | Development
|  |  |  | Bounceback |  | Significant | External | Closed | Development | Development

## Checklist (hidden)
Code Review Comments received from Client for 2.5 Sprint |  | S No | Execution Steps | Status
1 | index.tsx /AugustWeb/Features/ContactMaintenance/Components/index.tsx Search doesn't work on the details page. Please remove the search component from the header. | 1 | Code conflict | FALSE
2 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs If the admin doesn't set up any of the new options, then the system rejects every registration. | 2 | Coding Standard | FALSE
3 | PickEnrollmentPlanView.tsx /ParentWeb/ClientApp/src/pages/Registration/PickEnrollmentPlanView.tsx This should be filtered before this ternary statement so the "No enrollment plans" message could be shown if all plans are at capacity and closed. | 3 | Existing Functionality | FALSE
4 | ParentApiRegistrationController.cs /AugustWeb/Features/ParentAPI/ParentApiRegistrationController.cs Could we add a TermEnrollmentPlanId query parameter and query for it directly instead of pulling all the plans for the term? | 4 | Acceptance Criteria coverage | FALSE
|  | 5 | Code execute | FALSE
|  | 6 | Code Performance | FALSE
|  | 7 | Code cleanup | FALSE
|  | 8 | Understandable code comments | FALSE

## Details (hidden)
Root Cause category
Enhancements
Existing_Issues
Requirements
QA
Design
Documentation
Development
Project_Management
Environment_Related

## 4.16 - Sprint 2-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.16 Sprint 2 | 42826 | Arvinth | Bounceback | Comma in Address field made CSV to have extra column | Minor | Internal | Closed | QA | Want to identify the possible columns that has commas

## 4.16 - Sprint 2-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.16 Sprint 2 | Arvinth | 42810 | Mosaic - POS (Web) - Run Close Day Reports for Previous Days | 5 | 4.5 | Arvinth | Alpha | None | Alpha | None | 35348 | 2024-02-07 | 2024-02-07 | Subha | Spelling mistake in comments | Ying | 2024-02-07 | None | None | None | Closed
2 | 4.16 Sprint 2 | Alpha | 42927 | Mosaic - POS (Web) (SYSU) - Add Pre and Post Export (Close Year) | 5 | 5 | Alpha | Arvinth | Issue with Grade advancements | Arvinth | None | 35386 | 2024-02-09 | 2024-02-09 | Subha | Concern on Grade advancements(Graduate) | Ying | 2024-02-09 | None | Suggested for re-arranging columns in csv file | None | Closed
3 | 4.16 Sprint 2 | Arvinth | 42478 | Mosaic - POS (Web) - Add 'Last Payment Date' as a field to Custom Report Setup | 5 | 4 | Arvinth | Alpha | None | Alpha | None | 35371 | 2024-02-08 | 2024-02-08 | Subha | None | Ying | 2024-02-08 | None | None | None | Closed
4 | 4.16 Sprint 2 | Subhashri | 42689 | Mosaic - POS (Web) - Close Year Summary Report(SYSU) | 8 | 6 | Subhashri | Arvinth | None | Arvinth | None | 35375 | 2024-02-08 | 2024-02-08 | NA | NA | Ying | 2024-02-08 | None | None | None | Closed
5 | 4.16 Sprint 2 | Alpha | 42119 | Mosaic - Add warning when attempting to delete inactive student data (Close Year) | 3 | 3 | Alpha | Atchaiah | Pop up shouldn't come after close year is performed | Arvinth | None | 35410 | 2024-02-12 | 2024-02-12 | Subha | None | Ying | 2024-02-12 | None | None | None | Closed
6 | 4.16 Sprint 2 | Arvinth | 42826 | Mosaic - POS (Web) - Add CSV to Custom Student Report | 5 | 4 | Arvinth | Subha | None | Alpha | None | 35421 | 2024-02-12 | 2024-02-12 | Subha | Add comments over class file | Ying | 2024-02-12 | None | None | None | Closed
7 | 4.16 Sprint 2 | Alpha | 22839 | Mosaic FOH - MSBSSO - Confirm work email - Formatting is off/incorrect | 2 | 1 | Alpha | Arvinth | None | Arvinth | None | 35466 | 2024-02-15 | 2024-02-15 | Subha | None | Ying | 2024-02-15 | None | None | None | Closed
8 | 4.16 Sprint 2 | Atchaiah | 43471 | Mosaic-POS Automation | 8 | 8 | Atchaiah | NA | NA | NA | NA | 35311 | 2024-02-06 | 2024-02-06 | NA | NA | Ying | 2024-02-06 | None | NA | NA | Closed
9 | 4.16 Sprint 2 | Atchaiah | 43552 | Mosaic-POS Automation | 8 | 8 | Atchaiah | NA | NA | NA | NA | 35463 | 2024-02-15 | 2024-02-15 | NA | NA | Ying | 2024-02-15 | None | NA | NA | Closed

## 4.16 - Sprint 3-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.16 Sprint 3 | 22962 | Arvinth | Defect | In close day report while validating closed dates, serving date time formatting issue in hosted environment | Minor | Internal | Closed | Environment_Related | Issue occcuring only in hosted environment

## 4.16 - Sprint 3-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.16 Sprint 3 | Alpha | 43508 | Mosaic - POS (Web) (NJEIE) - Add NJEIE counts to Daily Sales Report | 3 | 3 | Alpha | Arvinth | None | Arvinth | None | 35553 | 2024-02-21 | 2024-02-21 | Subha | Revision history update | Ying | 2024-02-21 | None | None | None | Closed
2 | 4.16 Sprint 3 Stretch | Atchaiah | 43688 | Mosaic - POS Automation | 8 | 8 | Atchaiah | NA | NA | NA | NA | 35612 | 2024-02-23 | 2024-02-23 |  |  | Ying | 2024-02-23 | None | NA | NA | Closed
3 | 4.16 Sprint 3 | Subhasri | 43510 | Mosaic - POS (Web) (NJEIE) - Add NJEIE filter to Notification Letters (Reports) | 3 | 3 | Subhasri | Alpha | When changing the Notification letter dropdown, the Eligibility is resetting to blank and "Include EIG" is not disabling. | Alpha | None | 35568 | 2024-02-21 | 2024-02-21 | NA | NA | Ying | 2024-02-21 | NA | NJEIE UI filter can be placed before DisplayType dropdown | None | Closed
4 | 4.16 Sprint 3 | Subhasri | 43166 | Mosaic - POS (Web) - IL WINS SFSP Export | 3 | 3 | Subhasri | Alpha | When ISBEID is empty then mealcounts sums up to a single row. School selection is not retained after export is ran. | Alpha | None | 35536 | 2024-02-20 | 2024-02-20 | NA | NA | Ying | 2024-02-20 | NA | None | None | Closed
5 | 4.16 Sprint 3 | Alpha | 43435 | Mosaic - POS (Web) - Remove filtering from the No-ID section of the Edit Check Report | 1 | 1 | Alpha | Arvinth | None | Arvinth | None | [8 empty] | Suggested for holding it in feature branch since Gary wanted to check with customer | None | Inprogress
6 | 4.16 Sprint 3 | Arvinth | 42670 | Mosaic - POS (Web) - Add a new field to choose accounts to reset balances (Close Year Execute) | 2 | 2 | Arvinth | Atchai | None | Alpha | None | 35510 | 2024-02-19 | 2024-02-19 | Subha | Rename File (Add 1 before file name) | Ying | 2024-02-19 | NA | None | None | Closed
7 | 4.16 Sprint 3 | Arvinth | 43651 | Mosaic - POS (Web) - Add Deleted Filter to Student Listing Report (Only for HSS users) | 2 | 1.5 | Arvinth | Atchai | None | Alpha | None | 35565 | 2024-02-21 | 2024-02-22 | Subha | None | Ying | 2024-02-22 | None | None | None | Closed
8 | 4.16 Sprint 3 | Arvinth | 43652 | Mosaic - Data Lake (GCB) - Replace double quotes with single quote (for column values in 3 table exports) | 3 | 2.5 | Arvinth | NA | NA | Alpha | None | 35598 | 2024-02-22 | 2024-02-22 | Subha | None | Ying | 2024-02-22 | None | None | None | Closed
9 | 4.16 Sprint 3 | Arvinth | 43475 | Mosaic - POS (Web) - Add CSV to Student Listing as of Date Report | 5 | 4 | Arvinth | Alpha | None | Alpha | None | 35673 | 2024-02-27 | 2024-02-27 | Subha | None | Ying | 2024-02-27 | None | None | None | Closed
10 | 4.16 Sprint 3 | Alpha | 43544 | Mosaic - POS (Web) - Track Additional Changes in School History (SYSU) | 3 | 3.5 | Alpha | Arvinth | None | Arvinth | None | 35634 | 2024-02-26 | 2024-02-26 | Subha | Change System to Mosaic in the existing code. | Ying | 2024-02-26 | None | None | None | Closed
11 | 4.16 Sprint 3 | Alpha | 22890 | Mosaic FOH - Reports - Extended Sales Report - Each page shows date range instead of specific date | 2 | 1.5 | Alpha | Arvinth | None | Arvinth | None | 35633 | 2024-02-26 | 2024-02-26 | Subha | None | Ying | 2024-02-26 | None |  |  | Closed
12 | 4.16 Sprint 3 | Subhasri | 42828 | Mosaic - POS (Web) - Add Export to CSV option to User Search UI | 5 | 4 | Subhasri | Arvinth | when export download setting set to NO this error popup comes, Error pop shows "No user found" | Arvinth | None | 35648 | 2024-02-26 | 2024-02-26 | NA | NA | Ying | 2024-02-26 | None | None | None | Closed
13 | 4.16 Sprint 3 | Subhasri | 43562 | Mosaic POS(KDE) - Student Export - "Custom Lookup Group" filter Improvement | 2 | 1.5 | Subhasri | Arvinth | None | Arvinth | None | 35677 | 2024-02-27 | 2024-02-27 | NA | NA | Ying | 2024-02-27 | None | None | None | Closed
14 | 4.16 Sprint 3 | Alpha | 22873 | Mosaic POS (Web) - Setup - Scheduler Task not displaying correctly on Edit | 2 | 1.5 | Alpha | Arvinth | None | Arvinth | None | 35676 | 2024-02-27 | 2024-02-27 | Subha | None | Ying | 2024-02-27 | None
15 | 4.16 Sprint 3 Stretch | Alpha | 22929 | Mosaic POS (Web) - Reports - Student Barcode Report - Avery 10 per page only showing 8 per page | 1 | 1 | Alpha | Arvinth | None | Arvinth | None | 35719 | 2024-02-29 | 2024-02-29 | Subha | None | Ying | 2024-02-29 | None |  |  | Closed

## 4.16 - Sprint 4-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.16 Sprint 4 | Arvinth | 43487 | Mosaic - POS (Web) (NJEIE) - Add 'NJEIE Eligible' to Eligibility Statistics by Grade Report | 2 | 2 | Arvinth | Subha | None | Alpha | None | 35746 | 2024-03-01 | 2024-03-01 | Subha | None | Ying | 2024-03-01 | None | None | None | Closed
2 | 4.16 Sprint 4 Stretch | Arvinth | 43472 | Mosaic - POS (Web) - Add count to Attachments Tab (Student Maintenance) | 2 | 1 | Arvinth | Alpha | None | Alpha | None | 35833 | 2024-03-07 | 2024-03-07 | Subha | None | Ying | 2024-03-07 | None | None | None | Closed
3 | 4.16 Sprint 4 | Alpha | 22832 | Mosaic POS (Web) - Student Meal Report "Date Header" b/t pages | 2 | 1.5 | Alpha | Arvinth | None | Arvinth | None | 35762 | 2024-03-04 | 2024-03-04 | Subha | None | Ying | 2024-03-04 | None | None | None | Closed
4 | 4.16 Sprint 4 Stretch | Alpha | 43781 | Mosaic - POS (Web) - Add pagination to School Assignment when adding schools (Bulk Entry Form Setting) | 5 | 3 | Alpha | Arvinth | After reset and search the pager is not reset to first page if first page is not selected prior | Arvinth | None | 35830 | 2024-03-07 | 2024-03-07 | Subha | None | Ying | 2024-03-07 | None | None | None | Closed
5 | 4.16 Sprint 4 Stretch | Alpha | 42809 | Mosaic - POS (Web) - Exclude e-hps users from User Assignment Report | 3 | 2 | Alpha | Arvinth | None | Arvinth | Change in the ANSI_NULLS, QUOTED_IDENTIFIER and Go keyword in the stored procedure | 35831 | 2024-03-07 | 2024-03-07 | Subha | None | Ying | 2024-03-07 | None | None | None | Closed
6 | 4.16 Sprint 4 Stretch | Alpha | 43915 | Mosaic - POS (Web) - Remove e-hps users from User Report | 2 | 1.5 | Alpha | Arvinth | None | Arvinth | None | 35950 | 2024-03-14 | 2024-03-14 | Subha | None | Ying | 2024-03-14 | Script folder change from 4.16 to 4.17 | None | None | Closed
7 | 4.16 Sprint 4 | Arvinth | 43776 | Mosaic POS - Pendo changes (CEP, Visitor Role, isDemo, Expiration) | 5 | 3.5 | Arvinth | Alpha | None | Alpha | None | 35834 | 2024-03-07 | 2024-03-07 | Subha | None | Ying | 2024-03-07 | None | None | None | Closed
8 | 4.16 Sprint 4 Stretch | Alpha | 42825 | Mosaic - POS (Web) - Add a droplist for App Elig Reason (Student Export filter) | 3 | 3 | Alpha | Arvinth | None | Arvinth | None | 35949 | 2024-03-14 | 2024-03-14 | Subha | None | Ying | 2024-03-14 | None | None | None | Closed
9 | 4.16 Sprint 4 Stretch | Alpha | 23001 | Mosaic POS (Web) - Utilities - Student Balance Import Undo - Display issues with Undo List. | 2 | 2 | Alpha | Arvinth | None | Arvinth | None | 36197 | 2024-03-28 | 2024-03-28 | Subha | None | Ying | 2024-03-28 | None |  |  | Closed
10 | 4.16 Sprint 4 Stretch | Alpha | 22995 | Mosaic POS (Web) - Bulk Entry - Print Form not respecting order of sections | 2 | 2 | Alpha | Arvinth | None | Arvinth | None | 36196 | 2024-03-28 | 2024-03-28 | Subha | None | Ying | 2024-03-28 | None |  |  | Closed
11 | 4.16 Sprint 4 | Subha | 43617 | Mosaic - POS (Web) (NJEIE) - Add 'NJEIE Eligible' to Eligibility Statistics by School Report | 2 | 2 | Subha | Arvinth | None | Arvinth | None | 35750 | 2024-03-01 | 2024-03-01 | NA | NA | Ying | 2024-03-01 | None | None | None | Closed
12 | 4.16 Sprint 4 | Subha | 43828 | Mosaic - POS (Web) - Add Demo Site & Expire Date to District Maintenance (HSS Level 0 users only) | 3 | 2.5 | Subha | Arvinth | None | Arvinth | None | 35797 | 2024-03-05 | 2024-03-05 | NA | NA | Ying | 2024-03-05 | None | None | None | Closed

## 4.16 - Sprint 4-Defect (hidden)
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments
1 | 4.16 Sprint 4 | 43828 | Subhasri | Bounceback | Level 1 and level 2 support users priority should be changed. | Minor | Internal | Closed | QA | If smae user having two level access then level1 user should get prioritized access

## 4.16 - Sprint 5-CRC (hidden)
S.No | Sprint | Developer | Story ID/Defect ID | Description | Estimated(hrs/sp) | Actual(hrs/sp) | Unit testing | Peer Tested By | Peer Tested Comments, if any | Peer Reviewed By | Peer Code Review Comments, if any | PR Number/Link | PR Created Date | PR Approved Date | Reviewer 1 | Code Review Comments, if any | Reviewer 2 | Approved Date | Code Review Comments, if any | Internal PO -POV Comments | Client PO -POV Comments | Status | Comments
1 | 4.16 Sprint 5 | Atchaiah | 43876 | Mosaic-POS Automation | 8SP | 8 | Atchaiah |  |  |  |  | 35959 | 2024-03-21 | 2024-03-21 | Ying | No |  | 2024-03-21 |  | N/A | N/A | Closed
2 | 4.16 Sprint 5 | Atchaiah | 43834 | POS Automation (Testify Fixes) | 8SP | 8 | Atchaiah |  |  |  |  | 35938 | 2024-03-12 | 2024-03-20 | Ying | Several tests failed, Mainly due to NPOI dll change. |  | 2024-03-20 |  | N/A | N/A | Closed
3 | 4.16 Sprint 5 Stretch | Alpha | 23001 | Mosaic POS (Web) - Utilities - Student Balance Import Undo - Display issues with Undo List. | 2 | 2 | Alpha | Arvinth | None | Arvinth | None | 36197 | 2024-03-28 | 2024-03-28 | Subha | None | Ying | 2024-03-28 | None |  |  | Closed
4 | 4.16 Sprint 5 Stretch | Alpha | 22995 | Mosaic POS (Web) - Bulk Entry - Print Form not respecting order of sections | 2 | 2 | Alpha | Arvinth | None | Arvinth | None | 36196 | 2024-03-28 | 2024-03-28 | Subha | None | Ying | 2024-03-28 | None |  |  | Closed

## 4.16 - Sprint 5-Defect
S.No | Sprint # | Story/Defect ID | Developer | Issue Type | Issue Description | Priority | Type | Status | Root Cause Category | Comments

## Settings
Story Completed
Story Being Tested
Story Ready For Testing
Story Peer Review
Product Owner - Verify
Story Being Developed
Story Approved
Defect Found
Defect Verified
Defect Being Fixed
Defect Peer Review
Product Owner - Verify
Defect Ready For Testing
Defect Being Tested
Defect Fixed
Defect Rejected
Defect Needs More Info
Defect Blocked
Story Need More Info
Story Requested

## ExportData
1 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24428 | Mosaic - POS (Web) (4.19) - Delete button enables on name already exist popup while adding vending machine | Story Completed | 0.5 | 0.5 |  | Arvinth | Alpha | None | Alpha | None | 40170 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
2 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24425 | Mosaic - POS (Web) (4.19) - Delete button enables on adding local server while Name already exists popup opens | Story Completed | 0.5 | 0.5 |  | Arvinth | Alpha | None | Alpha | None | 40171 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
3 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin | 24433 | Mosaic - POS (Web) (4.19) - Name already exists popup is not showing up in POS Login Message screen | Story Completed | 0.5 | 0.5 |  | Arvinth | Alpha | None | Alpha | None | 40173 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
4 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24424 | Mosaic - POS (Web) (4.19) - Delete button enables on adding student letter while Name already exists popup opens | Story Completed | 0.5 | 0.5 |  | Arvinth | Alpha | None | Alpha | None | 40172 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
5 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24429 | Mosaic - POS (Web) (4.19) - Same name is allowing for Vending machine during edit | Story Completed | 1 | 1 |  | Subha | Arvinth | None | Arvinth | None | 40169 | 45659 | 45659 | NA | NA | Ying | 45659 | None | None | NA
6 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24431 | Mosaic - POS (Web) (4.19) - Name already exists popup is not showing up in POS Input Device screen | Story Completed | 0.5 | 0.5 |  | Subha | Arvinth | None | Arvinth | None | 40174 | 45659 | 45659 | NA | NA | Ying | 45659 | None | None | NA
7 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin | 24451 | 24451 - Mosaic - POS (Web) (4.19) - Lower limit balance and upper limit balance not working in student barcode report | Story Completed | 1 | 1 |  | Arvinth | Alpha | None | Alpha | None | 40175 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
8 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin | 24422 | Mosaic - POS (Web) (4.19) - 'This Name already exists' popup opens twice in Bus/Route Assignments | Story Completed | 0.5 | 0.5 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Rejected - Code changes for 24422 and 24423 are same
9 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24427 | Mosaic - POS (Web) (4.19) - Auto Include New Schools value is not retaining in School group | Story Completed | 1 | 1 |  | Alpha | Arvinth | None | Arvinth | None | 40177 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
10 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin/Atchaiah | 24426 | Mosaic - POS (Web) (4.19) - Add school group Search is not working for the first time | Story Completed | 1 | 1 |  | Alpha | Arvinth | None | Arvinth | None | 40179 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
11 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin | 24432 | Mosaic - POS (Web) (4.19) - Delete button is showing during add in POS Login Message screen | Story Completed | 0.5 | 0.5 |  | Alpha | Arvinth | None | Arvinth | None | 40180 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
12 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Ashwin | 24423 | Mosaic - POS (Web) (4.19) - 'This Name already exists' popup opens twice in POS Custom Lookup | Story Completed | 0.5 | 0.5 |  | Alpha | Arvinth | None | Arvinth | None | 40176 | 45659 | 45659 | Subha | None | Ying | 45659 | None | None | NA
13 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Arvinth | 24462 | Mosaic - POS (Web) (4.19) - School not closed report doesn't shows if current day is reopened | Story Completed | 2 | 2 |  | Arvinth | Alpha | None | Alpha | None | 40263 | 45666 | 45666 | Subha | None | Ying | 45666 | None | None | NA
14 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Arvinth/Alpha | 46700 | Mosaic - POS (Web) (CPS) - Schools not in School Groups (C0204) | Story Completed | 8 | 8 |  | Arvinth | Alpha | Add comma in display parameters for school groups | Alpha | None | 40262 | 45666 | 45666 | Subha | None | Ying | 45666 | None | None | NA
15 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Alpha | 43925 | Mosaic - POS (Web) - Add a new report type to POS Roster Report (Extended) | Story Completed | 3 | 3 |  | Alpha | Atchaiah | None | Arvinth | None | 40216 | 45664 | 45664 | Subha | None | Ying | 45664 | None | None | NA
16 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Alpha | 45938 | Mosaic - POS (SL) - Modify message in Already Logged In popup (DBS) | Story Completed | 2 | 2 |  | Alpha | Arvinth | None | Arvinth | None | 40258 | 45666 | 45666 | Subha | None | Ying | 45666 | None | None | NA
17 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Alpha | 43924 | Mosaic - POS (Web) - Add a new report type to POS Roster Report | Story Completed | 3 | 3 |  | Alpha | Atchaiah | None | Arvinth | None | 40259 | 45666 | 45666 | Subha | None | Ying | 45666 | None | None | NA
18 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Subhasri | 24405 | MFOH(4.19) - NC Claim Total Monthly Attendance is using MAX Date instead of Total | Story Completed | 2 | 2 |  | Subhasri | Alpha | None | Alpha | None | 40266 | 45666 | 45666 | NA | NA | Ying | 45666 | None | None | NA
19 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Arvinth | 46611 | Mosaic - FOH 4.19 (Regression) - POS(Web) | Story Completed | 2 | 2 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
20 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Atchai/Alpha/Arvinth | 46607 | Mosaic - FOH 4.19(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 3 | 3 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression testing
21 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 | Subhasri | 46077 | Mosaic - FOH - Rename the import file that mosaic creates on district's SFTP Folder ( DataHub API to SFTP Folder) | Story Completed | 2 | 2 |  | Subhasri | Alpha | None | Alpha | None | 40269 | 45666 | 45666 | NA | NA | Ying | 45666 | None | None | NA
22 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 Stretch | Arvinth | 24487 | MFOH - Update Sales Demo Data SQL failing on SQL 2008 | Story Completed | 2 | 2 |  | Arvinth | Subha | None | None | None | 40312 | 45671 | 45671 | Subha | None | Ying | 45671 | None | None | NA
23 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 Stretch | Ashwin | 46423 | Mosaic - POS (Web) - Add Effective Date column to Student Search Grid | Story Completed | 2 | 2 |  | Ashwin | Arvinth | None | Arvinth | Use common method for application year | 40285 | 45666 | 45666 | Subha | None | Ying | 45666 | None | None | NA
24 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 Stretch | Subhasri | 46696 | Mosaic - POS (Web) (CPS) - Dashboard V2 | Story Ready For Testing | 8 | 7 |  | Subhasri | Alpha | None | Alpha | None | 40265 | 45666 | 45666 | [7 empty] | Testing will be done by onsite QA
25 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 Stretch | Arvinth | 46539 | Mosaic - POS (Web) - Modify School Export to include new columns (DBS) | Story Being Developed | 5 |  |  | Arvinth
26 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 Stretch | Atchaiah | 46827 | MFOH-Automation | Story Completed | 8 | 8 |  | NA | NA | NA | NA | NA | 40338 | 45673 | 45679 | NA | NA | Ying | 45679 | NA | NA | NA
27 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 Stretch | Ashwin | 46017 | Mosaic - POS (Web) - Add new columns to Logout POS User Search (DBS) | Story Being Developed | 3 |  |  | Ashwin
28 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 Stretch | Alpha | 46675 | Mosaic - POS (Web) - Add an ability to assign POS Menu to multiple POS Numbers | Story Being Developed | 3
29 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 1 Stretch | Ashwin | 46424 | Mosaic - POS (Web) - Add Tracking for Menu Products (Log user who modified it) | Story Being Developed | 2 |  |  | Ashwin
1 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 | Arvinth | 46539 | Mosaic - POS (Web) - Modify School Export to include new columns (DBS) | Story Completed | 2 | 2 | 2 | Arvinth | Alpha | None | Alpha | None | 40368 | 45674 | 45674 | Subha | None | Ying | 45674 | None | None | NA
2 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 | Subhasri/Alpha | 46425 | Mosaic - POS (Web) - Add a warning popup when Deleting POS Menus | Story Completed | 3 | 3 |  | Subhasri | Atchaiah | When duplicate POS Menu is created and already exists error pop up is not closing properly | Arvinth | None | 40485 | 45681 | 45681 | NA | NA | Ying | 45681 | None | None | NA
3 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 | Alpha/Subhasri | 46675 | Mosaic - POS (Web) - Add the ability to assign POS Menus to multiple POS Numbers | Story Completed | 3 | 3 |  | Alpha | Arvinth | Validation and UI issues | Arvinth | None | 40542 | 45686 | 45686 | Subha | None | Ying | 45686 | None | None | None
4 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 | Ashwin/Alpha | 46945 | MFOH - Modify Layout and add Privacy Policy and Terms of Use link to Login Screen (Web) | Story Completed | 3 | 3 |  | Ashwin | Arvinth | None | Arvinth | None | 40420 | 45679 | 45679 | Subha | None | Ying | 45679 | None | Adjust the Mosaic logo to the perfect center of the login form | None
5 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 | Arvinth | 46029 | Mosaic FoH POS (KDE) - CEP Reimbursement Calculations Free/Paid "Reimbursement Due / Standard Claim" Reports | Story Completed | 5 | 5 |  | Arvinth | Alpha | None | Alpha | None | 40497 | 45684 | 45684 | Subha | None | Ying | 45684 | None | None | None
6 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 | Subhasri/Arvinth | 46111 | Mosaic - POS (Web) - Arrange Menu Products in Alphabetical Order (POS Menu Maintenance) (DBS) | Story Completed | 3 | 3 |  | Subhasri | Arvinth | None | Arvinth | None | 40531 | 45685 | 45685 | NA | NA | Ying | 45685 | None | None | NA
7 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 | Arvinth | 46060 | Mosaic - POS (Web) - Modify POS Menu Order to a droplist for Multiple Assignments | Story Completed | 3 | 3 |  | Arvinth | Alpha | None | Alpha | None | 40532 | 45685 | 45685 | Subha | None | Ying | 45685 | None | Change the POS Menu Order in Add Assignment | None
8 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 Stretch | Ashwin | 45797 | Mosaic - POS (Web) - Add a new report type 'Daily with Only Status' to POS Roster Report | Story Ready For Testing | 3 | 3 |  | Ashwin | Arvinth | None | Arvinth | None | 40543 | 45686 | 45686 | Subha | None | Ying | 45686 | None | None | None | Testing will be done by onsite QA - Mike in Sprint 3
9 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 Stretch | Ashwin | 45796 | Mosaic - POS (Web) - Add a new report type 'Daily with Only Status' to POS Roster Report (Extended) | Story Ready For Testing | 3 | 2 |  | Ashwin | Arvinth | None | Arvinth | None | 40547 | 45686 | 45686 | Subha | None | Ying | 45686 | None | None | None | Testing will be done by onsite QA - Mike in Sprint 3
10 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 Stretch | Atchaiah | 46973 | MFOH-Automation | Story Completed | 8 | 8 | [6 empty] | 40567 | 45687 | 45692 | Subha |  | Ying | 45692 | NA | NA | NA
11 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 Stretch | Ashwin | 45804 | Mosaic - POS (Web) - Add 'Include Barcode' filter to POS Roster Report | Story Peer Review | 3 |  |  | Ashwin | Arvinth | None | Arvinth | None |  |  |  | Subha |  |  |  |  | Remove the border line between Photo and Barcode |  | Story review with Onsite Lead - In Progress
12 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 2 Stretch | Ashwin | 45673 | Mosaic - POS (Web) - Add Bus Route filter to Student Barcode Report | Story Peer Review | 3 |  |  | Ashwin | [7 empty] | Subha | [6 empty] | Story review with Onsite Lead - In Progress
1 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 | Arvinth | 45612 | Mosaic - POS (Web) - Add SPP and SP droplist to SPEC Report (Close Day Reports) | Story Completed | 8 | 8 | 29 | Arvinth | Alpha | UI Issue on changing dropdown | Alpha | None | 45612 | 45699 | 45699 | Subha | None | Ying | 45699 | None | None | NA
2 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 | Subhasri | 23549 | MFOH (CPS - C0221) - ADA Visual Reports vs IL NSLP WINS Export | Defect Fixed | 5 | 5 | 16 | Subhasri | Alpha | None | Alpha | None | 40700 | 45695 | 45695 | NA | NA | Ying | 45695 | None | None | None
3 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 | Alpha/Arvinth | 46987 | MFOH - Add Student Effective Date and Student Eligibility Reason to Student Maintenance (NJ) | Story Completed | 5 | 5 | 18.25 | Alpha | Atchaiah | None | Arvinth | None | 40655 | 45693 | 45693 | Subha | Change the declaration from "" to string.Empty | Ying | 45693 | None | None | NA
4 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 | Alpha | 46955 | MFOH - Add alternate pathing options to the IL WINS NSLP Export | Story Completed | 3 | 3 | 10 | Alpha | Arvinth | Sub folder without slash at end, then that value is concatenating with the file name. | Arvinth | None | 40695 | 45695 | 45695 | Suba | None | Ying | 45695 | None | None | None
5 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 | Subhasri/Ashwin | 24493 | Mosaic POS (Web) - Transaction Export Download Defect | Defect Fixed | 1 | 1 | 3 | Subhasri | Ashwin | None | Ashwin | None | 40681 | 45694 | 45694 | NA | NA | Ying | 45694 | None | None | NA
6 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 | Subhasri/Alpha | 24489 | Spartanburg District Five - Building Summary Report Miscalculation | Defect Fixed | 2 | 2 | 7 | Subhasri | NA | NA | NA | NA | 40684 | 45694 | 45694 | NA | NA | Ying | 45694 | None | None | NA
7 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 | Ashwin/Alpha | 46424 | Mosaic - POS (Web) - Add Tracking for Menu Products (Log user who modified it) | Story Completed | 1 | 1 | 3 | Ashwin | Arvinth | None | Arvinth | None | 46424 | 45692 | 45692 | Subha | None | Ying | 45692 | None | None | None
8 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 Stretch | Ashwin | 46986 | MFOH - Add Serving Period Multi Select Droplist to Schools not in School Group Report (CPS) | Story Completed | 3 | 3 | 7 | Ashwin | Arvinth | None | Arvinth | None | 40736 | 45700 | 45700 | Subha | Remove unused code and comments | Ying | 45700 | None | None | None
9 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 Stretch | Atchaiah | 47118 | MFOH - Automation | Story Completed | 8 |  | 32 | NA | NA | NA | NA | NA | 40759 | 45701 | 45702 | NA |  | Ying | 45702 | None | None | None | 45796,45797,46060,46111,46423,46915 and 46946
10 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 Stretch | Alpha | 46783 | Mosaic - POS (Web) - A La Carte vs Meal - Revenue Export (for 4.21) | Story Being Developed | 8 |  | 28 | Alpha
11 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 Stretch | Ashwin | 43484 | Mosaic - POS (Web) - Display count for Mapping Translation (Student Import) (4.21) | Story Being Developed | 8
12 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 3 Stretch | Subhasri/Alpha | 24621 | MFOH - POS Number is always set to ALL when editing a menu assignment | Defect Fixed | 3 | 3 | 8 | Subhasri | Arvinth | 1. When school is changed then default value is not changed 2. When adding a new menu assignment, multi select dropdown is setting a different value | Arvinth | None | 40750 | 45700 | 45700 | NA | NA | Ying | 45700 | None | None | None
1 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Arvinth/Ashwin/Atchaiah | 47214 | Mosaic - FOH 4.20(Regression) - Setup | Story Completed | 5 | 5 | 24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
2 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Alpha/Atchaiah | 47213 | Mosaic - FOH 4.20(Regression) - Utilities | Story Completed | 5 | 5 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
3 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Subhasri/Atchaiah | 47216 | Mosaic - FOH 4.20(Regression) - End of Day | Story Completed | 5 | 5 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
4 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Arvinth/Atchaiah | 47234 | Mosaic - FOH 4.20(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 8 | 8 | 36 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
5 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Subhasri/Atchaiah | 47235 | Mosaic - FOH 4.20 (Regression) - POS(Menu Option) | Story Completed | 2 | 2 | 10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
6 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Alpha/Ashwin/Atchaiah | 47215 | Mosaic - FOH 4.20(Regression) - Students | Story Completed | 5 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
7 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Alpha/Arvinth/Atchaiah | 47219 | Mosaic - FOH 4.20 (Regression) - Eligibility (F&R) | Story Completed | 5 | 5 | 22 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
8 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Subhasri/Atchaiah | 47218 | Mosaic - FOH 4.20 (Regression) - Reports - Eligibility (F&R) | Story Completed | 3 | 3 | 14 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Regression Testing
9 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Alpha | 24732 | MFOH - (4.20 Regression) - Daily sales preview report displays school name partially | Defect Fixed | 0 | 0 | 0 | Ashwin | Alpha | None | Alpha | None | 40930 | 45713 | 45713 | NA | NA | Ying | 45713 | None | NA | NA | Regression Defects
10 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Alpha | 24733 | MFOH - (4.20 Regression) - New schools doesn't add to the school group even though Auto Include schools checkbox is checked | Defect Fixed | 0 | 0 | 0 | Ashwin | Alpha | None | Alpha | None | 40931 | 45713 | 45713 | NA | NA | Ying | 45713 | None | NA | NA | Regression Defects
11 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Alpha | 24734 | MFOH - (4.20 Regression) - Last updated date issue in Menu Product maintenance/Menu Product Import | Defect Fixed | 0 | 0 | 0 | Ashwin | Alpha | None | Alpha | None | 40932 | 45713 | 45713 | NA | NA | Ying | 45713 | None | NA | NA | Regression Defects
12 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Alpha | 24736 | MFOH - (4.20 Regression) - All Checkbox checked on deselecting grid items in School Maintenance | Defect Fixed | 0 | 0 | 0 | Ashwin | Alpha | None | Alpha | None | 40933 | 45713 | 45713 | NA | NA | Ying | 45713 | None | NA | NA | Regression Defects
13 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Arvinth | 24741 | MFOH - (4.20 Regression) - Generating 2 pages when no data in Reimbursement Due Report | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40939 | 45713 | 45713 | NA | NA | Ying | 45713 | None | NA | NA | Regression Defects
14 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Arvinth | 24739 | MFOH - (4.20 Regression) - Issue with main check box in the Student Grade Range Search screen | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | Header checked is checked when checking other grids check box | Arvinth | None | 40937 | 45713 | 45713 | NA | NA | Ying | 45713 | None | NA | NA | Regression Defects
15 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Arvinth | 24735 | MFOH - (4.20 Regression) - Delete button enabled while the name already exists on another Custom Report Setting popup shows up | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40938 | 45713 | 45713 | NA | NA | Ying | 45713 | None | NA | NA | Regression Defects
16 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Arvinth | 24737 | MFOH - (4.20 Regression) - Allergen, Allergen description and Allergen Active is disappearing during Save | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40976 | 45714 | 45714 | NA | NA | Ying | 45714 | None | NA | NA | Regression Defects
17 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Arvinth | 24740 | MFOH - (4.20 Regression) - Import Data button is present in Report as well | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40975 | 45714 | 45714 | NA | NA | Ying | 45714 | None | NA | NA | Regression Defects
18 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Arvinth | 24752 | MFOH - (4.20 Regression) - Name already exists popup enables delete button in Import & export setting | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40977 | 45714 | 45714 | NA | NA | Ying | 45714 | None | NA | NA | Regression Defects
19 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Ashwin/Arvinth | 24753 | MFOH - (4.20 Regression) - Adjustment Type drop down validation label is showing the propery name (IsDeposit) | Defect Fixed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 40974 | 45714 | 45714 | NA | NA | Ying | 45714 | None | NA | NA | Regression Defects
20 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.20 - Sprint 4 | Subhasri/Arvinth | 24756 | MFOH - (4.20 Regression) - Auto Include School clearing in School Group maintenance | Defect Fixed | 0 | 0 | 0 | Subhasri | NA | None | None | None | 40986 | 45714 | 45714 | NA | NA | Ying | 45714 | None | NA | NA | Regression Defects
1 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 | Arvinth | 47405 | MFOH - Tyler-MUNIS Financial Export | Story Completed | 13 | 13 | 45 | Arvinth | Alpha | None | Alpha | Include datatype the SqlParameter | 41171 | 45726 | 45726 | Subha | None | Ying | 45726 | None | None | NA
2 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 | Ashwin | 47362 | Mosaic FOH - Tiered Sales Model Drop List(Acceleration) | Story Completed | 3 | 3 | 6 | Ashwin | Arvinth | Code for save and Get Tier Level not added | Arvinth | None | 41118 | 45722 | 45722 | Subha | None | Ying | 45722 | None | None | NA
3 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 | Alpha | 46783 | Mosaic - POS (Web) - A La Carte & Meal - Revenue Export | Story Completed | 2 | 2 | 3 | Alpha | Arvinth | None | Arvinth | Remove unused property. | 41094 | 45721 | 45721 | Subha | None | Ying | 45721 | None | None | NA
4 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 | Ashwin | 47297 | MFOH - Add Label format options to Student Maintenance > Barcode Report (Corey's list) | Story Completed | 3 | 3 | 12 | Ashwin | Alpha | Starting label row and column should not change for Listing | Alpha | None | 41170 | 45726 | 45726 | Subha | Remove unwanted display parameters | Ying | 45726 | None | None | NA
5 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 | Subhasri/Alpha | 47077 | Mosaic FOH - Add Checks to Student Account Summary Report | Story Completed | 5 | 5 | 16 | Subhasri | Alpha | Add Cash and check payments for the a student, Report showing correctly. Then try adding the prepayments, the previous data loses from Credits > POS deposits and only prepayments showing. | Alpha | None | 41144 | 45723 | 45723 | NA | NA | Ying | 45723 | None | None | NA
6 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 Stretch | Alpha | 47168 | MFOH (SL) - Add the ability to see transactions that are Marked for Review | Story Ready For Testing | 5 | 5 | 17 | Alpha | Subha | None | Arvinth | None | 41198 | 45728 | 45728 | Subha | Revision history in one file | Steve | 45728 | None | None | NA | This story moved to onsite QA bucket.
7 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 Stretch | Atchaiah | 47433 | MFOH - Automation | Story Completed | 8 |  | 32 | [5 empty] | 41215 | 45729 |  |  |  | Ying | 45734 | NA | NA | NA | 46945, 46029, 46955, 46986, 46424 and upgraded selenium 3 to 4
8 | FOH | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 Stretch | Alpha | 47084 | Mosaic POS (Web) - SP Edit Check appears to be rounding based incorrectly | Story Being Developed | 8
9 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 Stretch | Subhasri | 47307 | MFOH - Allow Add Transactions only if the day is reopened from Open Previous Day option (Corey's list) | Story Being Developed | 5
10 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.21 - Sprint 1 Stretch | Ashwin | 46316 | Mosaic - POS (Web) - Improvements to A La Carte Report | Story Being Developed | 8 | 8 | 32 | Ashwin | Alpha | Generating blank page Error for in close day for existing records | Alpha | Change IsSummary to ReportType
1 | FOH Wave | 45730 | 45743 | 4.21 - Sprint 2 | Subhasri | 47307 | MFOH - Allow Add Transactions only if the day is reopened from Open Previous Day option (Corey's list) | Story Completed | 3 | 3 | 15 | Subhasri | Arvinth | NA | Arvinth | None | 41267 | 45733 | 45734 | NA | NA | Steve | 45734 | Only allow to add transactions to a day that has been opened using Open Previous Day as like Serving Line application | None | NA
2 | FOH Wave | 45730 | 45743 | 4.21 - Sprint 2 | Alpha | 47084 | Mosaic POS (Web) - SP Edit Check appears to be rounding based incorrectly | Story Completed | 2 | 2 | 3 | Alpha | Arvinth | None | Arvinth | None | 41280 | 45734 | 45735 | Subha | None | Ying | 45735 | None | None | NA
3 | FOH Wave | 45730 | 45743 | 4.21 - Sprint 2 | Ashwin/Alpha | 46017 | Mosaic - POS (Web) - Add new columns to Logout POS User Search | Story Completed | 2 | 2 | 4 | Ashwin | Alpha | None | Alpha | None | 41252 | 45733 | 45734 | Subha | None | Ying | 45734 | User record should be returned even there is no transaction record. | None | NA
4 | FOH Wave | 45730 | 45743 | 4.21 - Sprint 2 | Arvinth/Alpha | 47556 | MFOH - North Carolina SFS-4 Export | Story Completed | 8 | 8 | 27 | Arvinth | Alpha | Add datatype to SQLParameter | Alpha | None | 47556 | 45740 | 45740 | Subha | None | Ying | 45740 | None | None | None
5 | FOH | 45730 | 45743 | 4.21 - Sprint 2 | Ashwin/Arvinth | 46316 | Mosaic - POS (Web) - Improvements to A La Carte Report | Story Completed | 5 | 3 | 18 | Ashwin | Alpha | Generating blank page Error in close day for existing records | Alpha | Change IsSummary to ReportType | 41308 | 45736 | 45736 | Subha | None | Ying | 45736 | None | None | None
6 | FOH | 45730 | 45743 | 4.21 - Sprint 2 | Alpha | 46164 | Mosaic - POS (Web) - Add CEP ISP calculation to Chartwells Export | Story Being Tested | 5 | 5 | 14 | Alpha | Arvinth | None | Arvinth | None | 41329 | 45736 | 45736 | Subha | None | Ying | 45736 | None | None | NA | In QA(Mike) Bucket Mike was on PTO for last one week and once he was back he was busy in Release
7 | FOH | 45730 | 45743 | 4.21 - Sprint 2 | Subhasri/Alpha | 46867 | MFOH - Remove Student 2nd meals from VA SNP-12 Report | Story Completed | 2 | 2 | 7 | Subhasri | Alpha | NA | Alpha | None | 41268 | 45733 | 45733 |  |  | Ying | 45733 | None | None | NA
9 | FOH | 45730 | 45743 | 4.21 - Sprint 2 | Ashwin/Alpha/Arvinth | 47170 | MFOH - Add Blank option to Student Status filter in Student Maintenance (Corey's list) | Story Completed | 5 | 5 | 19 | Alpha | Arvinth | None | Arvinth | None | 41363 | 45740 | 45740 | Subha | None | Ying | 45740 | None | None | NA
8 | FOH | 45730 | 45743 | 4.21 - Sprint 2 Stretch | Atchaiah | 47638 | MFOH - Automation | Story Completed | 8 |  | 32 | [5 empty] | 41438 | 45743 | 45756 |  |  | Ying | 45756 |  |  |  | 45612-changes on Close Day Reports, 46987-Add Effective Date and Eligibility Reason to Student Maintenance, 46783-A La Carte & Meal-Revenue Export, 47297-Changes done on Barcode Report, 45675-Add 'Eligibility Status' filter to Disclosure Report
10 | FOH | 45730 | 45743 | 4.21 - Sprint 2 Stretch | Alpha | 44984 | Mosaic FOH - MSB Reconciliation (UI + Data structure changes) | Story Being Developed | 13
11 | FOH | 45730 | 45743 | 4.21 - Sprint 2 Stretch | Arvinth | 24779 | Mosaic POS (Web) - Aramark Export - Employee Meals appearing in Employee Alacarte NR | Story Being Developed | 3
12 | FOH | 45730 | 45743 | 4.21 - Sprint 2 Stretch | Subhasri | 47623 | MFOH - CPS Dashboard V3 | Story Being Developed | 13
13 | FOH | 45730 | 45743 | 4.21 - Sprint 2 Stretch | Alpha | 24842 | Error in Menu Product Maintenance while selecting an image | Story Ready For Testing | 1 |  | 4 | Alpha | Arvinth | None | Arvinth | None | 41254 | 45733 | 45733 | Subha | None | Ying | 45733 | None | None | NA
14 | FOH | 45730 | 45743 | 4.21 - Sprint 2 Stretch | Alpha | 24912 | MFOH - Remove unused/redundant code from Eligibility Record Report's CSV | Story Ready For Testing | 1 |  | 1 | Alpha | NA | NA | Arvinth | None | 41388 | 45741 | 45741 | Subha | None | Ying | 45741 | None | NA | NA
1 | FOH | 45744 | 45757 | 4.21 - Sprint 3 | Alpha | 47639 | Hide Student IDs in POS Serving Line(BOCES) | Story Completed | 3 | 3 | 14 | Alpha | Arvinth | System specific label alignment and POS override dropdown in system setting shows empty | Arvinth | None | 41597 | 45751 | 45754 | Subha | None | Steve/Ying | 45754 | None | None | NA
2 | FOH | 45744 | 45757 | 4.21 - Sprint 3 | Arvinth/Alpha | 47697 | MFOH - Modifications to NC SFS-4 Export | Story Completed | 3 | 3 | 9 | Arvinth | Alpha | None | Alpha | None | 41532 | 45748 | 45748 | Subha | None | Ying | 45748 | None | None | NA
3 | FOH | 45744 | 45757 | 4.21 - Sprint 3 | Alpha | 47670 | MFOH - Add NJEIE counts to Eligibility Record Listing Report | Story Completed | 3 | 3 | 11 | Alpha | Arvinth | None | Arvinth | None | 41590 | 45751 | 45751 | Subha | Revision history in one file | Ying | 45751 | None | None | NA
4 | FOH | 45744 | 45757 | 4.21 - Sprint 3 | Arvinth | 47669 | Add an ability to update ISP value for multiple schools | Story Completed | 5 | 5 | 17 | Arvinth | Alpha | None | Alpha | None | 41589 | 45751 | 45751 | Subha | Change naming | Ying | 45751 | None | None | NA
5 | FOH | 45744 | 45757 | 4.21 - Sprint 3 | Ashwin/Arvinth | 47677 | MFOH - Mosaic - POS - Update IEGs (2025-26) | Story Completed | 2 | 2 | 4 | NA | NA | NA | Arvinth | None | 41588 | 45751 | 45751 | NA | NA | Ying | 45751 | None | NA | NA
6 | FOH | 45744 | 45757 | 4.21 - Sprint 3 | Arvinth/Alpha | 24779 | Mosaic POS (Web) - Aramark Export - Employee Meals appearing in Employee Alacarte NR | Story Completed | 2 | 2 | 5 | Arvinth | Alpha | None | Alpha | None | 41570 | 45750 | 45750 | Subha | None | Ying | 45750 | None | None | NA
7 | FOH | 45744 | 45757 | 4.21 - Sprint 3 | Subhasri/Alpha | 47623 | MFOH - CPS Dashboard V3 | Story Completed | 13 | 13 | 40 | Subhasri | Alpha | 1.In the user dashboard, if we change the start date to prior date more than 30days, error pop up is blank | Alpha | None | 47623 | 45754 | 45754 |  |  | Steve | 45754 | None | None | NA
8 | FOH | 45744 | 45757 | 4.21 - Sprint 3 Stretch | Alpha | 47671 | MFOH - Add NJEIE counts to Eligibility Record Student Listing Report | Story Ready For Testing | 3 | 3 | 10 | Alpha | Arvinth | None | Arvinth | Date change | 41677 | 45757 | 45757 | Subha | None | Ying | 45757 | Instead of hard code the state, determine whether it's in any of the state that have income guideline | None | NA
9 | FOH | 45744 | 45757 | 4.21 - Sprint 3 Stretch | Atchaiah | 47817 | MFOH-Automation | Story Being Developed | 8 |  | 20 | NA | NA | NA | NA | NA |  |  |  | NA | NA |  |  |  | NA | NA
10 | FOH | 45744 | 45757 | 4.21 - Sprint 3 Stretch | Arvinth | 47548 | MFOH - MSB Reconciliation (Batch Detail Report) | Story Being Developed | 8 |  | 22
1 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Alpha/Atchaiah | 47868 | Mosaic - FOH 4.21(Regression) - Setup | Story Completed | 5 | 6 | 24 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Subhasri/Atchaiah | 47870 | Mosaic - FOH 4.21(Regression) - End of Day | Story Completed | 5 | 5.25 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Ashwin/Atchaiah | 47869 | Mosaic - FOH 4.21(Regression) - Students | Story Completed | 5 | 5.25 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Alpha/Atchaiah | 47875 | Mosaic - FOH 4.21(Regression) - Reports - (Excluding Free/Reduced) | Story Being Tested | 8 | 8.5 | 34 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | Since all the regression stories are assigned in the sprint, also we had few planned PTO as well. So client too expected some of the story might get carry forwaded.
5 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Ashwin/Atchaiah | 47876 | Mosaic - FOH 4.21 (Regression) - POS(Menu Option) | Story Completed | 2 | 2 | 8 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Atchaiah | 47872 | Mosaic - FOH 4.21 (Regression) - Reports - Eligibility (F&R) | Story Completed | 3 | 3 | 12 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Subhasri/Atchaiah | 47873 | Mosaic - FOH 4.21 (Regression) - Eligibility (F&R) | Story Completed | 5 | 5.25 | 21 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Arvinth/Atchaiah | 47867 | Mosaic - FOH 4.21(Regression) - Utilities | Story Completed | 5 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Vidhya/Subbulakshmi | 47526 | MFOH [WAVE] - Custom Report Improvements (Only Disallow/Hide Save) - Acceleration Initiative | Story Completed | 3 | 1 | 6 | Vidhya Subramani | Hemanath | None | Hemanath | None | 41709 | 45758 | 45758 | Subha | Add comments for the JS functions | Ying | 45758 | None | None | None
10 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Ashwin/Atchaiah | 25070 | MFOH - (4.21 Regression) - Contacts information is removing after saving student | Defect Fixed | 0 | 0 | 0 | Arvinth | Arvinth | None | Arvinth | None | 41879 | 45771 | 45771 | Subha | None | Ying | 45771 | None | None | NA
11 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Arvinth/Atchaiah | 25065 | MFOH - (4.21 Regression) - Console errors on Update Application Address & Email | Defect Fixed | 0 | 0 | 0 | Arvinth | NA | NA | NA | NA | 41863 | 45770 | 45770 | Subha | None | Ying | 45770 | None | None | NA
12 | FOH | 45758 | 45771 | 4.21 - Sprint 4 | Arvinth/Atchaiah | 25069 | MFOH - (4.21 Regression) - Hitting exception when clicking on Serving Period header in Time Frames tab | Defect Fixed | 0 | 0 | 0 | Arvinth | NA | NA | NA | NA | 41862 | 45770 | 45770 | Subha | None | Ying | 45770 | None | None | NA
13 | FOH | 45758 | 45771 | 4.21 - Sprint 4 Stretch | Arvinth | 47548 | MFOH - MSB Reconciliation (Batch Detail Report) | Story Being Developed | 3 | 1.5 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | FOH | 45758 | 45771 | 4.21 - Sprint 4 Stretch | Alpha | 44984 | Mosaic FOH - MSB Reconciliation (UI + Data structure changes) | Story Being Developed | 8 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
15 | FOH | 45758 | 45771 | 4.21 - Sprint 4 Stretch | Sabir Shaikh/Hemanath Jayaraman | 47575 | Mosaic -FOH 4.21 Admin View of Real-Time POS Transactions (Acceleration initiative) | Story Completed | 18 | 18 | 94 | Sabir/Hemanath | Vidhya | UI controls alignment issues, Console error,Items per page icon missing Pager icon missing. | Subha/Vidhya | UI controls alignment issues, Console error,Items per page icon missing Pager icon missing, Please format the stored procedure as standard followed in FOH. | 41869 | 45771 | 45772 | Subha | Please format the stored procedure as standard followed in FOH. Cashier field is username only, need to change the datatype size as like username column.Voided field - It can be Varchar (5) | Ying | 45772 | 1. Don't think you need to add single quote around the alias unless there is a space in alias. Please remove them as it's not a common practice for us . 2.change all the query parameters definition to : query.Parameters.Add(new SqlParameter("@SchoolID", SqlDbType.UniqueIdentifier) { Value = schoolID.Value}); 3.We still have customers that have sql server 2008, so can't use CONCAT, use "+" instead. | Multiple POV were conducted. Please fix the UI functionalities as per AC and per feedback suggestions | NA
16 | FOH | 45758 | 45771 | 4.21 - Sprint 4 Stretch | Vidhya | 47901 | MFOH [WAVE] - Add a new template for Application Student Listing to Custom Report | Story Being Developed | 8 | 7.5 | 30
17 | FOH | 45758 | 45771 | 4.21 - Sprint 4 Stretch | Hemanath Jayaraman | 45067 | MFOH [WAVE] - Add Supper section to Daily Performance Report | Story Being Developed | 7 |  | 14
1 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.22 - Sprint 1 | Arvinth/Alpha/Subha | 47875 | Mosaic - FOH 4.21(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 5 | 5 | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH | 45772 | 45785 | 4.22 - Sprint 1 | Arvinth | 47548 | MFOH - MSB Reconciliation (Batch Detail Report) | Story Completed | 3 | 3 | 6 | Arvinth | Alpha | Add footer line | Alpha | None | 42015 | 45779 | 45779 | Subha | Add summary over a class | Ying | 45779 | None | None | NA
3 | FOH | 45772 | 45785 | 4.22 - Sprint 1 Stretch | Atchaiah | 47817 | MFOH-Automation | Story Completed | 3 | 3 | 12 | NA | NA | NA | NA | NA | 42032 | 45782 | 45782 | NA | NA | Ying | 45782 | NA | NA | NA | 47405, 47556, 46476, 46017, 47307
4 | FOH | 45772 | 45785 | 4.22 - Sprint 1 | Alpha | 44984 | Mosaic FOH - MSB Reconciliation (UI + Data structure changes) | Story Completed | 8 | 8 | 26 | Alpha | Arvinth | None | Arvinth | Create table query correction, Time need to be included in received date time filter, Revision history, Remove Sql catch block. | 42060 | 45783 | 45783 | Subha | Add summary and Serializable over a class, set command timeout as 300. | Ying | 45783 | None | None | NA
5 | FOH | 45772 | 45785 | 4.22 - Sprint 1 | Hemanath Jayaraman | 45067 | MFOH [WAVE] - Add Supper section to Daily Performance Report | Story Completed | 7 | 3.5 | 14 | Hemanath | Subbulakshmi | None | Arvinth | 1. In the revision summary, remove the last name, and align the comments as per the previous ones and also update the updated date and copyright year to current year. 2. Update the SP DailyPerformanceReport to populate the supper meals count as per clarifications from PO. | 42013 | 45779 | 45779 | Subha | None | Ying | 45779 | None | None | NA | At the client side intended members are busy hence yet to do client POV
6 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.22 - Sprint 1 | Ashwin/Arvinth/Alpha | 25068 | d | Story Completed | 0 | 0 | 0 | Ashwin | Arvinth | None | Arvinth | None | 41900 | 45772 | 45772 | NA | NA | Ying | 45772 | None | None | NA
7 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.22 - Sprint 1 | Subhasri | 43742 | Mosaic - POS (Web) - Add Menu Product wise Sold Quantities to Daily Sales Preview | Story Completed | 5 | 4 | 20 | Subhasri | Arvinth | None | Arvinth | 1. Remove unused column Reimbursable column in SP | 42023 | 45779 | 45779 | NA | NA | Ying | 45779 | None | None | NA
8 | FOH | 45772 | 45785 | 4.22 - Sprint 1 | Vidhya/Subbulakshmi | 47901 | MFOH [WAVE] - Add a new template for Application Student Listing to Custom Report | Story Completed | 5 | 5 | 20 | Vidhya | Hemanath | 1. If there is no data for the selected period, then existing report shows blank page and the new report shows grand total section with 0 records. 2. When I provide temporary reason as ‘none’, getting the below exception in the code 3.If I provide group by school as ‘No’, then school wise total shouldn’t show up, only grand total should show. Here school wise total is showing with 0 records count | Hemanath | Nil | 42068 | 45784 | 45784 | Nil | Nil | Ying | 45784 | Nil | Spacing should be adjusted | Nil
9 | FOH | 45772 | 45785 | 4.22 - Sprint 1 Stretch | Arvinth | 45805 | Mosaic - POS (Web) - Add new field to Student Export and Custom Report | Story Being Developed | 3 | 2 | 8 | [15 empty] | Waiting for PR as per the client request
10 | FOH | 45772 | 45785 | 4.22 - Sprint 1 Stretch | Alpha | 48188 | MFOH - MSB Reconciliation (Add functionality for printing batch detail report from reconciliation screen) | Story Being Developed | 3 | [17 empty] | Waiting for PR as per the client request
11 | FOH | 45772 | 45785 | 4.22 - Sprint 1 Stretch | Subhasri/Ashwin | 45673 | Mosaic - POS (Web) - Add Bus Route filter to Student Barcode Report | Story Being Developed | 3 | [17 empty] | Waiting for PR as per the client request
12 | FOH | 45772 | 45785 | 4.22 - Sprint 1 Stretch | Subhasri/Ashwin | 25145 | MFOH - Issue with alternate coloring in A La Carte Report | Story Ready For Testing | 1 | 0.5 | 3 | Subhasri | Ashwin | None | Ashwin | None | 42072 | 45783 | 45783 | NA | NA | Ying | 45783 | None | None | NA
13 | FOH | 45772 | 45785 | 4.22 - Sprint 1 Stretch | Atchaiah | 48211 | MFOH-Automation | Story Being Developed | 8 | 3 | 12 | NA | NA | NA | [12 empty] | Started this story at the end of the sprint
14 | FOH | 45772 | 45785 | 4.22 - Sprint 1 Stretch | Hemanath Jayaraman | 47905 | MFOH [WAVE] - Add a new template for Student Meal to Custom Report | Story Being Developed | 5 |  |  | Hemanath | [14 empty] | Picked it up at the end of the sprint
15 | FOH | 45772 | 45785 | 4.22 - Sprint 1 Stretch | Arvinth | 47547 | MFOH - MSB Reconciliation (Batch Summary Report) | Story Being Developed | 8 |  | 6 | [15 empty] | Picked it up at the end of the sprint
16 | FOH | 45772 | 45785 | 4.22 - Sprint 1 | Sabir Shaikh | 47904 | MFOH [WAVE] Add a new template for A La Carte to Custom Report | Story Being Developed | 5 | 5 | 24 | sabir
1 | FOH | 45786 | 45799 | 4.22 - Sprint 2 | Hemanath Jayaraman/Subbulakshmi | 47905 | MFOH [WAVE] - Add a new template for Student Meal to Custom Report | Story Completed | 8 | 7.75 | 31 | Hemanath | Sabir | NA | Sabir | NA | 42272 | 45796 |  | Subha | NA |  |  |  | NA |  | The release was put on hold by client so a draft PR was created.
2 | FOH | 45786 | 45799 | 4.22 - Sprint 2 | Sabir Shaikh/Subbulakshmi | 48229 | 48229 - [WAVE] Mosaic FOH - Admin View of Real Time Transactions Modifications | Story Completed | 3 | 4.5 | 18 | Sabir | Hemanath | NA | Hemanath
3 | FOH | 45786 | 45799 | 4.22 - Sprint 2 | Vidhya/Subbulakshmi | 47904 | MFOH [WAVE] - Add a new template for A La Carte to Custom Report | Story Completed | 3 | 4 | 16 | Vidhya | Ashwin | Grand Total should not come if there is only one school in the report | Ashwin | Nil | 42270 | 45796 |  | Subha | Nil |  |  |  | Alignments and Spacing should be ensured |  | Drafted PR
4 | FOH | 45786 | 45799 | 4.22 - Sprint 2 | Vidhya/Subbulakshmi | 47909 | MFOH [WAVE] - Add a new template for Student Listing to Custom Report | Story Completed | 8 | 7.5 | 29.5 | Vidhya | Hemanath | Nil | Hemanath | Nil | 42334 | 45799 |  | Subha | Nil |  |  |  | Alignments and Spacing should be ensured |  | Drafted PR
5 | FOH Wave | Current Sprint Sheet | 26.1 - Sprint 3-Status | 4.22 - Sprint 2 Stretch | Hemanath Jayaraman | 47907 | MFOH [WAVE] - Add a new template for Menu Products Sold to Custom Report | Story Being Developed | 13 |  | 10 | [15 empty] | Picked it up at the end of the sprint.
7 | FOH | 45786 | 45799 | 4.22 - Sprint 2 Stretch | Sabir Shaikh | 47906 | MFOH [WAVE] - Add a new template for Eligibility Record Listing to Custom Report | Story Being Developed | 5 | 6.75 | 27 | Sabir | Hemanath | Found one bug.Resolved it. | [12 empty] | Carry forward to next sprint
8 | FOH | 45786 | 45799 | 4.22 - Sprint 2 Stretch | Subblakshmi | 48192 | MFOH Automation | Story Being Developed | 5 | 3 | 15 | [15 empty] | Carry forward to next sprint
1 | FOH | 45800 | 45813 | 4.22 - Sprint 3 Stretch | Hemanath Jayaraman/Subblakshmi | 47907 | MFOH [WAVE] - Add a new template for Menu Products Sold to Custom Report | Story Completed | 13 | 11.75 | 47 | [15 empty] | Story development got delayed due to the following reasons 1. Its a complex story and got a technical blocker during development 2. Planned PTOs
2 | FOH | 45800 | 45813 | 4.22 - Sprint 3 Stretch | Subblakshmi | 48192 | MFOH Automation | Story Being Developed | 2 | 1 | 8 | [15 empty] | Story development got delayed due to the following reasons 1. Its a complex story and got a technical blocker during development 2. Planned PTOs
3 | FOH | 45800 | 45813 | 4.22 - Sprint 3 Stretch | Vidhya/Subbulakshmi | 47773 | MFOH [WAVE] - Supplemental Programs Claims report (group by programs) | Story Completed | 13 | 13 | 52 | [15 empty] | Story development got delayed due to the following reasons 1. Its a complex story and got a technical blocker during development 2. Planned PTOs
4 | FOH | 45800 | 45813 | 4.22 - Sprint 3 Stretch | Sabir Shaikh/Subblakshmi | 47908 | MFOH -[WAVE] - Add a new template for Edit Check to Custom Report | Story Completed | 13 | 12 | 48 | [15 empty] | Story development got delayed due to the following reasons 1. Its a complex story and got a technical blocker during development 2. Planned PTOs
5 | FOH | 45800 | 45813 | 4.22 - Sprint 3 | Sabir Shaikh/Subblakshmi | 47906 | 47906-MFOH [WAVE] - Add a new template for Eligibility Record Listing to Custom Report | Story Completed | 1 | 1 | 4 | Sabir | Hemanath |  |  |  | 42440 | 45805
1 | FOH | 45814 | 45826 | 4.23 - Sprint 1 | Hemanath Jayaraman/subbulakshmi | 47907 | MFOH [WAVE] - Add a new template for Menu Products Sold to Custom Report | Story Completed | 5 | 9 | 36 | Hemanath | Vidhya | Grand total should display if the school has multiple serving lines / serving periods | Vidhya | NA | 42884 | 45825 | 45825 | Subha | NA | Ying Wang | 45825 | NA |  | Yet to Schedule | Faced some technical issues in dev express report development. Did some brain storming with the team to decide the alternate ideas. It took some time to try and decide which solution is working fine.It took some additional time to complete it due to the technical challenges faced during implementation/migration
2 | FOH | 45814 | 45826 | 4.23 - Sprint 1 | Vidhya/subbulakshmi | 47773 | [WAVE] -Mosaic-FOH- Supplemental Programs Claims report (group by programs) | Story Completed | 3 | 6 | 24 | Vidhya | Subbulakshmi |  | Arvinth | For enrolled school ADP is showing as 0 | 42843 | 45821 | 45821 |  |  |  | 45821 |  |  |  | Scope of the story got extended that requires additional story points to complete.
3 | FOH | 45814 | 45826 | 4.23 - Sprint 1 | Sabir Shaikh/Subbulakshmi | 47908 | MFOH [WAVE] - Add a new template for Edit Check to Custom Report | Story Completed | 2 | 2 | 12 |  | Vidhya |  | Vidhya |  | 42916 | 45820
4 | FOH | 45814 | 45826 | 4.23 - Sprint 1 Stretch | Subblakshmi | 48192 | MFOH Automation | Story Being Developed | 2 | 2 | 12
5 | FOH | 45814 | 45826 | 4.23 - Sprint 1 Stretch | Sabir Shaikh | 48640 | 48640-[WAVE] Mosaic -FOH Change ServingPeriodProgram "AfterSchool Snack" to "AfterschoolSnack (NSLP)" | Story Being Developed | 1 | 1 | 6 |  |  |  | Alpha |  | 42914
6 | FOH | 45814 | 45826 | 4.23 - Sprint 1 Stretch | Vidhya | 48015 | [WAVE] -Mosaic-FOH-Supplemental Programs Claim report (group by schools) | Story Being Developed | 13 | 4.5 | 18
7 | FOH | 45814 | 45826 | 4.23 - Sprint 1 Stretch | Sabir Shaikh | 48641 | 48641 [WAVE]-Mosaic -FOH Change SPROCS looking for "AfterSchool Snack" to look for "AfterSchoolSnack (NSLP)" | Story Being Developed | 5 | 5 | 30
1 | FOH | 45827 | 45840 | 4.23 - Sprint 2 | Hemanath Jayaraman | 48810 | [WAVE] -Mosaic FOH-Remove HeadStart from SPP droplist | Story Completed | 3 | 3 | 12 | Hemanath | Sabir | NA | Sabir | NA | 43057 | 45835 | 45838 | Subha | 1. Please remove using ID value directly. use name to find and remove the SPP. | Ying | 45838 | None | None | None
2 | FOH | 45827 | 45840 | 4.23 - Sprint 2 | Sabir Shaikh | 48640 | [WAVE] Mosaic -FOH Change ServingPeriodProgram "AfterSchool Snack" to "AfterschoolSnack (NSLP)" | Story Completed | 1 | 1 | 6 | Sabir | Alpha |  | Alpha |  | 42914 | 45826 | 45826 | Subha |  | Ying | 45826 | None | None | None
3 | FOH | 45827 | 45840 | 4.23 - Sprint 2 | Sabir Shaikh | 48641 | [WAVE]-Mosaic -FOH Change SPROCS looking for "AfterSchool Snack" to look for "AfterSchoolSnack (NSLP)" | Story Completed | 3 | 3 | 12 | Sabir | Arvinth |  | Arvinth |  | 43038 | 45832 | 45832 | Subha |  | Ying | 45832 | None | None | None
4 | FOH | 45827 | 45840 | 4.23 - Sprint 2 | Vidhya | 48015 | [WAVE] -Mosaic-FOH-Supplemental Programs Claim report (group by schools) | Story Completed | 8 | 8 | 25 | Vidhya | Alpha |  | Alpha |  | 43075 | 45838 | 45838 | Subha |  | Ying | 45838 | None | None | None
5 | FOH | 45827 | 45840 | 4.23 - Sprint 2 | Subbulakshmi | 48192 | MFOH Automation | Story Completed | 2 | 2 | 8 | [5 empty] | 42975 | 45832 | 45834 | Subha |  | Ying | 45834 | None | None | None
6 | FOH | 45827 | 45840 | 4.23 - Sprint 2 | Hemanath Jayaraman | 48813 | [WAVE] -Mosaic FOH-Remove Supper from SPP droplist | Story Completed | 3 | 3 | 12 | Hemanath | Sabir | NA | Sabir | NA | 43058 | 45835 | 45838 | Subha | NA | Ying | 45838 | None | None | None
7 | FOH | 45827 | 45840 | 4.23 - Sprint 2 Stretch | Sabir Shaikh | 47903 | MFOH [WAVE] - Add a new template for Transaction History to Custom Report | Story Being Developed | 8 | 8 | 48
8 | FOH | 45827 | 45840 | 4.23 - Sprint 2 Stretch | Subbulakshmi | 48862 | MFOH Automation | Story Being Developed | 3 | 1.75 | 7
9 | FOH | 45827 | 45840 | 4.23 - Sprint 2 Stretch | Hemanath Jayaraman | 46542 | MFOH [WAVE] - Modifications to Louisiana SFS-8C Report if a school qualifies for CEP | Story Being Developed | 5 | 1.5 | 6
1 | FOH Wave | 45842 | 45855 | 4.23 - Sprint 3 | Vidhya | 46542 | MFOH [WAVE] - Modifications to Louisiana SFS-8C Report if a school qualifies for CEP | Story Completed | 3 | 3 | 3 | Vidhya | Sabir/Alpha | None | Sabir/Alpha | Correct the version year and typo | 43331 | 45849 | 45849 | Subha | Set Quoted Identifier ON | Ying | 45849 | None | None | None
2 | FOH Wave | 45842 | 45855 | 4.23 - Sprint 3 | Sabir Shaikh | 47903 | MFOH [WAVE] - Add a new template for Transaction History to Custom Report | Story Completed | 2 | 2 | 12 | Sabir | Vidhya | ActiveDate is not showing when select DateType as ActiveDate | Vidhya | None | 43229 | 45846 | 45846 | Subhashri | Remove virtual keyword from method | Ying | 45846 | None | None | None | NA
3 | FOH Wave | 45842 | 45855 | 4.23 - Sprint 3 Stretch | Subhasri | 46537 | [WAVE] Mosaic - POS (Web) - Improvements to MA FP-9 Report (Silver Lake Regional School District) | Story Needs More Info | 3 | 2.5 | 11
4 | FOH Wave | 45842 | 45855 | 4.23 - Sprint 3 | Sabir Shaikh | 48714 | Mosaic FOH - Replace Serving Period with Serving Period Program GUID in Georgia DE0112 | Story Completed | 2 | 2 | 12 | Sabir | Ashwin | None | Ashwin | None | 43228 | 45846 | 45846 | Subhashri | None | Ying | 45846 | None | None | None | NA
5 | FOH Wave | 45842 | 45855 | 4.23 - Sprint 3 | Sabir Shaikh | 48334 | [WAVE] Mosaic FOH - Colorado Claim Export - Replace master serving period with serving period program | Story Completed | 3 | 3 | 18 | Sabir | Ashwin | None | Ashwin | None |  |  |  | Subhashri | None |  |  | None | None | None | Testing is done in feature branch by QA .Yet to create PR
6 | FOH Wave | 45842 | 45855 | 4.23 - Sprint 3 Stretch | Sabir Shaikh | 48411 | MFOH [WAVE] - Custom Report (Navigation) | Story Being Developed | 3 | 3 | 18
7 | FOH Wave | 45842 | 45855 | 4.23 - Sprint 3 Stretch | Hemanath Jayaraman | 25568 | MFOH [WAVE] - Custom and Report Designer should be accessible only by Tier 1 districts | Story Completed | 3 | 2.75 | 11 | Hemanath | Sabir | NA | Sabir | NA | 43376 | 45853 | 45853 | Subhashri | NA | Ying | 45853 | NA | NA | NA
8 | FOH Wave | 45842 | 45855 | 4.23 - Sprint 3 Stretch | Subbulakshmi | 48862 | MFOH Automation | Story Completed | 1 | 1 | 3 | Subbulaxmi | NA | NA | NA | NA | 43275 | 45847 | 45847 | NA | NA | Ying | 45847 | NA | NA | NA
1 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 | Sabir Shaikh | 48411 | MFOH [WAVE] - Custom Report (Navigation) | Story Completed | 1 | 1 | 4 | 45859 | 45859 | Sabir | Hemanath | None | Hemanath | None | 43472 | 45856 | 45856 | Subhashri | None | Ying | 45856 | None | NA
2 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 | Hemanath Jayaraman | 49267 | [WAVE]Mosaic - FOH 4.23(Regression) - Setup | Story Completed | 2 | 2 | 23 | 45860 | 45863 | Hemanath | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 | Vidhya | 49266 | [WAVE]Mosaic - FOH 4.23(Regression) - Utilities | Story Completed | 3 | 3 | 27 | 45860 | 45864 | Vidhya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 | Sabir Shaikh/Subbulakshmi | 49263 | [WAVE] Mosaic - FOH 4.23(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 8 | 8 | 43 | 45860 | 45863 | Sabir/Subbu | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 Stretch | Hemanath Jayaraman | 48354 | [WAVE] Mosaic FOH - Tennessee Claim Export - Replace master serving period with serving period program | Story Ready For Testing | 3 | 2.75 | 11 | 45856 | 45859 | Hemanath | Vidhya | NA | Vidhya | NA | NA | NA | NA | Subha | NA | NA | NA | NA | NA
6 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 Stretch | Sabir Shaikh | 48338 | [WAVE] Mosaic FOH - Rhode Island Claim Export - Replace master serving period with serving period program. | Story Ready For Testing | 3 | 2 | 12 | 45856 | 45859 | Sabir | Hemanath | None | Hemanath | NA | NA | NA | NA | Subhashri | change the updateddate in SQL Script | NA | NA | NA | NA
7 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 Stretch | Vidhya | 49176 | MFOH [WAVE] - Analysis on new widgets for Dashboard | Story Being Developed | 0 | 7.75 | 31 | 45856 | 45869 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 Stretch | Subbulakshmi | 49380 | 49380 MFOH [WAVE] - Automation (46542) | Story Completed | 2 | 2 | 8 | 45866 | 45867 | Subbu | NA | NA | NA | NA | 43669 | 45868 | 45868 | Subhashri | NA | YIng | 45868 | NA | NA
9 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 Stretch | Hemanath Jayaraman | 48362 | [WAVE] Mosaic FOH - MARS Claim Export - Replace master serving period with serving period program | Story Need More Info | 3 | 2.25 | 9 | 45866
10 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 Stretch | Sabir Shaikh | 48363 | [WAVE] Mosaic FOH - KY CNIPS Export SSO - Replace master serving period with serving period program | Story Need More Info | 3 | 2 | 10 | 45866
11 | FOH Wave | 45856 | 45869 | 4.23 - Sprint 4 Stretch | Sabir Shaikh | 48336 | [WAVE] Mosaic FOH - NorthCarolina Claim Export - Replace master serving period with serving period program | Story Ready For Testing | 3 | 2 | 10 | 45866 | 45867 | Sabir | Hemanath | NA | Hemanath | NA | NA | NA | NA | Subhashri | change the updateddate in SQL Script | NA | NA | NA | NA
1 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 | Subbulakshmi | 48354 | [WAVE] Mosaic FOH - Tennessee Claim Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | 45870 | 45870 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 | Subbulakshmi | 48338 | [WAVE] Mosaic FOH - Rhode Island Claim Export - Replace master serving period with serving period program. | Story Completed | 1 | 1 | 4 | 45873 | 45874 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 | Subbulakshmi | 48336 | [WAVE] Mosaic FOH - NorthCarolina Claim Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | 45870 | 45873 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 | Hemanath Jayaraman | 49422 | MFOH [WAVE]- Support for Credit Card in Additional Meal Programs (Condensed Daily Sales Summary Report) | Story Completed | 3 | 3 | 12 | 45870 | 45876 | Hemanath | Sabir | NA | Sabir | NA | 43838 | 45876 | 45876 | Subha | 1. Add revision history 2. Change the text lunch box to Mosaic 3. Update the SQL parameter passing syntax. | Ying | 45876 | NA | NA
5 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 | Vidhya | 48991 | MFOH [WAVE] - Support for Credit Card in Additional Meal Programs (Daily Sales by Serving Line Report) | Story Completed | 3 | 9 | 37 | 45870 | 45882 | Vidhya | Arvinth | NA | Arvinth | NA | 43950 | 45882 | 45882 | Subha | Serializable attribute is missing | Ying | 45882 | NA | NA
6 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 | Sabir Shaikh | 49421 | MFOH [WAVE]- Support for Credit Card in Additional Meal Programs (Daily Sales Summary Report) | Story Completed | 3 | 3 | 12 | 45870 | 45876 | Sabir | Hemanath | NA | Hemanath | NA | 43846 | 45876 | 45876 | Subha | 1. Add revision history 2. Change the text lunch box to Mosaic 3. Update the SQL parameter passing syntax. | Ying | 45876 | NA | NA
7 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 Stretch | Subbulakshmi | 49475 | 49475 MFOH [WAVE] - Automation (48015) | Story Completed | 3 | 3 | 12 | 45874 | 45876 | Subbulakshmi | NA | NA | NA | NA | 43842 | 45876 | 45876 | Subha | NA | Ying | 45876 | NA | NA
8 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 Stretch | Sabir Shaikh | 49465 | MFOH [WAVE] - Add a 'Delete' option to delete the User Created Custom Reports | Story Ready For Testing | 3 | 4 | 16 | 45874 | 45877 | Sabir | Hemanath | NA | Hemanath | NA | 43948 | 45882 | 45882 | Subha | 1. Add ReportResultSharedRecipient table in the delete query | Ying | 45882 | NA | NA
9 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 Stretch | Hemanath Jayaraman | 48362 | [WAVE] Mosaic FOH - MARS Claim Export - Replace master serving period with serving period program | Story Being Tested | 3 | 3.5 | 14 | 45877 | 45880 | Hemanath | Sabir | NA | Sabir | NA | NA | NA | NA | Subha | NA | NA | NA | NA | NA
10 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 Stretch | Sabir Shaikh | 49428 | MFOH [WAVE] - Allow the users to view the Dashboard Widgets in an enlarged version | Story Being Developed | 3 | 3 | 12
11 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 Stretch | Hemanath Jayaraman | 49596 | MFOH [WAVE]- Support for Credit Card in Additional Meal Programs (Extended Sales Report) | Story Being Developed | 3 | 3 | 13 | 45880
12 | FOH Wave | 45870 | 45883 | 4.24 - Sprint 1 Stretch | Vidhya | 49176 | MFOH [WAVE] - Duplicating/copying the Dashboard Widgets | Story Being Developed |  | 2.5 | 10
1 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 | Vidhya | 49176 | MFOH [WAVE] - Duplicating/copying the Dashboard Widgets | Story Completed | 3 | 4.5 | 18 | 45887 | 45894 | Vidhya | Alpha | NA | Alpha | NA | 44155 | 45894 | 45894 | Subha | NA | Ying | 45894 | NA | NA
2 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 | Subbulakshmi | 49465 | MFOH [WAVE] - Add a 'Delete' option to delete the User Created Custom Reports | Story Completed | 2 | 2 | 6 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 | Subbulakshmi | 48362 | [WAVE] Mosaic FOH - MARS Claim Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 | Sabir Shaikh | 49428 | MFOH [WAVE] - Allow the users to view the Dashboard Widgets in an enlarged version | Story Completed | 3 | 5 | 20 | 45887 | 45897 | Sabir | Arvinth | NA | Arvinth | NA | 44159 | 45894 | 45894 | Subha | NA | NA | 45894 | NA | NA
5 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 | Hemanath Jayaraman | 49596 | MFOH [WAVE]- Support for Credit Card in Additional Meal Programs (Extended Sales Report) | Story Completed | 1 | 1 | 6 | 45887 | 45888 | Hemanath | Vidhya | Huge amounts getting wrapped up in next line | Vidhya | NA | 44041 | 45888 | 45890 | Subha | NA | Ying | 45890 | NA | NA
6 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 Stretch | Hemanath Jayaraman | 49593 | MFOH [WAVE] - Add a new Data Source 'Daily Sales Summary Report' to Report Designer | Story Completed | 3 | 3 | 11 | 45889 | 45890 | Hemanath | Vidhya | NA | Vidhya | NA | 44093 | 45890 | 45890 | Subha | NA | Ying | 45890 | NA | NA
7 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 Stretch | Subbulakshmi | 49687 | MFOH [WAVE] - Automation (49465) | Story Being Developed | 3 | 1 | 8 | 45889 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
8 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 Stretch | Hemanath Jayaraman | 49594 | MFOH [WAVE] - Add a new template 'Daily Sales Summary' to Custom > Report Templates | Story Being Developed | 8 | 3 | 12 | 45891
9 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 Stretch | Vidhya | 49801 | MFOH [WAVE] - Fix the alignment issues in the Dashboard | Story Being Developed | 5 | 3 | 12 | 45895
10 | FOH Wave | 45884 | 45897 | 4.24 - Sprint 2 Stretch | Sabir Shaikh | 49591 | MFOH [WAVE] - Add a new Data Source 'Daily Sales By Serving Line Report' to Report Designer | Story Being Developed | 3 | 3 | 12 | 45894
1 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 | Vidhya | 49801 | MFOH [WAVE] - Fix the alignment issues in the Dashboard | Story Completed | 5 | 8.5 | 35 | 45898 | 45903 | Vidhya | Hemanath Jayaraman | NA | Hemanath Jayaraman | NA | 44369 | 45904 | 45904 | Subha | NA | Steve | 45904 | NA | 1. Multiple POVs and given suggestions for fixes during the POV. 2. Missed the serving period wrap changes which was the main reason for adding this story. 3. Alignment issues were there during the initial POVs
2 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 | Sabir | 49591 | MFOH [WAVE] - Add a new Data Source 'Daily Sales By Serving Line Report' to Report Designer | Story Completed | 1 | 1 | 4 | 45898 | 45908 | Sabir | Vidhya | NA | Vidhya | Version history is missing | 44315 | 45902 | 45902 | Subha | NA | Steve | 45902 | NA | NA
3 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 | Subbulakshmi | 49687 | MFOH [WAVE] - Automation (49465) | Story Completed | 2 | 2 | 8 | 45897 | 45903 | Subbulakshmi | NA | NA | NA | NA | 44331 | 45903 | 45903 | Subha | NA | Steve | 45903 | NA | NA
4 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 Stretch | Hemanath Jayaraman | 49594 | MFOH [WAVE] - Add a new template 'Daily Sales Summary' to Custom > Report Templates | Story Completed | 8 | 4.5 | 18 | 45898 | 45902 | Hemanath | Sabir | NA | Sabir | NA | 44325 | 45903 | 45903 | Subha | NA | Steve | 45903 | NA | NA
5 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 Stretch | Sabir | 49592 | MFOH [WAVE] - Add a new template 'Daily Sales By Serving Line Report' to Custom > Report Templates | Story Being Developed | 8 | 8 | 32 | 45901
6 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 Stretch | Vidhya | 49923 | MFOH [WAVE] - Make the new improvements to the Dashboard affect the existing Setups (Analysis) | Story Completed |  | 3.5 | 15 | 45904 | 45909 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
7 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 Stretch | Hemanath Jayaraman | 49762 | MFOH [WAVE] - Add 'Participation By' filter to the Standard Claim Report | Story Being Developed | 5 | 7.6 | 30.5 | 45903 |  | Hemanath | [12 empty] | 1. Shown POV exceeding the planned date and after multiple followps 2. Data error and suggested to fix it.
8 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 Stretch | Subbulakshmi | 50001 | MFOH [WAVE] - Automation (49593) | Story Completed | 2 | 2 | 8 | 45910 | 45911 | Subbulakshmi | NA | NA | NA | NA | 44519 | 45911 | 45911 | Subha | NA | Steve | 45911 | NA | NA
9 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 Stretch | Vidhya | 50003 | MFOH [WAVE] - Apply the new improvements to the existing Dashboard Setups | Story Being Developed | 3 | 1.5 | 6 | 45910 | 45911 | Vidhya | Alpha | Getting an exception while copying the widget
8 | FOH Wave | 45898 | 45911 | 4.24 - Sprint 3 Stretch | Subbulakshmi | 50002 | MFOH [WAVE] - Automation (49591) | Story Being Developed | 2 | 0.75 | 5 | 45911 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 | Vidhya | 50003 | MFOH [WAVE] - Apply the new improvements to the existing Dashboard Setups | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 | All | 50032 | [WAVE] Mosaic - FOH 4.24(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 8 | 16 | 65 | 45915 | 45924 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
3 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 | All | 50033 | [WAVE]Mosaic - FOH 4.24(Regression) - Utilities | Story Completed | 3 | 6 | 24 | 45916 | 45924 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
4 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 | All | 50034 | [WAVE]Mosaic - FOH 4.24(Regression) - SetUp | Story Completed | 2 | 10 | 40 | 45918 | 45924 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 | Vidhya | 25981 | MFOH (WAVE) (4.24 Regression) - Multiple extra pages are getting added when there is no data (Daily Sales Summary) | Defect Rejected |  |  |  | 45922 | 45923 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
6 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 | Sabir | 25999 | MFOH [WAVE] (4.24 Regression) - POS Offline Incident Report-Data is not bounding to report even though store procedure returning data. | Defect Fixed |  |  |  | 45923 | 45923 | Sabir | Vidhya | NA | Vidhya | NA | 44764 | 45924 | 45924 | Subha | NA | Ying | 45924 | Nil | NA
7 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 | Vidhya | 25983 | MFOH (4.24 Regression) - When editing the price for each eligibility status in the meal price template, got a console error and couldn't change the pr | Defect Fixed |  |  |  | 45924 | 45924 | Vidhya | Sabir | NA | Sabir | NA | 44759 | 45924 | 45924 | Subha | NA | Ying | 45924 | Nil | NA
8 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 Stretch | Subbulakshmi | 50182 | MFOH [WAVE] - Automation (49176) | Story Being Developed | 5 | 2 | 12 | 45923 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
9 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 Stretch | Hemanath Jayaraman | 49762 | MFOH [WAVE] - Add 'Participation By' filter to the Standard Claim Report | Story Being Developed | 3 | 6.25 | 25 | 45912 |  | Hemanath | Alpha | The ADP percentage is not matching with sales overview report for one school alone. | Alpha
10 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 Stretch | Sabir | 49592 | MFOH [WAVE] - Add a new template 'Daily Sales By Serving Line Report' to Custom > Report Templates | Story Being Developed | 2 | 2 | 6 | 45912 |  | Sabir | Vidhya | 1. Could not open the template in Report Designer. 2. Increase the space between 'Taxable Total' and 'Total Tax Collected' | Vidhya | NA
11 | FOH Wave | 45912 | 45925 | 4.24 - Sprint 4 Stretch | Subbulakshmi | 50002 | MFOH [WAVE] - Automation (49591) | Story Completed | 1 | 1 | 4 | 45911 | 45912 | Subbulakshmi | NA | NA | NA | NA | 44541 | 45912 | 45912 | Subha | NA | Steve | 45912 | NA | NA
1 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 | Hemanath Jayaraman | 49762 | MFOH [WAVE] - Add 'Participation By' filter to the Standard Claim Report | Story Completed | 2 | 2.25 | 9 | 45926 | 45929 | Hemanath | Alpha | NA | Alpha | NA | 44885 | 45930 | 45930 | Subhasri | 1.This is not needed in DirectorServiceClient.cs. 2. In a few pages, the revision history is still 4.24; change it to 4.25. | Steve | 45930 | NA | This story was taken for development on 9/3. POV was done twice since the development didn't meet the expected criteria during first time of POV. 2nd POV date was 9/29. Totally 63.5 hours logged in the story for development.
2 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 | Sabir Shaikh | 49592 | MFOH [WAVE] - Add a new template 'Daily Sales By Serving Line Report' to Custom > Report Templates | Story Completed | 1 | 1 | 4 | 45926 | 45926 | Sabir | Vidhya | 1.Page number format not matching with existing report. 2. increase the space between these two fields | Vidhya | Unnecessary empty lines are added. Please remove it | 44873 | 45929 | 45929 | Subhasri | NA | Steve | 45929 | NA | NA
3 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 | Sabir Shaikh | 49989 | [WAVE] Mosaic FOH- Addition of Serving Period Program to Reimbursement Rate screen | Story Need More Info | 3 | 2 | 8 | 45926 | 45926 | Sabir | Vidhya | NA | Vidhya | NA | 44911 | 45930 | 45930 | Subhasri | NA | Steve | 45930 | NA | NA
4 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 | Vidhya | 49997 | [WAVE] Mosaic FOH- Site level settings for SFSP Site Type | Story Completed | 3 | 3 | 12 | 45926 | 45929 | Vidhya | Hemanath | NA | Hemanath | NA | 44872 | 45929 | 45929 | Subhasri | NA | Steve | 45929 | NA | NA
5 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 | Hemanath Jayaraman | 49992 | [WAVE]- Mosaic FOH- Reimbursable Program field in Serving Period Maintenance | Story Completed | 1 | 1 | 4 | 45926 | 45929 | Hemanath | Sabir | NA | Sabir | NA | 44899 | 45930 | 45930 | Subhasri | NA | Steve | 45930 | NA | The story was partially developed. Had suggested comments during POV for changing the label in the serving period search grid since it was missing. Its a simple change but didn't meet the expectation during the POV.
6 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 | Vidhya | 50214 | MFOH - Modifications to Rhode Island Claim Export (Operating Days) | Story Completed | 2 | 2 | 8 | 45929 | 45930 | Vidhya | Sabir | NA | Arvinth | NA | 44945 | 45933 | 45933 | NA | NA | Steve | 45933 | NA | NA
7 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 | Sabir Shaikh | 50212 | MFOH - Modifications to Colorado Claim Export (Operating Days) | Story Completed | 2 | 2 | 8 | 45929 | 45930 | Sabir | Hemanath | NA | Hemanath | NA | 44950 | 45933 | 45933 | Subhasri | NA | Steve | 45933 | NA | POV was seen on Sep 30. The data wasn't entered and was unable to show the POV for the changes. Hence, asked to work on the data and show the pov once again. 2nd POV date Oct 3.
8 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 | Hemanath Jayaraman | 50215 | MFOH - Modifications to Tennessee Claim Export (Operating Days) | Story Completed | 2 | 1.8 | 7.5 | 45930 | 45933 | Hemanath | Vidhya | NA | Vidhya | NA | 44967 | 45936 | 45936 | Subhasri | NA | Steve | 45936 | NA | NA
9 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 Stretch | Subbulakshmi | 50182 | MFOH [WAVE] - Automation (49176) | Story Being Developed | 3 | 2 | 4 | 45923 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 Stretch | Vidhya | 49952 | MFOH [WAVE] - Add a Numerical Widget for MPLH | Story Being Developed | 5 | 5 | 20 | 45933 |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 Stretch | Sabir Shaikh | 48340 | [WAVE] Mosaic FOH - Wisconsin Claim Export - Replace master serving period with serving period program | Story Being Developed | 3 | 3 | 12 | 45933 | 45940 | Sabir | Hemanath | NA | NA | NA | 45065 | 45940 | 45940 | Subhasri | NA | Steve | 45940 | NA | NA
12 | FOH Wave | 45926 | 45939 | 4.25 - Sprint 1 Stretch | Hemanath Jayaraman | 50315 | MFOH [WAVE] - Add 'Participation By' filter to the Supplemental Programs Claim Report | Story Being Developed | 5 | 4 | 15.5 | 45936 | 45938 | Hemanath | Sabir | NA | Sabir | NA | 45064 | 45940 | 45940 | Subhasri | NA | Steve | 45940 | NA | POV date: 10/9/2025. The display parameter was not in the expected position after multiple discussions before POV and it looks wierd. Asked to fix it.
1 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 | Subbulakshmi | 50315 | MFOH [WAVE] - Add 'Participation By' filter to the Supplemental Programs Claim Report | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
2 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 | Subbulakshmi | 50182 | MFOH [WAVE] - Automation (49176) | Story Completed | 2 | 2 | 8 | 45940 | 45952 | Subbulakshmi | NA | NA | NA | NA | 45242 | 45952 | 45952 | Subha | NA | NA | 45952 | NA | NA
3 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 | Vidhya | 49952 | MFOH [WAVE] - Add a Numerical Widget for MPLH | Story Completed | 3 | 3 | 12 | 45940 | 45943 | Vidhya | Alpha | NA | Alpha | NA | 45123 | 45944 | 45944 | Subha | NA | Steve | 45944 | NA | POV Comment: 1. The handling for the exception when the labor hour is 0 was missing and hence throwed an error.
4 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 | Subbulakshmi | 48340 | [WAVE] Mosaic FOH - Wisconsin Claim Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 | Vidhya | 49953 | MFOH [WAVE] - Add a Numerical Widget for ADP% | Story Completed | 8 | 9 | 38 | 45944 | 45953 | Vidhya | Hemanath | ADP values not matching | Hemanath | NA | 45249 | 45952 | 45952 | Subha | NA | Steve | 45952 | NA | 1. Missing % symbol inside the widget and copied widget. 2. Widget value doesn't match with the standard claim report value for the school group selection.
5 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 Stretch | Sabir Shaikh | 50406 | MFOH - Modify Custom Student Report to meet Mosaic Standard | Story Completed | 3 | 4 | 16 | 45940 | 45946 | Sabir | Hemanath | 1.School Name is showing in Page Header 2. Decrease the space of right side of the page | Hemanath | NA | 45195 | 45947 | 45947 | Subha | NA | NA | 45947 | NA | POV Comment: 1. The color coding was missing for the rows. 2. The vertical and horizontal lines were missing.
6 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 Stretch | Hemanath Jayaraman | 50407 | FOH - Modify Student Attendance Import Results Report to meet Mosaic Standard | Story Completed | 3 | 3 | 12 | 45940 | 45945 | Hemanath | Vidhya | NA | Vidhya | NA | 45144 | 45945 | 45945 | Subha | NA | Steve | 45945 | NA | POV Comment: 1. The column headers were misplaced and it affected the understanding of the report.
7 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 Stretch | Hemanath Jayaraman | 43944 | MFOH - Modify the 'User Assignments Report' to meet Mosaic Standard | Story Being Developed | 3 | 3 | 12 | 45946 | 45952 | Hemanath | Sabir | If no parameters selected, then display parameters showing with empty borders | Sabir | NA | [8 empty] | NA
8 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 Stretch | Sabir Shaikh | 50453 | MFOH - Modify the 'Kershaw Condensed Daily Sales Summary' to meet Mosaic Standard | Story Ready For Testing | 3 | 2 | 8 | 45946 | 45953 | Sabir | Hemanath | Page Footer Line is missing | Hemanath | NA | 45263 | 45953 | 45953 | Subha | NA | Steve | 45953 | NA | NA
9 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 Stretch | Hemanath Jayaraman | 48361 | [WAVE] Mosaic FOH - KY CNIPS Export NSLP - Replace master serving period with serving period program | Story Being Developed | 3 | 1.25 | 5 | 45952
10 | FOH Wave | 45940 | 45953 | 4.25 - Sprint 2 Stretch | Sabir Shaikh | 48337 | [WAVE] Mosaic FOH - North Carolina SFS4 Export - Replace master serving period with serving period program | Story Being Developed | 3 | 2 | 8 | 45951
1 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 | Hemanath Jayaraman | 43944 | MFOH - Modify the 'User Assignments Report' to meet Mosaic Standard | Story Completed | 1 | 1.5 | 6 | 45954 | 45954 | Hemanath | Sabir | None | Sabir | None | 45293 | 45957 | 45957 | Subha | None | Steve | 45957 | None | None
2 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 | Hemanath Jayaraman | 48361 | [WAVE] Mosaic FOH - KY CNIPS Export NSLP - Replace master serving period with serving period program | Story Completed | 2 | 2.5 | 10 | 45957 | 45958 | Hemanath | Sabir | None | Sabir | None | NA | NA | NA | Subha | None | NA | NA | None | POV Comment: 1. The story was developed incorrectly. 2. The story development didn't meet any of the expectation.
3 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 | Sabir Shaikh | 48339 | [WAVE] Mosaic FOH - CNPWeb Export - Replace master serving period with serving period program | Story Completed | 3 | 2 | 8 | 45954 | 45957 | Sabir | Vidhya | None | Vidhya | None | NA | NA | NA | Subha | None | NA | NA | None | NA
4 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 | Vidhya | 50500 | MFOH[WAVE]- FOH-Legacy Imports to be moved to Utilities System setup | Story Completed | 3 | 3 | 12 | 45954 | 45957 | Vidhya | Hemanath | None | Hemanath | None | 45338 | 45958 | 45958 | Subha | None | Steve | 45958 | None | None
5 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Subbulakshmi | 50553 | MFOH [WAVE] - Automation | Story Being Developed | 2 | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None | None
6 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 | Sabir Shaikh | 48282 | [WAVE] Mosaic FOH - OR Est Reimb Due Report - Replace master serving period with serving period program | Story Completed | 3 | 2 | 8 | 45957 | 45958 | Sabir | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | None | NA | NA | None | None
7 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Vidhya | 50548 | MFOH [WAVE] - Copied widgets have issues when enlarged (Dashboard) | Story Completed | 5 | 6.5 | 26 | 45958 | 45965 | Vidhya | Hemanath | None | Hemanath | None | 45473 | 45965 | 45965 | Subha | None | Steve | 45965 | None | POV Comment: 1. Mismatch of data between the Standard claim and the ADP % single value widget.
8 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Hemanath Jayaraman | 50440 | MFOH [WAVE] - Export the format of the 'User Created Custom Reports' | Story Completed | 5 | 6.5 | 26 | 45958 | 45965 | Hemanath | Vidhya | None | Vidhya | None | 45475 | 45965 | 45965 | Subha | None | Steve | 45965 | None | None
9 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Sabir Shaikh | 50441 | MFOH [WAVE] - Import the format of the Custom Report | Product Owner - Verify | 5 | 5 | 20 | 45959 | 45965 | Sabir | Vidhya | check repotname exist condition with space and without space | Vidhya | NA |  |  |  | Subha | NA |  |  |  | POV Comment: 1. The story didn't meet any of the ACs given for the UI elements. 2. In the second POV, the validation for the xml file (custom report vs some other random files) wasn't set. 3. The import and cancel button arrangement is incorrect
10 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Hemanath Jayaraman | 48360 | [WAVE] Mosaic FOH - Meals Per Labor Hour Report - Replace master serving period with serving period program | Story Need More Info | 3 | 2 | 10 | 45966
11 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Vidhya | 50712 | MFOH [WAVE] - Rename 'Serving Period Program' to Reimbursable Program | Story Being Developed | 2 | 2 | 8 | 45966 | 45967 | Vidhya | Hemanath | None | Hemanath | None |  |  |  | Subha | None |  |  |  | None
12 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Sabir Shaikh | 48333 | [WAVE] Mosaic FOH - Kentucky D3 Report - Replace master serving period with serving period program | Story Need More Info | 3 | 1 | 4 | 45966
13 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Sabir Shaikh | 50722 | MFOH [WAVE] - Add a new Data Source 'Standard Claim' to Report Designer | Story Being Developed | 3 | 1 | 4 | 45967
14 | FOH Wave | 45954 | 45967 | 4.25 - Sprint 3 Stretch | Sabir Shaikh | 48337 | [WAVE] Mosaic FOH - North Carolina SFS4 Export - Replace master serving period with serving period program | Story Completed | 1 | 1 | 4 | 45967 | 45967 | Sabir | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | None | NA | NA | None | NA
1 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 | Vidhya | 50731 | MFOH [WAVE] - Add NSS ID to Visual Report (CPS) | Story Completed | 2 | 1.5 | 6 | 45968 | 45968 | Vidhya | Sabir | None | Sabir | None | 45692 | 45974 | 45974 | Subha | Change the procedure name properly and check in | Steve | 45974 | None | None
2 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 | Sabir | 50722 | MFOH [WAVE] - Add a new Data Source 'Standard Claim' to Report Designer | Story Completed | 3 | 2 | 8 | 45968 | 45972 | sabir | Vidhya | NA | Vidhya | NA | 45648 | 45972 | 45972 | Subha | None | NA | 45972 | NA | POV Date: 11/11/25 1. Additional unrelated UI parameters were added to the report UI.
3 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 | Sabir | 50441 | MFOH [WAVE] - Import the format of the Custom Report | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45649 | 45972 | 45972 | Subha | 1.This class doesn’t have a serialize annotation 2.Change the method Name to IsCustomReportNameExists 3.Check the spelling in the method name. Also, change the method name to IsCustomReportNameExists. 4.Change the method name to IsFilePathExists | NA | 45972 | NA | NA
4 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 | Vidhya | 50712 | MFOH [WAVE] - Rename 'Serving Period Program' to Reimbursable Program | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45556 | 45968 | 45968 | NA | NA | Steve | 45968 | None | NA
5 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 | Hemanath Jayaraman | 50749 | MFOH [WAVE] - Add a Scheduler Task Step for the IL WINS Export (CPS C0101) | Story Completed | 3 | 5 | 20 | 45968 | 45975 | Hemanath | Vidhya | None | Vidhya | None | 45693 | 45974 | 45975 | Subhasri | 1.You don't need any change in the SP - ILWINSExport.sql for adding a scheduler step. Please revert that change and look for an example - Alachua Meal Count Export. 2.Don't hardcode the filename in the scheduler. Use the model value using substring. | Steve | 45975 | I don't think this is the correct way to handle this. The School Group should be a scheduler task parameter. Please reach out to Jagan and Gary about this | None
6 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Sabir | 50721 | MFOH [WAVE] - Add a new template for Standard Claim to Custom Report | Product Owner - Verify | 5 | 4 | 16 | 45971 | 45978 | Sabir | Vidhya | 1. The selected school name is not appearing in the report 2. Number Formating is missing 3. Font size not match with for label 'Total Reimbursement Due' | Vidhya | None | NA | NA | NA | Subhasri | 1. You're adding report parameters in the xtrareportrunner. But report parameters lines removed for standardClaimreport if condition. Why this change is required then? | NA | NA | None | None
7 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Vidhya | 50728 | MFOH [WAVE] - Modify the Missing Sales Data Report to include the Sub-Site (CPS C0209) | Product Owner - Verify | 5 | 4.5 | 18 | 45971 | 45974 | Vidhya | Hemanath | None | Hemanath | 1. In MissingSalesDataReport.Sql - Please fix the indentation and set quoted identifier like the old one on the left, please refer the screen below 2. In MissingSalesDataReport.cshtml - Is there any specific reason why the first school is loaded in the document ready below | NA | NA | NA | Subha | None | NA | NA | NA | POV Date: 11/12/25 1. The report doesn't meet the standard format requirements.
8 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Subbulakshmi | 50553 | MFOH [WAVE] - Automation | Story Completed | 2 | 2 | 8 | 45971 | 45980 | NA | NA | NA | NA | NA | 45823 | 45980 | 45980 | Subha | None | Steve | 45980 | None | None
9 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Hemanath Jayaraman | 48356 | [WAVE] Mosaic FOH - Standard Claim Report- Replace master serving period with serving period program | Product Owner - Verify | 5 | 3.75 | 15 | 45974 | 45979 | Hemanath | Sabir | None | Sabir | None | NA | NA | NA | Subhasri | None | NA | NA | NA | None
10 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Vidhya | 50850 | MFOH [WAVE] - Add an indication when the filters are applied in the Visual Report | Product Owner - Verify | 3 | 3 | 12 | 45974 | 45979 | Vidhya | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | 1. Suggeated to change the method name to isDefaultFiltersSelected 2. Correct the typo for "default" | NA | NA | NA | None
11 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Sabir | 50851 | MFOH [WAVE] - Add a new Data Source 'Extended Daily Sales Summary Report' to Report Designer | Product Owner - Verify | 3 | 1.5 | 6 | 45978 | 45979 | Sabir | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | this should be always [axof:<Space><story ID> ] | NA | NA | NA | NA
12 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Vidhya | 50852 | MFOH [WAVE] - Add a new Data Source 'Extended Sales Report' to Report Designer | Story Being Developed | 3 | 3 | 12 | 45979 | 45980 | Vidhya | Hemanath | None | Hemanath | None | NA | NA | NA | Subha | Should be always [axof:<Space><story ID> ] | NA | NA | NA | None
13 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Sabir | 50855 | MFOH [WAVE] - Add a new template 'Extended Daily Sales Summary Report' to Custom > Report Templates | Story Being Developed | 5 | 2.5 | 10 | 45979 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
14 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Hemanath Jayaraman | 50853 | MFOH [WAVE] - Add a new Data Source 'Revenue Report' to Report Designer | Product Owner - Verify | 3 | 1.75 | 7 | 45979 | 45980 | Hemanath | Vidhya | None | Vidhya | None | NA | NA | NA | Subhasri | 1.Change it to display the entire report name as Name in the script. We must always consider the User's point of view. Displaying single word is not consistent in the application. | NA | NA | NA | None
15 | FOH Wave | 45968 | 45981 | 4.25 - Sprint 4 Stretch | Subbulakshmi | 50930 | MFOH [WAVE] - Automation (50722) | Story Being Developed | 2 | 1 | 4 | 45980 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
1 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Vidhya | 50850 | MFOH [WAVE] - Add an indication when the filters are applied in the Visual Report | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45868 | 45982 | 45982 | NA | NA | Steve | 45982 | None | NA
2 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Sabir | 50851 | MFOH [WAVE] - Add a new Data Source 'Extended Daily Sales Summary Report' to Report Designer | Story Completed | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 45875 | 45982 | 45982 | NA | NA | Steve | 45982 | None | NA
3 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Vidhya | 50852 | MFOH [WAVE] - Add a new Data Source 'Extended Sales Report' to Report Designer | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45867 | 45982 | 45982 | NA | NA | Steve | 45982 | None | NA
4 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Sabir | 50855 | MFOH [WAVE] - Add a new template 'Extended Daily Sales Summary Report' to Custom > Report Templates | Story Completed | 3 | 2.5 | 10 | 45982 | 45985 | Sabir | Vidhya | None | Vidhya | None | 45989 | 45992 | 45992 | Subha | rename the script file name | Ying | 45992 | None | None
5 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Hemanath Jayaraman | 50853 | MFOH [WAVE] - Add a new Data Source 'Revenue Report' to Report Designer | Story Completed | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 45870 | 45982 | 45982 | NA | NA | Steve | 45982 | None | NA
6 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Subbulakshmi | 50930 | MFOH [WAVE] - Automation (50722) | Story Completed | 1 | 1 | 4 | 45980 | 45982 | Subbulakshmi | NA | NA | NA | NA | 45879 | 45982 | 45982 | Subha | NA | Ying | 45982 | None | NA
7 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Vidhya | 50728 | MFOH [WAVE] - Modify the Missing Sales Data Report to include the Sub-Site (CPS C0209) | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | NA | 45869 | 45982 | 45982 | NA | NA | Steve | 45982 | None | NA
8 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Sabir | 50721 | MFOH [WAVE] - Add a new template for Standard Claim to Custom Report | Story Completed | 1 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 45872 | 45982 | 45982 | NA | NA | Steve | 45982 | None | NA
9 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Vidhya / Sabir/Hemanath | 50954 | [WAVE] Mosaic - FOH 4.25(Regression) - Reports - (Excluding Free/Reduced) | Story Completed | 8 | 28 | 112 | 45994 | 46008 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
10 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Vidhya / Hemanath | 50956 | [WAVE]Mosaic - FOH 4.25(Regression) - Setup | Story Completed | 2 | 7 | 31 | 45999 | 46008 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
11 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Sabir | 50955 | [WAVE]Mosaic - FOH 4.25(Regression) - Utilities | Story Completed | 3 | 4.5 | 19 | 45999 | 46009 | Sabir | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
12 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Hemanath Jayaraman | 26441 | MFOH (4.25 Regression) - Credit Card Listing Report order by filter is not working | Defect Fixed | 0 | 0 | 0 | 46001 | 46002 | Hemanath | Vidhya | None | Vidhya | None | 46189 | 46003 | 46003 | Subha | None | Ying | 46003 | None | None
13 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Sabir | 26442 | MFOH (4.25 Regression) - Claim month is missing in Standard Claim Report Template | Defect Fixed | 0 | 0 | 0 | 46001 | 46001 | Sabir | Vidhya | None | Vidhya | None | 46199 | 46003 | 46003 | Subha | None | Ying | 46003 | None | None
14 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Sabir | 26444 | MFOH (4.25 Regression) - Mosaic Global Search textbox lists the custom sub report names | Defect Fixed | 0 | 0 | 0 | 46002 | 46002 | Sabir | Hemanath | None | Hemanath | None | 46201 | 46003 | 46003 | Subha | None | Ying | 46003 | None | None
15 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Vidhya | 26443 | MFOH (4.25 Regression) - User Maintenance Screen has a console error | Defect Fixed | 0 | 0 | 0 | 46002 | 46002 | Vidhya | Sabir | None | Sabir | None | 46186 | 46003 | 46003 | Subha | None | Ying | 46003 | None | NA
16 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Vidhya | 26463 | MFOH (4.25 Regression) - Getting an Exception error while generating the Report using Display Type - Word/Word 2003 in Custom Report Templates | Defect Fixed | 0 | 0 | 0 | 46006 | 46006 | Vidhya | Hemanath | None | Hemanath | None | 46244 | 46007 | 46007 | Arvinth | None | Ying | 46007 | None | NA
17 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 | Vidhya | 26464 | MFOH (4.25 Regression) - Alachua Skyward Financial Export success popup is not displayed | Defect Fixed | 0 | 0 | 0 | 46006 | 46006 | Vidhya | Hemanath | None | Hemanath | None | 46241 | 46007 | 46007 | Arvinth | None | Ying | 46007 | None | NA
18 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 Stretch | Hemanath Jayaraman | 51249 | [WAVE] Mosaic FOH - Add "App Switcher" to Feature Flag | Story Being Developed | 1 | 1 | 4 | 46009 | 46009 | Hemanath | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
19 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 Stretch | Hemanath Jayaraman | 50857 | MFOH [WAVE] - Add a new template 'Revenue Report' to Custom > Report Templates | Story Being Tested | 8 | 7 | 29 | 45982 | 45992 | Hemanath | Sabir | None | Sabir | None | 46134 | 46000 | 46000 | Subha | None | Steve | 46000 | None | None
20 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 Stretch | Vidhya | 50856 | MFOH [WAVE] - Add a new template 'Extended Sales Report' to Custom > Report Templates | Story Being Developed | 13 | 13 | 56 | 45985 | 46009 | Vidhya | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
21 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 Stretch | Sabir | 50854 | MFOH [WAVE] - Add a new Data Source 'Total Income Report' to Report Designer | Story Completed | 2 | 1.5 | 6 | 45986 | 45987 | Sabir | Vidhya | None | Vidhya | None | 46145 | 46001 | 46001 | Subha | None | Steve | 46001 | None | POV Comment: The name of the datasource is incorrect and doesn't match the name given in the AC
22 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 Stretch | Sabir | 50858 | MFOH [WAVE] - Add a new template 'Total Income Report' to Custom > Report Templates | Story Completed | 8 | 7 | 27 | 45987 | 45993 | Sabir | Hemanath | None | Hemanath | None | 46146 | 46001 | 46001 | Subha | None | Steve | 46001 | None | None
25 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 Stretch | Hemanath Jayaraman | 51077 | MFOH [WAVE] - Add 'Default Language' to Feature Flag | Story Ready For Testing | 1 | 1 | 4 | 46008 | 46008 | Hemanath | Vidhya | None | Vidhya | None | 46277 | 46008 | 46008 | Subha | None | Ying | 46008 | None | None
23 | FOH Wave | 45982 | 46009 | 4.25 - Sprint 5 Stretch | Subbulakshmi | 51041 | 51041 MFOH [WAVE] - Automation (50851) | Story Completed | 2 | 2 | 8 | 45989 | 45994 | Subbulakshmi | NA | NA | NA | NA | 46042 | 45994 | 45994 | Subha | None | Ying | 45994 | None | NA
1 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Hemanath Jayaraman | 51249 | [WAVE] Mosaic FOH - Add "App Switcher" to Feature Flag | Story Completed | 1 | 1 | 4 | 46009 | 46009 | Hemanath | Vidhya | None | Vidhya | None | 46319 | 46010 | 46010 | Subha | None | Ying | 46010 | None | None
2 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Hemanath Jayaraman | 51110 | MFOH [WAVE] - Add 'Default Language' to the User Maintenance screen | Story Completed | 3 | 2.5 | 10 | 46010 | 46013 | Hemanath | Vidhya | None | Vidhya | None | 46445 | 46028 | 46028 | Subha | We don't need to add extended property for the foreign key, which is needed for new columns or altered columns in the script. Remove that in the script. | Steve | 46028 | None | None
3 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Vidhya | 50856 | MFOH [WAVE] - Add a new template 'Extended Sales Report' to Custom > Report Templates | Story Completed | 1 | 0.5 | 2 | 46010 | 46010 | Vidhya | Hemanath | None | Hemanath | None | 46316 | 46010 | 46010 | Subha | None | Ying | 46010 | None | None
4 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Vidhya | 48154 | MFOH [WAVE] - Add a Language tab to POS Menu Products | Story Completed | 5 | 6 | 24 | 46013 | 46017 | Vidhya | Hemanath | None | Hemanath | None | 46484 | 46029 | 46029 | Subha | 1. Add 1_ and 2_ or the scripts in the order of execution | Steve | 46029 | None | POV Date: 12/26/2025 Pov Comment 1: The POS Display Name field (textbox) inside the add language pop up allows to save the language record only with blank spaces. POV Comment 2: During edit of a menu product, the language tab goes to the second line POV Comment 3: In the Add Language popup, there is a mismatch between the width of the Language and POS Display Name fields.
5 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Subbulakshmi | 50857 | MFOH [WAVE] - Add a new template 'Revenue Report' to Custom > Report Templates | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | None | NA | NA | NA | NA | NA | NA | NA | NA | None
6 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Sabir Shaikh | 51323 | MFOH [WAVE] - Add a Language tab to Void Reasons | Story Completed | 5 | 4 | 16 | 46020 | 46028 | Sabir | Vidhya | None | Vidhya | None | 46627 | 46035 | 46035 | Subhasri | 1.In this story, Mosaic.Web.csproj this file doesn't have any changes. If no changes required then remove this file. | Steve | 46035 | Remove instance of VoidReasonLanguage List in VoidReasonsWCF.cs | POV Date: 01/06/2026 POV Comment 1: There was an error message that shows up during the save of a void reason record (after sorting the column headers in the language tab and try clicking save).
7 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Sabir Shaikh | 51321 | MFOH [WAVE] - Add a Language tab to Medical Alerts | Story Completed | 3 | 2 | 8 | 46029 | 46030 | Sabir | Vidhya | None | Vidhya | None | 46594 | 46034 | 46034 | Subhasri | None | Steve | 46034 | None | None
8 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Subbulakshmi | 51077 | MFOH [WAVE] - Add 'Default Language' to Feature Flag | Story Completed | 1 | 1 | 4 | NA | NA | NA | NA | NA | NA | None | NA | NA | NA | NA | NA | NA | NA | NA | None
9 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Vidhya | 48514 | MFOH [WAVE] - Add a Language tab to Serving Period | Story Completed | 3 | 4.25 | 17 | 46024 | 46027 | Vidhya | Sabir | None | Sabir | None | 46480 | 46029 | 46029 | Subha | 1. Add 1_ and 2_ or the scripts in the order of execution 2. DB length is 50, but why is it restricted to 15 in the UI 3. Wrong date format | Steve | 46029 | None | POV Date: 01/05/2026 POV Comment 1: The font size of the values between the Language droplist and POS Display Name is mismatching.
10 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Vidhya | 51322 | MFOH [WAVE] - Add a Language tab to POS Menu | Story Completed | 3 | 3.75 | 15 | 46028 | 46029 | Vidhya | Ashwin | Getting exception when click OK for the existing languages | Sabir | None | 46562 | 46031 | 46031 | Subha | It doesn’t have any changes, so remove this file. | Steve | 46031 | it's checking for if exits for name POSMenuLanguage, but it creates the table with name ServingLineMenuLanguage. So if you re-run the script it throws an error. | POV Date: 01/07/2026 POV Comment 1: There was an error message that shows up during the save of a POS Menu r record (after sorting the column headers in the language tab and try clicking save).
| FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 | Vidhya | 51156 | MFOH [WAVE] - Add a new System Setting 'Default Language' | Story Completed | 1 | 0.5 | 2 | 46031 | 46031 | Vidhya | Sabir | None | Sabir | None | 46563 | 46031 | 46031 | Subha | None | Steve | 46031 | None | None
11 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Hemanath Jayaraman | 50645 | [WAVE] Mosaic FOH(CPS C0224) - Meal Count Entry Audit Report | Story Completed | 13 | 18.5 | 74 | 46014 | 46035 | Hemanath | Arvinth | 1. If the selected month is current month or future month the data should not show for the future dates. 2.If a date has only non reimbursable meal count, that date should display in the report. 3. If a date has only ala carte or dept. count, that date should display in the report. | Arvinth | In the SPROC , 1.This condition is not required as the future year will not list down in the year dropdown. 2. We don’t need separate query for both NR meal and Alacarte/Dept 3. Add all the school name in actual query, instead of updating it separately. | 46628 | 46035 | 46035 | Subha | 1. A New method is added only for sorting the result set. This can be handled in the .cshtml file 2.Give a clear view of naming conventions for the script files as follows: InsertMealCountEntryAuditReport to Insert_MealCountEntryAudit_Report 3.[dbo].POSTransaction table is used in if NOT exists conditions, which is not recommended, as this will cause performance or screen freeze issues if it is a large district like CPS. Use any alternate way. 4.As discussed already in the catch-up call to use close day summary tables, I don’t see any summary table for the condition 5.I don’t see any query for a serving date that is closed and had 0 meal counts. | Steve | 46035 | None | POV Date: 01/09/2026 POV Comment 1: After performing a close day for a transaction (dated 1/9/26 and Breakfast Serving Period) done through Serving In the Classroom for a school, the report shows that particular school, that serving date, and that serving period in the report POV Comment 2: When the report is run for a school, the school is not showing in the display parameter section Once the above 2 gets fixed, please proceed to peer testing, code review, and PR. Its a basic standard that we follow for the mosaic reports and it will not be mentioned in the AC.
12 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51353 | MFOH [WAVE] - Automation (50851) | Story Completed | 1 | 1 | 4 | 46017 | 46028 | None | NA | NA | NA | None | 46448 | 46028 | 46028 | Subha | None | Steve | 46028 | None | NA
13 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51355 | MFOH [WAVE] - Automation (50854) | Story Completed | 1 | 1 | 4 | 46017 | 46028 | None | NA | NA | NA | None | 46449 | 46028 | 46028 | Subha | None | Steve | 46028 | None | NA
14 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51354 | MFOH [WAVE] - Automation (50853) | Story Completed | 1 | 1 | 4 | 46020 | 46028 | None | NA | NA | NA | None | 46452 | 46028 | 46028 | Subha | None | Steve | 46028 | None | NA
15 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51356 | MFOH [WAVE] - Automation (49952) | Story Completed | 2 | 2 | 8 | 46020 | 46028 | None | NA | NA | NA | None | 46451 | 46028 | 46028 | Subha | Suggested to add the Dashboard Testcases in Regression Test folder | Steve | 46028 | None | NA
16 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Subbulakshmi | 51358 | MFOH [WAVE] - Automation (50441) | Story Being Developed | 3 | 4 | 16 | 46024 | None | None | None | None | None | None | None | None | None | None | Suggested to use string.empty instead of "" | None | None | None | None
17 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Hemanath Jayaraman | 51469 | MFOH - Modify the 'Meal Report' to meet Mosaic Standard | Story Being Developed | 3 | 2 | 8 | 46034
18 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Sabir Shaikh | 51470 | MFOH [WAVE] - Modify the 'User Report' to meet Mosaic Standard | Story Being Developed | 3 | 2 | 8 | 46034 | 46035
19 | FOH Wave | 46010 | 46037 | 26.1 - Sprint 1 Stretch | Vidhya | 51458 | Change common table with category for Serving Period, Menu products, Void Reason, Medical alert (Default Language) | Story Being Developed | 3 | 1.5 | 6 | 46035
1 | FOH Wave | 46038 | 46051 | 26.1 - Sprint 2 | Subbulakshmi | 51358 | MFOH [WAVE] - Automation (50441) | Story Completed | 1 | 0.75 | 3 | 46038 | 46043 | NA | NA | NA | NA | NA | 46772 | 46043 | 46043 | Subha | None | Steve | 46043 | None | None
2 | FOH Wave | 46038 | 46051 | 26.1 - Sprint 2 | Hemanath Jayaraman | 51469 | MFOH - Modify the 'Meal Report' to meet Mosaic Standard | Story Completed | 1 | 3 | 12 | 46038 | 46051 | Hemanath | Sabir | None | Sabir | None | 46737 | 46042 | 46042 | Subha | None | Steve | 46042 | None | None
3 | FOH Wave | 46038 | 46051 | 26.1 - Sprint 2 | Sabir Shaikh | 51470 | MFOH [WAVE] - Modify the 'User Report' to meet Mosaic Standard | Story Completed | 1 | 1 | 4 | 46038 | 46038 | Sabir | Vidhya | None | Vidhya | None | 46739 | 46042 | 46042 | Subha | None | Steve | 46042 | None | None
4 | FOH Wave | 46038 | 46051 | 26.1 - Sprint 2 | Vidhya | 51458 | Change common table with category for Serving Period, Menu products, Void Reason, Medical alert (Default Language) | Story Completed | 1 | 1.75 | 7 | 46038 | 46043 | Vidhya | Hemanath | None | Hemanath | None | 46741 | 46042 | 46042 | Subha | None | Steve | 46042 | None | None
5 | FOH Wave | 46038 | 46051 | 26.1 - Sprint 2 | Subbulakshmi / Hemanath / Sabir / Vidhya | 51125 | [WAVE] Mosaic FOH - Knowledge Transfer from Mosaic BOH Team | Story Completed | 13 | 41.125 | 164.5 | 46036 | 46051 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA