## Dashboard
BOH

## Scorecard
Project Name | BOH
Engagement Model | Relevantz Co Owned
Overall Score | 99.07%
Current Sprint | 26.06 Sprint 2 (15-Apr-2026 to 28-Apr-2026)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% | 3 | 25% | 100%
Velocity | 100% | 20% |  | 20% | 95%
Defect-free Rate | 95.33% | 19.07% |  | 20% | 100%
Code Quality Index | 100% | 15% |  | 15% | 100%
Unit Testing & Code Coverage | 100% | 10% |  | 10% | 90%
Backlog Health | 100% | 10% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
04.11 Sprint 2 (15-Oct-2025 to 28-Oct-2025) | 46 | 48 | 100% | 48 | 100% | 1 | 0 | 2 | 8 | 30 | No |  |  | Completed all the committed stories and 2 from stretch |  |  |  |  | 45 | 45 |  |  | 37
04.11 Sprint 3 (29-Oct-2025 to 11-Nov-2025) | 44 | 51 | 100% | 49.5 | 100% | 1 | 1 | 2 | 10 | 30 | No |  |  | Completed all planned stories and more, 2 defects they couldn't reproduce |  |  |  |  | 45 | 45 |  |  | 37
04.02 Sprint 1 (12-Nov-2025 to 09-Dec-2025) | 36 | 77 | 100% | 58.6667 | 100% | 1 | 0 | 3 | 0 | 30 | No |  |  | Completed all planned stories and worked on stretch stories |  |  |  |  | 45 | 45 |  |  | 37
04.02 Sprint 2 (10-Dec-2025 to 06-Jan-2026) | 69 | 82 | 100% | 64.5 | 100% | 0 | 1 | 3 | 3 | 30 | No |  |  | Completed all planned stories and worked on stretch stories |  |  |  |  | 45 | 45 |  |  | 37
26.01 Sprint 3 (07-Jan-2026 to 20-Jan-2026) | 39 | 41 | 100% | 62.75 | 100% | 0 | 0 | 4 | 0 | 30 | No |  |  | Team worked on the regression stories. 21 existing defects were identified and it has been fixed |  |  |  |  | 45 | 45 |  |  | 37
26.03 Sprint 1 (21-Jan-2026 to 03-Feb-2026) | 45 | 54 | 100% | 63.5 | 100% | 0 | 0 | 3 | 2 | 40 | No |  |  | Completed all planned stories and worked on stretch stories |  |  |  |  | 45 | 45 |  |  | 37
26.03 Sprint 2 (04-Feb-2026 to 17-Feb-2026) | 41 | 47 | 100% | 56 | 100% | 0 | 0 | 0 | 6 | 40 | No | 8 | 10 | 6 existing issues were assigned as tasks. Completed all planned stories and worked on stretch stories |  |  |  |  | 45 | 45 |  |  | 37
26.03 Sprint 3 (18-Feb-2026 to 03-Mar-2026) | 42 | 52 | 100% | 48.5 | 100% | 0 | 0 | 0 | 2 | 40 | No | 4 | 5 | Completed all committed stories |  |  |  |  | 45 | 45 |  |  | 37
26.03 Sprint 4 (04-Mar-2026 to 31-Mar-2026) | 87 | 102 | 100% | 63.75 | 100% | 0 | 0 | 9 | 0 | 40 | No | 14 | 15 | Regression sprint for 4 weeks and successfully completed. These defects were assigned as tasks and fixed in the regression sprint. |  |  |  |  | 45 | 45 |  |  | 37
26.06 Sprint 1 (01-Apr-2026 to 14-Apr-2026) | 35 | 50 | 100% | 62.75 | 100% | 0 | 0 | 1 | 4 | 70 | No | 7 | 7 | Completed all committed stories |  |  |  |  | 45 | 45 |  |  | 37
26.06 Sprint 2 (15-Apr-2026 to 28-Apr-2026) | 53 | 53 | 100% | 64.25 | 100% | 0 | 0 | 1 | 2 | 140 | No | 3 | 3 | Completed all committed stories |  |  |  |  | 45 | 45 |  |  | 37
26.06 Sprint 3 (29-Apr-2026 to 12-May-2026) | 44 | 44 | 100% | 62.25 | 100% | 0 | 0 | 0 | 0 | 140 | Yes | 12 | 12 | Completed all committed stories |  |  |  |  | 45 | 45 |  |  | 37
[19 empty] | 45 | 45 |  |  | 37
[19 empty] | 45 | 45 |  |  | 37

## RCA
3 Why Analysis
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-04-03 | 3.19 - Sprint 1 (21 Feb - 05 Mar ) | Adding Product Groups to vendor orders created from requisition is not working Issue in Prepend "EMP-" to the HSS Users Production Summary Report sorting recipes incorrectly | External | Metric Deviation | Client Identified defects | Missed to identify in unit testing | Assumed will work in test environment with exsisting data. |  | Knowledge share with Team in Stand Up, So that similar type of Defect can be mitigated. | Sathiya | Closed | 2024-04-04 | Issue fixed and committed. | Metric Deviation
2 | 2024-04-16 | 3.19 Sprint 4 (03-Apr to 16-Apr) | Let's change the message to "Quantity cannot be 0." | External | Metric Deviation | Code Review Comments | Missed to check the existing approach method in similar page | Missed code optimization to reduce resource consumption. | Missed in Internal Review | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Krupa | Closed | 2024-04-17 | Comment fixed and committed. | Commitment Deviation
3 | 2024-04-30 | 3.19 Sprint 5 (17-Apr to 30-Apr) | Javascript is case sensitive... should this be ResponsePurchaseUnitWeight? (capital W) | External | Metric Deviation | Code Review Comments |  |  |  |  | Krupa | Closed | 2024-05-03 |  | Security Compliance
4 | 2024-04-30 | 3.19 Sprint 5 (17-Apr to 30-Apr) | One 13 SP carried to next sprint, Client CRC fix is inprogress. | External | Metric Deviation | Commitment Index Deviation | Client code review comment fix is inprogress |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa | Closed | 2024-05-03 |  | Not adhered to Policy
5 | 2024-06-25 | 3.20 Sprint 1 (12-Jun to 25-Jun) | 2 Defects reported by client | External | Metric Deviation | Client Identified defects |  |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Preethi | Closed | 2024-06-26 |  | Others
6 | 2024-07-23 | 3.20 Sprint 2 (26-Jun to 23-Jul) | 1 CRC and 1 defect repoted by client | External | Metric Deviation | Code Review Comments |  |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa | Closed | 2024-07-24
7 | 2024-08-05 | 3.20 Sprint 3 (24-Jul to 6-Aug) | 1 Code Review Comment reported by Client | External | Metric Deviation | Code Review Comments |  |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Charles | Closed | 2024-08-06
8 | 2024-09-03 | 3.20 Sprint 5 (21-Aug to 03-Sep) | 1 Escaped Defects and 1 Client CRC | External | Metric Deviation | Code Review Comments and 1 Escaped Defect | Suggestion - Lowercase "w" in within and capital "L" in Level, please | Minor Existing Issues - Client wants to work on this |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa/Preethi | Closed | 2024-09-03
9 | 2024-09-17 | 3.20 Sprint 6 (04-Sep to 17-Sep) | 2 Escaped Defects | External | Metric Deviation | Escaped Defect | Both the defects are already existing minor issues, clients wants to work in this sprint |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa/Vijay | Closed | 2024-09-17
10 | 2024-10-01 | 3.20 Sprint 7 (18-Sep to 1-Oct) | 1 Escaped Defects | External | Metric Deviation | Escaped Defect | Significant Existing Issues - Client wants to work on this - WRT to Special Character changes |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Vijay/Charles | Closed | 2024-10-01
11 | 2024-10-15 | 3.20 Sprint 8 (2-Oct to 15-Oct) | 1 Internal CRC | Internal | Metric Deviation | Code Review Comments | Few Suggestions: Award Summary button should be disabled if none of the item is selected Suggested a few cosmetic changes |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa | Closed | 2024-10-15
12 | 2024-11-12 | 3.20 Sprint 10 (30-Oct to 12-Nov) | 1 Story was Carry Forwarded | Internal | Metric Deviation | 1 Regression Story was Carry Forwarded because the Regression Story was Switched in Mid Sprint with newly Introduced Story "46412 and 46413", Once the Story was completed the Team picked this Story. | Defects were found, so the Team concentrated on those |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Charles | Closed | 2024-12-11 | The Story is currently in Progress
13 | 2024-12-10 | 3.20 Sprint 11 (13-Nov to 10-Dec) | 1 Story was Carry Forwarded and 2 QA Defect | Internal | Metric Deviation | Story Carry Forwarded and 2 QA Defects | Story Carry Forward The development for story "46525"-Mosaic BOH - Bidding - Add the ability to attach any doc in bid analysis - is completed however the testing and review is incomplete due to hot fix release and one of the hot fix change was affecting the story. Until that is fixed it could not be pushed | 2 QA Defects - were existing issues that were identified and given for release |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is well informed about the QA defects and will make sure the progress/process | Charles/Krupa | Closed | 2025-07-01 | The Story is currently in Progress. Defects were closed
14 | 2025-01-21 | 3.21 Sprint 2 (8-Jan to 21-Jan) | 2 Story was Carry Forwarded and 4 QA Defect | Internal/External | Metric Deviation | 1 Story was Carry Forwarded and 2 QA Defect, 2 Escaped Defects | The development for story was completed on 20/01/2025.However, the offshore tester found one issue so, fixed and pushed the PR on the next day.Also 20/01/2025 was onsite holiday. Ready for Testing. The Story will be tested by Onsite QA | 2 QA Defects - were existing issues which were in Production was identified and fixed - Mnor Issues | 2 Bouncebacks from the story development - It was addressed and closed. One is code issue and the another one is Development was not covered for multi user scenario | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is well informed about the QA defects and will make sure the progress/process | Charles/Krupa/Mohammed | Closed | 2025-01-21 | The Client QA will test the story.
15 | 2025-02-04 | 3.21 Sprint 3 (22-Jan to 4-Feb) | 1 Internal CRC | Internal | Metric Deviation | Code Review Comments | One Logical Comment to change the Code - Remove not mapping table join from stored procedure |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Mohammed | Closed | 2025-02-04
16 | 2025-02-18 | 3.21 Sprint 4 (5-Feb-2025 to 18-Feb-2025) | 3 Internal Defects | Internal/External | Metric Deviation | 3 Internal Defects | Development was not covered in Menus -> PQ Screen Existing production Issue Data issue for regression districts, fixed by charles |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa/Charles | Closed | 2025-02-19
17 | 2025-03-04 | 3.22 Sprint 1 (19-Feb-2025 to 04-March-2025) | 2 Internal Defects and 1 External Defects | Internal/External | Metric Deviation | 1 Bounceback, 1 Internal and 1 External QA | 1 Bounceback -Scenario was not covered as part of development. The Issue was fixed | 1 Internal Defect - Existing issue, missied to handle this scenario as a part of development. Issue is fixed | 1 External Defect - Existing Production Issue - The issue was not Major doesn't affect major feature | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is working on closely in | Charles/Mohammed | Closed | 2025-03-04
18 | 2025-03-18 | 3.22 Sprint 2 (05-Mar-2025 to 18-Mar-2025) | 1 Story Carry Forwarded, 2 CRC, Defect | Internal/External | Metric Deviation | 1 Story Carry Forwarded, 1 Internal CRC, 1 External CRC, 1 Defect | 1 Story Carry Forward - Development In-Progress, Few scenarios completed, have to cover few more scenarios. We completed menus and working on meal viewer sync.Also Unplanned PTO. | 1 Internal CRC - Suggestions - Remove excess space in the dropdown - existing issue Camel case 1 External CRC - Suggestion (Was not in AC) Limit the data field length to 50 chars | 1 Defect (External) - Production Defect Data Issue Potential bad data found when saving production quantities | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is working on closely moving forward to mitigate unplanned leaves. | Rajiv | Closed | 2025-04-01
19 | 2025-04-01 | 3.22 Sprint 3 (19-Mar-2025 to 01-Apr-2025) | Defects and Story carry forwarded | Internal/External | Metric Deviation | 2 Story Carry Forwarded, 3 Internal Defect, 1 External Defect | 2 Story carry forwarded 1. Story moved to testing. Since it has dependency with Mealviewer application, this story can be tested only in QA environment and there are lot to test in both the side and it's in progress. 2. 47441 -[WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Import Suggested Menus Carry over to next sprint due to amount of work and testing involved. Underestimated the effort during planning. | All the defects are Production data and Performance issue. All the defects are fixed |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is working on closely in | Charles/Deepika | Closed | 2025-04-15
20 | 2025-04-15 | 3.22 Sprint 4 (02-Apr-2025 to 15-Apr-2025) | Code Quality Index deviation CRC Peer - 1 CRC Onsite -3 CRC Client - 3 | Internal/External | Metric Deviation | CRC Peer - 1 CRC Onsite -3 CRC Client - 3 | The review comments were because of we missed something during development . Below are the comment we have received: Peer CRC :1 Remove commented codes, excell lines, and unwanted code pushes Onsite: 4 1.Separate Resource file for AI messages 2. Remove commented lines 3. Use Constants for text instead of HardCoded value External:3 1. inherit : BaseController instead of : Controller 2. UI popup at center, 2 option to adopt in same day 3. Filter District in Recipe data |  |  | CRC: Understand and implement AC , Follow coding standards properly | Rajiv/Joel/Deepika | Closed | 2025-04-15
21 | 2025-04-29 | 3.22 Sprint 5 (16-Apr-2025 to 29-Apr-2025) | Code Quality Index deviation | Internal | Metric Deviation | CRC Onsite - 1 | The review comments were because of we missed something during development . Below are the comment we have received: Onsite CRC :1 1. UI Issues | Cosmetic error | Missed to follow the coding standards | CRC: Understand and implement AC , Follow coding standards properly | Deepika | Closed | 2025-05-13
22 | 2025-04-29 | 3.22 Sprint 5 (16-Apr-2025 to 29-Apr-2025) | 2 Story Carry Forwarded | Internal | Metric Deviation | 2 Assigned stories got forward | 47441-Client suggest some UI changes in POV, and the UI fix has some concerns and taken more than estimated time, during the testing fixed the bugs. 47902 - Scope of the story got updated | Scope of the story got updated in the mid of the sprint |  | Team is currently working on that, and this will be prioritized early in the next sprint with better coordination to avoid future delays | Deepika/Rajiv/Joel | Closed | 2025-05-13
23 | 2025-05-13 | 3.22 Sprint 6 (30-Apr-2025 to 13-May-2025) | Defects | Internal | Metric Deviation | UI Issues | The issue was identified during regression testing and was caused by recent changes related to Kendo(Library) version 2025 Q1 Update. | Minor Cosmetic Issues |  | For the Library update Team will do more into Unit testing before give it to the QA | All Members | Closed | 2025-05-13
24 | 2025-05-27 | 3.23 Sprint 1 (14-May-2025 to 27-May-2025) | CRC, Defects | Internal/External | Metric Deviation | UI Issues | The issue was identified during regression testing and was caused by recent changes related to Kendo(Library) version 2025 Q1 Update. | Minor Cosmetic Issues |  | For the Library update Team will Document the unexpected behavior and any error messages and Use debugging tools, logs to reduce the number of UI issues. | All Members | Closed | 2025-05-27
25 | 2025-06-10 | 3.23 Sprint 2 (28-May-2025 to 10-Jun-2025) | CRC | internal/External | Metric Deviation | 1 - InternalCRC 1 - Client CRC |  | Minor Cosmetic Issues and Suggestions |  | For the Library update Team will Document the unexpected behavior and any error messages and Use debugging tools, logs may reduce the number of UI issues. | All Members | Closed | 2025-06-10
26 | 2025-06-24 | 3.23 Sprint 3 (11-Jun-2025 to 24-Jun-2025) | Commitment Deviation, Defects | Internal | Commitment Deviation | 7 - Internal Defects | The issue was identified during regression testing and team fixed the issues. | For Commitment Deviation - Team completed the Development but due to Testing environment unavailability need unable totest the stories. |  | Team focusing on boycot the GCP environment to test. | All Members | Closed | 2025-06-24
27 | 2025-06-24 | 3.23 Sprint 3 (11-June-2025 to 24-June-2025) | 2 assigned Stories got rolled over | Internal | Metric Deviation | Commitment Index Deviation | Remarks: Client is not ready to setup their GCP accounts on the web servers, due to this environment issue, we cannot tested the stories in this sprint, we have re-structured the database and call the AI through scheduler service. Stories: 1 out of 6 committed stories has been completed, 5 committed stories not completed. |  |  |  | All Members | Closed | 2025-07-08
28 | 2025-07-08 | 3.23 Sprint 4 (25-June-2025 to 8-July-2025) | 1 Internal Defects | Internal | Metric Deviation | Defect free Rate | The issue was identified during regression testing and was caused by recent changes related to Kendo version 2025 Q1 Update. It's a kendo default behaviour in recent update and looking for workaround to acheive the same functionality. |  |  |  | All Members | Closed | 2025-07-22
29 | 2025-07-08 | 3.23 Sprint 4 (25-June-2025 to 8-July-2025) | CRC | internal/External | Metric Deviation | 2 - InternalCRC | Minor Cosmetic Issues and Suggestions |  |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | All Members | Closed | 2025-07-08
30 | 2025-07-22 | 3.23 Sprint 5 (9-July-2025 to 22-July-2025) | CRC, Defects | internal/External | Metric Deviation | 2 - InternalCRC Defect free Rate -1 | The issue was identified during regression testing and was caused by recent changes related to Kendo(Library) version 2025 Q1 Update. | Minor Cosmetic Issues and Suggestions |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | All Members | Closed | 2025-08-05
31 | 2025-08-05 | 3.23 Sprint 6 (23-July-2025 to 05-Aug-2025) | Defects | internal/External | Metric Deviation | Defect free Rate -5 | 4 External defects in Production 1 Internal - Missed in the devlopement and internal Testing |  |  | Moving forward, Developers will also do proper Unit testing before pushing this to TST env.These defects will be prioritized early in the next sprint with better coordination to avoid future defects. | All Members | Closed | 2025-08-19
32 | 2025-10-14 | 4.1 Sprint 1 (01-Oct-2025 to 14-Oct-2025) | Defects | External | Metric Deviation |  | External defects in Production |  |  | Existing Production Defects | All Members | Closed | 2025-10-20
33 | 2025-10-14 | 4.1 Sprint 2 (15-Oct-2025 to 29-Oct-2025) | Defects | Internal | Metric Deviation |  | 2 Internal defects and 8 external defects | After the AI Release some issues are found,so created a defect.All these issues are existing in the Production Environment |  | Existing Production Defects | All Members | Closed | 2025-10-20
34 | 2025-11-11 | 4.1 Sprint 3 (29-Oct-2025 to 11-Nov-2025) | Defects | Internal/ External | Metric Deviation |  | 2 Internal defects and 10 external defects | External issues are existing in the Production Environment Internal are Bounce backs |  | Existing Production Defects It was edge case scenario, will try to cover more scenarios future | All Members | Closed | 2025-11-30
35 | 2025-11-11 | 4.1 Sprint 3 (29-Oct-2025 to 11-Nov-2025) | Code review comments | External | Others |  | Costemic change suggestion provided as review comments |  |  | Review the UI prototype with the client before the sprint starts and final the prototype | All Members | Closed | 2025-11-30
36 | 2025-12-10 | 4.2 Sprint 1 (12-Nov-2025 to 9-Dec-2025) | Defects | Internal/ External | Metric Deviation |  | 3 Internal defects | one defect -It's a existing common issue in all muliselect dropdownlist. 2 defects are minor defects related to cosmetic issues |  | Updating the kendo common code to fix. will try to cover more scenarios future | All Members | Closed | 2025-12-15
37 | 2026-01-06 | 4.2 Sprint 2 (10-Dec-2025 to 6-Jan-2026) | Code review comments | External | Others |  | Costemic change suggestion provided as review comments |  |  | RCA : It's a existing common issue in all muliselect dropdownlist Mitigation Plan: Updating the kendo common code to fix | All Members | Closed | 2026-01-06
38 | 2026-01-06 | 4.2 Sprint 2 (10-Dec-2025 to 6-Jan-2026) | Defects | Internal/ External | Others |  | 3 External and 3 Internal defects | 2 External defect were existing prod issue and 1 External defect was minor issue. 3 Internal defects are minor defects related to cosmetic issues |  | RCA: Existing production issues, it was found by internal QA. Due to delivery release deadline, we couldn't fix it on that time, So we fixed it now. Mitigation Plan: Manage the time for fixing the QA issues. Also increase the testing coverage to prevent issues. | All Members | Closed | 2026-01-06
39 | 2026-01-22 | 26.1 Sprint 3 (7-Jan-2026 to 20-Jan-2026) | Defects | Internal | Others |  | 4 Internal defects | 4 Internal defects are existing defects found during the testing |  | RCA: Existing production issues, it was found by internal QA during regression testing. Mitigation Plan: Increase the testing coverage to prevent issues. Also do more regression testing to address these kind of defects | All Members | Closed | 2026-01-20
40 | 2026-02-03 | 26.3 Sprint 1 (21-Jan-2026 to 3-Feb-2026) | Defects | Internal | Others |  | 3 Internal defects | 3 Internal defects are existing defects found during the regression testing |  | RCA: Existing production issues, it was found by internal QA during regression testing. Mitigation Plan: Increase the testing coverage to prevent issues. Also do more regression testing to address these kind of defects | All Members | Closed | 2026-02-04
41 | 2026-02-03 | 26.3 Sprint 1 (21-Jan-2026 to 3-Feb-2026) | Defects | External | Others |  | 2 External defects | 2 External defects are existing defects |  | RCA: Existing production issues, it was addressed in this sprint. These are edge case defects. Mitigation Plan: Edge cases are added to the test plan. It will be covered during the regression testing before release to production | All Members | Closed | 2026-02-04
42 | 2026-02-17 | 26.3 Sprint 2 (4-Feb-2026 to 17-Feb-2026) | Defects | External | Others |  | 6 External defects | 6 External defects are already existing defects and assigned as tasks |  | RCA: Existing production issues related Vega components in UI. Assigned as tasks in this sprint, it was fixed. These are edge case defects. Mitigation Plan: Increase the code coverage and identify the existing defects. It will be covered during the regression testing before release to production | All Members | Closed | 2026-02-17
43 | 2026-03-03 | 26.3 Sprint 3 (17-Feb-2026 to 3-Mar-2026) | Defects | External | Others |  | 2 External defects | 2 External defects are existing defects |  | RCA: Existing production issues, it was assigned as tasks in the current sprint. Mitigation Plan: Edge cases are added to the test plan. It will be covered during the regression testing before release to production | All Members | Closed | 2026-03-03
44 | 2026-03-31 | 26.3 Sprint 4 (4-Mar-2026 to 31-Mar-2026) | Defects | Internal | Others |  | 9 Internal defects | 9 Internal defects are existing defects found during regression testing in the current sprint and fixed all those defects. These defects were not introduced by this BOH team, it was already existing defects in the application Note: The entire sprint has been assigned for regression testing and defect fixing. |  | RCA: Existing issues in the system, it was found during regression testing sprint Mitigation Plan: Edge cases are added to the test plan. It will be covered during the regression testing before release to production During regression testing, the internal defects were found out and fixed to make the application more stable | All Members | Closed | 2026-03-31 | Regression testing sprint for 4 weeks
45 | 2026-04-14 | 26.06 Sprint 1 (01-Apr-2026 to 14-Apr-2026) | Defects | External | Others |  | 4 External defects | 4 external defects found during client QA testing |  | RCA: The recent Kendo update changed the way it pulls the element for error validation. It was found during testing and fixed as a defect. Mitigation Plan: Recent Kendo update changes were added to the test plan. It will be covered during the regression testing before release to production | Charles | Closed | 2026-04-14
46 | 2026-04-14 | 26.06 Sprint 1 (01-Apr-2026 to 14-Apr-2026) | Defects | Internal | Others |  | 1 Internal defect | The defect was related to CSS issue.Found during internal testing. |  | RCA: Minor issue related to CSS found during internal testing. Mitigation plan: Improve the unit testing to address this issue. | Krupa | Closed | 2026-04-14
47 | 2026-04-28 | 26.06 Sprint 2 (15-Apr-2026 to 28-Apr-2026) | Defects | External | Others |  | 2 External defects | 1. Missing Nutrients (N/A) showing as *0* in the totals. 2. Menus - Maintenance & Cycle - Breakfast Menus - Not flagging 2% and Whole milk as being restricted. |  | RCA: Value display and menus fix was found in previous regression testing cycles that has been fixed in this sprint. Mitigation Plan: Increase the code coverage to cover all the edge cases to address these kind of defects in the future. | Kavitha | Closed | 2026-04-28
48 | 2026-04-28 | 26.06 Sprint 2 (15-Apr-2026 to 28-Apr-2026) | Defects | Internal | Others |  | 1 Internal defect | The defect was related to bidding module and found during internal testing. |  | RCA: Minor issue related to bidding module, found during internal testing. Mitigation plan: Improve the unit testing to address this issue. | Deepika | Closed | 2026-04-28

## Instructions
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Config
Sprint | 0 | Relevantz Co Owned | #N/A | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted |  | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | #N/A | #N/A |  | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | #N/A | #N/A |  | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 100% | 20% |  |  |  | CF |  | Excellent |  | 25
Code Quality Index | #N/A | #N/A |  | Velocity
Unit Testing & Code Coverage | #N/A | #N/A |  | Goal | 20
Backlog Health | #N/A | #N/A
Code Coverage
|  |  |  | Goal | 90%
|  |  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  |  | Below Avg | 15 | Labels | Values |  | Story Points | 140
|  |  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  |  | Excellent | 30 | 15 | 10
|  |  |  | Total | 90 | 20 | 10
[6 empty] | 25 | 10
50

## Scorecard (2)
Project Name | BOH
Engagement Model | Relevantz Co Owned
Overall Score | 69.53%
Current Sprint | 3.22 Sprint 6 (30-Apr-2025 to 13-May-2025)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% | 12 | 25% | 100%
Velocity |  | 0% |  | 20% | 95%
Defect-free Rate | 100% | 20% |  | 20% | 100%
Code Quality Index | 96.88% | 14.53% |  | 15% | 100%
Unit Testing & Code Coverage | 100% | 10% |  | 10% | 90%
Backlog Health |  | 0% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data(2025)
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
3.19 Sprint 1 (21-Feb-2024 to 5-Mar-2024) | 23 | 12 | 52.17% | 20 | 90% | 5 | 0 | 2 | 3 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.19 Sprint 2 (6-Mar-2024 to 19-Mar-2024) | 20 | 26 | 100% | 20 | 90% | 3 | 0 | 3 | 4 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.19 - Sprint 3 (20-Mar-2024 to 02-Apr-2024 ) | 30 | 20 | 66.67% | 20 | 90% | 2 | 1 | 2 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.19 Sprint 4 (03-Apr-2024 to 16-Apr-2024) | 21 | 27 | 100% | 20 | 90% | 1 | 1 | 0 | 0 | 30 | No |  |  | Addition to committed stories, completed 3 stretch stories. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.19 Sprint 5 (17-Apr-2024 to 30-Apr-2024) | 28 | 15 | 53.57% | 22 | 90% | 1 | 2 | 0 | 0 | 30 | No |  |  | One 13 SP carried to next sprint, Client CRC fix is inprogress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.19 Sprint 6 (01-May-2024 to 14-May-2024) | 36 | 36 | 100% | 24.5 | 90% | 0 | 1 | 11 | 0 | 30 | No |  |  | All the QA defects are reported Internal during regression testing. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.19 Sprint 7 (15-May-2024 to 28-May-2024) | 30 | 30 | 100% | 27 | 90% | 0 | 0 | 12 | 0 | 30 | No |  |  | All the QA defects are reported Internal during regression testing. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.19 Sprint 8 (29-May-2024 to 11-Jun-2024) | #N/A | 14 | #N/A | 23.75 | 90% | 0 | 0 | 9 | 0 | 30 | No |  |  | All the QA defects are reported Internal during regression testing. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 1 (12-Jun-2024 to 25-Jun-2024) | 18 | 18 | 100% | 24.5 | 90% | 2 | 0 | 6 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 2 (26-Jun-2024 to 23-Jul-2024) | 31 | 31 | 100% | 23.25 | 90% | 0 | 1 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 3 (24-Jul-2024 to 6-Aug-2024) | 25 | 25 | 100% | 22 | 90% | 0 | 1 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 4 (7-Aug-2024 to 20-Aug-2024) | 24 | 24 | 100% | 24.5 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 5 (21-Aug-2024 to 03-Sep-2024) | 17 | 17 | 100% | 24.25 | 90% | 0 | 1 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 6 (04-Sep-2024 to 17-Sep-2024) | 37 | 37 | 100% | 25.75 | 90% | 0 | 0 | 0 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 7 (18-Sep-2024 to 1-Oct-2024) | 8 | 20 | 100% | 24.5 | 100% | 0 | 0 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 8 (2-Oct-2024 to 15-Oct-2024) | 18 | 15 | 83.33% | 22.25 | 100% | 1 | 0 | 0 | 0 | 30 | No |  |  | Development complete,testing is in progress |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 9 (16-Oct-2024 to 29-Oct-2024) | 25 | 30 | 100% | 25.5 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.20 Sprint 10 (30-Oct-2024 to 12-Nov-2024) | 30 | 30 | 100% | 23.75 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | Development Cum Regression Sprint. All the QA defects are reported Internal during regression testing. | [5 empty] | 20
3.20 Sprint 11 (13-Nov-2024 to 10-Dec-2024) | 25 | 20 | 80% | 23.75 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.21 Sprint 1 (11-Dec-2024 to 7-Jan-2025) | 25 | 25 | 100% | 26.25 | 100% | 1 | 0 | 1 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
3.21 Sprint 2 (8-Jan-2025 to 21-Jan-2025) | 20 | 20 | 100% | 23.75 | 100% | 1 | 0 | 2 | 2 | 30 | No | [8 empty] | 20
3.21 Sprint 3 (22-Jan-2025 to 4-Feb-2025) | 15 | 47.25 | 100% | 28.0625 | 90% | 1 | 0 | 0 | 0 | 30 | No | [8 empty] | 20
3.21 Sprint 4 (5-Feb-2025 to 18-Feb-2025) | 16 | 17 | 100% | 27.3125 | 100% | 0 | 0 | 3 | 0 | 30 | No | [8 empty] | 20
3.22 Sprint 1 (19-Feb-2025 to 04-Mar-2025) | 13 | 26 | 100% | 27.5625 | 100% | 0 | 0 | 2 | 1 | 30 | No | [8 empty] | 20
3.22 Sprint 2 (05-Mar-2025 to 18-Mar-2025) | 21 | 38 | 100% | 32.0625 | 75% | 1 | 1 | 0 | 1 | 30 | No | [8 empty] | 20
3.22 Sprint 3 (19-Mar-2025 to 01-Apr-2025) | 32 | 16 | 50% | 24.25 | 75% | 1 | 1 | 0 | 1 | 30 | No | [8 empty] | 20
3.22 Sprint 4 (02-Apr-2025 to 15-Apr-2025) | 32 | 50 | 100% | 32.5 | 85% | 0 | 0 | 3 | 1 | 30 | No | [8 empty] | 20
3.22 Sprint 5 (16-Apr-2025 to 29-Apr-2025) | 37 | 34 | 91.89% | 34.5 | 90% | 4 | 3 | 0 | 0 | 30 | No |  |  | 1. Four Stretch Stories have been carried forward because Scope of the story got updated, One put on hold due to depenency issue. 2. Regarding CRC: The review comments were because of developer missed something during development and need to follow code standards. | [5 empty] | 20
3.22 Sprint 6 (30-Apr-2025 to 13-May-2025) | 33 | 32 | 96.97% | 33 | 90% | 1 | 0 | 0 | 0 | 30 | No |  |  | 2 Assigned stories got golled over - 47441-Client suggest some UI changes in POV, and the UI fix has some concerns and taken more than estimated time, during the testing fixed the bugs. 47902 - Scope of the story got updated Regarding CRC: The review comments were because of developer missed something during development and need to follow code standards. | [5 empty] | 20
3.23 Sprint 1 (14-May-2025 to 27-May-2025) | 24 | 31 | 100% | 36.75 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | 37 Defects found when Kendo(Library) version 2025 Q1 Update. Team fixed all the UI issues | [5 empty] | 20
3.23 Sprint 2 (28-May-2025 to 10-June-2025) | 34 | 35 | 100% | 33 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | 47461- This is an Automation story. Team don't have specific estimates for Automation Stretch story, also,this same story will be taken to upcomming sprints for doing QA Automation work. 31 Defects found when Kendo(Library) version 2025 Q1 Update. Team fixed all the UI issues | [5 empty] | 20
3.23 Sprint 3 (11-June-2025 to 24-June-2025) | 31 | 12 | 38.71% | 27.5 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  | Remarks: Client is not ready to setup their GCP accounts on the web servers, due to this environment issue, we cannot tested the stories in this sprint, we have re-structured the database and call the AI through scheduler service. Stories: 1 out of 6 committed stories has been completed, 5 committed stories not completed. Defects:Fixed | [5 empty] | 20
3.23 Sprint 4 (25-June-2025 to 8-July-2025) | 46 | 45 | 97.83% | 30.75 | 100% | 2 | 0 | 1 | 0 | 30 | No |  |  | Stories: 8 out of 9 committed stories has been completed and 1 not completed Defects: 1 defect not completed | [5 empty] | 20
3.23 Sprint 5 (9-July-2025 to 22-July-2025) | 28 | 32 | 100% | 31 | 100% | 1 | 0 | 1 | 0 | 30 | No |  |  | BOH wave: Stories: 8 out of 9 committed stories has been completed and 1 not completed Defects: 1 defect not completed BOH: Committed Stories: Total 2 stories, 1 story completed, and 1 story development completed, testing spilled over to next sprint. Stretch: 1 story completed. Committed Defects: Total 2 defects,1 defect completed and 1 defect spilled over to next sprint. Introduced during sprint: 1 defect completed (5 SP) Stretch: 1 defect completed. The testing scope for developer was vast and it was a back testing scenario and same is the testing scope for tester.So the story is getting spilled over to next sprint.The story was under estimated. | [5 empty] | 20
3.23 Sprint 6 (23-July-2025 to 05-Aug-2025) | 33 | 35 | 100% | 31 | 100% | 0 | 0 | 5 | 0 | 30 | No |  |  | Stories: 1 story completed from main commit, and 1 story completed from stretch. Note: 4 stories development completed from stretch and ready for testing Defects: (Total 2 defects Completed) Main commit defect - 1, Stretch defect - 1 BOH wave: Stories: Out of 4 Committed stories, 3 has been completed and 1 not completed Defects: 1 committed defect has been completed Highlights: Inventory worksheet parsing and lot of research and testing on invertory work sheet parsing Kudos: Most of the stories were completed | [5 empty] | 20
4.0 Sprint 1 (06-Aug-2025 to 19-Aug-2025) | 23 | 45 | 100% | 39.25 | 100% | 0 | 0 | 5 | 0 | 30 | No |  |  | BOH wave: Stories: 4 Out of 4 Committed stories and 1 stretch story has been completed Defects: 1 stretch defect has been completed Highlights: New UI from mobile upload Kudos: Client is happy for the new mobile upload UI BOH: Stories: 5 stories completed from main commit, and 3 stories completed from stretch. | [5 empty] | 20
4.00 Sprint 2 (20-Aug-2025 to 02-Sep-2025) | 24 | 43 | 100% | 38.75 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  | Gen AI Improvements: Data from Images (Nutrient Fact Labels) | [5 empty] | 20
4.00 Sprint 3 (03-Sep-2025 to 30-Sep-2025) | 43 | 139 | 100% | 65.5 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  | Gen AI Improvements: Data from Images (Nutrient Fact Labels), Production Record, UI changes for physical count | [5 empty] | 20
4.10 Sprint 1 (01-Oct-2025 to 14-Oct-2025) | 49 | 52 | 100% | 69.75 | 100% | 0 | 0 | 7 | 0 | 30 | No |  |  | Improvements to Gen AI UX | [5 empty] | 20
4.11 Sprint 2 (15-Oct-2025 to 28-Oct-2025) | 46 | 48 | 100% | 70.5 | 100% | 1 | 0 | 2 | 8 | 30 | No |  |  | Completed all the committed stories and 2 from stretch | [5 empty] | 20
4.11 Sprint 3 (29-Oct-2025 to 11-Nov-2025) | 44 | 51 | 100% | 72.5 | 100% | 1 | 1 | 2 | 10 | 30 | No |  |  | Completed all planned stories and more, 2 defects they couldn't reproduce | [5 empty] | 20
4.2 Sprint 1 (12-Nov-2025 to 9-Dec-2025) | 36 | 77 | 100% | 57 | 100% | 1 | 0 | 3 | 0 | 30 | No |  |  | Completed all planned stories and worked on stretch stories | [5 empty] | 20
4.2 Sprint 2 (10-Dec-2025 to 6-Jan-2026) | 69 | 82 | 100% | 64.5 | 100% | 0 | 1 | 3 | 3 | 30 | No |  |  | Completed all planned stories and worked on stretch stories | [5 empty] | 20
26.1 Sprint 3 (7-Jan-2026 to 20-Jan-2026) | 39 | 41 | 100% | 62.75 | 100% | 0 | 0 | 4 | 0 | 30 | No |  |  | Team worked on the regression stories. 21 existing defects were identified and it has been fixed | [5 empty] | 20
26.3 Sprint 1 (21-Jan-2026 to 3-Feb-2026) | 45 | 54 | 100% | 63.5 | 100% | 0 | 0 | 3 | 2 | 30 | No |  |  | Completed all planned stories and worked on stretch stories | [5 empty] | 20
26.3 Sprint 2 (4-Feb-2026 to 17-Feb-2026) | 41 | 47 | 100% | 56 | 100% | 0 | 0 | 0 | 6 | 30 | No | 8 | 10 | 6 existing issues were assigned as tasks. Completed all planned stories and worked on stretch stories | [5 empty] | 20
26.3 Sprint 3 (18-Feb-2026 to 3-Mar-2026) | 42 | 52 | 100% | 48.5 | 100% | 0 | 0 | 0 | 2 | 30 | Yes | 4 | 5 | Completed all committed stories | [5 empty] | 20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20

## ExportData
c | 3.19 Sprint 1 (21-Feb-2024 to 5-Mar-2024) | 3.19 Sprint 1 | 2024-02-21 | 2024-03-05 | March | 23 | 12 | 0.52174 | 20 | 0.9 | 5 | 0 | 2 | 3 | #N/A | #N/A | 1 | 0.8 | 0.85
c | 3.19 Sprint 2 (6-Mar-2024 to 19-Mar-2024) | 3.19 Sprint 2 | 2024-03-06 | 2024-03-19 | March | 20 | 26 | 1 | 20 | 0.9 | 3 | 0 | 3 | 4 | 0.9275 | 1 | 1 | 0.8 | 0.85
c | 3.19 - Sprint 3 (20-Mar-2024 to 02-Apr-2024 ) | 3.19 - Sprint 3 | 2024-03-20 | 2024-04-02 | April | 30 | 20 | 0.66667 | 20 | 0.9 | 2 | 1 | 2 | 2 | #N/A | #N/A | 1 | 0.8 | 0.85
c | 3.19 Sprint 4 (03-Apr-2024 to 16-Apr-2024) | 3.19 Sprint 4 | 2024-04-03 | 2024-04-16 | April | 21 | 27 | 1 | 20 | 0.9 | 1 | 1 | 0 | 0 | 0.97889 | 1 | 1 | 1 | 0.92593
c | 3.19 Sprint 5 (17-Apr-2024 to 30-Apr-2024) | 3.19 Sprint 5 | 2024-04-17 | 2024-04-30 | April | 28 | 15 | 0.53571 | 20 | 0.9 | 1 | 2 | 0 | 0 | 0.84393 | 0.53571 | 1 | 1 | 0.8
c | 3.19 Sprint 6 (01-May-2024 to 14-May-2024) | 3.19 Sprint 6 | 2024-05-01 | 2024-05-14 | May | 36 | 36 | 1 | 20 | 0.9 | 0 | 1 | 11 | 0 | 0.87583 | 1 | 1 | 0.45 | 0.97222
c | 3.19 Sprint 7 (15-May-2024 to 28-May-2024) | 3.19 Sprint 7 | 2024-05-15 | 2024-05-28 | May | 30 | 30 | 1 | 20 | 0.9 | 0 | 0 | 12 | 0 | 0.87 | 1 | 1 | 0.4 | 1
c | 3.19 Sprint 8 (29-May-2024 to 11-Jun-2024) | 3.19 Sprint 8 | 2024-05-29 | 2024-06-11 | June | 14 | 14 | 1 | 20 | 0.9 | 0 | 0 | 9 | 0 | 0.9 | 1 | 1 | 0.55 | 1
c | 3.20 Sprint 1 (12-Jun-2024 to 25-Jun-2024) | 3.20 Sprint 1 | 2024-06-12 | 2024-06-25 | June | 18 | 18 | 1 | 20 | 0.9 | 2 | 0 | 6 | 2 | 0.89333 | 1 | 1 | 0.6 | 0.88889
c | 3.20 Sprint 2 (26-Jun-2024 to 23-Jul-2024) | 3.20 Sprint 2 | 2024-06-26 | 2024-07-23 | July | 31 | 31 | 1 | 20 | 0.9 | 0 | 1 | 0 | 1 | 0.97516 | 1 | 1 | 0.95 | 0.96774
c | 3.20 Sprint 3 (24-Jul-2024 to 6-Aug-2024) | 3.20 Sprint 3 | 2024-07-24 | 2024-08-06 | August | 25 | 25 | 1 | 20 | 0.9 | 0 | 1 | 0 | 0 | 0.984 | 1 | 1 | 1 | 0.96
c | 3.20 Sprint 4 (7-Aug-2024 to 20-Aug-2024) | 3.20 Sprint 4 | 2024-08-07 | 2024-08-20 | August | 24 | 24 | 1 | 20 | 0.9 | 0 | 0 | 0 | 0 | 0.99 | 1 | 1 | 1 | 1
c | 3.20 Sprint 5 (21-Aug-2024 to 03-Sep-2024) | 3.20 Sprint 5 | 2024-08-21 | 2024-09-03 | September | 17 | 17 | 1 | 20 | 0.9 | 0 | 1 | 0 | 1 | 0.98333 | 1 | 1 | 0.91667 | 1
c | 3.20 Sprint 6 (04-Sep-2024 to 17-Sep-2024) | 3.20 Sprint 6 | 2024-09-04 | 2024-09-17 | September | 37 | 37 | 1 | 20 | 0.9 | 0 | 0 | 0 | 2 | 0.98333 | 1 | 1 | 0.91667 | 1
c | 3.20 Sprint 7 (18-Sep-2024 to 1-Oct-2024) | 3.20 Sprint 7 | 2024-09-18 | 2024-10-01 | October | 8 | 20 | 1 | 24.5 | 1 | 0 | 0 | 0 | 1 | 0.98333 | 1 | 1 | 0.91667 | 1
c | 3.20 Sprint 8 (2-Oct-2024 to 15-Oct-2024) | 3.20 Sprint 8 | 2024-10-02 | 2024-10-15 | October | 18 | 15 | 0.83333 | 22.25 | 1 | 1 | 0 | 0 | 0 | 0.94167 | 0.83333 | 1 | 0.91667 | 1
c | 3.20 Sprint 9 (16-Oct-2024 to 29-Oct-2024) | 3.20 Sprint 9 | 2024-10-16 | 2024-10-29 | October | 25 | 30 | 1 | 25.5 | 1 | 0 | 0 | 0 | 0 | 0.98333 | 1 | 1 | 0.91667 | 1
c | 3.20 Sprint 10 (30-Oct-2024 to 12-Nov-2024) | 3.20 Sprint 10 | 2024-10-30 | 2024-11-12 | November | 30 | 30 | 1 | 24 | 1 | 0 | 0 | 0 | 0 | 0.89333 | 1 | 1 | 0.6 | 0.88889
c | 3.20 Sprint 11 (13-Nov-2024 to 10-Dec-2024) | 3.20 Sprint 11 | 2024-11-13 | 2024-12-10 | December | 25 | 20 | 0.8 | 24 | 1 | 0 | 0 | 2 | 0 | 0.89333 | 1 | 1 | 0.6 | 0.88889
c | 3.21 Sprint 1 (11-Dec-2024 to 7-Jan-2025) | 3.21 Sprint 1 | 2024-12-11 | 2025-01-07 | January | 25 | 25 | 1 | 26.25 | 1 | 1 | 0 | 1 | 0 | 0.98638 | 1 | 1 | 0.9619 | 0.96
c | 3.21 Sprint 2 (8-Jan-2025 to 21-Jan-2025) | 3.21 Sprint 2 | 2025-01-08 | 2025-01-21 | January | 20 | 20 | 1 | 24 | 1 | 1 | 0 | 2 | 2 | 0.95917 | 1 | 1 | 0.83333 | 0.95
c | 3.21 Sprint 3 (22-Jan-2025 to 4-Feb-2025) | 3.21 Sprint 3 | 2025-01-22 | 2025-02-04 | February | 15 | 47.25 | 1 | 29 | 0.9 | 1 | 0 | 0 | 0 | 0.98683 | 1 | 1 | 1 | 0.97884
c | 3.21 Sprint 4 (5-Feb-2025 to 18-Feb-2025) | 3.21 Sprint 4 | 2025-02-05 | 2025-02-18 | February | 16 | 17 | 1 | 27 | 1 | 0 | 0 | 3 | 0 | 0.97778 | 1 | 1 | 0.88889 | 1
c | 3.22 Sprint 1 (19-Feb-2025 to 04-March-2025) | 3.22 Sprint 1 | 2025-02-19 | 2024-12-04 | March | 13 | 26 | 1 | 28 | 1 | 0 | 0 | 2 | 1 | 0.97857 | 1 | 1 | 0.89286 | 1

## Sheet1
| 3.19 Sprint 1 (21-Feb-2024 to 5-Mar-2024) | 3.19 Sprint 2 (6-Mar-2024 to 19-Mar-2024) | 3.19 - Sprint 3 (20-Mar-2024 to 02-Apr-2024 ) | 3.19 Sprint 4 (03-Apr-2024 to 16-Apr-2024) | 3.19 Sprint 5 (17-Apr-2024 to 30-Apr-2024) | 3.19 Sprint 6 (01-May-2024 to 14-May-2024) | 3.19 Sprint 7 (15-May-2024 to 28-May-2024) | 3.19 Sprint 8 (29-May-2024 to 11-Jun-2024) | 3.20 Sprint 1 (12-Jun-2024 to 25-Jun-2024) | 3.20 Sprint 2 (26-Jun-2024 to 23-Jul-2024) | 3.20 Sprint 3 (24-Jul-2024 to 6-Aug-2024) | 3.20 Sprint 4 (7-Aug-2024 to 20-Aug-2024) | 3.20 Sprint 5 (21-Aug-2024 to 03-Sep-2024) | 3.20 Sprint 6 (04-Sep-2024 to 17-Sep-2024) | 3.20 Sprint 7 (18-Sep-2024 to 1-Oct-2024) | 3.20 Sprint 8 (2-Oct-2024 to 15-Oct-2024) | 3.20 Sprint 9 (16-Oct-2024 to 29-Oct-2024) | 3.20 Sprint 10 (30-Oct-2024 to 12-Nov-2024) | 3.20 Sprint 11 (13-Nov-2024 to 10-Dec-2024) | 3.21 Sprint 1 (11-Dec-2024 to 7-Jan-2025) | 3.21 Sprint 2 (8-Jan-2025 to 21-Jan-2025) | 3.21 Sprint 3 (22-Jan-2025 to 4-Feb-2025) | 3.21 Sprint 4 (5-Feb-2025 to 18-Feb-2025) | 3.22 Sprint 1 (19-Feb-2025 to 04-Mar-2025) | 3.22 Sprint 2 (05-Mar-2025 to 18-Mar-2025) | 3.22 Sprint 3 (19-Mar-2025 to 01-Apr-2025) | 3.22 Sprint 4 (02-Apr-2025 to 15-Apr-2025) | 3.22 Sprint 5 (16-Apr-2025 to 29-Apr-2025) | 3.22 Sprint 6 (30-Apr-2025 to 13-May-2025) | 3.23 Sprint 1 (14-May-2025 to 27-May-2025) | 3.23 Sprint 2 (28-May-2025 to 10-June-2025) | 3.23 Sprint 3 (11-June-2025 to 24-June-2025) | 3.23 Sprint 4 (25-June-2025 to 8-July-2025) | 3.23 Sprint 5 (9-July-2025 to 22-July-2025) | 3.23 Sprint 6 (23-July-2025 to 05-Aug-2025) | 4.0 Sprint 1 (06-Aug-2025 to 19-Aug-2025) | 4.00 Sprint 2 (20-Aug-2025 to 02-Sep-2025) | 4.00 Sprint 3 (03-Sep-2025 to 30-Sep-2025) | 4.10 Sprint 1 (01-Oct-2025 to 14-Oct-2025) | 4.11 Sprint 2 (15-Oct-2025 to 28-Oct-2025) | 4.11 Sprint 3 (29-Oct-2025 to 11-Nov-2025) | 4.2 Sprint 1 (12-Nov-2025 to 9-Dec-2025) | 4.2 Sprint 2 (10-Dec-2025 to 6-Jan-2026) | 26.1 Sprint 3 (7-Jan-2026 to 20-Jan-2026) | 26.3 Sprint 1 (21-Jan-2026 to 3-Feb-2026)
arr1 3.19 Sprint 1 (21-Feb-2024 to 5-Mar-2024) | 3.19 Sprint 2 (6-Mar-2024 to 19-Mar-2024) | 3.19 - Sprint 3 (20-Mar-2024 to 02-Apr-2024 ) | 3.19 Sprint 4 (03-Apr-2024 to 16-Apr-2024) | 3.19 Sprint 5 (17-Apr-2024 to 30-Apr-2024) | 3.19 Sprint 6 (01-May-2024 to 14-May-2024) | 3.19 Sprint 7 (15-May-2024 to 28-May-2024) | 3.19 Sprint 8 (29-May-2024 to 11-Jun-2024) | 3.20 Sprint 1 (12-Jun-2024 to 25-Jun-2024) | 3.20 Sprint 2 (26-Jun-2024 to 23-Jul-2024) | 3.20 Sprint 3 (24-Jul-2024 to 6-Aug-2024) | 3.20 Sprint 4 (7-Aug-2024 to 20-Aug-2024) | 3.20 Sprint 5 (21-Aug-2024 to 03-Sep-2024) | 3.20 Sprint 6 (04-Sep-2024 to 17-Sep-2024) | 3.20 Sprint 7 (18-Sep-2024 to 1-Oct-2024) | 3.20 Sprint 8 (2-Oct-2024 to 15-Oct-2024) | 3.20 Sprint 9 (16-Oct-2024 to 29-Oct-2024) | 3.20 Sprint 10 (30-Oct-2024 to 12-Nov-2024) | 3.20 Sprint 11 (13-Nov-2024 to 10-Dec-2024) | 3.21 Sprint 1 (11-Dec-2024 to 7-Jan-2025) | 3.21 Sprint 2 (8-Jan-2025 to 21-Jan-2025) | 3.21 Sprint 3 (22-Jan-2025 to 4-Feb-2025) | 3.21 Sprint 4 (5-Feb-2025 to 18-Feb-2025) | 3.22 Sprint 1 (19-Feb-2025 to 04-March-2025)
3.19 Sprint 1 (21-Feb-2024 to 5-Mar-2024)
3.19 Sprint 1 (21-Feb-2024 to 5-Mar-2024),3.19 Sprint 2 (6-Mar-2024 to 19-Mar-2024),3.19 - Sprint 3 (20-Mar-2024 to 02-Apr-2024 ),3.19 Sprint 4 (03-Apr-2024 to 16-Apr-2024),3.19 Sprint 5 (17-Apr-2024 to 30-Apr-2024),3.19 Sprint 6 (01-May-2024 to 14-May-2024),3.19 Sprint 7 (15-May-2024 to 28-May-2024),3.19 Sprint 8 (29-May-2024 to 11-Jun-2024),3.20 Sprint 1 (12-Jun-2024 to 25-Jun-2024),3.20 Sprint 2 (26-Jun-2024 to 23-Jul-2024),3.20 Sprint 3 (24-Jul-2024 to 6-Aug-2024),3.20 Sprint 4 (7-Aug-2024 to 20-Aug-2024),3.20 Sprint 5 (21-Aug-2024 to 03-Sep-2024),3.20 Sprint 6 (04-Sep-2024 to 17-Sep-2024),3.20 Sprint 7 (18-Sep-2024 to 1-Oct-2024),3.20 Sprint 8 (2-Oct-2024 to 15-Oct-2024),3.20 Sprint 9 (16-Oct-2024 to 29-Oct-2024),3.20 Sprint 10 (30-Oct-2024 to 12-Nov-2024),3.20 Sprint 11 (13-Nov-2024 to 10-Dec-2024),3.21 Sprint 1 (11-Dec-2024 to 7-Jan-2025),3.21 Sprint 2 (8-Jan-2025 to 21-Jan-2025),3.21 Sprint 3 (22-Jan-2025 to 4-Feb-2025),3.21 Sprint 4 (5-Feb-2025 to 18-Feb-2025)
Sprint,3.22 Sprint 1 (19-Feb-2025 to 04-Mar-2025),3.22 Sprint 2 (05-Mar-2025 to 18-Mar-2025),3.22 Sprint 3 (19-Mar-2025 to 01-Apr-2025),3.22 Sprint 4 (02-Apr-2025 to 15-Apr-2025),3.22 Sprint 5 (16-Apr-2025 to 29-Apr-2025),3.22 Sprint 6 (30-Apr-2025 to 13-May-2025),3.23 Sprint 1 (14-May-2025 to 27-May-2025),3.23 Sprint 2 (28-May-2025 to 10-June-2025),3.23 Sprint 3 (11-June-2025 to 24-June-2025),3.23 Sprint 4 (25-June-2025 to 8-July-2025),3.23 Sprint 5 (9-July-2025 to 22-July-2025),3.23 Sprint 6 (23-July-2025 to 05-Aug-2025),4.0 Sprint 1 (06-Aug-2025 to 19-Aug-2025),4.00 Sprint 2 (20-Aug-2025 to 02-Sep-2025),4.00 Sprint 3 (03-Sep-2025 to 30-Sep-2025),4.10 Sprint 1 (01-Oct-2025 to 14-Oct-2025),4.11 Sprint 2 (15-Oct-2025 to 28-Oct-2025),4.11 Sprint 3 (29-Oct-2025 to 11-Nov-2025),4.2 Sprint 1 (12-Nov-2025 to 9-Dec-2025),4.2 Sprint 2 (10-Dec-2025 to 6-Jan-2026),26.1 Sprint 3 (7-Jan-2026 to 20-Jan-2026),26.3 Sprint 1 (21-Jan-2026 to 3-Feb-2026)