## Dashboard
FOH

## Scorecard
Project Name | FOH
Engagement Model | Relevantz Co Owned
Overall Score | 107.4%
Current Sprint | 26.05 Sprint 4 (10-Apr-2026 to 23-Apr-2026)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 131.4% | 32.86% | 9 | 25% | 100%
Velocity | 100% | 20% |  | 20% | 95%
Defect-free Rate | 97.89% | 19.58% |  | 20% | 100%
Code Quality Index | 100% | 15% |  | 15% | 100%
Unit Testing & Code Coverage | 100% | 10% |  | 10% | 90%
Backlog Health | 100% | 10% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
4.25 Sprint 4 (7-Nov-2025 to 20-Nov-2025) | 32 | 40 | 125% | 40 | 100% | 24 | 1 | 2 | 0 | 30 | No |  |  | Completed all assigned stories and more |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
4.25 Sprint 5 (21-Nov-2025 to 18-Dec-2025) | 75 | 75 | 100% | 57.5 | 100% | 3 | 0 | 2 | 0 | 30 | No |  |  | Completed all assigned stories and more |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.01 Sprint 1 (19-Dec-2025 to 15-Jan-2026) | 60 | 81 | 135% | 65.3333 | 100% | 25 | 2 | 6 | 0 | 30 | No |  |  | Completed all assigned stories and more |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.01 Sprint 2 (16-Jan-2026 to 29-Jan-2026) | 52 | 58 | 111.5% | 63.5 | 100% | 3 | 0 | 1 | 0 | 30 | No |  |  | Completed all assigned stories and more |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.01 Sprint 3 (30-Jan-2026 to 12-Feb-2026) | 34 | 52 | 100% | 66.5 | 100% | 3 | 0 | 4 | 0 | 30 | No | 2 | 4 | Completed all assigned stories and more |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.01 Sprint 4 (13-Feb-2026 to 26-Feb-2026) | 39 | 42 | 100% | 58.25 | 100% | 0 | 0 | 0 | 0 | 30 | No | 4.5 | 8.5 | Regression testing completed for FOH |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.05 Sprint 1 (27-Feb-2026 to 12-Mar-2026) | 35 | 42 | 100% | 48.5 | 100% | 14 | 0 | 15 | 0 | 30 | No | 5 | 7 | Since FOH Wave team has started to work on BOH tasks from this sprint. As this is first sprint, defects and code review count were more as team is learning about the application and it will get reduced in the upcoming sprints |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.05 Sprint 2 (13-Mar-2026 to 26-Mar-2026) | 39 | 44 | 112.8% | 45 | 100% | 18 | 0 | 3 | 0 | 30 | No | 5.5 | 6.5 | Defects got reduced in the current sprint. Since team is new to BOH, 11 POV comments were received and it will get reduced once team gets the complete understanding of the application in the upcoming sprints. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.05 Sprint 3 (27-Mar-2026 to 9-Apr-2026) | 41 | 58 | 100% | 46.5 | 100% | 7 | 0 | 4 | 0 | 30 | No | 15 | 13 | Defects got reduced in the current sprint. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.05 Sprint 4 (10-Apr-2026 to 23-Apr-2026) | 35 | 46 | 131.4% | 47.5 | 100% | 0 | 0 | 1 | 0 | 30 | Yes | 9 | 10 | All committed stories were completed |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
0%
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## RCA
3 Why Analysis
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-04-03 | 3.19 - Sprint 1 (21 Feb - 05 Mar ) | Adding Product Groups to vendor orders created from requisition is not working Issue in Prepend "EMP-" to the HSS Users Production Summary Report sorting recipes incorrectly | External | Metric Deviation | Client Identified defects | Missed to identify in unit testing | Assumed will work in test environment with exsisting data. |  | Knowledge share with Team in Stand Up, So that similar type of Defect can be mitigated. | Sathiya | Closed | 2024-04-04 | Issue fixed and committed. | Metric Deviation
3 | 2024-04-16 | 3.19 Sprint 4 (03-Apr to 16-Apr) | Let's change the message to "Quantity cannot be 0." | External | Metric Deviation | Code Review Comments | Missed to check the existing approach method in similar page | Missed code optimization to reduce resource consumption. | Missed in Internal Review | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Krupa | Closed | 2024-04-17 | Comment fixed and committed. | Commitment Deviation
4 | 2024-04-30 | 3.19 Sprint 5 (17-Apr to 30-Apr) | Javascript is case sensitive... should this be ResponsePurchaseUnitWeight? (capital W) | External | Metric Deviation | Code Review Comments |  |  |  |  | Krupa | Closed | 2024-05-03 |  | Security Compliance
5 | 2024-04-30 | 3.19 Sprint 5 (17-Apr to 30-Apr) | One 13 SP carried to next sprint, Client CRC fix is inprogress. | External | Metric Deviation | Commitment Index Deviation | Client code review comment fix is inprogress |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa | Closed | 2024-05-03 |  | Not adhered to Policy
6 | 2024-06-25 | 3.20 Sprint 1 (12-Jun to 25-Jun) | 2 Defects reported by client | External | Metric Deviation | Client Identified defects |  |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Preethi | Closed | 2024-06-26 |  | Others
7 | 2024-07-23 | 3.20 Sprint 2 (26-Jun to 23-Jul) | 1 CRC and 1 defect repoted by client | External | Metric Deviation | Code Review Comments |  |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa | Closed | 2024-07-24
8 | 2024-08-05 | 3.20 Sprint 3 (24-Jul to 6-Aug) | 1 Code Review Comment reported by Client | External | Metric Deviation | Code Review Comments |  |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Charles | Closed | 2024-08-06
9 | 2024-09-03 | 3.20 Sprint 5 (21-Aug to 03-Sep) | 1 Escaped Defects and 1 Client CRC | External | Metric Deviation | Code Review Comments and 1 Escaped Defect | Suggestion - Lowercase "w" in within and capital "L" in Level, please | Minor Existing Issues - Client wants to work on this |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa/Preethi | Closed | 2024-09-03
10 | 2024-09-17 | 3.20 Sprint 6 (04-Sep to 17-Sep) | 2 Escaped Defects | External | Metric Deviation | Escaped Defect | Both the defects are already existing minor issues, clients wants to work in this sprint |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa/Vijay | Closed | 2024-09-17
11 | 2024-10-01 | 3.20 Sprint 7 (18-Sep to 1-Oct) | 1 Escaped Defects | External | Metric Deviation | Escaped Defect | Significant Existing Issues - Client wants to work on this - WRT to Special Character changes |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Vijay/Charles | Closed | 2024-10-01
12 | 2024-10-15 | 3.20 Sprint 8 (2-Oct to 15-Oct) | 1 Internal CRC | Internal | Metric Deviation | Code Review Comments | Few Suggestions: Award Summary button should be disabled if none of the item is selected Suggested a few cosmetic changes |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa | Closed | 2024-10-15
13 | 2024-11-12 | 3.20 Sprint 10 (30-Oct to 12-Nov) | 1 Story was Carry Forwarded | Internal | Metric Deviation | 1 Regression Story was Carry Forwarded because the Regression Story was Switched in Mid Sprint with newly Introduced Story "46412 and 46413", Once the Story was completed the Team picked this Story. | Defects were found, so the Team concentrated on those |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Charles | Closed | 2024-12-11 | The Story is currently in Progress
14 | 2024-12-10 | 3.20 Sprint 11 (13-Nov to 10-Dec) | 1 Story was Carry Forwarded and 2 QA Defect | Internal | Metric Deviation | Story Carry Forwarded and 2 QA Defects | Story Carry Forward The development for story "46525"-Mosaic BOH - Bidding - Add the ability to attach any doc in bid analysis - is completed however the testing and review is incomplete due to hot fix release and one of the hot fix change was affecting the story. Until that is fixed it could not be pushed | 2 QA Defects - were existing issues that were identified and given for release |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is well informed about the QA defects and will make sure the progress/process | Charles/Krupa | Inprogress | 2025-07-01 | The Story is currently in Progress. Defects were closed
15 | 2025-01-07 | 3.21 Sprint 1 (11-Dec to 7-Jan) | 1 Story was Carry Forwarded and 1 QA Defect, 1 Internal Peer Review Comment | Internal | Metric Deviation | 1 Story was Carry Forwarded and 1 QA Defect, 1 Internal Peer Review Comment | The development for story "46743" - is in progress as we have to update the Kendo controls to latest version and fix affected components across the application.The story could spill over few more sprints as the same was done earlier (story 35612) which took total 316 hrs. It is a Development ---- Working control wise,once done with one will move to next control | 1 QA Defect which was an existing issue that was identified prior and we fixed now | 1 Peer Review Comment - Suggestion - Code readability improvement | Kendo - The story is in progress as we have to update the Kendo controls to latest version.The story could spill over few more sprints as the same was done earlier (story 35612) which took total 316 hrs.Completed the dropdown control and moved to Grid but the functionality of grid paging affected the dropdown button color. | Charles/Krupa/Mohammed | Closed | 2025-01-07 | The Story will be in progress, it is targeted for next release and client is informed about this. The Developer will be working control wise, once one control is over they will move to next
16 | 2025-01-21 | 3.21 Sprint 2 (8-Jan to 21-Jan) | 2 Story was Carry Forwarded and 4 QA Defect | Internal/External | Metric Deviation | 1 Story was Carry Forwarded and 2 QA Defect, 2 Escaped Defects | The development for story was completed on 20/01/2025.However, the offshore tester found one issue so, fixed and pushed the PR on the next day.Also 20/01/2025 was onsite holiday. Ready for Testing. The Story will be tested by Onsite QA | 2 QA Defects - were existing issues which were in Production was identified and fixed - Mnor Issues | 2 Bouncebacks from the story development - It was addressed and closed. One is code issue and the another one is Development was not covered for multi user scenario | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is well informed about the QA defects and will make sure the progress/process | Charles/Krupa/Mohammed | Closed | 2025-01-21 | The Client QA will test the story.
17 | 2025-02-04 | 3.21 Sprint 3 (22-Jan to 4-Feb) | 1 Internal CRC | Internal | Metric Deviation | Code Review Comments | One Logical Comment to change the Code - Remove not mapping table join from stored procedure |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Mohammed | Closed | 2025-02-04
18 | 2025-02-18 | 3.21 Sprint 4 (5-Feb-2025 to 18-Feb-2025) | 3 Internal Defects | Internal/External | Metric Deviation | 3 Internal Defects | Development was not covered in Menus -> PQ Screen Existing production Issue Data issue for regression districts, fixed by charles |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Krupa/Charles | Closed | 2025-02-19
19 | 2025-03-04 | 3.22 Sprint 1 (19-Feb-2025 to 04-March-2025) | 2 Internal Defects and 1 External Defects | Internal/External | Metric Deviation | 1 Bounceback, 1 Internal and 1 External QA | 1 Bounceback -Scenario was not covered as part of development. The Issue was fixed | 1 Internal Defect - Existing issue, missied to handle this scenario as a part of development. Issue is fixed | 1 External Defect - Existing Production Issue - The issue was not Major doesn't affect major feature | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is working on closely in | Charles/Mohammed | Closed | 2025-03-04
20 | 2025-03-18 | 3.22 Sprint 2 (05-Mar-2025 to 18-Mar-2025) | 1 Story Carry Forwarded, 2 CRC, Defect | Internal/External | Metric Deviation | 1 Story Carry Forwarded, 1 Internal CRC, 1 External CRC, 1 Defect | 1 Story Carry Forward - Development In-Progress, Few scenarios completed, have to cover few more scenarios. We completed menus and working on meal viewer sync.Also Unplanned PTO. | 1 Internal CRC - Suggestions - Remove excess space in the dropdown - existing issue Camel case 1 External CRC - Suggestion (Was not in AC) Limit the data field length to 50 chars | 1 Defect (External) - Production Defect Data Issue Potential bad data found when saving production quantities | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is working on closely moving forward to mitigate unplanned leaves. | Rajiv | Closed | 2025-04-01
21 | 2025-04-01 | 3.22 Sprint 3 (19-Mar-2025 to 01-Apr-2025) | Defects and Story carry forwarded | Internal/External | Metric Deviation | 2 Story Carry Forwarded, 3 Internal Defect, 1 External Defect | 2 Story carry forwarded 1. Story moved to testing. Since it has dependency with Mealviewer application, this story can be tested only in QA environment and there are lot to test in both the side and it's in progress. 2. 47441 -[WAVE]Mosaic BOH - Gen AI (Initiative #37515) - Import Suggested Menus Carry over to next sprint due to amount of work and testing involved. Underestimated the effort during planning. | All the defects are Production data and Performance issue. All the defects are fixed |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. The Team is working on closely in | Charles/Deepika | Open | 2025-04-15
22 | 2025-04-15 | 3.22 Sprint 4 (02-Apr-2025 to 15-Apr-2025) | Code Quality Index deviation CRC Peer - 1 CRC Onsite -3 CRC Client - 3 | Internal/External | Metric Deviation | CRC Peer - 1 CRC Onsite -3 CRC Client - 3 | The review comments were because of we missed something during development . Below are the comment we have received: Peer CRC :1 Remove commented codes, excell lines, and unwanted code pushes Onsite: 4 1.Separate Resource file for AI messages 2. Remove commented lines 3. Use Constants for text instead of HardCoded value External:3 1. inherit : BaseController instead of : Controller 2. UI popup at center, 2 option to adopt in same day 3. Filter District in Recipe data |  |  | CRC: Understand and implement AC , Follow coding standards properly | Rajiv/Joel/Deepika | Closed | 2025-04-15
23 | 2025-04-29 | 3.22 Sprint 5 (16-Apr-2025 to 29-Apr-2025) | Code Quality Index deviation | Internal | Metric Deviation | CRC Onsite - 1 | The review comments were because of we missed something during development . Below are the comment we have received: Onsite CRC :1 1. UI Issues | Cosmetic error | Missed to follow the coding standards | CRC: Understand and implement AC , Follow coding standards properly | Deepika | Inprogress | 2025-05-13
24 | 2025-04-29 | 3.22 Sprint 5 (16-Apr-2025 to 29-Apr-2025) | 2 Story Carry Forwarded | Internal | Metric Deviation | 2 Assigned stories got forward | 47441-Client suggest some UI changes in POV, and the UI fix has some concerns and taken more than estimated time, during the testing fixed the bugs. 47902 - Scope of the story got updated | Scope of the story got updated in the mid of the sprint |  | Team is currently working on that, and this will be prioritized early in the next sprint with better coordination to avoid future delays | Deepika/Rajiv/Joel | Inprogress | 2025-05-13
25 | 2025-05-13 | 3.22 Sprint 6 (30-Apr-2025 to 13-May-2025) | Defects | Internal | Metric Deviation | UI Issues | The issue was identified during regression testing and was caused by recent changes related to Kendo(Library) version 2025 Q1 Update. | Minor Cosmetic Issues |  | For the Library update Team will do more into Unit testing before give it to the QA | All Members | Closed | 2025-05-13
26 | 2025-05-27 | 3.23 Sprint 1 (14-May-2025 to 27-May-2025) | CRC, Defects | Internal/External | Metric Deviation | UI Issues | The issue was identified during regression testing and was caused by recent changes related to Kendo(Library) version 2025 Q1 Update. | Minor Cosmetic Issues |  | For the Library update Team will Document the unexpected behavior and any error messages and Use debugging tools, logs to reduce the number of UI issues. | All Members | Closed | 2025-05-27
27 | 2025-06-10 | 3.23 Sprint 2 (28-May-2025 to 10-Jun-2025) | CRC | internal/External | Metric Deviation | 1 - InternalCRC 1 - Client CRC |  | Minor Cosmetic Issues and Suggestions |  | For the Library update Team will Document the unexpected behavior and any error messages and Use debugging tools, logs may reduce the number of UI issues. | All Members | Closed | 2025-06-10
28 | 2025-06-24 | 3.23 Sprint 3 (11-Jun-2025 to 24-Jun-2025) | Commitment Deviation, Defects | Internal | Commitment Deviation | 7 - Internal Defects | The issue was identified during regression testing and team fixed the issues. | For Commitment Deviation - Team completed the Development but due to Testing environment unavailability need unable totest the stories. |  | Team focusing on boycot the GCP environment to test. | All Members | Closed | 2025-06-24
29 | 2025-06-24 | 3.23 Sprint 3 (11-June-2025 to 24-June-2025) | 2 assigned Stories got rolled over | Internal | Metric Deviation | Commitment Index Deviation | Remarks: Client is not ready to setup their GCP accounts on the web servers, due to this environment issue, we cannot tested the stories in this sprint, we have re-structured the database and call the AI through scheduler service. Stories: 1 out of 6 committed stories has been completed, 5 committed stories not completed. |  |  |  | All Members | Closed | 2025-07-08
30 | 2025-07-08 | 3.23 Sprint 4 (25-June-2025 to 8-July-2025) | 1 Internal Defects | Internal | Metric Deviation | Defect free Rate | The issue was identified during regression testing and was caused by recent changes related to Kendo version 2025 Q1 Update. It's a kendo default behaviour in recent update and looking for workaround to acheive the same functionality. |  |  |  | All Members | Closed | 2025-07-22
31 | 2025-07-08 | 3.23 Sprint 4 (25-June-2025 to 8-July-2025) | CRC | internal/External | Metric Deviation | 2 - InternalCRC | Minor Cosmetic Issues and Suggestions |  |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | All Members | Closed | 2025-07-08
32 | 2025-07-22 | 3.23 Sprint 5 (9-July-2025 to 22-July-2025) | CRC, Defects | internal/External | Metric Deviation | 2 - InternalCRC Defect free Rate -1 | The issue was identified during regression testing and was caused by recent changes related to Kendo(Library) version 2025 Q1 Update. | Minor Cosmetic Issues and Suggestions |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | All Members | Closed | 2025-08-05
34 | 2025-08-05 | 3.23 Sprint 6 (23-July-2025 to 05-Aug-2025) | Defects | internal/External | Metric Deviation | Defect free Rate -5 | 4 External defects in Production 1 Internal - Missed in the devlopement and internal Testing |  |  | Moving forward, Developers will also do proper Unit testing before pushing this to TST env.These defects will be prioritized early in the next sprint with better coordination to avoid future defects. | All Members | Closed | 2025-08-19
35 | 2025-10-14 | 4.1 Sprint 1 (01-Oct-2025 to 14-Oct-2025) | Defects | External | Metric Deviation |  | External defects in Production |  |  | Existing Production Defects | All Members | Closed | 2025-10-20
36 | 2025-10-14 | 4.1 Sprint 2 (15-Oct-2025 to 29-Oct-2025) | Defects | Internal | Metric Deviation |  | 2 Internal defects and 8 external defects | After the AI Release some issues are found,so created a defect.All these issues are existing in the Production Environment |  | Existing Production Defects | All Members | Closed | 2025-10-20
37 | 2025-11-11 | 4.1 Sprint 3 (29-Oct-2025 to 11-Nov-2025) | Defects | Internal/ External | Metric Deviation |  | 2 Internal defects and 10 external defects | External issues are existing in the Production Environment Internal are Bounce backs |  | Existing Production Defects It was edge case scenario, will try to cover more scenarios future | All Members | Closed | 2025-11-30
38 | 2025-11-11 | 4.1 Sprint 3 (29-Oct-2025 to 11-Nov-2025) | Code review comments | External | Others |  | Costemic change suggestion provided as review comments |  |  | Review the UI prototype with the client before the sprint starts and final the prototype | All Members | Closed | 2025-11-30
39 | 2025-12-10 | 4.2 Sprint 1 (12-Nov-2025 to 9-Dec-2025) | Defects | Internal/ External | Metric Deviation |  | 3 Internal defects | one defect -It's a existing common issue in all muliselect dropdownlist. 2 defects are minor defects related to cosmetic issues |  | Updating the kendo common code to fix. will try to cover more scenarios future | All Members | Closed | 2025-12-15
40 | 2026-01-06 | 4.2 Sprint 2 (10-Dec-2025 to 6-Jan-2026) | Code review comments | External | Others |  | Costemic change suggestion provided as review comments |  |  | RCA : It's a existing common issue in all muliselect dropdownlist Mitigation Plan: Updating the kendo common code to fix | All Members | Closed | 2026-01-06
41 | 2026-01-06 | 4.2 Sprint 2 (10-Dec-2025 to 6-Jan-2026) | Defects | Internal/ External | Others |  | 3 External and 3 Internal defects | 2 External defect were existing prod issue and 1 External defect was minor issue. 3 Internal defects are minor defects related to cosmetic issues |  | RCA: Existing production issues, it was found by internal QA. Due to delivery release deadline, we couldn't fix it on that time, So we fixed it now. Mitigation Plan: Manage the time for fixing the QA issues. Also increase the testing coverage to prevent issues. | All Members | Closed | 2026-01-06
42 | 2026-01-22 | 26.1 Sprint 3 (7-Jan-2026 to 20-Jan-2026) | Defects | Internal | Others |  | 4 Internal defects | 4 Internal defects are existing defects found during the testing |  | RCA: Existing production issues, it was found by internal QA during regression testing. Mitigation Plan: Increase the testing coverage to prevent issues. Also do more regression testing to address these kind of defects | All Members | Closed | 2026-01-20
43 | 2026-02-12 | 26.1 - Sprint 3(30-Jan-2026 to 12-Feb-2026) | Defects | Internal | Others |  | 2 Internal defects | 1. css styling not handled and so improper visual spacing between UI components occured 2. Missed to show proper version format |  | RCA: 2 defects were mentioned as suggestions (Minor defects) Mitigation Plan: Increase the testing coverage to prevent issues. Also do more regression testing to address these kind of defects | All Members | Closed | 2026-02-13
44 | 2026-02-12 | 26.1 - Sprint 3(30-Jan-2026 to 12-Feb-2026) | Code review comments | Internal | Others |  | 3 Code review comments | Version history in one page, Suggestion to write the query in an another way, Insert to one detail table is not required |  | RCA: Suggestion to implement the code in another way Mitigation Plan: Team to follow the best coding standards and refer to the coding checklist documents | All Members | Closed | 2026-02-13
45 | 2026-02-26 | 26.1 - Sprint 4(13-Feb-2026 to 26-Feb-2026) | 2 assigned Stories got rolled over | Internal | Metric Deviation | Commitment Index Deviation | Remarks: 1) The testing support story was not completed as the team prioritized regression testing. As a result, testing for this item only began toward the end of the sprint. 2) All development activities from our side have been completed on time and it is pending with the Onsite QA." |  |  | RCA: 2 Stories were development completed and testing pending. Due to client reprioritization, team has to work on regression testing which resulted in 1 story carry forward. Another story got carry forward, as the client QA is not available and requires sign off from him Mitigation: Better sprint planning based on the capacity and highlight the risk of story carry forward to the client whenever there is reprioritization of the tasks | All Members | Closed | 2026-03-20
46 | 2026-03-12 | 26.05 - Sprint 1(27-Feb-2026 to 12-Mar-2026) | Defects | Internal | Others |  | 15 Internal defects | 1. UI validations should be added properly (4) 2. UI design issues (8) 3. Data issue (3) |  | RCA: 15 defects were mentioned as suggestions (Minor defects). Since FOH Wave team has started to work on BOH tasks from this sprint. As this is first sprint, defects count were more as team is learning about the application Mitigation Plan: Increase the testing coverage to prevent issues. Also do more unit testing to address these kind of defects during development phase | Sabir, Vidhya | Closed | 2026-03-20
47 | 2026-03-12 | 26.05 - Sprint 1(27-Feb-2026 to 12-Mar-2026) | Code review comments | Internal | Others |  | 14 Code review comments | 1. Missed to follow localization support (2) 2. Missed to follow exsiting coding standards (1) 3. unwanted code (1) 4. returning entity directly (1) |  | RCA: Suggestion to implement the code in another way. Since FOH Wave team has worked on BOH tasks from this sprint. As this is first sprint, code review count were more as team is learning about the application Mitigation Plan: Team to follow the best coding standards and refer to the coding checklist documents | Sabir, Vidhya | Closed | 2026-03-20
48 | 2026-03-26 | 26.05 - Sprint 2(13-Mar-2026 to 26-Mar-2026) | Defects | Internal | Others |  | 3 Internal defects | 1. UI design issues 2. Backend validation did not match the UI validation. (2) |  | RCA: UI design and validation issues which were minor ones Mitigation Plan: Increase the testing coverage to prevent issues. Also do more unit testing to address these kind of defects during development phase | Arvinth | Closed | 2026-03-26
49 | 2026-03-26 | 26.05 - Sprint 2(13-Mar-2026 to 26-Mar-2026) | Code review comments | Internal | Others |  | 18 Code review comments | Out of 18 CRC, 11 were POV comments provided by PO during internal reviews. Since FOH Wave team is working on BOH tasks, they are new to the application and receiving comments during POV Mitigation plan: Team to understand the application better by going through the recordings and documents to reduce the CRC comments |  | RCA: Out of 18 CRC, 11 were POV comments provided by PO during internal reviews. Since FOH Wave team is working on BOH tasks, they are new to the application and receiving comments during POV Mitigation plan: Team to understand the application better by going through the recordings and documents to reduce the CRC comments Team to follow the best coding standards and refer to the coding checklist documents | Sabir, Vidhya | Closed | 2026-03-26
50 | 2026-04-10 | 26.05 - Sprint 3 (27-Mar-2026 to 9-Apr-2026) | Commitment Index | Internal | Others |  | 1 story carry forward | 1 Story has been carry forwarded due to testing pending with QA from client side |  | RCA: UI design and validation issues which were minor ones Mitigation Plan: Increase the testing coverage to prevent issues. Also do more unit testing to address these kind of defects during development phase | Team | Closed | 2026-04-10
51 | 2026-04-10 | 26.05 - Sprint 3 (27-Mar-2026 to 9-Apr-2026) | Defects | Internal | Others |  | 4 Internal defects | 1. UI design issues (3) 2. Add more than 40 user then it gives an error in QA envirornment |  | RCA: UI design are minor issues and fixed it. One defect is due to it is working in local environment but getting in QA environment. Mitigation Plan: Increase the testing coverage and validate the application in various environments to ensure the application is working fine in different environments as per the expectations. Also do more unit testing to address these kind of defects during development phase. | Team | Closed | 2026-04-10
52 | 2026-04-10 | 26.05 - Sprint 3 (27-Mar-2026 to 9-Apr-2026) | Code review comments | Internal | Others |  | 7 Code review comments | 1. 2 new peer testing comments; the new parameter name was not replaced in all the areas. Additionally, we have fixed the 3 existing issues as well. Missed adding logic for bottom-line bidding and checkbox visibility control (2) Data issue (2) Missed to save the value of checkbox 2. Error during delete the existing entry. Missed adding logic for bottom-line bidding and checkbox visibility control (2) Data issue (2) Missed to save the value of checkebox 3. UI issues |  | RCA: Out of 7 CRC, 3 were POV comments provided by PO during internal reviews 4 were found during peer testing. Mitigation plan: Team has reduced the POV comments compared to previous sprints.Team is understanding the BOH better and they need to understand the application functionality better to reduce the POV and peer review comments.Team to follow the best coding standards and refer to the coding checklist documents | Team | Closed | 2026-04-10
53 | 2026-04-24 | 26.05 - Sprint 4 (10-Mar-2026 to 23-Apr-2026) | Defects | Internal | Others |  | 1 Internal defect | Data not retaining while uploading image (Data Issue) |  | RCA:Data not retaining while uploading image (Data Issue). Mitigation Plan: To do more unit testing to address these kind of defects during development phase itself and check the data in various environments to resolve the data issue. | Team | Closed | 2026-04-24

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Config
Sprint | #VALUE! | Relevantz Co Owned | #VALUE! | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted |  | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | #VALUE! | #VALUE! |  | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | #VALUE! | #VALUE! |  | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 100% | 20% |  |  |  | CF |  | Excellent |  | 25
Code Quality Index | #VALUE! | #VALUE! |  | Velocity
Unit Testing & Code Coverage | #VALUE! | #VALUE! |  | Goal | 20
Backlog Health | #VALUE! | #VALUE!
Code Coverage
|  |  |  | Goal | 90%
|  |  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  |  | Below Avg | 15 | Labels | Values |  | Story Points | 30
|  |  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  |  | Excellent | 30 | 15 | 10
|  |  |  | Total | 90 | 20 | 10
[6 empty] | 25 | 10
50

## Instructions
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## ExportData
FOH | 4.17 Sprint 1 (29-Mar-2024 to 11-Apr-2024) | 4.17 Sprint 1 | 2024-03-29 | 11-Apr-2024 | 2024 | 32 | 32 | 1 | 25 | 0.9 | 2 | 1 | 0 | 0 | 0.97594 | 1 | 1 | 1 | 0.90625
FOH | 4.17 Sprint 2 (12-Apr-2024 to 25-Apr-2024) | 4.17 Sprint 2 | 2024-04-12 | 25-Apr-2024 | 2024 | 21 | 39 | 1 | 25 | 0.9 | 1 | 2 | 0 | 0 | 0.97846 | 1 | 1 | 1 | 0.92308
FOH | 4.17 Sprint 3 (26-Apr-2024 to 09-May-2024) | 4.17 Sprint 3 | 2024-04-26 | 09-May-2024 | 2024 | 29 | 10 | 0.34483 | 25 | 0.9 | 2 | 0 | 0 | 0 | 0.77954 | 0.34483 | 1 | 1 | 0.8
FOH | 4.17 Sprint 4 (10-May-2024 to 23-May-2024) | 4.17 Sprint 4 | 2024-05-10 | 23-May-2024 | 2024 | 13 | 13 | 1 | 25 | 0.9 | 2 | 1 | 0 | 0 | 0.95538 | 1 | 1 | 1 | 0.76923
FOH | 4.18 Sprint 1 (24-May-2024 to 06-Jun-2024) | 4.18 Sprint 1 | 2024-05-24 | 06-Jun-2024 | 2024 | 40 | 32 | 0.8 | 25 | 0.9 | 0 | 2 | 1 | 0 | 0.92263 | 0.8 | 1 | 0.96 | 0.9375
FOH | 4.18 Sprint 2 (07-Jun-2024 to 20-Jun-2024) | 4.18 Sprint 2 | 2024-06-07 | 20-Jun-2024 | 2024 | 30 | 30 | 1 | 25 | 0.9 | 2 | 2 | 1 | 0 | 0.962 | 1 | 1 | 0.96 | 0.86667
FOH | 4.18 Sprint 3 (21-Jun-2024 to 18-Jul-2024) | 4.18 Sprint 3 | 2024-06-21 | 18-Jul-2024 | 2024 | 44 | 44 | 1 | 25 | 0.9 | 3 | 1 | 1 | 0 | 0.96836 | 1 | 1 | 0.96 | 0.90909
FOH | 4.18 Sprint 4 (19-Jul-2024 to 01-Aug-2024) | 4.18 Sprint 4 | 2024-07-19 | 01-Aug-2024 | 2024 | 37 | 37 | 1 | 25 | 0.9 | 4 | 0 | 0 | 0 | 0.97378 | 1 | 1 | 1 | 0.89189
FOH | 4.18 Sprint 5 (02-Aug-2024 to 15-Aug-2024) | 4.18 Sprint 5 | 2024-08-02 | 15-Aug-2024 | 2024 | 15 | 15 | 1 | 25 | 0.9 | 1 | 3 | 0 | 0 | 0.95 | 1 | 1 | 1 | 0.73333
FOH | 4.18 Sprint 6 (16-Aug-2024 to 29-Aug-2024) | 4.18 Sprint 6 | 2024-08-16 | 29-Aug-2024 | 2024 | 21 | 21 | 1 | 25 | 0.9 | 2 | 2 | 0 | 0 | 0.96143 | 1 | 1 | 1 | 0.80952
FOH | 4.18 Sprint 7 (30-Aug-2024 to 12-Sep-2024) | 4.18 Sprint 7 | 2024-08-30 | 12-Sep-2024 | 2024 | 38 | 38 | 1 | 25 | 0.9 | 0 | 0 | 0 | 0 | 0.99 | 1 | 1 | 1 | 1
FOH | 4.19 Sprint 1 (13-Sep-2024 to 26-Sep-2024) | 4.19 Sprint 1 | 2024-09-13 | 26-Sep-2024 | 2024 | 31 | 31 | 1 | 26 | 1 | 2 | 0 | 3 | 0 | 0.96725 | 1 | 1 | 0.88462 | 0.93548
FOH | 4.19 Sprint 2 (27-Sep-2024 to 24-Oct-2024) | 4.19 Sprint 2 | 2024-09-27 | 24-Oct-2024 | 2024 | 33 | 45.5 | 1 | 34 | 1 | 4 | 0 | 6 | 0 | 0.95152 | 1 | 1 | 0.82353 | 0.91209
FOH | 4.19 Sprint 3 (25-Oct-2024 to 7-Nov-2024) | 4.19 Sprint 3 | 2024-10-25 | 7-Nov-2024 | 2024 | 16 | 35 | 1 | 37 | 1 | 0 | 1 | 2 | 0 | 0.9849 | 1 | 1 | 0.94595 | 0.97143
FOH | 4.19 Sprint 4 (08-Nov-2024 to 21-Nov-2024) | 4.19 Sprint 4 | 2024-11-08 | 21-Nov-2024 | 2024 | 25 | 33 | 1 | 36 | 1 | 0 | 0 | 3 | 0 | 0.98333 | 1 | 1 | 0.91667 | 1
FOH | 4.19 Sprint 5 (22-Nov-2024 to 19-Dec-2024) | 4.19 Sprint 5 | 2024-11-22 | 19-Dec-2024 | 2024 | 60 | 70 | 1 | 46 | 1 | 2 | 1 | 3 | 0 | 0.98053 | 1 | 1 | 0.93478 | 0.95714
FOH | 4.20 Sprint 1 (20-Dec-2024 to 16-Jan-2025) | 4.20 Sprint 1 | 2024-12-20 | 16-Jan-2025 | 2025 | 35 | 46 | 1 | 46 | 1 | 1 | 0 | 14 | 0 | 0.93587 | 1 | 1 | 0.69565 | 0.97826
FOH | 4.20 Sprint 2 (17-Jan-2024 to 30-Jan-2025) | 4.20 Sprint 2 | 2024-01-17 | 30-Jan-2025 | 2025 | 22 | 27 | 1 | 44 | 1 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1
FOH | 4.20 Sprint 3 (31-Jan-2025 to 13-Feb-2025) | 4.20 Sprint 3 | 2025-01-31 | 13-Feb-2025 | 2025 | 25 | 31 | 1 | 43.5 | 1 | 2 | 0 | 4 | 0 | 0.97193 | 1 | 1 | 0.90805 | 0.93548
FOH | 4.20 Sprint 4 (14-Feb-2025 to 27-Feb-2025) | 4.20 Sprint 4 | 2025-02-14 | 27-Feb-2025 | 2025 | 38 | 38 | 1 | 35.5 | 1 | 0 | 0 | 13 | 0 | 0.92676 | 1 | 1 | 0.6338 | 1

## Data (2025)
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | last sprint? | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
4.17 Sprint 1 (29-Mar-2024 to 11-Apr-2024) | 32 | 32 | 100% | 25 | 90% | 2 | 1 | 0 | 0 | 30 | No | Regression testing completed for all modules. |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.17 Sprint 2 (12-Apr-2024 to 25-Apr-2024) | 21 | 39 | 100% | 25 | 90% | 1 | 2 | 0 | 0 | 30 | No | Completed all the assigned stories and addition to that completed Stretch Stories - 18 SP. |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.17 Sprint 3 (26-Apr-2024 to 09-May-2024) | 29 | 10 | 34.48% | 25 | 90% | 2 | 0 | 0 | 0 | 25 | No | PR approval for two stories (21 sp) delayed from Client side. |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.17 Sprint 4 (10-May-2024 to 23-May-2024) | 13 | 13 | 100% | 23.5 | 90% | 2 | 1 | 0 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.18 Sprint 1 (24-May-2024 to 06-Jun-2024) | 40 | 32 | 80% | 23.5 | 90% | 0 | 2 | 1 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.18 Sprint 2 (07-Jun-2024 to 20-Jun-2024) | 30 | 30 | 100% | 21.25 | 90% | 2 | 2 | 1 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.18 Sprint 3 (21-Jun-2024 to 18-Jul-2024) | 44 | 44 | 100% | 29.75 | 90% | 3 | 1 | 1 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.18 Sprint 4 (19-Jul-2024 to 01-Aug-2024) | 37 | 37 | 100% | 35.75 | 90% | 4 | 0 | 0 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.18 Sprint 5 (02-Aug-2024 to 15-Aug-2024) | 15 | 15 | 100% | 31.5 | 90% | 1 | 3 | 0 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.18 Sprint 6 (16-Aug-2024 to 29-Aug-2024) | 21 | 21 | 100% | 29.25 | 90% | 2 | 2 | 0 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.18 Sprint 7 (30-Aug-2024 to 12-Sep-2024) | 38 | 38 | 100% | 27.75 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.19 Sprint 1 (13-Sep-2024 to 26-Sep-2024) | 31 | 31 | 100% | 26.25 | 100% | 2 | 0 | 3 | 0 | 30 | No | 45834 is POC |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.19 Sprint 2 (27-Sep-2024 to 24-Oct-2024) | 33 | 45.5 | 100% | 33.875 | 100% | 4 | 0 | 6 | 0 | 30 | No | 4 Week Sprint |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.19 Sprint 3 (25-Oct-2024 to 7-Nov-2024) | 16 | 35 | 100% | 37.375 | 100% | 0 | 1 | 2 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.19 Sprint 4 (08-Nov-2024 to 21-Nov-2024) | 25 | 33 | 100% | 36.125 | 100% | 0 | 0 | 3 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.19 Sprint 5 (22-Nov-2024 to 19-Dec-2024) | 60 | 70 | 100% | 45.875 | 100% | 2 | 1 | 3 | 0 | 30 | Yes | 4 Week Sprint - Regression Sprint |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.20 - Sprint 1 (20-Dec-2024 to 16-Jan-2025) | 35 | 46 | 100% | 46 | 100% | 1 | 0 | 14 | 0 | 30 | No | Team took all the defects in backlog/Existing Issues, focused on addressing for the upcoming release |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.20 - Sprint 2 (17-Jan-2024 to 30-Jan-2025) | 22 | 27 | 100% | 44 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.20 - Sprint 3 (31-Jan-2025 to 13-Feb-2025) | 25 | 31 | 100% | 43.5 | 100% | 2 | 0 | 4 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.20 - Sprint 4 (14-Feb-2025 to 27-Feb-2025) | 38 | 38 | 100% | 35.5 | 100% | 0 | 0 | 13 | 0 | 30 | YEs |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.21 - Sprint 1 (28-Feb-2025 to 13-Mar-2025) | 26 | 31 | 100% | 31.75 | 100% | 4 | 0 | 0 | 0 | 30 | No |  |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.21 - Sprint 2 (14-Mar-2025 to 27-Mar-2025) | 32 | 32 | 100% | 33 | 100% | 1 | 2 | 0 | 0 | 30 | No | 1 Story Carry Forwarded In QA(Mike) Bucket Mike was on PTO for last one week and once he was back he was busy in Release |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.21 - Sprint 3(27-Mar-2025 to 10-Apr-2025) | 31 | 34 | 100% | 33.75 | 100% | 3 | 1 | 0 | 1 | 30 | No | Completed all the assigned stories. 3 Stretch stories has been rolled over to the next sprint 47671-Ready for Testing 47817 and 47548 - Development is in Progress |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.21 - Sprint 4(11-Apr-2025 to 24-Apr-2025) | 41 | 33 | 80.49% | 32.5 | 95% | 1 | 0 | 3 | 0 | 30 | Yes | 1 Story in Ready For Testing - Carry forwarded because of Planned PTO. Client aware of it 5 Stretch Stories Carry Forwarded 47575 - Ready For Testing 47901, 47548, 44984 and 45067 - Development is in Progress |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.22 - Sprint 1(25-Apr-2025 to 08-May-2025) | 35 | 31 | 88.57% | 32.5 | 95% | 5 | 0 | 2 | 0 | 30 | No | 1 Assigned story got carry forwarded - due to technical complexities​ and 7 Stretch stories got carried over. |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.22 - Sprint 2(09-May-2025 to 22-May-2025) | 30 | 38 | 126.7% | 34 | 100% | 1 | 0 | 1 | 0 | 30 | No | 8 Stretch stories Carry Forwarded - Stories started at the end of sprint. 4 of the stories in PR |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.22 - Sprint 3(23-May-2025 to 5-June-2025) | 22 | 28 | 127.3% | 32.5 | 100% | 1 | 0 | 1 | 2 | 30 | No | All assigned stories were completed. 8 stretch stories have been carried forward as they were initiated towards the end of the sprint. Story Breakdown: 4 stretch stories from FOH Wave 4 stretch stories from FOH Total merged count: 8 stories Defects: 2 external defects were identified as existing production issues during offshore regression testing. These were successfully resolved by the development team. 1 internal stretch defect is currently in progress. |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.23 - Sprint 1(06-Jun-2025 to 18-June-2025) | 25 | 28 | 112% | 31.25 | 100% | 7 | 0 | 0 | 0 | 30 | No | All assigned stories were completed. 8 stretch stories have been carried forward as they were initiated towards the end of the sprint. |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.23 - Sprint 2(19-Jun-2025 to 3-July-2025) | 41 | 37 | 90.24% | 32.75 | 100% | 5 | 0 | 1 | 0 | 30 | No | 1 story got carry forwarded. Pending reason: Story is in onsite QA bucket. 1 bug - Development in progress |  | 100% | 90% | 80% |  | 25 |  | 90% |  | 30
4.23 - Sprint 3(4-July-2025 to 17-July-2025) | 29 | 4.25 - Sprint 4(7-Nov-2025 to 20-Nov-2025) | 0% | 31 | 100% | 7 | 0 | 0 | 0 | 30 | No | Completed all assigned stories and more
4.23 - Sprint 4(17-July-2025 to 31-July-2025) | 39 | 51 | 130.8% | 38.6667 | 100% | 2 | 0 | 1 | 0 | 30 | No | Completed all assigned stories and more
4.24 - Sprint 1(1-Aug-2025 to 14-Aug-2025) | 24 | 30 | 125% | 39.3333 | 100% | 18 | 0 | 1 | 0 | 30 | No | Completed all assigned stories and more
4.24 - Sprint 2(15-Aug-2025 to 28-Aug-2025) | 16 | 25 | 156.2% | 35.3333 | 100% | 4 | 0 | 1 | 0 | 30 | No | Completed all assigned stories and more
4.24 - Sprint 3(29-Aug-2025 to 11-Sep-2025) | 21 | 38 | 181% | 36 | 100% | 10 | 0 | 1 | 0 | 30 | No | Completed all assigned stories and more
4.24 - Sprint 4(12-Sep-2025 to 25-Sep-2025) | 44 | 45 | 102.3% | 34.5 | 100% | 4 | 0 | 0 | 0 | 30 | No | Completed all assigned stories and more
4.25 - Sprint 1(26-Sep-2025 to 9-Oct-2025) | 35 | 44 | 125.7% | 38 | 100% | 7 | 0 | 1 | 0 | 30 | No | Completed all assigned stories and more
4.25 - Sprint 2(10-Oct-2025 to 23-Oct-2025) | 41 | 47 | 114.6% | 43.5 | 100% | 0 | 0 | 1 | 0 | 30 | No | Completed all assigned stories and more
4.25 - Sprint 3(24-Oct-2025 to 6-Nov-2025) | 45 | 61 | 135.6% | 49.25 | 100% | 9 | 0 | 1 | 0 | 30 | No | Completed all assigned stories and more
4.25 - Sprint 4(7-Nov-2025 to 20-Nov-2025) | 32 | 40 | 125% | 48 | 100% | 24 | 1 | 2 | 0 | 30 | No | Completed all assigned stories and more
4.25 - Sprint 5(21-Nov-2025 to 18-Dec-2025) | 75 | 75 | 100% | 55.75 | 100% | 3 | 0 | 2 | 0 | 30 | No | Completed all assigned stories and more
26.1 - Sprint 1(19-Dec-2025 to 15-Jan-2026) | 60 | 81 | 135% | 64.25 | 100% | 25 | 2 | 6 | 0 | 30 | No | Completed all assigned stories and more
Note on B28: Priyadharshini Ravichandran: Merged the FOH and FOH Wave Sprint metrics into a single aggregated count."