## Dashboard
BOH

## Scorecard
Project Name | GGO Mobile
Engagement Model | Relevantz Co Owned
Overall Score | 99%
Current Sprint | Q22 Mobile Sprint 1(14-Apr-2026 to 28-Apr-2026)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% | Completed all the committed stories. No RCA | 25% | 100%
Velocity | 100% | 20% |  | 20% | 95%
Defect-free Rate | 100% | 20% |  | 20% | 100%
Code Quality Index | 100% | 15% |  | 15% | 100%
Unit Testing & Code Coverage | 90% | 9% |  | 10% | 90%
Backlog Health | 100% | 10% |  | 10% | 100%
0
Completed all the committed stories. No RCA
100%
0.75
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
Q9 Sprint 2 (03-Apr-2024 to 16-Apr-2024) | 15 | 15 | 100% | 20 | 90% | 1 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q9 Sprint 3 (17-Apr-2024 to 30-Apr-2024) | 16 | 13 | 0.8125 | 20 | 0.9 | 0 | 0 | 1 | 0 | 30 | No | Internal QA reported a defect on a story while testing and issue fixing inprogress. |  | Internal QA reported a defect on a story while testing and issue fixing inprogress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q9 Sprint 4 (01-May-2024 to 14-May-2024) | 15 | 15 | 100% | 20 | 90% | 0 | 0 | 1 | 0 | 30 | No |  |  | Completed all the committed stories. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q10 Sprint 1 (15-May-2024 to 28-May-2024) | 20 | 15 | 75% | 20 | 90% | 2 | 0 | 0 | 0 | 30 | No |  |  | One story carried. Data is being sent properly, but due to a PAPI cert issue, no transactions are made. This is on the PAPI side and isn’t something to do with us. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q10 Sprint 2 (29-May-2024 to 11-Jun-2024) | 25 | 25 | 100% | 20 | 90% | 0 | 0 | 1 | 0 | 30 | No |  |  | Completed all the committed stories. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q10 Sprint 3 (12-Jun-2024 to 25-Jun-2024) | 11 | 11 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q10 Sprint 4 (26-Jun-2024 to 09-Jul-2024) | 12 | 12 | 100% | 20 | 90% | 0 | 0 | 1 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q11 Sprint 1 (10-Jul-2024 to 23-Jul-2024) | 20 | 17 | 85% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | One story carried, Code review Inprogress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q11 Sprint 2 (24-Jul-2024 to 06-Aug-2024) | 10 | 10 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q11 Sprint 3 (07-Aug-2024 to 20-Aug-2024) | 16 | 8 | 50% | 20 | 90% | 1 | 2 | 0 | 0 | 30 | No |  |  | One story carried, QA Inprogress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q11 Sprint 4 (21-Aug-2024 to 03-Sep-2024) | 18 | 13 | 72.22% | 20 | 90% | 4 | 4 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q12 Sprint 1 (4-Sep-2024 to 17-Sep-2024) | 11 | 6 | 54.55% | 20 | 90% | 0 | 0 | 3 | 2 | 30 | No |  |  | QA reported samall UI defect on a story while testing and issue fixing inprogress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q12 Sprint 2 (18-Sep-2024 to 01-Oct-2024) | 19 | 19 | 100% | 20 | 90% | 9 | 6 | 1 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q12 Sprint 3 (01-Oct-2024 to 15-Oct-2024) | 16 | 16 | 100% | 20 | 90% | 6 | 0 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q12 Sprint 4 (15-Oct-2024 to 29-Oct-2024) | 20 | 18 | 90% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | GGOM-1162 Ticket Carried Due to Mac and iOS UI Issue(In Mac and IOS, when updating the Bidder Notes the CheckIn Step 2 UI is not updating properly)
Q13 Sprint 1 (29-Oct-2024 to 12-Nov-2024) | 18 | 15 | 83.33% | 20 | 90% | 2 | 0 | 0 | 0 | 30 | No |  |  | GGOM-1182 Ticket Carried - Development completed as per AC. Somewhere facing delay when closing the popup after application selection.
Q13 Sprint 2 (12-Nov-2024 to 26-Nov-2024) | 18 | 21 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No
Q13 Sprint 3 (27-Nov-2024 to 10-Dec-2024) | 19 | 14 | 73.68% | 20 | 90% | 4 | 1 | 0 | 0 | 30 | No |  |  | GGOM-1179- Got carried over -Developemnt completed, QA testing only pending as the QA got the ticket on the last day of the sprint. This took longer as the initial development approach identified by Scott didn't work and the development approach was changed mid sprint. Also there were some unplanned offshore PTOs and Mohan's Windows machine was not available
Q13 Mobile Sprint 4 (10-Dec-2024 to 7-Jan-2025) | 24 | 37 | 100% | 20 | 90% | 15 | 5 | 0 | 2 | 30 | No
Q14 Mobile Sprint 1 (7-Jan-2025 to 21-Jan-2025) | 14 | 14 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q14 Mobile Sprint 2 (21-Jan-2025 to 4-Feb-2025) | 19 | 24 | 100% | 20 | 90% | 1 | 0 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q14 Mobile Sprint 3 (4-Feb-2025 to 18-Feb-2025) | 20 | 27 | 100% | 20 | 90% | 2 | 0 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q14 Mobile Sprint 4 (18-Feb-2025 to 4-Mar-2025) | 22 | 22 | 100% | 20 | 90% | 11 | 1 | 0 | 0 | 30 | No |  |  | The review comments were because of we missed something during development . Comparing everything with Go Time app was required while working on NextGen
Q15 Mobile Sprint 1 (4-Mar-2025 to 18-Mar-2025) | 17 | 16 | 94.12% | 20 | 90% | 4 | 0 | 0 | 0 | 30 | No |  |  | 1 story GGOM-1329 got caarried over because everyone is new to Fire base and a small script issue came up after upgrading to Firebase which needed additional analysis to resolve towards the end of the sprint
Q15 Mobile Sprint 2 (18-Mar-2025 to 1-Apr-2025) | 19 | 13 | 68.42% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | 2 Stories has been carried forward. Because, the approach of the story had to be modified at the last moment given it wasn't working. As per the new approach in collaboration with Sean , these stories will require some more code changes and pipeline updates to complete the story based on the new requirements.
Q15 Mobile Sprint 3 (1-Apr-2025 to 15-Apr-2025) | 18 | 24 | 100% | 20 | 90% | 5 | 1 | 1 | 0 | 30 | No |  |  | 1. Two Stretch Stories have been carried forward because we took the story at the end of the sprint. Also Scope of the story and story points got changed at the end of the sprint. 2. Regarding CRC: The review comments were because of developer missed something during development. And we will ensure to understand and implement the AC, and follow coding standards properly. 3. QA Defect: This defect is not something related to this sprint. Offshore QA found this bug while doing the regression Testing. And he put the defect in the backlog for future work.
Q15 Mobile Sprint 4 (15-Apr-2025 to 29-Apr-2025) | 24 | 24 | 100% | 20 | 90% | 9 | 1 | 2 | 0 | 30 | No |  |  | Completed all the committed stories. QA Defect: This defect is not something related to this sprint. Offshore QA found this bug while doing the regression Testing. And he put the defect in the backlog for future work. Regarding CRC: The review comments were because of developer missed something during development. And we will ensure to understand and implement the AC, and follow coding standards properly.
Q16 Mobile Sprint 1 (29-Apr-2025 to 13-May-2025) | 17 | 24 | 100% | 20 | 90% | 0 | 0 | 2 | 0 | 30 | No |  |  | Completed all the committed stories. QA Defect: 2 defects is not something related to this sprint. Offshore QA found this bug while doing the regression Testing. And he put the defect in the backlog for future work. 1 Stretch Story defect under GGO-1185 ->Rolled over due to the upgrade of .net 9 ,we are unable to edit some price fields.And team is working on that |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q16 Mobile Sprint 2 (13-May-2025 to 27-May-2025) | 20 | 20 | 100% | 20 | 90% | 2 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. Regarding CRC: The review comments were because of developer missed to update the display message during development. And we will ensure to understand and implement the AC, and follow coding standards properly. Also, 3 Stretch stories got carry forward due to .net9 Upgrade
Q16 Mobile Sprint 3 (27-May-2025 to 10-June-2025 ) | 18 | 21 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | 3 Story points were removed from the sprint board because, following the .NET 9 upgrade, the change project search control stopped functioning as expected. As a result, we were unable to proceed with resolving this bug. Two stretch stories, comprising six story points, were successfully completed and compensated. Additionally, two other stretch stories, which were picked up on the last day of the sprint, have been carried forward to the next sprint. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
Q16 Mobile Sprint 4 (10-June-2025 to 24-June-2025) | 19 | 19 | 100% | 20 | 90% | 2 | 1 | 1 | 0 | 30 | No |  |  | Completed all the assigned stories. Additionally, two other stretch stories was Unable to complete the ticket due to a dependency. Therefore, it has been flagged and moved to the backlog. Defect that were found was completed within the sprint by the team
Q17 Mobile Sprint 1 (24-June-2025 to 08-July-2025) | 19 | 22 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories.
Q17 Mobile Sprint 2 (08-July-2025 to 22-July-2025) | 18 | 15 | 83.33% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Pending: 1 story got carried forward.GGOM-1452 1. Understanding the legacy close section logic for time zones and section status was challenging. 2. In addition to that, we found the issue on the API status logic and informed to GGO team. They removed the status logic in API and we implemented the same in the mobile app. It's took long time. 3. We don't have a time to give QA testing.
Q17 Mobile Sprint 3 (22-July-2025 to 5-Aug-2025) | 19 | 24 | 100% | 20 | 90% | 3 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories.
Q17 Mobile Sprint 4(5-Aug-2025 to 19-Aug-2025) | 22 | 24 | 100% | 20 | 90% | 1 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories.
Q18 Mobile Sprint 1(19-Aug-2025 to 2-Sep-2025) | 18 | 15 | 83.33% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Pending: 1 story got carried forward.GGOM-1500 carried Missed handling the scenario for multiple organizations in the dropdown during analysis. Due to this oversight, last-minute development and testing could not be completed. The application is currently crashing on the Mac platform.
Q18 Mobile Sprint 2(2-Sep-2025 to 16-Sep-2025) | 22 | 24 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q18 Mobile Sprint 3(17-Sep-2025 to 30-Sep-2025) | 17 | 17 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q18 Mobile Sprint 4(30-Sep-2025 to 14-Oct-2025) | 21 | 21 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q19 Mobile Sprint 1(14-OCT-2025 to 28-Oct-2025) | 16 | 21 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q19 Mobile Sprint 2(28-OCT-2025 to 11-Nov-2025) | 22 | 22 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q19 Mobile Sprint 3(11-Nov-2025 to 25-Nov-2025) | 22 | 22 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q19 Mobile Sprint 4(25-Dec-2025 to 09-Dec-2025) | 13 | 22 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q20 Mobile Sprint 1(09-Dec-2025 to 06-Jan-2026) | 21 | 42 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q20 Mobile Sprint 2(06-Jan-2026 to 20-Jan-2026) | 19 | 19 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed all the committed stories. No RCA
Q20 Mobile Sprint 3(20-Jan-2026 to 03-Feb-2026) | 16 | 19 | 100% | 20 | 90% | 0 | 0 | 1 | 0 | 30 | No |  |  | Completed all the committed stories.
Q20 Mobile Sprint 4(03-Feb-2026 to 17-Feb-2026) | 23 | 27 | 100% | 20 | 90% | 2 | 0 | 0 | 0 | 30 | No | 1 | 1 | Completed all the committed stories.
Q21 Mobile Sprint 1(17-Feb-2026 to 03-Mar-2026) | 23 | 23 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No | 2 | 2 | Completed all the committed stories.
Q21 Mobile Sprint 2(03-Mar-2026 to 17-Mar-2026) | 24 | 24 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No | 1 | 1 | Completed all the committed stories. No RCA
Q21 Mobile Sprint 3(17-Mar-2026 to 31-Mar-2026) | 17 | 20 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No | 6 | 6 | Completed all the committed stories. No RCA
Q21 Mobile Sprint 4(31-Mar-2026 to 14-Apr-2026) | 22 | 25 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No | 2 | 2 | Completed all the committed stories. No RCA
Q22 Mobile Sprint 1(14-Apr-2026 to 28-Apr-2026) | 21 | 21 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | Yes | 3 | 3 | Completed all the committed stories. No RCA
Q22 Mobile Sprint 2(28-Apr-2026 to 12-May-2026) | 20 | 28 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | Yes | 2 | 2 | Completed all the committed stories. No RCA
Note on F1: Priyadharshini Ravichandran: This is the standard template we are using across all projects in the account. As discussed with Deepa, applying "NA" impacts both Unit Testing and Code Coverage metrics. Currently, we do not have SonarQube or any other tools available to capture screenshots or generate reports for code coverage.

## RCA
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-05-28 | Q10 Sprint 1 (15-May to 28-May) | Commitment Index deviation | External | Metric Deviation | Development completed and unit testing Inprogress. | Due to a PAPI cert issue, no transactions are made. | his is on the PAPI side and isn’t something to do with us. |  | PAPI cert issue was informed in client standup in well advanced. | Mohan | Closed | 2024-05-31 |  | Metric Deviation
3 | 2024-09-02 | Q11 Sprint 4 [21-Aug to - 03-Sep] | Commitment Index deviation | External | Metric Deviation | UI Issue | Issue with Telerik componenet |  |  | Dependant on global issue with Telerik controller. | Mohan / Vigneswari | Closed | 2024-09-03
4 | 2024-09-16 | Q12 Sprint 1 [4-Sep to - 17-Sep] | Commitment Index deviation | External | Metric Deviation | UI Issue | AC got revised and got opened with new issues. |  |  | Informed in standup to have proper impact analysis before coding. | Vigneswari | Closed | 2024-09-17 |  | Security Compliance
5 | 2024-10-01 | Q12 Sprint 2 [17-Sep to - 1-Oct] | Code Quality Index deviation | Internal | Metric Deviation | 6 CRC Comments | Development not done as per AC | Client Comments: 1. Make the package search bar look like the Supporter search bar, just like in the figma 2. Package Price label should not update with quantity change, only the price entry field should update 3. Sell Admission text should update with Theme changes properly, (see edit guest popup for details) 4. when I clicked the button to sell a new admission, selected a package, clicked the Assign admission checkbox, and then attempted to sell the new admission, I got this error. This error is probably because we removed the package icon in the search bar to make it look more like the supporter search bar 1. Fixed scrollview not updating with contents. 2. Fixed Lable placement on the UseExisitingPopup |  | Analyze AC with attention to every bullet point and create Unit test plan to cover each AC and its sub points. Have POV before the PR review | Mohankrishnan | Closed | 2024-10-01 |  | Not adhered to Policy
6 | 2024-10-29 | Q12 Sprint 3 [15-Oct to - 29-Oct] | Code Quality Index deviation | Internal | Metric Deviation |  | In Mac and IOS, when updating the Bidder Notes the CheckIn Step 2 UI is not updating properly |  |  | More analysis required | Vigneswari/Sudhakar | Closed | 2024-11-06 |  | Others
7 | 2024-11-12 | Q12 Sprint 4 [29-Oct to - 12-Nov] | Code Quality Index deviation | Internal | Metric Deviation |  | GGOM-1182 Ticket rolled over - Development completed as per AC. discovered UI issues during testing - delay when closing the popup after application selection. |  |  | Issue with BBPOS SDK so the current resolution will be to a a spinning wheel while processing the data. Also the testing was completely done by Mike Wall because he has the hardware required for testing. | Vigneswari/Sudhakar | Closed | 2024-11-12
8 | 2024-12-10 | Q13 Sprint 3(27-Nov to -10-Dec) | Commitment Index deviation | External | Metric Deviation | GGOM-1179- Got carried over. | Development completed, QA testing only pending as the QA got the ticket on the last day of the sprint | This took longer as the initial development approach identified by Scott didn't work and the development approach was changed mid sprint. | 3 days unplanned offshore PTOs and Mohan's Windows machine was not available | Nuget package update will not resolved the actual bug. Created a custom imgae control to fix the bug for mode change dark and light mode. In future required proper planning/spike story to handle these type of issues. | Sudhakar/Vigneswari | Closed | 2024-12-11
9 | 2025-01-07 | Q13 Sprint 4(10-Dec to -7-Jan) | Code Quality Index deviation | Internal | Metric Deviation | Peer Review comments | Developers didn't follow the new UI Figma documentation | Developers missed implementing AC properly | Missed following proper coding standards | Understand and implement AC , Follow coding standards properly | Sudhakar/Vigneswari | Closed | 2025-01-07
10 | 2025-03-04 | Q14 Mobile Sprint 4 (18-Feb-2025 to 4-Mar-2025) | Code Quality Index deviation | Internal | Metric Deviation | Peer Review comments | The review comments were because of we missed something during development . | Comparing everything with Go Time app was required while working on NextGen |  | Before starting work on any new NextGen story, proper understanding of existing Go Time functionality is required. There is a learning curve for Nextgen stories as it needs to be compared with the existing Go Time functionality ​ | Sudhakar/Vigneswari | Closed | 2025-03-04
11 | 2025-03-18 | Q15 Mobile Sprint 4 (4-Mar-2025 to 18-Mar-2025) | Commitment Index deviation | Internal | Metric Deviation |  | 1 story GGOM-1329 got caarried over because everyone is new to Fire base and a small script issue came up after upgrading to Firebase which needed additional analysis to resolve towards the end of the sprint | This issue never happened in Dev environment but showed in after deployment in TST environment |  | Firebase is new for the team and for any new platform there needs to be some knowledge transfer and the team had to get relevant access and learn the entire process | Sudhakar/Vigneswari | Closed | 2025-03-18
12 | 2025-04-01 | Q15 Mobile Sprint 2 (18-Mar-2025 to 1-Apr-2025) | Commitment Index deviation - Story Carry Forward | Internal | Metric Deviation | GGOM-1326 and GGO-1331- Got carried over. | 2 Stories has been carried forward. Because, the approach of the story had to be modified at the last moment given it wasn't working. As per the new approach in collaboration with Sean , these stories will require some more code changes and pipeline updates to complete the story based on the new requirements. |  |  | Investigation is required before we implement any new feature like FireBase in NextGen | Sudhakar/Vigneswari | Closed | 2025-04-15
13 | 2025-04-15 | Q15 Mobile Sprint 3 (1-Apr-2025 to 15-Apr-2025) | Code Quality Index deviation Peer CRC-1 Onsite CRC-4 Client CRC-1 | Internal/External | Metric Deviation | Peer CRC-1 Onsite CRC-4 Client CRC-1 | The review comments were because of we missed something during development . Below are the comment we have received: Peer CRC :1 Once internet is disconnected during the transaction popup opens, its accepting the swipe card payment and moving to pin entry screen. Onsite: 4 1.Error popup should display infront of transaction popup. We should not close transaction popup. Ref Android story GGOM-1344. 2. Timeout error should be remove. 3. UI issues 4. Bugs are identified while testing. External:1 1. Canceled car reader listener after closed TP. |  |  | CRC: Understand and implement AC , Follow coding standards properly | Sudhakar/Vigneswari/Mohan | Closed | 2025-04-15
13 | 2025-04-29 | Q15 Mobile Sprint 4 (15-Apr-2025 to 29-Apr-2025) | Code Quality Index deviation | Internal/External | Metric Deviation | Peer CRC-2 Onsite CRC-7 Client CRC-1 | The review comments were because of we missed something during development . Below are the comment we have received: Peer CRC :2 * Some variables and methods were not used, Need to remove. * Need to remove redundant assisgnment Onsite: 7 1. Received Build error - Fixed 2. Typo errors 3. The card reader was not detected after battery critical warning on Test Cardreader option. 4. Develop branch code has been missed in the PR branch. - Fixed 5. Don't introduce unnecessary codes. - Fixed 6. Test card reader option page swipe is not working after fall back and Insert card 7. App crashed after connected the cardreader on the Test Card Reader page External:1 1. Fallback error case was not working as expected when the battery level is critical. | Cosmetic Errors,Developers missed to follow coding standards | Missed to implement AC | CRC: Ensure team understand and implement AC , Follow coding standards properly | Sudhakar/Vigneswari/Mohan | Closed | 2025-05-13
14 | 2025-05-27 | Q16 Mobile Sprint 2 (13-May-2025 to 27-May-2025) | Code Quality Index deviation | Internal/External | Metric Deviation | Onsite - 2 | Onsite: 2 1. Card is not detecting Swipe/Tap on Testcard Reader after card has been removed from reader after message "Remove card to start a new transaction" appears. 2. 'Please remove card.' message should only display for Tap processing not for Dip card | Developers missed implementing AC properly | Missed following proper coding standards | Understand and implement the AC , Follow coding standards properly.Also Mandate peer code reviews to ensure adherence to AC and standards.​ Maintain and share up-to-date coding guidelines. | Sudhakar/Vigneswari | Closed | 2025-06-10
15 | 2025-06-24 | Q16 Mobile Sprint 4 (13-May-2025 to 27-May-2025) | Code Quality Index deviation | Internal/External | Metric Deviation | Code review comment | Onsite: 2 1. Refactor the code and updated automation id with proper standard. 2. Edit link was not working in Mobile. Client CRC: 1. Refactor the code | Suggestions Provided by the onsite and client to refractor the code |  | CRC: Ensure team understand and implement AC , Follow coding standards properly | Sudhakar/Vigneswari/Mohan | Closed | 2025-06-24
16 | 2025-08-22 | Q17 Mobile Sprint 2 (08-July-2025 to 22-July-2025) | Commitment Index deviation - Story Carry Forward | Internal | Metric Deviation | Commitment Index Deviation | 1 story got carried forward.GGOM-1452 1. Understanding the legacy close section logic for time zones and section status was challenging. 2. In addition to that, we found the issue on the API status logic and informed to GGO team. They removed the status logic in API and we implemented the same in the mobile app. It's took long time. 3. We don't have a time to give QA testing." | Analysis took more time to complete |  | Similar type of requirement has to identified and informed with client in well advance. | Sudhakar/Vigneswari/Mohan | Closed | 2025-08-05
17 | 2025-08-05 | Q17 Mobile Sprint 3 (22-July-2025 to 5-Aug-2025) | Code Quality Index deviation | Internal/External | Metric Deviation | Code review comment | Onsite: 3 1. iOS - Search bar showing multiple selected item. First select one supporter then click Reset button. repeat the same and open the search bar. Now could see multiple item got selected. 2. iOS crashed the app. - Repeat point 1 and scroll the search bar then app got crashed. 3. macOS: While clicking on Login as bidder button, I would see the white window on the screen. |  |  | Understand and implement the AC , Follow coding standards properly.Also Mandate peer code reviews to ensure adherence to AC and standards.​ Maintain and share up-to-date coding guidelines. | Sudhakar/Vigneswari/Mohan | Closed | 2025-08-05
18 | 2025-08-19 | Q17 Mobile Sprint 4(5-Aug-2025 to 19-Aug-2025) | Code Quality Index deviation | Internal/External | Metric Deviation | Code review comment | Onsite: 1 1. On moblie and tablets, the notifification message was not fully visible. | Design Issue |  | Analyze AC with attention to every bullet point and create Unit test plan to cover each AC and its sub points.One round of Unit testing is must before sending out the PR | Vigneswari/Mohan | Closed | 2025-08-19
19 | 2025-09-02 | Q18 Mobile Sprint 1(19-Aug-2025 to 2-Sep-2025) | Commitment Index deviation - Story Carry Forward | Internal | Metric Deviation | Commitment Index Deviation | Pending: 1 story got carried forward.GGOM-1500 carried Missed handling the scenario for multiple organizations in the dropdown during analysis. Due to this oversight, last-minute development and testing could not be completed. The application is currently crashing on the Mac platform. |  |  | More analysis required | Vigneswari/Sudhakar | Closed | 2025-09-16
20 | 2026-02-03 | Q20 Mobile Sprint 3(20-Jan-2026 to 03-Feb-2026) | 1 Defect | Internal | Metric Deviation | Defect free Rate | Reported bug is not part of the current sprint, it exists in develop build. |  |  | More analysis required | Vigneswari/Sudhakar | Closed | 2026-01-22
21 | 2026-02-17 | Q20 Mobile Sprint 4(03-Feb-2026 to 17-Feb-2026) | Code Quality Index deviation | Internal/External | Metric Deviation | Code review comment | Review comments : 1. The initial total due is $207.50. Then created a payment with $10. The remaining total due should be $197.50. However, the add payment page shows the initial amount $207.50. The initial total due is $207.50. Paid the entire amount. However, the add payment page shows the initial amount $207.50. This should show Zero Balance. Pay more amount. Then delete payment. Again it shows credit balance. This should shows the original total due. 2. The check number should be numeric not characters. It should allow max 6 digits. Android:The same issue as like windows. In addition to that |  |  | Understand and implement the AC , Follow coding standards properly.Also Mandate peer code reviews to ensure adherence to AC and standards.​ Maintain and share up-to-date coding guidelines. | Vigneswari/Sudhakar | Closed | 2026-02-17

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Config
Sprint | Q22 Mobile Sprint 1(14-Apr-2026 to 28-Apr-2026) | Relevantz Co Owned | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | 94.12% | 23.53% | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | 100% | 20% | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 100% | 20% |  |  | CF |  | Excellent |  | 25
Code Quality Index | 75% | 11.25% | Velocity
Unit Testing & Code Coverage | 90% | 9% | Goal | 20
Backlog Health | 100% | 10%
Code Coverage
|  |  | Goal | 90%
|  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  | Below Avg | 15 | Labels | Values |  | Story Points | 30
|  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  | Excellent | 30 | 15 | 10
|  |  | Total | 90 | 20 | 10
[5 empty] | 25 | 10
50

## Instructions
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## 3SprintData
Overall Score | 99% | 97.37% | 97.37% | 91% | 93% | 99% | 98% | 99% | 97% | 99% | 95% | 97% | 98% | 98% | 99% | 99% | 99%
Metrics | Overall Delivery | Q14 Mobile Sprint 2 (21-Jan-2025 to 4-Feb-2025) | Q14 Mobile Sprint 3 (4-Feb-2025 to 18-Feb-2025) | Q14 Mobile Sprint 4 (18-Feb-2025 to 4-Mar-2025) | Q15 Mobile Sprint 4 (15-Apr-2025 to 29-Apr-2025) | Q16 Mobile Sprint 1 (29-Apr-2025 to 13-May-2025) | Q16 Mobile Sprint 2 (14-May-2025 to 27-May-2025) | Q16 Mobile Sprint 3 (27-May-2025 to 10-June-2025 ) | Q16 Mobile Sprint 4 (10-June-2025 to 24-June-2025) | Q17 Mobile Sprint 1 (24-June-2025 to 08-July-2025) | Q17 Mobile Sprint 2 (08-July-2025 to 22-July-2025) | Q17 Mobile Sprint 3 (22-July-2025 to 5-Aug-2025) | Q17 Mobile Sprint 4(5-Aug-2025 to 19-Aug-2025) | Q17 Mobile Sprint 4(5-Aug-2025 to 19-Aug-2025) | Q18 Mobile Sprint 4(30-Sep-2025 to 14-Oct-2025) | Q19 Mobile Sprint 1(14-OCT-2025 to 28-Oct-2025) | Q19 Mobile Sprint 2(28-OCT-2025 to 11-Nov-2025)
Commitment Index | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 83% | 100% | 100% | 100% | 100% | 100% | 100%
Velocity | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Defect-free Rate | 100% | 95% | 95% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Code Quality Index | 90% | 95.83% | 92.59% | 45.45% | 58% | 100% | 90% | 100% | 90% | 100% | 100% | 90% | 96% | 96% | 100% | 100% | 100%
Unit Testing & Code Coverage | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90% | 90%
Backlog Health | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
Target
100%
95%
100%
100%
90%
100%

## ExportData
Mob | Q9 Sprint 2 (03-Apr-2024 to 16-Apr-2024) | Q9 Sprint 2 | 2024-04-03 | 2024-04-16 | April | 15 | 15 | 1 | 20 | 0.9 | 1 | 0 | 0 | 0 | 0.90818 | 1 | 1 | 1 | 0.45455
Mob | Q9 Sprint 3 (17-Apr-2024 to 30-Apr-2024) | Q9 Sprint 3 | 2024-04-17 | 2024-04-30 | April | 16 | 13 | 0.8125 | 20 | 0.9 | 0 | 0 | 1 | 0 | 0.90818 | 1 | 1 | 1 | 0.45455
Mob | Q9 Sprint 4 (01-May-2024 to 14-May-2024) | Q9 Sprint 4 | 2024-05-01 | 2024-05-14 | May | 15 | 15 | 1 | 20 | 0.9 | 0 | 0 | 1 | 0 | 0.90818 | 1 | 1 | 1 | 0.45455
Mob | Q10 Sprint 1 (15-May-2024 to 28-May-2024) | Q10 Sprint 1 | 2024-05-15 | 2024-05-28 | May | 20 | 15 | 0.75 | 20 | 0.9 | 2 | 0 | 0 | 0 | #N/A | #N/A | #N/A | 1 | #N/A
Mob | Q10 Sprint 2 (29-May-2024 to 11-Jun-2024) | Q10 Sprint 2 | 2024-05-29 | 2024-06-11 | June | 25 | 25 | 1 | 20 | 0.9 | 0 | 0 | 1 | 0 | #N/A | #N/A | #N/A | 1 | #N/A
Mob | Q10 Sprint 3 (12-Jun-2024 to 25-Jun-2024) | Q10 Sprint 3 | 2024-06-12 | 2024-06-25 | June | 11 | 11 | 1 | 20 | 0.9 | 0 | 0 | 0 | 0 | #N/A | #N/A | 1 | 1 | 1
Mob | Q10 Sprint 4 (26-Jun-2024 to 09-Jul-2024) | Q10 Sprint 4 | 2024-06-26 | 2024-07-09 | July | 12 | 12 | 1 | 20 | 0.9 | 0 | 0 | 1 | 0 | 0.98 | 1 | 1 | 0.95 | 1
Mob | Q11 Sprint 1 (10-Jul-2024 to 23-Jul-2024) | Q11 Sprint 1 | 2024-07-10 | 2024-07-23 | July | 20 | 17 | 0.85 | 20 | 0.9 | 0 | 0 | 0 | 0 | 0.9525 | 0.85 | 1 | 1 | 1
Mob | Q11 Sprint 2 (24-Jul-2024 to 06-Aug-2024) | Q11 Sprint 2 | 2024-07-24 | 2024-08-06 | August | 10 | 10 | 1 | 20 | 0.9 | 0 | 0 | 0 | 0 | 0.99 | 1 | 1 | 1 | 1
Mob | Q11 Sprint 3 (07-Aug-2024 to 20-Aug-2024) | Q11 Sprint 3 | 2024-08-07 | 2024-08-20 | August | 16 | 8 | 0.5 | 20 | 0.9 | 1 | 2 | 0 | 0 | 0.80875 | 0.5 | 1 | 1 | 0.625
Mob | Q11 Sprint 4 (21-Aug-2024 to 03-Sep-2024) | Q11 Sprint 4 | 2024-08-21 | 2024-09-03 | September | 18 | 13 | 0.72222 | 20 | 0.9 | 4 | 4 | 0 | 0 | 0.82825 | 0.72222 | 1 | 1 | 0.38462
Mob | Q12 Sprint 1 (4-Sep-2024 to 17-Sep-2024) | Q12 Sprint 1 | 2024-09-04 | 2024-09-17 | September | 11 | 6 | 0.54545 | 20 | 0.9 | 0 | 0 | 3 | 2 | 0.82636 | 0.54545 | 1 | 0.75 | 1
Mob | Q12 Sprint 2 (18-Sep-2024 to 01-Oct-2024) | Q12 Sprint 2 | 2024-09-18 | 2024-10-01 | October | 19 | 19 | 1 | 20 | 0.9 | 9 | 6 | 1 | 1 | 0.85158 | 1 | 1 | 0.9 | 0.21053
Mob | Q12 Sprint 3 (01-Oct-2024 to 15-Oct-2024) | Q12 Sprint 3 | 2024-10-01 | 2024-10-15 | October | 16 | 16 | 1 | 20 | 0.9 | 6 | 0 | 0 | 0 | 0.93375 | 1 | 1 | 1 | 0.625
Mob | Q12 Sprint 4 (15-Oct-2024 to 29-Oct-2024) | Q12 Sprint 4 | 2024-10-15 | 2024-10-29 | October | 20 | 18 | 0.9 | 20 | 0.9 | 0 | 0 | 0 | 0 | 0.965 | 0.9 | 1 | 1 | 1
Mob | Q13 Sprint 1 (29-Oct-2024 to 12-Nov-2024) | Q13 Sprint 1 | 2024-10-29 | 2024-11-12 | November | 18 | 15 | 0.83333 | 20 | 0.9 | 2 | 0 | 0 | 0 | 0.92833 | 0.83333 | 1 | 1 | 0.86667
Mob | Q13 Sprint 2 (12-Nov-2024 to 26-Nov-2024) | Q13 Sprint 2 | 2024-11-12 | 2024-11-26 | November | 18 | 21 | 1 | 20 | 0.9 | 0 | 0 | 0 | 0 | 0.99 | 1 | 1 | 1 | 1
Mob | Q13 Sprint 3 (27-Nov-2024 to 10-Dec-2024) | Q13 Sprint 3 | 2024-11-27 | 2024-12-10 | December | 19 | 14 | 0.73684 | 20 | 0.9 | 4 | 1 | 0 | 0 | 0.87064 | 0.73684 | 1 | 1 | 0.64286
Mob | Q13 Mobile Sprint 4 (10-Dec-2024 to 7-Jan-2025) | Q13 Mobile Sprint 4 | 2024-12-10 | 2025-01-07 | January | 24 | 37 | 1 | 20 | 0.9 | 15 | 5 | 0 | 2 | 0.965 | 0.9 | 1 | 1 | 1
Mob | Q14 Mobile Sprint 1 (7-Jan-2025 to 21-Jan-2025) | Q14 Mobile Sprint 1 | 2025-01-07 | 2025-01-21 | January | 14 | 14 | 1 | 20 | 0.9 | 0 | 0 | 0 | 0 | 0.99 | 1 | 1 | 1 | 1
Mob | Q14 Mobile Sprint 2 (21-Jan-2025 to 4-Feb-2025) | Q14 Mobile Sprint 2 | 2025-01-21 | 2025-02-04 | February | 19 | 24 | 1 | 20 | 0.9 | 1 | 0 | 0 | 1 | 0.97375 | 1 | 1 | 0.95 | 0.95833
Mob | Q14 Mobile Sprint 3 (4-Feb-2025 to 18-Feb-2025) | Q14 Mobile Sprint 3 | 2025-02-04 | 2025-02-18 | February | 20 | 27 | 1 | 20 | 0.9 | 2 | 0 | 0 | 1 | 0.96889 | 1 | 1 | 0.95 | 0.92593
Mob | Q14 Mobile Sprint 4 (18-Feb-2025 to 4-Mar-2025) | Q14 Mobile Sprint 4 | 2025-02-18 | 2025-03-04 | March | 22 | 22 | 1 | 20 | 0.9 | 11 | 1 | 0 | 0 | 0.90818 | 1 | 1 | 1 | 0.45455