## Dashboard
BOH

## Scorecard
Project Name | MCS
Engagement Model | Relevantz Co Owned
Overall Score | 96.33%
Current Sprint | MCS 26 Sprint 8 (24-Apr-2026 to 07-May-2026)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% | 0 | 25% | 100%
Velocity | 100% | 20% |  | 20% | 95%
Defect-free Rate | 96.67% | 19.33% |  | 20% | 100%
Code Quality Index | 80% | 12% |  | 15% | 100%
Unit Testing & Code Coverage | 100% | 10% |  | 10% | 90%
Backlog Health | 100% | 10% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
MCS 24 Sprint 17 (16-Aug-2024 to 29-Aug-2024) | 3 | 3 | 100% | 3 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 24 Sprint 18 (30-Aug -2024 to 12-Sep -2024) | 19 | 13 | 68.42% | 8 | 80% | 0 | 0 | 0 | 0 | 30 | No |  |  | Carry Forwarded to next sprint. As analysis took additional effort. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 24 Sprint 19 (13-Sep -2024 to 26-Sep -2024) | 12 | 12 | 100% | 9.33 | 100% | 0 | 2 | 4 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 24 Sprint 20 (27-Sep -2024 to 10-Oct -2024) | 18 | 18 | 100% | 11.5 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 24 Sprint 21 (11-Oct -2024 to 24-Oct -2024) | 11 | 11 | 100% | 13.5 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 24 Sprint 22 (25-Oct -2024 to 7-Nov -2024) | 11 | 11 | 100% | 13 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 24 Sprint 23 (08-Nov -2024 to 21-Nov-2024) | 13 | 7 | 53.85% | 11.75 | 80% | 0 | 2 | 1 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 24 Sprint 24 (22-Nov -2024 to 10-Dec-2024) | 25 | 12 | 48% | 10.25 | 80% | 0 | 4 | 0 | 0 | 30 | No |  |  | 1. POV is delayed due to unavailabilty of PO- Josh. 2. Since only one QA was available for this sprint, stories for this sprint was backloged in testing. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 24 Sprint 25 (11-Dec -2024 to 02 -Jan-2025) | 30 | 12 | 40% | 10.5 | 80% | 0 | 4 | 2 | 0 | 30 | Yes |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 01 (3-Jan -2025 to 16-Jan-2025) | 22 | 9 | 40.91% | 10 | 85% | 0 | 3 | 0 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 02 (17-Jan -2025 to 30-Jan-2025) | 9 | 9 | 100% | 10.5 | 90% | 0 | 2 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 03 (31-Jan -2025 to 13-Feb-2025) | 26 | 23 | 88.46% | 13.25 | 100% | 0 | 1 | 1 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 04 (14-Feb -2025 to 27-Feb-2025) | 34 | 29 | 85.29% | 17.5 | 100% | 1 | 1 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 05 (28-Feb -2025 to 13-Mar-2025) | 38 | 35 | 92.11% | 24 | 100% | 1 | 5 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 06 (14-Mar-2025 to 27-Mar-2025) | 54 | 40 | 74.07% | 31.75 | 100% | 1 | 1 | 0 | 0 | 30 | No |  |  | Milan - Onsite QA was not available. Testing Bandwidth was limited. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 07 (28-Mar-2025 to 10-Apr-2025) | 36 | 31 | 86.11% | 33.75 | 100% | 0 | 1 | 0 | 0 | 30 | No |  |  | 1 story has been carry forwarded to next Sprint, as testing is in progress |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 08 (11-Apr-2025 to 24-Apr-2025) | 12 | 25 | 100% | 32.75 | 95% | 0 | 1 | 2 | 0 | 30 | No |  |  | 1 stretch story & 2 defects have been carry forwarded to next Sprint with new estimate for testing. In one of the defect, New ACs were added and did an enhancement to this functionality of the application |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 09 (25-Apr-2025 to 08-May-2025) | 15 | 15 | 100% | 27.75 | 95% | 0 | 1 | 2 | 0 | 30 | No |  |  | 3 stretch stories & 1 defects have been carry forwarded to next Sprint with new estimate for testing. In one of the defect, This was a existing defect, while fixing new ACs were added and completed this as a enhancement. Defect Ready for peer review state. | [5 empty] | 20
MCS 25 Sprint 10 (09-May-2025 to 22-May-2025) | 18 | 23 | 100% | 23.5 | 95% | 0 | 3 | 2 | 0 | 30 | No |  |  | MCS Core: In MCS Core team all the comitted stories has been completed and started to work on the stretch stories development MCS Wave: In MCS Wave one story is getting carry forward as it needs to be reviewed by onsite developer. In the MCS Wave one Escalation has been happened in the current sprint from the client related to Code Quality is not as par Standards. | [5 empty] | 20
MCS 25 Sprint 11 (22-May-2025 to 05-Jun-2025) | 23 | 10 | 43.48% | 18.25 | 60% | 4 | 0 | 0 | 0 | 30 | No |  |  | MCS Core: In MCS Core team Most of the stories has been completed teh development and due to an Emergency leave of QA (Rajesh) the stores has kept on the backlog to test. MCS Wave: In MCS Wave all the comitted stories has been completed and the analysis of Newton Application is in progess. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 12 (06-Jun -2025 to 20-Jun-2025) | 35 | 26 | 74.29% | 18.5 | 85% | 1 | 3 | 0 | 0 | 30 | No |  |  | We have Completed most of the Comitted Stories and the remaining stories are in the testing phase and we have a testing backlog to move the stories into completed. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
MCS 25 Sprint 13 (23-Jun -2025 to 3-Jul-2025) | 42 | 33 | 78.57% | 23 | 87% | 2 | 1 | 0 | 0 | 30 | No |  |  | Completed most of the Comitted Stories and the remaining stories are in the testing phase and we have a testing backlog to move the stories into completed. | [5 empty] | 20
MCS 25 Sprint 14 (04-Jul -2025 to 17-Jul-2025) | 34 | 34 | 100% | 27 | 90% | 9 | 0 | 0 | 0 | 30 | No |  |  | Completed all the stories committed to the sprint, except the testing stories. | [5 empty] | 20
MCS 25 Sprint 15 (18-Jul -2025 to 31-Jul-2025) | 37 | 29 | 78.38% | 23 | 87% | 9 | 0 | 0 | 0 | 30 | No | [8 empty] | 20
MCS 25 Sprint 16 (1-Aug -2025 to 14-Aug-2025) | 36 | 28 | 77.78% | 23 | 87% | 5 | 0 | 0 | 0 | 30 | No | [8 empty] | 20
MCS 25 Sprint 17 (15-Aug -2025 to 28-Aug-2025) | 41 | 38 | 92.68% | 30 | 100% | 2 | 0 | 0 | 0 | 30 | No |  |  | Wave team completed the API migragion assigned to. | [5 empty] | 20
MCS 25 Sprint 18 (29-Aug -2025 to 11-Sep-2025) | 30 | 27 | 90% | 30 | 100% | 2 | 0 | 0 | 0 | 30 | No |  |  | Wave team completed the API migragion assigned to. | [5 empty] | 20
MCS 25 Sprint 19 (12-Sep -2025 to 24-Sep-2025) | 28 | 22 | 78.57% | 30 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | Wave team completed the API migragion assigned to. | [5 empty] | 20
MCS 25 Sprint 20 (25-Sep -2025 to 09-Oct-2025) | 26 | 22 | 84.62% | 30 | 100% | 10 | 1 | 0 | 0 | 30 | No |  |  | Wave team completed the API migragion assigned to. | [5 empty] | 20
MCS 25 Sprint 21 (10-Oct -2025 to 23-Oct-2025) | 23 | 19 | 82.61% | 30 | 100% | 0 | 0 | 0 | 0 | 30 | No | [8 empty] | 20
MCS 25 Sprint 22 (24-Oct -2025 to 06-Nov-2025) | 26 | 26 | 100% | 30 | 100% | 2 | 0 | 0 | 2 | 30 | No | [8 empty] | 20
MCS 25 Sprint 23 (07-Nov-2025 to 20-Nov-2025) | 28 | 32 | 114.3% | 30 | 100% | 0 | 3 | 0 | 1 | 30 | No |  |  | The issue was related to the DB end and it was fixed and gave the build to QA team. | [5 empty] | 20
MCS 25 Sprint 24 (21-Nov -2025 to 18-Dec-2025) | 42 | 42 | 100% | 30 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  | 1 QA internal defect is carry forwarded and testing in progress. | [5 empty] | 20
MCS 25 Sprint 25 (19-Dec -2025 to 15-Jan-2026) | 35 | 30 | 85.71% | 30 | 100% | 4 | 0 | 1 | 0 | 30 | No |  |  | 1 story carry forwarded and 1 story testing in progress. | [5 empty] | 20
MCS 26 Sprint 01 (16-Jan -2026 to 29-Jan-2026) | 24 | 20 | 83.33% | 30 | 100% | 5 | 1 | 0 | 0 | 30 | Yes | [8 empty] | 20
MCS 26 Sprint 02 (30-Jan -2026 to 11-Feb-2026) | 27 | 20 | 74.07% | 30 | 100% | 9 | 1 | 0 | 0 | 30 | Yes | [8 empty] | 20
MCS 26 Sprint 03 (12-Feb -2026 to 26-Feb-2026) | 25 | 22 | 88% | 30 | 100% | 1 | 0 | 0 | 0 | 30 | Yes |  |  | 1 story carry forwarded testing in progress. | [5 empty] | 20
MCS 26 Sprint 04 (27-Feb -2026 to 12-Mar-2026) | 24 | 28 | 100% | 30 | 100% | 0 | 0 | 1 | 2 | 30 | No |  |  | 1 QA internal defect Rejected and 1 Escaped defect completed other one is in Product owner verify. | [5 empty] | 20
MCS 26 Sprint 05 (13-Mar -2026 to 26-Mar-2026) | 20 | 38 | 68.42% | 30 | 100% | 4 | 1 | 0 | 2 | 30 | No | [8 empty] | 20
MCS 26 Sprint 6 (27-Mar-2026 to 09-Apr-2026) | 28 | 30 | 100% | 30 | 100% | 1 | 4 | 0 | 2 | 30 | No |  |  | 2 Escaped defects are completed | [5 empty] | 20
MCS 26 Sprint 7 (10-Mar-2026 to 23-Apr-2026) | 25 | 35 | 100% | 30 | 100% | 5 | 0 | 1 | 0 | 30 | No |  |  | 2 Escaped defects are completed | [5 empty] | 20
MCS 26 Sprint 8 (24-Apr-2026 to 07-May-2026) | 22 | 25 | 100% | 30 | 100% | 3 | 2 | 1 | 0 | 30 | No | [8 empty] | 20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20
20

## RCA
3 Why Analysis
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-09-12 | MCS 24 Sprint 18 (30-Aug to 12-Sep) | Commitment Index Deviation | Internal | Metric Deviation | Commitment Index Deviation | Carry Forwarded to next sprint. As analysis took additional effort. |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Boobalakrishnan | Inprogress | 2024-09-26 | Client is informed | Metric Deviation
2 | 2024-09-26 | MCS 24 Sprint 19 (13-Sep to 26-Sep) | Defect Findings and CRC Comments | External | Metric Deviation | 4 Defect Index and 2 CRC Comments from Client | 2 Defects - bounceback was found during Testing - Fixed and Closed | 2 Defects were Existing Issues | 2 CRC Comments were Client Suggestions on Validation Consistency and Level Ugarde | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Boobalakrishnan, Hari, Dinesh | Closed | 2024-09-26 | Client is Informed
3 | 2024-10-10 | MCS 24 Sprint 20 (27-Sep to 10-Oct) | Defect Findings | Internal | Metric Deviation | 1 Bounce back was identified. Fixed and Closed |  |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Hari | Closed | 2024-10-10 |  | Security Compliance
4 | 2024-11-07 | MCS 24 Sprint 22 (25-Oct to 7-Nov) | Defect Findings | Internal | Metric Deviation | 1 Defect was identified with respect to Integration Calculation Issues - Fixed and Closed |  |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Hari | Closed | 2024-11-07 |  | Not adhered to Policy
5 | 2024-11-21 | MCS 24 Sprint 23 (08-Nov to 21-Nov) | Commitment Index Deviation and Defect Index | Internal/External | Metric Deviation | Defects and Stories could not be closed. 2 QA Findings | 1 Defect and 1 Story could not be closed due to Client PO availability. Client PO will be back today. | 1 Defects was Existing Issues in the Production, which was in backlog, due to business requirement, the client assigned to us. (Client Developement). Defect Fixed | 1 Defect was Existing Issue. Defect was introduced by client. Analysis only completed. When analyzed, we found there is no functionality related to this issue, so we are going to implement a new feature that will oversee the future complications related to this defect. | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. Due to Client PTO's | Hari/Dinesh/Krish | Closed | 2024-12-19 | Client is Informed | Others
6 | 2024-12-10 | MCS 24 Sprint 24 (22-Nov to 10-Dec) | Commitment Index Deviation and Defect Index | Internal/External | Metric Deviation | Defects and Stories could not be closed. 4 CRC | 1. POV is delayed due to unavailabilty of PO- Josh. 2. Since only one QA was available for this sprint, stories for this sprint was backloged in testing. 3. Introduced new stories | There was one escaped defect from Production - Client Development, Client assigned this Production Issue, which was in Backlog and assigned to the Offshore Team - Business Decision | Internal Defect - Client Development, Client assigned this Production Issue, which was in Backlog and assigned to the Offshore Team - Business Decision | 1. POV is delayed due to unavailabilty of PO- Josh. 2. Since only one QA was available for this sprint, stories for this sprint was backloged in testing. (Client QA is on Vacation) The Team is currently working on the newly added commit stories, they are analyzing the stories assigned to them | Hari/Dinesh/Krish | Closed | 2025-01-02 | Client is Informed.
7 | 2025-01-02 | MCS 24 Sprint 25 (11-Dec to 02 -Jan) | Commitment Index Deviation, Defect Findings and CRC Comments | Internal/External | Metric Deviation | Defects and Stories could not be closed. 4 CRC | 1. Since only one QA was available for this sprint, stories for this sprint was backloged in testing. Client QA was on Leave. 2. Introduced new stories - Client wants to put onhold on the current story and wanted to work on another one | The Team was working on Defects. The Defects were Existing Issues, which was Client Development. | Functional and Logical Changes: 1. this one still needs to be changed 2. Performing the sort here does not guarantee that the data will be sorted correctly after it is grouped in the devexpress report. This field should be selected as a column named [SORT_KEY], just like the [GROUP_*] columns, and then sorting should be performed in the report. 3. Since this function returns just a single value and unit, change its declaration to void FormatWeightBasedOnThreshold(double grams, out double value, out double unit) 4. According to the incident name, only GDSNConnect import should perform this conversion. Check Plugin.ItemSource to figure out what kind of import is running. | SRX25080 - was introduced as a new production escalation task from Josh. Requested to Prioritize and release it as a HotFix. Client was out for last week hence PR approval and confirmation for any blockers were on-hold. Since Client QA(Milan) was on leave for the entire month. Only 1 QA - Andrews was available for testing. He was Involved in testing Client DEV stories as well. The Team will makesure to address the CRC moving forward. | Hari/Dinesh/Krish | Closed | 2025-01-20 | Client is Informed.
8 | 2025-01-16 | MCS 25 Sprint 1 (3-Jan to 16-Jan) | Commitment Index Deviation,and CRC Comments | Internal/External | Metric Deviation | 3 CRC Comments 1. Logical Suggestions 2. Missed to add code changes in another instance | 3 Story was Carry forwarded 1. New Escalation was reported - Completed 2. OAuth integration has dependency on SMTP approval from Relevantz for dev testing to be done. 3. Import proce contracts - UI has been completed after initial POV approval and working on backend for the same 4. Optiomazation of cafeteria permission - Need to combine the cafeteria category based user role permissions into the fetch query while login |  |  | Three Stories were carry forwarded. The Team is currently working on that. The Team will makesure to address the CRC moving forward | Hari/Dinesh/Krish | Closed | 2025-01-31 | Client is Informed.
9 | 2025-01-30 | MCS 25 Sprint 2 (17-Jan to 30-Jan) | Commitment Index Deviation,and CRC Comments | Internal/External | Metric Deviation | 1. CRC Comments 2. Escaped Defects 3. Story Being Carry Forwarded 4. Under estimated Stories | CRC Comments The Team got some Logical comments and Q&A, which were resolved. | 1 Escaped Defect was found during another development and the Offshore Team fixed and provided the fix which went through Hotfix. | 3. Story Being Carry Forwarded 4. Under estimated Stories The Stories had new AC that has been updated and all the stories started as EPIC and moved as development. Client was informed. Development was completed. There is QA Bandwidth | TWo Stories were carry forwarded. The Team has completed DEV work, its in QA. The Team will makesure to address the CRC moving forward | Hari/Dinesh/Krish | Closed | 2025-02-13 | Client is informed
10 | 2025-02-13 | MCS 25 Sprint 4 (31-Jan -2025 to 13-Feb-2025) | 1 CRC Comment, 2 Story Carry Forwarded, and 1 Defect | Internal/External | Metric Deviation | 1. CRC Comments 2. Escaped Defects 3. Story Being Carry Forwarded 4. Under estimated Stories | CRC Comment - 1 The Team got some Logical comment, which were resolved. | 1 Stories are carry forwarded - Currently in Testing | 1 Defect was Existing Issue. Defect was moved from Backlog. Analysis only completed. | TWo Stories were carry forwarded. The Team has completed DEV work, its in QA. The Team will makesure to address the CRC moving forward | Hari/Dinesh/Krish | Closed | 2025-02-27 | Client is informed. The MCS Team has only one QA (Relevantz) who is testing all stories, it takes time to complete ezch story considering they need to test the funtionality End-End irrespective of the stories feature.
11 | 2025-02-27 | MCS 25 Sprint 4 (14-Feb -2025 to 27-Feb-2025) | 2 CRC Comment, 2 Story Carry Forwarded, and 1 Defect | Internal/External | Metric Deviation | 1. CRC Comments 2. Escaped Defects 3. Story Being Carry Forwarded | 2 CRC Comments one is internal for Logic Change and Another one is from Client for a Suggestion for the New Component created by our Developer | 2 Stories are carry forwarded - One is Currently in Testing and another is in POV. The Client added additional AC/Requirements after the Dev completion, so the work extended | 1 Defect was an issue which needs to fixed in PROD. This is Client Development Root causse is found and it is fixed. As of now they are going fix the issue with script change provide by us. Defect is fixed as of now. (Store Procedure Script) It is fixed in the PROD | All the issues were fixed and addressed | Hari/Dinesh | Closed | 2025-03-13
12 | 2025-03-13 | MCS 25 Sprint 5 (28-Feb -2025 to 13-Mar-2025) | CRC Comments, Defects, Story Being Carry Forwarded | Internal/External | Metric Deviation | Internal CRC, External CRC, 1 External Defect and Story Being Carry forwarded | CRC: Internal - Logical Suggestion Usage Of DBNull.value should be replaced with some other valid conditions External CRC: (Suggestion and Code Refactoring) 1. When we will use DBItems.Cache.TryGetCatalogNumberInfo, this will not be needed anymore Fix the catalog number picker button. This will not return a usable path "instead of all this, let's just use one setting, called DatabaseType, which will correspond to the DatabaseType enum. The names will be hardcoded." These should be in PascalCase | 1 External Defect which was minor and Still its in Progress because it needs support from Nutrition Team | 2 Story has been carry forwarded due to Testing bandwidth and Laptop issue for the developer | The Team will work on CRC and have provided the plan where they will work on mitigating these issues in the future by having test plans. | Hariharan | Closed | 2025-03-27 | Testing Bandwidth and Laptop Issue for Developer
13 | 2025-03-27 | MCS 25 Sprint 6 (14-Mar-2025 to 27-Mar-2025) | 3 Stories were Carry Forwarded | External | Metric Deviation | 3 Stories were Carry Forwarded | 3 Stories were Carry Forwarded Milan - Onsite QA was not available. Testing Bandwidth was limited. |  |  |  | Hari/Kalai | Closed | 2025-04-10
14 | 2025-04-10 | MCS 25 Sprint 7 (28-Mar-2025 to 10-Apr-2025) | 1 story has been carry forwarded as it is in testing phase | External | Metric Deviation | 1 Stories were Carry Forwarded | 1 External code review comment has been given by Rudy related to the application histort tracker | Nil | 1 Story has been carry forwarded as it is in testing phase | The Team will work on CRC and have provided the plan where they will work on mitigating these issues in the future by having test plans. | kalai | Closed | 2025-04-23
15 | 2025-04-24 | MCS 25 Sprint 8 (11-Apr-2025 to 24-Apr-2025) | 2 defects have been carry forwarded to next Sprint with new estimate for testing. In one of the defect, New ACs were added and did an enhancement to this functionality of the application | External | Metric Deviation | 1 stretch Story and 2 external defects were Carry Forwarded | One external comment has been received from Rudy " add ¦¦ row.IsPlannedTotalZero here. So all groups with missing Planned qty will be shown even if "Include Unplanned" checkbox is not checked" to Krish | A suggestion has been given by rudy to include Unplanned Checkbox |  | The Team will work on CRC and have provided the plan where they will work on mitigating these issues in the future by having test plans. | Krish | Closed | 2025-05-08
16 | 2025-04-24 | MCS 25 Sprint 8 (11-Apr-2025 to 24-Apr-2025) | 2 defects have been carry forwarded to next Sprint with new estimate for testing. In one of the defect, New ACs were added and did an enhancement to this functionality of the application | External | Metric Deviation | 1 stretch Story and 2 external defects were Carry Forwarded | 2 defects have been carry forwarded to next Sprint with new estimate for testing. | This is an existing Issue and has been fixed and Defect Ready for testing. | After the defect analysis, New Acs were added and did a enhancement to this functionality of the application. Defect Ready for Testing. Will be carryforwarded to next sprint with new estimate for testing. | The Team will work on CRC and have provided the plan where they will work on mitigating these issues in the future by having test plans. | Hari | Closed | 2025-04-24
17 | 2025-05-08 | MCS 25 Sprint 9 (25-Apr-2025 to 08-May-2025) | 3 stretch stories & 1 defects have been carry forwarded to next Sprint with new estimate for testing. In one of the defect, This was a existing defect, while fixing new ACs were added and completed this as a enhancement. Defect Ready for peer review state. | External | Metric Deviation | 3 stretch Stories and 1 external defects were Carry Forwarded | 1 defects have been carry forwarded to next Sprint with new estimate for testing. | This was a existing defect, while fixing new ACs were added and completed this as a enhancement. Defect Ready for peer review state. | After the defect analysis, New Acs were added and did a enhancement to this functionality of the application. Defect Ready for Testing. Will be carryforwarded to next sprint with new estimate for testing. | The Team will work on CRC and have provided the plan where they will work on mitigating these issues in the future by having test plans. | Hari | Closed | 2025-05-21
18 | 2025-05-22 | MCS 25 Sprint 10 (09-May-2025 to 22-May-2025) | CRC | Internal/External | Metric Deviation | 3 External CRC | 3 External CRC has been raised by Client developer Patrick, Which states Variable Naming and the Existing method is not needed for the Current inmplementation | The Team has been worked on the SQLite Migration which has been duplicated the entire logic and the patrick has raised a concern on that stating that needs to be alligned in the proper way. |  | Once the Escalation has been raised , We proposed an approach to get the code review from the internal Architect (Ranjith) Who is accepted to help the team to follow the better coding practices along with better Approach to proceed. | Kalai | Closed | 2025-07-03
19 | 2025-06-06 | MCS 25 Sprint 11 (23-May-2025 to 05-Jun-2025) | CRC | Internal/External | Metric Deviation | 4 Internal CRC | 4 Internal Code review comments has been raised by the team | All the 4 Internal comments are related to the UI design related suggessions |  | As the review comments are given as a suggessions this sprint we havnt discussed any mitigation plan | hari | Closed | 2025-06-19
20 | 2025-06-06 | MCS 25 Sprint 11 (23-May-2025 to 05-Jun-2025) | Committment Index | Internal/External | Commitment Index Deviation | Commitment Index Deviation | Requirement has been changed in the middle of the sprint. Discussed with client and he agreed to refine the stories based on the updated requirement. |  |  | Discussed with client and updated the points during the Sprint refinement meeting | Hari | Closed | 2025-06-10
21 | 2025-06-20 | MCS 25 Sprint 12 (23-May-2025 to 05-Jun-2025) | CRC | Internal/External | Metric Deviation | 1 Internal and 3 External CRC | 1 Internal Code review comments has been raised by the team anf 3 External Code review comments has been provided by the client end | All the 3 Internal comments are related to the UI suggessions and to make use of the existing library files which has been into our project. |  | As the review comments are given as a suggessions this sprint we havnt discussed any mitigation plan | hari | Closed | 2025-06-20
22 | 2025-06-20 | MCS 25 Sprint 12 (23-May-2025 to 05-Jun-2025) | CRC | Internal/External | Metric Deviation | Commitment Index Deviation | Due to requirement change the taken stories has been delayed and unable meet the deadline |  |  | Discussed with client and updated the points during the Sprint refinement meeting | hari | Closed | 2025-06-20
23 | 2025-07-04 | MCS 25 Sprint 13 (23-Jun-2025 to 03-Jul-2025) | CRC | Internal/External | Metric Deviation | Commitment Index Deviation | Requirement has been changed in the middle of the sprint. Discussed with client and he agreed to refine the stories based on the updated requirement. |  |  | Discussed with client and updated the points during the Sprint refinement meeting | hari | Closed | 2025-07-01
24 | 2025-07-04 | MCS 25 Sprint 15 (18-Jul-2025 to 31-Jul-2025) | CRC | Internal/External | Metric Deviation | Commitment Index Deviation | Requirement has been changed in the middle of the sprint. Discussed with client and he agreed to refine the stories based on the updated requirement. |  |  | Discussed with client and updated the points during the Sprint refinement meeting | hari / Kalai | Closed | 2025-07-15
25 | 2025-08-14 | MCS 25 Sprint 16 (1-Aug-2025 to 14-Aug-2025) | Commitment Index Deviation | Internal/External | Metric Deviation | Commitment Index Deviation | Requirement has been changed in the middle of the sprint. Discussed with client and he agreed to refine the stories based on the updated requirement. |  |  | Discussed with client and updated the points during the Sprint refinement meeting | hari / Kalai | Closed | 2025-08-15
26 | 2025-09-23 | MCS 25 Sprint 18 (12-Sep -2025 to 24-Sep-2025) | Commitment Index Deviation | Internal/External | Metric Deviation | Commitment Index Deviation | Testing has been deliayed from the client side to close the Story. | The client QA Milan has taking his own course of direction to complete the testing from his end |  | Already communicated to EM and CP about the behviour. Also, escalated to the client QA manager about the delay of completing the QA. | hari / Kalai | Closed | 2025-09-25
27 | 2025-10-10 | MCS 25 Sprint 20 (25-Sep -2025 to 09-Oct-2025) | CRC | Internal/External | Metric Deviation | Commitment Index Deviation | Client provided a code review comments about team code to change the veribiage. | The veribage of the code was not update properly client asked to change the veribiage |  | The veribage has been updated and communicated team to keep in mind to follow thi in future | Hari/Kalai | Closed | 2025-10-10
28 | 2025-10-22 | MCS 25 Sprint 21 (10-Oct -2025 to 23-Oct-2025) | Commitment Index Deviation | Internal/External | Metric Deviation | Commitment Index Deviation | 2 Stories carry forwarded for testing, Testing bandwidth is limited | The client QA Milan has taking his own course of direction to complete the testing from his end |  | Already communicated to EM and CP about the behviour. Also, escalated to the client QA manager about the delay of completing the QA. | Hari | Closed | 2025-10-25
29 | 2025-11-20 | MCS 25 Sprint 23 (07-Nov -2025 to 20-Nov-2025) | Defect Findings | External | Metric Deviation | 1 External Defect | 1 External defect carry forwarded in Testing | The delay occured because QA ownership transitioned from Rajesh to Florida QA team, which required a KT plan during the sprint. Due to the KT activities and onboarding of the new QA member, the testing could not be completed within the planned sprint timeline |  | From the upcoming sprints, we will ensure well planned KT avoiding overlaps with active testing cycles | Kalai | Inprogress | 2025-11-20
| 2025-11-20 | MCS 25 Sprint 23 (07-Nov -2025 to 20-Nov-2025) | CRC | External | Metric Deviation | 3 CRC comments | 3 CRC Comments has been received | The code revew comments has been already in the existing code. Dicussed with client and update the comment given by them. Updated the client code review comments.
30 | 2025-12-18 | MCS 25 Sprint 24 (21-Nov -2025 to 18-Dec-2025) | Defect Findings | Internal | Metric Deviation | 1 Internal Defect | 1 Internal defect carry forwarded in Testing | QA is currently executing test scenarios and test cases across the entire application for each bug-fix build. In the last retrospective, it was agreed that the team would perform end-to-end testing of the whole application and consolidate all identified defects. Following this, Development will provide a single build addressing all fixes. As a result, defect #26336 has been carried forward to capture and log the remaining bugs. |  | Define clear scope for each build (bug fixes vs. regression). Separate critical regression tests from full application sweeps. QA should consolidate and log all identified defects and bugs under a single assigned story. This will enable the Development team to address all issues collectively and provide a unified solution in one build for QA validation. | Sathish | Inprogress
31 | 2026-01-15 | MCS 25 Sprint 25 19-Dec -2025 to 15-Jan-2026) | Commitment Index Deviation | Internal | Metric Deviation | 1 story carry forwarded and 1 story testing in progress. | Development was completed in the sprint 22; the current sprint focuses only on testing, but small ui implemention updated for Weekly format | We have a Testing backlog and Completed Pre-POV and currently addressing internal review comments. |  | *Manage review cycles tightly, validate data early, and align stakeholders to avoid rework. *We have a Testing backlog and we are trying to manage it by hiring the new resouce, she is trying her best to complete all the work. Need some time to align it properly | Vaishnavi | Inprogress | 2026-01-29
32 | 2026-01-29 | MCS 26 Sprint 1 (16-Jan -2026 to 29-Jan-2026) | Commitment Index Deviation | Internal/External | Metric Deviation | 2 Stories carry forwarded in testing in progress | Development for this story was completed in Sprint 25. However, since we had a number of high‑priority stories that needed to be pushed into production during the current sprint, the testing team focused on those items to ensure timely delivery. As a result, this story has been scheduled for completion in the next sprint. | According to the given AC the development was completed and in the POV a lot of Modifications and the Enhancements has been raised by the Client end and we were working on this in current sprint. |  | Going forward, we will factor in QA team availability when planning tickets and align development tasks accordingly. This will ensure that testing capacity is balanced with development output, reducing backlog and maintaining quality standards. To avoid similar rework in the future, we will ensure that clear and complete acceptance criteria are obtained from the client during planning. Additionally, tickets will be thoroughly analyzed before development begins, so that scope and expectations are aligned upfront. | All Members | Closed | 2026-02-11
33 | 2026-02-11 | MCS 26 Sprint 2 (30-Jan -2026 to 11-Feb-2026) | Commitment Index Deviation | Internal/External | Metric Deviation | 1 story carry forwarded and 1 story testing in progress. | We havnt taken this story as we worked on the other bounce backs and extending the current developments with modifications | POV Completed and Raised PR. Testing is in progress. As we have only one QA for Internal and External Development teams we are facing teating Backlogs for some of the tickts wheich we have completed the development |  | In future ticket planning, we must ensure that resource availability (including planned leaves) is accounted for, and that the number of tickets scheduled allows for sufficient backup or slack time to handle unforeseen issues. Previously, our mitigation plan involved limiting each ticket to only UI and backend development tasks, since we already had a QA backlog. However, with the recent influx of client-driven enhancements, we have adjusted our approach by prioritizing testing efforts to focus on the most critical tasks required for each sprint. | All Members | Closed | 2026-02-26
34 | 2026-03-12 | MCS 26 Sprint 4 (27-Feb -2026 to 12-Mar-2026) | 1 External defect is in Product owner verify status | External | Metric Deviation | 1 External defect is in Product owner verify status | This external defect is submitted to product owner for Pov not verified still Product owner verify status. They will decide whats the next step on it. |  |  | Client aware of it and will plan accordingly in next sprints | All Members | Closed | 2026-03-26
35 | 2026-03-26 | MCS 26 Sprint 5 (13-Mar -2026 to 26-Mar-2026) | 2 External defects | Internal/External | Metric Deviation | 2 External defects | The analysis took longer because the changes were made about 15 years ago, and it took extra time to get the functionality working. They asked for a second round POV. The defect was taken mid‑sprint. The implementation was completed, and dev testing is in progress. |  |  | Allowed additional analysis time for legacy changes and aligned with client on second POV. Defect picked mid‑sprint; development completed and dev testing is in progress to ensure stability before QA. | All Members | Closed | 2026-04-09
36 | 2026-04-24 | MCS 26 Sprint 7 (10-Mar -2026 to 23-Apr-2026) | 1 Internal defect carry forwarded | Internal | Metric Deviation | 1 Internal defect carry forwarded | This internal defect was created in last day so it is carry forwarded |  |  | Client aware of it and will plan accordingly in next sprints | All Members | Closed
37 | 2026-05-07 | MCS 26 Sprint 8 (24-Apr-2026 to 07-May-2026) | 1 Internal defect carry forwarded | Internal | Metric Deviation | 1 Internal defect carry forwarded | As this defect was raised in the end of this sprint we could not complete this story. |  |  | Client aware of it and will plan accordingly in next sprints | All Members | Closed
38
39
40
41
42
43

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Config
Sprint | MCS 24 Sprint 25 (11-Dec -2024 to 02 -Jan-2025) | Relevantz Co Owned | 64.69% | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted |  | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | 40% | 10% |  | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | 52.5% | 10.5% |  | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 80.95% | 16.19% |  |  |  | CF |  | Excellent |  | 25
Code Quality Index | 66.67% | 10% |  | Velocity
Unit Testing & Code Coverage | 80% | 8% |  | Goal | 20
Backlog Health | 100% | 10%
Code Coverage
|  |  |  | Goal | 90%
|  |  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  |  | Below Avg | 15 | Labels | Values |  | Story Points | 30
|  |  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  |  | Excellent | 30 | 15 | 10
|  |  |  | Total | 90 | 20 | 10
[6 empty] | 25 | 10
50

## Instructions
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## ExportData
dd | MCS 24 Sprint 17 (16-Aug-2024 to 29-Aug-2024) | MCS 24 Sprint 17 | 2024-08-16 | 2024-08-29 | August | 3 | 3 | 1 | 3 | 1 | 0 | 0 | 0 | 0 | 0.83 | 1 | 0.15 | 1 | 1
dd | MCS 24 Sprint 18 (30-Aug -2024 to 12-Sep -2024) | MCS 24 Sprint 18 | 2024-08-30 | 2024-09-12 | September | 19 | 13 | 0.68421 | 8 | 0.8 | 0 | 0 | 0 | 0 | 0.78105 | 0.68421 | 0.4 | 1 | 1
dd | MCS 24 Sprint 19 (13-Sep -2024 to 26-Sep -2024) | MCS 24 Sprint 19 | 2024-09-13 | 2024-09-26 | September | 12 | 12 | 1 | 9.33 | 1 | 0 | 2 | 4 | 0 | 0.78256 | 1 | 0.4665 | 0.57128 | 0.83333
dd | MCS 24 Sprint 20 (27-Sep -2024 to 10-Oct -2024) | MCS 24 Sprint 20 | 2024-09-27 | 2024-10-10 | October | 18 | 18 | 1 | 11.5 | 1 | 0 | 0 | 1 | 0 | 0.89761 | 1 | 0.575 | 0.91304 | 1
dd | MCS 24 Sprint 21 (11-Oct -2024 to 24-Oct -2024) | MCS 24 Sprint 21 | 2024-10-11 | 2024-10-24 | October | 11 | 11 | 1 | 13.5 | 1 | 0 | 0 | 0 | 0 | 0.935 | 1 | 0.675 | 1 | 1
dd | MCS 24 Sprint 22 (25-Oct -2024 to 7-Nov -2024) | MCS 24 Sprint 22 | 2024-10-25 | 2024-11-07 | November | 11 | 11 | 1 | 13 | 1 | 0 | 0 | 1 | 0 | 0.91462 | 1 | 0.65 | 0.92308 | 1
dd | MCS 24 Sprint 23 (08-Nov -2024 to 21-Nov-2024) | MCS 24 Sprint 23 | 2024-11-08 | 2024-11-21 | November | 13 | 7 | 0.53846 | 11.75 | 0.8 | 0 | 2 | 1 | 1 | 0.70522 | 0.53846 | 0.5875 | 0.82979 | 0.71429
dd | MCS 24 Sprint 24 (22-Nov -2024 to 10-Dec-2024) | MCS 24 Sprint 24 | 2024-11-22 | 2024-12-10 | December | 25 | 12 | 0.48 | 10.25 | 0.8 | 0 | 4 | 0 | 0 | 0.7025 | 0.48 | 0.5125 | 1 | 0.66667
dd | MCS 24 Sprint 25 (11-Dec -2024 to 02 -Jan-2025) | MCS 24 Sprint 25 | 2024-12-11 | 2025-01-02 | January | 30 | 12 | 0.4 | 10.5 | 0.8 | 0 | 4 | 2 | 0 | 0.6469 | 0.4 | 0.525 | 0.80952 | 0.66667
dd | MCS 25 Sprint 1 (3-Jan -2025 to 16-Jan-2025) | MCS 25 Sprint 1 | 2025-01-03 | 2025-01-16 | January | 22 | 9 | 0.40909 | 10 | 0.85 | 0 | 3 | 0 | 0 | 0.68727 | 0.40909 | 0.5 | 1 | 0.66667
dd | MCS 25 Sprint 2 (17-Jan -2025 to 30-Jan-2025) | MCS 25 Sprint 2 | 2025-01-17 | 2025-01-30 | January | 9 | 9 | 1 | 10.5 | 0.9 | 0 | 2 | 0 | 1 | 0.84262 | 1 | 0.525 | 0.90476 | 0.77778
dd | MCS 25 Sprint 3 (31-Jan -2025 to 13-Feb-2025) | MCS 25 Sprint 3 | 2025-01-31 | 2025-02-13 | February | 26 | 23 | 0.88462 | 13.25 | 1 | 0 | 1 | 1 | 0 | 0.88204 | 0.88462 | 0.6625 | 0.92453 | 0.95652
dd | MCS 25 Sprint 4 (14-Feb -2025 to 27-Feb-2025) | MCS 25 Sprint 4 | 2025-02-14 | 2025-02-27 | February | 34 | 29 | 0.85294 | 17.5 | 1 | 1 | 1 | 0 | 1 | 0.91646 | 0.85294 | 0.875 | 0.94286 | 0.93103