## Dashboard
BOH
INTERNAL CONFIDENTIAL

## Scorecard
Project Name | MSB Accounting
Engagement Model | Relevantz Co Owned
Overall Score | 93.85%
Current Sprint | 26.06 Sprint 1 (22-Apr-2026 to 05-May-2026)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% | 0 | 25% | 100%
Velocity | 98.75% | 19.75% |  | 20% | 95%
Defect-free Rate | 89.87% | 17.97% |  | 20% | 100%
Code Quality Index | 87.5% | 13.12% |  | 15% | 100%
Unit Testing & Code Coverage | 80% | 8% |  | 10% | 90%
Backlog Health | 100% | 10% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
13.7 Sprint 2 (27-Mar-2024 to 09-Apr-2024) | 18 | 12 | 66.67% | 20 | 90% | 2 | 2 | 3 | 0 | 30 | No |  |  | 3 Stories got carried. (1 - Deployment delay from Client side, 2 - Development Inprogress) |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.7 Sprint 3 (10-Apr-2024 to 23-Apr-2024) | 19 | 19 | 100% | 20 | 90% | 0 | 0 | 11 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 1 (24-Apr-2024 to 07-May-2024) | 16 | 11 | 68.75% | 20 | 90% | 1 | 0 | 3 | 0 | 30 | No |  |  | 1 Story got carried. Development completed and Testing in progress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 2 (08-May-2024 to 21-May-2024) | 20 | 17 | 85% | 20 | 90% | 1 | 0 | 2 | 1 | 30 | No |  |  | 1 Story got carried, development inprogress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 3 (22-May-2024 to 04-Jun-2024) | 21 | 17 | 80.95% | 20 | 90% | 1 | 0 | 4 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 4 (05-Jun-2024 to 18-Jun-2024) | 19 | 12 | 63.16% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | 2 Story got carried, development inprogress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 5 (19-Jun-2024 to 02-Jul-2024) | 16 | 3 | 18.75% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Identified more difference in source data during Data fix. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 6 (03-Jul-2024 to 16-Jul-2024) | 18 | 13 | 72.22% | 20 | 90% | 0 | 0 | 0 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 7 (17-Jul-2024 to 30-Jul-2024) | 32 | 32 | 100% | 20 | 90% | 0 | 0 | 3 | 3 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 8 (31-Jul-2024 to 13-Aug-2024) | 17 | 17 | 100% | 20 | 90% | 0 | 0 | 4 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 1 (14-Aug-2024 to 27-Aug-2024) | 10 | 10 | 100% | 20 | 90% | 0 | 0 | 2 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 2 (28-Aug-2024 to 10-Sep-2024) | 23 | 10 | 43.48% | 17.25 | 80% | 0 | 0 | 7 | 0 | 30 | No |  |  | Missed 13 sp because we couldnt completed regression in time because we had blocking items to complete |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 3 (11-Sep-2024 to 24-Sep-2024) | 24 | 21 | 87.5% | 14.5 | 90% | 0 | 0 | 3 | 0 | 30 | Yes |  |  | Regression Sprint |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 1 (25-Sep-2024 to 08-Oct-2024) | 15 | 10 | 66.67% | 13 | 85% | 0 | 0 | 1 | 0 | 30 | No |  |  | SRX24145 was in Testing |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 2 (09-Oct-2024 to 22-Oct-2024) | 28 | 20 | 71.43% | 15.25 | 85% | 0 | 0 | 8 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 3 (23-Oct-2024 to 5-Nov-2024) | 24 | 13 | 54.17% | 16 | 70% | 0 | 0 | 4 | 0 | 30 | No |  |  | 5sp - Accounting Data investigation. 8sp - Changes to the story was added late in the sprint. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 1 (06-Nov-2024 to 19-Nov-2024) | 14 | 14 | 100% | 14.25 | 100% | 0 | 0 | 1 | 5 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 2 (20-Nov-2024 to 3-Dec-2024) | 16 | 11 | 68.75% | 14.5 | 75% | 0 | 0 | 1 | 3 | 30 | No |  |  | 5 sp missed because the fix for the escalation defect is dependant on changes made in 46200 whcih is a stretch item still in progress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 3 (04-Dec-2024 to 17-Dec-2024) | 17 | 17.7 | 104.1% | 14 | 75% | 0 | 0 | 1 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 Sprint 1 (18-Dec-2024 to 14-Jan-2025) | 22 | 24 | 109.1% | 17 | 100% | 1 | 0 | 2 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 Sprint 2 (15-Jan-2025 to 28-Jan-2025) | 19 | 23 | 121.1% | 19 | 90% | 1 | 0 | 2 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 Sprint 3 (29-Jan-2025 to 11-Feb-2025) | 17 | 22 | 129.4% | 22 | 85% | 0 | 0 | 5 | 2 | 30 | Yes |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 Sprint 1 (12-Feb-2025 to 25-Feb-2025) | 17 | 37 | 217.6% | 26.5 | 100% | 0 | 2 | 2 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 Sprint 2 (26-Feb-2025 to 11-Mar-2025) | 23 | 32.5 | 141.3% | 28.6 | 100% | 0 | 1 | 0 | 4 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 Sprint 3 (12-Mar-2025 to 25-Mar-2025) | 27 | 34.5 | 127.8% | 31.5 | 95% | 1 | 0 | 1 | 3 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.6 Sprint 1 (26-Mar-2025 to 08-Apr-2025) | 22 | 17.3 | 78.64% | 30.325 | 85% | 0 | 0 | 2 | 2 | 30 | No |  |  | 3 Stories got carried because we few scenarios and it extended the scope during the development process 1 Stretch story - Completed data fixes for 10 out of 28 duplicate batches. The remaining fixes have been carried over to the next sprint. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.6 Sprint 2 (09-Apr-2025 to 22-Apr-2025) | 19 | 19 | 100% | 26 | 95% | 1 | 0 | 4 | 0 | 30 | No |  |  | 2 Stretch stories got carried over because Completed GL Account Maintenance screen . Unable to complete Others screens. Completed the Model part. 1 defect and 3 Bouncebacks found in the internal testing |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.6 Sprint 3 (23-Apr-2025 to 06-May-2025) | 21 | 23 | 109.5% | 23.4 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  | 3 Stretch stories got carried over because 2 Stories development got complete. Testing needs to done. 1 Story hold for regression. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.7 Sprint 1 (07-May-2025 to 20-May-2025) | 22 | 22 | 100% | 20.3 | 100% | 0 | 0 | 4 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.7 Sprint 2 (21-May-2025 to 03-Jun-2025) | 24 | 18 | 75% | 20.5 | 95% | 0 | 2 | 6 | 0 | 30 | No |  |  | 2 stories got carried Due to issue with Dev database slowness which affected testing from this sprint.
14.7 Sprint 3 (04-Jun-2025 to 17-Jun-2025) | 21 | 31 | 147.6% | 23.5 | 95% | 0 | 0 | 7 | 0 | 30 | No
15.0 Sprint 1 (18-Jun-2025 to 01-Jul-2025) | 16 | 8 | 50% | 19.75 | 80% | 0 | 1 | 2 | 0 | 30 | No |  |  | 3 Story points missed automation story since Client QA manager wasn't available on last 2 days to approve the PR 5 Story points Missed because Misplanned the Story points
15.0 Sprint 2 (2-Jul-2025 to 15-Jul-2025) | 23.5 | 15.5 | 65.96% | 19.75 | 80% | 2 | 1 | 1 | 0 | 30 | No |  |  | 6 Story points delayed due to over committed on the Alpine reports 6 Story points delayed due to blocker in Batchid.
15.0 Sprint 3 (16-Jul-2025 to 29-Jul-2025) | 27 | 29 | 107.4% | 20.875 | 80% | 1 | 1 | 1 | 0 | 30 | No |  |  | The regression went really well with the short time period.
15.1 Sprint 1 (30-Jul-2025 to 12-Aug-2025) | 27 | 26 | 96.3% | 19.625 | 80% | 0 | 0 | 0 | 3 | 30 | No |  |  | 15.0 Release went well
15.1 Sprint 2 (13-Aug-2025 to 26-Aug-2025) | 25 | 14 | 56% | 21.125 | 95% | 0 | 0 | 2 | 5 | 30 | No |  |  | Missed 11 sp due to time spent on escalations that came in during the sprint. The escaped defects are customer support ticket not from our deliverable.
15.1 Sprint 3 (27-Aug-2025 to 09-Sep-2025) | 28 | 31 | 110.7% | 25 | 100% | 0 | 0 | 2 | 4 | 30 | No |  |  | We had a good sprint. Completed a hotfix deployment and the escalation got resolved,
15.2 Sprint 1 (10-Sep-2025 to 23-Sep-2025) | 28 | 14 | 50% | 21.25 | 100% | 0 | 0 | 2 | 4 | 30 | No |  |  | Closed all 4 escalations. Successfull 15.1 deployment. Made good progress with automation test suite.
15.2 Sprint 2 (24-Sep-2025 to 07-OCt-2025) | 15 | 15 | 100% | 18.5 | 100% | 0 | 0 | 0 | 4 | 30 | No |  |  | We completed 15 SP s out of 15, but including 5 from stretch.
15.2 Sprint 3 (08-Oct-2025 to 21-OCt-2025) | 10 | 7 | 70% | 16.75 | 100% | 0 | 0 | 0 | 4 | 30 | No |  |  | Hotfix completed. 3 / 7 escalations closed in the sprint.
15.03 Sprint 1 (22-Oct-2025 to 04-Nov-2025) | 24 | 24 | 100% | 15 | 100% | 0 | 0 | 0 | 2 | 30 | No |  |  | Completed regression items. Closed 6/9 escalations in the sprint. Made good progress with stretch items.
15.03 Sprint 2 (05-Nov-2025 to 18-Nov-2025) | 23 | 27 | 117.4% | 18.25 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | Completed 22 SP from main commit and 5 SP from stretch. Couldn't complete 1 story with 1 SP because SSO login blocked due to WAF issue on MSB.
15.03 Sprint 3 (19-Nov-2025 to 02-Dec-2025) | 29.5 | 19.5 | 66.1% | 19.375 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  | Regression Sprint , closed all escalations.
20.01 Sprint 1 (03-Dec-2025 to 16-Dec-2025) | 26 | 20 | 76.92% | 22.625 | 100% | 0 | 1 | 3 | 3 | 30 | No
26.01 Sprint 2 (17-Dec-2025 to 13-Jan-2026) | 35 | 25 | 71.43% | 22.875 | 100% | 0 | 0 | 2 | 4 | 30 | No |  |  | 3 Stories carry forwarded
26.02 Sprint 3 (14-Jan-2026 to 27-Jan-2026) | 26 | 26 | 100% | 22.625 | 100% | 0 | 0 | 5 | 5 | 30 | No |  |  | 1 defect is carry forwarded which was pulled into the sprint on the last day with 0 SP.
26.03 Sprint 1 (28-Jan-2026 to 10-Feb-2026) | 23 | 26 | 113% | 24.25 | 100% | 0 | 0 | 5 | 5 | 30 | No | 2 | 4 | 1 story carry forwarded to next sprint due to 3 escalation tickets were assigned during mid of the sprint
26.03 Sprint 2 (11-Feb-2026 to 24-Feb-2026) | 15 | 19 | 126.7% | 24 | 100% | 0 | 0 | 6 | 2 | 30 | No | 1 | 2 | 1 story carry forwarded due to waiting for PR approval from the client for the last 2 days
26.03 Sprint 3 (25-Feb-2026 to 10-Mar-2026) | 19 | 14 | 73.68% | 21.25 | 100% | 0 | 1 | 4 | 1 | 30 | No | 7 | 9
26.04 Sprint 1 (11-Mar-2026 to 24-Mar-2026) | 16 | 19 | 118.8% | 19.5 | 100% | 0 | 0 | 1 | 6 | 30 | No | 7 | 10.5
26.04 Sprint 2 (25-Mar-2026 to 07-Apr-2026) | 11 | 24 | 100% | 19 | 100% | 0 | 0 | 3 | 3 | 30 | No | 4 | 5
26.04 Sprint 3 (08-Apr-2026 to 21-Apr-2026) | 44 | 33 | 75% | 22.5 | 100% | 0 | 0 | 3 | 2 | 111 | No | 3 | 3
26.06 Sprint 1 (22-Apr-2026 to 05-May-2026) | 22 | 25 | 100% | 25.25 | 100% | 0 | 0 | 2 | 2 | 103 | Yes | 4 | 4

## RCA
3 Why Analysis
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-04-08 | 13.7 Sprint 2 (27-Mar to 09-Apr) | 1 Story Deployment Got Delayed Which impact in Commitment Index | Internal | Metric Deviation | Commitment Index Deviation | PR approved by client on 08-Apr and deployment got delayed from client side. Due Other External Factor Delopment Got Delayed By Customer |  |  | Deployment Delayed By Customet which is Uncontrol and Can not Mitigate | Rijo | Closed | 2024-04-10 | To match with Axosoft Status, Delpoyment Delay from Customer also consider here as metric Deviation. | Metric Deviation
2 | 2024-04-08 | 13.7 Sprint 2 (27-Mar to 09-Apr) | 2 Stretch Story - Got extended beyond Sprint End, which impact in commitment Index | Internal | Metric Deviation | Commitment Index Deviation | Stretch Story - Got extended beyond Sprint End, because the Story 8th Day of Sprint | Since this Strretch Story it got Delyed |  | Stretch Story - Got extended beyond Sprint End | Rijo | Closed | 2024-04-10 | To match with Axosoft Status, Stretch Story Status also take as it is | Metric Deviation
3 | 2024-04-08 | 13.7 Sprint 2 (27-Mar to 09-Apr) | .First() will throw an exception if id is incorrectly passed. There should be a method in the schoolgroupsrepository to get by id directly. (Look at Tenant Manager in GetCurrentDistrictId (). | Internal | Metric Deviation | Code Review Comments | Missed to check the existing approach method in similar page | Missed code optimization to reduce resource consumption. | Missed in Internal Review | Knowledge share with Team in Stand Up, So that similar type of Defect can be mitigated. | Karthikeyan | Closed | 2024-04-10 | Review comment fixed in next sprint | Metric Deviation
4 | 2024-04-08 | 13.7 Sprint 2 (27-Mar to 09-Apr) | Rename to ""schoolgroup"" . group is a keyword used in C# for LINQ." | Internal | Metric Deviation | Code Review Comments | Limited Analaysis done on the This Specific Logic |  |  | Knowledge share with Team in Stand Up, So that similar type of Defect can be mitigated. | Rijo | Closed | 2024-04-10 | Review comment fixed in next sprint | Others
5 | 2024-04-23 | 13.7 Sprint 3 (10-Apr to 23-Apr) | Internal defects | Internal | [5 empty] | All the reported defects were identified during regression and existing issues. |  | Closed | 2024-04-23
6 | 2024-05-07 | 13.8 Sprint 1 (24-Apr to 07-May) | 1 Story testing is inprogress Which impact in Commitment Index | Internal | Metric Deviation | Commitment Index Deviation | Development completed on 02-May and testing is inprogress. Due Other External Factor Peer Review-2 Got Delayed By Customer |  |  | PR approval Delayed By Customet which is Uncontrol and Can not Mitigate | Karthikeyan | Closed | 2024-05-10
7 | 2024-05-21 | 13.8 Sprint 2 (08-May to 21-May) | 1 Story testing is inprogress Which impact in Commitment Index | Internal | Metric Deviation | Commitment Index Deviation | Limited Analaysis done on the This Specific Logic |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Rijo | Closed | 2024-05-21
8 | 2024-05-21 | 13.8 Sprint 2 (08-May to 21-May) | 1 External Defect. Blue Bear - Create Standard Stock Option in MSB | Internal | Metric Deviation | Defect Density | Missed to identify during internal testing |  |  | Knowledge share with Team in Stand Up, So that similar type of Defect can be mitigated. | Sushmitha | Closed | 2024-05-21
9 | 2024-06-18 | 13.8 Sprint 4 (05-Jun to 18-Jun) | Commitment Index 63% Deviation | Internal | Metric Deviation | Commitment Index Deviation | We need to give data fix for all the previous year's uncleared / undeleted transactions, and also need to update balance for all those accounts as well. So currently analysing the impacts about the new datafix updates |  |  | Prod data dependency | Karthikeyan | Closed | 2024-06-20
10 | 2024-07-02 | 13.8 Sprint 5 (19-Jun to 02-Jul) | Commitment Index 19% Deviation | Internal | Metric Deviation | Commitment Index Deviation | Identified more difference in source data during Data fix. |  |  | Knowledge share with Team in Stand Up, So that similar type can be mitigated. | Rijo | Closed | 2024-07-03
11 | 2024-07-16 | 13.8 Sprint 6 (03-Jul to 16-Jul) | 2 Defects reported by client | Internal | Metric Deviation | Defect Density | Incorrect Year End Warning and cash transfer warning |  |  | Knowledge share with Team in Stand Up, So that similar type can be mitigated. | Rijo | Closed | 2024-07-17
12 | 2024-08-28 | 14.1 Sprint 2 (28-Aug to 10-Sep) | Commitment Index was Low and Escalations (More Defects) | Internal | Metric Deviation | Commitment Index Deviation, and Defect Density | Missed 13 sp because we couldnt completed regression in time because we had blocking items to complete | Escalations were recorded |  | Knowledge share with Team in Stand Up, So that similar type can be mitigated. | Rijo | Closed | 2024-08-28
13 | 2024-10-08 | 14.2 Sprint 1 (25-Sep to 08-Oct) | Commitment Index was 67% | Internal | Metric Deviation | Commitment Index Deviation | SRX24145 was in Testing |  |  | Knowledge share with Team in Stand Up, So that similar type can be mitigated. | Rijo | Closed | 2024-10-08
14 | 2024-10-22 | 14.2 Sprint 2 (09-Oct to 22-Oct) | Defect Density - More Defects Commitment Index was low | Internal | Metric Deviation | Defect Density | More Existing Defects were worked upon | 8 sp - Detailed Accounting Analysis required |  | Knowledge share with Team in Stand Up, So that similar type can be mitigated. | Rijo | Closed | 2024-10-22
15 | 2024-11-05 | 14.2 Sprint 3 (23-Oct to 5-Nov) | Commitment Index 54% Deviation | Internal | Metric Deviation | Commitment Index Deviation | 5sp - Accounting Data investigation. 8sp - Changes to the story late in the sprint. |  |  | Client is Informed. Needed Discussion with Michael and Sarah. The other story investigating the accounting data for a customer. Only coding involved will be a data fix. | Rijo/Qadir | Closed | 2024-11-05
16 | 2024-11-19 | 14.3 Sprint 1 (06-Nov to 19-Nov) | Defect Density - More Defects Defect Free Index were low | External | Metric Deviation | Defect Density | 1 Defect was Bounceback, it was a Migration Issue. Client Development and was tested by Relevantz QA | 5 Escalations - 1. From MSB side 2. Known Existing Issue 3. Data Issues 4. Data Issues 5. Existing Known Issue (Data Fix) |  | Client is Informed. Knowledge share with Team in Stand Up, So that similar type of Defect can be mitigated. | Qadir | Closed | 2024-11-19 | 2 Escalations were closed, three Escalations were converted into defects and the defects were assigned in the current sprint which is being fixed
17 | 2024-12-03 | 14.3 Sprint 2 (20-Nov to 3-Dec) | Defect Density - More Defects Defect Free Index were low and Commitment Index Deviation | Internal/External | Metric Deviation | Defect Density and Commitment Index | Defect Density 1. 3 Escalations from the Customer - which was an existing issue in the Prod 2. One bounceback during Testing | Commitment Index - 5 sp missed because the fix for the escalation defect is dependant on changes made in 46200 whcih is a stretch item still in progress. |  | Client is Informed. Knowledge share with Team in Stand Up, So that similar type of Defect/Issues can be mitigated. | Qadir, Rijo and Karthik | Closed | 2024-12-17 | 2 Escalations were closed, and others are in progress
18 | 2024-12-17 | 14.3 Sprint 3 (04-Dec to 17-Dec) | Defect Index and Committed Stories are carry forwarded | Internal/External | Metric Deviation | 1 Bounceback, 1 Escalation, 2 Committed Stories are Carry Forwarded | 2 Committed Stories are Carry Forwarded 1. Will share the branch with team for review. Had POV on 17/12/2024, got review comments and will be working on the same 2. We know the email job isnt running because the background worker process is getting killed because of an exception. Noticed logs about timeout issues with the ImportPayments. Need to investigate if that is the cause of the BG Worked process failing | 1 External Escalation was a Existing Issue in the Production, based on Priority Client assigned. | 1 Bounceback from the existing story - 1. Batches Job type not added for district in sync setting and after mapping gateways to schools transactions are not received 2. The status field should updated with status "new" , but its updated as 0 3. Oldest transactions [Batches] are not available in batches grid 4. URL should be renamed as "Import MSB Batches" | Client was informed. We found some additional work to be done for this story to manage existing data, so when we deploy , this scenario works seamlessly. | Qadir, Rijo | Closed | 2025-01-14 | Escalation, Defect were closed, the team is working on the POV Comments and Stories carry forwarded
19 | 2025-01-14 | 14.4 Sprint 1 (18-Dec to 14-Jan) | 1 Internal CRC, Defect Index and Committed Stories are carry forwarded | Internal/External | Metric Deviation | 1 Internal CRC, Defect Index(1 Bounceback, 1 Defect and 1 Escaped Defect) and Committed Stories are carry forwarded | 2 sp story has been rolled over to the new sprint as a 8 sp story. We're still unsure of the reason the send email job isnt running. We've allocated more time to investigate the issue. Along the way we've found more issues on Production, which were Important to investigate to determine whether we need immediate fixes or not. | 1 Internal CRC - Suggestion - 1) Spelling correction. 2) Drop unused stored procedures. | QA Defects 1 Internal Defect was rejected 1 Bounceback reported logical/functional issues 1 Escaped Defect - This was an existing edge case issue in the application. We have just one customer who would use a multi school Bank Rec. | All the works were completed and defects were addressed. Knowledge share with Team in Stand Up, So that similar type of Defect/Issues can be mitigated. | Qadir, Rijo and Karthik | Closed | 2025-01-14
20 | 2025-01-28 | 14.4 Sprint 2 (15-Jan to 28-Jan) | 1 Internal CRC, Defect Index and Committed Stories are carry forwarded | Internal/External | Metric Deviation | 1 Internal CRC, Defect Index - 2 Bounceback and Committed Stories are carry forwarded | 1 Internal CRC is Use the existing IsActive flag instead of creating a new column.- Logical Suggestion | 2 Bounceback - "The popup error message was not loading when redirected back from msb, had to move it into inline error message for the login with msb option." "The bank deposits created from shared batch were causing the issue. The journaling and reversal was changing the status for the entire batch and that affected the other schools who use the same batch." | 1 Story was Carry Forwarded due to Team working with James simulataneoulsy to get the date picker completed as part of the commit. this was more complicated than anticipated because of the inability set a date in the grid. We may look at writing some custom code. | All the works were completed and defects were addressed. Knowledge share with Team in Stand Up, So that similar type of Defect/Issues can be mitigated. Only the Story is carry forwarded | Qadir, Rijo and Karthik | Closed | 2025-01-28
21 | 2025-02-11 | 14.4 Sprint 3 (29-Jan to 11-Feb) | 7 QA Defects and 1 Story was Carry Forwarded | Internal/External | Metric Deviation | 5 Internal Defects, 2 External Defects and Committed story was carry forwarded | 5 Internal defects were existing issue and two defects were closed and three were carry forwarded to the backlog | 2 External defects were in progress | 1 Story was Carry Forwarded POV completed with Pramod, got a comment to work on. Carry forwarded and re estimated to 1 sp. and Dev was on PTO for two days | All the Significant defects were addressed. Knowledge share with Team in Stand Up, So that similar type of Defect/Issues can be mitigated. Only the Story is carry forwarded | Qadir, Rijo and Karthik | Closed | 2025-02-28
22 | 2025-02-25 | 14.5 Sprint 1 (12-Feb-2025 to 25-Feb-2025) | CRC, 4 Defects | Internal/External | Metric Deviation | 2 CRC, 1 Bounceback, 1 Defect and 2 Escaped Defects | 2 CRC is for Automation stories. Owen Seiber suggested 1. All the cleanups need to have calls to delete in the event something fails during the test and it does not cleanup after it. 2. Even though this is valid to add multiple tests into one class file, we should split these into individual test files. We can have CreateEditDeleteSchools, CreateEditDeleteDistricts and CreateEditDeleteSchoolDistricAdmin.. The reason for this is if the browser crashes during one test, it will prevent the rest from running. | 1 Bounceback is 1. Relevantz developed 2. We made fix on dataset ordering for detail report's sorting issue on csv file. And it was applied for 1099 report as well since both are using same dataset. So removed that sorting fix from 1099 report dataset to fix this issue. 1 Defect was 1. Relevantz developed 2. We needed changes in setting to IIS AppPool to be in always running mode and the idle timeout to be much longer than 20 min. We didnt know that the ABP Framework required these settings for Jobs to run smoothly on the server. | 2 Escaped Defects were New requirement. MSB tickets were flowing through MSB without a provider, we made changes to include those to Accounting batches. and other Escaped defect was "Client Development. Existing issue. We needed to send the GL Account Types in lower case, and we were sending it with the first letter capitalised. This code has been there since the beginning, so maybe a change on the MSB side caused this to come up. This also affected the way MSB Tickets would be processing our GL Accounts, hence it was an escalation to be released ASAP. " | All the Significant defects were addressed. Knowledge share with Team in Stand Up, So that similar type of Defect/Issues can be mitigated. Only the Story is carry forwarded | Qadir, Rijo and Karthik | Closed | 2025-02-25
23 | 2025-03-11 | 14.5 Sprint 2 (26-Feb-2025 to 11-Mar-2025) | CRC, Defects | External | Metric Deviation | 1 CRC, 4 Defects | 1 CRC is from the Client regarding Automation Owen Seiber: 1. All the cleanups need to have calls to delete in the event something fails during the test and it does not cleanup after it. 2. Even though this is valid to add multiple tests into one class file, we should split these into individual test files. We can have CreateEditDeleteSchools, CreateEditDeleteDistricts and CreateEditDeleteSchoolDistricAdmin.. The reason for this is if the browser crashes during one test, it will prevent the rest from running. | 4 External Defects 2 External Defects were Client Development 2 Other External Defects were Envirnment Related and the other is Escalation from Prod - Sales Tax Error |  | All the Significant defects were addressed. Knowledge share with Team in Stand Up, So that similar type of Defect/Issues can be mitigated. | All Members | Closed | 2025-03-11
24 | 2025-03-25 | 14.5 Sprint 3 (12-Mar-2025 to 25-Mar-2025) | One Story Carryforwarded, PR Comments, Defects | Internal/External | Metric Deviation | 1 PR Comment, 1 Story Carry Forwarded, 4 Defects (1 Internal and 3 External) | 1 PR Comment - Suggestion - During PR Testing - The batch disappears after Jornalling the reversal deposit. This should happen only after Import, and not journalling the original deposit. | 1 Story Carryforwarded - Regression - Need to cover more modules | 4 Defects 1 Internal and 3 External which are Existing Issues and Environment Related | All the Significant defects were addressed. Knowledge share with Team in Stand Up, So that similar type of Defect/Issues can be mitigated. The Team is working on Segregating the Regression Story Module by Module | All Members | Closed | 2025-03-25
25 | 2025-04-08 | 14.6 Sprint 1 (26-Mar-2025 to 08-Apr-2025) | Story Carryforwarded | Internal/External | Metric Deviation | 3 Stories Carry forwarded | NA | Found few scenarios and extended the scope during the development process |  | To mitigate this issue, evaluate the impact of new scenarios, prioritize essential changes, adjust timelines and resources accordingly, and ensure transparent communication with all stakeholders. | All Members | Closed | 2025-04-22
26 | 2025-04-22 | 14.6 Sprint 2 (09-Apr-2025 to 22-Apr-2025) | CRC, Defect, Bouncebacks | Internal/External | Metric Deviation | 1 CRC, 1 Defect, 3 Bouncebacks | 1 Onsite CRC - UI issue Align Toggle to the right hand side of the table | 1 Defect - Found when analysing other ticket. Existing issue on the query | 3 Bouncebacks - Migration deployment | All the Significant defects were addressed and fixed. To mitigate these issues team should improve the Unit testing | All Members | Closed | 2025-04-22
27 | 2025-05-06 | 14.6 Sprint 3 (22-Apr-2025 to 06-May-2025) | Bouncebacks | Internal | Metric Deviation | 2 Bouncebacks |  |  | 2 Bouncebacks - Null value and Date validation | All the Significant defects were addressed and fixed. To mitigate these issues team should improve the Unit testing | Rijo/Karthik | Closed | 2025-05-06
28 | 2025-05-20 | 14.7 Sprint 1 (07-May-2025 to 20-May-2025) | Defects, Bouncebacks | internal/External | Metric Deviation | 1 Bounceback, 2 Internal Defect, 1 ExternalDefect |  | 1 Bounceback - Found during testing. The code was not setting from backend 2 Internal Defects - When bulk entry the framework was delay for multiple schools | 1 External issue - Import payments, bank deposits created balance error. Team fixed it by updating the amounts to zero to avoid calculation issues. | All the Significant defects were addressed and fixed. To mitigate these issues team trying to test with thirdparty data. | All Members | Closed | 2025-05-20
29 | 2025-05-21 | 14.7 Sprint 2 (21-May-2025 to 03-Jun-2025) | CRC,Defects, Bouncebacks | internal/External | Commitment Deviation | 1 Bounceback, 2 Internal Defect, 3 ExternalDefect | 2 Onsite CRC- Change return type for Task and Use localization | 1 Bounceback - Database Mapping issue 2 Internal Defects - Releted to mapping issue and flag update | 3 External Issue - Related to Database and Requirement gap | All the Significant defects were addressed and fixed. To mitigate these issues team shoud plan the Database mapping and Improve analysis | All Members | Closed | 2025-06-03
30 | 2025-06-04 | 14.7 Sprint 3 (04-Jun-2025 to 17-Jun-2025) | Defects, Bouncebacks | internal/External | Metric Deviation | 2 Bounceback, 3 Internal Defect, 2 ExternalDefect |  | 2 Bounceback - Issue found during testing and fixed by team 2 Internal Defects - Existing issued found during Regression testing. | 1 External Issue - Existing issue roll overed found when regression testing 1 - External Issue worked ny client | All the Significant defects were addressed and fixed. To mitigate these issues team shoud look more into existing workflow | Qadir | Closed | 2025-06-17
31 | 2025-06-18 | 15.0 Sprint 1 (18-Jun-2025 to 01-Jul-2025) | CRC, Storry Carried over, Defects | internal/External | Commitment Deviation | 1 External CRC, 2 Internal Defects, 8 Story points carried over | 1 Onsite CRC- QA Automation method validation | 2 Internal Defects - Existing issued found during Regression testing. | Ticket Carried Over - Due to Onsite QA vacation unable to get approval and Misplanned Story points | All the Defects were addressed and fixed. For Commitment Deviation Team need to analyse the story and plan before start to work and need to complete the task in early so that the unavailability will not occur | All Members | Closed | 2025-07-01
32 | 2025-06-18 | 15.0 Sprint 1 (18-Jun-2025 to 01-Jul-2025) | Committment Index Deviation | internal/External | Commitment Deviation | 8 Story points carried over | 3 SP missed because Owen was on vacation and couldnt review. 5 SP missed because we planned 2 stories with 5 sp each which eventually needed to be completed together to release. We could have planned this better. 2 SP from stretch was blocked because we need customer confirmation |  |  | Sprint planning was done properly for the supsequent sprint. Next sprint was planned to include the carry forwarded story. Owen completed the story after he return from vacation | All Members | Closed | 2025-07-17
33 | 2025-07-17 | 15.0 Sprint 2 (02-Jul-2025 to 16-Jul-2025) | CRC, Storry Carried over, Defects | internal/External | Commitment Deviation | 12 Story points carried over | Over committment with the stories taken for the sprints. Alphine reports got extended. There is blocker with a with story on Batchid. | 1Internal Defects - Existing issued found during Regression testing. |  | Over filled stories are communicated with client taken for the subsequent sprint to completed | All Members | Closed | 2025-07-17
34 | 2025-08-26 | 15.0 Sprint 2 (13-Aug-2025 to 26-Aug-2025) | Story Carryforwarded | internal/External | Commitment Deviation | 11 Story points carried over | Missed 11 sp due to time spent on escalations that came in during the sprint. Most of the customer support required new feature implementation or impossible to implement. | During the anaylsis we have found the |  | Discussed with client and set the expectation. Working on with client to how to handle the scenarios | All Members | Closed | 2025-09-09
35 | 2025-09-23 | 15.2 Sprint ` (10-Sep-2025 to 23-Sep-2025) | Story Carryforwarded | internal/External | Commitment Deviation | 14 Story points carried over | The alpine stories took more time than expected, and also few AC points were added later to the story. We had some escalations and spent time looking for the rooot cause. | AC were added at the last minute |  | Worked with PO to set the expecation with client on delay | All Members | Closed | 2025-09-23
36 | 2025-10-21 | 15.2 Sprint 3 (8-Oct-2025 to 21-Oct-2025) | Committment Index Deviation | internal/External | Commitment Deviation | 3 Stories Carry forwarded | This was initially forecast as a Regression sprint, however, due to escalations from the customer on a number of stories from the backlog, we had to work on those instead. The team completed all the work on escalaltion that caused a deviation in our planning, and also released a hotfix to an issue which arised from duplicate FeeIds for different products on the batches, as well as the ability to update the dates on reversal entries. | Escalations were recorded |  | Try to neogiate with client on completion of the customer escalation. Not include as part of the sprint comittments | All Members | Closed | 2025-10-21
37 | 2025-11-04 | 15.3 Sprint 1 (22-Oct-2025 to 04-Nov-2025) | 2 External defects | External | Commitment Deviation | 2 External defects | Existing issues, escalation tickets were assigned |  |  | Going foward will concentrate on main commit story/defects and plan accordingly | Qadir | Closed | 2025-11-04
38 | 2025-11-04 | 15.3 Sprint 1 (22-Oct-2025 to 04-Nov-2025) | Story Carryforwarded | internal/External | Commitment Deviation | 2 Story/Defect Carry forwarded | 2 items of 1SP each missed from main commit.(Alpine SSO due to focus on other high priority issues at hand and Beginning bal defect verification due to prod db backup delay.) |  |  | Going foward will concentrate on main commit story/defects and plan accordingly | Qadir | Closed | 2025-11-04
39 | 2025-11-18 | 15.3 Sprint 2 (05-Nov-2025 to 18-Nov-2025) | Story Carryforwarded | internal/External | Commitment Deviation | 1 Story Carry forwarded | SSO login blocked due to WAF issue on MSB. |  |  | Planning to complete in next sprint since its low priority concentrated on high so there was some delay. | Qadir | Closed | 2025-11-18
40 | 2025-12-02 | 15.3 Sprint 3 (19-Nov-2025 to 02-Dec-2025) | Committment Index Deviation | internal/External | Commitment Deviation | 4 Stories / 1 Defect Carry forwarded | A WAF issue originating from MSB, which we cannot resolve ourselves and must wait for MSB or other teams to fix. | 1. (26348) We have been waiting for customer feedback for some time. Since this defect originated from a customer escalation, we cannot proceed with closure until their feedback is received. 2.(50920) During testing, we identified new performance issues that were not part of the original scope of this story. | Regression stories - A migration issue was encountered on the CERT server, where one migration did not execute during deployment.This issue could not be reproduced on local development or the Dev server. | 1.Ongoing escalations, which required prioritization and diverted focus.If team members remain occupied with escalations, we will delegate this work to other available team members. (WAF Issue) 2.We are planning to incorporate load testing to ensure system stability and scalability on given the increasing number of users and the potential for handling larger datasets for performances issue. 3. For Migration issue will try to improve visibility and troubleshooting, we plan to add logging to future migrations so that such issues can be identified more easily. | All Members | Closed | 2025-12-16
41 | 2025-12-19 | 20.1 Sprint 1 (03-Dec-2025 to 16-Dec-2025) | Committment Index Deviation | internal/External | Commitment Deviation | 2 Stories Carry forwarded | New and only 1 QA so Could not complete testing as we took a bit more time than expected to complete testing. | Both stories were in the testing phase and close to completion. However, the testing process took longer than expected, and we were unable to close them within the sprint. Our sole QA was recently replaced by a new team member who is still ramping up. We expect the workflow to stabilize and run smoothly within the next few weeks. |  | Will speed up QA through improved test planning and prioritization of core scenerios | Sowjanya | Closed | 2025-12-22
42 | 2025-12-24 | 20.1 Sprint 1 (03-Dec-2025 to 16-Dec-2025) | 3 Internal defects | Internal | Others | 3 Internal defects | All defects were not identified and fixed in the same sprint | Some defects orginated from the legacy application, which got reported over time and still in the backlog. Those will be worked on priority in the future. And the defects that we finds during regressions also being kept in the backlog, which will be pulled later for working. |  | Going foward will plan and schedule the backlog fixes. | All Members | Closed | 2025-12-18
43 | 2025-12-24 | 20.1 Sprint 1 (03-Dec-2025 to 16-Dec-2025) | 3 External defects | External | Others | 3 External defects | All defects were not identified and fixed in the same sprint | Some defects orginated from the legacy application, which got reported over time and still in the backlog. Those will be worked on priority in the future. And the defects that we finds during regressions also being kept in the backlog, which will be pulled later for working. |  | Going foward will plan and schedule the backlog fixes. | All Members | Closed | 2025-12-18
44 | 2025-12-24 | 20.1 Sprint 1 (03-Dec-2025 to 16-Dec-2025) | CRC | internal/External | Others | CRC | Identified the null validation missing | Updated the null validation as per the client comment and updated the code |  | Will ensure follow the coding standard practice | All Members | Closed | 2025-12-18
45 | 2026-01-13 | 26.01 Sprint 2 (17-Dec-2025 to 13-Jan-2026) | Committment Index Deviation | internal/External | Commitment Deviation | 3 Stories Carry forwarded | 49897 - We severely underestimated the work involved and the number of issues we found during release and deployment. | 48709, 51242 - The dev(Rijo) was completely blocked from work for 3 days due to e-hps login blocker because of authenticator issue. We have created a ticket with support team and continuously followed up, informed client scrum master, PO and Manager. It still took 3 days to resolve. |  | *Need to get more details before planning and estimate higher considering the unknowns. *The client team will follow up with the support team to make the process faster, nothing much we can do here | All Members | Closed | 2026-01-27
46 | 2026-01-13 | 26.01 Sprint 2 (17-Dec-2025 to 13-Jan-2026) | 4 External defects | internal/External | Others | 4 External defects | 26570 - This defect was created a day before sprint end date from one of the escalation, and it was not estimated(0 SP). |  |  | Going foward will plan accordingly. | Karthik | Closed | 2026-01-27
47 | 2026-01-27 | 26.2 Sprint 3(14-Jan-2026 to 27-Jan-2026) | 5 Internal defects | Internal | Others | 5 Internal defects | Completed all commited items from main sprint except 1 defect which was pulled into the sprint on the last day with 0 SP. |  |  | All the Significant defects were addressed and fixed. To mitigate these issues team should improve the Unit testing | All Members | Closed | 2026-01-27
48 | 2026-01-27 | 26.2 Sprint 3(14-Jan-2026 to 27-Jan-2026) | 5 External defects | External | Others | 5 External defects | Completed all commited items from main sprint except 1 defect which was pulled into the sprint on the last day with 0 SP. |  |  | All the Significant defects were addressed and fixed. To mitigate these issues team should improve the Unit testing | All Members | Closed | 2026-01-27
49 | 2026-01-27 | 26.2 Sprint 3(14-Jan-2026 to 27-Jan-2026) | 1 defect Carry forwarded | internal/External | Commitment Deviation | 1 defect Carry forwarded | Completed all commited items from main sprint except 1 defect which was pulled into the sprint on the last day with 0 SP. |  |  | Assign story points and estimate properly. Review why it was added late and address the root cause. Communicate clearly in sprint review to maintain transparency. | All Members | Closed | 2026-01-27
50 | 2026-02-10 | 26.3 Sprint 1(28-Jan-2026 to 10-Feb-2026) | 1 story carry forwarded | Internal | Others | Commitment index deviation | One story carry forwarded due to escalation tickets prioritization | Team was assigned 3 escalation tickets during the mid of the sprint, so one story with 5 sp is carry forwarded to next sprint |  | Assign story points and estimate properly. Review why it was added late and address the root cause. Communicate clearly in sprint review to maintain transparency. | All Members | Closed | 2026-02-10
51 | 2026-02-10 | 26.3 Sprint 1(28-Jan-2026 to 10-Feb-2026) | 5 Internal defects | Internal | Others | 5 Internal defects | Existing defects identified during regression testing | Identified this issue from error logs. The vendor category was not pre-populating on purchase orders, invoices, and manual check entries based on the selected vendor. The reversal entry was being created when confirming, before the reversal entry form was opened, instead of on form submission |  | All the Significant defects were addressed and fixed. To mitigate these issues team should improve the Unit testing | All Members | Closed | 2026-02-10
52 | 2026-02-10 | 26.3 Sprint 1(28-Jan-2026 to 10-Feb-2026) | 5 External defects | External | Others | 5 External defects | Existing production defects assigned as tasks | Existing production defects that were assigned as tasks and fixed those defects. 3 are escalation tickets were assigned, out of which 2 escalation tickets were completed and one escalation ticket is pending for data validation which will be closed by 20th Feb |  | Increase the unit testing coverage to eliminate the production defects | All Members | Closed | 2026-02-20
53 | 2026-02-24 | 26.3 Sprint 2(11-Feb-2026 to 24-Feb-2026) | 1 story carry forwarded | Internal | Others | Commitment index deviation | One story carry forwarded due to PR pending for client approval | Team has completed the story but it was pending for PR approval from client end |  | Communicate clearly to the client and highlight the risk of spill over of the story due to the approval process | All Members | Closed | 2026-02-24
54 | 2026-02-24 | 26.3 Sprint 2(11-Feb-2026 to 24-Feb-2026) | 6 Internal defects | Internal | Others | 6 Internal defects | Existing defects assigned as tasks | Existing issue from the beginning when we got the project. It was reported and added in the back log long time back. Now we are clearing defects from backlog. |  | All the Significant defects were addressed and fixed. These were assigned as tasks to fix the existing issues in the system | All Members | Closed | 2026-02-24
55 | 2026-02-24 | 26.3 Sprint 1(28-Jan-2026 to 10-Feb-2026) | 2 External defects | External | Others | 2 External defects | Existing production defects assigned as tasks | Production data issue. Fixed with data update query on production db. |  | Increase the testing coverage to eliminate the production issues that are related to data | All Members | Closed | 2026-02-24
56 | 2026-03-10 | 26.3 Sprint 3(25-Feb-2026 to 10-Mar-2026) | 2 story carry forwarded | External | Others | Commitment index deviation | 2 stories carry forwarded due to 1 story testing pending with client QA and 1 story pending for POV approval from client | Team has completed the story but it was pending for testing and POV approval from client |  | Communicate clearly to the client and highlight the risk of spill over of the story due to the approval process | All Members | Closed | 2026-03-10
57 | 2026-03-10 | 26.3 Sprint 3(25-Feb-2026 to 10-Mar-2026) | 4 Internal defects | Internal | Others | 4 Internal defects | Existing defects assigned as tasks | Existing issue from the beginning when we got the project. It was reported and added in the back log long time back. Now we are clearing defects from backlog. |  | All the Significant defects were addressed and fixed. These were assigned as tasks to fix the existing issues in the system | All Members | Closed | 2026-03-10
58 | 2026-03-10 | 26.3 Sprint 3(25-Feb-2026 to 10-Mar-2026) | 1 External defects | External | Others | 1 External defects | Existing production defects assigned as tasks | Existing production defects that were assigned as tasks and fixed those defects. 1 escalation ticket assigned and it was closed |  | Increase the testing coverage to eliminate the production issues that are related to data | All Members | Closed | 2026-03-10
59 | 2026-03-10 | 26.3 Sprint 3(25-Feb-2026 to 10-Mar-2026) | 1 CRC comments | External | Others | 1 External CRC | Client has provided a suggestion as part of the CRC | Warning icon is missing in popup. The symbols are flashing on the screen at page load time. |  | Will ensure follow the coding standard practice | All Members | Closed | 2026-03-10
60 | 2026-03-24 | 26.4 Sprint 1(11-Mar-2026 to 24-Mar-2026) | 1 Internal defects | Internal | Others | 1 Internal defect | Existing defect found during internal regression testing | Existing issue that was found during the regression testing phase |  | All the Significant defects were addressed and fixed. Increase the regression testing coverage to find and fix the existing defects | All Members | Closed | 2026-03-25
61 | 2026-03-24 | 26.4 Sprint 1(11-Mar-2026 to 24-Mar-2026) | 6 External defects | External | Others | 6 External defects | Existing production defects assigned as tasks | Existing production defects that were assigned as tasks and fixed those defects. 5 escalation tickets and 1 defect task were assigned and it were closed |  | Increase the testing coverage to eliminate the production issues that are related to data | All Members | Closed | 2026-03-25
62 | 2026-03-24 | 26.4 Sprint 1(11-Mar-2026 to 24-Mar-2026) | 1 story carry forwarded | External | Others | 1 Story Carry forwarded | Overall, it was a good sprint. We completed all committed items from the main sprint except one, which is pending PR creation due to an unexpected team member’s sick leave. Additionally, we completed two stretch items and made good progress on the remaining stretch goals. | Client has been informed during the sprint that one story would be spill over due to one of the team member's emergency leave |  | Communicate clearly to the client and highlight the risk of spill over of the story due tounexpected team member's leave | All Members | Closed | 2026-03-25
63 | 2026-04-07 | 26.4 Sprint 2(25-Mar-2026 to 07-Apr-2026) | 3 Internal defects | Internal | Others | 3 Internal defects | Existing issue, but recently found. The initial 0s before a digit was getting truncated. Existing issue, account number search doesn't find masked number if search with unmasked numbers. Existing issue, This issue occured in time zones other than the central time zone | Existing issue that was found during the regression testing phase |  | These are existing defects due to data issues and timezone. All the Significant defects were addressed and fixed. Increase the regression testing coverage to find and fix the existing defects | All Members | Closed | 2026-04-07
64 | 2026-04-07 | 26.4 Sprint 2(25-Mar-2026 to 07-Apr-2026) | 3 External defects | External | Others | 3 External defects | 1. Existing issue with vendor object mapping for refund check types. A code fix is required, so we may need to provide a hotfix based on the customer's requirement. 2. To handle duplicate records showing up in the reports 3. Existing issue with vendor object mapping for refund check types. | Existing production defects that were assigned as tasks and fixed those defects. |  | Increase the testing coverage to eliminate the production issues and handle the edge case scenarios. | All Members | Closed | 2026-04-07
65 | 2026-04-21 | 26.04 Sprint 3( 08-Apr-2026 to 21-Apr-2026) | 3 story carry forwarded | External | Others | 3 Story Carry forwarded | 3 Regression testing stories were carry fwd and continue to do the regression testing and do the defect fixes before the release. | Client is aware that the regression testing stories would be carry fwd to the next sprint for the defect fixes. |  | Communicate clearly to the client and highlight the risk of spill over of the story due tounexpected team member's leave | All Members | Closed | 2026-05-05
66 | 2026-04-21 | 26.04 Sprint 3( 08-Apr-2026 to 21-Apr-2026) | 3 Internal defects | Internal | Others | 3 Internal defects | This issue occured in time zones other than the central time zone because the GL account maintenance current balance was calculated using the server's current date and time. Existing issue, the header row of the first entry in a standard transfer was not printed in the CSV | Existing issue that was found during the regression testing phase |  | Defects were found during the regression testing and it has been fixed. Increase the unit testing to eliminate the defects. | All Members | Closed | 2026-04-22
67 | 2026-04-21 | 26.04 Sprint 3( 08-Apr-2026 to 21-Apr-2026) | 2 External defects | External | Others | 2 External defects | Issue with PO zip code validation was an existing issue Backorder not saving (Glendale) | Existing production defects that were assigned as tasks and fixed those defects. |  | Increase the testing coverage to eliminate the production issues and handle the edge case scenarios. | All Members | Closed | 2026-04-22
68 | 2026-05-05 | 26.06 Sprint 1 (22-Apr-2026 to 05-May-2026) | 2 Internal defects | Internal | Others | 2 Internal defects | 1. Existing issue. When the user change the account number using re-number merge, the mapped gl account in import msb becomes invalid. This is a scenario we haven't considered while designing the mapping. 2. Existing issue. The cancel button is in disabled state while viewing the transfer and receipt entry. | This is an existing issue found during the regression testing phase |  | Defects were found during the regression testing and it has been fixed. Increase the unit testing to eliminate the defects. | All Members | Closed | 2026-05-05
69 | 2026-05-05 | 26.06 Sprint 1 (22-Apr-2026 to 05-May-2026) | 2 External defects | External | Others | 2 External defects | The customer had a duplicate adjustment entry in bank reconciliation. We were unable to replicate the issue, so we created a new defect to investigate the root cause. We also performed a data fix to resolve the customer's blocker. Existing issue. We had this in backlog for a long time since it is a low priority issue. The issue was "Submit" button getting disabled while opening popup. | Duplicate adjustment entry in bank reconciliation. Data fix provided to resolve it |  | Increase the testing coverage and find the data issues in lower environment and handle the edge case scenarios. | All Members | Closed | 2026-05-05

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Instructions (hidden)
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## Config
Sprint | 14.1 Sprint 3 (11-Sep-2024 to 24-Sep-2024) |  | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | 87.5% | 21.88% | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | 72.5% | 14.5% | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 79.31% | 15.86% |  |  | CF |  | Excellent |  | 25
Code Quality Index | 100% | 15% | Velocity
Unit Testing & Code Coverage | 90% | 9% | Goal | 20
Backlog Health | 100% | 10%
Code Coverage
|  |  | Goal | 90%
|  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  | Below Avg | 15 | Labels | Values |  | Story Points | 30
|  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  | Excellent | 30 | 15 | 10
|  |  | Total | 90 | 20 | 10
[5 empty] | 25 | 10
50