## Dashboard
BOH

## Scorecard
Project Name | MSB Activities
Engagement Model | Relevantz Co Owned
Overall Score | 100%
Current Sprint | 04.0 Sprint 2 (2-Jul-2025 to 15-July-2025)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% | 0 | 25% | 100%
Velocity | 100% | 20% |  | 20% | 95%
Defect-free Rate | 100% | 20% |  | 20% | 100%
Code Quality Index | 100% | 25% |  | 15% | 100%
Backlog Health | 100% | 10% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
03.0 Sprint 1 (27-Mar-2024 to 09-Apr-2024) | 14 | 9 | 64.29% | 20 | 90% | 0 | 3 | 1 | 1 | 30 | No |  |  | One of the offshore developer is on planned leave for the entire Sprint. Development completed for all 4 committed stories. (3 - Closed, 1 - Client POV pending) Development completed for 3 out of 4 stretch stories. (3 - PR approval pending from client, 1 - Development in progress) |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.0 Sprint 2 (10-Apr-2024 to 23-Apr-2024) | 20 | 12 | 60% | 20 | 90% | 0 | 1 | 1 | 4 | 30 | No |  |  | Development completed on 17-Apr, Client POV happened only on 22-Apr (Which is uncontrol) PR created on 22-Apr, Review 2 pending from client and stroy moved to next sprint. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.0 Sprint 3 (24-Apr-2024 to 07-May-2024) | 31 | 31 | 100% | 20 | 90% | 0 | 1 | 1 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.1 Sprint 1 (08-May-2024 to 21-May-2024) | 29 | 16 | 55.17% | 20 | 90% | 0 | 1 | 3 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.1 Sprint 2 (22-May-2024 to 04-Jun-2024) | 23 | 23 | 100% | 20 | 90% | 0 | 1 | 2 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.1 Sprint 3 (05-Jun-2024 to 18-Jun-2024) | 29 | 29 | 100% | 20 | 90% | 0 | 1 | 2 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.2 Sprint 1 (19-Jun-2024 to 02-Jul-2024) | 30 | 14 | 46.67% | 20 | 90% | 0 | 0 | 1 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.2 Sprint 2 (03-Jul-2024 to 16-Jul-2024) | 26 | 26 | 100% | 20 | 90% | 1 | 0 | 3 | 1 | 30 | No |  |  | 3.2 Sprint S2 Retro Appreciation : Assignees: Kristy MacCheyne - Client PO Kudos to everyone on the team. This was an awesome sprint. Allen - Leadership ensuring the team is all on the same page working toward our goals, helping out with getting stories completed to make 3.2 even better. His research for upcoming efforts and suggestions for how to best handle everything. Hari - Always extremely grateful for all of Hari's efforts. I can always trust that anything Hari takes on will be great. Kanchana - Kanchana continuously does an incredible job in this role ensuring we are all communicating effectively and that if/when there are questions we are able to discuss them to get on the same page. Her efforts to ensure we have stories written up for Refinements based on prioritized efforts is greatly appreciated. I also appreciate her collaboration with my new Business Analyst for my other team, Kanchana models how helpful her role can be to Product Management and I appreciate her willingness to provide guidance to my other team's BA. Kaliammal - Great work on wrapping up her first stories since getting access figured out. Manjunathan - Attention to detail and catching impressive finds while testing stories (ie: the final bounceback on 44444), ensuring testing wrapped up on everything heading into Planning for Regression. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.2 Sprint 3 (17-Jul-2024 to 30-Jul-2024) | 29 | 29 | 100% | 20 | 90% | 3 | 0 | 1 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.3 Sprint 1 (31-Jul-2024 to 13-Aug-2024) | #N/A | 24 | #N/A | 20 | 90% | 3 | 0 | 2 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.3 Sprint 2 (14-Aug-2024 to 27-Aug-2024) | 32 | 19 | 59.38% | 20 | 90% | 0 | 0 | 8 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.3 Sprint 3 (28-Aug-2024 to 10-Sep-2024) | 21 | 19 | 90.48% | 20 | 90% | 0 | 2 | 5 | 1 | 30 | Yes |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.4 Sprint 1 (11-Sep-2024 to 24-Sep-2024) | 23 | 23 | 100% | 20 | 90% | 0 | 1 | 2 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.4 Sprint 2 (25-Sep-2024 to 08-Oct-2024) | 22 | 21 | 95.45% | 20.5 | 90% | 2 | 2 | 3 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.4 Sprint 3 (09-Oct-2024 to 22-Oct-2024) | 14 | 22 | 100% | 21 | 100% | 1 | 0 | 0 | 0 | 30 | Yes |  |  | Regression Sprint |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.5 Sprint 1 (23-Oct-2024 to 05-Nov-2024) | 24 | 11 | 45.83% | 20.75 | 80% | 1 | 0 | 0 | 0 | 30 | No |  |  | 46323 - Testing not completed due to PTO of both offshore and client QA 46336 - PR delayed due to existing issues in related component Regression Sprint 46355 - Timebox story 46032 - Stretch story |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.05 Sprint 2 (06-Nov-2024 to 19-Nov-2024) | 29 | 37 | 100% | 22.25 | 100% | 0 | 0 | 2 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.05 Sprint 3 (20-Nov-2024 to 03-Dec-2024) | 21 | 39 | 100% | 22 | 100% | 2 | 2 | 6 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.05 Sprint S4 (04-Dec-2024 to 02-Jan-2025) | 24 | 55 | 100% | 24.5 | 100% | 0 | 0 | 7 | 2 | 30 | Yes |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.06 Sprint S1 (03-Jan-2025 to 14-Jan-2025) | 14 | 32 | 100% | 22 | 100% | 1 | 1 | 2 | 2 | 30 | No |  |  | Few Stories are moved to 3.7 that Contains DataBase Column Name Changes - Slated for 3.7 release. One Story is On hold by Client QA |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.06 Sprint S2 (15-Jan-2025 to 28-Jan-2025) | 43 | 50 | 100% | 25.5 | 100% | 0 | 2 | 7 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.06 Sprint S3 (29-Jan-2025 to 11-Feb-2025) | 20 | 31 | 100% | 25.25 | 100% | 1 | 0 | 7 | 1 | 30 | Yes |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.07 Sprint 1 (12-Feb-2025 to 25-Feb-2025) | 23 | 37 | 100% | 25 | 100% | 0 | 2 | 2 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.07 Sprint 2 (26-Feb-2025 to 11-Mar-2025) | 23 | 38 | 100% | 39 | 100% | 1 | 5 | 2 | 3 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.07 Sprint 3 (12-Mar-2025 to 25-Mar-2025) | 15 | 25 | 100% | 32.75 | 100% | 0 | 1 | 0 | 0 | 30 | Yes |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.08 Sprint 1 (26-Mar-2025 to 08-Apr-2025) | 36 | 28 | 77.78% | 32 | 90% | 5 | 1 | 3 | 1 | 30 | No |  |  | Due to lot of POV Comments the development time has been extended and carry forward to the next sprint with 8 SP |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.08 Sprint 2 (09-Apr-2025 to 22-Apr-2025) | 29 | 27 | 93.1% | 29.5 | 95% | 2 | 2 | 0 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.08 Sprint 3 (23-Apr-2025 to 06-May-2025) | 9 | 19 | 100% | 24.75 | 100% | 2 | 1 | 0 | 0 | 30 | Yes |  |  | Everything went Well. No Defects, No Carry Forward |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.09 Sprint 1 (07-May-2025 to 20-May-2025) | 26 | 23 | 88.46% | 24.25 | 93% | 1 | 2 | 4 | 1 | 30 | No |  |  | Mostly all the commiteed Stories has been completed. Only one story has the AC change and its in Testing Phase. Out of 3 Strech stories 2 of tem are completed from development and its in testing phase. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
03.9 Sprint 2 (21-May-2025 to 3-Jun-2025) | 24 | 29 | 100% | 24.5 | 100% | 0 | 0 | 3 | 3 | 30 | No |  |  | All the Comitted stories has been completed and worked on strech stories too.
03.9 Sprint 3 (4-Jun-2025 to 17-Jun-2025) | 32 | 52 | 100% | 30.75 | 100% | 0 | 0 | 2 | 2 | 30 | Yes |  |  | Everything went well. All the Committed stories have been completed, and worked on stretch stories too. Both internal and External defects were also fixed by the team.
04.0 Sprint 1 (18-Jun-2025 to 1-July-2025) | 37 | 44 | 100% | 30.75 | 100% | 3 | 3 | 0 | 0 | 30 | Yes |  |  | Everything went well. All the Committed stories have been completed, and worked on stretch stories too.
04.0 Sprint 2 (2-Jul-2025 to 15-July-2025) | 40 | 47 | 100% | 30.75 | 100% | 0 | 0 | 1 | 0 | 30 | Yes |  |  | Everything went well. All the Committed stories have been completed.
04.0 Sprint 3 (16-Jul-2025 to 29-July-2025) | 27 | 28 | 100% | 30 | 100% | 0 | 0 | 1 | 0 | 30 | Yes |  |  | Completion of Regression Testing within the sprint
04.1 Sprint s1 (30-Jul-2025 to 12-Aug-2025) | 31 | 34 | 100% | 30 | 100% | 4 | 0 | 5 | 0 | 30 | Yes |  |  | 1.Completed View All[Registrations] page to Server Side sorting 2.Completed converting the CSHTML pages to React a) Record-Not-Found b) Tenant mismatch c) Site mismatch 3.Completed the analysis of Site Registrations URL (discovery)
04.1 Sprint s2 (13-Aug-2025 to 26-Aug-2025) | 32 | 37 | 100% | 30 | 100% | 1 | 0 | 0 | 3 | 30 |  |  |  | The 3 escaped defects from the earlier release not with current sprint deliverable.
04.1 Sprint s3 (27-Aug-2025 to 09-Sep-2025) | 28 | 28 | 100% | 30 | 100% | 5 | 0 | 1 | 0 | 30 | Yes |  |  | 4.1 went for regression testing.
04.2 Sprint S1 (10-Sep-2025 to 23-Sep-2025) | 35 | 35 | 100% | 30 | 100% | 1 | 0 | 1 | 0 | 30 | Yes |  |  | 4.2 release started.
04.2 Sprint S2 (24-Sep-2025 to 07-Oct-2025) | 22 | 23 | 100% | 30 | 100% | 0 | 0 | 0 | 0 | 30 | Yes |  |  | 4.2 Sprint 2 delivered key outcomes.
04.2 Sprint S3 (08-Oct-2025 to 21-Oct-2025) | 29 | 30 | 100% | 30 | 100% | 0 | 0 | 0 | 0 | 30 | Yes |  |  | 4.2 Sprint 2 delivered key outcomes.
04.3 Sprint S1 (22-Oct-2025 to 04-Nov-2025) | 39 | 39 | 100% | 30 | 100% | 1 | 2 | 0 | 0 | 30 | Yes
04.3 Sprint S2 (05-Nov-2025 to 18-Nov-2025) | 33 | 36 | 100% | 30 | 100% | 5 | 0 | 0 | 0 | 30 | Yes |  |  | 4.3 Sprint 2 delivered key outcomes
04.3 Sprint S3(19-Nov-2025 to 02-Dec-2025) | 23 | 33 | 100% | 30 | 100% | 0 | 0 | 0 | 1 | 30 | No |  |  | 4.3 Sprint 3 delivered key outcomes
26.2 Sprint S1(03-Dec-2025 to 16-Dec-2025) | 30 | 37 | 100% | 30 | 100% | 4 | 0 | 3 | 4 | 30 | No
26.2 Sprint S2(17-Dec-2025 to 13-Jan-2026) | 63 | 71 | 100% | 30 | 100% | 0 | 3 | 3 | 0 | 30 | No |  |  | 1 Story is carry forwarded in testing
26.2 Sprint S3(14-Jan-2026 to 27-Jan-2026) | 30 | 15 | 50% | 30 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | 3 Stories is carry forwarded in Peer review.
26.3 Sprint S1(28-Jan-2026 to 10-Feb-2026) | 26 | 39 | 100% | 30 | 100% | 0 | 1 | 5 | 0 | 30 | No
26.03 Sprint S2(11-Feb-2026 to 24-Feb-2026) | 26 | 35 | 100% | 30 | 100% | 0 | 1 | 5 | 2 | 30 | No
26.03 Sprint S3(25-Feb-2026 to 10-Mar-2026) | 6 | 12 | 100% | 30 | 100% | 0 | 2 | 1 | 3 | 30 | No
26.05 Sprint S1(11-Mar-2026 to 24-Mar-2026) | 28 | 23 | 82.14% | 30 | 100% | 0 | 8 | 2 | 0 | 30 | No
26.5 Sprint S2(25-Mar-2026 to 07-Apr-2026) | 35 | 28 | 80% | 30 | 100% | 0 | 3 | 2 | 1 | 30 | Yes |  |  | Internal defects are completed and External defect carry forwarded along 2 stories carry forwarded in testing phase
26.5 Sprint S3 (08-Apr-2026 to 21-Apr-2026) | 16 | 22 | 100% | 30 | 100% | 0 | 1 | 6 | 2 | 30 | Yes |  |  | External defects are completed and Internal defect carry forwarded along with 1 defect from main , Regression Sprint
26.5 Sprint S4 (22-Apr-2026 to 05-May-2026) | 9 | 9 | 100% | 30 | 100% | 0 | 1 | 9 | 0 | 30 | Yes |  |  | Internal defects are completed

## RCA
3 Why Analysis
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-04-08 | 3.0 Sprint 1 (27-Mar to 09-Apr) | Commitment index 67% acheived | External | Metric Deviation | Commitment Index Deviation | Client POV pending for 1 story, even though Relevantz development Work has been completed couple of days before sprint end and shared for PO Verification | Client PO went on Vacations, Which is uncontrol |  | Client PO went on Vacations, Which is uncontrol and can not Mitigate | Deva | Closed | 2024-04-10 | Reason for carried is informed during client standup. | Metric Deviation
2 | 2024-04-08 | 3.0 Sprint 1 (27-Mar to 09-Apr) | Popup Incorrect Msg displayed for New User Role | External | Metric Deviation | UI defect | Missed to Check for Pop Error Msg when another Role login | Missed to Unit Test in multiple Role Scenario | Assumed the one (Master Role ) will cover all the Scenario Type and Couldnt Test for individual Role Login | Similar type of requirement has to unit tested in all the Roles instead of Mast role- Knowledge share with Team in Stand Up, So that similar type of Defect can be mitigated. | Allen | Closed | 2024-04-08 | Issue should be identified during first round of internal Unit testing | Security Compliance
3 | 2024-04-08 | 3.0 Sprint 1 (27-Mar to 09-Apr) | Insted of Role ID , Role Name is Used which impact the Coding STD | External | Metric Deviation | Codding STD Missed | Missed the Stds in role ID configure in specific logic | Limited Analaysis done on the This Specific Logic |  |  | Hari / Allen | Closed | 2024-04-08 | Refix Given | Not adhered to Policy
4 | 2024-04-24 | 3.0 Sprint 3 (24-Apr to 07-May) | Typo - should be Unauthorized | External | Metric Deviation | Codding STD Missed | Typo error in automation code |  |  | Knowledge share with Team in Stand Up, So that similar type of review can be mitigated. | Allen | Closed | 2024-04-25
5 | 2024-05-20 | 3.1 Sprint 1 (08-May to 21-May) | Commitment index 55% acheived | Internal | Metric Deviation | Commitment Index Deviation | Client code review pending for 1 story, even though Relevantz development Work has been completed couple of days before sprint end. | Client Dev went on Vacations, Which is uncontrol |  | Client Dev went on Vacations, Which is uncontrol and can not Mitigate | Allen | Closed | 2024-05-21
6 | 2024-05-20 | 3.1 Sprint 1 (08-May to 21-May) | Code Review Comments 6% | Internal | Metric Deviation | Codding STD Missed | Limited Analaysis done on the This Specific Logic |  |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Allen | Closed | 2024-05-21
7 | 2024-06-04 | 3.1 Sprint 2 (22-May to 04-Jun) | Code Review Comments 4% | External | Metric Deviation | Codding STD Missed | Date check missed in Server side. | Limited Analaysis done on the This Specific Logic |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Hari | Closed | 2024-06-05
8 | 2024-07-02 | 3.2 Sprint 1 (19-Jun to 02-Jul) | Commitment index 47% acheived | Internal | Metric Deviation | Commitment Index Deviation | Development completed and issue reported during testing. | Limited Analaysis done on this Specific Logic |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Allen / Hari | Closed | 2024-07-04
9 | 2024-08-26 | 3.3 Sprint 2 (14-Aug to 27-Aug) | Commitment index 59% acheived | Internal | Metric Deviation | Commitment Index Deviation | Custom Registration Report story QA Inprogress, carried to next sprint. | Limited Analaysis done on this Specific Logic |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Kaliammal | Closed | 2024-08-26
10 | 2024-09-10 | 3.3 Sprint 3 (28-Aug to 10-Sep) | 2 External CRC, 1 Escapted Defects and 5 QA Defects | Internal/External | Metric Deviation | 2 External CRC, 1 Escapted Defects and 5 QA Defects | CRC -I don't think this gives the correct list of students, this seems to give every student in students list that isn't in the list of studentIDs in the queryParams | 1 Escaped Defect is | 5 QA Defects are the part of Regression Findings | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Kaliammal/Hari/Allen | Closed | 2024-09-10
11 | 2024-09-24 | 3.4 Sprint 1 (11-Sep to 24-Sep) | 1 External CRC, 2 QA Defects | Internal/External | Metric Deviation | Commitment Index Deviation | 2 QA Defects were Internal Findings | CRC - Suggestions and Changes - 1.Can we add permission checks for HSS users only on the functions in the controller 2.Consider moving all of these to a new DBDynamicReports class/file instead of adding them to DBTenants, I think that would follow our existing pattern of having a DB class to match the table in SQL. |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Hari / Allen | Closed | 2024-09-24
12 | 2024-10-08 | 3.4 Sprint 2 (25-Sep to 08-Oct) | 2 External CRC, 3 QA Defects | Internal/External | Metric Deviation | Commitment Index Deviation | CRC - Should this say Node instead of Mode? Can we please parameterize the userRecId in the 3 places that we use it in the SQL query | 3 QA Defects - Internal Findings and One Client Findings |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Kaliammal/Hari/Allen | Closed | 2024-10-08
13 | 2024-10-22 | 3.4 Sprint 3 (09-Oct to 22-Oct) | 1 Internal CRC | Internal | Metric Deviation | Commitment Index Deviation | CRC - Suggestion - Rename the PurchaseLastDate to PurchaseEndDate |  |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Kaliammal | Closed | 2024-10-22
14 | 2024-11-05 | 3.5 Sprint 1 (23-Oct to 05-Nov) | Commitment Index is 46% | Internal | Metric Deviation | 46323 - Testing not completed due to PTO of both offshore and client QA 46336 - PR delayed due to existing issues in related component Regression Sprint 46355 - Timebox story 46032 - Stretch story | Planned QA PTO's | Timebox Stories in Commit | PR was delayed due to existing issues in Related component | QA was on PTO and Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Hari / Allen | Closed | 2024-11-05 | The Client is well informed about the Stories and the Timebox stories are been carry forwarded to Next Sprint
15 | 2024-11-19 | 3.5 Sprint 2 (06-Nov to 19-Nov) | 3 Defects Identified | Internal/External | Metric Deviation | 2 Internal QA Defect Findings and 1 Production Issue | Production Issue - Existing Issue, Identified during last Smoke Test during Release, Since its not Critical, we worked now | The Other Defects were Existing Issue identified by Offshore QA | The Third defect was created as Story, because it needs more code changes overall reports. | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Hari / Allen | Closed | 2024-11-19 | The Client is well informed about the Defects.
16 | 2024-11-27 | 3.5 Sprint 3 (20-Nov to 03-Dec) | 6 Defects Reports and CRC Comments | Internal/External | Metric Deviation | 2 Internal CRC and 2 Client CRC 6 Defects Findings | CRC Comments: 1. Page break not returning report while selecting multiple site 2. Apply Bulk Registartion End Date ,Validation not working properly 3. typo in activities parameter name 4. The messaging on this error is specific to Enrollment Plans, but this is in the shared DataTable component, can we pass in a string prop that contains the name, or take some other approach to make this reusable | 4 Bounceback were reported during testing and 2 Internal defects were taken. The Internal Defects were already existing |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Hari/Allen/Kaliammal | Closed | 2024-12-04 | The Client is well informed about the Defects. All the reported issues were addressed, tested and closed
17 | 2025-01-02 | 3.5 Sprint 4 (04-Dec to 02-Jan) | 7 Defects | Internal/External | Metric Deviation | 7 Internal QA Defects | 7 Internal QA Defects were already Existing Issues which was fixed as a part of Regression and 4 Week Sprint |  |  | The Defects were already existing logical and functional changes, the team were given walk through on how to handle in the future | Hari/Allen/Kaliammal | Closed | 2025-01-16
18 | 2025-01-14 | 3.6 Sprint 1 (03-Jan to 14-Jan) | CRC, QA Defects, Carry Forwareded | Internal/External | Metric Deviation | 2 CRC, 4 QA Defects, Carry Forwarded | Few Stories are moved to 3.7 that Contains DataBase Column Name Changes - Slated for 3.7 release. One Story is On hold by Client QA to complete the remaining stories | 2 CRC - It's to change the logical/functional way of implementing the functionality | 4 QA Defects - 2 Bouncebacks and 2 QA Defects. PROD Issue,Found in the last sprint and carry forwarded to the current sprint QA,Integration and Cert env broken,Found in the last sprint and carry forwarded to the current sprint | The Defects were already existing logical and functional changes, the team were given walk through on how to handle in the future. | Hari/Allen/Kaliammal | Closed | 2025-01-14
19 | 2025-01-28 | 3.6 Sprint 2 (15-Jan to 28-Jan) | CRC, QA Defects, Carry Forwareded | Internal/External | Metric Deviation | 2 CRC, 7 Bounceback, 2 External QA Defects, Story Carry Forwarded | 2 CRC. One Q&A for the Dev and Other is for UI Representation Change | One Story is Carry Forwarded due to Lot of Testing Scenarios | 7 Bounceback - we had lot of scenarios to test and the team had some findings at the QA Testing. All were addressed. 2 External Qa defects, both are prod issues, both the defects have been adddressed | The Defects were already existing logical and functional changes, the team were given walk through on how to handle in the future. Have conveyed them to look for Unit Testing | Hari/Allen/Kaliammal | Open | 2025-02-11 | Client was informed. The Team had some last minute Prod issues, which changes their current working stories and also they had lot of scenarios to be tested.
20 | 2025-02-11 | 3.6 Sprint 3 (29-Jan to 11-Feb) | CRC, QA Defects | Internal/External | Metric Deviation | 1 CRC, 4 Bounceback, 3 Internal Defects and 1 External Defects | 1 CRC was suggestion on code restructuring | 4 Bounceback were internal findings which was carry forwarded from previous sprint | 3 Defects were regression defects which were addressed. One was carry forwarded since Its not going for Releas | 1 External defect was found Client QA moved to next sprint | Hari/Allen/Kaliammal | Open | 2025-02-26
21 | 2025-02-25 | 3.7 Sprint 1 (12-Feb-2025 to 25-Feb-2025) | CRC, QA Defects | Internal | Metric Deviation | 2 CRC, 2 Internal Defects and 1 Escaped Defects | 2 CRC was suggestion on code restructuring and logical suggestion from Client (Client has created one component and they want to move with same component in all places) | 2 Internal defects - Both were carry forwarded from Previous sprint, which is related to Custom Report. The issues were identified by Relevantz and Fixed | 1 Escaped defect which was found by Relevantz PO, during analysis, since it is not major and no one reported this issue, the client moved to stretch. The Dev work is completed and testing is carry forwarded to next sprint. | The Team fixed most of the issues and they have addressed all the defects. Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Hari/Kaliammal | Closed | 2025-02-25
22 | 2025-03-11 | 3.7 Sprint 2 (26-Feb-2025 to 11-Mar-2025) | CRC, QA Defects | Internal/External | Metric Deviation | 5 CRC, 3 External Defects, and 2 Bouncebacks | CRC: 1 Internal CRC - Code Optimization -Optimize the code for data table changes 5 External CRC - Logical Change as well as Code Refactoring I think this should be IS NOT NULL? If the column was just added, we'll be missing the constraint that was added above when the table is originally added. I think we need to conditionally add the UK_SITE_Name constraint here if the column exists but the constraint does not Missing BEGIN after IF Suggestions: I think this comment is left from the old process, can we remove or update it to reflect the new approach The constraint name being added here doesn't match the name used below (UK_SITENAME) so it will be added a second time | 3 External Defects - All the defects were found by Relevantz PO, those are already existing. Not a Showstopper. | 2 Bouncebacks - Index Error and Sorting issue | The Team fixed most of the issues and they have addressed all the defects. Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. Onsite Lead is working on a Mitigation plan to oversee the Code Quality as well as Defect Index. | All Members | Closed | 2025-03-11 | Allen - Onsite Lead and Andy - Client Dev are working on Setting up a Code Standards. So most of the comments they get are levelling up the codes.
23 | 2025-03-25 | 3.7 Sprint 3 (12-Mar-2025 to 25-Mar-2025) | CRC | External | Metric Deviation | 1 External CRC | Client Suggested to have a Filter Parameterized --- The filter text needs to be parameterized to prevent against SQL injection |  |  | The Team has addressed most of their defects, and have performed well in this sprint. They have one CRC which is a suggestion on a new approach for a feature | Allen | Closed | 2025-03-25 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
24 | 2025-04-09 | 3.8 Sprint 1 (26-Mar-2025 to 08-Apr-2025) | CRC, QA Defects | Internal/External | Metric Deviation | 6 CRC, 2 Internal Defects, and 2 Bouncebacks | Minor Code level cchanges has been raised as a CRC from Internal and Onsite Developer. Removing the Fields and hover changes has been given as a CRC | 2 internal defects - from the stretch stories from the Internal PO and 2 bounce back from the onsite and internal QA | Due to a lot of POV comments / suggestions from the team the development time has been extended and carry forwarded this story to the next sprint | Asked the team to analyse and get the knowledge of the AC completely before starting the developemnt | Allen | Closed | 2025-04-22 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
25 | 2025-04-23 | 3.8 Sprint 2 (09-Apr-2025 to 22-Apr-2025) | CRC, QA Defects | Internal/External | Metric Deviation | 4 CRC, 2 External Defects | 1. Minor level of code change has been raised as a Internal CRC "Remove unused imports" & "Remove isSubTextMode from IProps since it is not used" & Suggessions of External CRC has been raised (Standards Missed) 2. 2 of the Escalations has been spotted in this sprint, 1 is related to the DB change and other one is an Existing issue |  |  | 1.The Team fixed most of the issues and they have addressed all the defects. Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. 2. Coding STDS document is in enahancement based on the current client Expectation | Allen | Closed | 2025-05-16 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
26 | 2025-05-07 | 3.8 Sprint 3 (23-Apr-2025 to 06-May-2025) | CRC | Internal/External | Metric Deviation | 1 Onsite CRC & 1 Client CRC | 1. 1 Onsite CRC has been given to remove the particular line from the JSON file which is not needed and not noticed by the team 2. 1 Client CRC has been given to the team which comes as a suggession to change the variable name which leads to confusion | The team has not noticed the particular line which is not needed and the suggession given by the client is to avoid the confusion |  | Given the awarness to the team to check the code what ever has been modified / developed to be compared using the GIT and only the necessary details should be moved into the Azure Devops for Code Review | Kaliammal/Hari | Closed | 2025-05-07 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
27 | 2025-05-21 | 3.9 Sprint 1 (07-May-2025 to 20-May-2025) | CRC | Internal/External | Metric Deviation | 1 Onsite CRC & 2 Client CRC | 1. 1 Onsite CRC has been given to Change the variable name as a Naming conversion we follow as per Coding Standards. 2. 2 Client CRC has been given to the team as a suggesion that they have implemented a new approach on related to the infinite scroll down. | The team has not noticed the variable which we are following the coding standards on the Naming conversions |  | Given the awarness to the team to check the code what ever has been modified / developed to be compared using the GIT and only the necessary details should be moved into the Azure Devops for Code Review | Allen | Closed | 2025-05-20 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
28 | 2025-05-21 | 3.9 Sprint 1 (07-May-2025 to 20-May-2025) | QA Defects / Bounceback | Internal/External | Metric Deviation | 4 Bounceback and 1 Defect | 1. 4 Bounceback has been found in the current sprint by our internal QA for the current sprint 2. 1 Defect has been found from the external end which is an existing issue from the application which came as a defect. | Some of the negative scenarios has been missed by the developer in the Dev environment and found that as a defect from our Internal QA. |  | 1. One of the Mitigation plan we have proposed is, Gettign the negative scenarios from the QA while doing the manual unit testing from the developer end once the devlopment has been completed. | Allen / Hari | Closed | 2025-06-03
29 | 2025-06-04 | 3.9 Sprint 2 (21-May-2025 to 03-Jun-2025) | QA Defects / Bounceback | Internal/External | Metric Deviation | 4 Bounceback and 2 Defect | 1. 4 Bounceback has been found in the current sprint by our internal QA for the current sprint 2. 2 Defect has been found from the external end which is an existing issue from the application which came as a defect and 1 found by QA | Some of the negative scenarios has been missed by the developer in the Dev environment and found that as a defect from our Internal QA. |  | 1. One of the Mitigation plan we have proposed is, Gettign the negative scenarios from the QA while doing the manual unit testing from the developer end once the devlopment has been completed. | Allen / Hari | Closed | 2025-06-17
30 | 2025-06-18 | 3.9 Sprint 3 (4-Jun-2025 to 17-Jun-2025) | QA Defects / Bounceback | Internal/External | Metric Deviation | 2 Internal and 2 External Defect | 1. 3 Defects and 1 bounce back has been raised by the team 2. In the 3 defects two of them are existing prod issues and 1 has been fiund by our internal QA. 3. One bounce back has been raised by our internal team in the current sprint cycle. | Some of them are production existing issues and 1 bounce back is missed in the DEV testing |  | 1. One of the Mitigation plan we have proposed is, Gettign the negative scenarios from the QA while doing the manual unit testing from the developer end once the devlopment has been completed. | Allen / Hari | Closed | 2025-07-02
31 | 2025-07-02 | 4.0 Sprint 1 (18-Jun-2025 to 1-July-2025) | QA Defects / Bounceback | Internal/External | Metric Deviation | NIL | NIL | NIL | NIL | NIL | Allen / Hari | Closed | 2025-07-15
32 | 2025-07-02 | 4.0 Sprint 1 (18-Jun-2025 to 1-July-2025) | CRC | Internal/External | Metric Deviation | Client Code Review Comments | Received client to update the function name based on the return value. Also, asked to removed unwanted code as a suggestion. | NIL | NIL | Updated the function name as return value and removed the unwanted code. | Allen / Hari | Closed | 2025-07-15
33 | 2025-08-26 | 4.1 Sprint 2 (13-Aug-2025 to 26-Aug-2025) | QA Defects | Internal/External | Metric Deviation | 3 External Defect identified | The client qa identified 3 issues | Due to the issue with previous build the 3 issues were poped out now. | NIL | Requested the internal QA todo the regression properly before releasing to the client ensure there won't be any bug from the previous release | Allen / Hari | Closed | 2025-07-15
34 | 2025-12-02 | 4.3 Sprint S3 (19-Nov-2025 to 02-Dec-2025) | Defect | Internal/External | Metric Deviation | 1 External Defect identified | The issue identified from Production and existing one. | Site selection must be dynamically updated in response to changes in district selection, regardless of repeated selections. Additionally, the current site selection should always be accurately reflected in the site selector interface. | This item is scheduled for the next release (20.1) in accordance with the client's request and due to the client team's vacation. Development completed | We will ensure that all test cases are covered by QA team before moving to production and well plan accordingly | Ram | Closed | 2025-12-16
35 | 2026-01-13 | 26.2 Sprint S2(17-Dec-2025 to 13-Jan-2026) | Story Carry Forwareded | Internal/External | Metric Deviation | Commitment Index Deviation | This Story # 51138 - Activities - Non Student Registration - Update validation for checking for students in the msb household - Development is completed and pending for client approval Note – There were dependencies on MSB APIs, which became blockers for this story. The blockers were identified one after another and discussed with Allen and the client developer, Andy, for confirmation. The PR has been approved by Allen and is currently pending approval from the client developer, Andy. |  |  | Moving forward, Spend less time doing our own discovery when working with other teams (APIs) and go to the team with the information sooner | Sivaraja | Closed | 2026-01-27
36 | 2026-01-27 | 26.2 Sprint S3(14-Jan-2026 to 27-Jan-2026) | Story Carry Forwareded | External | Metric Deviation | Commitment Index Deviation | During the regression sprint, we completed development and Product Owner verification. The pull request will be merged only after the regression sprint ends. Note: As informed by the client, this story will be carried over to the next sprint for PR merging and testing efforts. |  |  | These stories were assigned a low priority during the regression sprint, as their target release was version 26.3. We recommend requesting the client to classify such items as development stories at the time of story creation during regression sprints. | All Members | Closed | 2026-02-10
37 | 2026-02-24 | 26.3 Sprint S2(11-Feb-2026 to 24-Feb-2026) | External Defect converted as Story and carry forwarded | External | Metric Deviation | 1 External Defect converted as Story and carry forwarded | Created as defect and stayed in backlog for 2 years then the team identifies it is not defect and more of enhancement so client agreed and created the story for next sprint |  |  | NIL | All Members | Closed
38 | 2026-03-24 | 26.5 Sprint S1(11-Mar-2026 to 24-Mar-2026) | Story Carry Forwareded | External | Metric Deviation | Commitment Index Deviation | This #52259 story is being carried forward to the testing phase only due to a last-minute design change request that modified the originally accepted design specifications and acceptance criteria.The client stakeholder has been informed and acknowledges the current status and the revised scope resulting from the design change |  |  | Client stakeholder has been informed, agreed to the revised scope, and acknowledged the updated delivery status. | All Members | Inprogress
39 | 2026-03-24 | 26.5 Sprint S1(11-Mar-2026 to 24-Mar-2026) | CRC | Internal/External | Metric Deviation | 8 Client CRC | Ethan Manager, as a new member of the team, inquired about these changes, and we provided him with a detailed explanation of the requirements. |  |  | Knowledge transfer and requirement walkthroughs were necessary to him thats the plan | All Members | Inprogress
40 | 2026-04-07 | 26.5 Sprint S2(25-Mar-2026 to -07-Apr-2026) | 2 Stories Carry Forwareded | Internal/External | Metric Deviation | Commitment Index Deviation | This story is carry forward to next sprint due to team got blocker as all lower environment were down for two days during this sprint. So Test effort will be carry forward. |  |  | Story is carried forward due to lower environment downtime. Test effort will be resumed in the next sprint once environments are stable, with priority given to complete pending testing activities. | All Members | Inprogress
41 | 2026-04-07 | 26.5 Sprint S2(25-Mar-2026 to -07-Apr-2026) | 1 External defect carry forwarded | External | Metric Deviation | Commitment Index Deviation | This defect is added on stretch with low priority, which is carry forwarded to next sprint main commit |  |  | Defect was added as a low‑priority stretch item and carried forward to the next sprint main commit. It will be addressed based on priority without impacting committed sprint deliverables. | All Members | Inprogress
42 | 2026-04-21 | 26.5 Sprint S3(08-Apr-2026 to -21-Apr-2026) | 1 defect carry forwarded | Internal/External | Metric Deviation | Commitment Index Deviation | Regression defect #27238 was identified at the end of the sprint and has been classified as low priority. Development has been completed, and the related testing effort will be carried forward to the next sprint. |  |  | Client agreed on the same and will accordingly in Future | All Members | Inprogress
43 | 2026-04-21 | 26.5 Sprint S3(08-Apr-2026 to -21-Apr-2026) | 1 Internal defect | Internal/External | Metric Deviation | Commitment Index Deviation | This defect found on end of the sprint, its low priority, and development effort is completed, test effort will be carry forward. |  |  | Client agreed on the same and will accordingly in Future | All Members | Inprogress
44
45

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 25% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 0% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Config
Sprint | 03.3 Sprint 3 (28-Aug-2024 to 10-Sep-2024) |  | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | 90.48% | 22.62% | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | 100% | 20% | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 70% | 14% |  |  | CF |  | Excellent |  | 25
Code Quality Index | 89.47% | 22.37% | Velocity
#REF! | 90% | 0% | Goal | 20
Backlog Health | 100% | 10%
Code Coverage
|  |  | Goal | 90%
|  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  | Below Avg | 15 | Labels | Values |  | Story Points | 30
|  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  | Excellent | 30 | 15 | 10
|  |  | Total | 90 | 20 | 10
[5 empty] | 25 | 10
50

## Instructions (hidden)
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data