## Dashboard
BOH

## Scorecard
Project Name | MSB DevServices
Engagement Model | Relevantz Co Owned
Overall Score | 92.59%
Current Sprint | 26.5 DS Sprint 2 (17-Apr-2026 to 30-Apr-2026)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% | #N/A | 25% | 100%
Velocity | 95.45% | 19.09% |  | 20% | 95%
Defect-free Rate | 90.84% | 18.17% |  | 20% | 100%
Code Quality Index | 75.57% | 11.34% |  | 15% | 100%
Unit Testing & Code Coverage | 90% | 9% |  | 10% | 90%
Backlog Health | 100% | 10% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
[16 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.01 DS Sprint 3 (12-Dec-2025 to 08-Jan-2026) | 54 | 67 | 100% | 67 | 90% | 2 | 0 | 2 | 0 | 30 | yes
26.03 DS Sprint 1 (09-Jan-2025 to 22-Jan-2026) | 41 | 27 | 65.85% | 47 | 90% | 14 | 2 | 2 | 0 | 30 | yes |  |  | Due to wave team inability, we are unable to complete the commitment.
26.03 DS Sprint 2 (23-Jan-2025 to 05-Feb-2026) | 55 | 42 | 76.36% | 45.3333 | 90% | 9 | 4 | 8 | 0 | 30 | yes |  |  | Due to wave team inability and unplanned leaves, we are unable to complete the commitment.
26.03 DS Sprint 3 (06-Feb-2026 to 19-Feb-2026) | 45 | 40 | 88.89% | 44 | 90% | 0 | 0 | 0 | 0 | 30 | yes
26.04 DS Sprint 1 (20-Feb-2026 to 05-Mar-2026) | 29 | 36 | 100% | 36.25 | 90% | 0 | 5 | 5 | 3 | 30 | No
26.04 DS Sprint 2 (06-Feb-2026 to 19-Mar-2026) | 27 | 30 | 100% | 37 | 90% | 0 | 0 | 1 | 3 | 30 | No |  |  | QA defect and Escaped defects are completed.
26.04 DS Sprint 3 (20-Mar-2026 to 02-Apr-2026) | 34 | 36 | 100% | 35.5 | 90% | 0 | 0 | 0 | 1 | 30 | No |  |  | External defect is closed
26.5 DS Sprint 1 (3-Apr-2026 to 16-Apr-2026) | 24 | 26 | 100% | 32 | 90% | 0 | 0 | 4 | 0 | 30 | No |  |  | QA defects are completed
26.5 DS Sprint 2 (17-Apr-2026 to 30-Apr-2026) | 36 | 39 | 100% | 32.75 | 90% | 7 | 1 | 2 | 1 | 30 | No
26.5 DS Sprint 3 (1-May-2026 to 14-May-2026) | 29 | 33 | 100% | 33.5 | 90% | 3 | 1 | 1 | 1 | 30 | No |  |  | QA defect and Escaped defects are completed.

## RCA
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Why 4? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-09-05 | 14.1 Sprint 3( Aug-23 to Sep-5) | 2 Escaped Defects | Internal/External | Metric Deviation | Commitment Index Deviation | 2 Escaped Defects from Production but givem for release in this version |  |  |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Prisla | Closed | 2024-09-05 |  | Not adhered to Policy
2 | 2024-09-19 | 14.2 Sprint 1(Sep-6 to Sep-19) | 2 External CRC, 2 QA Defects and 1 Escaped Defects | Internal/External | Metric Deviation | Commitment Index Deviation | External CRC - Suggestion - 1.Check for empty string first before comparing and Logical Findings - Move the business logic into util class. Add new DB column with the rest of the columns when the table is created and this column will be added automatically. | 2 QA Defects - Development Issues | 1 Escaped Defects - Development Issues |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Michael/Mahesh/Prisla | Closed | 2024-09-19 |  | Others
3 | 2024-10-03 | 14.2 Sprint 2[Sep-20 to Oct-3]​ | 2 Internal CRC, 5 External CRC and 6 QA Defects | Internal/External | Metric Deviation | Commitment Index Deviation | 2 Internal CRC - Suggestions - 1) Use getAppProps().getAppTimezone() 2) Include comment that past year has been restricted to 3 years on JS file | 5 External CRC - Suggestions and Logical Change - 1.Adjust this to use a temp table if necessary to prevent table locking. See StudentQueryAgentWorker.findStudents for an example. 2.This block of code should be in another try catch block so we don't skip the other fees should one fail. 3.These next 4 lines should be inside of the try as well so we don't count/log a failed delete as successful. 1) Avoide the duplicate code and modifying the adapter to accept a start date 2) Validate that the provider is actually a file mapping adapter | 6 QA Defects - Development, Requirement Gap |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Mahesh/Aravindth/Prisla | Closed | 2024-10-03
4 | 2024-10-17 | 14.2 Sprint 3 (Oct-4 to Oct-17) | 1 External CRC, 4 QA Defects | Internal/External | Metric Deviation | Commitment Index Deviation | External CRC - Suggestion - 1.this should be appProps that match the student, not the primary | 4 QA defects are existing findings during regression |  |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Mahesh/Aravindth/Prisla | Closed | 2024-10-17
5 | 2024-10-31 | 14.3 Sprint 1 (Oct-18 to Oct-31) | 7 Escaped Defects and 3 Internal Defects | Internal/External | Metric Deviation | Client Identified defects, Relevantz QA Findings, and Other Product Dependency (MSB Mobile) | Very Long Existing Issues, but we targeted these defects to work now | MSB Mobile Dependency (API Specific) | 3 Internal Defects are bouceback which are addressed |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Mahesh | Open (1 Pending and 9 Closed) | 2024-11-14 | 9 Closed and 1 is in Stretch Yet to be closed (Targeting in Next Sprint) | Metric Deviation
6 | 2024-11-14 | 14.3 Sprint 2 (1-Nov to 14-Nov) | 2 QA Defects and 1 Escaped Defects. 78% Commitment Index | Internal/External | Metric Deviation | 2 Defects were Bouncebacks and 1 is Prod Issue. Couldn't complete the Committed stories | 1Bounceback was identified during Internal Testing - Closed | Prod Issue was rare, it is not repro. The Team is working on this | Another Bounceback is in progress | Client QA is Testing . Needs to test in different timezones | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Prisla, Aravindh | 3 Open and 1 Closed | 2024-11-28 | The Client is informed about this. And they are currently testing the story. | Security Compliance
7 | 2024-11-28 | 14.3 Sprint 3 (15-Nov to 28-Nov) | 1 QA Defect and 2 Escaped Defect | Internal/External | Metric Deviation | 1 Defect was bounceback which was Timezone related issue that needs to be tested in all timezone. Closed | 2 Escaped Defects from Production but given for release in this version. Existing Production Defect. Based on Priority we took this in to Stretch. Minor Defect. |  |  |  | The Defects were fixed and the Team closed the defects with Testing | Prisla, Aravindh | Closed | 2024-11-28
8 | 2024-12-12 | 14.4 Sprint 1 (29-Nov to 12-Dec) | 1 QA Defect and 4 Escaped Defect | Internal/External | Metric Deviation | 1 Defect was bounceback which was related to Not handle null for multi client scenario. Closed | 4 Escaped defects were Existing Production Defect. Based on Priority we took this in to Stretch. Minor Defect. And 2 other analysis oriented |  |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis and Knowledge Shared to the other team members | Mahesh/Aravindth/Prisla | Closed | 2024-12-12
9 | 2025-01-09 | 14.4 Sprint 2 (13-Dec to 09-Jan) | 2 CRC Comments and 3 Defects | Internal/External | Metric Deviation | 2 CRC Comments and 2 Bounceback and 1 Defect | Suggestion from Clients: 1.see comment in the adapter code about this... there are some examples in StudentInfo that I can look for if you don't find them yourself 2.add a trace log here so you can be sure this code is called for Genesis and doesn't get called for the IC adapter | 2 Bounceback are from QA Testing Offshore: Exception not handel properly on implementation Offshore: Missed a single scenario on implementation 1 Defect was due to Offshore: Missed scenario on implementation |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis and Knowledge Shared to the other team members | Mahesh/Aravindth/Prisla | Closed | 2025-01-09
10 | 2025-01-23 | 14.4 Sprint 3 (10-Jan to 23-Jan) | 2 Defects | Internal/External | Metric Deviation | 1 Bounceback and 1 External Defect | 1 Bounceback from the story worked Offshore: Missed scenario on implementation | 1 External Defect - Logical Issue Existing issue from the Production. Was existing for long time. |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis and Knowledge Shared to the other team members | Prisla | Closed | 2025-01-23
11 | 2025-02-06 | 14.5 Sprint 1 (24-Jan to 06-Feb) | CRC, Defects, One Story Carry Forwarded | Internal/External | Metric Deviation | 1 Story Carry Forwarded, 11 CRC, 3 Defects | 2 Bounceback from the story worked Offshore: Missed scenario on implementation 1 Defect which is Struts frame work migration All the Defects are Closed | 11 CRC Internal CRC - 4 External CRC - 7 All the CRC's are Logical Reasons and Suggestions Some are: 1.method needs in-line comments throughout 2.302, 401, 404, others are also valid... if status >=500 we should fail this, but also write the response into logger 3.match the get/set name | One committed story got carry forwarded with 5SP(Development completed and testing need to be done). |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward. | All Members | Closed | 2025-02-19
12 | 2025-02-20 | 14.5 Sprint 2 (07-Feb-2025 to 20-Feb-2025) | CRC, Defects | Internal/External | Metric Deviation | 4 Bouncebacks, 3 External Defects and 9 CRC | 4 Boucebacks due to Story Testing The Team missed Scenario during Implementation and Data Error | 3 External Defects from Prod due to mised configuration, missed existing issues, data error | 8 CRC regarding logical issues, suggestions and code cleanup |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward. | All Members | Closed | 2025-02-20
13 | 2025-03-06 | 14.5 Sprint 3 (21-Feb-2025 to 06-Mar-2025) | CRC, Defects | Internal/External | Metric Deviation | 1 Defect, 7 Internal CRC and 1 External CRC | 1 Defect was Tab issue, which was a minor existing issue. Offshore: Missed scenario on testing | 7 Internal CRC which were internal CRC comments from the Team regarding logical and naming suggestions | 1 External CRC related to update the changelog |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward. The mitigation plan have been arrived where the team will a sync after unit testing and they will have an Internal POV and Internal PR testing | All Members | Closed | 2025-03-06
14 | 2025-03-06 | 14.6 Sprint 1 (07-Mar-2025 to 20-Mar-2025) | CRC, Defects | Internal/External | Metric Deviation | 1 Defect, 10 Internal CRC and 1 External CRC | 1 External Defect which was a minor existing issue in Prod for Longtime, this was found by the team and they have provided the fix | 10 Internal Peer Review Comments which were internal PR comments from the Team regarding logical and naming suggestions, (this was before raising a PR) |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward. The mitigation plan have been arrived where the team will a sync after unit testing and they will have an Internal POV and Internal PR testing. | All Members | Closed | 2025-03-20 | Note: These are PR Tested Comments not CRC
15 | 2025-04-03 | 14.6 Sprint 2 (21-Mar-2025 to 03-Apr-2025) | CRC, Defects,Bouncebacks | Internal/External | Metric Deviation | 1 Defect, 6 Internal CRC, 3 External CRC and 1 Bounceback | 6 Internal CRC which was a minor found by our internal peer review and 3 External CRC which has been provided by onsite Developer | 1 Defect which was a minor found by our internal tester and 1 Bounce back has been found by our tester internally | 1 Entire Story with 13 SP has been carry forwarded as the AC was modified and it completely changed the functional logic. So needs to be worked from scratch |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward. The mitigation plan have been arrived where the team will a sync after unit testing and they will have an Internal POV and Internal PR testing. Also, Once the sprint has beeen started planned to have a grooming session with the team to understand the logical and functional workflow of the task to proceed further. | All Members | Open | 2025-04-17 | The story is carry forwarding from last 2 sprints with 13 SP
16 | 2025-04-17 | 14.6 Sprint 3 (04-Apr-2025 to 17-Apr-2025) | CRC, Defects,Bouncebacks | internal/External | Metric Deviation | 2 Defect, 10 Internal CRC, 4 External CRC and 1 Bounceback | 10 Internal CRC which was a minor found by our internal peer review and 4 External CRC which has been provided by onsite Developer | 2 Defect which was a minor found by our internal tester and 1 Bounce back has been found by our tester internally |  |  | Understand and implement AC , Follow coding standards properly | All Members | Closed | 2025-04-17
17 | 2025-05-03 | 14.7 Sprint 1 (18-Apr-2025 to 01-May-2025) | CRC | Internal/External | Metric Deviation | 3 Internal & 5 External CRC has been given | All the internal CRC has been related to the Comments which we have provided on the code and suggessions has been given to work on the scenarioes. | The External CRC is related to the Exception handling and the Naming conventions along with the scenario suggessions according to the null values and Exceptions |  |  | The No of CRC has been spoken with the team and ask them to prepare the Document related to the coding Standards to mitigate the No of CRC's | All Members | closed | 2025-05-01
18 | 2025-05-03 | 14.7 Sprint 1 (18-Apr-2025 to 01-May-2025) | Defects and Bounceback | Internal/External | Metric Deviation | 2 Defects and 1 Bounce Back has been provided | The 2 Defects has been found as the existing issue and we found it in the regression part | The one of the issue has been missed out while unit testing from the developer and we found it internally from the QA and considered as the bounce back. | We ask the team to do the 2 level of unit testing with all the positive and Negative scenarios before handling it over to QA |  | The Defects were fixed and bounce back is on testing and the Team closed the defects with Testing, Analysis. Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward. | All Members | Open | 2025-05-14
19 | 2025-05-16 | 14.7 Sprint 2 (02-May-2025 to 15-May-2025) | CRC | Internal/External | Metric Deviation | 8 Internal and 4 External CRC has beeen Given | All the 8 Internal CRC's has been from the Dev services and the Wave team. Which has been provided from the team to improve the coding standards and functionalities | The External CRC is related to the Suggessions to improving the coding standards and functional logic along with the scenario suggessions. |  |  | The No of CRC has been spoken with the team and ask them to prepare the Document related to the coding Standards to mitigate the No of CRC's | All Members | closed | 2025-05-16
20 | 2025-05-16 | 14.7 Sprint 2 (02-May-2025 to 15-May-2025) | Defects and Bounceback | Internal/External | Metric Deviation | 1 Defects and 3 Bounce Back has been provided | The 1 Defects has been found as the existing issue and we found it in the current sprint | The 3 of the bounceback issue has been missed out while unit testing from the developer and we found it internally from the QA and considered as the bounce back. | We ask the team to do the 2 level of unit testing with all the positive and Negative scenarios before handling it over to QA |  | The Defects were fixed and bounce back is on testing and the Team closed the defects with Testing, Analysis. Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward. | All Members | closed | 2025-05-16
21 | 2025-05-30 | 14.7 Sprint 3 (16-May-2025 to 29-May-2025) | CRC | Internal/External | Metric Deviation | 10 Internal CRC has been raised by the team. | The 10 Internal peer review comments has been addressed by the team during the regression testing | All the comments by the team is the basic coding standard over the test case scenario in the regression sprint. |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | closed | 2025-05-29
22 | 2025-05-30 | 14.7 Sprint 3 (16-May-2025 to 29-May-2025) | QA Defects | Internal/External | Metric Deviation | 1 QA defect and 1 Escaped Defect has been raised by the team | The QA Defect has been found by our internal QA related to the Functionality change | 1 Escaped Defect would be the Existing Issues identied in the current sprint and worked on that accordingly. |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. | All Members | closed | 2025-05-29
23 | 2025-06-12 | 15.0 Sprint 1 ( 30-May-2025 to 12-June-2025) | CRC | Internal/External | Metric Deviation | 9 Internal CRC and 5 External has been raised | All the 14 CRC's has been from the Dev services and the Wave team that has been provided from the team to improve the coding standards and functionalities also related to appropriate comments,naming conventions and suggestions. These are all addressed by the team | Cosmetic changes |  |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | All Members | closed | 2025-06-12
24 | 2025-06-12 | 15.0 Sprint 1 ( 30-May-2025 to 12-June-2025) | QA Defects | Internal/External | Metric Deviation | 7 QA defects has been raised by the team | The 2 Defects has been found as the existing issue snd team worked on it and closed the same. | The 5 of the bounceback issue has been missed out while unit testing from the developer and we found it internally from the QA and considered as the bounce back. |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. | All Members | closed | 2025-06-12
25 | 2025-06-12 | 15.0 Sprint 1 ( 30-May-2025 to 12-June-2025) | 1 story carried forward | Internal | Metric Deviation | 2 story points story has been carried forward | One 2 story point assigned story was carried forward due to a redirection based on configuration. Samuel (Dev) initially misunderstood the task despite discussions with leads. After PR submission, the reviewer suggested a change in approach. Prisla (Onsite Coordinator) intervened and resolved the issue with a new approach. The story is now in Peer Review. | Shifted to an alternative solution path |  |  | This story has been prioritized for the upcoming sprint and will be completed early as part of the mitigation plan | Samuel | Closed | 2025-06-26
26 | 2025-06-27 | 15.0 Sprint 2 ( 13-June-2025 to 26-June-2025) | CRC | Internal/External | Metric Deviation | We have recieved arount 23 internal CRC and 14 External CRC | All the internal CRC has been related to the Sujjessions and funtinality missing to avoid the defects and external / Cleient review. And, The External CRC has been given from the onsite lead related to the suggession and inprovements. | All the comments by the team is the basic coding standard over the test case scenario |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | Inprogress | 2025-07-10
27 | 2025-06-27 | 15.0 Sprint 2 ( 13-June-2025 to 26-June-2025) | QA Defects | Internal/External | Metric Deviation | We have found 1 QA Defects internally | The identified defect has been found only observed in the test environment, whereas other environments are functioning correctly. Therefore, an investigation is needed, and the fix should be applied to the test environment. | We are parellely working on this to make sure the error is environment issue or an Bug |  |  | This story has been prioritized for the upcoming sprint and will be completed early as part of the mitigation plan | All Members | Inprogress | 2025-07-10
28 | 2025-07-11 | 15.0 Sprint 3 ( 27-June-2025 to 10-Jul-2025) | CRC | Internal | Metric Deviation | We have received around 13 internal CRC | All the internal CRC has been related to the suggestions and AC updates to avoid the CRC will follow the coding standards. | All the comments by the team is the basic coding standard over the test case scenario |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | Closed | 2025-07-24
29 | 2025-07-11 | 15.0 Sprint 3 ( 27-June-2025 to 10-Jul-2025) | QA Defects | Internal | Metric Deviation | We have found 1 QA Defects internally | The identified defect has been found only observed in the test environment, whereas other environments are functioning correctly. Therefore, an investigation is needed, and the fix should be applied to the test environment. | We are parellely working on this to make sure the error is environment issue or an Bug |  |  | This story has been prioritized for the upcoming sprint and will be completed early as part of the mitigation plan | All Members | Closed | 2025-07-24
30 | 2025-07-25 | 15.1 Sprint 1 ( 11-June-2025 to 24-Jul-2025) | CRC | Internal/External | Metric Deviation | We have recieved around 4 internal CRC and 11 External CRC | All the internal CRC has been related to the Suggesstions and funtionality missing to avoid the defects and external / Client review. And, The External CRC has been given from the onsite lead related to the suggession and i3provements. | All the comments by the team is the basic coding standard over the test case scenario |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | Closed | 2025-08-06
31 | 2025-07-25 | 15.1 Sprint 1 ( 11-June-2025 to 24-Jul-2025) | QA Defects | internal/External | Metric Deviation | We have found 9 QA Defects internally | 3 defects found existing issue and team worked on it als closed. Rest identified defect has been found only observed in the test environment, whereas other environments are functioning correctly. | 2 Defect which was a minor found by our internal tester and 5 Bounce back has been found by our tester internally |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. | All Members | Closed | 2025-08-06
32 | 2025-08-08 | 15.1 Sprint 2 ( 25-June-2025 to 07-Aug-2025) | CRC | internal/External | Metric Deviation | We have recieved around 8 internal CRC and 4 External CRC | All the internal CRC has been related to the Suggesstions and funtionality missing to avoid the defects and external / Client review. And, The External CRC has been given from the onsite lead related to the suggession and improvements. | All the comments by the team is the basic coding standard over the test case scenario |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | Closed | 2025-08-20
33 |  | 15.1 Sprint 2 ( 25-June-2025 to 07-Aug-2025) | QA Defects | internal/External | Metric Deviation | We have found 8 QA Defects internally | 2 defects found existing issue and team worked on it als closed. Rest identified defect has been found only observed in the test environment, whereas other environments are functioning correctly. | 4 Defect which was a minor found by our internal tester and 4 Bounce back has been found by our tester internally |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. | All Members | Closed | 2025-08-20
34 |  | 15.1 Sprint 3 ( 08-Aug-2025 to 21-Aug-2025) | CRC | internal/External | Metric Deviation | We have recieved around 11 internal CRC and 1 External CRC | All the internal CRC has been related to the Suggesstions and funtionality missing to avoid the defects and external / Client review. And, The External CRC has been given from the onsite lead related to the suggession and improvements. | All the comments by the team is the basic coding standard over the test case scenario |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | Closed | 2025-11-21
35 |  | 15.1 Sprint 3 ( 08-Aug-2025 to 21-Aug-2025) | QA Defects | internal/External | Metric Deviation | We have found 4 QA Defects internally | 1 defects found existing issue and team worked on it als closed. Rest identified defect has been found only observed in the test environment, whereas other environments are functioning correctly. | 1 Defect which was a minor found by our internal tester and 3 Bounce back has been found by our tester internally |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. | All Members | Closed | 2025-11-21
36 |  | 15.2 DS Sprint 1 (22-Aug-2025 to 04-Sep-2025) | CRC | internal/External | Metric Deviation | We have recieved arount 7 internal CRC and 1 External CRC | All the internal CRC has been related to the Suggesstions and funtionality missing to avoid the defects and external / Client review. And, The External CRC has been given from the onsite lead related to the suggession and improvements. | All the comments by the team is the basic coding standard over the test case scenario |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | Closed | 2025-09-02
37 |  | 15.2 DS Sprint 1 (22-Aug-2025 to 04-Sep-2025) | QA Defects | Internal | Metric Deviation | We have found 3 QA Defects internally | 2 defects found existing issue and team worked on it als closed. | 2 Defect which was a minor found by our internal tester and 3 Bounce back has been found by our tester internally |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. | All Members | Closed | 2025-09-02
38 |  | 15.2 DS Sprint 2 (05-Sep-2025 to 18-Sep-2025) | CRC | Internal/External | Metric Deviation | We have recieved around 5 internal CRC and 1 External CRC | All the internal CRC has been related to the Suggesstions and funtionality missing to avoid the defects and external / Client review. And, The External CRC has been given from the onsite lead related to the suggession and improvements. | All the comments by the team is the basic coding standard over the test case scenario |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | Closed | 2025-09-17
39 |  | 15.2 DS Sprint 2 (05-Sep-2025 to 18-Sep-2025) | QA Defects | Internal/External | Metric Deviation | We have found 3 QA Defects internally | 2 defects found existing issue and team worked on it als closed. Rest identified defect has been found only observed in the test environment, whereas other environments are functioning correctly. | 2 Defect which was a minor found by our internal tester and 1 Bounce back has been found by our tester internally |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. | All Members | Closed | 2025-09-17
40 |  | 15.2 DS Sprint 2 (05-Sep-2025 to 18-Sep-2025) | 2 Story Carry forward | Internal | Commitment Index Deviation | 2 Stories got carried | Team facing struggle when implementing new concept. Took much time to understand the AC and imlementation. |  |  |  | Meeting conducted and explained the Criteria. To mitigate this moving forward to conduct meeting in the early day of the sprint and discuss the stories | All Members | Closed | 2025-09-17
41 |  | 15.2 DS Sprint 3 (19-Sep-2025 to 02-Oct-2025) | CRC | Internal/External | Metric Deviation | We have recieved around 1 internal CRC and 1 External CRC | All the internal CRC has been related to the Suggesstions and funtionality missing to avoid the defects and external / Client review. And, The External CRC has been given from the onsite lead related to the suggession and improvements. | All the comments by the team is the basic coding standard over the test case scenario |  |  | Conducted a sync up call with the team to explain the importance of CRC and how to mitigate these moving forward by providing the coding standard document to follow the basic level of coding standards. | All Members | Closed | 2025-10-01
42 |  | 15.2 DS Sprint 3 (19-Sep-2025 to 02-Oct-2025) | QA Defects | Internal/External | Metric Deviation |  | 2 defects found existing issue and team worked on it als closed. | 1 Defect which was a minor found by our internal tester and 1 Bounce back has been found by our tester internally |  |  | The Defects were fixed and the Team closed the defects with Testing, Analysis. | All Members | Closed | 2025-10-01
43 | 2025-02-05 | 26.3 DS Sprint 2 (23-Jan-2025 to 05-Feb-2026) | 2 Stories carry forwarded | Internal/External | Metric Deviation | 2 Stories got carried | Assigned developer Suresh has taken several unplanned leaves and permissions, and he has not yet worked on this task. Prisla and Mahesh have started and completed the development, and it is now in testing. | Development has been completed, and developer testing is in progress. Due to the large number of scenarios to cover, each scenario needs to be executed sequentially, which takes additional time depending on the adapter. Since testing involves nine adapters, this is the reason it has not been completed on schedule. |  |  | We will plan to pull the stories and inform the client in advance for time‑consuming stories, requesting them to be split into two parts. Team members will also be instructed to avoid taking unplanned leaves and permissions. | All Members | Closed
44 | 2025-02-05 | 26.3 DS Sprint 2 (23-Jan-2025 to 05-Feb-2026) | CRC | Internal/External | Metric Deviation | 9 internal CRC and 4 External CRC | Most of the feedback we received was related to loggers, documentation comments, and naming conventions |  |  |  | In this sprint, we introduced code reviews using Copilot. Most of the feedback we received was related to loggers, documentation comments, and naming conventions. We have started following these standards, and we also conduct internal reviews with Copilot before raising a pull request. This approach helps reduce the number of comments during PR reviews. | All Members | Closed
45 | 2025-02-19 | 26.3 DS Sprint 3 (06-Feb-2025 to 19-Feb-2026) | 1 Story carry forwarded | Internal/External | Metric Deviation | Commitment Index Deviation | One committed story was carried forward with 5SP to the next sprint due to the story has been moved to the next release (26.4). |  |  |  | Will ensure the planning it in first place in coming sprints accordingly. | Aravindh | Closed
46 | 2025-03-05 | 26.4 DS Sprint 1 (20-Feb-2026 to 05-Mar-2026) | QA Defects | Internal/External | Others | We have found 5 QA Defects(Bouncebacks) internally 1 closed | "The issue occurs only in the test environment. To analyze it, we requested server logs, but no one—including the client’s development manager—has access to them. Only high-level access is available. Since the client also requested the logs, there has been a delay in obtaining them from the test environment. Therefore, all Bouncebacks were consolidated, a defect (26912) was created, and this story was closed. " |  |  |  | 1 Defect closed all other are consolidated as one defect agreed by client. | All Members | Closed
47 | 2025-03-05 | 26.4 DS Sprint 1 (20-Feb-2026 to 05-Mar-2026) | CRC | Internal/External | Others | 5 External CRC | The client reassigned the task to Prisla, but most comments weren’t related to the current story changes—they were about existing code that needed fixes. |  |  |  | Conducted a sync up call with the team and how to mitigate these moving forward by providing the coding standard document. | All Members | Closed
48 | 2025-04-30 | 26.5 DS Sprint 2 (17-Apr-2026 to 30-Apr-2026) | CRC | Internal | Others | 5 Internal CRC | One of the stories received more peer review comments because it was missing some standard code practices such as documentation comments, logging, and avoiding duplicate code. Although these items are included in our checklist, they were missed in this story. |  |  |  | Going forward, we will ensure that the code standards are followed based on the checklist. | Aravindh
49 | 2025-04-30 | 26.5 DS Sprint 2 (17-Apr-2026 to 30-Apr-2026) | 2 Stories carry forwarded | Internal/External | Metric Deviation | 2 Stories got carried | The story requested an investigation into performance issues. After analysis, no tuning opportunities were found, and no delays were observed in local, test, or staging environments. The issue occurs only in the production environment, so additional logs were added to the full cart creation process for further analysis. | The implementation was completed based on the acceptance criteria (AC), and a proof of value (POV) was presented to the client. During the POV, the client requested a few additional changes, after which the AC was updated accordingly. The developer submitted the code for peer review more than three times, and the peer reviewer identified several issues. Some testing scenarios were missed during testing and the internal POV. During the peer review process, the peer reviewer identified and consolidated the issues and communicated them to the team. After code implementation Alex requested to change some requestBody [Differ from Story AC] and we worked on it. The story has been carried forward because of bouncebacks |  |  | Production‑specific logging has been added to the full cart creation flow to capture detailed insights. Logs will be monitored and analyzed to identify the root cause, and corrective actions will be planned based on findings without impacting lower environments. Ensure ACs are finalized and signed off before POV. Incorporate a comprehensive test scenario checklist for internal testing and POV. Address peer review feedback in a consolidated manner before resubmission, and route post‑implementation changes through a formal change request process to minimize rework and bouncebacks. | All Members

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Config
Sprint | 26.01 DS Sprint 3 (12-Dec-2025 to 08-Jan-2026) |  | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | #N/A | #N/A | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | #N/A | #N/A | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 100% | 20% |  |  | CF |  | Excellent |  | 25
Code Quality Index | #N/A | #N/A | Velocity
Unit Testing & Code Coverage | #N/A | #N/A | Goal | 20
Backlog Health | #N/A | #N/A
0 |  |  | Code Coverage
|  |  | Goal | 90%
|  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  | Below Avg | 15 | Labels | Values |  | Story Points | #N/A
|  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  | Excellent | 30 | 15 | 10
|  |  | Total | 90 | 20 | 10
[5 empty] | 25 | 10
50

## Instructions (hidden)
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## ExportData
EE | 13.7 Sprint 1 (22-Mar-2024 to 04-Apr-2024) | 13.7 Sprint 1 | 2024-03-22 | 2024-04-04 | April | 25 | 10 | 0.4 | 28 | 0.9 | 2 | 2 | 4 | 0 | #N/A | #N/A | 1 | 0.6 | 0.6
EE | 13.7 Sprint 2 (05-Apr-2024 to 18-Apr-2024) | 13.7 Sprint 2 | 2024-04-05 | 2024-04-18 | April | 26 | 21 | 0.80769 | 25 | 0.91 | 2 | 1 | 3 | 0 | 0.87626 | 0.80769 | 1 | 0.85714 | 0.85714
EE | 13.7 Sprint 3 (19-Apr-2024 to 2-May-2024) | 13.7 Sprint 3 | 2024-04-19 | 2024-05-02 | May | 43 | 29 | 0.67442 | 27 | 0.95 | 0 | 0 | 1 | 0 | 0.90671 | 0.67442 | 1 | 0.96552 | 1
EE | 13.8 Sprint 1 (3-May-2024 to 16-May-2024) | 13.8 Sprint 1 | 2024-05-03 | 2024-05-16 | May | 18 | 23 | 1 | 20.75 | 1 | 0 | 0 | 2 | 0 | 0.98261 | 1 | 1 | 0.91304 | 1
EE | 13.8 Sprint 2 (17-May-2024 to 30-May-2024) | 13.8 Sprint 2 | 2024-05-17 | 2024-05-30 | May | 31 | 23 | 0.74194 | 24 | 1 | 0 | 2 | 1 | 0 | 0.89708 | 0.74194 | 1 | 0.95652 | 0.91304
EE | 13.8 Sprint 3 (May-31-2024 to Jun-13-2024) | 13.8 Sprint 3 | 2024-05-31 | 2024-06-13 | June | 36 | 36 | 1 | 27.75 | 1 | 0 | 1 | 2 | 0 | 0.98472 | 1 | 1 | 0.94444 | 0.97222
EE | 14.0 Sprint 1 (Jun-14-2024 to Jun-27-2024) | 14.0 Sprint 1 | 2024-06-14 | 2024-06-27 | June | 29 | 32 | 1 | 28.5 | 1 | 1 | 0 | 2 | 0 | 0.98281 | 1 | 1 | 0.9375 | 0.96875
EE | 14.0 Sprint 2 (Jun-28-2024 to Jul-11-2024) | 14.0 Sprint 2 | 2024-06-28 | 2024-07-11 | July | 27 | 32 | 1 | 30.75 | 1 | 1 | 0 | 3 | 0 | 0.97656 | 1 | 1 | 0.90625 | 0.96875
EE | 14.0 Sprint 3 (Jul-12-2024 to Jul-25-2024) | 14.0 Sprint 3 | 2024-07-12 | 2024-07-25 | July | 40 | 56 | 1 | 39 | 1 | 1 | 0 | 1 | 0 | 0.99375 | 1 | 1 | 0.98214 | 0.98214
EE | 14.1 Sprint 1 (Jul-26-2024 to Aug-8-2024) | 14.1 Sprint 1 | 2024-07-26 | 2024-08-08 | August | 36 | 36 | 1 | 39 | 1 | 1 | 1 | 0 | 2 | 0.98056 | 1 | 1 | 0.94444 | 0.94444
EE | 14.1 Sprint 2 (Aug-9-2024 to Aug-22-2024) | 14.1 Sprint 2 | 2024-08-09 | 2024-08-22 | August | 36 | 49 | 1 | 43.25 | 1 | 0 | 0 | 2 | 1 | 0.98776 | 1 | 1 | 0.93878 | 1
EE | 14.1 Sprint 3 ( Aug-23-2024 to Sep-5-2024) | 14.1 Sprint 3 | 2024-08-23 | 2024-09-05 | September | 36 | 23 | 0.63889 | 41 | 1 | 0 | 0 | 0 | 2 | 0.89233 | 0.63889 | 1 | 0.91304 | 1
EE | 14.2 Sprint 1 (Sep-6-2024 to Sep-19-2024) | 14.2 Sprint 1 | 2024-09-06 | 2024-09-19 | September | 28 | 27 | 0.96429 | 33.75 | 1 | 0 | 2 | 2 | 1 | 0.95774 | 0.96429 | 1 | 0.88889 | 0.92593
EE | 14.2 Sprint 2 (20-Sep-2024 to 03-Oct-2024) | 14.2 Sprint 2 | 2024-09-20 | 2024-10-03 | October | 33 | 22 | 0.66667 | 30.25 | 1 | 2 | 5 | 6 | 0 | 0.81439 | 0.66667 | 1 | 0.72727 | 0.68182
EE | 14.2 Sprint 3 (Oct-4-2024 to Oct-17-2024) | 14.2 Sprint 3 | 2024-10-04 | 2024-10-17 | October | 36 | 41 | 1 | 28.25 | 1 | 0 | 1 | 4 | 0 | 0.97683 | 1 | 1 | 0.90244 | 0.97561
EE | 14.3 Sprint 1 (Oct-18-2024 to Oct-31-2024) | 14.3 Sprint 1 | 2024-10-18 | 2024-10-31 | October | 23 | 44 | 1 | 33.5 | 1 | 0 | 3 | 3 | 7 | 0.94432 | 1 | 1 | 0.77273 | 0.93182
EE | 14.3 Sprint 2 (1-Nov-2024 to 14-Nov-2024) | 14.3 Sprint 2 | 2024-11-01 | 2024-11-14 | November | 23 | 18 | 0.78261 | 31.25 | 0.95 | 0 | 0 | 2 | 1 | 0.90732 | 0.78261 | 1 | 0.83333 | 1
EE | 14.3 Sprint 3 (15-Nov-2024 to 28-Nov-2024) | 14.3 Sprint 3 | 2024-11-15 | 2024-11-28 | November | 37 | 39 | 1 | 35.5 | 1 | 0 | 0 | 1 | 2 | 0.98462 | 1 | 1 | 0.92308 | 1
EE | 14.4 Sprint 1 (29-Nov-2024 to 12-Dec-2024) | 14.4 Sprint 1 | 2024-11-29 | 2024-12-12 | December | 21 | 27 | 1 | 32 | 1 | 0 | 0 | 1 | 4 | 0.96296 | 1 | 1 | 0.81481 | 1
EE | 14.4 Sprint 2 (13-Dec-2024 to 09-Jan-2025) | 14.4 Sprint 2 | 2024-12-13 | 2025-01-09 | January | 38 | 41 | 1 | 31.25 | 1 | 0 | 2 | 3 | 0 | 0.97805 | 1 | 1 | 0.92683 | 0.95122
EE | 14.4 Sprint 3 (10-Jan-2025 to 23-Jan-2025) | 14.4 Sprint 3 | 2025-01-10 | 2025-01-23 | January | 45 | 45 | 1 | 38 | 1 | 0 | 0 | 1 | 1 | 0.99111 | 1 | 1 | 0.95556 | 1
EE | 14.5 Sprint 1 (24-Jan-2025 to 06-Feb-2025) | 14.5 Sprint 1 | 2025-01-24 | 2025-02-06 | February | 37 | 34 | 0.91892 | 37 | 1 | 2 | 7 | 4 | 1 | 0.91061 | 0.91892 | 1 | 0.85294 | 0.73529
EE | 14.5 Sprint 2 (07-Feb-2025 to 20-Feb-2025) | 14.5 Sprint 2 | 2025-02-07 | 2025-02-20 | February | 29 | 48 | 1 | 42 | 1 | 8 | 1 | 4 | 3 | 0.94271 | 1 | 1 | 0.85417 | 0.8125
EE | 14.5 Sprint 3 (21-Feb-2025 to 06-Mar-2025) | 14.5 Sprint 3 | 2025-02-21 | 2025-03-06 | March | 44 | 50 | 1 | 44.25 | 1 | 7 | 0 | 1 | 0 | 0.975 | 1 | 1 | 0.98 | 0.86

## Archive
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
13.7 Sprint 1 (22-Mar-2024 to 04-Apr-2024) | 25 | 10 | 40% | 28 | 90% | 2 | 2 | 4 | 0 | 30 | No |  |  | 2 stories got carried. Development completed and testing inprogress. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.7 Sprint 2 (05-Apr-2024 to 18-Apr-2024) | 26 | 21 | 80.77% | 25 | 91% | 2 | 1 | 3 | 0 | 25 | No |  |  | Stretch Stories completed with 7sp,5sp story is on hold (Development completed and not able to test because Destiny(Vendor) side getting error for refund payments) |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.7 Sprint 3 (19-Apr-2024 to 2-May-2024) | 43 | 29 | 67.44% | 27 | 95% | 0 | 0 | 1 | 0 | 30 | No |  |  | Regression story get carried forwarded due to code build not yet deployed on staging & staging CA. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 1 (3-May-2024 to 16-May-2024) | 18 | 23 | 100% | 20.75 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 2 (17-May-2024 to 30-May-2024) | 31 | 23 | 74.19% | 24 | 100% | 0 | 2 | 1 | 0 | 25 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
13.8 Sprint 3 (May-31-2024 to Jun-13-2024) | 36 | 36 | 100% | 27.75 | 100% | 0 | 1 | 2 | 0 | 30 | No |  |  | Regression Sprint |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.0 Sprint 1 (Jun-14-2024 to Jun-27-2024) | 29 | 32 | 100% | 28.5 | 100% | 1 | 0 | 2 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.0 Sprint 2 (Jun-28-2024 to Jul-11-2024) | 27 | 32 | 100% | 30.75 | 100% | 1 | 0 | 3 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.0 Sprint 3 (Jul-12-2024 to Jul-25-2024) | 40 | 56 | 100% | 39 | 100% | 1 | 0 | 1 | 0 | 30 | Yes |  |  | Regression Sprint |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 1 (Jul-26-2024 to Aug-8-2024) | 36 | 36 | 100% | 39 | 100% | 1 | 1 | 0 | 2 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 2 (Aug-9-2024 to Aug-22-2024) | 36 | 49 | 100% | 43.25 | 100% | 0 | 0 | 2 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 3 ( Aug-23-2024 to Sep-5-2024) | 36 | 23 | 63.89% | 41 | 100% | 0 | 0 | 0 | 2 | 30 | Yes |  |  | Regression Sprint |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 1 (Sep-6-2024 to Sep-19-2024) | 28 | 27 | 96.43% | 33.75 | 100% | 0 | 2 | 2 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 2 (20-Sep-2024 to 03-Oct-2024) | 33 | 22 | 66.67% | 30.25 | 100% | 2 | 5 | 6 | 0 | 30 | No |  |  | Three committed story got carry forwarded with 16SP(1 story is on review with 5sp and 2 stories are on testing with 11sp) - Due to Hotfix |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 3 (Oct-4-2024 to Oct-17-2024) | 36 | 41 | 100% | 28.25 | 100% | 0 | 1 | 4 | 0 | 30 | Yes |  |  | Regression Sprint |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 1 (Oct-18-2024 to Oct-31-2024) | 23 | 44 | 100% | 33.5 | 100% | 0 | 3 | 3 | 7 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 2 (1-Nov-2024 to 14-Nov-2024) | 23 | 18 | 78.26% | 31.25 | 95% | 0 | 0 | 2 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 3 (15-Nov-2024 to 28-Nov-2024) | 37 | 39 | 100% | 35.5 | 100% | 0 | 0 | 1 | 2 | 30 | Yes |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 Sprint 1 (29-Nov-2024 to 12-Dec-2024) | 21 | 27 | 100% | 32 | 100% | 0 | 0 | 1 | 4 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 Sprint 2 (13-Dec-2024 to 09-Jan-2025) | 38 | 41 | 100% | 31.25 | 100% | 0 | 2 | 3 | 0 | 30 | No |  |  | 4 Weeks Sprint |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 Sprint 3 (10-Jan-2025 to 23-Jan-2025) | 45 | 45 | 100% | 38 | 100% | 0 | 0 | 1 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 Sprint 1 (24-Jan-2025 to 06-Feb-2025) | 37 | 34 | 91.89% | 37 | 100% | 2 | 7 | 4 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 Sprint 2 (07-Feb-2025 to 20-Feb-2025) | 29 | 48 | 100% | 42 | 100% | 8 | 1 | 4 | 3 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 Sprint 3 (21-Feb-2025 to 06-Mar-2025) | 44 | 50 | 100% | 44.25 | 100% | 7 | 0 | 1 | 0 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.6 Sprint 1 (07-Mar-2025 to 20-Mar-2025) | 31 | 47 | 100% | 44.75 | 100% | 10 | 1 | 0 | 1 | 30 | No |  |  |  |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.6 Sprint 2 (21-Mar-2025 to 03-Apr-2025) | 47 | 41 | 87.23% | 46.5 | 100% | 6 | 3 | 1 | 1 | 30 | No |  |  | 1 Story has been carry forwarded because of the AC change. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.6 Sprint 3 (04-Apr-2025 to 17-Apr-2025) | 81 | 78 | 96.3% | 54 | 95% | 10 | 4 | 1 | 2 | 30 | No |  |  | 1. Regarding CRC: The review comments were because of developer missed something during development. Follow the coding and Standard and Naming conversions properly 2. Defect: This defect are related to API. All the defects got closed |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.7 Sprint 1 (18-Apr-2025 to 01-May-2025) | 43 | 46 | 100% | 53 | 100% | 3 | 5 | 2 | 1 | 30 | No |  |  | 1. CRC : 3 Internal and 5 External CRC was given. All the 3 Internal CRC was related to the Appropriate Comments and Suggessions. 5 External CRC is related to the Exception Handling and the Naming conventions. 2. Defect: 2 Defects and 1 Bounce back. All the 2 defects are Existing one and 1 scenario has been missed out while testing and found as a bounce back.
14.7 Sprint 2 (02-May-2025 to 15-May-2025) | 35 | 47 | 100% | 53 | 100% | 8 | 4 | 3 | 1 | 30 | No |  |  | 1. CRC : 8 Internal and 4 External CRC was given. All the 8 Internal CRC was related to the removing of unwanted lines and Suggessions. 4 External CRC is related to the Suggessions and the functional change of the code 2. Defect: 1 Defects and 3 Bounce back. All the 1 defects are Existing one which has been identified ny the internal team in the current sprint and 3 bounce back from the internal has been a scenario that has been missed out while development testing and found as a bounce back.
14.7 Sprint 3 (16-May-2025 to 29-May-2025) | 65 | 63 | 96.92% | 58.5 | 100% | 10 | 0 | 1 | 2 | 30 | No |  |  | All the committed stories has been completed with 1 rejected story as the reason as "started analyzing the story, but we were unable to automate it. We informed the clients and they rejected it."
15.0 Sprint 1 ( 30-May-2025 to 12-June-2025) | 39 | 49 | 100% | 51.25 | 100% | 9 | 5 | 5 | 0 | 30 | No |  |  | Completed more than the planned work. One 2 story point assigned story was carried forward due to a redirection based on configuration. Samuel (Dev) initially misunderstood the task despite discussions with leads. After PR submission, the reviewer suggested a change in approach. Prisla (Onsite Coordinator) intervened and resolved the issue with a new approach. The story is now in Peer Review. To compensate, stretch stories were taken up and completed successfully. Raised 9 Internal and 5 External CRCs related to appropriate comments,naming conventions and suggestions. 7 QA defects were identified and resolved by the team within the timeline.
15.0 Sprint 2 ( 13-June-2025 to 26-June-2025) | 29 | 47 | 100% | 51.5 | 100% | 23 | 14 | 1 | 0 | 30 | No |  |  | We delivered around twice the amount of story pointers and we have completed most of the stretch stories. We tried to find most of the review commets internally and worked on the sme to avoid the external and client review comments.
15.0 Sprint 3 ( 27-June-2025 to 10-Jul-2025) | 32 | 38 | 100% | 49.25 | 100% | 13 | 0 | 1 | 0 | 30 | No |  |  | Team completed all the assigned stories
15.1 DS Sprint 1 (11-Jul-2025 to 24-Jul-2025) | 39 | 34 | 87.18% | 53.75 | 95% | 4 | 11 | 6 | 3 | 30 | No |  |  | 1. Offshore developer was not available. So unable to achieve the sprint Goal. 2. Team encountered challenges implementing Google reCAPTCHA, specifically with the modal file.
15.1 DS Sprint 2 (25-Jul-2025 to 07-Aug-2025) | 35 | 48 | 100% | 41.75 | 100% | 8 | 4 | 3 | 5 | 30 | No |  |  | Team completed all the assigned stories
15.1 DS Sprint 3 (08-Aug-2025 to 21-Aug-2025) | 71 | 79 | 100% | 49.75 | 94% | 11 | 1 | 1 | 3 | 30 | No |  |  | Team completed all the assigned stories and also completed the stretch stories
15.2 DS Sprint 1 (22-Aug-2025 to 04-Sep-2025) | 29 | 35 | 100% | 49 | 100% | 7 | 1 | 3 | 0 | 30 | No |  |  | Team completed all the assigned stories
15.2 DS Sprint 2 (05-Sep-2025 to 18-Sep-2025) | 34 | 31 | 91.18% | 48.25 | 95% | 5 | 1 | 3 | 2 | 30 | No |  |  | 2 Stories got carried over because of the Table ID mismatch issue and the api data.
15.2 DS Sprint 3 (19-Sep-2025 to 02-Oct-2025) | 64 | 66 | 100% | 52.75 | 100% | 1 | 1 | 1 | 1 | 30 | No |  |  | Team completed all the assigned stories
15.3 DS Sprint 1 (03-Oct-2025 to 16-Oct-2025) | 42 | 35 | 83.33% | 41.75 | 85% | 7 | 2 | 10 | 3 | 30 | no |  |  | 1. Due to Offshore developer unavailability the story assigned to another developer. 2. Onside QA Carmin unavailability the ticket carried to next sprint
15.03 DS Sprint 2 (17-Oct-2025 to 30-Oct-2025) | 53 | 33 | 62.26% | 41.25 | 75% | 5 | 1 | 1 | 4 | 30 | Yes |  |  | 1. Development completed. Due to testing time constraint the ticket got carried 2. Next ticket got carried because of the environment issue
15.03 DS Sprint 3 (31-Oct-2025 to 13-Nov-2025) | 53 | 60 | 100% | 48.5 | 90% | 0 | 0 | 0 | 0 | 30 | yes |  |  | Automation completed
26.01 DS Sprint 1 (14-Nov-2025 to 1-Dec-2025) | 38 | 53 | 100% | 45.25 | 90% | 1 | 0 | 1 | 0 | 30 | yes
26.01 DS Sprint 2 (2-Dec-2025 to 11-Dec-2025) | 39 | 55 | 100% | 50.25 | 90% | 2 | 0 | 2 | 0 | 30 | yes