## Dashboard
BOH

## Scorecard
Project Name | MSB Kaleida Wave
Engagement Model | Relevantz Co Owned
Overall Score | 89.19%
Current Sprint | 15.0 Sprint 2 (25-Jun-2025 to 8-Jul-2025)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% |  | 25% | 100%
Velocity | 100% | 20% |  | 20% | 95%
Defect-free Rate | 65% | 13% |  | 20% | 100%
Code Quality Index | 81.25% | 12.19% |  | 15% | 100%
Unit Testing | 90% | 9% |  | 10% | 90%
Backlog Health | 100% | 10% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
15.0 Sprint 1 (11-Jun-2025 to 24-Jun-2025) | 11 | 11 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | None
15.0 Sprint 2 (25-Jun-2025 to 8-Jul-2025) | 16 | 16 | 100% | 20 | 90% | 2 | 1 | 7 | 0 | 30 | No |  |  | None
15.0 Sprint 3 (9-Jul-2025 to 22-Jul-2025) | 24 | 24 | 100% |  | 90% | 4 | 1 | 1 | 0 | 30 | No |  |  | None
15.1 Sprint 1 (23-Jul-2025 to 4-Aug-2025) | 39 | 39 | 100% |  | 90% | 2 | 0 | 3 | 0 | 30 | No |  |  | None
15.1 Sprint 2 (5-Aug-2025 to 18-Aug-2025) | 39 | 39 | 100% | 20 | 90% | 4 | 1 | 2 | 0 | 30 | No |  |  | None
15.1 Sprint 3 (19-Aug-2025 to 2-Sep-2025) | 31 | 30 | 96.77% | 20 | 90% | 0 | 0 | 1 | 0 | 30 | No |  |  | None
15.2 Sprint 1 (2-Sep-2025 to 16-Sep-2025) | 16 | 16 | 100% | 20 | 90% | 3 | 2 | 1 | 0 | 30 | No |  |  | None
15.2 Sprint 2 (17-Sep-2025 to 29-Sep-2025) | 18 | 18 | 100% | 20 | 90% | 1 | 1 | 0 | 0 | 30 | No |  |  | None
15.3 Sprint 1 (30-Sep-2025 to 14-Oct-2025) | 10 | 10 | 100% | 20 | 90% | 0 | 2 | 0 | 0 | 30 | No |  |  | None |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
15.3 Sprint 2 (15-Sep-2025 to 28-Oct-2025) | 21 | 5 | 23.81% | 20 | 90% | 0 | 1 | 0 | 0 | 30 | No |  |  | 3 stories carrried forward due to this below reason 50420 - (Tharanya) - PR raised before the sprint end and then review is still pending from internal. Since there are more changes while converting boostrap3 to bootstrap5. 50422 - (Poornima) - The POC migration from Bootstrap 3 to 5 requires a complete code overhaul, with additional effort to refactor unsupported pie chart and pagination components. 50421 - (Preeti) - Development is inprogress and yet to raise PR. Since we are new converting boostrap3 to bootstrap5 there is lot of challenges technically. Need a complete code changes and after done there lot of functionality is breaking and debugging takes a lot of time. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
15.3 Sprint 3 (28-Oct-2025 to 11-Nov-2025) | 27 | 13 | 48.15% | 20 | 90% | 0 | 1 | 0 | 0 | 30 | No |  |  | This sprint is regression sprint and dev team were work in automation testing and the rest of the stories are under peer review and its carry forward to next sprint
26.01 Sprint 1 (12-Nov-2025 to 25-Nov-2025) | 20 | 17 | 85% | 20 | 90% | 0 | 1 | 0 | 0 | 30 | No |  |  | The Orders page (Add/Edit/View) has been completed as part of the current sprint. Since the Orders module contains multiple web forms with varied input fields and several redirections across pages, the Bootstrap 5 conversion requires additional effort. Client propose carrying forward the remaining BS5 migration tasks into the next sprint to ensure consistency and quality across all order-related functionalities.
26.01 Sprint 2 (26-Nov-2025 to 9-Dec-2025) | 29 | 28 | 96.55% | 20 | 90% | 0 | 1 | 0 | 0 | 30 | No |  |  | Reason for carry forward stories are due to environment issues in Test environment and peer review pending with the client
26.01 Sprint 3 (10-Dec-2025 to 6-Jan-2026) | 78 | 54.5 | 69.87% | 20 | 90% | 0 | 1 | 0 | 0 | 30 | No |  |  | None
26.03 Sprint 1 (7-Jan-2026 to 20-Jan-2026) | 47 | 30 | 63.83% | 20 | 90% | 0 | 2 | 0 | 0 | 30 | No |  |  | None
26.03 Sprint 2 (21-Jan-2026 to 3-Feb-2026) | 30 | 33 | 100% | 20 | 90% | 0 | 1 | 0 | 0 | 30 | No |  |  | In this sprint we have only one stretch #51645 and SP is 5, as part of development completed 3SP.
26.03 Sprint 3 (4-Feb-2026 to 17-Feb-2026) | 29 | 30.5 | 100% | 20 | 90% | 0 | 2 | 1 | 0 | 30 | No | 1 | 1 | 3 defects are already existing issues that were assigned as tasks
26.04 Sprint 1 (18-Feb-2026 to 3-Mar-2026) | 30.5 | 32.5 | 100% | 20 | 90% | 0 | 1 | 1 | 0 | 30 | No | 1 | 1 | 1 defect - already existing issue that was assigned as task
26.04 Sprint 2 (4-Mar-2026 to 17-Mar-2026) | 30 | 40.5 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No | 1 | 2
26.04 Sprint 3 (18-Mar-2026 to 31-Mar-2026) | 24 | 33 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No | 4 | 5 | Automation and regression testing sprint
26.05 Sprint 1 (01-Apr-2026 to 14-Apr-2026) | 18 | 31 | 100% | 20 | 90% | 0 | 0 | 0 | 1 | 30 | No | 1 | 2
26.05 Sprint 2 (15-Apr-2026 to 28-Apr-2026) | 18.5 | 38 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No | 1 | 1
26.05 Sprint 3 (29-Apr-2026 to 12-May-2026) | 29 | 34 | 100% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | Yes | 2 | 3

## RCA
3 Why Analysis
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2025-10-14 | 15.3 Sprint 1 (09-Sep-2025 to 14-Oct-2025) | 1 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | Comments: For a number of reasons, we should use Event Listeners like this [https://dev.azure.com/heartlandschools/MySchoolBucks/_git/SchoolBucks/pullrequest/44998] | Nice To Have from Client |  | This is not an issue. Client need to use advanced Jquery function, so client suggested this listerner function to maintain consistency. | Tharanya | Closed | 2025-10-14 |  | Metric Deviation
2 | 2025-10-14 | 15.3 Sprint 1 (09-Sep-2025 to 14-Oct-2025) | 1 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | Comments: This file is needed at all if we use <jsp:include page="/ver2/shared/vega/errors.jsp"/> as suggested in the JSP file. We should not have any message areas to close. [https://dev.azure.com/heartlandschools/MySchoolBucks/_git/SchoolBucks/pullrequest/44986] | Cosmetic Issue |  | This was already taken care by another script which we weren't aware. As we get more familier with project these can easily be avoided | Preeti | Closed | 2025-10-14 |  | Metric Deviation
3 | 2025-10-28 | 15.3 Sprint 2 (14-Oct-2025 to 28-Oct-2025) | 3 Story carrry forward | Internal | Metric Deviation | Commitment Index Deviation | 50420 - (Tharanya) - PR raised before the sprint end and then review is still pending from internal. Since we are new to converting boostrap3 to bootstrap5 there is lot of challenges technically. 50422 - (Poornima) - PR raised before the sprint end and then review is still pending from internal. Since we are new to converting boostrap3 to bootstrap5 there is lot of challenges technically. 50421 - (Preeti) - Development is inprogress and yet to raise PR. Since we are new converting boostrap3 to bootstrap5 there is lot of challenges technically. Need a complete code changes and after done there lot of functionality is breaking and debugging takes a lot of time. |  |  | It takes some time to understand the conversion of bootstrap3 to bootstrap5. Also need a access for copilot to get it done soon. | Tharanya Preeti Poornima | Closed | 2025-10-28 |  | Metric Deviation
4 | 2025-10-28 | 15.3 Sprint 2 (14-Oct-2025 to 28-Oct-2025) | 1 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | We reference `selectRole` in script `editrole.js` but it was missed. | UI Issue |  | Need to do more testing before the deliverable to avoid such a minor cosmetic issue | Mohan | Closed | 2025-10-28 |  | Metric Deviation
5 | 2025-11-11 | 15.3 Sprint 3 (28-Oct-2025 to 11-Nov-2025) | 4 Story carrry forward | Internal | Metric Deviation | Commitment Index Deviation | 50421: Development completed also PR get approved, but due to clients request this feature needs to go only in 15.4 release, hence on hold. That's the reason story is in peer review status. 50614: Fixing local setup for Automation taking time. 50420: Development completed also PR get approved, but due to clients request this feature needs to go only in 15.4 release, hence on hold. That's the reason story is in peer review status. 50422: Development completed also PR get approved, but due to clients request this feature needs to go only in 15.4 release, hence on hold. That's the reason story is in peer review status. | Cosmetic Issue |  | 50421, 50420, 50422 - Due to client comments its not went for current release 50614 - It takes some time to understand the automation testcase. Once we get familiar then we can complete ASAP. | Tharanya Preeti Poornima | Closed | 2025-11-17 |  | Metric Deviation
6 | 2025-11-11 | 15.3 Sprint 3 (28-Oct-2025 to 11-Nov-2025) | 1 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | We reference `selectRole` in script `editrole.js` but it was missed. | Code Issue |  | Getting id's value/reference instead of directly using in js file from jsp | Tharanya | Closed | 2025-11-10 |  | Metric Deviation
7 | 2025-11-25 | 26.1 Sprint 1 (12-Nov-2025 to 25-Nov-2025) | Commitment Index deviation | Internal | Metric Deviation | Commitment Index Deviation | The Orders page (Add/Edit/View) has been completed as part of the current sprint. Since the Orders module contains multiple web forms with varied input fields and several redirections across pages, the Bootstrap 5 conversion requires additional effort. | Estimation |  | Dev team to check in with team/PO on plan for the approach of the feature to make sure we’re going in the right direction. Dive deeper to get a full picture before start of the sprint. | Tharanya Preeti Poornima | Closed | 2025-12-09
8 | 2025-11-25 | 26.1 Sprint 1 (12-Nov-2025 to 25-Nov-2025) | 1 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | CRC Comment: This is not needed since we are doing basically the same thing above. |  |  | RCA: During the conversion from Bootstrap 3 (bs3) to Bootstrap 5 (bs5), certain bs3-related code fragments were not fully removed. Mitigation plan: Document the review comments clearly for traceability.nal effort. | Tharanya Preeti Poornima | Closed | 2025-12-09
9 | 2025-12-10 | 26.1 Sprint 2 (26-Nov-2025 to 9-Dec-2025) | 2 Story carry forward | Internal | Metric Deviation | Commitment Index Deviation | Reason for carry forward story (50445) : Task 50445 was delayed due to deployment postponement due to pipeline issue which resulted in delay in testing the functionalities Reason for carry forward story (50538) : PR raised on Dec 04, 2025 EOD but still the PR approval gets delayed from client side | Environment Issue |  | Dev team to check with the client lead for the deployment issue and resolve it. Also onsite lead to followup with the client for the code review completion. | Poornima Tharanya Karthik | Closed | 2025-12-16
10 | 2025-12-10 | 26.1 Sprint 2 (26-Nov-2025 to 9-Dec-2025) | 1- Code Quality Index | External | Metric Deviation | Commitment Index Deviation | CRC Comment : Sanitization logic is handled in msbApp.js and msbappvega.js. Bootstrap popover and modal were updated to close correctly. |  |  | RCA: The issue arise during migration to Bootstrap 5, as the existing popover and modal implementation was not compatible with the Bs5. Mitigation plan: Review comments have been documented for traceability. | Poornima Tharanya Karthik | Closed | 2025-12-16
11 | 2026-01-06 | 26.1 Sprint 3 (9-Dec-2025 to 6-Jan-2026) | 1- Code Quality Index | External | Metric Deviation | Commitment Index Deviation | CRC Comment : Validation logic for add/edit webform should be maintain in common place to make code reuseable |  |  | RCA: Client needs existing validation method, it should be maintained in common place to make code resuable. Mitigation plan: In future, we can maintain common validation code in common file. | Poornima Tharanya Karthik | Closed | 2026-01-07
12 | 2026-01-06 | 26.1 Sprint 3 (9-Dec-2025 to 6-Jan-2026) | 3 Story carrry forward | External | Metric Deviation | Commitment Index Deviation | Reason for carry forward stories (51148, 51149, 51150) to next sprint is : It's stretch story taken after the main story completion and done partially |  |  | RCA: Client needs existing validation method, it should be maintained in common place to make code resuable. Mitigation plan: In future, we can maintain common validation code in common file. | Poornima Tharanya Karthik | Closed | 2026-01-07
13 | 2026-01-20 | 26.3 Sprint 1 (7-Jan-2026 to 20-Jan-2026) | 1 Story carry forward | External | Metric Deviation | Commitment Index Deviation | Reason for carry forward stories (51150, 51151) to next sprint is : Found new challenges for the scenario child table in the Orders List page and Products list page. So from client side we get confirmation and implemented in a such a way. |  |  | RCA: Dev team to check in with team/PO on plan for the approach of the feature to make sure we’re going in the right direction. Mitigation plan: Dive deeper to get a full picture before start of the sprint. Did proper analysis before implementation | Poornima Tharanya Karthik | Closed | 2026-01-20
14 | 2026-01-20 | 26.3 Sprint 1 (7-Jan-2026 to 20-Jan-2026) | 2 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | CRC comment 1: There is probably no reason for this comment to be in the rendered HTML. You can either remove it entirely or wrap it in a JSP comment so it does not make it into the generated HTML. A JSP comment starts with tag <%-- and ends with tag --%>. I generally use both JSP and HTML comment tags for syntax highlighting like this <%--<!-- some comment -->--%> but you can just remove it all together. RCA: the comment was not required so simply removed it. |  |  | RCA: Client needs to remove unnecessary comments Mitigation plan:will make sure not to add it in other pages | Poornima Tharanya Karthik | Closed | 2026-01-20
15 | 2026-02-03 | 26.3 Sprint 2 (21-Jan-2026 to 3-Feb-2026) | 1 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | Remove this listener and update the edit link, Suggestion given to place the filter item multi select at last for look and free RCA:Suggestion given for placement of multi-select and edit link href # convert to method name. Team followed the non-vega functionality to place and link |  |  | will make sure to follow the vega one in the upcoming stories | Poornima Tharanya Karthik | Closed | 2026-02-03
16 | 2026-02-17 | 26.3 Sprint 3 (4-Feb-2026 to 17-Feb-2026) | 2 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | CRC comment : Review comment: I know existing code does not follow our normal pattern, but the name field should be a Quick View and not a link to the view page. This would make our pages more consistent. It appears the viewprovider.jsp and the /ver2/admin/payments/providers/viewprovider action class are setup for a preview, so it would be a small change. RCA: this was an added functionality mitigation plan: This was an added functionality Review comment: This was used to focus on the search field when the dropdown is shown. There may be a better way, but make sure we do not remove that functionality. RCA: Custom search functionality added, required a different way to highlight the field Mitigation Plan: Deeper analysis on how certain functionality can be achieved in vega |  |  | RCA: 2 Onsite CRC - 1 Suggestion provided for UI change, Custom search functionality added, required a different way to highlight the field Mitigation plan:Deeper analysis will be done on how certain functionality can be achieved in vega | All team members | Closed | 2026-02-18
17 | 2026-02-17 | 26.3 Sprint 3 (4-Feb-2026 to 17-Feb-2026) | 1 - Internal defects | Internal | Metric Deviation | Internal defects | Role based validation and some links should not be visible in different role |  |  | RCA:. 1 Edge case scenario identified during regression testing. Mitigation plan: Add the edge cases to the test suite to valid it during the regression testing. | All team members | Closed | 2026-02-18
18 | 2026-03-03 | 26.4 Sprint 1 (18-Feb-2026 to 3-Mar-2026) | 1 - Code Quality Index | External | Metric Deviation | Commitment Index Deviation | CRC comment : We already have a stripHtml in utils.js. |  |  | RCA : Instead of reusing the utility, the script HTML was converted directly into a popup message. Mitigation Plan : It’s been noted—will check the existing common utilities next time before adding new ones | Poornima | Closed | 2026-03-03
19 | 2026-03-03 | 26.4 Sprint 1 (18-Feb-2026 to 3-Mar-2026) | 1 - Internal defects | Internal | Metric Deviation | Internal defects | List Payment Transfer Page not working in Non-Vega component page |  |  | RCA:. 1 Edge case scenario identified during regression testing. Mitigation plan: Add the edge cases to the test suite to valid it during the regression testing. | All team members | Closed | 2026-03-03
20 | 2026-04-14 | 26.05 Sprint 1 (1-Apr-2026 to 14-Apr-2026) | 1 - External defect | External | Metric Deviation | External defect | Search Email Custom Content grid not working as expected |  |  | RCA:. This is an existing issue found during regression testing and assigned as a task Mitigation plan: Add the edge cases to the test suite to valid it during the regression testing. | All team members | Closed | 2026-04-14

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%
|  | 0.12 | 88%

## Config
Sprint | 26.05 Sprint 3 (29-Apr-2026 to 12-May-2026) | MSB Kaleida Wave | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | 100% | 25% | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | 100% | 20% | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 100% | 20% |  |  | CF |  | Excellent |  | 25
Code Quality Index | 100% | 15% | Velocity
Unit Testing | 90% | 9% | Goal | 20
Backlog Health | 100% | 10%
Code Coverage
|  |  | Goal | 90%
|  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  | Below Avg | 15 | Labels | Values |  | Story Points | 30
|  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  | Excellent | 30 | 15 | 10
|  |  | Total | 90 | 20 | 10
[5 empty] | 25 | 10
50

## Instructions (hidden)
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## Sheet1
Sprint Date | Committed | Delivered | RCA | Mitigation Plan
15.3 Sprint 2 (15-Sep-2025 to 28-Oct-2025) | 21 | 5 | 50420 - (Tharanya) - PR raised before the sprint end and then review is still pending from internal. Since we are new to converting boostrap3 to bootstrap5 there is lot of challenges technically. 50422 - (Poornima) - PR raised before the sprint end and then review is still pending from internal. Since we are new to converting boostrap3 to bootstrap5 there is lot of challenges technically. 50421 - (Preeti) - Development is inprogress and yet to raise PR. Since we are new converting boostrap3 to bootstrap5 there is lot of challenges technically. Need a complete code changes and after done there lot of functionality is breaking and debugging takes a lot of time. | Bootstrap upgrade along with CSS changes to make it look like modern UI design which had lot of complexities in the screen. Client is aware of the technical complexity and understand the challenges in the project. In the upcoming sprints, analyze the complexity of the stories during planning phase and plan the sprint stories and stretch stories accordingly.
15.3 Sprint 3 (28-Oct-2025 to 11-Nov-2025) | 27 | 13 | 50421: Development completed also PR get approved, but due to clients request this feature needs to go only in 15.4 release, hence on hold. That's the reason story is in peer review status. 50614: Fixing local setup for Automation taking time. 50420: Development completed also PR get approved, but due to clients request this feature needs to go only in 15.4 release, hence on hold. That's the reason story is in peer review status. 50422: Development completed also PR get approved, but due to clients request this feature needs to go only in 15.4 release, hence on hold. That's the reason story is in peer review status. | Due to client request, the approved PR has been put on hold. We will track the onhold stories to closure.
26.1 Sprint 1 (12-Nov-2025 to 25-Nov-2025) | 20 | 17 | The Orders page (Add/Edit/View) has been completed as part of the current sprint. Since the Orders module contains multiple web forms with varied input fields and several redirections across pages, the Bootstrap 5 conversion requires additional effort. | Bootstrap upgrade along with CSS changes to make it look like modern UI design which had lot of complexities in the screen. Client is aware of the technical complexity and understand the challenges in the project. Going forward, analyze the complexity of the stories during planning phase and plan the sprint stories and stretch stories accordingly.
26.1 Sprint 2 (26-Nov-2025 to 9-Dec-2025) | 29 | 25 | Reason for carry forward story (50445) : Task 50445 was delayed due to deployment postponement due to pipeline issue which resulted in delay in testing the functionalities Reason for carry forward story (50538) : PR raised on Dec 04, 2025 EOD but still the PR approval gets delayed from client side | Due to client priorities, the PR approval gets delayed from client side. We will track the approved PR to closure.
26.1 Sprint 3 (10-Dec-2025 to 6-Jan-2026) | 78 | 54.5 | Reason for carry forward stories (51148, 51149, 51150) to next sprint is : It's stretch story taken after the main story completion and done partially | It is stretch story and has been carried forward
26.3 Sprint 1 (7-Jan-2026 to 20-Jan-2026) | 47 | 30 | Reason for carry forward stories (51150, 51151) to next sprint is : Found new challenges for the scenario child table in the Orders List page and Products list page. So from client side we get confirmation and implemented in a such a way. | Additional scenario found during the implementation phase, which caused deviation in the commitment index. Going forward, analyze the story during planning phase and discuss with the client to mitigate this deviation