## Dashboard
BOH

## Scorecard
Project Name | MSB Mobile
Engagement Model | Relevantz Co Owned
Overall Score | 86.52%
Current Sprint | 26.5 M Sprint 3 (1-May-2026 to 14-May-2026)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 100% | 25% | #N/A | 25% | 100%
Velocity | 100% | 20% |  | 20% | 95%
Defect-free Rate | 100% | 20% |  | 20% | 100%
Code Quality Index | 54.55% | 8.182% |  | 15% | 100%
Unit Testing & Code Coverage | 100% | 10% |  | 10% | 90%
Backlog Health | 33.33% | 3.333% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | Bounce backs | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
[15 empty] | 0 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.01 M Sprint 3 (12-Dec-2025 to 08-Jan-2026) | 41 | 38 | 92.68% | 30 | 100% | 4 | 5 | 0 | 0 | 10 | No |  |  | 1 Story carry forwarded
26.03 M Sprint 1 (09-Jan-2026 to 22-Jan-2026) | 23.5 | 36 | 100% | 30 | 100% | 1 | 1 | 0 | 0 | 10 | No |  |  | 2 Stories carry forwarded due BB created and onsite developers working on it.
26.03 M Sprint 2 (23-Jan-2026 to 05-Feb-2026) | 21.5 | 39 | 100% | 30 | 100% | 2 | 4 | 0 | 0 | 10 | No |  |  | 1 Story carry forwarded due BB created and onsite developers working on it.
26.03 M Sprint 3 (06-Feb-2026 to 19-Feb-2026) | 38 | 22 | 57.89% | 30 | 100% | 1 | 7 | 0 | 0 | 10 | No |  |  | 1 Story carry forwarded due BB created and onsite developers working on it.
26.04 M Sprint 1 (20-Feb-2026 to 05-Mar-2026) | 39.5 | 36.5 | 92.41% | 30 | 100% | 2 | 7 | 0 | 0 | 10 | Yes |  |  | 1 Story carry forwarded due to AC change and 3 defects carry forwarded in Regression sprint.
26.04 M Sprint 2 (06-Mar-2026 to 19-Mar-2026) | 32 | 32.5 | 100% | 30 | 100% | 0 | 7 | 0 | 0 | 10 | Yes |  |  | 2 Stories carry forwarded and 2 defects carry forwarded
26.04 M Sprint 3 (20-Mar-2026 to 02-Apr-2026) | 32 | 29 | 90.62% | 30 | 100% | 9 | 18 | 0 | 0 | 20 | Yes
26.5 M Sprint 1 (03-Apr-2026 to 16-Apr-2026) | 33.5 | 17.5 | 52.24% | 30 | 100% | 5 | 24 | 0 | 0 | 20 | Yes |  |  | Regression sprint
26.5 M Sprint 2 (17-Apr-2026 to 30-Apr-2026) | 19 | 19 | 100% | 30 | 100% | 4 | 1 | 0 | 0 | 20 | No
26.5 M Sprint 3 (1-May-2026 to 14-May-2026) | 13 | 22 | 100% | 30 | 100% | 5 | 5 | 0 | 0 | 10 | No |  |  | Regression sprint

## RCA
3 Why Analysis
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-04-16 | 13.7 Sprint 2 (03-Apr to 16-Apr) | 2 stories got carried | Internal | Metric Deviation | Commitment Index Deviation | Development completed, but new AC is added at end of this sprint so this story is carried to next sprint for POV and Testing | Scope of AC chages were due to external factors. |  | Changes done by Customer which is Uncontrol and Can not Mitigate | Sambath/Ashwin | Inprogress | 2024-04-22 | Will be completed in nest sprint | Metric Deviation
2 | 2024-04-08 | 13.7 Sprint 2 (03-Apr to 16-Apr) | 2 External defects. - Print Receipt alignment - Barcode scanner | External | Metric Deviation | Client reported defects | Defect was identified while testing through Client physical devices (Receipt printer and Barcode scanner) |  |  | Dependecy with client devices. | Gokul | Closed | 2024-04-11 | Fix provided within Sprint. | Security Compliance
3 | 2024-07-10 | 14.0 Sprint 2 (26-Jun to 11-Jul) | Move color code to resouce | External | Metric Deviation | Customer reported CRC | Suggestion during Code Review |  |  | Should make sure on Code optimization | Gokul | Closed | 2024-07-11 | Fix provided within Sprint. | Not adhered to Policy
4 | 2024-09-19 | 14.2 Sprint 1(6-sep to 19-Sep) | 4 QA Defects | Internal/External | Metric Deviation | Internal, Bounceback and External Client reported Defects | All the defects were part of pervious release and took some major issues that client and QA reported |  |  | Knowledge Sharing was done and the Client was well informed | Ashwin/Gokul | Inprogress | 2024-09-30
5 | 2024-10-03 | 14.2 Sprint 2(20-sep to 03-Oct) | 1 QA Defect | Internal | Metric Deviation | Defect reported by Internal QA | Defect was identified while testing report. |  |  | Knowledge Sharing was done and the Client was well informed | Ashwin | Closed | 2024-10-03
6 | 2024-10-17 | 14.2 Sprint 3(04-Oct to 17-Oct)) | 3 QA Defects | Internal | Metric Deviation | 2 Defects and 1 Bounceback | Bounceback was while testing the story | 2 other defects were internal findings |  | Knowledge Sharing was done and the Client was well informed | Ashwin/Sambath/Vaishnavi | Closed | 2024-10-17
7 | 2024-10-31 | 14.3 Sprint 1(18-Oct to 31-Oct)) | Commitment Index Deviation, 3 Bouncebacks | Internal | Metric Deviation | Low Commitment Index and 3 Boucebacks | 3 Bouncebacks were identified by Internal QA during Testing | Dev completed and testing pending | continue to working on MAUI. Bussiness logics completed, working on UI Binidngs | Knowledge Sharing was done and the Client was well informed | Sambath/Gokul | Closed | 2024-11-14 | Business Logics is done. MAUI is a new framework to be implemented and Client Dependency | Others
8 | 2024-11-14 | 14.3 Sprint 2 (Nov -1 to Nov -14) | Commitment Index Deviation, 5 Bouncebacks | Internal | Metric Deviation | Low Commitment Index and 5 Boucebacks | Development completed and moved to testing. Bounceback's are addressed (4 BB) | Existing BB fixed, but due to some pending clarifications required, development will be continued on next sprint | Due to GSOC priority story, development for this story will be continued to next sprint | Client changed their requirement after POv. Knowledge sharing based on clients expectations | Gokul/Ashwin | Closed | 2024-11-28 | Client expectations changed, we had new changes coming in with respect to GSOC and MAUI
9 | 2024-12-02 | 14.3 Sprint 3 (15-Nov to 02-Dec) | Commitment Index Deviation, Defect Index and CRC | Internal/External | Metric Deviation | Commitment Index Deviation, Defect Index and 3 External CRC | MSBP regression could not be completed due to external dependency for greenLight testing(functionality).The workflow in GLs end was changed which was not intimated until Letashia tested it and found it. GL cannot be tested offshore due to region specific restriction. Dotnet 9 update caused the bottom sheet issues(Internal Component) so MAUI stories could not be tested. | Defect Index - 3 Regression Findinds were reported and one bounceback was reported | JSON prop names need to match with case sensitivity to the return Remove commented code | GL cannot be tested offshore due to region specific restriction. Dotnet 9 update caused the bottom sheet issues(Internal Component) so MAUI stories could not be tested. | All Members | Closed | 2024-12-31 | 2 Regression Defects have been closed. Currently Onsite Client Team is working on the Blocker, once the issue is resolved, we can move further.
10 | 2024-12-12 | 14.4 Sprint 1 (3-Dec to 12-Dec) | Bouncebacks | Internal | Metric Deviation | Commitment Index Deviation due to Internal QA Bounceback | All the Bounceback were given by Internal QA - Environement Related issues |  |  | The Issues will be fixed in next sprint since we took it in Stretch. Some bounceback are due to already existing blocker. Client are looking into that | Gokul/Ashwin | Closed | 2025-01-09
11 | 2025-01-09 | 14.4 Sprint 2 (13-Dec to 09-Jan) | Bouncebacks and CRC | Internal/External | Metric Deviation | Commitment Index Deviation due to Internal QA Bounceback and CRC Comments | 1 Internal and 3 External CRC - All are Suggestions from the Clients - Replaced wtih Vertical and HorizotalLayout instead of StackLayout | 4 Bouncebacks - Issues occuring with newer versions in MUAI when comparing with Xamarin on the devices |  | The Bouncebacks are due to newer version of Maui when comparing the devices. The Team will update to the latest version of Maui | Gokul/Ashwin/Sambath | Closed | 2025-01-09
12 | 2025-01-23 | 14.4 Sprint 3 (10-Jan to 23-Jan) | 1 Bounceback and 4 QA Findings for Client | Internal | Metric Deviation | 1 Bounceback from the Stretch Story Development and 4 QA Findings | 1 Bounceback from the Story - Development findings | 4 Defects are related to Environment issues. Findings were from Offshore QA and fixed by Onshore Team |  | The Issues are fixed and we are working on them. The Team is working on fixing the bounceback which is in stretch | Sambath/Vaishnavi | Closed | 2025-01-23
12 | 2025-02-06 | 14.5 Sprint 1 (24-Jan to 6-Feb) | 5 QA Defects, 2 CRC | Internal/External | Metric Deviation | 5 QA Defects which are bouncebacks - Development related. Maui version not working as Xamarin. | 2 CRC - Logical and Suggestions 1.We should split these up into their respective classes at some point e.g. StudentExtension 2.Null check all the things, BasketPreview 3.Do we need to carry this around on the AppSession? - Use the ValueCompletionSource - Use the return type of the sheet instead of using a message - Use RadCollectionView instead of RadListView - Remove ContentView |  |  | The Issues are fixed and we are working on them. The Team is working on fixing the bounceback which is in stretch | Sambath/Gokul/Ashwin | Closed | 2025-02-06
13 | 2025-02-20 | 14.5 Sprint 2 (07-Feb-2025 to 20-Feb-2025) | 2 CRC, 11 Defects | Internal/External | Metric Deviation | 2 CRC, 8 Internal Defects and 3 External Defects | 2 CRC are for suggestions and logical comments | 8 Internal defects The Team is currently working on MAUI migration and they have been working on a defect sheet to be completed after the migration process. The Client is aware of this. The Defects are related to Android and iOS wrks as well as MAUI conversion | 3 External Defects are Existing issues that needs to be worked on after MAUI Migration | The Defects are fixed and its related to MAUI Conversion and Android and iOS. The Defects are fixed. | All Members | Closed | 2025-02-20
14 | 2025-03-06 | 14.5 M Sprint 3 (21-Feb-2025 to 06-Mar-2025) | 5 Defects and 12 Regression Defect Fixes | Internal | Metric Deviation | 5 Internal Defects and 12 Regression Defect Fixes | In this sprint we worked on defects which were identified earlier during Xamarin to Maui conversion. As per the discussion with Client - Brian, these issues were maintained in a separate sheet and later added as a defect. |  |  | As per the discussion with Client - Brian, these issues were maintained in a separate sheet and later added as a defect. The Team is working on the defects after the conversion to MAUI | All Members | Closed | 2025-03-06
15 | 2025-03-24 | 14.6 M Sprint 1 (7-Mar-2025 to 24-Mar-2025) | Defects and Bounceback | Internal | Metric Deviation | 20 Defects and 1 Bounceback | 20 Internal Defects Client has approved to work in Defects, considering the Migration to MAUI is done for Major Stories. Telerik CollectionView control is having some issues some of which are still open issues tickets. Hence we are migrating to native collection view and it is missing some features of Telerik control. So working on it to manully replicate the features in native control. Please Note: All the Defects found were logged directly to Commit. These defects were found during Post migration Maui Regression testing. | 1 Bounceback - Issues Found during Testing. |  | As per the discussion with Client - Brian, these issues were maintained in a separate sheet and later added as a defect. The Team is working on the defects after the conversion to MAUI | All Members | Closed | 2025-03-24 | Client has approved to work in Defects, considering the Migration to MAUI is done for Major Stories. Please Note: All the Defects found were logged directly to Commit. These defects were found during Post migration Maui Regression testing.
16 | 2025-04-03 | 14.6 M Sprint 2 (25-Mar-2025 to 03-Apr-2025) | Defects and Bounceback | Internal | Metric Deviation | 9 Defects and 1 Bounceback | 9 internal defects These defects were found during Post migration Maui Regression testing. | 1 Bounceback - Issues Found during Testing. |  | As per the discussion with Client - Brian, these issues were maintained in a separate sheet and later added as a defect. The Team is working on the defects after the conversion to MAUI | All Members | Closed | 2025-04-03
17 | 2025-04-17 | 14.6 M Sprint 3 (04-Apr-2025 to 17-Apr-2025) | Defects | Internal | Metric Deviation | 14 Defects | 14 internal defects These defects were found during Post migration Maui Regression testing. |  |  | As per the discussion with Client - Brian, these issues were maintained in a separate sheet and later added as a defect. The Team is working on the defects after the conversion to MAUI | All Members | Closed | 2025-04-17
18 | 2025-05-01 | 14.7 M Sprint 1 (18-Apr-2025 to 01-May-2025) | Defects | Internal | Metric Deviation | 1 Defect | 1 internal defect. Cause: When approving permissions after selecting student icon for picture, receiving the message usually seen at denial and camera options never open. Able to open the picture menu as expected afterwards |  |  | As per the discussion with Client - Brian, these issues were maintained in a separate sheet and later added as a defect. The Team is working on the defects after the conversion to MAUI | Ashwin | Closed | 2025-05-15
19 | 2025-05-15 | 14.7 M Sprint 2 (02-May-2025 to 15-May-2025) | Defects and Bounceback | Internal | Metric Deviation | External Defects - 1 Internal Defects - 1 Bouncebacks- 2 | 2-Bouncbacks Cause: Exisiting Xamarin behaviour and due to Xamarin to Maui conversion | 1 -Internal defect Cause : Found during Xamarint to Maui conversion story testing |  | As per the discussion with Client - Brian, these issues were maintained in a separate sheet and later added as a defect. The Team is working on the defects after the conversion to MAUI | All Members | Closed | 2025-05-15
20 | 2025-05-29 | 14.7 M Sprint 3(16-May-2025 to 29-May-2025) | Committment Index | Internal/External | Metric Deviation | Committed 12 Delivered 7 | Due to an iOS app crash, testing and development activities were blocked. |  |  | As per the discussion with the client, their developer has committed to fixing the iOS app crash. | All Members | Closed | 2025-06-12
21 | 2025-05-29 | 14.7 M Sprint 3(16-May-2025 to 29-May-2025) | Defects | External | Metric Deviation | External Defect - Defects | 6 External defects Cause: Exisiting Xamarin behaviour due to Xamarin to Maui conversion |  |  | The Defects are fixed and its related to MAUI Conversion. | All Members | 2 Defect closed. 4 Inprogress. | 2025-05-29 | Issues identified by Client and fixed by Relevantz team
22 | 2025-07-12 | 15.0 M Sprint 1(30-May-2025 to 12-June-2025) | Defects | Internal/External | Metric Deviation | 21 External Defects and 3 Internal defects | Client has approved to work in Defects, considering the Migration to MAUI is done for Major Stories. Most of the defects were found during the regresion testing. | 21 External defects cause: Defects were found by Client QA/Dev and fixed/tested by Relevantz Team | 3 Internal defects cause: Xamarin to Maui coversion | The Defects are fixed and its related to MAUI Conversion. | All Members | Closed - 11 Inprogress - 10 | 2025-06-12 | 10 defects were still in progress.
23 | 2025-07-25 | 15.0 M Sprint 2(13-June-2025 to 25-June-2025) | Defects | Internal/External | Metric Deviation | External Defects - 18 Internal Defects - 4 | Client has approved to work in Defects, considering the Migration to MAUI is done for Major Stories. | 18 External defects cause: Defects were found by Client QA/Dev and fixed/tested by Relevantz Team | 4 Internal defects cause: Xamarin to Maui coversion | The Defects are fixed and its related to MAUI Conversion. | All Members | Closed - 20 Inprogress - 2 | 2025-06-25 | 2 defects carried to next sprint.
24 | 2025-07-10 | 15.0 M Sprint 3(25-June-2025 to 10-July-2025) | Defects and Bounceback | Internal/External | Metric Deviation | External Defects - 4 Internal Defects - 1 Bouncebacks- 1 | Defects/bouncebacks found during xamarin to Maui conversion. | 1-bouncebacks found during the Maui conversion Story testing |  | All defects were fixed and 1 Bouncbacks is carried to next sprint | All Members | Closed - 5 Inprogress - 1 | 2025-07-10 | 1 bouncebacks carried to next sprint
25 | 2025-07-10 | 15.0 M Sprint 3(25-June-2025 to 10-July-2025) |  | Internal/External | Others |  | RCA: Due to issues with Owen's environment and there is no proper framework, automation fails in Owen's system. Some of the framework are not reusable due to that which is causing delay in automation work. Fix: Needs a discussion with Ashwin and Owen on this | Work with Owen to find his environment setup issue and resolve it. |  | Work with Owen to find his environment setup issue and resolve it. | All Members |  | 2025-07-30
26 | 2025-08-07 | 15.1 M Sprint 2(25-June-2025 to 10-July-2025) | Committment Index | Internal/External | Others |  | RCA: Due to Owen availability some of the use cases are pending with peer review. Waiting for his approval | Finish the use case much earlier to get his time instead going for last minute |  | Work with Owen to find his time. | All Members |  | 2025-07-30
27 | 2025-08-21 | 15.1 M Sprint 3 (8-Aug-2025 to 21-Aug-2025) | Committment Index | Internal/External | Others | Client Code Review comment | RCA:UI Relaiablity related review comments has been shared to change the UI validation in the code | Accepted the client comment and updated the code with UI validation and reliablity |  | Accepted the client comment and updated the code with UI validation and reliablity | Sambath |  | 2025-08-20
28 | 2025-10-17 | 15.3 M Sprint 1 (03-Oct-2025 to 16-Oct-2025) | Committment Index | Internal/External | Others |  | There 4 points not completed. 2 points went onhold another 2 point, the story completed however the POV delayed | Client accepted it and asked the team to available for POV validation |  | Moving forward ensure to present the story before instead of end of the sprint for POV | Sambath
29 | 2025-10-30 | 15.3 M Sprint 2 (17-Oct-2025 to 30-Oct-2025) | Committment Index | Internal/External | Others |  | The Automation story 3 point was not completed due to failing randomly when run end to end in BS​ | Client accepted it and carry forwarded to next sprint. |  | Going forward, Will ensure thorough planning and root cause analysis are conducted before initiating any automation-related stories. | Sambath |  | 2025-10-30
30 | 2025-11-26 | 20.1 M Sprint 1 (14-Nov-2025 to 26-Nov-2025) | Committment Index | Internal/External | Metric Deviation |  | 1 Story carry forwarded due to last minute AC change by client and 2 defects there was delay in review due to PTO' of offshore Engineer confirmation and no clear data. | Client accepted it and carry forwarded to next sprint. |  | We will ensure thorough planning and root cause analysis to complete our commitment. Maintain backup reviewer and Validate test data early and create readiness checklist for defect review. | All Members | Completed | 2025-12-10
31 | 2025-12-12 | 26.1 M Sprint 2 (27-Nov-2025 to 11-Dec-2025) | Committment Index | Internal/External | Metric Deviation |  | 1 Story carry forwarded due to last minute AC change by client and BB came based on fix | Client accepted it and carry forwarded to next sprint. |  | We will ensure about the proper impact analysis before commiting. | Rupesh | Completed
32 | 2025-12-11 | 26.1 M Sprint 2 (27-Nov-2025 to 11-Dec-2025) | CRC | Internal/External | Metric Deviation | Client Code Review comment | Most of the review comments we have been receiving from the client are related to refactoring existing code, which is not part of the current story or defect. We assuming that the client developer may be intentionally creating multiple review comments per PR using some AI tool such as Copilot or something similar. After discussing with the client developer, He shared a review checklist that we are expected to follow in order to refactor, clean, and make the code easier to understand. These comments have been consistently raised over the last couple of weeks. We discussed this with the client developer who is reviewing the PRs, and he confirmed that all items in the checklist should be considered while implementing stories or defects. | We started using the same checklist for internal code review comments its kind of filteration before moving to client. |  | We are continuing to work on reducing the review comments based on their checklist and we have already discussed this matter with our manager and the onsite delivery manager. Address legacy code improvements wherever feasible during story implementation. Perform additional peer reviews before PR submission to reduce external comments. | All Members | Completed
33 | 2026-01-08 | 26.1 M Sprint 3 (12-Dec-2025 to 08-Jan-2026) | Committment Index | Internal/External | Metric Deviation | 1 Story carry forwarded | This story was initially estimated only for a .NET 10 and package update, but due to the update, many pages has UI issues and page navigation stopped working. As discussed in the standup, we are finding and fixing these issues within the existing story so we couldn’t close this story within this sprint. |  |  | Document why the upgrade caused these issues. Share findings with the team to improve future estimation and planning. | Sambath | Completed
34 | 2026-02-19 | 26.3 M Sprint 3 (06-Feb-2026 to 19-Feb-2026) | Committment Index | Internal/External | Metric Deviation | 2 Stories carry forwarded and 1 Regression story blocked | Due to recent scope updates and UI refinements, this story is being carried forward to the next sprint. Additional acceptance criteria were introduced, including filter behavior updates, refund flow handling, admin popup implementation, and the addition of Unit Price and Quantity fields. These changes were not part of the original design and required extra alignment and rework. We also addressed multiple UI issues across devices to ensure a consistent experience. | This task take additional effort due to a known .NET MAUI issue with the Liquid Water Glass feature on iOS. After another PR enabled the feature, it impacted the completed story. Merging into main caused an unexpected bounce-back, which required rework and a new PR. | Onsite Developer Sean has to push the deployment to store for MSBA CA production apps. Already communicated to client aswell. Testing was not started and it is blocked. | • We are finalizing all updated requirements and aligning them with the team before development. • Missing design scenarios are being identified upfront to avoid gaps. • Cross-device validation will be done earlier in the cycle. • Any new scope additions will go through impact analysis before commitment. | All Members | Completed
35 | 2026-02-19 | 26.3 M Sprint 3 (06-Feb-2026 to 19-Feb-2026) | CRC | External | Others | CRC comments | he client’s review comments are mostly minor, such as moving color codes to a resource file instead of using them directly in the design file, replacing obsolete layouts with updated ones, and fixing code misalignment issues. |  |  | Centralize all hard‑coded colors into a shared resource file and update references across design files. Quick regression check to ensure no UI impact. Identify outdated layouts and swap them with the latest approved components. Validate UI alignment and responsiveness after updates. | All Members | Completed
36 | 2026-03-05 | 26.4 M Sprint 1 (20-Feb-2026 to 05-Mar-2026) | Committment Index | Internal/External | Metric Deviation | 1 Story carry forwarded and 3 defects carry forwarded | Story - AC Changed by Client, Few changes was discussed along with development with client. (27 Feb)Again AC Requirement changed by client discussion in progress | For 1 Defect - The original issue has been fixed. During testing, a spacing issue was identified in both Featured and Products, which has now been resolved. Currently, when clicking collapse and expand, the data is not displaying under Featured and Products. | 2 Defects - this is regression sprint and picked up very late client agreed to carry over the regression by onsite QA and these defects created at last days sprint & picked up at last day that too development is done, testing in different scenario and POV is pending. | We will ensure thorough planning and follow the below Freeze AC before development starts – Any client changes must go through a proper change request to avoid rework during the sprint. this is unavoidable situation. Do thorough developer self‑testing – This helps avoid UI issues/regressions like spacing or collapse/expand problems. Start regression early and avoid last‑day pickups – Defects should be raised and tested earlier to prevent spillover and last-minute rush. | All Members | Completed
37 | 2026-03-05 | 26.4 M Sprint 1 (20-Feb-2026 to 05-Mar-2026) | CRC | External | Metric Deviation | CRC comments | he client’s review comments are mostly minor, such as moving color codes to a resource file instead of using them directly in the design file, replacing obsolete layouts with updated ones, and fixing code misalignment issues. |  |  | Prepared a standard checklist for all code review comments and will use it consistently going forward to avoid repeating the same issues. | All Members | Completed
38 | 2026-03-19 | 26.4 M Sprint 2 (06-Mar-2026 to 19-Mar-2026) | Committment Index | Internal/External | Metric Deviation | 2 Stories carry forwarded and 2 defects carry forwarded | For this story, the Acceptance Criteria were changed by the client and discussed over Slack, specifically related to barcode and other functionalities. Since the exact Figma designs were not available, development was carried out based on the updated AC points. The AC change on 11 Mar required additional rework and adjustments, impacting the planned progress. For this particular story, extensive clarifications were required due to evolving requirements. In the previous sprint, there were multiple rounds of Acceptance Criteria (AC) discussions with stakeholders, which resulted in continued development across iterations. Additionally, several CRC comments were received and subsequently resolved to align with the client’s updated expectations. | The defect could not be reproduced because the card reader was not connected on Android, and connectivity issues were also faced on iOS devices. Due to the unavailability of a stable device setup, testing and reproduction were blocked. This was already communicated to the team. By the end of the sprint, during sprint planning, the client decided on the next steps, which impacted timely resolution within the same sprint. | this defect was created and picked up on the last day of the sprint. Development was completed from a POV perspective; however, both internal and external PR reviews were still pending. Due to the late pickup and pending reviews, the defect could not be completed within the sprint and was carried forward to the next sprint. | 1.Finalize and get sign-off on ACs before starting development, and align client expectations early to avoid multiple revisions and rework during the sprint. 2.Ensure ACs and finalized Figma designs are available and signed off before development starts, and assess timeline impact immediately for any mid-sprint AC changes. 3.Ensure defects are picked earlier in the sprint to allow sufficient time for development and PR reviews, and prioritize early initiation of internal and external reviews to avoid spillover. | All Members | Completed
39 | 2026-03-19 | 26.4 M Sprint 2 (06-Mar-2026 to 19-Mar-2026) | CRC | External | Metric Deviation | CRC comments | he client’s review comments are mostly minor, such as moving color codes to a resource file instead of using them directly in the design file, replacing obsolete layouts with updated ones, and fixing code misalignment issues. |  |  | Prepared a standard checklist for all code review comments and will use it consistently going forward to avoid repeating the same issues. | All Members | Completed
40 | 2026-04-02 | 26.4 M Sprint 3 (20-Mar-2026 to 02-Apr-2026) | Committment Index | Internal/External | Metric Deviation | 4 defects carry forwarded in developed , 3 in Peer review and 2 in testing. 2 stories in need more info | This was a regression sprint where defects were identified and addressed in parallel. Some defects were raised and picked up late in the sprint, including on the last day, across development, peer review, and testing phases. Client is aware and agreed to this approach for regression handling | Two stories in the main sprint require additional information as the client has put them on hold with lower priority, which blocked further testing activities. |  | Defect pickup and fixes were aligned with client expectations for a regression sprint. Priority-based handling was followed, and remaining validation activities were planned with client agreement to ensure no delivery risk. Stories will remain on hold until client provides the required inputs and has dependency as well in queue. Once details are confirmed, testing will be planned and executed in the subsequent sprint based on client‑approved priority. | All Members | Completed
41 | 2026-04-02 | 26.4 M Sprint 3 (20-Mar-2026 to 02-Apr-2026) | CRC | Internal/External | Metric Deviation | CRC comments | This was the first story for Kalieda after Kaleida components where added so had comments for all the controls to be replaced with Kaleida components resulting in high PR comment count | This story has been delayed due to new Kaleida control changes. At the same time, Avery working with Kaleida control libraries, which has caused multiple issues while integrating the control into the MSBA project. In addition, Some new AC has been updated, which has further delayed the move to testing. |  | Preparing and adding more to standard checklist for all code review comments and will use it consistently going forward to avoid repeating the same issues. | All Members | Completed
42 | 2026-04-16 | 26.5 M Sprint 1 (03-Apr-2026 to 16-Apr-2026) | Committment Index | Internal/External | Metric Deviation | 4 Stories carry forwarded in development, 2 in testing and 2 defects carry forwarded in Peer review and dev. | Testing was delayed due to dependency on Kaleida branch merge and defect 27072 completion. Additional bounce backs were identified during QA, including sales tag format issues, and some were added after POV. Design changes, delayed client feedback, merge conflicts, and dependency on story 51972 (Admin Settings) increased the time required for fixes and re-validation, resulting in carry-forward to the next sprint. | The defect was assigned to Jagdeep on 14 April and was fixed on 15 April, including POV completion and PR creation. PR reviews from Ashwin and the client were pending, and testing could not be completed within the sprint timeline. Additionally, the task was temporarily on hold due to support provided to team members on higher-priority main stories, resulting in carry-forward to the next sprint. |  | Introduced a mandatory Peer Testing process before QA to identify issues early and reduce bounce backs. Ensure all dependencies and merges are completed before starting testing. Conduct early POV and design/AC sign-off to avoid late-stage changes. Ensure PR reviews and approvals are prioritized for completed defects to avoid spillover. Plan capacity buffer for support activities, ensuring critical defect closures are not impacted. | All Members | Completed
43 | 2026-04-16 | 26.5 M Sprint 1 (03-Apr-2026 to 16-Apr-2026) | CRC | Internal/External | Metric Deviation | CRC comments | CRC comments were raised due to required code refactoring, removal of duplicate code/comments, and client‑requested changes to patterns and structure as per updated story requirements, even after the initial fix was provided. Additional minor changes were needed due to new combinations, along with suggestions to introduce new Kalida components based on evolving client needs during PR review. |  |  | Preparing and adding more to standard checklist for all code review comments and will use it consistently going forward to avoid repeating the same issues. Will try to reduce the 50% code refactoring comments. There is no standard format to follow from clients using AI so will try to optimize and reduce it. | All Members | Completed
44 | 2026-04-30 | 26.5 M Sprint 2 (17-Apr-2026 to 30-Apr-2026) | CRC | Internal/External | Metric Deviation | CRC comments | CRC comments were raised due to required code refactoring with some additional minor changes. |  |  | Preparing and adding more to standard checklist for all code review comments and will use it consistently going forward to avoid repeating the same issues. Will try to reduce the 50% code refactoring comments. | All Members | Completed
45 |  | 26.5 M Sprint 3 (1-May-2026 to 14-May-2026) | Committment Index | Internal/External | Metric Deviation | 2 Defects carry forwarded one was worked by onsite developer | Picked up on 13th May as this regression defect was created at the last moment. |  |  | There is delay in Regression so created at last days and client agreed on the same | All Members | Inprogress | 2026-06-03
46
47
48
49
50
51

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Config (hidden)
Sprint | 26.04 M Sprint 1 (20-Feb-2026 to 05-Mar-2026) | Relevantz Co Owned | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | #N/A | #N/A | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | #N/A | #N/A | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 100% | 20% |  |  | CF |  | Excellent |  | 25
Code Quality Index | #N/A | #N/A | Velocity
Unit Testing & Code Coverage | #N/A | #N/A | Goal | 20
Backlog Health | #N/A | #N/A
Code Coverage
|  |  | Goal | 90%
|  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  | Below Avg | 15 | Labels | Values |  | Story Points | #N/A
|  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  | Excellent | 30 | 15 | 10
|  |  | Total | 90 | 20 | 10
[5 empty] | 25 | 10
50

## Instructions (hidden)
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## ExportData (hidden)
ff | 13.7 Sprint 2 (03-Apr-2024 to 16-Apr-2024) | 13.7 Sprint 2 | 2024-04-03 | 2024-04-16 | April | 21 | 15 | 0.71429 | 0.15 | 0.9 | 0 | 0 | 0 | 2 | #N/A | #N/A | 0.0075 | -212.3333 | 1
ff | 13.7 Sprint 3 (17-Apr-2024 to 30-Apr-2024) | 13.7 Sprint 3 | 2024-04-17 | 2024-04-30 | April | 12 | 12 | 1 | 20 | 0.9 | 0 | 0 | 0 | 0 | #VALUE! | 1 | 1 | -0.5 | 1
ff | 13.8 Sprint 1 (01-May-2024 to 14-May-2024) | 13.8 Sprint 1 | 2024-05-01 | 2024-05-14 | May | 10 | 10 | 1 | 20 | 0.9 | 0 | 0 | 0 | 0 | #VALUE! | 1 | 1 | -0.5 | 1
ff | 13.8 Sprint 2 (15-May-2024 to 28-May-2024) | 13.8 Sprint 2 | 2024-05-15 | 2024-05-28 | May | 22 | 17 | 0.77273 | 20 | 0.9 | 0 | 1 | 0 | 0 | #VALUE! | 0.77273 | 1 | -0.5 | 0.94118
ff | 13.8 Sprint 3 (29-May-2024 to 11-Jun-2024) | 13.8 Sprint 3 | 2024-05-29 | 2024-06-11 | June | 25 | 21 | 0.84 | 20 | 0.9 | 0 | 0 | 0 | 1 | #VALUE! | 0.84 | 1 | -0.55 | 1
ff | 14.0 Sprint 1 (12-Jun-2024 to 25-Jun-2024) | 14.0 Sprint 1 | 2024-06-12 | 2024-06-25 | June | 14 | 11 | 0.78571 | 20 | 0.9 | 0 | 0 | 0 | 0 | #VALUE! | 0.78571 | 1 | -0.5 | 1
ff | 14.0 Sprint 2 (26-Jun-2024 to 11-Jul-2024) | 14.0 Sprint 2 | 2024-06-26 | 2024-07-11 | July | 13 | 13 | 1 | 20 | 0.9 | 1 | 1 | 0 | 0 | #VALUE! | 1 | 1 | -0.5 | 0.84615
ff | 14.0 Sprint 3 (12-Jul-2024 to 25-Jul-2024) | 14.0 Sprint 3 | 2024-07-12 | 2024-07-25 | July | 13 | 13 | 1 | 20 | 0.9 | 0 | 0 | 0 | 4 | #VALUE! | 1 | 1 | -0.7 | 1
ff | 14.1 Sprint 1 (26-Jul-2024 to 08-Aug-2024) | 14.1 Sprint 1 | 2024-07-26 | 2024-08-08 | August | 11 | 11 | 1 | 20 | 0.9 | 0 | 0 | 0 | 3 | #VALUE! | 1 | 1 | -0.65 | 1
ff | 14.1 Sprint 2 (09-Aug-2024 to 22-Aug-2024) | 14.1 Sprint 2 | 2024-08-09 | 2024-08-22 | August | 7 | 7 | 1 | 20 | 0.9 | 0 | 0 | 0 | 2 | #VALUE! | 1 | 1 | -0.6 | 1
ff | 14.1 Sprint 3 (23-Aug-2024 to 5-Sep-2024) | 14.1 Sprint 3 | 2024-08-23 | 2024-09-05 | September | 29 | 27.5 | 1 | 27 | 0.9 | 0 | 0 | 0 | 0 | #VALUE! | 1 | 1 | -0.11111 | 1
ff | 14.2 Sprint 1(6-sep-2024 to 19-Sep-2024) | 14.2 Sprint 1 | 2024-09-06 | 2024-09-19 | September | 8.5 | 13.5 | 1 | 15 | 1 | 0 | 0 | 4 | 0 | #VALUE! | 1 | 0.75 | -1 | 1
ff | 14.2 Sprint 2 (20-sep-2024 to 03-Oct-2024) | 14.2 Sprint 2 | 2024-09-20 | 2024-10-03 | October | 14 | 14 | 1 | 18 | 1 | 0 | 0 | 1 | 0 | #VALUE! | 1 | 0.9 | -0.66667 | 1
ff | 14.2 Sprint 3 (04-Oct-2024 to 17-Oct-2024) | 14.2 Sprint 3 | 2024-10-04 | 2024-10-17 | October | 13 | 16 | 1 | 17.75 | 1 | 0 | 0 | 3 | 0 | #VALUE! | 1 | 0.8875 | -0.69014 | 1
ff | 14.3 Sprint 1 (18-Oct-2024 to 31-Oct-2024) | 14.3 Sprint 1 | 2024-10-18 | 2024-10-31 | October | 19 | 14 | 1 | 14.4 | 0.85 | 1 | 2 | 3 | 0 | #VALUE! | 1 | 0.72 | -1.0833 | 0.78571
ff | 14.3 Sprint 2 (Nov-1-2024 to Nov-14-2024) | 14.3 Sprint 2 | 2024-11-01 | 2024-11-14 | November | 17.5 | 6.5 | 0.73684 | 12.7 | 0.45 | 0 | 0 | 5 | 0 | #VALUE! | 0.73684 | 0.635 | -1.3622 | 1
ff | 14.3 Sprint 3 (15-Nov-2024 to 02-Dec-2024) | 14.3 Sprint 3 | 2024-11-15 | 2024-12-02 | December | 15 | 5 | 0.37143 | 10.4 | 0.3 | 0 | 3 | 4 | 0 | #VALUE! | 0.37143 | 0.52 | -1.8846 | 0.4
ff | 14.4 M Sprint 1 (3-Dec-2024 to 12-Dec-2024) | 14.4 M Sprint 1 | 2024-12-03 | 2024-12-12 | December | 11 | 11.3 | 0.33333 | 9.2 | 0.95 | 0 | 0 | 3 | 0 | #VALUE! | 0.33333 | 0.46 | -2.2609 | 1
ff | 14.4 M Sprint 2 (13-Dec-2024 to 09-Jan-2025) | 14.4 M Sprint 2 | 2024-12-13 | 2025-01-09 | January | 10 | 16 | 1 | 9.7 | 1 | 1 | 3 | 4 | 0 | #VALUE! | 1 | 0.485 | -2.0928 | 0.75
ff | 14.4 M Sprint 3 (10-Jan-2025 to 23-Jan-2025) | 14.4 M Sprint 3 | 2025-01-10 | 2025-01-23 | January | 12 | 13 | 1 | 11 | 1 | 0 | 0 | 1 | 0 | #VALUE! | 1 | 0.55 | -1.7273 | 1
ff | 14.5 M Sprint 1 (24-Jan-2025 to 6-Feb-2025) | 14.5 M Sprint 1 | 2025-01-24 | 2025-02-06 | February | 12 | 19 | 1 | 15 | 1 | 0 | 2 | 5 | 0 | #VALUE! | 1 | 0.75 | -1 | 0.89474
ff | 14.5 M Sprint 2 (07-Feb-2025 to 20-Feb-2025) | 14.5 M Sprint 2 | 2025-02-07 | 2025-02-20 | February | 21 | 35 | 1 | 21 | 1 | 2 | 0 | 5 | 3 | #VALUE! | 1 | 1 | -0.57143 | 0.94286
ff | 14.5 M Sprint 3 (21-Feb-2025 to 06-Mar-2025) | 14.5 M Sprint 3 | 2025-02-21 | 2025-03-06 | March | 21 | 33.5 | 1.5952 | 25.125 | 1 | 0 | 0 |  | 0 | #VALUE! | 1.5952 | 1 | -0.19403 | 1

## Archive
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | Bounce backs | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
13.8 Sprint 3 (29-May-2024 to 11-Jun-2024) | 25 | 21 | 84% | 20 | 90% | 0 | 0 | 0 | 1 | 30 | No |  |  |  | 0 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.0 Sprint 1 (12-Jun-2024 to 25-Jun-2024) | 14 | 11 | 78.57% | 20 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  |  | 0 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.0 Sprint 2 (26-Jun-2024 to 11-Jul-2024) | 13 | 13 | 100% | 20 | 90% | 1 | 1 | 0 | 0 | 30 | No |  |  |  | 0 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.0 Sprint 3 (12-Jul-2024 to 25-Jul-2024) | 13 | 13 | 100% | 20 | 90% | 0 | 0 | 0 | 4 | 30 | No |  |  |  | 0 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 1 (26-Jul-2024 to 08-Aug-2024) | 11 | 11 | 100% | 20 | 90% | 0 | 0 | 0 | 3 | 30 | No |  |  |  | 0 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 2 (09-Aug-2024 to 22-Aug-2024) | 7 | 7 | 100% | 20 | 90% | 0 | 0 | 0 | 2 | 30 | Yes |  |  |  | 0 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.1 Sprint 3 (23-Aug-2024 to 5-Sep-2024) | 29 | 27.5 | 100% | 27 | 90% | 0 | 0 | 0 | 0 | 30 | Yes |  |  |  | 0 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 1(6-sep-2024 to 19-Sep-2024) | 8.5 | 13.5 | 100% | 15 | 100% | 0 | 0 | 4 | 0 | 30 | No |  |  |  | 4 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 2 (20-sep-2024 to 03-Oct-2024) | 14 | 14 | 100% | 18 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  |  | 1 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.2 Sprint 3 (04-Oct-2024 to 17-Oct-2024) | 13 | 16 | 100% | 17.75 | 100% | 0 | 0 | 3 | 0 | 30 | No |  |  |  | 3 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 1 (18-Oct-2024 to 31-Oct-2024) | 19 | 14 | 100% | 14.4 | 85% | 1 | 2 | 3 | 0 | 30 | No |  |  |  | 3 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 2 (Nov-1-2024 to Nov-14-2024) | 17.5 | 6.5 | 73.68% | 12.7 | 45% | 0 | 0 | 5 | 0 | 30 | No |  |  | Client expectations changed, we had new changes coming in with respect to GSOC and MAUI | 5 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.3 Sprint 3 (15-Nov-2024 to 02-Dec-2024) | 15 | 5 | 37.14% | 10.4 | 30% | 0 | 3 | 4 | 0 | 30 | Yes |  |  |  | 4 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 M Sprint 1 (3-Dec-2024 to 12-Dec-2024) | 11 | 11.3 | 33.33% | 9.2 | 95% | 0 | 0 | 3 | 0 | 30 | No |  |  | 8 Day Sprint. Dotnet 9 and Telerik updated caused the bottom sheet issues(Internal Component) and input modal crash issue respectively. So MAUI stories could not be tested. The Blockers were addressed by Client Dev. | 3 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 M Sprint 2 (13-Dec-2024 to 09-Jan-2025) | 10 | 16 | 100% | 9.7 | 100% | 1 | 3 | 4 | 0 | 30 | No |  |  | 4 Weeks Sprint - Test env down for 3 days | 4 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.4 M Sprint 3 (10-Jan-2025 to 23-Jan-2025) | 12 | 13 | 100% | 11 | 100% | 0 | 0 | 1 | 0 | 30 | Yes |  |  |  | 1 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 M Sprint 1 (24-Jan-2025 to 6-Feb-2025) | 12 | 19 | 100% | 15 | 100% | 0 | 2 | 5 | 0 | 30 | No |  |  |  | 5 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 M Sprint 2 (07-Feb-2025 to 20-Feb-2025) | 21 | 35 | 100% | 21 | 100% | 2 | 0 | 5 | 3 | 30 | No |  |  |  | 3 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.5 M Sprint 3 (21-Feb-2025 to 06-Mar-2025) | 21 | 33.5 | 100% | 25.125 | 100% | 0 | 0 | 5 | 0 | 30 | Yes |  |  |  | 5 (Added as of now with Internal Defects) |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.6 M Sprint 1 (7-Mar-2025 to 24-Mar-2025) | 26.5 | 52.88 | 100% | 35.1 | 100% | 0 | 0 | 20 | 0 | 30 | No |  |  | 12 Working Day Sprint Next Sprint will be 7 Day Sprint | 1 |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
14.6 M Sprint 2 (25-Mar-2025 to 03-Apr-2025) | 14.5 | 15.5 | 100% | 34.22 | 93% | 0 | 0 | 10 | 0 | 30 | No |  |  | Due to UI issues , Xamarin to MAUi conversion is in progress. | 1
14.6 M Sprint 3 (04-Apr-2025 to 17-Apr-2025) | 5 | 31.75 | 100% | 33.4 | 95% | 0 | 0 | 14 | 0 | 30 | No |  |  | Due to UI issues , Xamarin to MAUi conversion is in progresss. | 5 (Added as of now with Internal Defects)
14.7 M Sprint 1 (18-Apr-2025 to 01-May-2025) | 3 | 8 | 100% | 27.03 | 95% | 0 | 0 | 1 | 0 | 30 | No |  |  | Due to UI issues , Xamarin to MAUi conversion is in progressed. | 1 (Added as of now with Internal Defects)
14.7 M Sprint 2 (02-May-2025 to 15-May-2025) | 18.5 | 20.5 | 100% | 19.9 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Exisiting Xamarin behaviour and due to Xamarin to Maui conversion.
14.7 M Sprint 3 (16-May-2025 to 29-May-2025) | 12 | 7 | 58.33% | 17.75 | 90% | 0 | 0 | 0 | 0 | 30 | No |  |  | Due to an iOS app crash, testing and development activities were blocked
15.0 M Sprint 1 (30-May-2025 to 12-Jun-2025) | 42 | 31 | 73.81% | 15.56 | 90% | 3 | 0 | 0 | 0 | 30 | Yes |  |  | Defects were tested and closed at the end of the sprint as we were unable to test in IOS devices due to build issues in iOS.
15.0 M Sprint 2 (13-Jun-2025 to 25-Jun-2025) | 28.5 | 26 | 91.23% | 19.9 | 90% | 0 | 0 | 0 | 0 | 30 | Yes
15.0 M Sprint 3 (26-Jun-2025 to 10-Jul-2025) | 40 | 24 | 60% | 15 | 90% | 0 | 0 | 1 | 0 | 30 | Yes |  |  | 1. MSBP Maui Regression 2. Appium setup in iOS and android 3. Few automation stories development completed, waiting for client review. 4. MSBA Stretch stories completed.
15.1 M Sprint 1 (11-Ju1-2025 to 24-Jul-2025) | 38 | 14 | 36.84% | 20 | 90% | 2 | 6 | 0 | 0 | 30 | Yes |  |  | 1. CA MSBP Smoke Testing against Prod version 2. Few automation stories completed. 3. MSBA Maui coversion stories completed 4. Development completed for automation stories, client review is pending
15.1 M Sprint 2 (25-Ju1-2025 to 07-Aug-2025) | 46 | 32 | 69.57% | 30 | 90% | 0 | 0 | 0 | 0 | 30 | Yes |  |  | Completed Main sprint automation.
15.1 M Sprint 3 (8-Aug-2025 to 21-Aug-2025) | 25 | 35 | 100% | 30 | 90% | 2 | 0 | 3 | 0 | 30 | Yes
15.2 M Sprint 1 (22-Aug-2025 to 4-Sep-2025) | 23 | 48 | 100% | 30 | 100% | 2 | 1 | 0 | 0 | 30 | Yes |  |  | 1. Completed all completed MSBA/MSBP defects 2. Automation stories completed
15.2 M Sprint 2 (05-Sep-2025 to 18-Sep-2025) | 18.5 | 21 | 100% | 30 | 100% | 0 | 0 | 0 | 0 | 30 | Yes |  |  | 1. Completed all completed MSBA/MSBP defects 2. Automation stories completed
15.2 M Sprint 3 (19-Sep-2025 to 02-Oct-2025) | 50.5 | 50.5 | 100% | 30 | 100% | 0 | 0 | 0 | 0 | 30 | Yes |  |  | 1. Testing and Development Completed for all the committed stories 2. Regression Testing completed. 3. Developers fixed the Production defect
15.3 M Sprint 1 (03-Oct-2025 to 16-Oct-2025) | 22.5 | 18.5 | 82.22% | 30 | 100% | 2 | 2 | 1 | 0 | 30 | Yes |  |  | 1. Testing and Development Completed for most of the committed stories 2. Planning completed for MSBA automation. 3. Defects fixed and tested
15.03 M Sprint 2 (17-Oct-2025 to 30-Oct-2025) | 23.5 | 20.5 | 87.23% | 30 | 100% | 1 | 2 | 0 | 0 | 30 | Yes |  |  | 1. Testing and Development Completed for most of the committed stories 2. Automation fixes for most of the workflow completed in MSBP Maui. 3. Defects fixed and tested
15.03 M Sprint 3 (31-Oct-2025 to 13-Nov-2025) | 28.5 | 28.5 | 100% | 30 | 100% | 0 | 1 | 0 | 0 | 30 | Yes |  |  | 1. Testing and Development Completed for all the committed stories 2. Regression Testing completed. 3. Developers fixed the Production defect
20.01 M Sprint 1 (14-Nov-2025 to 26-Nov-2025) | 16.5 | 10.5 | 63.64% | 30 | 100% | 1 | 1 | 0 | 0 | 10 | No |  |  | 1 Story carry forwarded due to last minute AC change by client and 1 defect there was delay in review due to PTO of Offshore engineer confirmation and for 1 Defect unable to find the root cause since we have only production data to find the root Also delay in our side by supporting on multiple things.
26.01 M Sprint 2 (27-Nov-2025 to 11-Dec-2025) | 24.5 | 27 | 100% | 30 | 100% | 17 | 37 | 0 | 0 | 10 | Yes |  |  | 1 Story carry forwarded due to last minute AC change by client and BB.