## Dashboard
MSB Web US

## Scorecard
Project Name | MSB Web US
Engagement Model | Relevantz Co Owned
Overall Score | 100.3%
Current Sprint | 26.05 Sprint 01 (08-Apr-2026 to 21-Apr-2026)
Metrics | UnWeighted | Weighted | Notes |  | Target
Commitment Index | 103.3% | 25.83% | #N/A | 25% | 100%
Velocity | 100% | 20% |  | 20% | 95%
Defect-free Rate | 97.37% | 19.47% |  | 20% | 100%
Code Quality Index | 100% | 15% |  | 15% | 100%
Unit Testing & Code Coverage | 100% | 10% |  | 10% | 90%
Backlog Health | 100% | 10% |  | 10% | 100%
Note on D7: Incase of any Non-Compliance, Root-cause must be available.

## Data
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | Last Sprint? | Planned Leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
26.1 Sprint 03 (17-Dec-2025 to 13-Jan-2026) | 71 | 88 | 100% | 88 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  | All the Committed stories has been Completed and more |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.3 Sprint 01 (14-Jan-2026 to 27-Jan-2026) | 50 | 50 | 100% | 69 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | All the Committed stories has been Completed and more |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.3 Sprint 02 (28-Jan-2026 to 10-Feb-2026) | 35 | 46 | 100% | 61.3333 | 100% | 0 | 0 | 0 | 2 | 30 | No | 2 | 4 | All the Committed stories has been Completed and more |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.3 Sprint 03 (11-Feb-2026 to 24-Feb-2026) | 47 | 51 | 100% | 58.75 | 100% | 0 | 0 | 4 | 0 | 30 | No | 2 | 3.5 | All the Committed stories has been Completed and more. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.04 Sprint 01 (25-Feb-2026 to 10-Mar-2026) | 34 | 38 | 100% | 46.25 | 100% | 0 | 0 | 2 | 2 | 30 | No | 1 | 1 | All the Committed stories has been Completed |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.04 Sprint 02 (11-Mar-2026 to 24-Mar-2026) | 35 | 35 | 100% | 42.5 | 100% | 0 | 0 | 0 | 0 | 30 | No | 1 | 1 | All the Committed stories has been Completed |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.04 Sprint 03 (25-Mar-2026 to 7-Apr-2026) | 46 | 48 | 104.3% | 43 | 100% | 0 | 0 | 0 | 0 | 30 | No | 6 | 6 | All the Committed stories has been Completed |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.05 Sprint 01 (08-Apr-2026 to 21-Apr-2026) | 30 | 31 | 103.3% | 38 | 100% | 0 | 0 | 0 | 1 | 142 | No | 6 | 6 | All the Committed stories has been Completed |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
26.05 Sprint 02 (22-Apr-2026 to 05-May-2026) | 27 | 21 | 77.78% | 33.75 | 100% | 0 | 0 | 3 | 1 | 136 | Yes | 1 | 2 | One story got carry forward due to delay in the client side PR review and approval. From our end, we have completed the development on time. |  | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
0%
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
|  |  | 0% | [12 empty] | 100% | 90% | 80% |  | 20 |  | 90% |  | 30
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%
0%

## RCA
3 Why Analysis
Sl.No | Issue/ Date | Sprint Date (DD-MMM-YY to DD-MMM-YY) | Issue Description | Issue Type | Root Cause category | Sub category | Why 1? | Why 2? | Why 3? | Action ( Issue /Risk mitigation plan) | Owner | Status | Target Date | Comments | Root Cause category
1 | 2024-04-09 | 13.7 Sprint 1 (27-Mar to 09-Apr) | commitment index 67% acheived Deviated 33% | Internal | Metric Deviation | Commitment Index Deviation | [5 empty] | Closed | 2022-04-04 | ABC | Metric Deviation
2 | 2024-10-08 | 14.2 Sprint 2(25-Sep to 8-Oct) | More QA Defects | Internal | Metric Deviation | QA Defects | Existing Issues | Requirements Gap |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Adi | Closed | 2024-08-10 |  | Security Compliance
3 | 2024-10-22 | 14.2 Sprint 3(9-Oct to 22-Oct) | 2 QA Defects | Internal | Metric Deviation | QA Defects | Regression Sprint with 1 Internal Defect and 1 Bounceback |  |  |  |  | Closed | 2024-10-22
4 | 2024-11-05 | 14.3 Sprint 1(23- Oct to 5-Nov) | More QA Defects | Internal | Metric Deviation | QA Defects | Existing Issues | Requirements Gap |  | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Adi/Vijay | Closed | 2024-05-11 |  | Not adhered to Policy
5 | 2024-11-19 | 14.3 Sprint 2 (06-Nov to 19-Nov) | More QA Defects and CRC Comments | Internal & External | Metric Deviation | 5 QA Defects and 2 Client CRC | 2 Production Defects - That was added from the previous release, since the defect was not critical, the team worked for this release | 3 Internal QA Defects - 2 were Bounceback and 1 was Existing Issue | Related to ReactJS - Comments are for New UI changes 1.We should not mutate the input parameter. 2. always evaluate to undefined unless we are modifying fieldsByPage which we should not be doing. | Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Adi/Vijay | Closed | 19/11/2024 | Client was informed and they knew about the defects. | Others
6 | 2024-12-03 | 14.3 Sprint 3 (20-Nov to 3-Dec) | 1QA Defect Findings Reported | Internal | Metric Deviation | 1 Defect Findings was reported during Regression | This defect was identified during regression testing as part of the end-to-end (E2E) testing for the invoice functionality. |  |  | Defect was addressed and Closed | Michael | Closed | 2024-03-12
7 | 2024-12-17 | 14.4 Sprint 1 (4-Dec to 17-Dec) | Peer CRC: 1 Internal Defects: 2 External Defects: 1 | Internal & External | Metric Deviation | 1 CRC from Onshore Relevantz Lead, 2 Defects | 1 CRC from Onshore Relevantz. It was name suggestion. sendFamilyPassUpdateToBraze (suggestion for the method name) | 1 Internal QA Defect - Not a Production Issue. Found this defect while testing the 46084 [FamilyPass] MSB - Web - Braze - Send Current Status End Date story and Michael fixed it. 1 Bounceback is related to the current development story minor pagination issue | 1 Escaped Defect - This defect was reported by Eric Rubin. We were unable to reproduce it in lower environments, and it is no longer an issue in production. However, Doug implemented a fix for the arithmetic overflow error and we tested the entire MLM report functionality as part of the defect resolution. Its Fixed | Defect was addressed and Closed. | Michael/Adi/Vijay | Closed | 2024-12-17
8 | 2025-01-14 | 14.4 Sprint 2 (18-Dec to 14-Jan) | Internal Defect-1 2 Bounceback | Internal | Metric Deviation | 1 Defect Findings was reported 2 Bounceback | 1 QA Defect This defect Kiran found while testing the Report Dashboard functionality it's an existing minor UI issue on column alignment and Adi fixed it. UI Issue | 2 Bounceback - Minor UI Issues |  | Defect was addressed and Closed.Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Adi/Sankar | Closed | 2025-01-14
9 | 2025-01-28 | 14.4 Sprint 3 (15-Jan to 28-Jan) | 2 Defects | Internal & External | Metric Deviation | 1 QA Finding and 1 Prod Defect | 1 Internal Finding - Team's notes - Found this issue while testing the 'Delete Inactive User' functionality in the Lab environment. The 'Delete Inactive User' housekeeping task throws an error, and this defect was present only in the Lab environment. There are no issues in the test and staging environments. It is an environmental issue. (Case sesitivity in template name) | 1 External Defect- Team's notes - The issue occurs when the balance transitions from 0 to negative. This issue has been verified in Production, and Michael has found the root cause |  | Defect was addressed. | Michael/Jim | Closed | 2025-01-28
10 | 2025-02-11 | 14.5 Sprint 1 (29-Jan to 11-Feb) | 2 Defecrs | Internal | Metric Deviation | 2 Internal Defects | One defect was Project management related - Due to the update of the Struts libraries, the dropdowns are not working.. The Other is related Development related. Defect was addressed by client and tested by offshore |  |  | Defect was addressed. | Michael | Closed | 2025-02-11
11 | 2025-02-25 | 14.5 Sprint 2 (12-Feb-2025 to 25-Feb-2025) | 2 Defects | Internal | Metric Deviation | 1 Bounceback and 1 Defect | 1 bounceback - Found during testing, the Dev missed the scenario - Its fixed | 1 QA Defect - It's a minor existing issue, not a showstopper, so nobody noticed it and it kept rolling on for so long in prod. We identified and fixed it. |  | Defects were Addressed. | Adi/Michael | Closed | 2025-02-25
12 | 2025-03-11 | 14.5 Sprint 3 (26-Feb-2025 to 11-Mar-2025) | External Defects | External | Metric Deviation | 4 External Defects | The External Defects are already exsting issue. The Defects were identfied and fixed as a part of release. The Defects were minor and significant and it doesn't cause any major escalations |  |  | Defects were Addressed. Closed.Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Adi/Michael | Closed | 2025-03-11
13 | 2025-03-25 | 14.6 Sprint 1 (12-Mar-2025 to 25-March-2025) | CRC, External Defects | Internal/External | Metric Deviation | 1 Internal CRC and 1 External Defect | 1 Internal CRC - Suggestion to Add the setCourseCodeForCourseIDs method separatly for the courseID to load the course from the Provider | 1 External Defect - Recipients count is not correct, When searching for recipients, the list displays only unique students, but the count label giving the count including duplicates, Kiran found this during regression but the defect priority is low so moved it in this sprint and it is fixed |  | Defects were Addressed. Closed.Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Michael/Sankar | Closed | 2025-03-25
14 | 2025-04-09 | 14.6 Sprint 2 (26-Mar-2025 to 08-Apr-2025) | CRC, Internal Defects | Internal | Metric Deviation | 1 External CRC and 2 Bounce backs | resource the text Include Future enrollments | 2 Bounceback - Minor UI Issues | 1 story has been carry forwarded because of Forwarded to Product Team for Alternative solution from Portico and Colannade after being spent time on investigation | Defects were Addressed. | michael / Kiran | Closed | 2025-04-22 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
15 | 2025-04-23 | 14.6 Sprint 3 (09-Apr-2025 to 22-Apr-2025) | Internal. External Defects | Internal & External | Metric Deviation | 2 Internal Defects & 2 External Defects |  | 2 Internal defects has been found on the Regression testing and 2 External Defects found in the prod Environemnt from exists long time. |  | Defects were Addressed. | Issac / Michael | Closed | 2025-05-06 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
16 | 2025-05-07 | 14.7 Sprint 1 (23-Apr-2025 to 06-May-2025) | Internal. External CRC | Internal & External | Metric Deviation | 2 Internal CRC and 1 External CRC | 2 Internal CRC has been given to the team as a suggession to reove the unwaned code and comments | The team missed out or not noticed the comments / unwanted code |  | Given the awarness to the team to check the code what ever has been modified / developed to be compared using the GIT and only the necessary details should be moved into the Azure Devops for Code Review | Maria / Sankar | Closed | 2025-05-07 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
17 | 2025-05-07 | 14.7 Sprint 1 (23-Apr-2025 to 06-May-2025) | BounceBack | Internal | Metric Deviation | 2 Bounce Back | 2 Bounce back has been recived to the team from the internal QA | Team missed out some of the negative scenarioes which has been handled on the unit testing from dev team. |  | Given the awarness to the team to test the Negative scenarios in the manual unit testing once the development has been completed / the peer review has to be tested the negative scenarioes must | Maria / Sankar | Closed | 2025-05-20 | Team will have knowledge share on the Coding stds and using the Coplite Code Refinement
17 | 2025-05-07 | 14.7 Sprint 1 (23-Apr-2025 to 06-May-2025) | Metric Deviation | Internal | Metric Deviation | Story carry forwarded | 2 story got carry forwarded. | `1st story reason "We hit the roadblock on the confirmation screen itself before starting background process. It was explained to client and the fix for confirmation page is done with a refactoring. Actually story started late." | 2nd Story reason "Our QA was not available due to medical emergency. With available resources, we got feedback on the story late in the sprint because of which the story is not closed." | Addressed the concern from the team related to the QA Medical Emergency and ask the other QA to take the responsibilities when the collegue is not available and provided the team to analyse the story in the sprint planning. | Adinarayanan | Closed | 2025-05-20 | Defects were Addressed.
18 | 2025-05-20 | 14.7 Sprint 2 (07-May-2025 to 20-May-2025) | CRC | internal & External | Metric Deviation | 1 Internal CRC and 1 External CRC | 1 Internal CRC - Suggestion to remove the extra space which is present in the file. | 1 External CRC - Which has been given as a suggession to use the existing functionality as we have already done the code as a common to use. |  | Defects were Addressed. Closed.Knowledge share with Team in Stand Up, So that similar type of issue can be mitigated. | Kiran | Closed | 2025-05-20 | Defects were Addressed.
19 | 2025-05-20 | 14.7 Sprint 2 (07-May-2025 to 20-May-2025) | BounceBack | internal & External | Metric Deviation | 4 Bounceback | 1. 4 Bounceback has been found in the current sprint by our internal QA | Some of the negative scenarios has been missed by the developer in the Dev environment and found that as a defect from our Internal QA. |  | 1. One of the Mitigation plan we have proposed is, Gettign the negative scenarios from the QA while doing the manual unit testing from the developer end once the devlopment has been completed. | Kiran | Closed | 2025-05-20 | Defects were Addressed.
20 | 2025-06-03 | 14.7 Sprint 3 (21-May-2025 to 03-Jun-2025) | QA Defect | internal & External | Metric Deviation | 6 QA Defect | 1. 6 QA Defect thas been found in the current sprint by our internal QA and 2 QA defect has been found by external | Most of the issues has been found in the regression testing as the current sprint taken as a regression sprint. |  |  | Kiran | Closed | 2025-06-03 | Defects were Addressed.
21 | 2025-06-18 | 15.0 Sprint 1 (04-Jun-2025 to 17-Jun-2025) | QA Defect and Bounceback | internal & External | Metric Deviation | 1 QA Defect and 1 BounceBack | 1. 1 QA defect has been found internally as a BounceBack and 1 External defect has been found as the Enhancement for the production issue. | 1 Enhancement has been given from the External team related to the development and 1 QA bounce back has been given as a tooltip change |  |  | Kiran | Closed | 2025-06-18 | Defects were Addressed.
22 | 2025-07-02 | 15.0 Sprint 1 (18-Jun-2025 to 1-Jul-2025) | CRC | internal & External | Metric Deviation | 2 External CRC | 1. 2 External CRC has been provided from the onsite lead related to the Bilingual Language code | 1 The current implementation compares string to identifies UI elements, which may break if the UI language is changed from English 2.The text for these should use resources from pageValues.messages |  |  | Rahul | Closed | 2025-07-01 | Defects were Addressed.
23 | 2025-07-02 | 15.0 Sprint 1 (18-Jun-2025 to 1-Jul-2025) | QA Defect | internal & External | Metric Deviation | 2 QA Defect | 1.2 of the QA defects has been found from the External Team | All the 2 defects are an Existing issue and it has been found by the external team while checking the current scenario |  |  | Michael/Vijay | Closed | 2025-07-01 | Defects were Addressed.
24 | 2025-10-07 | 15.2 Sprint 3 ( 9-Sep-2025 to 7-Oct-2025) | QA Defect | internal & External | Metric Deviation | 1 QA Defect and 3 External | External defect are pre existing production defects and 1 internal defect found during regression testing | For the internal defect : Report is generated for 366 days but actual ask was 365 days |  |  | Michael/Vijay/Kiran/Adi | Closed | 2025-10-07 | Defects were Addressed.
25 | 2025-10-21 | 15.3 Sprint 1 ( 8-Oct-2025 to 21-Oct-2025) | Commitment Index | External | Metric Deviation | 2 External development stories | "1 story was for One trust which had a dependency on client credentials and a new system approach lead to rolling over the story to next sprint | Next story which got rolled over was the Web - Braze - Lunch Crunch , development is complete only testing needs to be done . Testing is currently blocked due to instability of the Braze API as accessed via Apigee |  | External Client dependency | Michael/Kiran/Sankar | Closed | 2025-10-21
26 | 2025-10-21 | 15.3 Sprint 1 ( 8-Oct-2025 to 21-Oct-2025) | QA Defect | External | Metric Deviation | 1 external | The Clear Purchases option on the UI in MSB does not set a purchase to a deleted status or remove from the table if it is unable to join on the student key. So orphaned records are unable to be cleared and prevent data resend from the POS that contain the same purchase ID from being uploaded - rejected as duplicate. |  |  | It is a existing issue unrelated to our recent developments. When a student record is deleted, the associated cafeteria purchase data is not properly cleared, resulting in orphaned purchase entries | Michael / Kiran | Closed | 2025-10-21
27 | 2025-11-04 | 15.3 Sprint 2 (22-Oct-2025 to 4-Nov-2025) | QA Defect | External | Metric Deviation | 4 External Defects | It is an existing issue unrelated to our recent developments. |  |  | existing issue unrelated to our recent developments | Michael / Kiran | Closed | 2025-11-04
28 | 2025-11-18 | 15.3 Sprint 3 (05-Nov-2025 to 18-Nov-2025) | QA Defect | internal & External | Metric Deviation | 3 internal and 3 external | External defects are existing issues unrelated to our recent development. | Internal defect:Doug updated the JAX-RS and JAX-WS plugins for SOAP services and migrated all SOAP endpoints from the Axis framework to Apache CXF. This migration have affecting the cashier payment functionality. |  | The external defects are existing production issues and the the internal defects were minor ones which found during regression test before going to production which due to a change introduced by Client | Michael / Kiran | Closed | 2025-11-18
29 | 2025-12-03 | 26.1 Sprint 1 (19-Nov-2025 to 2-Dec-2025) | QA Defect | internal & External | Metric Deviation | 1 Internal and 2 External | This is an existing defect and not related to recent development. The root cause is the absence of RTF entries in the Department Daily Status emails, which need to be added. | This defect was identified during regression testing and is not present in production. We addressed it in the current sprint and plan to deploy the fix in the upcoming release. The issue relates to permissions: we are hiding the 'Create G/L Account' button on the product page if the admin does not have the required access. |  | It is a existing issue unrelated to our recent developments. | Michael / Kiran | Closed | 2025-12-03
30 | 2025-12-16 | 26.1 Sprint 2 (3-Dec-2025 to 16-Dec-2025) | Commitment Index | External | Metric Deviation | 2 External | QA deployment delays caused offshore teams to receive builds a day late. | 2 stories got moved to the next sprint due to the build pipeline issues which caused delay in deployments |  | Working with the client ITOps team to resolve the build issue | Michael/Kiran/Sankar | Closed | 2025-12-22
31 | 2025-12-16 | 26.1 Sprint 2 (3-Dec-2025 to 16-Dec-2025) | QA Defect | internal & External | Metric Deviation | 3 internal and 2 external | The defects occurred because the automation did not run reliably following the framework upgrade for the eTransfer services. This instability affected the automation execution, resulting in a few minor edge cases being overlooked and subsequently reported as escaped defects. |  |  | QA team members have added manual test cases to ensure these edge cases are covered in the regression test suite. Starting from the next run, the automation test coverage will increase, which is expected to reduce the number of escaped defects. | Kiran/Sudhakar | Closed | 2025-12-31
32 | 2026-01-14 | 26.1 Sprint 3 (17-Dec-2025 to 13-Jan-2026) | QA Defect | Internal | Metric Deviation | 2 internal | This is an existing issue not related to recent development. The root cause is When attempting to export schedules, the export process completes but the resulting file does not contain the expected data. | These issues are not part of any recent developement, these defects found during regression testing |  | Increase the automation test coverage and reduce the manual testing to reduce these defects | Kiran/Sudhakar | Closed | 2025-01-14
33 | 2026-02-10 | 26.3 Sprint 2 (28-Jan-2026 to 10-Feb-2026) | QA Defect | Internal | Metric Deviation | 2 external | Vega layout - cosmetic issue, Another existing issue - The root cause is The blank screen occurred because the large number of selected schools (over 1100) caused the form submission to exceed request parameter limits; the issue was resolved by consolidating selected school keys into a single hidden field (schoolKeysString) instead of submitting them individually | These issues are not part of any recent developement, these defects found during regression testing |  | Increase the automation test coverage and reduce the manual testing to reduce these defects | Kiran/Sudhakar | Closed | 2025-02-10
34 | 2026-02-24 | 26.3 Sprint 3 (11-Feb-2026 to 24-Feb-2026) | QA Defect | Internal | Metric Deviation | 4 Internal | 1 Development : Error during the UI redirect phase of the "Vega" workflow despite successful data processing | Incomplete Action Mapping. Although the back-end logic successfully persisted the G/L account to the database, the Struts action configuration lacked a defined result path for the SUCCESS_VEGA navigation string. |  | Increase the automation test coverage and reduce the manual testing to reduce these defects | Kiran | Closed | 2025-02-24 | 3 are existing issues found during regression testing and fixed it.
35 | 2026-03-10 | 26.4 Sprint 1 (25-Feb-2026 to 10-Feb-2026) | QA Defect | External | Metric Deviation | 2 External | 2 Design level changes: MSB has discontinued new FamilyPass subscriptions, but existing plans remain active until expiration. Braze – Cafeteria Purchase Amount is inaccurate due to inclusion of payment data and negative values | These issues are not part of any recent development, these defects were found recently as part of the design changes |  | QA team members have added manual test cases to ensure these edge cases are covered in the regression test suite. Starting from the next run, the automation test coverage will increase, which is expected to reduce the number of escaped defects. | Kiran | Closed | 2025-03-10
36 | 2026-03-10 | 26.4 Sprint 1 (25-Feb-2026 to 10-Feb-2026) | QA Defect | Internal | Metric Deviation | 2 Internal | 2 Design level changes: MSB - Web - Invoices - Load Template Displays All Invoice Templates for Restricted Admins Product - Pricing and inventory Options - Validation Error on Bulk Price Update when using Integer values (e.g., '20') instead of Decimals | These issues are not part of any recent development, these defects were found recently as part of the design changes |  | QA team members have added manual test cases to ensure these edge cases are covered in the regression test suite. Starting from the next run, the automation test coverage will increase, which is expected to reduce the number of escaped defects. | Kiran | Closed | 2025-03-10
37 | 2026-04-21 | 26.05 Sprint 1 (08-Apr-2026 to 21-Apr-2026) | QA Defect | External | Metric Deviation | 1 External | Search Store Does Not Trigger Search on Enter Key Press - Firewall or security restrictions may be limiting the functionality | it only occurs within the HSS system and provided workaround for the security restrictions |  | Increase the automation test coverage, which is expected to reduce the number of escaped defects. | Kiran | Closed | 2025-05-02
38 | 2026-05-05 | 26.05 Sprint 2 (22-Apr-2026 to 05-May-2026) | Commitment Index | External | Metric Deviation | 1 External | There was a delay in PR review and approval, which caused the G/L import option story to remain incomplete in testing. Development was finished on schedule, but testing could not be completed within the sprint due to delay on client side PR review and approval | 1 story got carry forwarded due to PR review and approval delay from the client side |  | Onsite lead working with client SME for PR review and approval | Michael/Adi/Kiran | In progress | 2026-05-12
39 | 2026-05-05 | 26.05 Sprint 2 (22-Apr-2026 to 05-May-2026) | QA Defect | Internal | Metric Deviation | 3 Internal | 1. For real‑time cashier payments, it used an invoice item reference that didn’t exist (missing/mismatched reference), causing the invoice item lookup to fail and resulting in a stop‑sign “page not found” error. 2.The “Send Invite” button state was not correctly updated when student rows were selected due to missing/incorrect toggle logic binding, leaving the button enabled instead of being disabled during multi‑selection. 3. The Move To Top/Bottom actions were reordering rows without consistently closing all active popovers, leaving Bootstrap popups orphaned and stuck on the screen, overlapping action buttons. | Missing reference links and UI related issues found during the testing phase |  | To increase the unit test cases coverage and validate the edge test cases before deploying it in the test environment | Vijay/Adinarayana | Closed | 2025-05-05
40 | 2026-05-05 | 26.05 Sprint 2 (22-Apr-2026 to 05-May-2026) | QA Defect | External | Metric Deviation | 1 External | The email language was incorrectly determined using a shared or previously initialized localization context (ResourceBean), causing contact emails (without users) to inherit the language preference of a previously processed parent recipient. | This was already existing known issue found during the regression testing phase and added to the backlog which was fixed in this sprint |  | Increase the automation test coverage, which is expected to reduce the number of escaped defects. | Kiran | Closed | 2025-05-05

## QualityMetrics-Definition
Key Performance Indicator | Description | Formula | Weightage | Green | Amber | Red | Client Approved
Commitment Index | Indicates the percentage of story points fulfilled relative to the commitment for each sprint. | Completed Story Points/ Planned Story Points | 25% | 100 | 81-99 | <=80%
Velocity | Denotes the overall count of story points accomplished in each sprint. | Completed Story Points/Average of 4 sprints (4 sprints after the team completely onboarded and started the project related activities) The above formulae is customized and should not be below the value derived from 8*1(2 Weeks Sprint)*(Number of Team Members) | 20% | 95% | 80-94 | <80%
Defect-free Rate | The number of defects identified post-development | (Internal+Escaped) Defects Found/ Size (actual in Story Points) | 20% | 100% | 99-80 | >20%
Code Quality Index | Evaluate the code quality across various dimensions, whether through manual code review or automated analysis using tools like SonarCube. Assess aspects such as correctness, readability, maintainability, efficiency, consistency, testability, scalability, security, documentation, and adherence to established standards. | (Peer + Client) Code Review/ Size (actual in Story Points) | 15% | >=80 | 79-65 | <65%
Unit Testing & Code Coverage | Unit Test Results should be >85% Code Coverage should be >85% | Average of Unit Test & Code Coverage | 10% | >=90 | 71-89 | <=70%
Backlog Health | Shows the health of backlog in as total number of Story Points available in backlog Vs Average Velocity (last 6 Sprints) | No. Of stories points (Velocity of the Team) ready for (N+1)th Sprint | 10% | 100 | 81-99 | <=80%
Delivery Score |  | Sum of all the scores from different metrics | NA | >=90% | 81-89 | <=80%

## Config
Sprint | #VALUE! | Relevantz Co Owned | #VALUE! | Commitment Index |  | Status |  |  | Less Than | Greater Than
Metrics | UnWeighted | Weighted |  | Goal | 100% | Ready |  | Below Avg | 5
Commitment Index | #VALUE! | #VALUE! |  | Risk | 90% | Committed |  | Avg | 10 | 15
Velocity | #VALUE! | #VALUE! |  | Issue | 80% | Done |  | Good | 15 | 20
Defect-free Rate | 100% | 20% |  |  |  | CF |  | Excellent |  | 25
Code Quality Index | #VALUE! | #VALUE! |  | Velocity
Unit Testing & Code Coverage | #VALUE! | #VALUE! |  | Goal | 20
Backlog Health | #VALUE! | #VALUE!
Code Coverage
|  |  |  | Goal | 90%
|  |  |  | Backlog Health - Categories |  | Story Point Labels |  |  | Backlog Health - Achieved
|  |  |  | Below Avg | 15 | Labels | Values |  | Story Points | #N/A
|  |  |  | Avg | 20 | 5 | 10 |  | Thickness | 1
|  |  |  | Good | 25 | 10 | 10 |  | Indicator | 30
|  |  |  | Excellent | 30 | 15 | 10
|  |  |  | Total | 90 | 20 | 10
[6 empty] | 25 | 10
50

## Instructions
Instructions
1. Define the metrics that are required for the project in the "QualityMetrics-Defintion" sheet 2. For the defined metrics, update the Data in the "Data" sheet. 3. Update the Goals in the "Data" sheet from Column AC to AL - Add/Delete the required goals as necessary - This is used in the Scorecard metrics calculation 4. Update the Project details in the "Scorecard" sheet 5. As per the goals defined, update the formulae required to calculate the metrics 6. As per the goals defined, update the "Conditional Formatting" rules to reflect the correct color coding as per the defined goals 7. To update the Dashboard charts, Open the document in desktop version and select the required sprints (cycles) to display the data

## Data-2025
Sprint | Committed | Delivered | Commitment Index | Velocity | Code Coverage | Code Review Comments - Internal | Code Review Comments - External | QA Defects | Escaped Defects | Backlog Health | last Sprint? | Planned leaves | Availed Leaves | Remarks | CommitmentIndex | Goal | Risk | Issue | Velocity | Goal | Code Coverage | Goal | Backlog Health | Goal
13.7 Sprint 1 (27-Mar-2024 to 09-Apr-2024) | 34 | 21 | 61.76% | 20 | 90% | 0 | 0 | 6 | 1 | 30 | No |  |  | 1 story got carried. Development inprogress. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
13.7 Sprint 2 (10-Apr-2024 to 23 Apr-2024) | 36 | 36 | 100% | 26 | 90% | 0 | 0 | 1 | 0 | 33 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
13.7 Sprint 3 (24-Apr-2024 to 7-May-2024) | 43 | 29 | 67% | 27 | 90% | 1 | 0 | 0 | 0 | 33 | No |  |  | None |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
13.8 Sprint 1 (8-May-2024 to 21-May-2024) | 39 | 39 | 100% | 31.25 | 90% | 3 | 0 | 1 | 0 | 35 | No |  |  | None |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
13.8 Sprint 2 (22-May-2024 to 4-June-2024) | 23 | 23 | 100% | 31.75 | 100% | 1 | 0 | 0 | 0 | 35 | No |  |  | None |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
13.8 Sprint 3 (5-Jun-2024 to 18-Jun-2024) | 42 | 42 | 100% | 33.25 | 100% | 0 | 0 | 1 | 0 | 31 | No |  |  | Regression Sprint. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.0 Sprint 1 (19-Jun-2024 to 2-Jul-2024) | 16 | 16 | 100% | 30 | 100% | 2 | 1 | 1 | 0 | 30 | No |  |  | None |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.0 Sprint 2 (3-Jul-2024 to 16-Jul-2024) | 23 | 16 | 69.57% | 24.25 | 100% | 5 | 0 | 1 | 0 | 30 | No |  |  | Testing of story 45240 pending and delayed due to the dependency with third party API |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.0 Sprint 3 (Jul-17-2024 to Jul-30-2024) | 32 | 24 | 75% | 24.5 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.1 Sprint 1 (Jul-31-2024 to Aug-13-2024) | 21 | 26 | 100% | 20.5 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.1 Sprint 2 (Aug-14-2024 to Aug-27-2024) | 17 | 17 | 100% | 20.75 | 100% | 0 | 0 | 4 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.1 Sprint 3 (Aug-28-2024 to Sep-10-2024) | 46 | 46 | 100% | 28.25 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.2 Sprint 1 (11-Sep-2024 to 24-Sep-2024) | 31 | 22 | 70.97% | 27.75 | 100% | 1 | 1 | 0 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.2 Sprint 2 (25-Sep-2024 to 8-Oct-2024) | 31 | 21 | 67.74% | 26.5 | 85% | 0 | 0 | 9 | 0 | 30 | No |  |  | 46046 - Carry forward due to the story being tested |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.2 Sprint 3 (9-Oct-2024 to 22-Oct-2024) | 45 | 47 | 100% | 34 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.3 Sprint 1 (23- Oct-2024 to 5-Nov-2024) | 25 | 25 | 100% | 28.75 | 100% | 0 | 0 | 4 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.3 Sprint 2 (06-Nov-2024 to 19-Nov-2024) | 32 | 35 | 100% | 32 | 100% | 0 | 2 | 3 | 2 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.3 Sprint 3 (20-Nov-2024 to 3-Dec-2024) | 45 | 45 | 100% | 38 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.4 Sprint 1 (4-Dec-2024 to 17-Dec-2024) | 31 | 31 | 100% | 34 | 100% | 1 | 0 | 2 | 1 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.4 Sprint 2 (18-Dec-2024 to 14-Jan-2025) | 38 | 47 | 100% | 39.5 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  | 4-Weeks Sprint |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.4 Sprint 3 (15-Jan-2025 to 28-Jan-2025) | 44 | 44 | 100% | 41.75 | 100% | 0 | 0 | 1 | 1 | 30 | No |  |  | Regression Sprint. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.5 Sprint 1 (29-Jan-2025 to 11-Feb-2025) | 43 | 45 | 100% | 41.75 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.5 Sprint 2 (12-Feb-2025 to 25-Feb-2025) | 43 | 47 | 100% | 45.75 | 100% | 0 | 0 | 1 | 1 | 30 | No |  |  | Comment added for Testing |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.5 Sprint 3 (26-Feb-2025 to 11-Mar-2025) | 64 | 66 | 100% | 50.5 | 100% | 0 | 0 | 0 | 4 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.6 Sprint 1 (12-Mar-2025 to 25-Mar-2025) | 46 | 56 | 100% | 53.5 | 100% | 1 | 0 | 1 | 0 | 30 | No |  |  |  |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.6 Sprint 2 (26-Mar-2025 to 08-Apr-2025) | 53 | 53 | 100% | 55.5 | 100% | 0 | 1 | 0 | 2 | 30 | No |  |  | #47553 The story has been carry forwarded to Product Team for Alternative solution from Portico and Colannade. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.6 Sprint 3 (09-Apr-2025 to 22-Apr-2025) | 67 | 67 | 100% | 60.5 | 100% | 0 | 0 | 2 | 2 | 30 | No |  |  | Regression Sprint. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.7 Sprint 1 (23-Apr-2025 to 06-May-2025) | 55 | 34 | 61.82% | 52.5 | 80% | 2 | 1 | 0 | 2 | 30 | No |  |  | 1 story got carry Forwarded #47917, In the analysis phase itself the team found the show stopper and let the client know with the fix. The client changed the requirement and the development has been started at the mid of the sprint. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.7 Sprint 2 (07-May-2025 to 20-May-2025) | 26 | 57 | 100% | 52.75 | 80% | 1 | 1 | 4 | 0 | 30 | No |  |  | All the Committed stories has been Completed and along with that Some of the Strech stories has also been completed in this current sprint. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
14.7 Sprint 3 (21-May-2025 to 03-Jun-2025) | 70 | 70 | 100% | 57 | 100% | 0 | 0 | 4 | 2 | 30 | No |  |  | All the Committed stories has been Completed. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
15.0 Sprint 1 (04-Jun-2025 to 17-Jun-2025) | 53 | 53 | 100% | 53.5 | 100% | 0 | 0 | 1 | 1 | 30 | No |  |  | All the Committed stories has been Completed and one streach story is in the testing phase. |  | #VALUE! | #VALUE! | #VALUE! |  | #VALUE! |  | #VALUE! |  | 30
15.0 Sprint 2 (18-Jun-2025 to 1-Jul-2025) | 48 | 48 | 100% | 57 | 100% | 0 | 2 | 2 | 0 | 30 | No |  |  | All the Committed stories has been Completed and one streach story is in the testing phase.
15.0 Sprint 3 (2-Jul-2025 to 15-Jul-2025) | 64 | 64 | 100% | 58.75 | 100% | 0 | 0 | 2 | 1 | 30 | No |  |  | All the Committed stories has been Completed
15.1 Sprint 1 (16-Jul-2025 to 29-Jul-2025) | 45 | 50 | 100% | 53.75 | 100% | 0 | 0 | 1 | 2 | 30 | No |  |  | All the Committed stories has been Completed and one 5 points stretch story as well
15.1 Sprint 2 (30-Jul-2025 to 12-Aug-2025) | 57 | 65 | 100% | 56.75 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  | All the Committed stories has been Completed and 2 stretch bugs and 1 stretch story as well
15.1 Sprint 3 (13-Aug-2025 to 26-Aug-2025) | 60 | 60 | 100% | 59.75 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | All the Committed stories has been Completed
15.2 Sprint 1 (27-Aug-2025 to 9-Sep-2025) | 50 | 50 | 100% | 56.25 | 100% | 0 | 0 | 1 | 0 | 30 | No |  |  | All the Committed stories has been Completed
15.2 Sprint 2 (10-Sep-2025 to 23-Sep-2025) | 52 | 64 | 100% | 59.75 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | All the Committed stories has been Completed and 3 stretch stories as well
15.2 Sprint 3 (24-Sep-2025 to 7-Oct-2025) | 64 | 66 | 100% | 60 | 100% | 0 | 0 | 1 | 3 | 30 | No |  |  | All the Committed stories has been Completed and one 2 points stretch story as well
15.3 Sprint 1 (8-Oct-2025 to 21-Oct-2025) | 57 | 44 | 77.19% | 56 | 100% | 0 | 0 | 0 | 1 | 30 | No |  |  | 1 story was for One trust which had a dependency on client credentials and a new system approach lead to rolling over the story to next sprint Next story which got rolled over was the Web - Braze - Lunch Crunch , development is complete only testing needs to be done . Testing is currently blocked due to instability of the Braze API as accessed via Apigee
15.3 Sprint 2 (22-Oct-2025 to 4-Nov-2025) | 58 | 63 | 100% | 59.25 | 100% | 0 | 0 | 0 | 4 | 30 | No |  |  | The team did an excellent job, focusing on fee workflow enhancements, reporting accuracy, and POS conversion improvements
15.3 Sprint 3 (05-Nov-2025 to 18-Nov-2025) | 71 | 73 | 100% | 61.5 | 100% | 0 | 0 | 3 | 3 | 30 | No |  |  | All the Committed stories has been Completed and more
26.01 Sprint 1 (19-Nov-2025 to 2-Dec-2025) | 50 | 55 | 100% | 58.75 | 100% | 0 | 0 | 1 | 1 | 30 | No |  |  | All the Committed stories has been Completed and more
26.01 Sprint 2 (3-Dec-2025 to 16-Dec-2025) | 54 | 49 | 90.74% | 60 | 100% | 0 | 0 | 3 | 2 | 30 | No |  |  | 2 stories got moved to the next sprint due to the build pipeline issues which caused delay in deployments
26.01 Sprint 3 (17-Dec-2025 to 13-Jan-2026) | 71 | 88 | 100% | 66.25 | 100% | 0 | 0 | 2 | 0 | 30 | No |  |  | All the Committed stories has been Completed and more
26.03 Sprint 1 (14-Jan-2026 to 27-Jan-2026) | 50 | 50 | 100% | 60.5 | 100% | 0 | 0 | 0 | 0 | 30 | No |  |  | All the Committed stories has been Completed and more
26.03 Sprint 2 (28-Jan-2026 to 10-Feb-2026) | 35 | 46 | 100% | 58.25 | 100% | 0 | 0 | 0 | 2 | 30 | No | 2 | 4 | All the Committed stories has been Completed and more
26.03 Sprint 3 (11-Feb-2026 to 24-Feb-2026) | 47 | 51 | 100% | 58.75 | 100% | 0 | 0 | 4 | 0 | 30 | No | 2 | 3.5 | All the Committed stories has been Completed and more.
26.04 Sprint 1 (25-Feb-2026 to 10-Mar-2026) | 34 | 38 | 100% | 46.25 | 100% | 0 | 0 | 2 | 2 | 30 | No | 1 | 1 | All the Committed stories has been Completed
26.04 Sprint 2 (11-Mar-2026 to 24-Mar-2026) | 35 | 35 | 100% | 42.5 | 100% | 0 | 0 | 0 | 0 | 30 | Yes | 1 | 1 | All the Committed stories has been Completed